## Cover Page
WF1

## WF5
Note on K83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $84.45 for LM and 42.25 for Coupler
Roads built as winter as well as all-season
All-season
Rig mats are based on actual LEMs, while bridges and rig mats are linked to Exhibit B rates
Rental Rates were changed after July 2021, i.e., old rates are used until July 1st
Rental Cost till March 2022 (invoices available)
Forecasted Rental Cost till estimated end date
Culvert and Rig mats only have one time pruchase, while bridges rental are charged monthly

## Export
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22 | Column23 | Column24 | Column25 | Column26 | Column27 | Column28 | Column29 | Column30 | Column31 | Column32 | Column33 | Column34 | Column35 | Column36 | Column37 | Column38 | Column39 | Column40 | Column41 | Column42 | Column43 | Column44 | Column45 | Column46 | Column47 | Column48 | Column49 | Column50 | Column51 | Column52 | Column53 | Column54 | Column55 | Column56 | Column57 | Column58 | Column59 | Column60 | Column61 | Column62 | Column63 | Column64
Corbiere and Sons Contracting | 6 | 0 | 223 | 20190923 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR |  |  |  |  | 891 | 115.83 | 1006.83 | 2019-09-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Project Supervision for start up activities.-Supervision / Yard |  |  |  | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting22320190923Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting22320190923Loader JD 524 to 624 or equal9891Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 223 | 20190923 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 70 | HR |  |  |  |  | 2100 | 273 | 2373 | 2019-09-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Project Supervision for start up activities.-Supervision / Yard |  |  |  | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting22320190923Light Truck - Pick up702100 | Corbiere and Sons Contracting22320190923Light Truck - Pick up702100Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 223 | 20190923 | 53520101 | Clearing | 0 | Mechanics Truck | 55 | 10 | HR |  |  |  |  | 550 | 71.5 | 621.5 | 2019-09-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Project Supervision for start up activities.-Supervision / Yard |  |  |  | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting22320190923Mechanics Truck10550 | Corbiere and Sons Contracting22320190923Mechanics Truck10550Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 550 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 223 | 20190923 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-09-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Project Supervision for start up activities.-Supervision / Yard |  |  |  | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting22320190923Project Manager121320 | Corbiere and Sons Contracting22320190923Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 223 | 20190923 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-09-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Project Supervision for start up activities.-Supervision / Yard |  |  |  | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting22320190923Superintendent121260 | Corbiere and Sons Contracting22320190923Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 223 | 20190923 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-09-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Project Supervision for start up activities.-Supervision / Yard |  |  |  | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting22320190923Project Coordinator12960 | Corbiere and Sons Contracting22320190923Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 223 | 20190923 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-09-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Project Supervision for start up activities.-Supervision / Yard |  |  |  | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting22320190923Construction Coordinator11880 | Corbiere and Sons Contracting22320190923Construction Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 223 | 20190923 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-09-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Project Supervision for start up activities.-Supervision / Yard |  |  |  | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting22320190923Safety Advisor121020 | Corbiere and Sons Contracting22320190923Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 223 | 20190923 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-09-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Project Supervision for start up activities.-Supervision / Yard |  |  |  | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting22320190923Project Controls10700 | Corbiere and Sons Contracting22320190923Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 223 | 20190923 | 53520101 | Clearing | 0 | Foreman | 95 | 11 | HR |  |  |  | 0 | 1045 | 135.85 | 1180.85 | 2019-09-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Project Supervision for start up activities.-Supervision / Yard |  |  |  | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting22320190923Foreman111045 | Corbiere and Sons Contracting22320190923Foreman111045Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1045 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 223 | 20190923 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-09-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Project Supervision for start up activities.-Supervision / Yard |  |  |  | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting22320190923Operator - Principle221980 | Corbiere and Sons Contracting22320190923Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 223 | 20190923 | 53520101 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-09-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Project Supervision for start up activities.-Supervision / Yard |  |  |  | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting22320190923Labourer - General11715 | Corbiere and Sons Contracting22320190923Labourer - General11715Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 223 | 20190923 | 53520101 | Clearing | 0 | Mechanic | 90 | 10 | HR |  |  |  | 0 | 900 | 117 | 1017 | 2019-09-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Project Supervision for start up activities.-Supervision / Yard |  |  |  | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting22320190923Mechanic10900 | Corbiere and Sons Contracting22320190923Mechanic10900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 223 | 20190923 | 53520101 | Clearing | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2019-09-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Project Supervision for start up activities.-Supervision / Yard |  |  |  | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting22320190923L.O.A.102100 | Corbiere and Sons Contracting22320190923L.O.A.102100Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 224 | 20190924-R01 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR |  |  |  |  | 891 | 115.83 | 1006.83 | 2019-11-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Supervision / Kickoff-Orientations, yard set up |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting22420190924-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting22420190924-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 224 | 20190924-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 70 | HR |  |  |  |  | 2100 | 273 | 2373 | 2019-11-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Supervision / Kickoff-Orientations, yard set up |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting22420190924-R01Light Truck - Pick up702100 | Corbiere and Sons Contracting22420190924-R01Light Truck - Pick up702100Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 224 | 20190924-R01 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Supervision / Kickoff-Orientations, yard set up |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting22420190924-R01Project Manager121320 | Corbiere and Sons Contracting22420190924-R01Project Manager121320Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 224 | 20190924-R01 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Supervision / Kickoff-Orientations, yard set up |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting22420190924-R01Superintendent121260 | Corbiere and Sons Contracting22420190924-R01Superintendent121260Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 224 | 20190924-R01 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Supervision / Kickoff-Orientations, yard set up |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting22420190924-R01Project Coordinator12960 | Corbiere and Sons Contracting22420190924-R01Project Coordinator12960Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 224 | 20190924-R01 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Supervision / Kickoff-Orientations, yard set up |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting22420190924-R01Construction Coordinator12960 | Corbiere and Sons Contracting22420190924-R01Construction Coordinator12960Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 224 | 20190924-R01 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Supervision / Kickoff-Orientations, yard set up |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting22420190924-R01Safety Advisor121020 | Corbiere and Sons Contracting22420190924-R01Safety Advisor121020Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 224 | 20190924-R01 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-11-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Supervision / Kickoff-Orientations, yard set up |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting22420190924-R01Project Controls10700 | Corbiere and Sons Contracting22420190924-R01Project Controls10700Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 224 | 20190924-R01 | 53520101 | Clearing | 0 | Foreman | 95 | 10 | HR |  |  |  | 0 | 950 | 123.5 | 1073.5 | 2019-11-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Supervision / Kickoff-Orientations, yard set up |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting22420190924-R01Foreman10950 | Corbiere and Sons Contracting22420190924-R01Foreman10950Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 224 | 20190924-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 74 | HR |  |  |  | 0 | 6660 | 865.8 | 7525.8 | 2019-11-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Supervision / Kickoff-Orientations, yard set up |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting22420190924-R01Operator - Principle746660 | Corbiere and Sons Contracting22420190924-R01Operator - Principle746660Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 6660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 224 | 20190924-R01 | 53520101 | Clearing | 0 | Operator - Intermdiate | 75 | 10 | HR |  |  |  | 0 | 750 | 97.5 | 847.5 | 2019-11-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Supervision / Kickoff-Orientations, yard set up |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting22420190924-R01Operator - Intermdiate10750 | Corbiere and Sons Contracting22420190924-R01Operator - Intermdiate10750Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 224 | 20190924-R01 | 53520101 | Clearing | 0 | Labourer - Specialized | 75 | 40 | HR |  |  |  | 0 | 3000 | 390 | 3390 | 2019-11-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Supervision / Kickoff-Orientations, yard set up |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting22420190924-R01Labourer - Specialized403000 | Corbiere and Sons Contracting22420190924-R01Labourer - Specialized403000Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3000 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 224 | 20190924-R01 | 53520101 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-11-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Supervision / Kickoff-Orientations, yard set up |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting22420190924-R01Labourer - General10650 | Corbiere and Sons Contracting22420190924-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 224 | 20190924-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 16 | DAY |  |  |  | 0 | 3360 | 436.8 | 3796.8 | 2019-11-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Supervision / Kickoff-Orientations, yard set up |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting22420190924-R01L.O.A.163360 | Corbiere and Sons Contracting22420190924-R01L.O.A.163360Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 100 | 20190925-2-R02 | 53520105 | Clearing | 0 | Feller Buncher | 240 | 4 | HR |  |  |  |  | 960 | 124.8 | 1084.8 | 2019-09-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Yard Preparation |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10020190925-2-R02Feller Buncher4960 | Corbiere and Sons Contracting10020190925-2-R02Feller Buncher4960Inv#004-R02 |  |  | WF1-Indirects |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 100 | 20190925-2-R02 | 53520105 | Clearing | 0 | Mulcher | 205 | 9 | HR |  |  |  |  | 1845 | 239.85 | 2084.85 | 2019-09-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Yard Preparation |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10020190925-2-R02Mulcher91845 | Corbiere and Sons Contracting10020190925-2-R02Mulcher91845Inv#004-R02 |  |  | WF1-Indirects |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 100 | 20190925-2-R02 | 53520105 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR |  |  |  |  | 1539 | 200.07 | 1739.07 | 2019-09-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Yard Preparation |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10020190925-2-R02Excavator - 36 ton91539 | Corbiere and Sons Contracting10020190925-2-R02Excavator - 36 ton91539Inv#004-R02 |  |  | WF1-Indirects |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 100 | 20190925-2-R02 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR |  |  |  |  | 891 | 115.83 | 1006.83 | 2019-09-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Yard Preparation |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10020190925-2-R02Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting10020190925-2-R02Loader JD 524 to 624 or equal9891Inv#004-R02 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 100 | 20190925-2-R02 | 53520105 | Clearing | 0 | ATV - Side by Side w/ roll bar | 22.5 | 9 | HR |  |  |  |  | 202.5 | 26.325 | 228.825 | 2019-09-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Yard Preparation |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10020190925-2-R02ATV - Side by Side w/ roll bar9202.5 | Corbiere and Sons Contracting10020190925-2-R02ATV - Side by Side w/ roll bar9202.5Inv#004-R02 |  |  | WF1-Indirects |  |  | 1 | 202.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 100 | 20190925-2-R02 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 70 | HR |  |  |  | 0 | 6300 | 819 | 7119 | 2019-09-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Yard Preparation |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10020190925-2-R02Operator - Principle706300 | Corbiere and Sons Contracting10020190925-2-R02Operator - Principle706300Inv#004-R02 |  |  | WF1-Indirects |  |  | 1 | 6300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 100 | 20190925-2-R02 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 16 | HR |  |  |  | 0 | 1200 | 156 | 1356 | 2019-09-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Yard Preparation |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10020190925-2-R02Operator - Intermdiate161200 | Corbiere and Sons Contracting10020190925-2-R02Operator - Intermdiate161200Inv#004-R02 |  |  | WF1-Indirects |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 100 | 20190925-2-R02 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 15 | HR |  |  |  | 0 | 1125 | 146.25 | 1271.25 | 2019-09-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Yard Preparation |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10020190925-2-R02Labourer - Specialized151125 | Corbiere and Sons Contracting10020190925-2-R02Labourer - Specialized151125Inv#004-R02 |  |  | WF1-Indirects |  |  | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 100 | 20190925-2-R02 | 53520105 | Clearing | 0 | Labourer - General | 65 | 21 | HR |  |  |  | 0 | 1365 | 177.45 | 1542.45 | 2019-09-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Yard Preparation |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10020190925-2-R02Labourer - General211365 | Corbiere and Sons Contracting10020190925-2-R02Labourer - General211365Inv#004-R02 |  |  | WF1-Indirects |  |  | 1 | 1365 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 100 | 20190925-2-R02 | 53520105 | Clearing | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2019-09-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Yard Preparation |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10020190925-2-R02L.O.A.102100 | Corbiere and Sons Contracting10020190925-2-R02L.O.A.102100Inv#004-R02 |  |  | WF1-Indirects |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 101 | 20190925-3-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 5 | HR |  |  |  |  | 1200 | 156 | 1356 | 2019-09-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10120190925-3-R01Feller Buncher51200 | Corbiere and Sons Contracting10120190925-3-R01Feller Buncher51200Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 101 | 20190925-3-R01 | 53520101 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 4 | HR |  |  |  |  | 540 | 70.2 | 610.2 | 2019-09-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10120190925-3-R01Tractor Trailer - 60 Ton4540 | Corbiere and Sons Contracting10120190925-3-R01Tractor Trailer - 60 Ton4540Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 540 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 101 | 20190925-3-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 5 | HR |  |  |  | 0 | 450 | 58.5 | 508.5 | 2019-09-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10120190925-3-R01Operator - Principle5450 | Corbiere and Sons Contracting10120190925-3-R01Operator - Principle5450Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 101 | 20190925-3-R01 | 53520101 | Clearing | 0 | Operator - Intermdiate | 75 | 4 | HR |  |  |  | 0 | 300 | 39 | 339 | 2019-09-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10120190925-3-R01Operator - Intermdiate4300 | Corbiere and Sons Contracting10120190925-3-R01Operator - Intermdiate4300Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 101 | 20190925-3-R01 | 53520101 | Clearing | 0 | Labourer - General | 65 | 5 | HR |  |  |  | 0 | 325 | 42.25 | 367.25 | 2019-09-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10120190925-3-R01Labourer - General5325 | Corbiere and Sons Contracting10120190925-3-R01Labourer - General5325Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 325 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 102 | 20190926-1-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 70 | HR | 22.5 | 0 |  |  | 2100 | 273 | 2373 | 2019-09-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Pending |  |  | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10220190926-1-R01Light Truck - Pick up702100 | Corbiere and Sons Contracting10220190926-1-R01Light Truck - Pick up702100Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 102 | 20190926-1-R01 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-09-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Pending |  |  | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10220190926-1-R01Project Manager121320 | Corbiere and Sons Contracting10220190926-1-R01Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 102 | 20190926-1-R01 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-09-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Pending |  |  | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10220190926-1-R01Superintendent121260 | Corbiere and Sons Contracting10220190926-1-R01Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 102 | 20190926-1-R01 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-09-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Pending |  |  | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10220190926-1-R01Project Coordinator12960 | Corbiere and Sons Contracting10220190926-1-R01Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 102 | 20190926-1-R01 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-09-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Pending |  |  | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10220190926-1-R01Construction Coordinator11880 | Corbiere and Sons Contracting10220190926-1-R01Construction Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 102 | 20190926-1-R01 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-09-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Pending |  |  | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10220190926-1-R01Safety Advisor121020 | Corbiere and Sons Contracting10220190926-1-R01Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 102 | 20190926-1-R01 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-09-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Pending |  |  | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10220190926-1-R01Project Controls10700 | Corbiere and Sons Contracting10220190926-1-R01Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 102 | 20190926-1-R01 | 53520101 | Clearing | 0 | Foreman | 95 | 11 | HR |  |  |  | 0 | 1045 | 135.85 | 1180.85 | 2019-09-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Pending |  |  | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10220190926-1-R01Foreman111045 | Corbiere and Sons Contracting10220190926-1-R01Foreman111045Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1045 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 102 | 20190926-1-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-09-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Pending |  |  | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10220190926-1-R01L.O.A.71470 | Corbiere and Sons Contracting10220190926-1-R01L.O.A.71470Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 103 | 20190926-2-R02 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR |  |  |  |  | 891 | 115.83 | 1006.83 | 2019-09-26 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM in error due to wrong rate for Operator - Intermdiate. LEM shows $90/hr. For equipment only the ATV and Mechanic's truck is correct on LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Preperation and care of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10320190926-2-R02Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting10320190926-2-R02Loader JD 524 to 624 or equal9891Inv#004-R02 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 103 | 20190926-2-R02 | 53520105 | Clearing | 0 | ATV - Side by Side w/ roll bar | 22.5 | 10 | HR |  |  |  |  | 225 | 29.25 | 254.25 | 2019-09-26 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM in error due to wrong rate for Operator - Intermdiate. LEM shows $90/hr. For equipment only the ATV and Mechanic's truck is correct on LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Preperation and care of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10320190926-2-R02ATV - Side by Side w/ roll bar10225 | Corbiere and Sons Contracting10320190926-2-R02ATV - Side by Side w/ roll bar10225Inv#004-R02 |  |  | WF1-Indirects |  |  | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 103 | 20190926-2-R02 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR |  |  |  |  | 1350 | 175.5 | 1525.5 | 2019-09-26 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM in error due to wrong rate for Operator - Intermdiate. LEM shows $90/hr. For equipment only the ATV and Mechanic's truck is correct on LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Preperation and care of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10320190926-2-R02Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting10320190926-2-R02Tractor Trailer - 60 Ton101350Inv#004-R02 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 103 | 20190926-2-R02 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-09-26 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM in error due to wrong rate for Operator - Intermdiate. LEM shows $90/hr. For equipment only the ATV and Mechanic's truck is correct on LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Preperation and care of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10320190926-2-R02Operator - Principle332970 | Corbiere and Sons Contracting10320190926-2-R02Operator - Principle332970Inv#004-R02 |  |  | WF1-Indirects |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 103 | 20190926-2-R02 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-09-26 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM in error due to wrong rate for Operator - Intermdiate. LEM shows $90/hr. For equipment only the ATV and Mechanic's truck is correct on LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Preperation and care of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10320190926-2-R02Operator - Intermdiate11825 | Corbiere and Sons Contracting10320190926-2-R02Operator - Intermdiate11825Inv#004-R02 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 103 | 20190926-2-R02 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 22 | HR |  |  |  | 0 | 1650 | 214.5 | 1864.5 | 2019-09-26 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM in error due to wrong rate for Operator - Intermdiate. LEM shows $90/hr. For equipment only the ATV and Mechanic's truck is correct on LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Preperation and care of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10320190926-2-R02Labourer - Specialized221650 | Corbiere and Sons Contracting10320190926-2-R02Labourer - Specialized221650Inv#004-R02 |  |  | WF1-Indirects |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 103 | 20190926-2-R02 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-09-26 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM in error due to wrong rate for Operator - Intermdiate. LEM shows $90/hr. For equipment only the ATV and Mechanic's truck is correct on LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Preperation and care of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10320190926-2-R02Labourer - General10650 | Corbiere and Sons Contracting10320190926-2-R02Labourer - General10650Inv#004-R02 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 103 | 20190926-2-R02 | 53520105 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-09-26 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM in error due to wrong rate for Operator - Intermdiate. LEM shows $90/hr. For equipment only the ATV and Mechanic's truck is correct on LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Preperation and care of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10320190926-2-R02L.O.A.4840 | Corbiere and Sons Contracting10320190926-2-R02L.O.A.4840Inv#004-R02 |  |  | WF1-Indirects |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 104 | 20190926-3-R01-SplitA | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR |  |  |  |  | 2160 | 280.8 | 2440.8 | 2019-09-26 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Splitted for invoicing on inv#004 - the remaining LEM amount is listed as SplitB and was invoiced on inv#005 - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10420190926-3-R01-SplitAFeller Buncher92160 | Corbiere and Sons Contracting10420190926-3-R01-SplitAFeller Buncher92160Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 104 | 20190926-3-R01-SplitA | 53520101 | Clearing | 0 | Mulcher | 205 | 4 | HR |  |  |  |  | 820 | 106.6 | 926.6 | 2019-09-26 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Splitted for invoicing on inv#004 - the remaining LEM amount is listed as SplitB and was invoiced on inv#005 - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10420190926-3-R01-SplitAMulcher4820 | Corbiere and Sons Contracting10420190926-3-R01-SplitAMulcher4820Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 820 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 104 | 20190926-3-R01-SplitA | 53520101 | Clearing | 0 | Skidder | 171 | 2 | HR |  |  |  |  | 342 | 44.46 | 386.46 | 2019-09-26 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Splitted for invoicing on inv#004 - the remaining LEM amount is listed as SplitB and was invoiced on inv#005 - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10420190926-3-R01-SplitASkidder 2342 | Corbiere and Sons Contracting10420190926-3-R01-SplitASkidder 2342Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 342 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 104 | 20190926-3-R01-SplitA | 53520101 | Clearing | 0 | Dozer D6 or equal | 135 | 6 | HR |  |  |  |  | 810 | 105.3 | 915.3 | 2019-09-26 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Splitted for invoicing on inv#004 - the remaining LEM amount is listed as SplitB and was invoiced on inv#005 - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10420190926-3-R01-SplitADozer D6 or equal6810 | Corbiere and Sons Contracting10420190926-3-R01-SplitADozer D6 or equal6810Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 810 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 104 | 20190926-3-R01-SplitA | 53520101 | Clearing | 0 | Excavator - 30 ton | 139.5 | 6 | HR | 104.63 |  |  |  | 837 | 108.81 | 945.81 | 2019-09-26 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Splitted for invoicing on inv#004 - the remaining LEM amount is listed as SplitB and was invoiced on inv#005 - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10420190926-3-R01-SplitAExcavator - 30 ton6837 | Corbiere and Sons Contracting10420190926-3-R01-SplitAExcavator - 30 ton6837Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 837 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 104 | 20190926-3-R01-SplitA | 53520101 | Clearing | 0 | Operator - Principle | 90 | 19.4974 | HR |  |  |  | 0 | 1754.766 | 228.1196 | 1982.8856 | 2019-09-26 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Splitted for invoicing on inv#004 - the remaining LEM amount is listed as SplitB and was invoiced on inv#005 - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10420190926-3-R01-SplitAOperator - Principle19.49741754.766 | Corbiere and Sons Contracting10420190926-3-R01-SplitAOperator - Principle19.49741754.766Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1754.766 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 104 | 20190926-3-R01-SplitA | 53520101 | Clearing | 0 | Labourer - General | 65 | 22 | HR |  |  |  | 0 | 1430 | 185.9 | 1615.9 | 2019-09-26 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Splitted for invoicing on inv#004 - the remaining LEM amount is listed as SplitB and was invoiced on inv#005 - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10420190926-3-R01-SplitALabourer - General221430 | Corbiere and Sons Contracting10420190926-3-R01-SplitALabourer - General221430Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1430 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 104 | 20190926-3-R01-SplitA | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-09-26 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Splitted for invoicing on inv#004 - the remaining LEM amount is listed as SplitB and was invoiced on inv#005 - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10420190926-3-R01-SplitAL.O.A.51050 | Corbiere and Sons Contracting10420190926-3-R01-SplitAL.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1032 | 20190926-3-R01-SplitB | 53520101 | Clearing | 0 | Operator - Principle | 90 | 24.5026 | HR |  |  | 0 | 0 | 2205.234 | 286.6804 | 2491.9144 | 2019-09-26 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Splitted for invoicing on inv#005 - the remaining LEM amount is listed as SplitA and was invoiced on inv#004 - NM |  |  |  |  | Clearing A003 |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting103220190926-3-R01-SplitBOperator - Principle24.50262205.234 | Corbiere and Sons Contracting103220190926-3-R01-SplitBOperator - Principle24.50262205.234Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2205.234 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 105 | 20190927-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 70 | HR | 22.5 | 0 |  |  | 2100 | 273 | 2373 | 2019-09-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10520190927-1Light Truck - Pick up702100 | Corbiere and Sons Contracting10520190927-1Light Truck - Pick up702100Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 105 | 20190927-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-09-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10520190927-1Project Manager121320 | Corbiere and Sons Contracting10520190927-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 105 | 20190927-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-09-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10520190927-1Superintendent121260 | Corbiere and Sons Contracting10520190927-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 105 | 20190927-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-09-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10520190927-1Project Coordinator12960 | Corbiere and Sons Contracting10520190927-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 105 | 20190927-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-09-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10520190927-1Construction Coordinator11880 | Corbiere and Sons Contracting10520190927-1Construction Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 105 | 20190927-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-09-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10520190927-1Safety Advisor121020 | Corbiere and Sons Contracting10520190927-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 105 | 20190927-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-09-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10520190927-1Project Controls10700 | Corbiere and Sons Contracting10520190927-1Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 105 | 20190927-1 | 53520101 | Clearing | 0 | Foreman | 95 | 11 | HR |  |  |  | 0 | 1045 | 135.85 | 1180.85 | 2019-09-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10520190927-1Foreman111045 | Corbiere and Sons Contracting10520190927-1Foreman111045Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1045 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 105 | 20190927-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-09-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10520190927-1L.O.A.71470 | Corbiere and Sons Contracting10520190927-1L.O.A.71470Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 106 | 20190927-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR |  |  |  |  | 891 | 115.83 | 1006.83 | 2019-09-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Error noted due to wrong rate for Loader and Tractor Trailer as per rate sheet provided. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10620190927-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting10620190927-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 106 | 20190927-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR |  |  |  |  | 1350 | 175.5 | 1525.5 | 2019-09-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Error noted due to wrong rate for Loader and Tractor Trailer as per rate sheet provided. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10620190927-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting10620190927-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 106 | 20190927-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-09-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Error noted due to wrong rate for Loader and Tractor Trailer as per rate sheet provided. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10620190927-2-R01Operator - Principle11990 | Corbiere and Sons Contracting10620190927-2-R01Operator - Principle11990Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 106 | 20190927-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-09-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Error noted due to wrong rate for Loader and Tractor Trailer as per rate sheet provided. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10620190927-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting10620190927-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 106 | 20190927-2-R01 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 10 | HR |  |  |  | 0 | 750 | 97.5 | 847.5 | 2019-09-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Error noted due to wrong rate for Loader and Tractor Trailer as per rate sheet provided. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10620190927-2-R01Labourer - Specialized10750 | Corbiere and Sons Contracting10620190927-2-R01Labourer - Specialized10750Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 106 | 20190927-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-09-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Error noted due to wrong rate for Loader and Tractor Trailer as per rate sheet provided. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10620190927-2-R01Labourer - General10650 | Corbiere and Sons Contracting10620190927-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 106 | 20190927-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-09-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Error noted due to wrong rate for Loader and Tractor Trailer as per rate sheet provided. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10620190927-2-R01L.O.A.2420 | Corbiere and Sons Contracting10620190927-2-R01L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 107 | 20190927-3-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR |  |  |  |  | 2160 | 280.8 | 2440.8 | 2019-09-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10720190927-3-R01Feller Buncher92160 | Corbiere and Sons Contracting10720190927-3-R01Feller Buncher92160Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 107 | 20190927-3-R01 | 53520101 | Clearing | 0 | Mulcher | 205 | 9 | HR |  |  |  |  | 1845 | 239.85 | 2084.85 | 2019-09-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10720190927-3-R01Mulcher91845 | Corbiere and Sons Contracting10720190927-3-R01Mulcher91845Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 107 | 20190927-3-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR |  |  |  |  | 1539 | 200.07 | 1739.07 | 2019-09-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10720190927-3-R01Skidder 91539 | Corbiere and Sons Contracting10720190927-3-R01Skidder 91539Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 107 | 20190927-3-R01 | 53520101 | Clearing | 0 | Dozer D6 or equal | 135 | 9 | HR |  |  |  |  | 1215 | 157.95 | 1372.95 | 2019-09-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10720190927-3-R01Dozer D6 or equal91215 | Corbiere and Sons Contracting10720190927-3-R01Dozer D6 or equal91215Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 107 | 20190927-3-R01 | 53520101 | Clearing | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 |  |  |  | 1255.5 | 163.215 | 1418.715 | 2019-09-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10720190927-3-R01Excavator - 30 ton91255.5 | Corbiere and Sons Contracting10720190927-3-R01Excavator - 30 ton91255.5Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 107 | 20190927-3-R01 | 53520101 | Clearing | 0 | ATV - Side by Side w/ roll bar | 22.5 | 9 | HR |  |  |  |  | 202.5 | 26.325 | 228.825 | 2019-09-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10720190927-3-R01ATV - Side by Side w/ roll bar9202.5 | Corbiere and Sons Contracting10720190927-3-R01ATV - Side by Side w/ roll bar9202.5Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 202.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 107 | 20190927-3-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 55 | HR |  |  |  | 0 | 4950 | 643.5 | 5593.5 | 2019-09-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10720190927-3-R01Operator - Principle554950 | Corbiere and Sons Contracting10720190927-3-R01Operator - Principle554950Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 107 | 20190927-3-R01 | 53520101 | Clearing | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-09-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10720190927-3-R01Labourer - Specialized11825 | Corbiere and Sons Contracting10720190927-3-R01Labourer - Specialized11825Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 107 | 20190927-3-R01 | 53520101 | Clearing | 0 | Labourer - General | 65 | 22 | HR |  |  |  | 0 | 1430 | 185.9 | 1615.9 | 2019-09-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10720190927-3-R01Labourer - General221430 | Corbiere and Sons Contracting10720190927-3-R01Labourer - General221430Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1430 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 107 | 20190927-3-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-09-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  | A003 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting10720190927-3-R01L.O.A.61260 | Corbiere and Sons Contracting10720190927-3-R01L.O.A.61260Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 111 | 20190928-03-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR |  |  |  |  | 2160 | 280.8 | 2440.8 | 2019-09-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003-A010 |  |  | A003-A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11120190928-03-R01Feller Buncher92160 | Corbiere and Sons Contracting11120190928-03-R01Feller Buncher92160Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 111 | 20190928-03-R01 | 53520101 | Clearing | 0 | Mulcher | 205 | 9 | HR |  |  |  |  | 1845 | 239.85 | 2084.85 | 2019-09-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003-A010 |  |  | A003-A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11120190928-03-R01Mulcher91845 | Corbiere and Sons Contracting11120190928-03-R01Mulcher91845Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 111 | 20190928-03-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR |  |  |  |  | 1539 | 200.07 | 1739.07 | 2019-09-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003-A010 |  |  | A003-A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11120190928-03-R01Skidder 91539 | Corbiere and Sons Contracting11120190928-03-R01Skidder 91539Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 111 | 20190928-03-R01 | 53520101 | Clearing | 0 | Dozer D6 or equal | 135 | 9 | HR |  |  |  |  | 1215 | 157.95 | 1372.95 | 2019-09-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003-A010 |  |  | A003-A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11120190928-03-R01Dozer D6 or equal91215 | Corbiere and Sons Contracting11120190928-03-R01Dozer D6 or equal91215Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 111 | 20190928-03-R01 | 53520101 | Clearing | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 |  |  |  | 1255.5 | 163.215 | 1418.715 | 2019-09-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003-A010 |  |  | A003-A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11120190928-03-R01Excavator - 30 ton91255.5 | Corbiere and Sons Contracting11120190928-03-R01Excavator - 30 ton91255.5Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 111 | 20190928-03-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 55 | HR |  |  |  | 0 | 4950 | 643.5 | 5593.5 | 2019-09-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003-A010 |  |  | A003-A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11120190928-03-R01Operator - Principle554950 | Corbiere and Sons Contracting11120190928-03-R01Operator - Principle554950Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 111 | 20190928-03-R01 | 53520101 | Clearing | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-09-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003-A010 |  |  | A003-A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11120190928-03-R01Labourer - Specialized11825 | Corbiere and Sons Contracting11120190928-03-R01Labourer - Specialized11825Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 111 | 20190928-03-R01 | 53520101 | Clearing | 0 | Labourer - General | 65 | 22 | HR |  |  |  | 0 | 1430 | 185.9 | 1615.9 | 2019-09-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003-A010 |  |  | A003-A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11120190928-03-R01Labourer - General221430 | Corbiere and Sons Contracting11120190928-03-R01Labourer - General221430Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1430 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 111 | 20190928-03-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-09-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003-A010 |  |  | A003-A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11120190928-03-R01L.O.A.61260 | Corbiere and Sons Contracting11120190928-03-R01L.O.A.61260Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 109 | 20190928-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 70 | HR |  |  |  |  | 2100 | 273 | 2373 | 2019-09-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10920190928-1Light Truck - Pick up702100 | Corbiere and Sons Contracting10920190928-1Light Truck - Pick up702100Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 109 | 20190928-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-09-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10920190928-1Project Manager121320 | Corbiere and Sons Contracting10920190928-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 109 | 20190928-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-09-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10920190928-1Superintendent121260 | Corbiere and Sons Contracting10920190928-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 109 | 20190928-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-09-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10920190928-1Project Coordinator12960 | Corbiere and Sons Contracting10920190928-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 109 | 20190928-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-09-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10920190928-1Construction Coordinator11880 | Corbiere and Sons Contracting10920190928-1Construction Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 109 | 20190928-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-09-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10920190928-1Safety Advisor121020 | Corbiere and Sons Contracting10920190928-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 109 | 20190928-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-09-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10920190928-1Project Controls10700 | Corbiere and Sons Contracting10920190928-1Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 109 | 20190928-1 | 53520101 | Clearing | 0 | Foreman | 95 | 11 | HR |  |  |  | 0 | 1045 | 135.85 | 1180.85 | 2019-09-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10920190928-1Foreman111045 | Corbiere and Sons Contracting10920190928-1Foreman111045Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1045 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 109 | 20190928-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-09-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting10920190928-1L.O.A.71470 | Corbiere and Sons Contracting10920190928-1L.O.A.71470Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 110 | 20190928-2-R01 | 53520105 | Clearing | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 |  |  |  | 1255.5 | 163.215 | 1418.715 | 2019-09-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11020190928-2-R01Excavator - 30 ton91255.5 | Corbiere and Sons Contracting11020190928-2-R01Excavator - 30 ton91255.5Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 110 | 20190928-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR |  |  |  |  | 891 | 115.83 | 1006.83 | 2019-09-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11020190928-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting11020190928-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 110 | 20190928-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 9 | HR |  |  |  |  | 1215 | 157.95 | 1372.95 | 2019-09-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11020190928-2-R01Tractor Trailer - 60 Ton91215 | Corbiere and Sons Contracting11020190928-2-R01Tractor Trailer - 60 Ton91215Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 110 | 20190928-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-09-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11020190928-2-R01Operator - Principle221980 | Corbiere and Sons Contracting11020190928-2-R01Operator - Principle221980Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 110 | 20190928-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-09-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11020190928-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting11020190928-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 110 | 20190928-2-R01 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-09-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11020190928-2-R01Labourer - Specialized11825 | Corbiere and Sons Contracting11020190928-2-R01Labourer - Specialized11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 110 | 20190928-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-09-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11020190928-2-R01Labourer - General10650 | Corbiere and Sons Contracting11020190928-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 110 | 20190928-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-09-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11020190928-2-R01L.O.A.3630 | Corbiere and Sons Contracting11020190928-2-R01L.O.A.3630Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 112 | 20190929-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 70 | HR |  |  |  |  | 2100 | 273 | 2373 | 2019-09-29 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11220190929-1Light Truck - Pick up702100 | Corbiere and Sons Contracting11220190929-1Light Truck - Pick up702100Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 112 | 20190929-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-09-29 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11220190929-1Project Manager121320 | Corbiere and Sons Contracting11220190929-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 112 | 20190929-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-09-29 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11220190929-1Superintendent121260 | Corbiere and Sons Contracting11220190929-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 112 | 20190929-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-09-29 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11220190929-1Project Coordinator12960 | Corbiere and Sons Contracting11220190929-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 112 | 20190929-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-09-29 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11220190929-1Construction Coordinator11880 | Corbiere and Sons Contracting11220190929-1Construction Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 112 | 20190929-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-09-29 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11220190929-1Safety Advisor121020 | Corbiere and Sons Contracting11220190929-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 112 | 20190929-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-09-29 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11220190929-1Project Controls10700 | Corbiere and Sons Contracting11220190929-1Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 112 | 20190929-1 | 53520101 | Clearing | 0 | Foreman | 95 | 11 | HR |  |  |  | 0 | 1045 | 135.85 | 1180.85 | 2019-09-29 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11220190929-1Foreman111045 | Corbiere and Sons Contracting11220190929-1Foreman111045Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1045 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 112 | 20190929-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-09-29 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11220190929-1L.O.A.71470 | Corbiere and Sons Contracting11220190929-1L.O.A.71470Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 113 | 20190929-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 6 | HR |  |  |  |  | 594 | 77.22 | 671.22 | 2019-09-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11320190929-2-R01Loader JD 524 to 624 or equal6594 | Corbiere and Sons Contracting11320190929-2-R01Loader JD 524 to 624 or equal6594Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 594 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 113 | 20190929-2-R01 | 53520105 | Clearing | 0 | ATV - Side by Side w/ roll bar | 22.5 | 9 | HR |  |  |  |  | 202.5 | 26.325 | 228.825 | 2019-09-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11320190929-2-R01ATV - Side by Side w/ roll bar9202.5 | Corbiere and Sons Contracting11320190929-2-R01ATV - Side by Side w/ roll bar9202.5Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 202.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 113 | 20190929-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR |  |  |  |  | 1350 | 175.5 | 1525.5 | 2019-09-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11320190929-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting11320190929-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 113 | 20190929-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-09-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11320190929-2-R01Operator - Principle11990 | Corbiere and Sons Contracting11320190929-2-R01Operator - Principle11990Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 113 | 20190929-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-09-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11320190929-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting11320190929-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 113 | 20190929-2-R01 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-09-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11320190929-2-R01Labourer - Specialized11825 | Corbiere and Sons Contracting11320190929-2-R01Labourer - Specialized11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 113 | 20190929-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-09-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11320190929-2-R01Labourer - General10650 | Corbiere and Sons Contracting11320190929-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 113 | 20190929-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-09-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11320190929-2-R01L.O.A.2420 | Corbiere and Sons Contracting11320190929-2-R01L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 114 | 20190929-3-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR |  |  |  |  | 2160 | 280.8 | 2440.8 | 2019-09-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11420190929-3-R01Feller Buncher92160 | Corbiere and Sons Contracting11420190929-3-R01Feller Buncher92160Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 114 | 20190929-3-R01 | 53520101 | Clearing | 0 | Mulcher | 205 | 5 | HR |  |  |  |  | 1025 | 133.25 | 1158.25 | 2019-09-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11420190929-3-R01Mulcher51025 | Corbiere and Sons Contracting11420190929-3-R01Mulcher51025Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1025 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 114 | 20190929-3-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 15 | HR |  |  |  |  | 2565 | 333.45 | 2898.45 | 2019-09-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11420190929-3-R01Skidder 152565 | Corbiere and Sons Contracting11420190929-3-R01Skidder 152565Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2565 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 114 | 20190929-3-R01 | 53520101 | Clearing | 0 | Dozer D6 or equal | 135 | 9 | HR |  |  |  |  | 1215 | 157.95 | 1372.95 | 2019-09-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11420190929-3-R01Dozer D6 or equal91215 | Corbiere and Sons Contracting11420190929-3-R01Dozer D6 or equal91215Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 114 | 20190929-3-R01 | 53520101 | Clearing | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 |  |  |  | 1255.5 | 163.215 | 1418.715 | 2019-09-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11420190929-3-R01Excavator - 30 ton91255.5 | Corbiere and Sons Contracting11420190929-3-R01Excavator - 30 ton91255.5Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 114 | 20190929-3-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 61 | HR |  |  |  | 0 | 5490 | 713.7 | 6203.7 | 2019-09-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11420190929-3-R01Operator - Principle615490 | Corbiere and Sons Contracting11420190929-3-R01Operator - Principle615490Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5490 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 114 | 20190929-3-R01 | 53520101 | Clearing | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-09-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11420190929-3-R01Labourer - Specialized11825 | Corbiere and Sons Contracting11420190929-3-R01Labourer - Specialized11825Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 114 | 20190929-3-R01 | 53520102 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-09-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11420190929-3-R01Labourer - General11715 | Corbiere and Sons Contracting11420190929-3-R01Labourer - General11715Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 114 | 20190929-3-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-09-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11420190929-3-R01L.O.A.71470 | Corbiere and Sons Contracting11420190929-3-R01L.O.A.71470Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 115 | 20190930-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 70 | HR |  |  |  |  | 2100 | 273 | 2373 | 2019-09-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11520190930-1Light Truck - Pick up702100 | Corbiere and Sons Contracting11520190930-1Light Truck - Pick up702100Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 115 | 20190930-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-09-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11520190930-1Project Manager121320 | Corbiere and Sons Contracting11520190930-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 115 | 20190930-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-09-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11520190930-1Superintendent121260 | Corbiere and Sons Contracting11520190930-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 115 | 20190930-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-09-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11520190930-1Project Coordinator12960 | Corbiere and Sons Contracting11520190930-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 115 | 20190930-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-09-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11520190930-1Construction Coordinator11880 | Corbiere and Sons Contracting11520190930-1Construction Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 115 | 20190930-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-09-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11520190930-1Safety Advisor121020 | Corbiere and Sons Contracting11520190930-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 115 | 20190930-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-09-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11520190930-1Project Controls10700 | Corbiere and Sons Contracting11520190930-1Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 115 | 20190930-1 | 53520101 | Clearing | 0 | Foreman | 95 | 11 | HR |  |  |  | 0 | 1045 | 135.85 | 1180.85 | 2019-09-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11520190930-1Foreman111045 | Corbiere and Sons Contracting11520190930-1Foreman111045Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1045 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 115 | 20190930-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-09-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11520190930-1L.O.A.71470 | Corbiere and Sons Contracting11520190930-1L.O.A.71470Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 116 | 20190930-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 2 | HR |  |  |  |  | 198 | 25.74 | 223.74 | 2019-09-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11620190930-2-R01Loader JD 524 to 624 or equal2198 | Corbiere and Sons Contracting11620190930-2-R01Loader JD 524 to 624 or equal2198Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 198 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 116 | 20190930-2-R01 | 53520105 | Clearing | 0 | ATV - Side by Side w/ roll bar | 22.5 | 9 | HR |  |  |  |  | 202.5 | 26.325 | 228.825 | 2019-09-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11620190930-2-R01ATV - Side by Side w/ roll bar9202.5 | Corbiere and Sons Contracting11620190930-2-R01ATV - Side by Side w/ roll bar9202.5Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 202.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 116 | 20190930-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 5.5 | HR |  |  |  |  | 742.5 | 96.525 | 839.025 | 2019-09-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11620190930-2-R01Tractor Trailer - 60 Ton5.5742.5 | Corbiere and Sons Contracting11620190930-2-R01Tractor Trailer - 60 Ton5.5742.5Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 742.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 116 | 20190930-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 6 | HR |  |  |  | 0 | 540 | 70.2 | 610.2 | 2019-09-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11620190930-2-R01Operator - Principle6540 | Corbiere and Sons Contracting11620190930-2-R01Operator - Principle6540Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 540 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 116 | 20190930-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 8 | HR |  |  |  | 0 | 600 | 78 | 678 | 2019-09-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11620190930-2-R01Operator - Intermdiate8600 | Corbiere and Sons Contracting11620190930-2-R01Operator - Intermdiate8600Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 116 | 20190930-2-R01 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 6 | HR |  |  |  | 0 | 450 | 58.5 | 508.5 | 2019-09-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11620190930-2-R01Labourer - Specialized6450 | Corbiere and Sons Contracting11620190930-2-R01Labourer - Specialized6450Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 116 | 20190930-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-09-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11620190930-2-R01Labourer - General10650 | Corbiere and Sons Contracting11620190930-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 116 | 20190930-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-09-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11620190930-2-R01L.O.A.2420 | Corbiere and Sons Contracting11620190930-2-R01L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 117 | 20190930-3-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 |  |  |  | 2160 | 280.8 | 2440.8 | 2019-09-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11720190930-3-R01Feller Buncher92160 | Corbiere and Sons Contracting11720190930-3-R01Feller Buncher92160Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 117 | 20190930-3-R01 | 53520101 | Clearing | 0 | Mulcher | 205 | 9 | HR |  |  |  |  | 1845 | 239.85 | 2084.85 | 2019-09-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11720190930-3-R01Mulcher91845 | Corbiere and Sons Contracting11720190930-3-R01Mulcher91845Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 117 | 20190930-3-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 15 | HR | 128.25 |  |  |  | 2565 | 333.45 | 2898.45 | 2019-09-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11720190930-3-R01Skidder 152565 | Corbiere and Sons Contracting11720190930-3-R01Skidder 152565Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2565 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 117 | 20190930-3-R01 | 53520101 | Clearing | 0 | Dozer D6 or equal | 135 | 9 | HR |  |  |  |  | 1215 | 157.95 | 1372.95 | 2019-09-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11720190930-3-R01Dozer D6 or equal91215 | Corbiere and Sons Contracting11720190930-3-R01Dozer D6 or equal91215Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 117 | 20190930-3-R01 | 53520101 | Clearing | 0 | Excavator - 30 ton | 139.5 | 6 | HR | 104.63 |  |  |  | 837 | 108.81 | 945.81 | 2019-09-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11720190930-3-R01Excavator - 30 ton6837 | Corbiere and Sons Contracting11720190930-3-R01Excavator - 30 ton6837Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 837 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 117 | 20190930-3-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 63 | HR |  |  |  | 0 | 5670 | 737.1 | 6407.1 | 2019-09-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11720190930-3-R01Operator - Principle635670 | Corbiere and Sons Contracting11720190930-3-R01Operator - Principle635670Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5670 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 117 | 20190930-3-R01 | 53520101 | Clearing | 0 | Labourer - General | 65 | 22 | HR |  |  |  | 0 | 1430 | 185.9 | 1615.9 | 2019-09-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11720190930-3-R01Labourer - General221430 | Corbiere and Sons Contracting11720190930-3-R01Labourer - General221430Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1430 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 117 | 20190930-3-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-09-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting11720190930-3-R01L.O.A.71470 | Corbiere and Sons Contracting11720190930-3-R01L.O.A.71470Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 119 | 20191001-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 70 | HR |  |  |  |  | 2100 | 273 | 2373 | 2019-10-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11920191001-1Light Truck - Pick up702100 | Corbiere and Sons Contracting11920191001-1Light Truck - Pick up702100Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 119 | 20191001-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11920191001-1Project Manager121320 | Corbiere and Sons Contracting11920191001-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 119 | 20191001-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11920191001-1Superintendent121260 | Corbiere and Sons Contracting11920191001-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 119 | 20191001-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11920191001-1Project Coordinator12960 | Corbiere and Sons Contracting11920191001-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 119 | 20191001-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-10-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11920191001-1Construction Coordinator11880 | Corbiere and Sons Contracting11920191001-1Construction Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 119 | 20191001-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11920191001-1Safety Advisor121020 | Corbiere and Sons Contracting11920191001-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 119 | 20191001-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-10-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11920191001-1Project Controls10700 | Corbiere and Sons Contracting11920191001-1Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 119 | 20191001-1 | 53520101 | Clearing | 0 | Foreman | 95 | 11 | HR |  |  |  | 0 | 1045 | 135.85 | 1180.85 | 2019-10-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11920191001-1Foreman111045 | Corbiere and Sons Contracting11920191001-1Foreman111045Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1045 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 119 | 20191001-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-10-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting11920191001-1L.O.A.71470 | Corbiere and Sons Contracting11920191001-1L.O.A.71470Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 120 | 20191001-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR |  |  |  |  | 891 | 115.83 | 1006.83 | 2019-10-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12020191001-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting12020191001-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 120 | 20191001-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 21 | HR |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2019-10-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12020191001-2-R01Operator - Principle211890 | Corbiere and Sons Contracting12020191001-2-R01Operator - Principle211890Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 120 | 20191001-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12020191001-2-R01Labourer - General10650 | Corbiere and Sons Contracting12020191001-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 120 | 20191001-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12020191001-2-R01L.O.A.2420 | Corbiere and Sons Contracting12020191001-2-R01L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 121 | 20191001-3 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR |  |  |  |  | 2160 | 280.8 | 2440.8 | 2019-10-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12120191001-3Feller Buncher92160 | Corbiere and Sons Contracting12120191001-3Feller Buncher92160Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 121 | 20191001-3 | 53520101 | Clearing | 0 | Mulcher | 205 | 9 | HR |  |  |  |  | 1845 | 239.85 | 2084.85 | 2019-10-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12120191001-3Mulcher91845 | Corbiere and Sons Contracting12120191001-3Mulcher91845Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 121 | 20191001-3 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR |  |  |  |  | 1539 | 200.07 | 1739.07 | 2019-10-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12120191001-3Skidder 91539 | Corbiere and Sons Contracting12120191001-3Skidder 91539Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 121 | 20191001-3 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR |  |  |  |  | 600 | 78 | 678 | 2019-10-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12120191001-3Light Truck - Pick up20600 | Corbiere and Sons Contracting12120191001-3Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 121 | 20191001-3 | 53520101 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 5.5 | HR |  |  |  |  | 742.5 | 96.525 | 839.025 | 2019-10-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12120191001-3Tractor Trailer - 60 Ton5.5742.5 | Corbiere and Sons Contracting12120191001-3Tractor Trailer - 60 Ton5.5742.5Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 742.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 121 | 20191001-3 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-10-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12120191001-3Operator - Principle332970 | Corbiere and Sons Contracting12120191001-3Operator - Principle332970Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 121 | 20191001-3 | 53520101 | Clearing | 0 | Operator - Intermdiate | 75 | 5.5 | HR |  |  |  | 0 | 412.5 | 53.625 | 466.125 | 2019-10-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12120191001-3Operator - Intermdiate5.5412.5 | Corbiere and Sons Contracting12120191001-3Operator - Intermdiate5.5412.5Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 412.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 121 | 20191001-3 | 53520101 | Clearing | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-10-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12120191001-3Labourer - Specialized11825 | Corbiere and Sons Contracting12120191001-3Labourer - Specialized11825Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 121 | 20191001-3 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-10-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12120191001-3L.O.A.4840 | Corbiere and Sons Contracting12120191001-3L.O.A.4840Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 123 | 20191002-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 70 | HR |  |  |  |  | 2100 | 273 | 2373 | 2019-10-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting12320191002-1Light Truck - Pick up702100 | Corbiere and Sons Contracting12320191002-1Light Truck - Pick up702100Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 123 | 20191002-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting12320191002-1Project Manager121320 | Corbiere and Sons Contracting12320191002-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 123 | 20191002-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting12320191002-1Superintendent121260 | Corbiere and Sons Contracting12320191002-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 123 | 20191002-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting12320191002-1Project Coordinator12960 | Corbiere and Sons Contracting12320191002-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 123 | 20191002-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-10-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting12320191002-1Construction Coordinator11880 | Corbiere and Sons Contracting12320191002-1Construction Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 123 | 20191002-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting12320191002-1Safety Advisor121020 | Corbiere and Sons Contracting12320191002-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 123 | 20191002-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-10-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting12320191002-1Project Controls10700 | Corbiere and Sons Contracting12320191002-1Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 123 | 20191002-1 | 53520101 | Clearing | 0 | Foreman | 95 | 11 | HR |  |  |  | 0 | 1045 | 135.85 | 1180.85 | 2019-10-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting12320191002-1Foreman111045 | Corbiere and Sons Contracting12320191002-1Foreman111045Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1045 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 123 | 20191002-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-10-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting12320191002-1L.O.A.71470 | Corbiere and Sons Contracting12320191002-1L.O.A.71470Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 124 | 20191002-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR |  |  |  |  | 891 | 115.83 | 1006.83 | 2019-10-02 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12420191002-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting12420191002-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 124 | 20191002-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR |  |  |  |  | 1350 | 175.5 | 1525.5 | 2019-10-02 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12420191002-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting12420191002-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 124 | 20191002-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 21 | HR |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2019-10-02 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12420191002-2-R01Operator - Principle211890 | Corbiere and Sons Contracting12420191002-2-R01Operator - Principle211890Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 124 | 20191002-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-10-02 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12420191002-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting12420191002-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 124 | 20191002-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-02 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12420191002-2-R01Labourer - General10650 | Corbiere and Sons Contracting12420191002-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 124 | 20191002-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-02 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General maintenance of yard and equipment |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12420191002-2-R01L.O.A.3630 | Corbiere and Sons Contracting12420191002-2-R01L.O.A.3630Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 125 | 20191002-3 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR |  |  |  |  | 2160 | 280.8 | 2440.8 | 2019-10-02 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12520191002-3Feller Buncher92160 | Corbiere and Sons Contracting12520191002-3Feller Buncher92160Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 125 | 20191002-3 | 53520101 | Clearing | 0 | Mulcher | 205 | 9 | HR |  |  |  |  | 1845 | 239.85 | 2084.85 | 2019-10-02 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12520191002-3Mulcher91845 | Corbiere and Sons Contracting12520191002-3Mulcher91845Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 125 | 20191002-3 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR |  |  |  |  | 1539 | 200.07 | 1739.07 | 2019-10-02 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12520191002-3Skidder 91539 | Corbiere and Sons Contracting12520191002-3Skidder 91539Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 125 | 20191002-3 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR |  |  |  |  | 600 | 78 | 678 | 2019-10-02 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12520191002-3Light Truck - Pick up20600 | Corbiere and Sons Contracting12520191002-3Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 125 | 20191002-3 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-10-02 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12520191002-3Operator - Principle332970 | Corbiere and Sons Contracting12520191002-3Operator - Principle332970Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 125 | 20191002-3 | 53520101 | Clearing | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-10-02 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12520191002-3Labourer - Specialized11825 | Corbiere and Sons Contracting12520191002-3Labourer - Specialized11825Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 125 | 20191002-3 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-02 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12520191002-3L.O.A.3630 | Corbiere and Sons Contracting12520191002-3L.O.A.3630Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 128 | 20191003-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 70 | HR |  |  |  |  | 2100 | 273 | 2373 | 2019-10-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting12820191003-1Light Truck - Pick up702100 | Corbiere and Sons Contracting12820191003-1Light Truck - Pick up702100Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 128 | 20191003-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting12820191003-1Project Manager121320 | Corbiere and Sons Contracting12820191003-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 128 | 20191003-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting12820191003-1Superintendent121260 | Corbiere and Sons Contracting12820191003-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 128 | 20191003-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting12820191003-1Project Coordinator12960 | Corbiere and Sons Contracting12820191003-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 128 | 20191003-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-10-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting12820191003-1Construction Coordinator11880 | Corbiere and Sons Contracting12820191003-1Construction Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 128 | 20191003-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting12820191003-1Safety Advisor121020 | Corbiere and Sons Contracting12820191003-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 128 | 20191003-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-10-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting12820191003-1Project Controls10700 | Corbiere and Sons Contracting12820191003-1Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 128 | 20191003-1 | 53520101 | Clearing | 0 | Foreman | 95 | 11 | HR |  |  |  | 0 | 1045 | 135.85 | 1180.85 | 2019-10-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting12820191003-1Foreman111045 | Corbiere and Sons Contracting12820191003-1Foreman111045Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1045 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 128 | 20191003-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-10-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting12820191003-1L.O.A.71470 | Corbiere and Sons Contracting12820191003-1L.O.A.71470Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 129 | 20191003-2 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR |  |  |  |  | 891 | 115.83 | 1006.83 | 2019-10-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM shows Operator-Principle with a rate of $90/hr and $75/hr. LEM is in error. - Corrected Nov 16, 19 RR Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard cleanup and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12920191003-2Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting12920191003-2Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 129 | 20191003-2 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 9 | HR |  |  |  |  | 1215 | 157.95 | 1372.95 | 2019-10-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM shows Operator-Principle with a rate of $90/hr and $75/hr. LEM is in error. - Corrected Nov 16, 19 RR Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard cleanup and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12920191003-2Tractor Trailer - 60 Ton91215 | Corbiere and Sons Contracting12920191003-2Tractor Trailer - 60 Ton91215Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 129 | 20191003-2 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM shows Operator-Principle with a rate of $90/hr and $75/hr. LEM is in error. - Corrected Nov 16, 19 RR Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard cleanup and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12920191003-2Operator - Principle11990 | Corbiere and Sons Contracting12920191003-2Operator - Principle11990Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 129 | 20191003-2 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-10-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM shows Operator-Principle with a rate of $90/hr and $75/hr. LEM is in error. - Corrected Nov 16, 19 RR Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard cleanup and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12920191003-2Operator - Intermdiate11825 | Corbiere and Sons Contracting12920191003-2Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 129 | 20191003-2 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM shows Operator-Principle with a rate of $90/hr and $75/hr. LEM is in error. - Corrected Nov 16, 19 RR Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard cleanup and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12920191003-2Labourer - General10650 | Corbiere and Sons Contracting12920191003-2Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 129 | 20191003-2 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM shows Operator-Principle with a rate of $90/hr and $75/hr. LEM is in error. - Corrected Nov 16, 19 RR Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard cleanup and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting12920191003-2L.O.A.2420 | Corbiere and Sons Contracting12920191003-2L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 130 | 20191003-3 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 4 | HR |  |  |  |  | 960 | 124.8 | 1084.8 | 2019-10-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and access |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting13020191003-3Feller Buncher4960 | Corbiere and Sons Contracting13020191003-3Feller Buncher4960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 130 | 20191003-3 | 53520101 | Clearing | 0 | Mulcher | 205 | 9 | HR |  |  |  |  | 1845 | 239.85 | 2084.85 | 2019-10-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and access |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting13020191003-3Mulcher91845 | Corbiere and Sons Contracting13020191003-3Mulcher91845Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 130 | 20191003-3 | 53520101 | Clearing | 0 | Skidder | 171 | 8 | HR |  |  |  |  | 1368 | 177.84 | 1545.84 | 2019-10-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and access |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting13020191003-3Skidder 81368 | Corbiere and Sons Contracting13020191003-3Skidder 81368Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1368 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 130 | 20191003-3 | 53520101 | Clearing | 0 | Dozer D6 or equal | 135 | 4 | HR |  |  |  |  | 540 | 70.2 | 610.2 | 2019-10-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and access |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting13020191003-3Dozer D6 or equal4540 | Corbiere and Sons Contracting13020191003-3Dozer D6 or equal4540Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 540 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 130 | 20191003-3 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR |  |  |  |  | 300 | 39 | 339 | 2019-10-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and access |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting13020191003-3Light Truck - Pick up10300 | Corbiere and Sons Contracting13020191003-3Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 130 | 20191003-3 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 31 | HR |  |  |  | 0 | 2790 | 362.7 | 3152.7 | 2019-10-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and access |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting13020191003-3Operator - Principle312790 | Corbiere and Sons Contracting13020191003-3Operator - Principle312790Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2790 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 130 | 20191003-3 | 53520101 | Clearing | 0 | Labourer - Specialized | 75 | 16 | HR |  |  |  | 0 | 1200 | 156 | 1356 | 2019-10-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and access |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting13020191003-3Labourer - Specialized161200 | Corbiere and Sons Contracting13020191003-3Labourer - Specialized161200Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 130 | 20191003-3 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-10-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and access |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting13020191003-3L.O.A.51050 | Corbiere and Sons Contracting13020191003-3L.O.A.51050Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 131 | 20191003-4 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR |  |  |  |  | 2280 | 296.4 | 2576.4 | 2019-10-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and access-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting13120191003-4Feller Buncher9.52280 | Corbiere and Sons Contracting13120191003-4Feller Buncher9.52280Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 131 | 20191003-4 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR |  |  |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and access-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting13120191003-4Skidder 9.51624.5 | Corbiere and Sons Contracting13120191003-4Skidder 9.51624.5Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 131 | 20191003-4 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR |  |  |  |  | 900 | 117 | 1017 | 2019-10-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and access-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting13120191003-4Light Truck - Pick up30900 | Corbiere and Sons Contracting13120191003-4Light Truck - Pick up30900Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 131 | 20191003-4 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-10-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and access-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting13120191003-4Foreman4380 | Corbiere and Sons Contracting13120191003-4Foreman4380Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 131 | 20191003-4 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and access-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting13120191003-4Operator - Principle221980 | Corbiere and Sons Contracting13120191003-4Operator - Principle221980Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 131 | 20191003-4 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and access-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting13120191003-4L.O.A.3630 | Corbiere and Sons Contracting13120191003-4L.O.A.3630Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 133 | 20191003-6 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 5 | HR |  |  |  |  | 2784 | 361.92 | 3145.92 | 2019-10-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material-A003-A010 |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting13320191003-6Grinder - 4710 Peterson or equal52784 | Corbiere and Sons Contracting13320191003-6Grinder - 4710 Peterson or equal52784Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2784 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 133 | 20191003-6 | 53520102 | Clearing | 0 | Log Loader | 153 | 5 | HR |  |  |  |  | 765 | 99.45 | 864.45 | 2019-10-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material-A003-A010 |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting13320191003-6Log Loader5765 | Corbiere and Sons Contracting13320191003-6Log Loader5765Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 765 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 133 | 20191003-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR |  |  |  |  | 300 | 39 | 339 | 2019-10-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material-A003-A010 |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting13320191003-6Light Truck - Pick up10300 | Corbiere and Sons Contracting13320191003-6Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 133 | 20191003-6 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 7 | HR |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material-A003-A010 |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting13320191003-6Operator - Principle7630 | Corbiere and Sons Contracting13320191003-6Operator - Principle7630Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 133 | 20191003-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material-A003-A010 |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting13320191003-6L.O.A.1210 | Corbiere and Sons Contracting13320191003-6L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 134 | 20191004-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR |  |  |  |  | 1800 | 234 | 2034 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting13420191004-1Light Truck - Pick up601800 | Corbiere and Sons Contracting13420191004-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 134 | 20191004-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting13420191004-1Project Manager121320 | Corbiere and Sons Contracting13420191004-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 134 | 20191004-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting13420191004-1Superintendent121260 | Corbiere and Sons Contracting13420191004-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 134 | 20191004-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 12 | 960 | 124.8 | 1084.8 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting13420191004-1Project Coordinator12960 | Corbiere and Sons Contracting13420191004-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 134 | 20191004-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting13420191004-1Construction Coordinator11880 | Corbiere and Sons Contracting13420191004-1Construction Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 134 | 20191004-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting13420191004-1Safety Advisor121020 | Corbiere and Sons Contracting13420191004-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 134 | 20191004-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting13420191004-1Project Controls10700 | Corbiere and Sons Contracting13420191004-1Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 134 | 20191004-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting13420191004-1L.O.A.61260 | Corbiere and Sons Contracting13420191004-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 135 | 20191004-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR |  |  |  |  | 891 | 115.83 | 1006.83 | 2019-10-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting13520191004-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting13520191004-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 135 | 20191004-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR |  |  |  |  | 1350 | 175.5 | 1525.5 | 2019-10-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting13520191004-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting13520191004-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 135 | 20191004-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-10-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting13520191004-2-R01Operator - Principle121080 | Corbiere and Sons Contracting13520191004-2-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 135 | 20191004-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-10-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting13520191004-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting13520191004-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 135 | 20191004-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting13520191004-2-R01Labourer - General10650 | Corbiere and Sons Contracting13520191004-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 135 | 20191004-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting13520191004-2-R01L.O.A.2420 | Corbiere and Sons Contracting13520191004-2-R01L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 136 | 20191004-3-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR |  |  |  |  | 2160 | 280.8 | 2440.8 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing and access-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting13620191004-3-R01Feller Buncher92160 | Corbiere and Sons Contracting13620191004-3-R01Feller Buncher92160Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 136 | 20191004-3-R01 | 53520101 | Clearing | 0 | Mulcher | 205 | 9 | HR |  |  |  |  | 1845 | 239.85 | 2084.85 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing and access-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting13620191004-3-R01Mulcher91845 | Corbiere and Sons Contracting13620191004-3-R01Mulcher91845Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 136 | 20191004-3-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR |  |  |  |  | 1539 | 200.07 | 1739.07 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing and access-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting13620191004-3-R01Skidder 91539 | Corbiere and Sons Contracting13620191004-3-R01Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 136 | 20191004-3-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR |  |  |  |  | 600 | 78 | 678 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing and access-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting13620191004-3-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting13620191004-3-R01Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 136 | 20191004-3-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing and access-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting13620191004-3-R01Operator - Principle332970 | Corbiere and Sons Contracting13620191004-3-R01Operator - Principle332970Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 136 | 20191004-3-R01 | 53520101 | Clearing | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing and access-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting13620191004-3-R01Labourer - Specialized11825 | Corbiere and Sons Contracting13620191004-3-R01Labourer - Specialized11825Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 136 | 20191004-3-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing and access-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting13620191004-3-R01L.O.A.3630 | Corbiere and Sons Contracting13620191004-3-R01L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 137 | 20191004-4 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR |  |  |  |  | 2280 | 296.4 | 2576.4 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing and Access-A028 |  |  | A028 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting13720191004-4Feller Buncher9.52280 | Corbiere and Sons Contracting13720191004-4Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 137 | 20191004-4 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR |  |  |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing and Access-A028 |  |  | A028 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting13720191004-4Skidder 9.51624.5 | Corbiere and Sons Contracting13720191004-4Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 137 | 20191004-4 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR |  |  |  |  | 900 | 117 | 1017 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing and Access-A028 |  |  | A028 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting13720191004-4Light Truck - Pick up30900 | Corbiere and Sons Contracting13720191004-4Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 137 | 20191004-4 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing and Access-A028 |  |  | A028 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting13720191004-4Foreman4380 | Corbiere and Sons Contracting13720191004-4Foreman4380Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 137 | 20191004-4 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing and Access-A028 |  |  | A028 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting13720191004-4Operator - Principle221980 | Corbiere and Sons Contracting13720191004-4Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 137 | 20191004-4 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing and Access-A028 |  |  | A028 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting13720191004-4L.O.A.3630 | Corbiere and Sons Contracting13720191004-4L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 140 | 20191004-7 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR |  |  |  |  | 5011.2 | 651.456 | 5662.656 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting14020191004-7Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting14020191004-7Grinder - 4710 Peterson or equal95011.2Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 140 | 20191004-7 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR |  |  |  |  | 1377 | 179.01 | 1556.01 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting14020191004-7Log Loader91377 | Corbiere and Sons Contracting14020191004-7Log Loader91377Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 140 | 20191004-7 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR |  |  |  |  | 300 | 39 | 339 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting14020191004-7Light Truck - Pick up10300 | Corbiere and Sons Contracting14020191004-7Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 140 | 20191004-7 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting14020191004-7Operator - Principle11990 | Corbiere and Sons Contracting14020191004-7Operator - Principle11990Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 140 | 20191004-7 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting14020191004-7L.O.A.1210 | Corbiere and Sons Contracting14020191004-7L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 143 | 20191005-03-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR |  |  |  |  | 2280 | 296.4 | 2576.4 | 2019-10-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Equipment rates are wrong in DB as to the LEMS provided. RR- Corrected Nov 16, 2019 |  |  |  |  | North Shore - Clearing and Access-A028 |  |  | A028 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting14320191005-03-R01Feller Buncher9.52280 | Corbiere and Sons Contracting14320191005-03-R01Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 143 | 20191005-03-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR |  |  |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Equipment rates are wrong in DB as to the LEMS provided. RR- Corrected Nov 16, 2019 |  |  |  |  | North Shore - Clearing and Access-A028 |  |  | A028 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting14320191005-03-R01Skidder 9.51624.5 | Corbiere and Sons Contracting14320191005-03-R01Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 143 | 20191005-03-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR |  |  |  |  | 900 | 117 | 1017 | 2019-10-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Equipment rates are wrong in DB as to the LEMS provided. RR- Corrected Nov 16, 2019 |  |  |  |  | North Shore - Clearing and Access-A028 |  |  | A028 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting14320191005-03-R01Light Truck - Pick up30900 | Corbiere and Sons Contracting14320191005-03-R01Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 143 | 20191005-03-R01 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-10-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Equipment rates are wrong in DB as to the LEMS provided. RR- Corrected Nov 16, 2019 |  |  |  |  | North Shore - Clearing and Access-A028 |  |  | A028 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting14320191005-03-R01Foreman4380 | Corbiere and Sons Contracting14320191005-03-R01Foreman4380Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 143 | 20191005-03-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Equipment rates are wrong in DB as to the LEMS provided. RR- Corrected Nov 16, 2019 |  |  |  |  | North Shore - Clearing and Access-A028 |  |  | A028 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting14320191005-03-R01Operator - Principle221980 | Corbiere and Sons Contracting14320191005-03-R01Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 143 | 20191005-03-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Equipment rates are wrong in DB as to the LEMS provided. RR- Corrected Nov 16, 2019 |  |  |  |  | North Shore - Clearing and Access-A028 |  |  | A028 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting14320191005-03-R01L.O.A.3630 | Corbiere and Sons Contracting14320191005-03-R01L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 145 | 20191005-05-R01 | 53510112 | Access | 0 | Dozer D6 or equal | 135 | 3 | HR |  |  |  |  | 405 | 52.65 | 457.65 | 2019-10-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Equipment rates off, and LEM identifies LOA but not totalling properly. Missing 210.00. RR- Corrected Nov 16, 19 |  |  |  |  | Maintenance of access road-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting14520191005-05-R01Dozer D6 or equal3405 | Corbiere and Sons Contracting14520191005-05-R01Dozer D6 or equal3405Inv#002-R01 | [5 empty] | 1 | 405 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 145 | 20191005-05-R01 | 53510112 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR |  |  |  |  | 300 | 39 | 339 | 2019-10-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Equipment rates off, and LEM identifies LOA but not totalling properly. Missing 210.00. RR- Corrected Nov 16, 19 |  |  |  |  | Maintenance of access road-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting14520191005-05-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting14520191005-05-R01Light Truck - Pick up10300Inv#002-R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 145 | 20191005-05-R01 | 53510112 | Access | 0 | Operator - Principle | 90 | 4 | HR |  |  |  | 0 | 360 | 46.8 | 406.8 | 2019-10-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Equipment rates off, and LEM identifies LOA but not totalling properly. Missing 210.00. RR- Corrected Nov 16, 19 |  |  |  |  | Maintenance of access road-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting14520191005-05-R01Operator - Principle4360 | Corbiere and Sons Contracting14520191005-05-R01Operator - Principle4360Inv#002-R01 | [5 empty] | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 141 | 20191005-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR |  |  |  |  | 1800 | 234 | 2034 | 2019-10-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting14120191005-1Light Truck - Pick up601800 | Corbiere and Sons Contracting14120191005-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 141 | 20191005-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting14120191005-1Project Manager121320 | Corbiere and Sons Contracting14120191005-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 141 | 20191005-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting14120191005-1Superintendent121260 | Corbiere and Sons Contracting14120191005-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 141 | 20191005-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting14120191005-1Project Coordinator12960 | Corbiere and Sons Contracting14120191005-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 141 | 20191005-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-10-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting14120191005-1Construction Coordinator11880 | Corbiere and Sons Contracting14120191005-1Construction Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 141 | 20191005-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting14120191005-1Safety Advisor121020 | Corbiere and Sons Contracting14120191005-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 141 | 20191005-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-10-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting14120191005-1Project Controls10700 | Corbiere and Sons Contracting14120191005-1Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 141 | 20191005-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting14120191005-1L.O.A.61260 | Corbiere and Sons Contracting14120191005-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 142 | 20191005-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR |  |  |  |  | 891 | 115.83 | 1006.83 | 2019-10-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting14220191005-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting14220191005-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 142 | 20191005-2-R01 | 53520101 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR |  |  |  |  | 1350 | 175.5 | 1525.5 | 2019-10-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting14220191005-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting14220191005-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 142 | 20191005-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-10-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting14220191005-2-R01Operator - Principle121080 | Corbiere and Sons Contracting14220191005-2-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 142 | 20191005-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-10-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting14220191005-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting14220191005-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 142 | 20191005-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting14220191005-2-R01Labourer - General10650 | Corbiere and Sons Contracting14220191005-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 142 | 20191005-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting14220191005-2-R01L.O.A.2420 | Corbiere and Sons Contracting14220191005-2-R01L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 147 | 20191005-7 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 8 | HR |  |  |  |  | 4454.4 | 579.072 | 5033.472 | 2019-10-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting14720191005-7Grinder - 4710 Peterson or equal84454.4 | Corbiere and Sons Contracting14720191005-7Grinder - 4710 Peterson or equal84454.4Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4454.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 147 | 20191005-7 | 53520102 | Clearing | 0 | Log Loader | 153 | 8 | HR |  |  |  |  | 1224 | 159.12 | 1383.12 | 2019-10-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting14720191005-7Log Loader81224 | Corbiere and Sons Contracting14720191005-7Log Loader81224Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1224 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 147 | 20191005-7 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR |  |  |  |  | 300 | 39 | 339 | 2019-10-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting14720191005-7Light Truck - Pick up10300 | Corbiere and Sons Contracting14720191005-7Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 147 | 20191005-7 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 10 | HR |  |  |  | 0 | 900 | 117 | 1017 | 2019-10-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting14720191005-7Operator - Principle10900 | Corbiere and Sons Contracting14720191005-7Operator - Principle10900Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 147 | 20191005-7 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting14720191005-7L.O.A.1210 | Corbiere and Sons Contracting14720191005-7L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 148 | 20191006-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR |  |  |  |  | 1500 | 195 | 1695 | 2019-10-06 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM | [8 empty] | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting14820191006-1Light Truck - Pick up501500 | Corbiere and Sons Contracting14820191006-1Light Truck - Pick up501500Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 148 | 20191006-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-06 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM | [8 empty] | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting14820191006-1Project Manager121320 | Corbiere and Sons Contracting14820191006-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 148 | 20191006-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-06 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM | [8 empty] | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting14820191006-1Superintendent121260 | Corbiere and Sons Contracting14820191006-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 148 | 20191006-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-06 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM | [8 empty] | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting14820191006-1Project Coordinator12960 | Corbiere and Sons Contracting14820191006-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 148 | 20191006-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-10-06 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM | [8 empty] | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting14820191006-1Construction Coordinator11880 | Corbiere and Sons Contracting14820191006-1Construction Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 148 | 20191006-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-06 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM | [8 empty] | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting14820191006-1Safety Advisor121020 | Corbiere and Sons Contracting14820191006-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 148 | 20191006-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 0 | HR |  |  |  | 0 | 0 | 0 | 0 | 2019-10-06 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM | [8 empty] | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting14820191006-1Project Controls00 | Corbiere and Sons Contracting14820191006-1Project Controls00Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 0 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 148 | 20191006-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-06 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM | [8 empty] | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting14820191006-1L.O.A.61260 | Corbiere and Sons Contracting14820191006-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 149 | 20191006-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR |  |  |  |  | 891 | 115.83 | 1006.83 | 2019-10-06 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. Orientations. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting14920191006-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting14920191006-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 149 | 20191006-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR |  |  |  |  | 1350 | 175.5 | 1525.5 | 2019-10-06 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. Orientations. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting14920191006-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting14920191006-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 149 | 20191006-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 32 | HR |  |  |  | 0 | 2880 | 374.4 | 3254.4 | 2019-10-06 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. Orientations. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting14920191006-2-R01Operator - Principle322880 | Corbiere and Sons Contracting14920191006-2-R01Operator - Principle322880Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 2880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 149 | 20191006-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-10-06 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. Orientations. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting14920191006-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting14920191006-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 149 | 20191006-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-06 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. Orientations. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting14920191006-2-R01Labourer - General10650 | Corbiere and Sons Contracting14920191006-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 149 | 20191006-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-06 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. Orientations. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting14920191006-2-R01L.O.A.61260 | Corbiere and Sons Contracting14920191006-2-R01L.O.A.61260Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 150 | 20191006-3 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR |  |  |  |  | 2160 | 280.8 | 2440.8 | 2019-10-06 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM | [7 empty] | A003 to A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting15020191006-3Feller Buncher92160 | Corbiere and Sons Contracting15020191006-3Feller Buncher92160Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 150 | 20191006-3 | 53520101 | Clearing | 0 | Skidder | 171 | 4.5 | HR |  |  |  |  | 769.5 | 100.035 | 869.535 | 2019-10-06 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM | [7 empty] | A003 to A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting15020191006-3Skidder 4.5769.5 | Corbiere and Sons Contracting15020191006-3Skidder 4.5769.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 769.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 150 | 20191006-3 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR |  |  |  |  | 300 | 39 | 339 | 2019-10-06 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM | [7 empty] | A003 to A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting15020191006-3Light Truck - Pick up10300 | Corbiere and Sons Contracting15020191006-3Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 150 | 20191006-3 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 18 | HR |  |  |  | 0 | 1620 | 210.6 | 1830.6 | 2019-10-06 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM | [7 empty] | A003 to A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting15020191006-3Operator - Principle181620 | Corbiere and Sons Contracting15020191006-3Operator - Principle181620Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1620 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 150 | 20191006-3 | 53520101 | Clearing | 0 | L.O.A. | 210 | 0 | DAY |  |  |  | 0 | 0 | 0 | 0 | 2019-10-06 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM | [7 empty] | A003 to A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting15020191006-3L.O.A.00 | Corbiere and Sons Contracting15020191006-3L.O.A.00Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 0 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 152 | 20191006-5 | 53510112 | Access | 0 | Excavator - 30 ton | 139.5 | 3.5 | HR | 104.63 |  |  |  | 488.25 | 63.4725 | 551.7225 | 2019-10-06 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Maintenance of access road-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting15220191006-5Excavator - 30 ton3.5488.25 | Corbiere and Sons Contracting15220191006-5Excavator - 30 ton3.5488.25Inv#002-R01 | [5 empty] | 1 | 488.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 152 | 20191006-5 | 53510112 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR |  |  |  |  | 300 | 39 | 339 | 2019-10-06 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Maintenance of access road-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting15220191006-5Light Truck - Pick up10300 | Corbiere and Sons Contracting15220191006-5Light Truck - Pick up10300Inv#002-R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 152 | 20191006-5 | 53510112 | Access | 0 | Operator - Principle | 90 | 4 | HR |  |  |  | 0 | 360 | 46.8 | 406.8 | 2019-10-06 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Maintenance of access road-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting15220191006-5Operator - Principle4360 | Corbiere and Sons Contracting15220191006-5Operator - Principle4360Inv#002-R01 | [5 empty] | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 152 | 20191006-5 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-06 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Maintenance of access road-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting15220191006-5L.O.A.1210 | Corbiere and Sons Contracting15220191006-5L.O.A.1210Inv#002-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 154 | 20191006-7 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR |  |  |  |  | 5011.2 | 651.456 | 5662.656 | 2019-10-06 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting15420191006-7Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting15420191006-7Grinder - 4710 Peterson or equal95011.2Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 154 | 20191006-7 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR |  |  |  |  | 1377 | 179.01 | 1556.01 | 2019-10-06 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting15420191006-7Log Loader91377 | Corbiere and Sons Contracting15420191006-7Log Loader91377Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 154 | 20191006-7 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR |  |  |  |  | 300 | 39 | 339 | 2019-10-06 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting15420191006-7Light Truck - Pick up10300 | Corbiere and Sons Contracting15420191006-7Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 154 | 20191006-7 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-06 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting15420191006-7Operator - Principle11990 | Corbiere and Sons Contracting15420191006-7Operator - Principle11990Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 154 | 20191006-7 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-06 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting15420191006-7L.O.A.1210 | Corbiere and Sons Contracting15420191006-7L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 155 | 20191007-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR |  |  |  |  | 1800 | 234 | 2034 | 2019-10-07 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting15520191007-1Light Truck - Pick up601800 | Corbiere and Sons Contracting15520191007-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 155 | 20191007-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-07 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting15520191007-1Project Manager121320 | Corbiere and Sons Contracting15520191007-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 155 | 20191007-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-07 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting15520191007-1Superintendent121260 | Corbiere and Sons Contracting15520191007-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 155 | 20191007-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-10-07 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting15520191007-1Project Coordinator11880 | Corbiere and Sons Contracting15520191007-1Project Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 155 | 20191007-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-10-07 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting15520191007-1Construction Coordinator11880 | Corbiere and Sons Contracting15520191007-1Construction Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 155 | 20191007-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-07 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting15520191007-1Safety Advisor121020 | Corbiere and Sons Contracting15520191007-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 155 | 20191007-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-10-07 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting15520191007-1Project Controls10700 | Corbiere and Sons Contracting15520191007-1Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 155 | 20191007-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-07 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting15520191007-1L.O.A.61260 | Corbiere and Sons Contracting15520191007-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 156 | 20191007-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR |  |  |  |  | 891 | 115.83 | 1006.83 | 2019-10-07 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. Orientations. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting15620191007-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting15620191007-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 156 | 20191007-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR |  |  |  |  | 1350 | 175.5 | 1525.5 | 2019-10-07 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. Orientations. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting15620191007-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting15620191007-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 156 | 20191007-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 32 | HR |  |  |  | 0 | 2880 | 374.4 | 3254.4 | 2019-10-07 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. Orientations. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting15620191007-2-R01Operator - Principle322880 | Corbiere and Sons Contracting15620191007-2-R01Operator - Principle322880Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 2880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 156 | 20191007-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-10-07 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. Orientations. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting15620191007-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting15620191007-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 156 | 20191007-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-07 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. Orientations. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting15620191007-2-R01Labourer - General10650 | Corbiere and Sons Contracting15620191007-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 156 | 20191007-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-10-07 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. Orientations. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting15620191007-2-R01L.O.A.51050 | Corbiere and Sons Contracting15620191007-2-R01L.O.A.51050Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 157 | 20191007-3-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 18 | HR |  |  |  |  | 4320 | 561.6 | 4881.6 | 2019-10-07 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing and Access in segment 1 |  |  | A003 to A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting15720191007-3-R01Feller Buncher184320 | Corbiere and Sons Contracting15720191007-3-R01Feller Buncher184320Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 157 | 20191007-3-R01 | 53520101 | Clearing | 0 | Mulcher | 205 | 9 | HR |  |  |  |  | 1845 | 239.85 | 2084.85 | 2019-10-07 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing and Access in segment 1 |  |  | A003 to A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting15720191007-3-R01Mulcher91845 | Corbiere and Sons Contracting15720191007-3-R01Mulcher91845Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 157 | 20191007-3-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR |  |  |  |  | 1539 | 200.07 | 1739.07 | 2019-10-07 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing and Access in segment 1 |  |  | A003 to A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting15720191007-3-R01Skidder 91539 | Corbiere and Sons Contracting15720191007-3-R01Skidder 91539Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 157 | 20191007-3-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR |  |  |  |  | 600 | 78 | 678 | 2019-10-07 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing and Access in segment 1 |  |  | A003 to A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting15720191007-3-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting15720191007-3-R01Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 157 | 20191007-3-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-10-07 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing and Access in segment 1 |  |  | A003 to A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting15720191007-3-R01Operator - Principle443960 | Corbiere and Sons Contracting15720191007-3-R01Operator - Principle443960Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 157 | 20191007-3-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-10-07 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing and Access in segment 1 |  |  | A003 to A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting15720191007-3-R01L.O.A.4840 | Corbiere and Sons Contracting15720191007-3-R01L.O.A.4840Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 158 | 20191007-4 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR |  |  |  |  | 2280 | 296.4 | 2576.4 | 2019-10-07 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A26 |  |  | A026 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting15820191007-4Feller Buncher9.52280 | Corbiere and Sons Contracting15820191007-4Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 158 | 20191007-4 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR |  |  |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-07 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A26 |  |  | A026 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting15820191007-4Skidder 9.51624.5 | Corbiere and Sons Contracting15820191007-4Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 158 | 20191007-4 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR |  |  |  |  | 900 | 117 | 1017 | 2019-10-07 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A26 |  |  | A026 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting15820191007-4Light Truck - Pick up30900 | Corbiere and Sons Contracting15820191007-4Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 158 | 20191007-4 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-10-07 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A26 |  |  | A026 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting15820191007-4Foreman4380 | Corbiere and Sons Contracting15820191007-4Foreman4380Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 158 | 20191007-4 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-07 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A26 |  |  | A026 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting15820191007-4Operator - Principle221980 | Corbiere and Sons Contracting15820191007-4Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 158 | 20191007-4 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-07 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A26 |  |  | A026 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting15820191007-4L.O.A.3630 | Corbiere and Sons Contracting15820191007-4L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 161 | 20191007-7 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR |  |  |  |  | 5011.2 | 651.456 | 5662.656 | 2019-10-07 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting16120191007-7Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting16120191007-7Grinder - 4710 Peterson or equal95011.2Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 161 | 20191007-7 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR |  |  |  |  | 1377 | 179.01 | 1556.01 | 2019-10-07 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting16120191007-7Log Loader91377 | Corbiere and Sons Contracting16120191007-7Log Loader91377Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 161 | 20191007-7 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR |  |  |  |  | 300 | 39 | 339 | 2019-10-07 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting16120191007-7Light Truck - Pick up10300 | Corbiere and Sons Contracting16120191007-7Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 161 | 20191007-7 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-07 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting16120191007-7Operator - Principle11990 | Corbiere and Sons Contracting16120191007-7Operator - Principle11990Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 161 | 20191007-7 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-07 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting16120191007-7L.O.A.1210 | Corbiere and Sons Contracting16120191007-7L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 162 | 20191008-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR |  |  |  |  | 1800 | 234 | 2034 | 2019-10-08 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting16220191008-1Light Truck - Pick up601800 | Corbiere and Sons Contracting16220191008-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 162 | 20191008-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-08 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting16220191008-1Project Manager121320 | Corbiere and Sons Contracting16220191008-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 162 | 20191008-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-08 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting16220191008-1Superintendent121260 | Corbiere and Sons Contracting16220191008-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 162 | 20191008-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-10-08 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting16220191008-1Project Coordinator11880 | Corbiere and Sons Contracting16220191008-1Project Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 162 | 20191008-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-10-08 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting16220191008-1Construction Coordinator11880 | Corbiere and Sons Contracting16220191008-1Construction Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 162 | 20191008-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-08 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting16220191008-1Safety Advisor121020 | Corbiere and Sons Contracting16220191008-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 162 | 20191008-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-10-08 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting16220191008-1Project Controls10700 | Corbiere and Sons Contracting16220191008-1Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 162 | 20191008-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-08 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting16220191008-1L.O.A.61260 | Corbiere and Sons Contracting16220191008-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 163 | 20191008-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR |  |  |  |  | 891 | 115.83 | 1006.83 | 2019-10-08 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting16320191008-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting16320191008-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 163 | 20191008-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 12 | HR |  |  |  |  | 1620 | 210.6 | 1830.6 | 2019-10-08 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting16320191008-2-R01Tractor Trailer - 60 Ton121620 | Corbiere and Sons Contracting16320191008-2-R01Tractor Trailer - 60 Ton121620Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1620 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 163 | 20191008-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-10-08 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting16320191008-2-R01Operator - Principle121080 | Corbiere and Sons Contracting16320191008-2-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 163 | 20191008-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 13 | HR |  |  |  | 0 | 975 | 126.75 | 1101.75 | 2019-10-08 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting16320191008-2-R01Operator - Intermdiate13975 | Corbiere and Sons Contracting16320191008-2-R01Operator - Intermdiate13975Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 163 | 20191008-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-08 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting16320191008-2-R01Labourer - General10650 | Corbiere and Sons Contracting16320191008-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 163 | 20191008-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-08 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting16320191008-2-R01L.O.A.2420 | Corbiere and Sons Contracting16320191008-2-R01L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 164 | 20191008-3-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 18 | HR | 180 |  |  |  | 4320 | 561.6 | 4881.6 | 2019-10-08 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing and Access in segment 1-A003 to A010 |  |  | A003 to A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting16420191008-3-R01Feller Buncher184320 | Corbiere and Sons Contracting16420191008-3-R01Feller Buncher184320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 164 | 20191008-3-R01 | 53520101 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 |  |  |  | 1845 | 239.85 | 2084.85 | 2019-10-08 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing and Access in segment 1-A003 to A010 |  |  | A003 to A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting16420191008-3-R01Mulcher91845 | Corbiere and Sons Contracting16420191008-3-R01Mulcher91845Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 164 | 20191008-3-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 |  |  |  | 1539 | 200.07 | 1739.07 | 2019-10-08 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing and Access in segment 1-A003 to A010 |  |  | A003 to A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting16420191008-3-R01Skidder 91539 | Corbiere and Sons Contracting16420191008-3-R01Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 164 | 20191008-3-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 |  |  |  | 600 | 78 | 678 | 2019-10-08 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing and Access in segment 1-A003 to A010 |  |  | A003 to A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting16420191008-3-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting16420191008-3-R01Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 164 | 20191008-3-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-10-08 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing and Access in segment 1-A003 to A010 |  |  | A003 to A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting16420191008-3-R01Operator - Principle443960 | Corbiere and Sons Contracting16420191008-3-R01Operator - Principle443960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 164 | 20191008-3-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-10-08 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing and Access in segment 1-A003 to A010 |  |  | A003 to A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting16420191008-3-R01L.O.A.4840 | Corbiere and Sons Contracting16420191008-3-R01L.O.A.4840Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 165 | 20191008-4 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR |  |  |  |  | 2280 | 296.4 | 2576.4 | 2019-10-08 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A025 |  |  | A025 | 0 |  |  | 12 | 43811 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting16520191008-4Feller Buncher9.52280 | Corbiere and Sons Contracting16520191008-4Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 165 | 20191008-4 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR |  |  |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-08 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A025 |  |  | A025 | 0 |  |  | 12 | 43811 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting16520191008-4Skidder 9.51624.5 | Corbiere and Sons Contracting16520191008-4Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 165 | 20191008-4 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR |  |  |  |  | 900 | 117 | 1017 | 2019-10-08 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A025 |  |  | A025 | 0 |  |  | 12 | 43811 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting16520191008-4Light Truck - Pick up30900 | Corbiere and Sons Contracting16520191008-4Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 165 | 20191008-4 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-10-08 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A025 |  |  | A025 | 0 |  |  | 12 | 43811 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting16520191008-4Foreman4380 | Corbiere and Sons Contracting16520191008-4Foreman4380Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 165 | 20191008-4 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-08 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A025 |  |  | A025 | 0 |  |  | 12 | 43811 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting16520191008-4Operator - Principle221980 | Corbiere and Sons Contracting16520191008-4Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 165 | 20191008-4 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-08 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A025 |  |  | A025 | 0 |  |  | 12 | 43811 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting16520191008-4L.O.A.3630 | Corbiere and Sons Contracting16520191008-4L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 168 | 20191008-7 | 53520101 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR |  |  |  |  | 5011.2 | 651.456 | 5662.656 | 2019-10-08 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting16820191008-7Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting16820191008-7Grinder - 4710 Peterson or equal95011.2Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 168 | 20191008-7 | 53520101 | Clearing | 0 | Log Loader | 153 | 9 | HR |  |  |  |  | 1377 | 179.01 | 1556.01 | 2019-10-08 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting16820191008-7Log Loader91377 | Corbiere and Sons Contracting16820191008-7Log Loader91377Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 168 | 20191008-7 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR |  |  |  |  | 300 | 39 | 339 | 2019-10-08 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting16820191008-7Light Truck - Pick up10300 | Corbiere and Sons Contracting16820191008-7Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 168 | 20191008-7 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-08 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting16820191008-7Operator - Principle11990 | Corbiere and Sons Contracting16820191008-7Operator - Principle11990Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 168 | 20191008-7 | 53520101 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-08 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting16820191008-7L.O.A.1210 | Corbiere and Sons Contracting16820191008-7L.O.A.1210Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 171 | 20191009-03-R02 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 18 | HR |  |  |  |  | 4320 | 561.6 | 4881.6 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tagged due to no standby for mulcher and other equipment rates being different than the LEM. RR- Corrected Nov 16, 19 |  |  |  |  | Clearing and Access in segment 1-A003 to A010 |  |  | A003 to A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting17120191009-03-R02Feller Buncher184320 | Corbiere and Sons Contracting17120191009-03-R02Feller Buncher184320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 171 | 20191009-03-R02 | 53520101 | Clearing | 0 | Mulcher | 205 | 3.5 | HR |  |  |  |  | 717.5 | 93.275 | 810.775 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tagged due to no standby for mulcher and other equipment rates being different than the LEM. RR- Corrected Nov 16, 19 |  |  |  |  | Clearing and Access in segment 1-A003 to A010 |  |  | A003 to A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting17120191009-03-R02Mulcher3.5717.5 | Corbiere and Sons Contracting17120191009-03-R02Mulcher3.5717.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 717.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 171 | 20191009-03-R02 | 53520102 | Clearing | 0 | Mulcher | 205 |  | HR | 153.75 | 6 |  |  | 922.5 | 119.925 | 1042.425 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tagged due to no standby for mulcher and other equipment rates being different than the LEM. RR- Corrected Nov 16, 19 |  |  |  |  | Clearing and Access in segment 1-A003 to A010 |  |  | A003 to A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting17120191009-03-R02Mulcher922.5 | Corbiere and Sons Contracting17120191009-03-R02Mulcher922.5Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 922.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 171 | 20191009-03-R02 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR |  |  |  |  | 1539 | 200.07 | 1739.07 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tagged due to no standby for mulcher and other equipment rates being different than the LEM. RR- Corrected Nov 16, 19 |  |  |  |  | Clearing and Access in segment 1-A003 to A010 |  |  | A003 to A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting17120191009-03-R02Skidder 91539 | Corbiere and Sons Contracting17120191009-03-R02Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 171 | 20191009-03-R02 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR |  |  |  |  | 600 | 78 | 678 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tagged due to no standby for mulcher and other equipment rates being different than the LEM. RR- Corrected Nov 16, 19 |  |  |  |  | Clearing and Access in segment 1-A003 to A010 |  |  | A003 to A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting17120191009-03-R02Light Truck - Pick up20600 | Corbiere and Sons Contracting17120191009-03-R02Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 171 | 20191009-03-R02 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tagged due to no standby for mulcher and other equipment rates being different than the LEM. RR- Corrected Nov 16, 19 |  |  |  |  | Clearing and Access in segment 1-A003 to A010 |  |  | A003 to A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting17120191009-03-R02Operator - Principle443960 | Corbiere and Sons Contracting17120191009-03-R02Operator - Principle443960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 171 | 20191009-03-R02 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tagged due to no standby for mulcher and other equipment rates being different than the LEM. RR- Corrected Nov 16, 19 |  |  |  |  | Clearing and Access in segment 1-A003 to A010 |  |  | A003 to A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting17120191009-03-R02L.O.A.4840 | Corbiere and Sons Contracting17120191009-03-R02L.O.A.4840Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 169 | 20191009-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR |  |  |  |  | 1800 | 234 | 2034 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting16920191009-1Light Truck - Pick up601800 | Corbiere and Sons Contracting16920191009-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 169 | 20191009-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting16920191009-1Project Manager121320 | Corbiere and Sons Contracting16920191009-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 169 | 20191009-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting16920191009-1Superintendent121260 | Corbiere and Sons Contracting16920191009-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 169 | 20191009-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting16920191009-1Project Coordinator11880 | Corbiere and Sons Contracting16920191009-1Project Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 169 | 20191009-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting16920191009-1Construction Coordinator11880 | Corbiere and Sons Contracting16920191009-1Construction Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 169 | 20191009-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting16920191009-1Safety Advisor121020 | Corbiere and Sons Contracting16920191009-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 169 | 20191009-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting16920191009-1Project Controls10700 | Corbiere and Sons Contracting16920191009-1Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 169 | 20191009-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting16920191009-1L.O.A.61260 | Corbiere and Sons Contracting16920191009-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 170 | 20191009-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR |  |  |  |  | 891 | 115.83 | 1006.83 | 2019-10-09 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting17020191009-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting17020191009-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 170 | 20191009-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 |  |  |  | 1350 | 175.5 | 1525.5 | 2019-10-09 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting17020191009-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting17020191009-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 170 | 20191009-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-10-09 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting17020191009-2-R01Operator - Principle121080 | Corbiere and Sons Contracting17020191009-2-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 170 | 20191009-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-10-09 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting17020191009-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting17020191009-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 170 | 20191009-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-09 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting17020191009-2-R01Labourer - General10650 | Corbiere and Sons Contracting17020191009-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 170 | 20191009-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-10-09 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting17020191009-2-R01Labourer - General11715 | Corbiere and Sons Contracting17020191009-2-R01Labourer - General11715Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 170 | 20191009-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  |  | 420 | 54.6 | 474.6 | 2019-10-09 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting17020191009-2-R01L.O.A.2420 | Corbiere and Sons Contracting17020191009-2-R01L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 172 | 20191009-4 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR |  |  |  |  | 2280 | 296.4 | 2576.4 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A024 |  |  | A024 | 0 |  |  | 12 | 43811 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting17220191009-4Feller Buncher9.52280 | Corbiere and Sons Contracting17220191009-4Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 172 | 20191009-4 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR |  |  |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A024 |  |  | A024 | 0 |  |  | 12 | 43811 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting17220191009-4Skidder 9.51624.5 | Corbiere and Sons Contracting17220191009-4Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 172 | 20191009-4 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR |  |  |  |  | 900 | 117 | 1017 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A024 |  |  | A024 | 0 |  |  | 12 | 43811 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting17220191009-4Light Truck - Pick up30900 | Corbiere and Sons Contracting17220191009-4Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 172 | 20191009-4 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A024 |  |  | A024 | 0 |  |  | 12 | 43811 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting17220191009-4Foreman4380 | Corbiere and Sons Contracting17220191009-4Foreman4380Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 172 | 20191009-4 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A024 |  |  | A024 | 0 |  |  | 12 | 43811 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting17220191009-4Operator - Principle221980 | Corbiere and Sons Contracting17220191009-4Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 172 | 20191009-4 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A024 |  |  | A024 | 0 |  |  | 12 | 43811 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting17220191009-4L.O.A.3630 | Corbiere and Sons Contracting17220191009-4L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 175 | 20191009-7 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR |  |  |  |  | 5011.2 | 651.456 | 5662.656 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting17520191009-7Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting17520191009-7Grinder - 4710 Peterson or equal95011.2Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 175 | 20191009-7 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR |  |  |  |  | 1377 | 179.01 | 1556.01 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting17520191009-7Log Loader91377 | Corbiere and Sons Contracting17520191009-7Log Loader91377Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 175 | 20191009-7 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR |  |  |  |  | 300 | 39 | 339 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting17520191009-7Light Truck - Pick up10300 | Corbiere and Sons Contracting17520191009-7Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 175 | 20191009-7 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting17520191009-7Operator - Principle11990 | Corbiere and Sons Contracting17520191009-7Operator - Principle11990Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 175 | 20191009-7 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting17520191009-7L.O.A.1210 | Corbiere and Sons Contracting17520191009-7L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 178 | 20191010-03-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 18 | HR |  |  |  |  | 4320 | 561.6 | 4881.6 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to wrong rate for Labourer-specialized, and wrong rates for equipment. RR- Corrected Nov 16, 19 |  |  |  |  | Clearing and Access in segment 1-A003 to A010 |  |  | A003 to A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting17820191010-03-R01Feller Buncher184320 | Corbiere and Sons Contracting17820191010-03-R01Feller Buncher184320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 178 | 20191010-03-R01 | 53520101 | Clearing | 0 | Mulcher | 205 | 9 | HR |  |  |  |  | 1845 | 239.85 | 2084.85 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to wrong rate for Labourer-specialized, and wrong rates for equipment. RR- Corrected Nov 16, 19 |  |  |  |  | Clearing and Access in segment 1-A003 to A010 |  |  | A003 to A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting17820191010-03-R01Mulcher91845 | Corbiere and Sons Contracting17820191010-03-R01Mulcher91845Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 178 | 20191010-03-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR |  |  |  |  | 1539 | 200.07 | 1739.07 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to wrong rate for Labourer-specialized, and wrong rates for equipment. RR- Corrected Nov 16, 19 |  |  |  |  | Clearing and Access in segment 1-A003 to A010 |  |  | A003 to A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting17820191010-03-R01Skidder 91539 | Corbiere and Sons Contracting17820191010-03-R01Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 178 | 20191010-03-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR |  |  |  |  | 600 | 78 | 678 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to wrong rate for Labourer-specialized, and wrong rates for equipment. RR- Corrected Nov 16, 19 |  |  |  |  | Clearing and Access in segment 1-A003 to A010 |  |  | A003 to A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting17820191010-03-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting17820191010-03-R01Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 178 | 20191010-03-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to wrong rate for Labourer-specialized, and wrong rates for equipment. RR- Corrected Nov 16, 19 |  |  |  |  | Clearing and Access in segment 1-A003 to A010 |  |  | A003 to A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting17820191010-03-R01Operator - Principle443960 | Corbiere and Sons Contracting17820191010-03-R01Operator - Principle443960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 178 | 20191010-03-R01 | 53520101 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to wrong rate for Labourer-specialized, and wrong rates for equipment. RR- Corrected Nov 16, 19 |  |  |  |  | Clearing and Access in segment 1-A003 to A010 |  |  | A003 to A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting17820191010-03-R01Labourer - General11715 | Corbiere and Sons Contracting17820191010-03-R01Labourer - General11715Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 178 | 20191010-03-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to wrong rate for Labourer-specialized, and wrong rates for equipment. RR- Corrected Nov 16, 19 |  |  |  |  | Clearing and Access in segment 1-A003 to A010 |  |  | A003 to A010 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting17820191010-03-R01L.O.A.51050 | Corbiere and Sons Contracting17820191010-03-R01L.O.A.51050Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 176 | 20191010-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR |  |  |  |  | 1800 | 234 | 2034 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting17620191010-1Light Truck - Pick up601800 | Corbiere and Sons Contracting17620191010-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 176 | 20191010-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting17620191010-1Project Manager121320 | Corbiere and Sons Contracting17620191010-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 176 | 20191010-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting17620191010-1Superintendent121260 | Corbiere and Sons Contracting17620191010-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 176 | 20191010-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting17620191010-1Project Coordinator11880 | Corbiere and Sons Contracting17620191010-1Project Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 176 | 20191010-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting17620191010-1Construction Coordinator11880 | Corbiere and Sons Contracting17620191010-1Construction Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 176 | 20191010-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting17620191010-1Safety Advisor121020 | Corbiere and Sons Contracting17620191010-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 176 | 20191010-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting17620191010-1Project Controls10700 | Corbiere and Sons Contracting17620191010-1Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 176 | 20191010-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting17620191010-1L.O.A.61260 | Corbiere and Sons Contracting17620191010-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 177 | 20191010-2 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR |  |  |  |  | 891 | 115.83 | 1006.83 | 2019-10-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting17720191010-2Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting17720191010-2Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 177 | 20191010-2 | 53520101 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR |  |  |  |  | 1350 | 175.5 | 1525.5 | 2019-10-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting17720191010-2Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting17720191010-2Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 177 | 20191010-2 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-10-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting17720191010-2Operator - Principle121080 | Corbiere and Sons Contracting17720191010-2Operator - Principle121080Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 177 | 20191010-2 | 53520101 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-10-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting17720191010-2Operator - Intermdiate11825 | Corbiere and Sons Contracting17720191010-2Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 177 | 20191010-2 | 53520101 | Clearing | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-10-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting17720191010-2Labourer - Specialized11825 | Corbiere and Sons Contracting17720191010-2Labourer - Specialized11825Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 177 | 20191010-2 | 53520101 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting17720191010-2Labourer - General10650 | Corbiere and Sons Contracting17720191010-2Labourer - General10650Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 177 | 20191010-2 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting17720191010-2L.O.A.2420 | Corbiere and Sons Contracting17720191010-2L.O.A.2420Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 179 | 20191010-4 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR |  |  |  |  | 2280 | 296.4 | 2576.4 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A023 |  |  | A023 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting17920191010-4Feller Buncher9.52280 | Corbiere and Sons Contracting17920191010-4Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 179 | 20191010-4 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR |  |  |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A023 |  |  | A023 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting17920191010-4Skidder 9.51624.5 | Corbiere and Sons Contracting17920191010-4Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 179 | 20191010-4 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR |  |  |  |  | 900 | 117 | 1017 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A023 |  |  | A023 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting17920191010-4Light Truck - Pick up30900 | Corbiere and Sons Contracting17920191010-4Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 179 | 20191010-4 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A023 |  |  | A023 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting17920191010-4Foreman4380 | Corbiere and Sons Contracting17920191010-4Foreman4380Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 179 | 20191010-4 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A023 |  |  | A023 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting17920191010-4Operator - Principle221980 | Corbiere and Sons Contracting17920191010-4Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 179 | 20191010-4 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | North Shore - Clearing near tower A023 |  |  | A023 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting17920191010-4L.O.A.3630 | Corbiere and Sons Contracting17920191010-4L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 182 | 20191010-7 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR |  |  |  |  | 5011.2 | 651.456 | 5662.656 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 34 | 43794 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting18220191010-7Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting18220191010-7Grinder - 4710 Peterson or equal95011.2Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 182 | 20191010-7 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR |  |  |  |  | 1377 | 179.01 | 1556.01 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 34 | 43794 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting18220191010-7Log Loader91377 | Corbiere and Sons Contracting18220191010-7Log Loader91377Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 182 | 20191010-7 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR |  |  |  |  | 300 | 39 | 339 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 34 | 43794 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting18220191010-7Light Truck - Pick up10300 | Corbiere and Sons Contracting18220191010-7Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 182 | 20191010-7 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 34 | 43794 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting18220191010-7Operator - Principle11990 | Corbiere and Sons Contracting18220191010-7Operator - Principle11990Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 182 | 20191010-7 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-10 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material-A003 - A010 |  |  | A003 - A010 | 0 |  |  | 34 | 43794 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting18220191010-7L.O.A.1210 | Corbiere and Sons Contracting18220191010-7L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 184 | 20191011-02-R02 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 |  |  |  | 891 | 115.83 | 1006.83 | 2019-10-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Error tag due to no Standby rate for Loader for 9hrs. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Project Supervision for start up activities. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18420191011-02-R02Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting18420191011-02-R02Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 184 | 20191011-02-R02 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-10-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Error tag due to no Standby rate for Loader for 9hrs. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Project Supervision for start up activities. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18420191011-02-R02Operator - Principle121080 | Corbiere and Sons Contracting18420191011-02-R02Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 184 | 20191011-02-R02 | 53520105 | Clearing | 0 | Labourer - General | 65 | 4 | HR |  |  |  | 0 | 260 | 33.8 | 293.8 | 2019-10-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Error tag due to no Standby rate for Loader for 9hrs. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Project Supervision for start up activities. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18420191011-02-R02Labourer - General4260 | Corbiere and Sons Contracting18420191011-02-R02Labourer - General4260Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 184 | 20191011-02-R02 | 53520105 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Error tag due to no Standby rate for Loader for 9hrs. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Project Supervision for start up activities. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18420191011-02-R02L.O.A.1210 | Corbiere and Sons Contracting18420191011-02-R02L.O.A.1210Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 185 | 20191011-03-R03 | 53520101 | Clearing | 0 | Feller Buncher | 240 |  | HR | 180 | 18 |  |  | 3240 | 421.2 | 3661.2 | 2019-10-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Rain Out and 3 people for Orientation | 1 |  |  | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18520191011-03-R03Feller Buncher3240 | Corbiere and Sons Contracting18520191011-03-R03Feller Buncher3240Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 185 | 20191011-03-R03 | 53520101 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 |  | HR | 417.6 | 9 |  |  | 3758.4 | 488.592 | 4246.992 | 2019-10-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Rain Out and 3 people for Orientation | 1 |  |  | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18520191011-03-R03Grinder - 4710 Peterson or equal3758.4 | Corbiere and Sons Contracting18520191011-03-R03Grinder - 4710 Peterson or equal3758.4Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3758.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 185 | 20191011-03-R03 | 53520101 | Clearing | 0 | Log Loader | 153 |  | HR | 114.75 | 9 |  |  | 1032.75 | 134.2575 | 1167.0075 | 2019-10-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Rain Out and 3 people for Orientation | 1 |  |  | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18520191011-03-R03Log Loader1032.75 | Corbiere and Sons Contracting18520191011-03-R03Log Loader1032.75Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1032.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 185 | 20191011-03-R03 | 53520101 | Clearing | 0 | Mulcher | 205 |  | HR | 153.75 | 9 |  |  | 1383.75 | 179.8875 | 1563.6375 | 2019-10-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Rain Out and 3 people for Orientation | 1 |  |  | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18520191011-03-R03Mulcher1383.75 | Corbiere and Sons Contracting18520191011-03-R03Mulcher1383.75Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1383.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 185 | 20191011-03-R03 | 53520101 | Clearing | 0 | Skidder | 171 |  | HR | 128.25 | 9 |  |  | 1154.25 | 150.0525 | 1304.3025 | 2019-10-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Rain Out and 3 people for Orientation | 1 |  |  | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18520191011-03-R03Skidder 1154.25 | Corbiere and Sons Contracting18520191011-03-R03Skidder 1154.25Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1154.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 185 | 20191011-03-R03 | 53520101 | Clearing | 0 | Dozer D6 or equal | 135 |  | HR | 101.25 | 9 |  |  | 911.25 | 118.4625 | 1029.7125 | 2019-10-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Rain Out and 3 people for Orientation | 1 |  |  | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18520191011-03-R03Dozer D6 or equal911.25 | Corbiere and Sons Contracting18520191011-03-R03Dozer D6 or equal911.25Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 911.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 185 | 20191011-03-R03 | 53520101 | Clearing | 0 | Excavator - 30 ton | 139.5 |  | HR | 104.63 | 18 |  |  | 1883.34 | 244.8342 | 2128.1742 | 2019-10-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Rain Out and 3 people for Orientation | 1 |  |  | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18520191011-03-R03Excavator - 30 ton1883.34 | Corbiere and Sons Contracting18520191011-03-R03Excavator - 30 ton1883.34Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1883.34 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 185 | 20191011-03-R03 | 53520101 | Clearing | 0 | Excavator - 36 ton | 171 |  | HR | 128.25 | 18 |  |  | 2308.5 | 300.105 | 2608.605 | 2019-10-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Rain Out and 3 people for Orientation | 1 |  |  | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18520191011-03-R03Excavator - 36 ton2308.5 | Corbiere and Sons Contracting18520191011-03-R03Excavator - 36 ton2308.5Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2308.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 185 | 20191011-03-R03 | 53520101 | Clearing | 0 | ATV - Side by Side w/ roll bar | 22.5 |  | HR | 16.88 | 9 |  |  | 151.92 | 19.7496 | 171.6696 | 2019-10-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Rain Out and 3 people for Orientation | 1 |  |  | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18520191011-03-R03ATV - Side by Side w/ roll bar151.92 | Corbiere and Sons Contracting18520191011-03-R03ATV - Side by Side w/ roll bar151.92Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 151.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 185 | 20191011-03-R03 | 53520101 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 |  | HR | 101.25 | 10 |  |  | 1012.5 | 131.625 | 1144.125 | 2019-10-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Rain Out and 3 people for Orientation | 1 |  |  | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18520191011-03-R03Tractor Trailer - 60 Ton1012.5 | Corbiere and Sons Contracting18520191011-03-R03Tractor Trailer - 60 Ton1012.5Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1012.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 185 | 20191011-03-R03 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 55 | HR |  |  |  | 0 | 4950 | 643.5 | 5593.5 | 2019-10-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Rain Out and 3 people for Orientation | 1 |  |  | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18520191011-03-R03Operator - Principle554950 | Corbiere and Sons Contracting18520191011-03-R03Operator - Principle554950Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 185 | 20191011-03-R03 | 53520101 | Clearing | 0 | Operator - Intermdiate | 75 | 8 | HR |  |  |  | 0 | 600 | 78 | 678 | 2019-10-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Rain Out and 3 people for Orientation | 1 |  |  | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18520191011-03-R03Operator - Intermdiate8600 | Corbiere and Sons Contracting18520191011-03-R03Operator - Intermdiate8600Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 185 | 20191011-03-R03 | 53520101 | Clearing | 0 | Labourer - Specialized | 75 | 4 | HR |  |  |  | 0 | 300 | 39 | 339 | 2019-10-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Rain Out and 3 people for Orientation | 1 |  |  | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18520191011-03-R03Labourer - Specialized4300 | Corbiere and Sons Contracting18520191011-03-R03Labourer - Specialized4300Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 185 | 20191011-03-R03 | 53520101 | Clearing | 0 | Labourer - General | 65 | 4 | HR |  |  |  | 0 | 260 | 33.8 | 293.8 | 2019-10-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Rain Out and 3 people for Orientation | 1 |  |  | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18520191011-03-R03Labourer - General4260 | Corbiere and Sons Contracting18520191011-03-R03Labourer - General4260Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 185 | 20191011-03-R03 | 53520101 | Clearing | 0 | L.O.A. | 210 | 13 | DAY |  |  |  | 0 | 2730 | 354.9 | 3084.9 | 2019-10-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Rain Out and 3 people for Orientation | 1 |  |  | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18520191011-03-R03L.O.A.132730 | Corbiere and Sons Contracting18520191011-03-R03L.O.A.132730Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2730 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 186 | 20191011-04-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 1.5 | HR | 180 | 8 |  |  | 1800 | 234 | 2034 | 2019-10-11 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to no rates in DB for Standby for Feller buncher and Skidder. RR- Corrected Nov 16, 19 |  | Approved |  |  | Clearing Tower Site #23 This was a rain day. Equipment worked 1.5 hours and was then shutdown per instruction by Valard. Operators and Supervisor paid at 4hours, Equipment at standby after shutdown. |  |  |  | 0 |  |  | 40 | 43988 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting18620191011-04-R01Feller Buncher1.51800 | Corbiere and Sons Contracting18620191011-04-R01Feller Buncher1.51800INV#30-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 186 | 20191011-04-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 1.5 | HR | 128.25 | 8 |  |  | 1282.5 | 166.725 | 1449.225 | 2019-10-11 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to no rates in DB for Standby for Feller buncher and Skidder. RR- Corrected Nov 16, 19 |  | Approved |  |  | Clearing Tower Site #23 This was a rain day. Equipment worked 1.5 hours and was then shutdown per instruction by Valard. Operators and Supervisor paid at 4hours, Equipment at standby after shutdown. |  |  |  | 0 |  |  | 40 | 43988 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting18620191011-04-R01Skidder 1.51282.5 | Corbiere and Sons Contracting18620191011-04-R01Skidder 1.51282.5INV#30-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1282.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 186 | 20191011-04-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 |  | HR | 22.5 | 30 |  |  | 675 | 87.75 | 762.75 | 2019-10-11 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to no rates in DB for Standby for Feller buncher and Skidder. RR- Corrected Nov 16, 19 |  | Approved |  |  | Clearing Tower Site #23 This was a rain day. Equipment worked 1.5 hours and was then shutdown per instruction by Valard. Operators and Supervisor paid at 4hours, Equipment at standby after shutdown. |  |  |  | 0 |  |  | 40 | 43988 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting18620191011-04-R01Light Truck - Pick up675 | Corbiere and Sons Contracting18620191011-04-R01Light Truck - Pick up675INV#30-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 186 | 20191011-04-R01 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-10-11 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to no rates in DB for Standby for Feller buncher and Skidder. RR- Corrected Nov 16, 19 |  | Approved |  |  | Clearing Tower Site #23 This was a rain day. Equipment worked 1.5 hours and was then shutdown per instruction by Valard. Operators and Supervisor paid at 4hours, Equipment at standby after shutdown. |  |  |  | 0 |  |  | 40 | 43988 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting18620191011-04-R01Foreman4380 | Corbiere and Sons Contracting18620191011-04-R01Foreman4380INV#30-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 186 | 20191011-04-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 8 | HR |  |  |  | 0 | 720 | 93.6 | 813.6 | 2019-10-11 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to no rates in DB for Standby for Feller buncher and Skidder. RR- Corrected Nov 16, 19 |  | Approved |  |  | Clearing Tower Site #23 This was a rain day. Equipment worked 1.5 hours and was then shutdown per instruction by Valard. Operators and Supervisor paid at 4hours, Equipment at standby after shutdown. |  |  |  | 0 |  |  | 40 | 43988 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting18620191011-04-R01Operator - Principle8720 | Corbiere and Sons Contracting18620191011-04-R01Operator - Principle8720INV#30-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 186 | 20191011-04-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-11 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to no rates in DB for Standby for Feller buncher and Skidder. RR- Corrected Nov 16, 19 |  | Approved |  |  | Clearing Tower Site #23 This was a rain day. Equipment worked 1.5 hours and was then shutdown per instruction by Valard. Operators and Supervisor paid at 4hours, Equipment at standby after shutdown. |  |  |  | 0 |  |  | 40 | 43988 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting18620191011-04-R01L.O.A.3630 | Corbiere and Sons Contracting18620191011-04-R01L.O.A.3630INV#30-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 183 | 20191011-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR |  |  |  |  | 1800 | 234 | 2034 | 2019-10-11 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting18320191011-1Light Truck - Pick up601800 | Corbiere and Sons Contracting18320191011-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 183 | 20191011-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-11 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting18320191011-1Project Manager121320 | Corbiere and Sons Contracting18320191011-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 183 | 20191011-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-11 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting18320191011-1Superintendent121260 | Corbiere and Sons Contracting18320191011-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 183 | 20191011-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-11 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting18320191011-1Project Coordinator12960 | Corbiere and Sons Contracting18320191011-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 183 | 20191011-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-10-11 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting18320191011-1Construction Coordinator11880 | Corbiere and Sons Contracting18320191011-1Construction Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 183 | 20191011-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-11 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting18320191011-1Safety Advisor121020 | Corbiere and Sons Contracting18320191011-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 183 | 20191011-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-10-11 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting18320191011-1Project Controls10700 | Corbiere and Sons Contracting18320191011-1Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 183 | 20191011-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-11 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision for start up activities. |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting18320191011-1L.O.A.61260 | Corbiere and Sons Contracting18320191011-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 190 | 20191012-04-R03 | 53520101 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 |  | HR | 417.6 | 9 |  |  | 3758.4 | 488.592 | 4246.992 | 2019-10-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Weather Delay | 1 | Highway 17 to A-017 | MacGregor | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19020191012-04-R03Grinder - 4710 Peterson or equal3758.4 | Corbiere and Sons Contracting19020191012-04-R03Grinder - 4710 Peterson or equal3758.4Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3758.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 190 | 20191012-04-R03 | 53520101 | Clearing | 0 | Log Loader | 153 |  | HR | 114.75 | 9 |  |  | 1032.75 | 134.2575 | 1167.0075 | 2019-10-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Weather Delay | 1 | Highway 17 to A-017 | MacGregor | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19020191012-04-R03Log Loader1032.75 | Corbiere and Sons Contracting19020191012-04-R03Log Loader1032.75Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1032.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 190 | 20191012-04-R03 | 53520101 | Clearing | 0 | Mulcher | 205 |  | HR | 153.75 | 9 |  |  | 1383.75 | 179.8875 | 1563.6375 | 2019-10-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Weather Delay | 1 | Highway 17 to A-017 | MacGregor | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19020191012-04-R03Mulcher1383.75 | Corbiere and Sons Contracting19020191012-04-R03Mulcher1383.75Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1383.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 190 | 20191012-04-R03 | 53520101 | Clearing | 0 | Skidder | 171 |  | HR | 128.25 | 9 |  |  | 1154.25 | 150.0525 | 1304.3025 | 2019-10-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Weather Delay | 1 | Highway 17 to A-017 | MacGregor | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19020191012-04-R03Skidder 1154.25 | Corbiere and Sons Contracting19020191012-04-R03Skidder 1154.25Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1154.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 190 | 20191012-04-R03 | 53520101 | Clearing | 0 | Dozer D6 or equal | 135 |  | HR | 101.25 | 9 |  |  | 911.25 | 118.4625 | 1029.7125 | 2019-10-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Weather Delay | 1 | Highway 17 to A-017 | MacGregor | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19020191012-04-R03Dozer D6 or equal911.25 | Corbiere and Sons Contracting19020191012-04-R03Dozer D6 or equal911.25Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 911.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 190 | 20191012-04-R03 | 53520101 | Clearing | 0 | Excavator - 30 ton | 139.5 |  | HR | 104.63 | 18 |  |  | 1883.34 | 244.8342 | 2128.1742 | 2019-10-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Weather Delay | 1 | Highway 17 to A-017 | MacGregor | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19020191012-04-R03Excavator - 30 ton1883.34 | Corbiere and Sons Contracting19020191012-04-R03Excavator - 30 ton1883.34Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1883.34 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 190 | 20191012-04-R03 | 53520101 | Clearing | 0 | Excavator - 36 ton | 171 |  | HR | 128.25 | 18 |  |  | 2308.5 | 300.105 | 2608.605 | 2019-10-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Weather Delay | 1 | Highway 17 to A-017 | MacGregor | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19020191012-04-R03Excavator - 36 ton2308.5 | Corbiere and Sons Contracting19020191012-04-R03Excavator - 36 ton2308.5Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2308.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 190 | 20191012-04-R03 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 36 | HR |  |  |  | 0 | 3240 | 421.2 | 3661.2 | 2019-10-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Weather Delay | 1 | Highway 17 to A-017 | MacGregor | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19020191012-04-R03Operator - Principle363240 | Corbiere and Sons Contracting19020191012-04-R03Operator - Principle363240Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 190 | 20191012-04-R03 | 53520101 | Clearing | 0 | Labourer - Specialized | 75 | 4 | HR |  |  |  | 0 | 300 | 39 | 339 | 2019-10-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Weather Delay | 1 | Highway 17 to A-017 | MacGregor | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19020191012-04-R03Labourer - Specialized4300 | Corbiere and Sons Contracting19020191012-04-R03Labourer - Specialized4300Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 190 | 20191012-04-R03 | 53520101 | Clearing | 0 | Labourer - General | 65 | 8 | HR |  |  |  | 0 | 520 | 67.6 | 587.6 | 2019-10-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Weather Delay | 1 | Highway 17 to A-017 | MacGregor | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19020191012-04-R03Labourer - General8520 | Corbiere and Sons Contracting19020191012-04-R03Labourer - General8520Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 520 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 190 | 20191012-04-R03 | 53520101 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-10-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Weather Delay | 1 | Highway 17 to A-017 | MacGregor | 1 | 43858 |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19020191012-04-R03L.O.A.71470 | Corbiere and Sons Contracting19020191012-04-R03L.O.A.71470Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 187 | 20191012-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR |  |  |  |  | 1800 | 234 | 2034 | 2019-10-12 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting18720191012-1Light Truck - Pick up601800 | Corbiere and Sons Contracting18720191012-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 187 | 20191012-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-12 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting18720191012-1Project Manager121320 | Corbiere and Sons Contracting18720191012-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 187 | 20191012-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-12 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting18720191012-1Superintendent121260 | Corbiere and Sons Contracting18720191012-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 187 | 20191012-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-10-12 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting18720191012-1Project Coordinator11880 | Corbiere and Sons Contracting18720191012-1Project Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 187 | 20191012-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-10-12 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting18720191012-1Construction Coordinator11880 | Corbiere and Sons Contracting18720191012-1Construction Coordinator11880Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 187 | 20191012-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-12 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting18720191012-1Safety Advisor121020 | Corbiere and Sons Contracting18720191012-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 187 | 20191012-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-10-12 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting18720191012-1Project Controls10700 | Corbiere and Sons Contracting18720191012-1Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 187 | 20191012-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-12 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting18720191012-1L.O.A.61260 | Corbiere and Sons Contracting18720191012-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 188 | 20191012-2-R02 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR |  |  |  |  | 891 | 115.83 | 1006.83 | 2019-10-12 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to no Standby rate for Loader JD 524 to 624. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18820191012-2-R02Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting18820191012-2-R02Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 188 | 20191012-2-R02 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR |  |  |  |  | 1350 | 175.5 | 1525.5 | 2019-10-12 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to no Standby rate for Loader JD 524 to 624. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18820191012-2-R02Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting18820191012-2-R02Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 188 | 20191012-2-R02 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-10-12 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to no Standby rate for Loader JD 524 to 624. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18820191012-2-R02Operator - Principle121080 | Corbiere and Sons Contracting18820191012-2-R02Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 188 | 20191012-2-R02 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-10-12 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to no Standby rate for Loader JD 524 to 624. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18820191012-2-R02Operator - Intermdiate11825 | Corbiere and Sons Contracting18820191012-2-R02Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 188 | 20191012-2-R02 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-12 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to no Standby rate for Loader JD 524 to 624. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18820191012-2-R02Labourer - General10650 | Corbiere and Sons Contracting18820191012-2-R02Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 188 | 20191012-2-R02 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-12 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to no Standby rate for Loader JD 524 to 624. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard maintenance and equipment repair. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting18820191012-2-R02L.O.A.2420 | Corbiere and Sons Contracting18820191012-2-R02L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 189 | 20191012-3-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 18 | HR |  |  |  |  | 4320 | 561.6 | 4881.6 | 2019-10-12 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing East of tower 8 and west of tower 11 - Pat Steinberg performed repairs to Mulcher in field. Charlie Sylvester walked 3 separate machines to laydown after float moves. |  |  | A008-A011 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting18920191012-3-R01Feller Buncher184320 | Corbiere and Sons Contracting18920191012-3-R01Feller Buncher184320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 189 | 20191012-3-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR |  |  |  |  | 1539 | 200.07 | 1739.07 | 2019-10-12 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing East of tower 8 and west of tower 11 - Pat Steinberg performed repairs to Mulcher in field. Charlie Sylvester walked 3 separate machines to laydown after float moves. |  |  | A008-A011 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting18920191012-3-R01Skidder 91539 | Corbiere and Sons Contracting18920191012-3-R01Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 189 | 20191012-3-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR |  |  |  |  | 600 | 78 | 678 | 2019-10-12 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing East of tower 8 and west of tower 11 - Pat Steinberg performed repairs to Mulcher in field. Charlie Sylvester walked 3 separate machines to laydown after float moves. |  |  | A008-A011 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting18920191012-3-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting18920191012-3-R01Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 189 | 20191012-3-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 50 | HR |  |  |  | 0 | 4500 | 585 | 5085 | 2019-10-12 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing East of tower 8 and west of tower 11 - Pat Steinberg performed repairs to Mulcher in field. Charlie Sylvester walked 3 separate machines to laydown after float moves. |  |  | A008-A011 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting18920191012-3-R01Operator - Principle504500 | Corbiere and Sons Contracting18920191012-3-R01Operator - Principle504500Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 189 | 20191012-3-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-10-12 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing East of tower 8 and west of tower 11 - Pat Steinberg performed repairs to Mulcher in field. Charlie Sylvester walked 3 separate machines to laydown after float moves. |  |  | A008-A011 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting18920191012-3-R01L.O.A.51050 | Corbiere and Sons Contracting18920191012-3-R01L.O.A.51050Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 192 | 20191013-02-R02 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR |  |  |  |  | 891 | 115.83 | 1006.83 | 2019-10-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to equipment rates for Loader and Tractor Trailer being different in DB as on LEM. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Yard and Warehouse Maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19220191013-02-R02Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting19220191013-02-R02Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 192 | 20191013-02-R02 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR |  |  |  |  | 1350 | 175.5 | 1525.5 | 2019-10-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to equipment rates for Loader and Tractor Trailer being different in DB as on LEM. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Yard and Warehouse Maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19220191013-02-R02Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting19220191013-02-R02Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 192 | 20191013-02-R02 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-10-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to equipment rates for Loader and Tractor Trailer being different in DB as on LEM. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Yard and Warehouse Maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19220191013-02-R02Operator - Principle121080 | Corbiere and Sons Contracting19220191013-02-R02Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 192 | 20191013-02-R02 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-10-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to equipment rates for Loader and Tractor Trailer being different in DB as on LEM. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Yard and Warehouse Maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19220191013-02-R02Operator - Intermdiate11825 | Corbiere and Sons Contracting19220191013-02-R02Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 192 | 20191013-02-R02 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to equipment rates for Loader and Tractor Trailer being different in DB as on LEM. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Yard and Warehouse Maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19220191013-02-R02Labourer - General10650 | Corbiere and Sons Contracting19220191013-02-R02Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 192 | 20191013-02-R02 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to equipment rates for Loader and Tractor Trailer being different in DB as on LEM. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Yard and Warehouse Maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19220191013-02-R02L.O.A.2420 | Corbiere and Sons Contracting19220191013-02-R02L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 193 | 20191013-03-R01 | 53520101 | Clearing | 0 | Brusher | 202.5 | 9 | HR |  |  |  |  | 1822.5 | 236.925 | 2059.425 | 2019-10-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR | [8 empty] | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19320191013-03-R01Brusher91822.5 | Corbiere and Sons Contracting19320191013-03-R01Brusher91822.5Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 193 | 20191013-03-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 27 | HR |  |  |  |  | 6480 | 842.4 | 7322.4 | 2019-10-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR | [8 empty] | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19320191013-03-R01Feller Buncher276480 | Corbiere and Sons Contracting19320191013-03-R01Feller Buncher276480Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 6480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 193 | 20191013-03-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR |  |  |  |  | 1539 | 200.07 | 1739.07 | 2019-10-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR | [8 empty] | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19320191013-03-R01Skidder 91539 | Corbiere and Sons Contracting19320191013-03-R01Skidder 91539Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 193 | 20191013-03-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR |  |  |  |  | 600 | 78 | 678 | 2019-10-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR | [8 empty] | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19320191013-03-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting19320191013-03-R01Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 193 | 20191013-03-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 55 | HR |  |  |  | 0 | 4950 | 643.5 | 5593.5 | 2019-10-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR | [8 empty] | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19320191013-03-R01Operator - Principle554950 | Corbiere and Sons Contracting19320191013-03-R01Operator - Principle554950Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 193 | 20191013-03-R01 | 53520101 | Clearing | 0 | Labourer - General | 65 | 8 | HR |  |  |  | 0 | 520 | 67.6 | 587.6 | 2019-10-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR | [8 empty] | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19320191013-03-R01Labourer - General8520 | Corbiere and Sons Contracting19320191013-03-R01Labourer - General8520Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 520 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 193 | 20191013-03-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-10-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR | [8 empty] | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19320191013-03-R01L.O.A.51050 | Corbiere and Sons Contracting19320191013-03-R01L.O.A.51050Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 191 | 20191013-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR |  |  |  |  | 1800 | 234 | 2034 | 2019-10-13 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [10 empty] | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting19120191013-1Light Truck - Pick up601800 | Corbiere and Sons Contracting19120191013-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 191 | 20191013-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-13 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [10 empty] | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting19120191013-1Project Manager121320 | Corbiere and Sons Contracting19120191013-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 191 | 20191013-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-13 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [10 empty] | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting19120191013-1Superintendent121260 | Corbiere and Sons Contracting19120191013-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 191 | 20191013-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 8 | HR |  |  |  | 0 | 640 | 83.2 | 723.2 | 2019-10-13 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [10 empty] | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting19120191013-1Project Coordinator8640 | Corbiere and Sons Contracting19120191013-1Project Coordinator8640Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 191 | 20191013-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-13 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [10 empty] | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting19120191013-1Construction Coordinator12960 | Corbiere and Sons Contracting19120191013-1Construction Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 191 | 20191013-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-13 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [10 empty] | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting19120191013-1Safety Advisor121020 | Corbiere and Sons Contracting19120191013-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 191 | 20191013-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 4 | HR |  |  |  | 0 | 280 | 36.4 | 316.4 | 2019-10-13 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [10 empty] | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting19120191013-1Project Controls4280 | Corbiere and Sons Contracting19120191013-1Project Controls4280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 191 | 20191013-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-13 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [10 empty] | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting19120191013-1L.O.A.61260 | Corbiere and Sons Contracting19120191013-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 199 | 20191014-05 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR |  |  |  |  | 2280 | 296.4 | 2576.4 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing done at A022 |  |  | Segment 4 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting19920191014-05Feller Buncher9.52280 | Corbiere and Sons Contracting19920191014-05Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 199 | 20191014-05 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR |  |  |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing done at A022 |  |  | Segment 4 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting19920191014-05Skidder 9.51624.5 | Corbiere and Sons Contracting19920191014-05Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 199 | 20191014-05 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR |  |  |  |  | 900 | 117 | 1017 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing done at A022 |  |  | Segment 4 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting19920191014-05Light Truck - Pick up30900 | Corbiere and Sons Contracting19920191014-05Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 199 | 20191014-05 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing done at A022 |  |  | Segment 4 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting19920191014-05Foreman4380 | Corbiere and Sons Contracting19920191014-05Foreman4380Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 199 | 20191014-05 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing done at A022 |  |  | Segment 4 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting19920191014-05Operator - Principle221980 | Corbiere and Sons Contracting19920191014-05Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 199 | 20191014-05 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing done at A022 |  |  | Segment 4 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting19920191014-05L.O.A.3630 | Corbiere and Sons Contracting19920191014-05L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 195 | 20191014-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR |  |  |  |  | 1800 | 234 | 2034 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting19520191014-1Light Truck - Pick up601800 | Corbiere and Sons Contracting19520191014-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 195 | 20191014-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting19520191014-1Project Manager121320 | Corbiere and Sons Contracting19520191014-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 195 | 20191014-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting19520191014-1Superintendent121260 | Corbiere and Sons Contracting19520191014-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 195 | 20191014-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 8 | HR |  |  |  | 0 | 640 | 83.2 | 723.2 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting19520191014-1Project Coordinator8640 | Corbiere and Sons Contracting19520191014-1Project Coordinator8640Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 195 | 20191014-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting19520191014-1Construction Coordinator12960 | Corbiere and Sons Contracting19520191014-1Construction Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 195 | 20191014-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting19520191014-1Safety Advisor121020 | Corbiere and Sons Contracting19520191014-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 195 | 20191014-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting19520191014-1Project Controls12840 | Corbiere and Sons Contracting19520191014-1Project Controls12840Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 195 | 20191014-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting19520191014-1L.O.A.61260 | Corbiere and Sons Contracting19520191014-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 196 | 20191014-2-R02 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR |  |  |  |  | 891 | 115.83 | 1006.83 | 2019-10-14 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error checked due to wrong Operator-Intermediate rate, and equipment rate in DB is different than LEM. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Yard and Warehouse Maintenance. Orientation for Glen Stephens. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19620191014-2-R02Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting19620191014-2-R02Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 196 | 20191014-2-R02 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR |  |  |  |  | 1350 | 175.5 | 1525.5 | 2019-10-14 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error checked due to wrong Operator-Intermediate rate, and equipment rate in DB is different than LEM. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Yard and Warehouse Maintenance. Orientation for Glen Stephens. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19620191014-2-R02Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting19620191014-2-R02Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 196 | 20191014-2-R02 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 17 | HR |  |  |  | 0 | 1530 | 198.9 | 1728.9 | 2019-10-14 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error checked due to wrong Operator-Intermediate rate, and equipment rate in DB is different than LEM. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Yard and Warehouse Maintenance. Orientation for Glen Stephens. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19620191014-2-R02Operator - Principle171530 | Corbiere and Sons Contracting19620191014-2-R02Operator - Principle171530Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1530 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 196 | 20191014-2-R02 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-10-14 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error checked due to wrong Operator-Intermediate rate, and equipment rate in DB is different than LEM. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Yard and Warehouse Maintenance. Orientation for Glen Stephens. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19620191014-2-R02Operator - Intermdiate11825 | Corbiere and Sons Contracting19620191014-2-R02Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 196 | 20191014-2-R02 | 53520105 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-14 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error checked due to wrong Operator-Intermediate rate, and equipment rate in DB is different than LEM. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Yard and Warehouse Maintenance. Orientation for Glen Stephens. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting19620191014-2-R02L.O.A.3630 | Corbiere and Sons Contracting19620191014-2-R02L.O.A.3630Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 197 | 20191014-3 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 16 | HR |  |  |  |  | 3840 | 499.2 | 4339.2 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing done from A010 East |  |  | A010 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting19720191014-3Feller Buncher163840 | Corbiere and Sons Contracting19720191014-3Feller Buncher163840Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 197 | 20191014-3 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR |  |  |  |  | 1539 | 200.07 | 1739.07 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing done from A010 East |  |  | A010 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting19720191014-3Skidder 91539 | Corbiere and Sons Contracting19720191014-3Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 197 | 20191014-3 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR |  |  |  |  | 300 | 39 | 339 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing done from A010 East |  |  | A010 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting19720191014-3Light Truck - Pick up10300 | Corbiere and Sons Contracting19720191014-3Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 197 | 20191014-3 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing done from A010 East |  |  | A010 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting19720191014-3Operator - Principle332970 | Corbiere and Sons Contracting19720191014-3Operator - Principle332970Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 197 | 20191014-3 | 53520101 | Clearing | 0 | Labourer - General | 65 | 4 | HR |  |  |  | 0 | 260 | 33.8 | 293.8 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing done from A010 East |  |  | A010 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting19720191014-3Labourer - General4260 | Corbiere and Sons Contracting19720191014-3Labourer - General4260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 197 | 20191014-3 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing done from A010 East |  |  | A010 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting19720191014-3L.O.A.3630 | Corbiere and Sons Contracting19720191014-3L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 198 | 20191014-4-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR |  |  |  |  | 2160 | 280.8 | 2440.8 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing done at 31 East |  |  | Segment 4 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting19820191014-4-R01Feller Buncher92160 | Corbiere and Sons Contracting19820191014-4-R01Feller Buncher92160Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 198 | 20191014-4-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing done at 31 East |  |  | Segment 4 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting19820191014-4-R01Operator - Principle11990 | Corbiere and Sons Contracting19820191014-4-R01Operator - Principle11990Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 202 | 20191014-8 | 53510112 | Access | 0 | Dozer D6 or equal | 135 | 9.5 | HR |  |  |  |  | 1282.5 | 166.725 | 1449.225 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Maintenance of McGregor access road including shoefly. |  |  |  | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting20220191014-8Dozer D6 or equal9.51282.5 | Corbiere and Sons Contracting20220191014-8Dozer D6 or equal9.51282.5Inv#002-R01 | [5 empty] | 1 | 1282.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 202 | 20191014-8 | 53510112 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Maintenance of McGregor access road including shoefly. |  |  |  | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting20220191014-8Operator - Principle11990 | Corbiere and Sons Contracting20220191014-8Operator - Principle11990Inv#002-R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 202 | 20191014-8 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-14 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Maintenance of McGregor access road including shoefly. |  |  |  | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting20220191014-8L.O.A.1210 | Corbiere and Sons Contracting20220191014-8L.O.A.1210Inv#002-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 204 | 20191015-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR |  |  |  |  | 1800 | 234 | 2034 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting20420191015-1Light Truck - Pick up601800 | Corbiere and Sons Contracting20420191015-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 204 | 20191015-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting20420191015-1Project Manager121320 | Corbiere and Sons Contracting20420191015-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 204 | 20191015-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting20420191015-1Superintendent121260 | Corbiere and Sons Contracting20420191015-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 204 | 20191015-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting20420191015-1Project Coordinator12960 | Corbiere and Sons Contracting20420191015-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 204 | 20191015-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting20420191015-1Construction Coordinator12960 | Corbiere and Sons Contracting20420191015-1Construction Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 204 | 20191015-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting20420191015-1Safety Advisor121020 | Corbiere and Sons Contracting20420191015-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 204 | 20191015-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting20420191015-1Project Controls10700 | Corbiere and Sons Contracting20420191015-1Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 204 | 20191015-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting20420191015-1L.O.A.61260 | Corbiere and Sons Contracting20420191015-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3003 | 20191015-10-R02 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-10-15 | 1 | INV#30-R02 | 43993 | 92 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 31 | Approved | Indirects/other | 9030 | Orientation | 0 |  |  | 1 |  |  | 40 | 43999 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting300320191015-10-R02Light Truck - Pick up20600 | Corbiere and Sons Contracting300320191015-10-R02Light Truck - Pick up20600INV#30-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3003 | 20191015-10-R02 | 53520102 | Clearing | 0 | Foreman | 95 | 9 | HR |  |  | 95 | 0 | 855 | 111.15 | 966.15 | 2019-10-15 | 1 | INV#30-R02 | 43993 | 92 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 31 | Approved | Indirects/other | 9030 | Orientation | 0 |  |  | 1 |  |  | 40 | 43999 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting300320191015-10-R02Foreman9855 | Corbiere and Sons Contracting300320191015-10-R02Foreman9855INV#30-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 855 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3003 | 20191015-10-R02 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 18 | HR |  |  |  | 0 | 1620 | 210.6 | 1830.6 | 2019-10-15 | 1 | INV#30-R02 | 43993 | 92 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 31 | Approved | Indirects/other | 9030 | Orientation | 0 |  |  | 1 |  |  | 40 | 43999 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting300320191015-10-R02Operator - Principle181620 | Corbiere and Sons Contracting300320191015-10-R02Operator - Principle181620INV#30-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1620 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3003 | 20191015-10-R02 | 53520102 | Clearing | 0 | Labourer - General | 65 | 27 | HR |  |  |  | 0 | 1755 | 228.15 | 1983.15 | 2019-10-15 | 1 | INV#30-R02 | 43993 | 92 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 31 | Approved | Indirects/other | 9030 | Orientation | 0 |  |  | 1 |  |  | 40 | 43999 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting300320191015-10-R02Labourer - General271755 | Corbiere and Sons Contracting300320191015-10-R02Labourer - General271755INV#30-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1755 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3003 | 20191015-10-R02 | 53520102 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-15 | 1 | INV#30-R02 | 43993 | 92 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 31 | Approved | Indirects/other | 9030 | Orientation | 0 |  |  | 1 |  |  | 40 | 43999 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting300320191015-10-R02L.O.A.61260 | Corbiere and Sons Contracting300320191015-10-R02L.O.A.61260INV#30-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 205 | 20191015-2-R02 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR |  |  |  |  | 891 | 115.83 | 1006.83 | 2019-10-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tagged due to discrepancy with rates for equipment in DB as to LEM. REQUIRES ADDITIONAL REVISION - Total amount on ticket does not add up RR- Corrected Nov 16, 10 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. Float Driver moved multiple pieces of equipment for McKay (Sub) as well as Corbiere. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting20520191015-2-R02Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting20520191015-2-R02Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 205 | 20191015-2-R02 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 13 | HR |  |  |  |  | 1755 | 228.15 | 1983.15 | 2019-10-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tagged due to discrepancy with rates for equipment in DB as to LEM. REQUIRES ADDITIONAL REVISION - Total amount on ticket does not add up RR- Corrected Nov 16, 10 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. Float Driver moved multiple pieces of equipment for McKay (Sub) as well as Corbiere. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting20520191015-2-R02Tractor Trailer - 60 Ton131755 | Corbiere and Sons Contracting20520191015-2-R02Tractor Trailer - 60 Ton131755Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1755 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 205 | 20191015-2-R02 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-10-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tagged due to discrepancy with rates for equipment in DB as to LEM. REQUIRES ADDITIONAL REVISION - Total amount on ticket does not add up RR- Corrected Nov 16, 10 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. Float Driver moved multiple pieces of equipment for McKay (Sub) as well as Corbiere. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting20520191015-2-R02Operator - Principle121080 | Corbiere and Sons Contracting20520191015-2-R02Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 205 | 20191015-2-R02 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 14 | HR |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-10-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tagged due to discrepancy with rates for equipment in DB as to LEM. REQUIRES ADDITIONAL REVISION - Total amount on ticket does not add up RR- Corrected Nov 16, 10 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. Float Driver moved multiple pieces of equipment for McKay (Sub) as well as Corbiere. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting20520191015-2-R02Operator - Intermdiate141050 | Corbiere and Sons Contracting20520191015-2-R02Operator - Intermdiate141050Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 205 | 20191015-2-R02 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 12 | HR |  |  |  | 0 | 900 | 117 | 1017 | 2019-10-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tagged due to discrepancy with rates for equipment in DB as to LEM. REQUIRES ADDITIONAL REVISION - Total amount on ticket does not add up RR- Corrected Nov 16, 10 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. Float Driver moved multiple pieces of equipment for McKay (Sub) as well as Corbiere. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting20520191015-2-R02Labourer - Specialized12900 | Corbiere and Sons Contracting20520191015-2-R02Labourer - Specialized12900Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 205 | 20191015-2-R02 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tagged due to discrepancy with rates for equipment in DB as to LEM. REQUIRES ADDITIONAL REVISION - Total amount on ticket does not add up RR- Corrected Nov 16, 10 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. Float Driver moved multiple pieces of equipment for McKay (Sub) as well as Corbiere. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting20520191015-2-R02Labourer - General10650 | Corbiere and Sons Contracting20520191015-2-R02Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 205 | 20191015-2-R02 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tagged due to discrepancy with rates for equipment in DB as to LEM. REQUIRES ADDITIONAL REVISION - Total amount on ticket does not add up RR- Corrected Nov 16, 10 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. Float Driver moved multiple pieces of equipment for McKay (Sub) as well as Corbiere. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting20520191015-2-R02L.O.A.2420 | Corbiere and Sons Contracting20520191015-2-R02L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 206 | 20191015-3-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 14 | HR |  |  |  |  | 3360 | 436.8 | 3796.8 | 2019-10-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Tree Clearing and Skidding |  |  | Clearing from A010 both eastward and westward | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting20620191015-3-R01Feller Buncher143360 | Corbiere and Sons Contracting20620191015-3-R01Feller Buncher143360Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 206 | 20191015-3-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR |  |  |  |  | 300 | 39 | 339 | 2019-10-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Tree Clearing and Skidding |  |  | Clearing from A010 both eastward and westward | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting20620191015-3-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting20620191015-3-R01Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 206 | 20191015-3-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 17 | HR |  |  |  | 0 | 1530 | 198.9 | 1728.9 | 2019-10-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Tree Clearing and Skidding |  |  | Clearing from A010 both eastward and westward | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting20620191015-3-R01Operator - Principle171530 | Corbiere and Sons Contracting20620191015-3-R01Operator - Principle171530Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1530 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 206 | 20191015-3-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Tree Clearing and Skidding |  |  | Clearing from A010 both eastward and westward | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting20620191015-3-R01L.O.A.2420 | Corbiere and Sons Contracting20620191015-3-R01L.O.A.2420Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 207 | 20191015-4 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 14.5 | HR |  |  |  |  | 3480 | 452.4 | 3932.4 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing - One Operator on SB for equipment delivery from Supplier. |  |  | Clearing from A031 eastward | 0 |  |  | 34 | 43794 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting20720191015-4Feller Buncher14.53480 | Corbiere and Sons Contracting20720191015-4Feller Buncher14.53480Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 207 | 20191015-4 | 53520101 | Clearing | 0 | Mulcher | 205 | 4.5 | HR | 153.75 | 0 |  |  | 922.5 | 119.925 | 1042.425 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing - One Operator on SB for equipment delivery from Supplier. |  |  | Clearing from A031 eastward | 0 |  |  | 34 | 43794 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting20720191015-4Mulcher4.5922.5 | Corbiere and Sons Contracting20720191015-4Mulcher4.5922.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 922.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 207 | 20191015-4 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR | 128.25 | 0 |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing - One Operator on SB for equipment delivery from Supplier. |  |  | Clearing from A031 eastward | 0 |  |  | 34 | 43794 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting20720191015-4Skidder 9.51624.5 | Corbiere and Sons Contracting20720191015-4Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 207 | 20191015-4 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR |  |  |  |  | 300 | 39 | 339 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing - One Operator on SB for equipment delivery from Supplier. |  |  | Clearing from A031 eastward | 0 |  |  | 34 | 43794 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting20720191015-4Light Truck - Pick up10300 | Corbiere and Sons Contracting20720191015-4Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 207 | 20191015-4 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing - One Operator on SB for equipment delivery from Supplier. |  |  | Clearing from A031 eastward | 0 |  |  | 34 | 43794 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting20720191015-4Operator - Principle332970 | Corbiere and Sons Contracting20720191015-4Operator - Principle332970Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 207 | 20191015-4 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing - One Operator on SB for equipment delivery from Supplier. |  |  | Clearing from A031 eastward | 0 |  |  | 34 | 43794 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting20720191015-4L.O.A.2420 | Corbiere and Sons Contracting20720191015-4L.O.A.2420Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 208 | 20191015-5 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR |  |  |  |  | 2280 | 296.4 | 2576.4 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing Tower A021 |  |  | A021 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting20820191015-5Feller Buncher9.52280 | Corbiere and Sons Contracting20820191015-5Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 208 | 20191015-5 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR |  |  |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing Tower A021 |  |  | A021 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting20820191015-5Skidder 9.51624.5 | Corbiere and Sons Contracting20820191015-5Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 208 | 20191015-5 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR |  |  |  |  | 900 | 117 | 1017 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing Tower A021 |  |  | A021 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting20820191015-5Light Truck - Pick up30900 | Corbiere and Sons Contracting20820191015-5Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 208 | 20191015-5 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing Tower A021 |  |  | A021 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting20820191015-5Foreman4380 | Corbiere and Sons Contracting20820191015-5Foreman4380Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 208 | 20191015-5 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing Tower A021 |  |  | A021 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting20820191015-5Operator - Principle221980 | Corbiere and Sons Contracting20820191015-5Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 208 | 20191015-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing Tower A021 |  |  | A021 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting20820191015-5L.O.A.3630 | Corbiere and Sons Contracting20820191015-5L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 209 | 20191015-6 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR |  |  |  |  | 5011.2 | 651.456 | 5662.656 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tagged due to rates in db being different than the LEM for equipment. Also note that there is 18hrs for equipment and only 11 hrs for labour. I believe that either we are being overcharged or missing an operator. RR- Corrected Nov 16, 19 |  |  |  |  | Grinding material-A028 |  |  | A028 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting20920191015-6Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting20920191015-6Grinder - 4710 Peterson or equal95011.2Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 209 | 20191015-6 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR |  |  |  |  | 1377 | 179.01 | 1556.01 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tagged due to rates in db being different than the LEM for equipment. Also note that there is 18hrs for equipment and only 11 hrs for labour. I believe that either we are being overcharged or missing an operator. RR- Corrected Nov 16, 19 |  |  |  |  | Grinding material-A028 |  |  | A028 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting20920191015-6Log Loader91377 | Corbiere and Sons Contracting20920191015-6Log Loader91377Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 209 | 20191015-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR |  |  |  |  | 300 | 39 | 339 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tagged due to rates in db being different than the LEM for equipment. Also note that there is 18hrs for equipment and only 11 hrs for labour. I believe that either we are being overcharged or missing an operator. RR- Corrected Nov 16, 19 |  |  |  |  | Grinding material-A028 |  |  | A028 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting20920191015-6Light Truck - Pick up10300 | Corbiere and Sons Contracting20920191015-6Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 209 | 20191015-6 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tagged due to rates in db being different than the LEM for equipment. Also note that there is 18hrs for equipment and only 11 hrs for labour. I believe that either we are being overcharged or missing an operator. RR- Corrected Nov 16, 19 |  |  |  |  | Grinding material-A028 |  |  | A028 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting20920191015-6Operator - Principle11990 | Corbiere and Sons Contracting20920191015-6Operator - Principle11990Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 209 | 20191015-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-15 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tagged due to rates in db being different than the LEM for equipment. Also note that there is 18hrs for equipment and only 11 hrs for labour. I believe that either we are being overcharged or missing an operator. RR- Corrected Nov 16, 19 |  |  |  |  | Grinding material-A028 |  |  | A028 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting20920191015-6L.O.A.1210 | Corbiere and Sons Contracting20920191015-6L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 216 | 20191016-04 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR |  |  |  |  | 2280 | 296.4 | 2576.4 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to difference in equipment rate in DB and on LEM. RR- Corrected Nov 16, 19 |  |  |  |  | Clearing at Tower A020 |  |  | A020 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting21620191016-04Feller Buncher9.52280 | Corbiere and Sons Contracting21620191016-04Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 216 | 20191016-04 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR |  |  |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to difference in equipment rate in DB and on LEM. RR- Corrected Nov 16, 19 |  |  |  |  | Clearing at Tower A020 |  |  | A020 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting21620191016-04Skidder 9.51624.5 | Corbiere and Sons Contracting21620191016-04Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 216 | 20191016-04 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR |  |  |  |  | 900 | 117 | 1017 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to difference in equipment rate in DB and on LEM. RR- Corrected Nov 16, 19 |  |  |  |  | Clearing at Tower A020 |  |  | A020 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting21620191016-04Light Truck - Pick up30900 | Corbiere and Sons Contracting21620191016-04Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 216 | 20191016-04 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to difference in equipment rate in DB and on LEM. RR- Corrected Nov 16, 19 |  |  |  |  | Clearing at Tower A020 |  |  | A020 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting21620191016-04Foreman4380 | Corbiere and Sons Contracting21620191016-04Foreman4380Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 216 | 20191016-04 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to difference in equipment rate in DB and on LEM. RR- Corrected Nov 16, 19 |  |  |  |  | Clearing at Tower A020 |  |  | A020 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting21620191016-04Operator - Principle221980 | Corbiere and Sons Contracting21620191016-04Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 216 | 20191016-04 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to difference in equipment rate in DB and on LEM. RR- Corrected Nov 16, 19 |  |  |  |  | Clearing at Tower A020 |  |  | A020 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting21620191016-04L.O.A.3630 | Corbiere and Sons Contracting21620191016-04L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 213 | 20191016-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR |  |  |  |  | 1800 | 234 | 2034 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting21320191016-1Light Truck - Pick up601800 | Corbiere and Sons Contracting21320191016-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 213 | 20191016-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting21320191016-1Project Manager121320 | Corbiere and Sons Contracting21320191016-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 213 | 20191016-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting21320191016-1Superintendent121260 | Corbiere and Sons Contracting21320191016-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 213 | 20191016-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 14 | HR |  |  |  | 0 | 1120 | 145.6 | 1265.6 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting21320191016-1Project Coordinator141120 | Corbiere and Sons Contracting21320191016-1Project Coordinator141120Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 213 | 20191016-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting21320191016-1Construction Coordinator12960 | Corbiere and Sons Contracting21320191016-1Construction Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 213 | 20191016-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting21320191016-1Safety Advisor121020 | Corbiere and Sons Contracting21320191016-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 213 | 20191016-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting21320191016-1Project Controls10700 | Corbiere and Sons Contracting21320191016-1Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 213 | 20191016-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting21320191016-1L.O.A.61260 | Corbiere and Sons Contracting21320191016-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 214 | 20191016-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR |  |  |  |  | 891 | 115.83 | 1006.83 | 2019-10-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to equipment rate in DB being different than the LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. Float Driver moved 2 bunchers, 2 skidders and cinder blocks. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting21420191016-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting21420191016-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 214 | 20191016-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10.5 | HR |  |  |  |  | 1417.5 | 184.275 | 1601.775 | 2019-10-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to equipment rate in DB being different than the LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. Float Driver moved 2 bunchers, 2 skidders and cinder blocks. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting21420191016-2-R01Tractor Trailer - 60 Ton10.51417.5 | Corbiere and Sons Contracting21420191016-2-R01Tractor Trailer - 60 Ton10.51417.5Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1417.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 214 | 20191016-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-10-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to equipment rate in DB being different than the LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. Float Driver moved 2 bunchers, 2 skidders and cinder blocks. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting21420191016-2-R01Operator - Principle121080 | Corbiere and Sons Contracting21420191016-2-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 214 | 20191016-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11.5 | HR |  |  |  | 0 | 862.5 | 112.125 | 974.625 | 2019-10-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to equipment rate in DB being different than the LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. Float Driver moved 2 bunchers, 2 skidders and cinder blocks. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting21420191016-2-R01Operator - Intermdiate11.5862.5 | Corbiere and Sons Contracting21420191016-2-R01Operator - Intermdiate11.5862.5Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 214 | 20191016-2-R01 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-10-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to equipment rate in DB being different than the LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. Float Driver moved 2 bunchers, 2 skidders and cinder blocks. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting21420191016-2-R01Labourer - Specialized11825 | Corbiere and Sons Contracting21420191016-2-R01Labourer - Specialized11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 214 | 20191016-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to equipment rate in DB being different than the LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. Float Driver moved 2 bunchers, 2 skidders and cinder blocks. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting21420191016-2-R01Labourer - General10650 | Corbiere and Sons Contracting21420191016-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 214 | 20191016-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to equipment rate in DB being different than the LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. Float Driver moved 2 bunchers, 2 skidders and cinder blocks. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting21420191016-2-R01L.O.A.3630 | Corbiere and Sons Contracting21420191016-2-R01L.O.A.3630Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 215 | 20191016-3 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 4 | HR |  |  |  |  | 960 | 124.8 | 1084.8 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Tree Clearing and Skidding-A010 |  |  | A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting21520191016-3Feller Buncher4960 | Corbiere and Sons Contracting21520191016-3Feller Buncher4960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 215 | 20191016-3 | 53520101 | Clearing | 0 | Skidder | 171 | 4 | HR |  |  |  |  | 684 | 88.92 | 772.92 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Tree Clearing and Skidding-A010 |  |  | A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting21520191016-3Skidder 4684 | Corbiere and Sons Contracting21520191016-3Skidder 4684Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 684 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 215 | 20191016-3 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR |  |  |  |  | 300 | 39 | 339 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Tree Clearing and Skidding-A010 |  |  | A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting21520191016-3Light Truck - Pick up10300 | Corbiere and Sons Contracting21520191016-3Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 215 | 20191016-3 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 10 | HR |  |  |  | 0 | 900 | 117 | 1017 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Tree Clearing and Skidding-A010 |  |  | A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting21520191016-3Operator - Principle10900 | Corbiere and Sons Contracting21520191016-3Operator - Principle10900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 215 | 20191016-3 | 53520101 | Clearing | 0 | Labourer - Specialized | 75 | 5 | HR |  |  |  | 0 | 375 | 48.75 | 423.75 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Tree Clearing and Skidding-A010 |  |  | A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting21520191016-3Labourer - Specialized5375 | Corbiere and Sons Contracting21520191016-3Labourer - Specialized5375Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 215 | 20191016-3 | 53520101 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Tree Clearing and Skidding-A010 |  |  | A010 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting21520191016-3L.O.A.1210 | Corbiere and Sons Contracting21520191016-3L.O.A.1210Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 217 | 20191016-5-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR |  |  |  |  | 2160 | 280.8 | 2440.8 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing A031 Eastward |  |  | A031 Eastward | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting21720191016-5-R01Feller Buncher92160 | Corbiere and Sons Contracting21720191016-5-R01Feller Buncher92160Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 217 | 20191016-5-R01 | 53520101 | Clearing | 0 | Mulcher | 205 | 9 | HR |  |  |  |  | 1845 | 239.85 | 2084.85 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing A031 Eastward |  |  | A031 Eastward | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting21720191016-5-R01Mulcher91845 | Corbiere and Sons Contracting21720191016-5-R01Mulcher91845Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 217 | 20191016-5-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR |  |  |  |  | 600 | 78 | 678 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing A031 Eastward |  |  | A031 Eastward | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting21720191016-5-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting21720191016-5-R01Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 217 | 20191016-5-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing A031 Eastward |  |  | A031 Eastward | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting21720191016-5-R01Operator - Principle221980 | Corbiere and Sons Contracting21720191016-5-R01Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 217 | 20191016-5-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Clearing A031 Eastward |  |  | A031 Eastward | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting21720191016-5-R01L.O.A.2420 | Corbiere and Sons Contracting21720191016-5-R01L.O.A.2420Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 218 | 20191016-6-R02 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 23.5 | HR |  |  |  |  | 5640 | 733.2 | 6373.2 | 2019-10-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to difference between equipment rate in DB and on LEM. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing, Skidding, labourers flagging among other duties. |  |  | Clearing off of Beck rd. | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting21820191016-6-R02Feller Buncher23.55640 | Corbiere and Sons Contracting21820191016-6-R02Feller Buncher23.55640Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 218 | 20191016-6-R02 | 53520101 | Clearing | 0 | Skidder | 171 | 5.5 | HR |  |  |  |  | 940.5 | 122.265 | 1062.765 | 2019-10-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to difference between equipment rate in DB and on LEM. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing, Skidding, labourers flagging among other duties. |  |  | Clearing off of Beck rd. | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting21820191016-6-R02Skidder 5.5940.5 | Corbiere and Sons Contracting21820191016-6-R02Skidder 5.5940.5Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 940.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 218 | 20191016-6-R02 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR |  |  |  |  | 300 | 39 | 339 | 2019-10-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to difference between equipment rate in DB and on LEM. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing, Skidding, labourers flagging among other duties. |  |  | Clearing off of Beck rd. | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting21820191016-6-R02Light Truck - Pick up10300 | Corbiere and Sons Contracting21820191016-6-R02Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 218 | 20191016-6-R02 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 34 | HR |  |  |  | 0 | 3060 | 397.8 | 3457.8 | 2019-10-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to difference between equipment rate in DB and on LEM. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing, Skidding, labourers flagging among other duties. |  |  | Clearing off of Beck rd. | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting21820191016-6-R02Operator - Principle343060 | Corbiere and Sons Contracting21820191016-6-R02Operator - Principle343060Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3060 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 218 | 20191016-6-R02 | 53520101 | Clearing | 0 | Labourer - Specialized | 75 | 6 | HR |  |  |  | 0 | 450 | 58.5 | 508.5 | 2019-10-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to difference between equipment rate in DB and on LEM. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing, Skidding, labourers flagging among other duties. |  |  | Clearing off of Beck rd. | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting21820191016-6-R02Labourer - Specialized6450 | Corbiere and Sons Contracting21820191016-6-R02Labourer - Specialized6450Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 218 | 20191016-6-R02 | 53520101 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-10-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to difference between equipment rate in DB and on LEM. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing, Skidding, labourers flagging among other duties. |  |  | Clearing off of Beck rd. | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting21820191016-6-R02Labourer - General11715 | Corbiere and Sons Contracting21820191016-6-R02Labourer - General11715Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 218 | 20191016-6-R02 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | error tag due to difference between equipment rate in DB and on LEM. RR- Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing, Skidding, labourers flagging among other duties. |  |  | Clearing off of Beck rd. | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting21820191016-6-R02L.O.A.2420 | Corbiere and Sons Contracting21820191016-6-R02L.O.A.2420Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 219 | 20191016-7 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR |  |  |  |  | 5011.2 | 651.456 | 5662.656 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding material-A028 |  |  | A028 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting21920191016-7Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting21920191016-7Grinder - 4710 Peterson or equal95011.2Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 219 | 20191016-7 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR |  |  |  |  | 1377 | 179.01 | 1556.01 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding material-A028 |  |  | A028 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting21920191016-7Log Loader91377 | Corbiere and Sons Contracting21920191016-7Log Loader91377Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 219 | 20191016-7 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR |  |  |  |  | 300 | 39 | 339 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding material-A028 |  |  | A028 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting21920191016-7Light Truck - Pick up10300 | Corbiere and Sons Contracting21920191016-7Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 219 | 20191016-7 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding material-A028 |  |  | A028 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting21920191016-7Operator - Principle11990 | Corbiere and Sons Contracting21920191016-7Operator - Principle11990Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 219 | 20191016-7 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-16 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | LEM Merge - NM |  |  |  |  | Grinding material-A028 |  |  | A028 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting21920191016-7L.O.A.1210 | Corbiere and Sons Contracting21920191016-7L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 233 | 20191017-03 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR | 180 | 0 |  |  | 2280 | 296.4 | 2576.4 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing Tower A019 |  |  | A019 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting23320191017-03Feller Buncher9.52280 | Corbiere and Sons Contracting23320191017-03Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 233 | 20191017-03 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR | 128.25 | 0 |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing Tower A019 |  |  | A019 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting23320191017-03Skidder 9.51624.5 | Corbiere and Sons Contracting23320191017-03Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 233 | 20191017-03 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing Tower A019 |  |  | A019 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting23320191017-03Light Truck - Pick up30900 | Corbiere and Sons Contracting23320191017-03Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 233 | 20191017-03 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing Tower A019 |  |  | A019 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting23320191017-03Foreman4380 | Corbiere and Sons Contracting23320191017-03Foreman4380Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 233 | 20191017-03 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing Tower A019 |  |  | A019 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting23320191017-03Operator - Principle221980 | Corbiere and Sons Contracting23320191017-03Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 233 | 20191017-03 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing Tower A019 |  |  | A019 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting23320191017-03L.O.A.3630 | Corbiere and Sons Contracting23320191017-03L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 231 | 20191017-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting23120191017-1Light Truck - Pick up601800 | Corbiere and Sons Contracting23120191017-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 231 | 20191017-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting23120191017-1Project Manager121320 | Corbiere and Sons Contracting23120191017-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 231 | 20191017-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting23120191017-1Superintendent121260 | Corbiere and Sons Contracting23120191017-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 231 | 20191017-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 14 | HR |  |  |  | 0 | 1120 | 145.6 | 1265.6 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting23120191017-1Project Coordinator141120 | Corbiere and Sons Contracting23120191017-1Project Coordinator141120Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 231 | 20191017-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting23120191017-1Construction Coordinator12960 | Corbiere and Sons Contracting23120191017-1Construction Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 231 | 20191017-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting23120191017-1Safety Advisor121020 | Corbiere and Sons Contracting23120191017-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 231 | 20191017-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting23120191017-1Project Controls10700 | Corbiere and Sons Contracting23120191017-1Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 231 | 20191017-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting23120191017-1L.O.A.61260 | Corbiere and Sons Contracting23120191017-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 240 | 20191017-10-R01 | 53510112 | Access | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and continuing working towards ROW from Beck road. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24020191017-10-R01Brusher91822.5 | Corbiere and Sons Contracting24020191017-10-R01Brusher91822.5Inv#002-R01 | [5 empty] | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 240 | 20191017-10-R01 | 53510112 | Access | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and continuing working towards ROW from Beck road. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24020191017-10-R01Excavator - 36 ton91539 | Corbiere and Sons Contracting24020191017-10-R01Excavator - 36 ton91539Inv#002-R01 | [5 empty] | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 240 | 20191017-10-R01 | 53510112 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and continuing working towards ROW from Beck road. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24020191017-10-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting24020191017-10-R01Light Truck - Pick up10300Inv#002-R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 240 | 20191017-10-R01 | 53510112 | Access | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and continuing working towards ROW from Beck road. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24020191017-10-R01Operator - Principle221980 | Corbiere and Sons Contracting24020191017-10-R01Operator - Principle221980Inv#002-R01 | [5 empty] | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 240 | 20191017-10-R01 | 53510112 | Access | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and continuing working towards ROW from Beck road. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24020191017-10-R01Labourer - Specialized11825 | Corbiere and Sons Contracting24020191017-10-R01Labourer - Specialized11825Inv#002-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 240 | 20191017-10-R01 | 53510112 | Access | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and continuing working towards ROW from Beck road. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24020191017-10-R01Labourer - General11715 | Corbiere and Sons Contracting24020191017-10-R01Labourer - General11715Inv#002-R01 | [5 empty] | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 240 | 20191017-10-R01 | 53510112 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and continuing working towards ROW from Beck road. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24020191017-10-R01L.O.A.3630 | Corbiere and Sons Contracting24020191017-10-R01L.O.A.3630Inv#002-R01 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 232 | 20191017-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-10-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 to 624 or equal has incorrect rate on LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting23220191017-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting23220191017-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 232 | 20191017-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2019-10-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 to 624 or equal has incorrect rate on LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting23220191017-2-R01Tractor Trailer - 60 Ton91215 | Corbiere and Sons Contracting23220191017-2-R01Tractor Trailer - 60 Ton91215Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 232 | 20191017-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-10-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 to 624 or equal has incorrect rate on LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting23220191017-2-R01Operator - Principle121080 | Corbiere and Sons Contracting23220191017-2-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 232 | 20191017-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-10-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 to 624 or equal has incorrect rate on LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting23220191017-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting23220191017-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 232 | 20191017-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 to 624 or equal has incorrect rate on LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting23220191017-2-R01Labourer - General10650 | Corbiere and Sons Contracting23220191017-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 232 | 20191017-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 to 624 or equal has incorrect rate on LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting23220191017-2-R01L.O.A.2420 | Corbiere and Sons Contracting23220191017-2-R01L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 234 | 20191017-4-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-10-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting23420191017-4-R01Feller Buncher92160 | Corbiere and Sons Contracting23420191017-4-R01Feller Buncher92160Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 234 | 20191017-4-R01 | 53520101 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-10-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting23420191017-4-R01Mulcher91845 | Corbiere and Sons Contracting23420191017-4-R01Mulcher91845Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 234 | 20191017-4-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-10-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting23420191017-4-R01Skidder 91539 | Corbiere and Sons Contracting23420191017-4-R01Skidder 91539Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 234 | 20191017-4-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-10-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting23420191017-4-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting23420191017-4-R01Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 234 | 20191017-4-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-10-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting23420191017-4-R01Operator - Principle332970 | Corbiere and Sons Contracting23420191017-4-R01Operator - Principle332970Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 234 | 20191017-4-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting23420191017-4-R01L.O.A.3630 | Corbiere and Sons Contracting23420191017-4-R01L.O.A.3630Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 235 | 20191017-5-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 23.5 | HR | 180 | 0 |  |  | 5640 | 733.2 | 6373.2 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and Skidding A045 Westerly |  |  | A045 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting23520191017-5-R01Feller Buncher23.55640 | Corbiere and Sons Contracting23520191017-5-R01Feller Buncher23.55640Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 235 | 20191017-5-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 5.5 | HR | 128.25 | 0 |  |  | 940.5 | 122.265 | 1062.765 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and Skidding A045 Westerly |  |  | A045 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting23520191017-5-R01Skidder 5.5940.5 | Corbiere and Sons Contracting23520191017-5-R01Skidder 5.5940.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 940.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 235 | 20191017-5-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and Skidding A045 Westerly |  |  | A045 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting23520191017-5-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting23520191017-5-R01Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 235 | 20191017-5-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and Skidding A045 Westerly |  |  | A045 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting23520191017-5-R01Operator - Principle443960 | Corbiere and Sons Contracting23520191017-5-R01Operator - Principle443960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 235 | 20191017-5-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and Skidding A045 Westerly |  |  | A045 | 0 |  |  | 34 | 43812 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting23520191017-5-R01L.O.A.2420 | Corbiere and Sons Contracting23520191017-5-R01L.O.A.2420Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 236 | 20191017-6 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting23620191017-6Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting23620191017-6Grinder - 4710 Peterson or equal95011.2Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 236 | 20191017-6 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting23620191017-6Log Loader91377 | Corbiere and Sons Contracting23620191017-6Log Loader91377Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 236 | 20191017-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting23620191017-6Light Truck - Pick up10300 | Corbiere and Sons Contracting23620191017-6Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 236 | 20191017-6 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting23620191017-6Operator - Principle11990 | Corbiere and Sons Contracting23620191017-6Operator - Principle11990Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 236 | 20191017-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting23620191017-6L.O.A.1210 | Corbiere and Sons Contracting23620191017-6L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 244 | 20191018-03 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR | 180 | 0 |  |  | 2280 | 296.4 | 2576.4 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North Shore - Clearing Tower #21 West of creek - Start of Retention blocks before tower 20 |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24420191018-03Feller Buncher9.52280 | Corbiere and Sons Contracting24420191018-03Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 244 | 20191018-03 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR | 128.25 | 0 |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North Shore - Clearing Tower #21 West of creek - Start of Retention blocks before tower 20 |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24420191018-03Skidder 9.51624.5 | Corbiere and Sons Contracting24420191018-03Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 244 | 20191018-03 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North Shore - Clearing Tower #21 West of creek - Start of Retention blocks before tower 20 |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24420191018-03Light Truck - Pick up30900 | Corbiere and Sons Contracting24420191018-03Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 244 | 20191018-03 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North Shore - Clearing Tower #21 West of creek - Start of Retention blocks before tower 20 |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24420191018-03Foreman4380 | Corbiere and Sons Contracting24420191018-03Foreman4380Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 244 | 20191018-03 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North Shore - Clearing Tower #21 West of creek - Start of Retention blocks before tower 20 |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24420191018-03Operator - Principle221980 | Corbiere and Sons Contracting24420191018-03Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 244 | 20191018-03 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North Shore - Clearing Tower #21 West of creek - Start of Retention blocks before tower 20 |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24420191018-03L.O.A.3630 | Corbiere and Sons Contracting24420191018-03L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 242 | 20191018-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting24220191018-1Light Truck - Pick up601800 | Corbiere and Sons Contracting24220191018-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 242 | 20191018-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting24220191018-1Project Manager121320 | Corbiere and Sons Contracting24220191018-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 242 | 20191018-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting24220191018-1Superintendent121260 | Corbiere and Sons Contracting24220191018-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 242 | 20191018-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting24220191018-1Project Coordinator12960 | Corbiere and Sons Contracting24220191018-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 242 | 20191018-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting24220191018-1Construction Coordinator12960 | Corbiere and Sons Contracting24220191018-1Construction Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 242 | 20191018-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting24220191018-1Safety Advisor121020 | Corbiere and Sons Contracting24220191018-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 242 | 20191018-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting24220191018-1Project Controls10700 | Corbiere and Sons Contracting24220191018-1Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 242 | 20191018-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting24220191018-1L.O.A.61260 | Corbiere and Sons Contracting24220191018-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 243 | 20191018-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-10-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 to 624 or equal has incorrect rate listed on LEM. REVISED 11152019 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting24320191018-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting24320191018-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 243 | 20191018-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2019-10-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 to 624 or equal has incorrect rate listed on LEM. REVISED 11152019 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting24320191018-2-R01Tractor Trailer - 60 Ton91215 | Corbiere and Sons Contracting24320191018-2-R01Tractor Trailer - 60 Ton91215Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 243 | 20191018-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-10-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 to 624 or equal has incorrect rate listed on LEM. REVISED 11152019 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting24320191018-2-R01Operator - Principle121080 | Corbiere and Sons Contracting24320191018-2-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 243 | 20191018-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-10-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 to 624 or equal has incorrect rate listed on LEM. REVISED 11152019 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting24320191018-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting24320191018-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 243 | 20191018-2-R01 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-10-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 to 624 or equal has incorrect rate listed on LEM. REVISED 11152019 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting24320191018-2-R01Labourer - Specialized11825 | Corbiere and Sons Contracting24320191018-2-R01Labourer - Specialized11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 243 | 20191018-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 to 624 or equal has incorrect rate listed on LEM. REVISED 11152019 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting24320191018-2-R01Labourer - General10650 | Corbiere and Sons Contracting24320191018-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 243 | 20191018-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 to 624 or equal has incorrect rate listed on LEM. REVISED 11152019 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting24320191018-2-R01L.O.A.3630 | Corbiere and Sons Contracting24320191018-2-R01L.O.A.3630Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 245 | 20191018-4-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | A032 Eastward |  |  | A032 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24520191018-4-R01Feller Buncher92160 | Corbiere and Sons Contracting24520191018-4-R01Feller Buncher92160Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 245 | 20191018-4-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | A032 Eastward |  |  | A032 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24520191018-4-R01Skidder 91539 | Corbiere and Sons Contracting24520191018-4-R01Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 245 | 20191018-4-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | A032 Eastward |  |  | A032 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24520191018-4-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting24520191018-4-R01Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 245 | 20191018-4-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | A032 Eastward |  |  | A032 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24520191018-4-R01Operator - Principle221980 | Corbiere and Sons Contracting24520191018-4-R01Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 245 | 20191018-4-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | A032 Eastward |  |  | A032 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24520191018-4-R01L.O.A.2420 | Corbiere and Sons Contracting24520191018-4-R01L.O.A.2420Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 246 | 20191018-5-R01 | 53520101 | Clearing | 0 | Brusher | 202.5 | 4.5 | HR | 151.88 | 0 |  |  | 911.25 | 118.4625 | 1029.7125 | 2019-10-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing / skidding Beck Road. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting24620191018-5-R01Brusher4.5911.25 | Corbiere and Sons Contracting24620191018-5-R01Brusher4.5911.25Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 911.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 246 | 20191018-5-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 23.5 | HR | 180 | 0 |  |  | 5640 | 733.2 | 6373.2 | 2019-10-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing / skidding Beck Road. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting24620191018-5-R01Feller Buncher23.55640 | Corbiere and Sons Contracting24620191018-5-R01Feller Buncher23.55640Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 246 | 20191018-5-R01 | 53520101 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-10-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing / skidding Beck Road. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting24620191018-5-R01Mulcher91845 | Corbiere and Sons Contracting24620191018-5-R01Mulcher91845Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 246 | 20191018-5-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 5.5 | HR | 128.25 | 0 |  |  | 940.5 | 122.265 | 1062.765 | 2019-10-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing / skidding Beck Road. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting24620191018-5-R01Skidder 5.5940.5 | Corbiere and Sons Contracting24620191018-5-R01Skidder 5.5940.5Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 940.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 246 | 20191018-5-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-10-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing / skidding Beck Road. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting24620191018-5-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting24620191018-5-R01Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 246 | 20191018-5-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 60.5 | HR |  |  |  | 0 | 5445 | 707.85 | 6152.85 | 2019-10-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing / skidding Beck Road. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting24620191018-5-R01Operator - Principle60.55445 | Corbiere and Sons Contracting24620191018-5-R01Operator - Principle60.55445Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5445 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 246 | 20191018-5-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-10-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing / skidding Beck Road. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting24620191018-5-R01L.O.A.4840 | Corbiere and Sons Contracting24620191018-5-R01L.O.A.4840Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 247 | 20191018-6 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  | A028 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24720191018-6Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting24720191018-6Grinder - 4710 Peterson or equal95011.2Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 247 | 20191018-6 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  | A028 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24720191018-6Log Loader91377 | Corbiere and Sons Contracting24720191018-6Log Loader91377Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 247 | 20191018-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  | A028 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24720191018-6Light Truck - Pick up10300 | Corbiere and Sons Contracting24720191018-6Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 247 | 20191018-6 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  | A028 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24720191018-6Operator - Principle11990 | Corbiere and Sons Contracting24720191018-6Operator - Principle11990Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 247 | 20191018-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-18 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  | A028 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting24720191018-6L.O.A.1210 | Corbiere and Sons Contracting24720191018-6L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 253 | 20191019-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-10-19 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting25320191019-1Light Truck - Pick up601800 | Corbiere and Sons Contracting25320191019-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 253 | 20191019-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-19 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting25320191019-1Project Manager121320 | Corbiere and Sons Contracting25320191019-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 253 | 20191019-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-19 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting25320191019-1Superintendent121260 | Corbiere and Sons Contracting25320191019-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 253 | 20191019-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-19 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting25320191019-1Project Coordinator12960 | Corbiere and Sons Contracting25320191019-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 253 | 20191019-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-19 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting25320191019-1Construction Coordinator12960 | Corbiere and Sons Contracting25320191019-1Construction Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 253 | 20191019-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-19 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting25320191019-1Safety Advisor121020 | Corbiere and Sons Contracting25320191019-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 253 | 20191019-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-10-19 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting25320191019-1Project Controls10700 | Corbiere and Sons Contracting25320191019-1Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 253 | 20191019-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-19 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting25320191019-1L.O.A.61260 | Corbiere and Sons Contracting25320191019-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 254 | 20191019-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-10-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 to 624 or equal has incorrect rate listed on LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting25420191019-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting25420191019-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 254 | 20191019-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-10-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 to 624 or equal has incorrect rate listed on LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting25420191019-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting25420191019-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 254 | 20191019-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-10-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 to 624 or equal has incorrect rate listed on LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting25420191019-2-R01Operator - Principle121080 | Corbiere and Sons Contracting25420191019-2-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 254 | 20191019-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-10-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 to 624 or equal has incorrect rate listed on LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting25420191019-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting25420191019-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 254 | 20191019-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 to 624 or equal has incorrect rate listed on LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting25420191019-2-R01Labourer - General10650 | Corbiere and Sons Contracting25420191019-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 254 | 20191019-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 to 624 or equal has incorrect rate listed on LEM. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting25420191019-2-R01L.O.A.2420 | Corbiere and Sons Contracting25420191019-2-R01L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 255 | 20191019-3-R01 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-10-19 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mulcher finishing at A021 - Buncher and Skidder at A034. |  |  | A021, A034 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting25520191019-3-R01Feller Buncher92160 | Corbiere and Sons Contracting25520191019-3-R01Feller Buncher92160Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 255 | 20191019-3-R01 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-10-19 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mulcher finishing at A021 - Buncher and Skidder at A034. |  |  | A021, A034 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting25520191019-3-R01Mulcher91845 | Corbiere and Sons Contracting25520191019-3-R01Mulcher91845Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 255 | 20191019-3-R01 | 53520102 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-10-19 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mulcher finishing at A021 - Buncher and Skidder at A034. |  |  | A021, A034 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting25520191019-3-R01Skidder 91539 | Corbiere and Sons Contracting25520191019-3-R01Skidder 91539Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 255 | 20191019-3-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-10-19 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mulcher finishing at A021 - Buncher and Skidder at A034. |  |  | A021, A034 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting25520191019-3-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting25520191019-3-R01Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 255 | 20191019-3-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-10-19 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mulcher finishing at A021 - Buncher and Skidder at A034. |  |  | A021, A034 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting25520191019-3-R01Operator - Principle332970 | Corbiere and Sons Contracting25520191019-3-R01Operator - Principle332970Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 255 | 20191019-3-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-19 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mulcher finishing at A021 - Buncher and Skidder at A034. |  |  | A021, A034 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting25520191019-3-R01L.O.A.3630 | Corbiere and Sons Contracting25520191019-3-R01L.O.A.3630Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 256 | 20191019-4-R01 | 53520101 | Clearing | 0 | Brusher | 202.5 | 4.5 | HR | 151.88 | 0 |  |  | 911.25 | 118.4625 | 1029.7125 | 2019-10-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing and access going on from 43 to 46, seperating and pilling white birch for landowner. |  |  | 43-46 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting25620191019-4-R01Brusher4.5911.25 | Corbiere and Sons Contracting25620191019-4-R01Brusher4.5911.25Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 911.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 256 | 20191019-4-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 23.5 | HR | 180 | 0 |  |  | 5640 | 733.2 | 6373.2 | 2019-10-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing and access going on from 43 to 46, seperating and pilling white birch for landowner. |  |  | 43-46 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting25620191019-4-R01Feller Buncher23.55640 | Corbiere and Sons Contracting25620191019-4-R01Feller Buncher23.55640Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 256 | 20191019-4-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 5 | HR | 128.25 | 0 |  |  | 855 | 111.15 | 966.15 | 2019-10-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing and access going on from 43 to 46, seperating and pilling white birch for landowner. |  |  | 43-46 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting25620191019-4-R01Skidder 5855 | Corbiere and Sons Contracting25620191019-4-R01Skidder 5855Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 855 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 256 | 20191019-4-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-10-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing and access going on from 43 to 46, seperating and pilling white birch for landowner. |  |  | 43-46 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting25620191019-4-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting25620191019-4-R01Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 256 | 20191019-4-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-10-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing and access going on from 43 to 46, seperating and pilling white birch for landowner. |  |  | 43-46 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting25620191019-4-R01Operator - Principle443960 | Corbiere and Sons Contracting25620191019-4-R01Operator - Principle443960Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 256 | 20191019-4-R01 | 53520101 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-10-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing and access going on from 43 to 46, seperating and pilling white birch for landowner. |  |  | 43-46 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting25620191019-4-R01Labourer - General11715 | Corbiere and Sons Contracting25620191019-4-R01Labourer - General11715Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 256 | 20191019-4-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-10-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing and access going on from 43 to 46, seperating and pilling white birch for landowner. |  |  | 43-46 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting25620191019-4-R01L.O.A.4840 | Corbiere and Sons Contracting25620191019-4-R01L.O.A.4840Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 257 | 20191019-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-10-19 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting25720191019-5Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting25720191019-5Grinder - 4710 Peterson or equal95011.2Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 257 | 20191019-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-10-19 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting25720191019-5Log Loader91377 | Corbiere and Sons Contracting25720191019-5Log Loader91377Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 257 | 20191019-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-19 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting25720191019-5Light Truck - Pick up10300 | Corbiere and Sons Contracting25720191019-5Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 257 | 20191019-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-19 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting25720191019-5Operator - Principle11990 | Corbiere and Sons Contracting25720191019-5Operator - Principle11990Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 257 | 20191019-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-19 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting25720191019-5L.O.A.1210 | Corbiere and Sons Contracting25720191019-5L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 267 | 20191020-06-R01 | 53510112 | Access | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fixed existing approaches to bridge at 7 with rock- Build RO road a A009-A010 Eastward - Fixed existing access road from McGregor road to site due to weather. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting26720191020-06-R01Dozer D6 or equal91215 | Corbiere and Sons Contracting26720191020-06-R01Dozer D6 or equal91215Inv#002-R01 | [5 empty] | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 267 | 20191020-06-R01 | 53510112 | Access | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fixed existing approaches to bridge at 7 with rock- Build RO road a A009-A010 Eastward - Fixed existing access road from McGregor road to site due to weather. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting26720191020-06-R01Excavator - 30 ton91255.5 | Corbiere and Sons Contracting26720191020-06-R01Excavator - 30 ton91255.5Inv#002-R01 | [5 empty] | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 267 | 20191020-06-R01 | 53510112 | Access | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fixed existing approaches to bridge at 7 with rock- Build RO road a A009-A010 Eastward - Fixed existing access road from McGregor road to site due to weather. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting26720191020-06-R01Excavator - 36 ton91539 | Corbiere and Sons Contracting26720191020-06-R01Excavator - 36 ton91539Inv#002-R01 | [5 empty] | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 267 | 20191020-06-R01 | 53510112 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fixed existing approaches to bridge at 7 with rock- Build RO road a A009-A010 Eastward - Fixed existing access road from McGregor road to site due to weather. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting26720191020-06-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting26720191020-06-R01Light Truck - Pick up10300Inv#002-R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 267 | 20191020-06-R01 | 53510112 | Access | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fixed existing approaches to bridge at 7 with rock- Build RO road a A009-A010 Eastward - Fixed existing access road from McGregor road to site due to weather. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting26720191020-06-R01Operator - Principle332970 | Corbiere and Sons Contracting26720191020-06-R01Operator - Principle332970Inv#002-R01 | [5 empty] | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 267 | 20191020-06-R01 | 53510112 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fixed existing approaches to bridge at 7 with rock- Build RO road a A009-A010 Eastward - Fixed existing access road from McGregor road to site due to weather. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting26720191020-06-R01L.O.A.3630 | Corbiere and Sons Contracting26720191020-06-R01L.O.A.3630Inv#002-R01 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 262 | 20191020-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting26220191020-1Light Truck - Pick up601800 | Corbiere and Sons Contracting26220191020-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 262 | 20191020-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting26220191020-1Project Manager121320 | Corbiere and Sons Contracting26220191020-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 262 | 20191020-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting26220191020-1Superintendent121260 | Corbiere and Sons Contracting26220191020-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 262 | 20191020-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting26220191020-1Project Coordinator12960 | Corbiere and Sons Contracting26220191020-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 262 | 20191020-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting26220191020-1Construction Coordinator12960 | Corbiere and Sons Contracting26220191020-1Construction Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 262 | 20191020-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting26220191020-1Safety Advisor121020 | Corbiere and Sons Contracting26220191020-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 262 | 20191020-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 9 | HR |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting26220191020-1Project Controls9630 | Corbiere and Sons Contracting26220191020-1Project Controls9630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 262 | 20191020-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting26220191020-1L.O.A.61260 | Corbiere and Sons Contracting26220191020-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 263 | 20191020-2-R02 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 |  | HR | 74.25 | 9 |  |  | 668.25 | 86.8725 | 755.1225 | 2019-10-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Possibly missing hours for Operator and Labourer? Rate for Loader JD 524-624 or equal is incorrect - as it is standby should be $74.25 * REQUIRES FURTHER REVISION LOADER - CALCULATION IS INCORRECT TOTAL SHOULD BE 668.25 RR- Corrected Nov 16, 2019 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting26320191020-2-R02Loader JD 524 to 624 or equal668.25 | Corbiere and Sons Contracting26320191020-2-R02Loader JD 524 to 624 or equal668.25Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 668.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 263 | 20191020-2-R02 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-10-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Possibly missing hours for Operator and Labourer? Rate for Loader JD 524-624 or equal is incorrect - as it is standby should be $74.25 * REQUIRES FURTHER REVISION LOADER - CALCULATION IS INCORRECT TOTAL SHOULD BE 668.25 RR- Corrected Nov 16, 2019 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting26320191020-2-R02Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting26320191020-2-R02Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 263 | 20191020-2-R02 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-10-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Possibly missing hours for Operator and Labourer? Rate for Loader JD 524-624 or equal is incorrect - as it is standby should be $74.25 * REQUIRES FURTHER REVISION LOADER - CALCULATION IS INCORRECT TOTAL SHOULD BE 668.25 RR- Corrected Nov 16, 2019 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting26320191020-2-R02Operator - Intermdiate11825 | Corbiere and Sons Contracting26320191020-2-R02Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 263 | 20191020-2-R02 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Possibly missing hours for Operator and Labourer? Rate for Loader JD 524-624 or equal is incorrect - as it is standby should be $74.25 * REQUIRES FURTHER REVISION LOADER - CALCULATION IS INCORRECT TOTAL SHOULD BE 668.25 RR- Corrected Nov 16, 2019 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting26320191020-2-R02L.O.A.2420 | Corbiere and Sons Contracting26320191020-2-R02L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 264 | 20191020-3-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Buncher and Skidder at A034. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting26420191020-3-R01Feller Buncher92160 | Corbiere and Sons Contracting26420191020-3-R01Feller Buncher92160Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 264 | 20191020-3-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Buncher and Skidder at A034. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting26420191020-3-R01Skidder 91539 | Corbiere and Sons Contracting26420191020-3-R01Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 264 | 20191020-3-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Buncher and Skidder at A034. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting26420191020-3-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting26420191020-3-R01Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 264 | 20191020-3-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Buncher and Skidder at A034. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting26420191020-3-R01Operator - Principle221980 | Corbiere and Sons Contracting26420191020-3-R01Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 264 | 20191020-3-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Buncher and Skidder at A034. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting26420191020-3-R01L.O.A.2420 | Corbiere and Sons Contracting26420191020-3-R01L.O.A.2420Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 265 | 20191020-4-R01 | 53520101 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-10-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Clinton Robinson rate is incorrect. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing from 46-47, includes pull area up to creek and crossing bridge - brushing from 46-43 west. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting26520191020-4-R01Brusher91822.5 | Corbiere and Sons Contracting26520191020-4-R01Brusher91822.5Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 265 | 20191020-4-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 23.5 | HR | 180 | 0 |  |  | 5640 | 733.2 | 6373.2 | 2019-10-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Clinton Robinson rate is incorrect. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing from 46-47, includes pull area up to creek and crossing bridge - brushing from 46-43 west. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting26520191020-4-R01Feller Buncher23.55640 | Corbiere and Sons Contracting26520191020-4-R01Feller Buncher23.55640Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 265 | 20191020-4-R01 | 53520101 | Clearing | 0 | Mulcher | 205 | 7 | HR | 153.75 | 0 |  |  | 1435 | 186.55 | 1621.55 | 2019-10-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Clinton Robinson rate is incorrect. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing from 46-47, includes pull area up to creek and crossing bridge - brushing from 46-43 west. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting26520191020-4-R01Mulcher71435 | Corbiere and Sons Contracting26520191020-4-R01Mulcher71435Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1435 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 265 | 20191020-4-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-10-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Clinton Robinson rate is incorrect. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing from 46-47, includes pull area up to creek and crossing bridge - brushing from 46-43 west. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting26520191020-4-R01Skidder 91539 | Corbiere and Sons Contracting26520191020-4-R01Skidder 91539Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 265 | 20191020-4-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-10-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Clinton Robinson rate is incorrect. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing from 46-47, includes pull area up to creek and crossing bridge - brushing from 46-43 west. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting26520191020-4-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting26520191020-4-R01Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 265 | 20191020-4-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 63 | HR |  |  |  | 0 | 5670 | 737.1 | 6407.1 | 2019-10-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Clinton Robinson rate is incorrect. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing from 46-47, includes pull area up to creek and crossing bridge - brushing from 46-43 west. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting26520191020-4-R01Operator - Principle635670 | Corbiere and Sons Contracting26520191020-4-R01Operator - Principle635670Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5670 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 265 | 20191020-4-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-10-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Clinton Robinson rate is incorrect. REVISED 11152019 DK Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing from 46-47, includes pull area up to creek and crossing bridge - brushing from 46-43 west. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting26520191020-4-R01L.O.A.4840 | Corbiere and Sons Contracting26520191020-4-R01L.O.A.4840Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 266 | 20191020-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting26620191020-5Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting26620191020-5Grinder - 4710 Peterson or equal95011.2Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 266 | 20191020-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting26620191020-5Log Loader91377 | Corbiere and Sons Contracting26620191020-5Log Loader91377Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 266 | 20191020-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting26620191020-5Light Truck - Pick up10300 | Corbiere and Sons Contracting26620191020-5Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 266 | 20191020-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting26620191020-5Operator - Principle11990 | Corbiere and Sons Contracting26620191020-5Operator - Principle11990Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 266 | 20191020-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-20 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting26620191020-5L.O.A.1210 | Corbiere and Sons Contracting26620191020-5L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 274 | 20191021-03 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR | 180 | 0 |  |  | 2280 | 296.4 | 2576.4 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North - shore - clearing tower A019 heading west. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting27420191021-03Feller Buncher9.52280 | Corbiere and Sons Contracting27420191021-03Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 274 | 20191021-03 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR | 128.25 | 0 |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North - shore - clearing tower A019 heading west. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting27420191021-03Skidder 9.51624.5 | Corbiere and Sons Contracting27420191021-03Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 274 | 20191021-03 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North - shore - clearing tower A019 heading west. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting27420191021-03Light Truck - Pick up30900 | Corbiere and Sons Contracting27420191021-03Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 274 | 20191021-03 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North - shore - clearing tower A019 heading west. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting27420191021-03Foreman4380 | Corbiere and Sons Contracting27420191021-03Foreman4380Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 274 | 20191021-03 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North - shore - clearing tower A019 heading west. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting27420191021-03Operator - Principle221980 | Corbiere and Sons Contracting27420191021-03Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 274 | 20191021-03 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North - shore - clearing tower A019 heading west. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting27420191021-03L.O.A.3630 | Corbiere and Sons Contracting27420191021-03L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 271 | 20191021-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting27120191021-1Light Truck - Pick up601800 | Corbiere and Sons Contracting27120191021-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 271 | 20191021-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting27120191021-1Project Manager121320 | Corbiere and Sons Contracting27120191021-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 271 | 20191021-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting27120191021-1Superintendent121260 | Corbiere and Sons Contracting27120191021-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 271 | 20191021-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting27120191021-1Project Coordinator12960 | Corbiere and Sons Contracting27120191021-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 271 | 20191021-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting27120191021-1Construction Coordinator12960 | Corbiere and Sons Contracting27120191021-1Construction Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 271 | 20191021-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting27120191021-1Safety Advisor121020 | Corbiere and Sons Contracting27120191021-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 271 | 20191021-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 9 | HR |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting27120191021-1Project Controls9630 | Corbiere and Sons Contracting27120191021-1Project Controls9630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 271 | 20191021-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting27120191021-1L.O.A.61260 | Corbiere and Sons Contracting27120191021-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 273 | 20191021-2-R02 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-10-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting27320191021-2-R02Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting27320191021-2-R02Loader JD 524 to 624 or equal9891Inv#006R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 273 | 20191021-2-R02 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2019-10-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting27320191021-2-R02Tractor Trailer - 60 Ton91215 | Corbiere and Sons Contracting27320191021-2-R02Tractor Trailer - 60 Ton91215Inv#006R01 |  |  | WF1-Indirects |  |  | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 273 | 20191021-2-R02 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 12 | HR |  |  | 70 | 0 | 900 | 117 | 1017 | 2019-10-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting27320191021-2-R02Operator - Intermdiate12900 | Corbiere and Sons Contracting27320191021-2-R02Operator - Intermdiate12900Inv#006R01 |  |  | WF1-Indirects |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 273 | 20191021-2-R02 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-10-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting27320191021-2-R02Operator - Intermdiate11825 | Corbiere and Sons Contracting27320191021-2-R02Operator - Intermdiate11825Inv#006R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 273 | 20191021-2-R02 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting27320191021-2-R02Labourer - General10650 | Corbiere and Sons Contracting27320191021-2-R02Labourer - General10650Inv#006R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 273 | 20191021-2-R02 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting27320191021-2-R02L.O.A.2420 | Corbiere and Sons Contracting27320191021-2-R02L.O.A.2420Inv#006R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 275 | 20191021-4-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Buncher and Skidder at A034 - Cleaning up and sorting wood for landowner. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting27520191021-4-R01Feller Buncher92160 | Corbiere and Sons Contracting27520191021-4-R01Feller Buncher92160Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 275 | 20191021-4-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Buncher and Skidder at A034 - Cleaning up and sorting wood for landowner. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting27520191021-4-R01Skidder 91539 | Corbiere and Sons Contracting27520191021-4-R01Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 275 | 20191021-4-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Buncher and Skidder at A034 - Cleaning up and sorting wood for landowner. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting27520191021-4-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting27520191021-4-R01Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 275 | 20191021-4-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Buncher and Skidder at A034 - Cleaning up and sorting wood for landowner. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting27520191021-4-R01Operator - Principle221980 | Corbiere and Sons Contracting27520191021-4-R01Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 275 | 20191021-4-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Buncher and Skidder at A034 - Cleaning up and sorting wood for landowner. |  |  |  | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting27520191021-4-R01L.O.A.2420 | Corbiere and Sons Contracting27520191021-4-R01L.O.A.2420Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 276 | 20191021-5 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 25.5 | HR | 180 | 0 |  |  | 6120 | 795.6 | 6915.6 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brusher out of service - mulcher down for 2.5hrs - finished clearing 48 west to river. Crossed railway with equipment and proceeded cutting East. |  |  |  | 0 |  |  | 10 | 43792 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting27620191021-5Feller Buncher25.56120 | Corbiere and Sons Contracting27620191021-5Feller Buncher25.56120Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 6120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 276 | 20191021-5 | 53520101 | Clearing | 0 | Mulcher | 205 | 6 | HR | 153.75 | 0 |  |  | 1230 | 159.9 | 1389.9 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brusher out of service - mulcher down for 2.5hrs - finished clearing 48 west to river. Crossed railway with equipment and proceeded cutting East. |  |  |  | 0 |  |  | 10 | 43792 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting27620191021-5Mulcher61230 | Corbiere and Sons Contracting27620191021-5Mulcher61230Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1230 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 276 | 20191021-5 | 53520101 | Clearing | 0 | Skidder | 171 | 8.5 | HR | 128.25 | 0 |  |  | 1453.5 | 188.955 | 1642.455 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brusher out of service - mulcher down for 2.5hrs - finished clearing 48 west to river. Crossed railway with equipment and proceeded cutting East. |  |  |  | 0 |  |  | 10 | 43792 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting27620191021-5Skidder 8.51453.5 | Corbiere and Sons Contracting27620191021-5Skidder 8.51453.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1453.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 276 | 20191021-5 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brusher out of service - mulcher down for 2.5hrs - finished clearing 48 west to river. Crossed railway with equipment and proceeded cutting East. |  |  |  | 0 |  |  | 10 | 43792 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting27620191021-5Light Truck - Pick up20600 | Corbiere and Sons Contracting27620191021-5Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 276 | 20191021-5 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 50 | HR |  |  |  | 0 | 4500 | 585 | 5085 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brusher out of service - mulcher down for 2.5hrs - finished clearing 48 west to river. Crossed railway with equipment and proceeded cutting East. |  |  |  | 0 |  |  | 10 | 43792 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting27620191021-5Operator - Principle504500 | Corbiere and Sons Contracting27620191021-5Operator - Principle504500Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 276 | 20191021-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brusher out of service - mulcher down for 2.5hrs - finished clearing 48 west to river. Crossed railway with equipment and proceeded cutting East. |  |  |  | 0 |  |  | 10 | 43792 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting27620191021-5L.O.A.3630 | Corbiere and Sons Contracting27620191021-5L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 278 | 20191021-6 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting27820191021-6Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting27820191021-6Grinder - 4710 Peterson or equal95011.2Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 278 | 20191021-6 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting27820191021-6Log Loader91377 | Corbiere and Sons Contracting27820191021-6Log Loader91377Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 278 | 20191021-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting27820191021-6Light Truck - Pick up10300 | Corbiere and Sons Contracting27820191021-6Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 278 | 20191021-6 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting27820191021-6Operator - Principle11990 | Corbiere and Sons Contracting27820191021-6Operator - Principle11990Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 278 | 20191021-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-21 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting27820191021-6L.O.A.1210 | Corbiere and Sons Contracting27820191021-6L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 283 | 20191022-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting28320191022-1Light Truck - Pick up601800 | Corbiere and Sons Contracting28320191022-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 283 | 20191022-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting28320191022-1Project Manager121320 | Corbiere and Sons Contracting28320191022-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 283 | 20191022-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting28320191022-1Superintendent121260 | Corbiere and Sons Contracting28320191022-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 283 | 20191022-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting28320191022-1Project Coordinator12960 | Corbiere and Sons Contracting28320191022-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 283 | 20191022-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting28320191022-1Construction Coordinator12960 | Corbiere and Sons Contracting28320191022-1Construction Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 283 | 20191022-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting28320191022-1Safety Advisor121020 | Corbiere and Sons Contracting28320191022-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 283 | 20191022-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 11 | HR |  |  |  | 0 | 770 | 100.1 | 870.1 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting28320191022-1Project Controls11770 | Corbiere and Sons Contracting28320191022-1Project Controls11770Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 283 | 20191022-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting28320191022-1L.O.A.61260 | Corbiere and Sons Contracting28320191022-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 284 | 20191022-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-10-22 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting28420191022-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting28420191022-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 284 | 20191022-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2019-10-22 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting28420191022-2-R01Tractor Trailer - 60 Ton91215 | Corbiere and Sons Contracting28420191022-2-R01Tractor Trailer - 60 Ton91215Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 284 | 20191022-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-10-22 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting28420191022-2-R01Operator - Principle121080 | Corbiere and Sons Contracting28420191022-2-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 284 | 20191022-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-22 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting28420191022-2-R01Labourer - General10650 | Corbiere and Sons Contracting28420191022-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 284 | 20191022-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-22 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting28420191022-2-R01L.O.A.1210 | Corbiere and Sons Contracting28420191022-2-R01L.O.A.1210Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 285 | 20191022-3 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR | 180 | 0 |  |  | 2280 | 296.4 | 2576.4 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and cutting towers A013-A014, Skidder tower A022 |  |  | A013, A014, A022 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting28520191022-3Feller Buncher9.52280 | Corbiere and Sons Contracting28520191022-3Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 285 | 20191022-3 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR | 128.25 | 0 |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and cutting towers A013-A014, Skidder tower A022 |  |  | A013, A014, A022 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting28520191022-3Skidder 9.51624.5 | Corbiere and Sons Contracting28520191022-3Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 285 | 20191022-3 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and cutting towers A013-A014, Skidder tower A022 |  |  | A013, A014, A022 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting28520191022-3Light Truck - Pick up30900 | Corbiere and Sons Contracting28520191022-3Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 285 | 20191022-3 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and cutting towers A013-A014, Skidder tower A022 |  |  | A013, A014, A022 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting28520191022-3Foreman4380 | Corbiere and Sons Contracting28520191022-3Foreman4380Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 285 | 20191022-3 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and cutting towers A013-A014, Skidder tower A022 |  |  | A013, A014, A022 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting28520191022-3Operator - Principle221980 | Corbiere and Sons Contracting28520191022-3Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 285 | 20191022-3 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and cutting towers A013-A014, Skidder tower A022 |  |  | A013, A014, A022 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting28520191022-3L.O.A.3630 | Corbiere and Sons Contracting28520191022-3L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 286 | 20191022-4 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR | 180 | 0 |  |  | 2280 | 296.4 | 2576.4 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Buncher and Skidder at A012-A013 |  |  | A012-A013 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting28620191022-4Feller Buncher9.52280 | Corbiere and Sons Contracting28620191022-4Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 286 | 20191022-4 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR | 128.25 | 0 |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Buncher and Skidder at A012-A013 |  |  | A012-A013 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting28620191022-4Skidder 9.51624.5 | Corbiere and Sons Contracting28620191022-4Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 286 | 20191022-4 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Buncher and Skidder at A012-A013 |  |  | A012-A013 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting28620191022-4Light Truck - Pick up20600 | Corbiere and Sons Contracting28620191022-4Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 286 | 20191022-4 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Buncher and Skidder at A012-A013 |  |  | A012-A013 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting28620191022-4Operator - Principle221980 | Corbiere and Sons Contracting28620191022-4Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 286 | 20191022-4 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Buncher and Skidder at A012-A013 |  |  | A012-A013 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting28620191022-4L.O.A.2420 | Corbiere and Sons Contracting28620191022-4L.O.A.2420Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 287 | 20191022-5-R02 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 10.5 | HR | 180 |  |  |  | 2520 | 327.6 | 2847.6 | 2019-10-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | Shutdown due to Mackenzie River overflowing access road at bridge - Started at A048 |  |  |  | 0 |  | Stoppage of Work | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting28720191022-5-R02Feller Buncher10.52520 | Corbiere and Sons Contracting28720191022-5-R02Feller Buncher10.52520Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2520 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 287 | 20191022-5-R02 | 53520102 | Clearing | 0 | Feller Buncher | 240 |  | HR | 180 | 16.5 |  |  | 2970 | 386.1 | 3356.1 | 2019-10-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | Shutdown due to Mackenzie River overflowing access road at bridge - Started at A048 |  |  |  | 1 |  | Stoppage of Work | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting28720191022-5-R02Feller Buncher2970 | Corbiere and Sons Contracting28720191022-5-R02Feller Buncher2970Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 287 | 20191022-5-R02 | 53520102 | Clearing | 0 | Mulcher | 205 | 3.5 | HR | 153.75 |  |  |  | 717.5 | 93.275 | 810.775 | 2019-10-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | Shutdown due to Mackenzie River overflowing access road at bridge - Started at A048 |  |  |  | 0 |  | Stoppage of Work | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting28720191022-5-R02Mulcher3.5717.5 | Corbiere and Sons Contracting28720191022-5-R02Mulcher3.5717.5Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 717.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 287 | 20191022-5-R02 | 53520102 | Clearing | 0 | Mulcher | 205 |  | HR | 153.75 | 5.5 |  |  | 845.625 | 109.9313 | 955.5562 | 2019-10-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | Shutdown due to Mackenzie River overflowing access road at bridge - Started at A048 |  |  |  | 1 |  | Stoppage of Work | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting28720191022-5-R02Mulcher845.625 | Corbiere and Sons Contracting28720191022-5-R02Mulcher845.625Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 845.625 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 287 | 20191022-5-R02 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 |  |  |  | 600 | 78 | 678 | 2019-10-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | Shutdown due to Mackenzie River overflowing access road at bridge - Started at A048 |  |  |  | 0 |  | Stoppage of Work | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting28720191022-5-R02Light Truck - Pick up20600 | Corbiere and Sons Contracting28720191022-5-R02Light Truck - Pick up20600Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 287 | 20191022-5-R02 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 25 | HR |  |  |  | 0 | 2250 | 292.5 | 2542.5 | 2019-10-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | Shutdown due to Mackenzie River overflowing access road at bridge - Started at A048 |  |  |  | 0 |  | Stoppage of Work | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting28720191022-5-R02Operator - Principle252250 | Corbiere and Sons Contracting28720191022-5-R02Operator - Principle252250Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2250 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 287 | 20191022-5-R02 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | Shutdown due to Mackenzie River overflowing access road at bridge - Started at A048 |  |  |  | 0 |  | Stoppage of Work | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting28720191022-5-R02L.O.A.3630 | Corbiere and Sons Contracting28720191022-5-R02L.O.A.3630Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 288 | 20191022-6 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting28820191022-6Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting28820191022-6Grinder - 4710 Peterson or equal95011.2Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 288 | 20191022-6 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting28820191022-6Log Loader91377 | Corbiere and Sons Contracting28820191022-6Log Loader91377Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 288 | 20191022-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting28820191022-6Light Truck - Pick up10300 | Corbiere and Sons Contracting28820191022-6Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 288 | 20191022-6 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting28820191022-6Operator - Principle11990 | Corbiere and Sons Contracting28820191022-6Operator - Principle11990Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 288 | 20191022-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-22 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting28820191022-6L.O.A.1210 | Corbiere and Sons Contracting28820191022-6L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 296 | 20191023-05-R02 | 53520101 | Clearing | 0 | Feller Buncher | 240 |  | HR | 180 | 27 |  |  | 4860 | 631.8 | 5491.8 | 2019-10-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Weather Delay | 1 |  |  | 1 |  |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting29620191023-05-R02Feller Buncher4860 | Corbiere and Sons Contracting29620191023-05-R02Feller Buncher4860Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4860 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 296 | 20191023-05-R02 | 53520101 | Clearing | 0 | Mulcher | 205 |  | HR | 153.75 | 9 |  |  | 1383.75 | 179.8875 | 1563.6375 | 2019-10-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Weather Delay | 1 |  |  | 1 |  |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting29620191023-05-R02Mulcher1383.75 | Corbiere and Sons Contracting29620191023-05-R02Mulcher1383.75Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1383.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 296 | 20191023-05-R02 | 53520101 | Clearing | 0 | Skidder | 171 |  | HR | 128.25 | 9 |  |  | 1154.25 | 150.0525 | 1304.3025 | 2019-10-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Weather Delay | 1 |  |  | 1 |  |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting29620191023-05-R02Skidder 1154.25 | Corbiere and Sons Contracting29620191023-05-R02Skidder 1154.25Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1154.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 296 | 20191023-05-R02 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 20 | HR |  |  |  | 0 | 1800 | 234 | 2034 | 2019-10-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Weather Delay | 1 |  |  | 1 |  |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting29620191023-05-R02Operator - Principle201800 | Corbiere and Sons Contracting29620191023-05-R02Operator - Principle201800Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 296 | 20191023-05-R02 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 12 | Approved | ROW INTERNAL - STANDBY WEATHER DELAY OCTOBER 1-31, 2019 | 9012 | Weather Delay | 1 |  |  | 1 |  |  | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting29620191023-05-R02L.O.A.3630 | Corbiere and Sons Contracting29620191023-05-R02L.O.A.3630Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 293 | 20191023-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-10-23 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting29320191023-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting29320191023-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 293 | 20191023-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-10-23 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting29320191023-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting29320191023-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 293 | 20191023-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-10-23 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting29320191023-2-R01Operator - Principle121080 | Corbiere and Sons Contracting29320191023-2-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 293 | 20191023-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-10-23 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting29320191023-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting29320191023-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 293 | 20191023-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-23 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting29320191023-2-R01Labourer - General10650 | Corbiere and Sons Contracting29320191023-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 293 | 20191023-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 11.5 | HR |  |  |  | 0 | 747.5 | 97.175 | 844.675 | 2019-10-23 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting29320191023-2-R01Labourer - General11.5747.5 | Corbiere and Sons Contracting29320191023-2-R01Labourer - General11.5747.5Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 747.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 293 | 20191023-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-23 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting29320191023-2-R01L.O.A.3630 | Corbiere and Sons Contracting29320191023-2-R01L.O.A.3630Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 294 | 20191023-3 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR | 180 | 0 |  |  | 2280 | 296.4 | 2576.4 | 2019-10-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Buncher float from pit road tower A019 to McGregor Rd. Cut from Tower A013 to the left. Skidder clearing Tower A019 and Tower A022. |  |  | A019, A013, A022 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting29420191023-3Feller Buncher9.52280 | Corbiere and Sons Contracting29420191023-3Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 294 | 20191023-3 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-10-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Buncher float from pit road tower A019 to McGregor Rd. Cut from Tower A013 to the left. Skidder clearing Tower A019 and Tower A022. |  |  | A019, A013, A022 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting29420191023-3Skidder 91539 | Corbiere and Sons Contracting29420191023-3Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 294 | 20191023-3 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-10-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Buncher float from pit road tower A019 to McGregor Rd. Cut from Tower A013 to the left. Skidder clearing Tower A019 and Tower A022. |  |  | A019, A013, A022 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting29420191023-3Light Truck - Pick up30900 | Corbiere and Sons Contracting29420191023-3Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 294 | 20191023-3 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-10-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Buncher float from pit road tower A019 to McGregor Rd. Cut from Tower A013 to the left. Skidder clearing Tower A019 and Tower A022. |  |  | A019, A013, A022 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting29420191023-3Foreman4380 | Corbiere and Sons Contracting29420191023-3Foreman4380Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 294 | 20191023-3 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Buncher float from pit road tower A019 to McGregor Rd. Cut from Tower A013 to the left. Skidder clearing Tower A019 and Tower A022. |  |  | A019, A013, A022 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting29420191023-3Operator - Principle221980 | Corbiere and Sons Contracting29420191023-3Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 294 | 20191023-3 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Buncher float from pit road tower A019 to McGregor Rd. Cut from Tower A013 to the left. Skidder clearing Tower A019 and Tower A022. |  |  | A019, A013, A022 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting29420191023-3L.O.A.3630 | Corbiere and Sons Contracting29420191023-3L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 295 | 20191023-4 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR | 180 | 0 |  |  | 2280 | 296.4 | 2576.4 | 2019-10-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Tower A013 |  |  | A013 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting29520191023-4Feller Buncher9.52280 | Corbiere and Sons Contracting29520191023-4Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 295 | 20191023-4 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR | 128.25 | 0 |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Tower A013 |  |  | A013 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting29520191023-4Skidder 9.51624.5 | Corbiere and Sons Contracting29520191023-4Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 295 | 20191023-4 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Tower A013 |  |  | A013 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting29520191023-4Light Truck - Pick up10300 | Corbiere and Sons Contracting29520191023-4Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 295 | 20191023-4 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Tower A013 |  |  | A013 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting29520191023-4Operator - Principle221980 | Corbiere and Sons Contracting29520191023-4Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 295 | 20191023-4 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Tower A013 |  |  | A013 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting29520191023-4L.O.A.2420 | Corbiere and Sons Contracting29520191023-4L.O.A.2420Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 297 | 20191023-6 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-10-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting29720191023-6Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting29720191023-6Grinder - 4710 Peterson or equal95011.2Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 297 | 20191023-6 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-10-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting29720191023-6Log Loader91377 | Corbiere and Sons Contracting29720191023-6Log Loader91377Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 297 | 20191023-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting29720191023-6Light Truck - Pick up10300 | Corbiere and Sons Contracting29720191023-6Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 297 | 20191023-6 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting29720191023-6Operator - Principle11990 | Corbiere and Sons Contracting29720191023-6Operator - Principle11990Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 297 | 20191023-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-23 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting29720191023-6L.O.A.1210 | Corbiere and Sons Contracting29720191023-6L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 301 | 20191024-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-10-24 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting30120191024-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting30120191024-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 301 | 20191024-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-10-24 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting30120191024-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting30120191024-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 301 | 20191024-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-10-24 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting30120191024-2-R01Operator - Principle121080 | Corbiere and Sons Contracting30120191024-2-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 301 | 20191024-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-10-24 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting30120191024-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting30120191024-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 301 | 20191024-2-R01 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 11.5 | HR |  |  |  | 0 | 862.5 | 112.125 | 974.625 | 2019-10-24 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting30120191024-2-R01Labourer - Specialized11.5862.5 | Corbiere and Sons Contracting30120191024-2-R01Labourer - Specialized11.5862.5Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 301 | 20191024-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-24 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting30120191024-2-R01Labourer - General10650 | Corbiere and Sons Contracting30120191024-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 301 | 20191024-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-24 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting30120191024-2-R01L.O.A.2420 | Corbiere and Sons Contracting30120191024-2-R01L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 302 | 20191024-3 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR | 180 | 0 |  |  | 2280 | 296.4 | 2576.4 | 2019-10-24 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and cutting towers A013 to A014, Skidder tower A022 |  |  | A013, A014, A022 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting30220191024-3Feller Buncher9.52280 | Corbiere and Sons Contracting30220191024-3Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 302 | 20191024-3 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR | 128.25 | 0 |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-24 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and cutting towers A013 to A014, Skidder tower A022 |  |  | A013, A014, A022 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting30220191024-3Skidder 9.51624.5 | Corbiere and Sons Contracting30220191024-3Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 302 | 20191024-3 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-10-24 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and cutting towers A013 to A014, Skidder tower A022 |  |  | A013, A014, A022 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting30220191024-3Light Truck - Pick up30900 | Corbiere and Sons Contracting30220191024-3Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 302 | 20191024-3 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-10-24 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and cutting towers A013 to A014, Skidder tower A022 |  |  | A013, A014, A022 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting30220191024-3Foreman4380 | Corbiere and Sons Contracting30220191024-3Foreman4380Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 302 | 20191024-3 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-24 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and cutting towers A013 to A014, Skidder tower A022 |  |  | A013, A014, A022 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting30220191024-3Operator - Principle221980 | Corbiere and Sons Contracting30220191024-3Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 302 | 20191024-3 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-24 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and cutting towers A013 to A014, Skidder tower A022 |  |  | A013, A014, A022 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting30220191024-3L.O.A.3630 | Corbiere and Sons Contracting30220191024-3L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 303 | 20191024-4 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR | 180 | 0 |  |  | 2280 | 296.4 | 2576.4 | 2019-10-24 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Tower A012 - A013 |  |  | A012 - A013 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting30320191024-4Feller Buncher9.52280 | Corbiere and Sons Contracting30320191024-4Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 303 | 20191024-4 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR | 128.25 | 0 |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-24 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Tower A012 - A013 |  |  | A012 - A013 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting30320191024-4Skidder 9.51624.5 | Corbiere and Sons Contracting30320191024-4Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 303 | 20191024-4 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-10-24 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Tower A012 - A013 |  |  | A012 - A013 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting30320191024-4Light Truck - Pick up20600 | Corbiere and Sons Contracting30320191024-4Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 303 | 20191024-4 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-24 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Tower A012 - A013 |  |  | A012 - A013 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting30320191024-4Operator - Principle221980 | Corbiere and Sons Contracting30320191024-4Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 303 | 20191024-4 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-24 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Tower A012 - A013 |  |  | A012 - A013 | 0 |  |  | 34 | 43792 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting30320191024-4L.O.A.2420 | Corbiere and Sons Contracting30320191024-4L.O.A.2420Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 304 | 20191024-5-R02 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 18 | HR | 180 | 0 |  |  | 4320 | 561.6 | 4881.6 | 2019-10-24 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Error on LOA Count on LEM - RR-Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing from A048 Eastward - Mulcher broke down, no hours. |  |  | A048 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting30420191024-5-R02Feller Buncher184320 | Corbiere and Sons Contracting30420191024-5-R02Feller Buncher184320Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 304 | 20191024-5-R02 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-10-24 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Error on LOA Count on LEM - RR-Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing from A048 Eastward - Mulcher broke down, no hours. |  |  | A048 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting30420191024-5-R02Skidder 91539 | Corbiere and Sons Contracting30420191024-5-R02Skidder 91539Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 304 | 20191024-5-R02 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-10-24 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Error on LOA Count on LEM - RR-Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing from A048 Eastward - Mulcher broke down, no hours. |  |  | A048 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting30420191024-5-R02Light Truck - Pick up20600 | Corbiere and Sons Contracting30420191024-5-R02Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 304 | 20191024-5-R02 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 37 | HR |  |  |  | 0 | 3330 | 432.9 | 3762.9 | 2019-10-24 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Error on LOA Count on LEM - RR-Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing from A048 Eastward - Mulcher broke down, no hours. |  |  | A048 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting30420191024-5-R02Operator - Principle373330 | Corbiere and Sons Contracting30420191024-5-R02Operator - Principle373330Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3330 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 304 | 20191024-5-R02 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-24 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Error on LOA Count on LEM - RR-Corrected Nov 16, 19 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearing from A048 Eastward - Mulcher broke down, no hours. |  |  | A048 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting30420191024-5-R02L.O.A.3630 | Corbiere and Sons Contracting30420191024-5-R02L.O.A.3630Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 305 | 20191024-6 | 53520101 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-10-24 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting30520191024-6Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting30520191024-6Grinder - 4710 Peterson or equal95011.2Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 305 | 20191024-6 | 53520101 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-10-24 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting30520191024-6Log Loader91377 | Corbiere and Sons Contracting30520191024-6Log Loader91377Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 305 | 20191024-6 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-24 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting30520191024-6Light Truck - Pick up10300 | Corbiere and Sons Contracting30520191024-6Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 305 | 20191024-6 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-24 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting30520191024-6Operator - Principle11990 | Corbiere and Sons Contracting30520191024-6Operator - Principle11990Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 305 | 20191024-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-24 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting30520191024-6L.O.A.1210 | Corbiere and Sons Contracting30520191024-6L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 313 | 20191025-03 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR | 180 | 0 |  |  | 2280 | 296.4 | 2576.4 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Feller buncher cutting from tower A014 to A016, grapple skidder clearing tower A021. |  |  | A014, A016, A021 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting31320191025-03Feller Buncher9.52280 | Corbiere and Sons Contracting31320191025-03Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 313 | 20191025-03 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR | 128.25 | 0 |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Feller buncher cutting from tower A014 to A016, grapple skidder clearing tower A021. |  |  | A014, A016, A021 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting31320191025-03Skidder 9.51624.5 | Corbiere and Sons Contracting31320191025-03Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 313 | 20191025-03 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Feller buncher cutting from tower A014 to A016, grapple skidder clearing tower A021. |  |  | A014, A016, A021 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting31320191025-03Light Truck - Pick up30900 | Corbiere and Sons Contracting31320191025-03Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 313 | 20191025-03 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Feller buncher cutting from tower A014 to A016, grapple skidder clearing tower A021. |  |  | A014, A016, A021 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting31320191025-03Foreman4380 | Corbiere and Sons Contracting31320191025-03Foreman4380Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 313 | 20191025-03 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Feller buncher cutting from tower A014 to A016, grapple skidder clearing tower A021. |  |  | A014, A016, A021 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting31320191025-03Operator - Principle221980 | Corbiere and Sons Contracting31320191025-03Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 313 | 20191025-03 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Feller buncher cutting from tower A014 to A016, grapple skidder clearing tower A021. |  |  | A014, A016, A021 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting31320191025-03L.O.A.3630 | Corbiere and Sons Contracting31320191025-03L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 314 | 20191025-04-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Tower A012-A013 |  |  | A012-A013 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting31420191025-04-R01Feller Buncher92160 | Corbiere and Sons Contracting31420191025-04-R01Feller Buncher92160Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 314 | 20191025-04-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Tower A012-A013 |  |  | A012-A013 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting31420191025-04-R01Skidder 91539 | Corbiere and Sons Contracting31420191025-04-R01Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 314 | 20191025-04-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Tower A012-A013 |  |  | A012-A013 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting31420191025-04-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting31420191025-04-R01Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 314 | 20191025-04-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Tower A012-A013 |  |  | A012-A013 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting31420191025-04-R01Operator - Principle221980 | Corbiere and Sons Contracting31420191025-04-R01Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 314 | 20191025-04-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Tower A012-A013 |  |  | A012-A013 | 0 |  |  | 17 | 43812 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting31420191025-04-R01L.O.A.2420 | Corbiere and Sons Contracting31420191025-04-R01L.O.A.2420Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 315 | 20191025-05-R01 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-10-25 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | A047 going Eastward |  |  | A047 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting31520191025-05-R01Mulcher91845 | Corbiere and Sons Contracting31520191025-05-R01Mulcher91845Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 315 | 20191025-05-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-25 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | A047 going Eastward |  |  | A047 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting31520191025-05-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting31520191025-05-R01Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 315 | 20191025-05-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-25 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | A047 going Eastward |  |  | A047 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting31520191025-05-R01Operator - Principle11990 | Corbiere and Sons Contracting31520191025-05-R01Operator - Principle11990Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 315 | 20191025-05-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-25 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | A047 going Eastward |  |  | A047 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting31520191025-05-R01L.O.A.1210 | Corbiere and Sons Contracting31520191025-05-R01L.O.A.1210Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 316 | 20191025-06-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 18 | HR | 180 | 0 |  |  | 4320 | 561.6 | 4881.6 | 2019-10-25 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearingat tower A050 going Eastward - Moved and fixed landowners gate at A048 |  |  | A050, A048 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting31620191025-06-R01Feller Buncher184320 | Corbiere and Sons Contracting31620191025-06-R01Feller Buncher184320Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 316 | 20191025-06-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-10-25 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearingat tower A050 going Eastward - Moved and fixed landowners gate at A048 |  |  | A050, A048 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting31620191025-06-R01Skidder 91539 | Corbiere and Sons Contracting31620191025-06-R01Skidder 91539Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 316 | 20191025-06-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-25 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearingat tower A050 going Eastward - Moved and fixed landowners gate at A048 |  |  | A050, A048 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting31620191025-06-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting31620191025-06-R01Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 316 | 20191025-06-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-10-25 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearingat tower A050 going Eastward - Moved and fixed landowners gate at A048 |  |  | A050, A048 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting31620191025-06-R01Operator - Principle332970 | Corbiere and Sons Contracting31620191025-06-R01Operator - Principle332970Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 316 | 20191025-06-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-25 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Clearingat tower A050 going Eastward - Moved and fixed landowners gate at A048 |  |  | A050, A048 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting31620191025-06-R01L.O.A.2420 | Corbiere and Sons Contracting31620191025-06-R01L.O.A.2420Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 311 | 20191025-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting31120191025-1Light Truck - Pick up601800 | Corbiere and Sons Contracting31120191025-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 311 | 20191025-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting31120191025-1Project Manager121320 | Corbiere and Sons Contracting31120191025-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 311 | 20191025-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting31120191025-1Superintendent121260 | Corbiere and Sons Contracting31120191025-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 311 | 20191025-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 13 | HR |  |  |  | 0 | 1040 | 135.2 | 1175.2 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting31120191025-1Project Coordinator131040 | Corbiere and Sons Contracting31120191025-1Project Coordinator131040Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1040 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 311 | 20191025-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting31120191025-1Construction Coordinator12960 | Corbiere and Sons Contracting31120191025-1Construction Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 311 | 20191025-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting31120191025-1Safety Advisor121020 | Corbiere and Sons Contracting31120191025-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 311 | 20191025-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 11 | HR |  |  |  | 0 | 770 | 100.1 | 870.1 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting31120191025-1Project Controls11770 | Corbiere and Sons Contracting31120191025-1Project Controls11770Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 311 | 20191025-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting31120191025-1L.O.A.61260 | Corbiere and Sons Contracting31120191025-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 312 | 20191025-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-10-25 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting31220191025-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting31220191025-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 312 | 20191025-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-10-25 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting31220191025-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting31220191025-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 312 | 20191025-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-10-25 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting31220191025-2-R01Operator - Principle121080 | Corbiere and Sons Contracting31220191025-2-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 312 | 20191025-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-10-25 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting31220191025-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting31220191025-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 312 | 20191025-2-R01 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 11.5 | HR |  |  |  | 0 | 862.5 | 112.125 | 974.625 | 2019-10-25 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting31220191025-2-R01Labourer - Specialized11.5862.5 | Corbiere and Sons Contracting31220191025-2-R01Labourer - Specialized11.5862.5Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 312 | 20191025-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-25 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting31220191025-2-R01Labourer - General10650 | Corbiere and Sons Contracting31220191025-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 312 | 20191025-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-25 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting31220191025-2-R01L.O.A.2420 | Corbiere and Sons Contracting31220191025-2-R01L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 317 | 20191025-7 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material |  |  |  | 0 |  |  | 10 | 43793 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting31720191025-7Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting31720191025-7Grinder - 4710 Peterson or equal95011.2Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 317 | 20191025-7 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material |  |  |  | 0 |  |  | 10 | 43793 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting31720191025-7Log Loader91377 | Corbiere and Sons Contracting31720191025-7Log Loader91377Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 317 | 20191025-7 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material |  |  |  | 0 |  |  | 10 | 43793 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting31720191025-7Light Truck - Pick up10300 | Corbiere and Sons Contracting31720191025-7Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 317 | 20191025-7 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material |  |  |  | 0 |  |  | 10 | 43793 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting31720191025-7Operator - Principle11990 | Corbiere and Sons Contracting31720191025-7Operator - Principle11990Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 317 | 20191025-7 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-25 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material |  |  |  | 0 |  |  | 10 | 43793 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting31720191025-7L.O.A.1210 | Corbiere and Sons Contracting31720191025-7L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 326 | 20191026-04-R01 | 53520101 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-10-26 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Cleared up to A051 and a half then moved to A053 and started working Westward. |  |  | A051, A053 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting32620191026-04-R01Brusher91822.5 | Corbiere and Sons Contracting32620191026-04-R01Brusher91822.5Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 326 | 20191026-04-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 21 | HR | 180 | 0 |  |  | 5040 | 655.2 | 5695.2 | 2019-10-26 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Cleared up to A051 and a half then moved to A053 and started working Westward. |  |  | A051, A053 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting32620191026-04-R01Feller Buncher215040 | Corbiere and Sons Contracting32620191026-04-R01Feller Buncher215040Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5040 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 326 | 20191026-04-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-10-26 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Cleared up to A051 and a half then moved to A053 and started working Westward. |  |  | A051, A053 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting32620191026-04-R01Skidder 91539 | Corbiere and Sons Contracting32620191026-04-R01Skidder 91539Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 326 | 20191026-04-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-10-26 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Cleared up to A051 and a half then moved to A053 and started working Westward. |  |  | A051, A053 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting32620191026-04-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting32620191026-04-R01Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 326 | 20191026-04-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 48 | HR |  |  |  | 0 | 4320 | 561.6 | 4881.6 | 2019-10-26 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Cleared up to A051 and a half then moved to A053 and started working Westward. |  |  | A051, A053 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting32620191026-04-R01Operator - Principle484320 | Corbiere and Sons Contracting32620191026-04-R01Operator - Principle484320Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 326 | 20191026-04-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-10-26 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Cleared up to A051 and a half then moved to A053 and started working Westward. |  |  | A051, A053 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting32620191026-04-R01L.O.A.4840 | Corbiere and Sons Contracting32620191026-04-R01L.O.A.4840Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 323 | 20191026-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-10-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting32320191026-1Light Truck - Pick up601800 | Corbiere and Sons Contracting32320191026-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 323 | 20191026-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting32320191026-1Project Manager121320 | Corbiere and Sons Contracting32320191026-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 323 | 20191026-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting32320191026-1Superintendent121260 | Corbiere and Sons Contracting32320191026-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 323 | 20191026-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting32320191026-1Project Coordinator12960 | Corbiere and Sons Contracting32320191026-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 323 | 20191026-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting32320191026-1Construction Coordinator12960 | Corbiere and Sons Contracting32320191026-1Construction Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 323 | 20191026-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting32320191026-1Safety Advisor121020 | Corbiere and Sons Contracting32320191026-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 323 | 20191026-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-10-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting32320191026-1Project Controls12840 | Corbiere and Sons Contracting32320191026-1Project Controls12840Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 323 | 20191026-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting32320191026-1L.O.A.61260 | Corbiere and Sons Contracting32320191026-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 324 | 20191026-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-10-26 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting32420191026-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting32420191026-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 324 | 20191026-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-10-26 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting32420191026-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting32420191026-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 324 | 20191026-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-10-26 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting32420191026-2-R01Operator - Principle121080 | Corbiere and Sons Contracting32420191026-2-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 324 | 20191026-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-10-26 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting32420191026-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting32420191026-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 324 | 20191026-2-R01 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-10-26 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting32420191026-2-R01Labourer - Specialized11825 | Corbiere and Sons Contracting32420191026-2-R01Labourer - Specialized11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 324 | 20191026-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-26 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting32420191026-2-R01Labourer - General10650 | Corbiere and Sons Contracting32420191026-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 324 | 20191026-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-26 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting32420191026-2-R01L.O.A.2420 | Corbiere and Sons Contracting32420191026-2-R01L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 325 | 20191026-3 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-10-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and skidding at A016 |  |  | A016 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting32520191026-3Feller Buncher92160 | Corbiere and Sons Contracting32520191026-3Feller Buncher92160Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 325 | 20191026-3 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-10-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and skidding at A016 |  |  | A016 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting32520191026-3Skidder 91539 | Corbiere and Sons Contracting32520191026-3Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 325 | 20191026-3 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-10-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and skidding at A016 |  |  | A016 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting32520191026-3Light Truck - Pick up20600 | Corbiere and Sons Contracting32520191026-3Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 325 | 20191026-3 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and skidding at A016 |  |  | A016 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting32520191026-3Operator - Principle221980 | Corbiere and Sons Contracting32520191026-3Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 325 | 20191026-3 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and skidding at A016 |  |  | A016 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting32520191026-3L.O.A.2420 | Corbiere and Sons Contracting32520191026-3L.O.A.2420Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 327 | 20191026-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-10-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material |  |  | A024 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting32720191026-5Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting32720191026-5Grinder - 4710 Peterson or equal95011.2Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 327 | 20191026-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-10-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material |  |  | A024 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting32720191026-5Log Loader91377 | Corbiere and Sons Contracting32720191026-5Log Loader91377Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 327 | 20191026-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material |  |  | A024 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting32720191026-5Light Truck - Pick up10300 | Corbiere and Sons Contracting32720191026-5Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 327 | 20191026-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material |  |  | A024 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting32720191026-5Operator - Principle11990 | Corbiere and Sons Contracting32720191026-5Operator - Principle11990Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 327 | 20191026-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-26 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material |  |  | A024 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting32720191026-5L.O.A.1210 | Corbiere and Sons Contracting32720191026-5L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 334 | 20191027-02-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-10-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate on Loader JD: REVISED DK 11152019 Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting33420191027-02-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting33420191027-02-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 334 | 20191027-02-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-10-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate on Loader JD: REVISED DK 11152019 Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting33420191027-02-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting33420191027-02-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 334 | 20191027-02-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-10-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate on Loader JD: REVISED DK 11152019 Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting33420191027-02-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting33420191027-02-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 334 | 20191027-02-R01 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-10-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate on Loader JD: REVISED DK 11152019 Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting33420191027-02-R01Labourer - Specialized11825 | Corbiere and Sons Contracting33420191027-02-R01Labourer - Specialized11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 334 | 20191027-02-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate on Loader JD: REVISED DK 11152019 Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting33420191027-02-R01Labourer - General10650 | Corbiere and Sons Contracting33420191027-02-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 334 | 20191027-02-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate on Loader JD: REVISED DK 11152019 Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting33420191027-02-R01L.O.A.2420 | Corbiere and Sons Contracting33420191027-02-R01L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 335 | 20191027-03-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and skidding at A013 |  |  | A013 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting33520191027-03-R01Feller Buncher92160 | Corbiere and Sons Contracting33520191027-03-R01Feller Buncher92160Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 335 | 20191027-03-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and skidding at A013 |  |  | A013 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting33520191027-03-R01Skidder 91539 | Corbiere and Sons Contracting33520191027-03-R01Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 335 | 20191027-03-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and skidding at A013 |  |  | A013 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting33520191027-03-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting33520191027-03-R01Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 335 | 20191027-03-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and skidding at A013 |  |  | A013 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting33520191027-03-R01Operator - Principle221980 | Corbiere and Sons Contracting33520191027-03-R01Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 335 | 20191027-03-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and skidding at A013 |  |  | A013 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting33520191027-03-R01L.O.A.2420 | Corbiere and Sons Contracting33520191027-03-R01L.O.A.2420Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 336 | 20191027-04-R01 | 53520101 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-10-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Finished clearing at A053 West - Moved equipment to A054 |  |  | A053, A054 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting33620191027-04-R01Brusher91822.5 | Corbiere and Sons Contracting33620191027-04-R01Brusher91822.5Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 336 | 20191027-04-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 18 | HR | 180 | 0 |  |  | 4320 | 561.6 | 4881.6 | 2019-10-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Finished clearing at A053 West - Moved equipment to A054 |  |  | A053, A054 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting33620191027-04-R01Feller Buncher184320 | Corbiere and Sons Contracting33620191027-04-R01Feller Buncher184320Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 336 | 20191027-04-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-10-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Finished clearing at A053 West - Moved equipment to A054 |  |  | A053, A054 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting33620191027-04-R01Skidder 91539 | Corbiere and Sons Contracting33620191027-04-R01Skidder 91539Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 336 | 20191027-04-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-10-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Finished clearing at A053 West - Moved equipment to A054 |  |  | A053, A054 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting33620191027-04-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting33620191027-04-R01Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 336 | 20191027-04-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-10-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Finished clearing at A053 West - Moved equipment to A054 |  |  | A053, A054 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting33620191027-04-R01Operator - Principle443960 | Corbiere and Sons Contracting33620191027-04-R01Operator - Principle443960Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 336 | 20191027-04-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-27 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Finished clearing at A053 West - Moved equipment to A054 |  |  | A053, A054 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting33620191027-04-R01L.O.A.3630 | Corbiere and Sons Contracting33620191027-04-R01L.O.A.3630Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 340 | 20191027-08-R01 | 53510112 | Access | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Excavator 36 ton has incorrect rate on LEM. |  |  |  |  | Gravelling at McGregor Rd. |  |  | segment 1 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34020191027-08-R01Dozer D6 or equal91215 | Corbiere and Sons Contracting34020191027-08-R01Dozer D6 or equal91215Inv#002-R01 | [5 empty] | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 340 | 20191027-08-R01 | 53510112 | Access | 0 | Excavator - 30 ton | 139.5 | 18 | HR | 104.63 | 0 |  |  | 2511 | 326.43 | 2837.43 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Excavator 36 ton has incorrect rate on LEM. |  |  |  |  | Gravelling at McGregor Rd. |  |  | segment 1 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34020191027-08-R01Excavator - 30 ton182511 | Corbiere and Sons Contracting34020191027-08-R01Excavator - 30 ton182511Inv#002-R01 | [5 empty] | 1 | 2511 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 340 | 20191027-08-R01 | 53510112 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Excavator 36 ton has incorrect rate on LEM. |  |  |  |  | Gravelling at McGregor Rd. |  |  | segment 1 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34020191027-08-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting34020191027-08-R01Light Truck - Pick up10300Inv#002-R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 340 | 20191027-08-R01 | 53510112 | Access | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Excavator 36 ton has incorrect rate on LEM. |  |  |  |  | Gravelling at McGregor Rd. |  |  | segment 1 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34020191027-08-R01Operator - Principle332970 | Corbiere and Sons Contracting34020191027-08-R01Operator - Principle332970Inv#002-R01 | [5 empty] | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 340 | 20191027-08-R01 | 53510112 | Access | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Excavator 36 ton has incorrect rate on LEM. |  |  |  |  | Gravelling at McGregor Rd. |  |  | segment 1 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34020191027-08-R01Labourer - General11715 | Corbiere and Sons Contracting34020191027-08-R01Labourer - General11715Inv#002-R01 | [5 empty] | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 340 | 20191027-08-R01 | 53510112 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Excavator 36 ton has incorrect rate on LEM. |  |  |  |  | Gravelling at McGregor Rd. |  |  | segment 1 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34020191027-08-R01L.O.A.3630 | Corbiere and Sons Contracting34020191027-08-R01L.O.A.3630Inv#002-R01 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 333 | 20191027-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting33320191027-1Light Truck - Pick up601800 | Corbiere and Sons Contracting33320191027-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 333 | 20191027-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting33320191027-1Project Manager121320 | Corbiere and Sons Contracting33320191027-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 333 | 20191027-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting33320191027-1Superintendent121260 | Corbiere and Sons Contracting33320191027-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 333 | 20191027-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 10 | HR |  |  |  | 0 | 800 | 104 | 904 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting33320191027-1Project Coordinator10800 | Corbiere and Sons Contracting33320191027-1Project Coordinator10800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 333 | 20191027-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting33320191027-1Construction Coordinator12960 | Corbiere and Sons Contracting33320191027-1Construction Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 333 | 20191027-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting33320191027-1Safety Advisor121020 | Corbiere and Sons Contracting33320191027-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 333 | 20191027-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 4 | HR |  |  |  | 0 | 280 | 36.4 | 316.4 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting33320191027-1Project Controls4280 | Corbiere and Sons Contracting33320191027-1Project Controls4280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 333 | 20191027-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting33320191027-1L.O.A.61260 | Corbiere and Sons Contracting33320191027-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 337 | 20191027-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material |  |  |  | 0 |  |  | 10 | 43793 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting33720191027-5Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting33720191027-5Grinder - 4710 Peterson or equal95011.2Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 337 | 20191027-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material |  |  |  | 0 |  |  | 10 | 43793 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting33720191027-5Log Loader91377 | Corbiere and Sons Contracting33720191027-5Log Loader91377Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 337 | 20191027-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material |  |  |  | 0 |  |  | 10 | 43793 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting33720191027-5Light Truck - Pick up10300 | Corbiere and Sons Contracting33720191027-5Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 337 | 20191027-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material |  |  |  | 0 |  |  | 10 | 43793 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting33720191027-5Operator - Principle11990 | Corbiere and Sons Contracting33720191027-5Operator - Principle11990Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 337 | 20191027-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-27 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material |  |  |  | 0 |  |  | 10 | 43793 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting33720191027-5L.O.A.1210 | Corbiere and Sons Contracting33720191027-5L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 345 | 20191028-02-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-10-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for Loader JD on LEM - REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting34520191028-02-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting34520191028-02-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 345 | 20191028-02-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-10-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for Loader JD on LEM - REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting34520191028-02-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting34520191028-02-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 345 | 20191028-02-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 8 | HR |  |  | 70 | 0 | 600 | 78 | 678 | 2019-10-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for Loader JD on LEM - REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting34520191028-02-R01Operator - Intermdiate8600 | Corbiere and Sons Contracting34520191028-02-R01Operator - Intermdiate8600Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 345 | 20191028-02-R01 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 8 | HR |  |  |  | 0 | 600 | 78 | 678 | 2019-10-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for Loader JD on LEM - REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting34520191028-02-R01Labourer - Specialized8600 | Corbiere and Sons Contracting34520191028-02-R01Labourer - Specialized8600Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 345 | 20191028-02-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for Loader JD on LEM - REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting34520191028-02-R01Labourer - General10650 | Corbiere and Sons Contracting34520191028-02-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 345 | 20191028-02-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-28 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for Loader JD on LEM - REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting34520191028-02-R01L.O.A.2420 | Corbiere and Sons Contracting34520191028-02-R01L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 347 | 20191028-04 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR | 180 | 0 |  |  | 2280 | 296.4 | 2576.4 | 2019-10-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing towers - feller buncher floated from McGregor road to Eldorado Road, cut tower A058. Skidder started at Tower A021, floated to tower A058. |  |  | A058, A021 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34720191028-04Feller Buncher9.52280 | Corbiere and Sons Contracting34720191028-04Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 347 | 20191028-04 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR | 128.25 | 0 |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing towers - feller buncher floated from McGregor road to Eldorado Road, cut tower A058. Skidder started at Tower A021, floated to tower A058. |  |  | A058, A021 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34720191028-04Skidder 9.51624.5 | Corbiere and Sons Contracting34720191028-04Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 347 | 20191028-04 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-10-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing towers - feller buncher floated from McGregor road to Eldorado Road, cut tower A058. Skidder started at Tower A021, floated to tower A058. |  |  | A058, A021 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34720191028-04Light Truck - Pick up30900 | Corbiere and Sons Contracting34720191028-04Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 347 | 20191028-04 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-10-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing towers - feller buncher floated from McGregor road to Eldorado Road, cut tower A058. Skidder started at Tower A021, floated to tower A058. |  |  | A058, A021 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34720191028-04Foreman4380 | Corbiere and Sons Contracting34720191028-04Foreman4380Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 347 | 20191028-04 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing towers - feller buncher floated from McGregor road to Eldorado Road, cut tower A058. Skidder started at Tower A021, floated to tower A058. |  |  | A058, A021 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34720191028-04Operator - Principle221980 | Corbiere and Sons Contracting34720191028-04Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 347 | 20191028-04 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing towers - feller buncher floated from McGregor road to Eldorado Road, cut tower A058. Skidder started at Tower A021, floated to tower A058. |  |  | A058, A021 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34720191028-04L.O.A.3630 | Corbiere and Sons Contracting34720191028-04L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 348 | 20191028-05-R01 | 53520101 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-10-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing around archeological site at tower A053 and finish clearing and cutting at Tower A054. |  |  | A053, A054 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34820191028-05-R01Brusher91822.5 | Corbiere and Sons Contracting34820191028-05-R01Brusher91822.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 348 | 20191028-05-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 18 | HR | 180 | 0 |  |  | 4320 | 561.6 | 4881.6 | 2019-10-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing around archeological site at tower A053 and finish clearing and cutting at Tower A054. |  |  | A053, A054 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34820191028-05-R01Feller Buncher184320 | Corbiere and Sons Contracting34820191028-05-R01Feller Buncher184320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 348 | 20191028-05-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-10-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing around archeological site at tower A053 and finish clearing and cutting at Tower A054. |  |  | A053, A054 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34820191028-05-R01Skidder 91539 | Corbiere and Sons Contracting34820191028-05-R01Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 348 | 20191028-05-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-10-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing around archeological site at tower A053 and finish clearing and cutting at Tower A054. |  |  | A053, A054 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34820191028-05-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting34820191028-05-R01Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 348 | 20191028-05-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-10-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing around archeological site at tower A053 and finish clearing and cutting at Tower A054. |  |  | A053, A054 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34820191028-05-R01Operator - Principle443960 | Corbiere and Sons Contracting34820191028-05-R01Operator - Principle443960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 348 | 20191028-05-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing around archeological site at tower A053 and finish clearing and cutting at Tower A054. |  |  | A053, A054 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34820191028-05-R01L.O.A.3630 | Corbiere and Sons Contracting34820191028-05-R01L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 774 | 20191028-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting77420191028-1Light Truck - Pick up601800 | Corbiere and Sons Contracting77420191028-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 774 | 20191028-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting77420191028-1Project Manager121320 | Corbiere and Sons Contracting77420191028-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 774 | 20191028-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting77420191028-1Superintendent121260 | Corbiere and Sons Contracting77420191028-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 774 | 20191028-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 13 | HR |  |  |  | 0 | 1040 | 135.2 | 1175.2 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting77420191028-1Project Coordinator131040 | Corbiere and Sons Contracting77420191028-1Project Coordinator131040Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1040 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 774 | 20191028-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting77420191028-1Construction Coordinator12960 | Corbiere and Sons Contracting77420191028-1Construction Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 774 | 20191028-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting77420191028-1Safety Advisor121020 | Corbiere and Sons Contracting77420191028-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 774 | 20191028-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 10 | HR |  |  |  | 0 | 700 | 91 | 791 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting77420191028-1Project Controls10700 | Corbiere and Sons Contracting77420191028-1Project Controls10700Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 774 | 20191028-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting77420191028-1L.O.A.61260 | Corbiere and Sons Contracting77420191028-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 346 | 20191028-3-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-10-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and skidding at A013 |  |  | A013 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34620191028-3-R01Feller Buncher92160 | Corbiere and Sons Contracting34620191028-3-R01Feller Buncher92160Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 346 | 20191028-3-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-10-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and skidding at A013 |  |  | A013 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34620191028-3-R01Skidder 91539 | Corbiere and Sons Contracting34620191028-3-R01Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 346 | 20191028-3-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-10-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and skidding at A013 |  |  | A013 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34620191028-3-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting34620191028-3-R01Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 346 | 20191028-3-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and skidding at A013 |  |  | A013 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34620191028-3-R01Operator - Principle221980 | Corbiere and Sons Contracting34620191028-3-R01Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 346 | 20191028-3-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing and skidding at A013 |  |  | A013 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting34620191028-3-R01L.O.A.2420 | Corbiere and Sons Contracting34620191028-3-R01L.O.A.2420Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 349 | 20191028-6 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-10-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 |  |  | 10 | 43793 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting34920191028-6Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting34920191028-6Grinder - 4710 Peterson or equal95011.2Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 349 | 20191028-6 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-10-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 |  |  | 10 | 43793 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting34920191028-6Log Loader91377 | Corbiere and Sons Contracting34920191028-6Log Loader91377Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 349 | 20191028-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 |  |  | 10 | 43793 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting34920191028-6Light Truck - Pick up10300 | Corbiere and Sons Contracting34920191028-6Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 349 | 20191028-6 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 |  |  | 10 | 43793 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting34920191028-6Operator - Principle11990 | Corbiere and Sons Contracting34920191028-6Operator - Principle11990Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 349 | 20191028-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-28 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding Material |  |  |  | 0 |  |  | 10 | 43793 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting34920191028-6L.O.A.1210 | Corbiere and Sons Contracting34920191028-6L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 356 | 20191029-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-10-29 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting35620191029-1Light Truck - Pick up601800 | Corbiere and Sons Contracting35620191029-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 356 | 20191029-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-29 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting35620191029-1Project Manager121320 | Corbiere and Sons Contracting35620191029-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 356 | 20191029-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-29 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting35620191029-1Superintendent121260 | Corbiere and Sons Contracting35620191029-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 356 | 20191029-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-29 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting35620191029-1Project Coordinator12960 | Corbiere and Sons Contracting35620191029-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 356 | 20191029-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-29 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting35620191029-1Construction Coordinator12960 | Corbiere and Sons Contracting35620191029-1Construction Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 356 | 20191029-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-29 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting35620191029-1Safety Advisor121020 | Corbiere and Sons Contracting35620191029-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 356 | 20191029-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-10-29 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting35620191029-1Project Controls12840 | Corbiere and Sons Contracting35620191029-1Project Controls12840Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 356 | 20191029-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-29 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting35620191029-1L.O.A.61260 | Corbiere and Sons Contracting35620191029-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 357 | 20191029-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-10-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD has incorrect rate on LEM. - REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - Moved feller buncher and skidder to A058. Floated CORFB001 back to yard for repairs. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting35720191029-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting35720191029-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 357 | 20191029-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-10-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD has incorrect rate on LEM. - REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - Moved feller buncher and skidder to A058. Floated CORFB001 back to yard for repairs. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting35720191029-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting35720191029-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 357 | 20191029-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-10-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD has incorrect rate on LEM. - REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - Moved feller buncher and skidder to A058. Floated CORFB001 back to yard for repairs. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting35720191029-2-R01Operator - Principle121080 | Corbiere and Sons Contracting35720191029-2-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 357 | 20191029-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-10-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD has incorrect rate on LEM. - REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - Moved feller buncher and skidder to A058. Floated CORFB001 back to yard for repairs. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting35720191029-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting35720191029-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 357 | 20191029-2-R01 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 24 | HR |  |  |  | 0 | 1800 | 234 | 2034 | 2019-10-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD has incorrect rate on LEM. - REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - Moved feller buncher and skidder to A058. Floated CORFB001 back to yard for repairs. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting35720191029-2-R01Labourer - Specialized241800 | Corbiere and Sons Contracting35720191029-2-R01Labourer - Specialized241800Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 357 | 20191029-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD has incorrect rate on LEM. - REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - Moved feller buncher and skidder to A058. Floated CORFB001 back to yard for repairs. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting35720191029-2-R01Labourer - General10650 | Corbiere and Sons Contracting35720191029-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 357 | 20191029-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-29 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD has incorrect rate on LEM. - REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - Moved feller buncher and skidder to A058. Floated CORFB001 back to yard for repairs. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting35720191029-2-R01L.O.A.3630 | Corbiere and Sons Contracting35720191029-2-R01L.O.A.3630Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 358 | 20191029-3-R1 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 6.5 | HR | 180 |  |  |  | 1560 | 202.8 | 1762.8 | 2019-10-29 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing tower A058 to Cross Road before tower A057. 2pm called into Dorion Yard by Valard for meeting. |  |  | A058, A057 | 0 |  |  | 40 | 43967 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting35820191029-3-R1Feller Buncher6.51560 | Corbiere and Sons Contracting35820191029-3-R1Feller Buncher6.51560INV#027 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 358 | 20191029-3-R1 | 53520101 | Clearing | 0 | Skidder | 171 | 6.5 | HR | 128.25 |  |  |  | 1111.5 | 144.495 | 1255.995 | 2019-10-29 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing tower A058 to Cross Road before tower A057. 2pm called into Dorion Yard by Valard for meeting. |  |  | A058, A057 | 0 |  |  | 40 | 43967 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting35820191029-3-R1Skidder 6.51111.5 | Corbiere and Sons Contracting35820191029-3-R1Skidder 6.51111.5INV#027 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1111.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 358 | 20191029-3-R1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-10-29 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing tower A058 to Cross Road before tower A057. 2pm called into Dorion Yard by Valard for meeting. |  |  | A058, A057 | 0 |  |  | 40 | 43967 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting35820191029-3-R1Light Truck - Pick up30900 | Corbiere and Sons Contracting35820191029-3-R1Light Truck - Pick up30900INV#027 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 358 | 20191029-3-R1 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-10-29 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing tower A058 to Cross Road before tower A057. 2pm called into Dorion Yard by Valard for meeting. |  |  | A058, A057 | 0 |  |  | 40 | 43967 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting35820191029-3-R1Foreman4380 | Corbiere and Sons Contracting35820191029-3-R1Foreman4380INV#027 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 358 | 20191029-3-R1 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-29 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing tower A058 to Cross Road before tower A057. 2pm called into Dorion Yard by Valard for meeting. |  |  | A058, A057 | 0 |  |  | 40 | 43967 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting35820191029-3-R1Operator - Principle221980 | Corbiere and Sons Contracting35820191029-3-R1Operator - Principle221980INV#027 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 358 | 20191029-3-R1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-29 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing tower A058 to Cross Road before tower A057. 2pm called into Dorion Yard by Valard for meeting. |  |  | A058, A057 | 0 |  |  | 40 | 43967 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting35820191029-3-R1L.O.A.2420 | Corbiere and Sons Contracting35820191029-3-R1L.O.A.2420INV#027 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 359 | 20191029-4-R1 | 53520101 | Clearing | 0 | Brusher | 202.5 | 6 | HR | 151.88 | 3 |  |  | 1670.64 | 217.1832 | 1887.8232 | 2019-10-29 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing between A048-A059 - Rodney walked equipment for float moves. Safety shutdown after 2pm. |  |  | A048-A059 | 0 |  |  | 35 | 43843 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting35920191029-4-R1Brusher61670.64 | Corbiere and Sons Contracting35920191029-4-R1Brusher61670.64Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1670.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 359 | 20191029-4-R1 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 18 | HR | 180 | 9 |  |  | 5940 | 772.2 | 6712.2 | 2019-10-29 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing between A048-A059 - Rodney walked equipment for float moves. Safety shutdown after 2pm. |  |  | A048-A059 | 0 |  |  | 35 | 43843 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting35920191029-4-R1Feller Buncher185940 | Corbiere and Sons Contracting35920191029-4-R1Feller Buncher185940Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5940 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 359 | 20191029-4-R1 | 53520101 | Clearing | 0 | Mulcher | 205 | 6 | HR | 153.75 | 3 |  |  | 1691.25 | 219.8625 | 1911.1125 | 2019-10-29 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing between A048-A059 - Rodney walked equipment for float moves. Safety shutdown after 2pm. |  |  | A048-A059 | 0 |  |  | 35 | 43843 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting35920191029-4-R1Mulcher61691.25 | Corbiere and Sons Contracting35920191029-4-R1Mulcher61691.25Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1691.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 359 | 20191029-4-R1 | 53520101 | Clearing | 0 | Skidder | 171 | 12 | HR | 128.25 | 6 |  |  | 2821.5 | 366.795 | 3188.295 | 2019-10-29 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing between A048-A059 - Rodney walked equipment for float moves. Safety shutdown after 2pm. |  |  | A048-A059 | 0 |  |  | 35 | 43843 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting35920191029-4-R1Skidder 122821.5 | Corbiere and Sons Contracting35920191029-4-R1Skidder 122821.5Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2821.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 359 | 20191029-4-R1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-10-29 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing between A048-A059 - Rodney walked equipment for float moves. Safety shutdown after 2pm. |  |  | A048-A059 | 0 |  |  | 35 | 43843 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting35920191029-4-R1Light Truck - Pick up30900 | Corbiere and Sons Contracting35920191029-4-R1Light Truck - Pick up30900Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 359 | 20191029-4-R1 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 66 | HR |  |  |  | 0 | 5940 | 772.2 | 6712.2 | 2019-10-29 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing between A048-A059 - Rodney walked equipment for float moves. Safety shutdown after 2pm. |  |  | A048-A059 | 0 |  |  | 35 | 43843 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting35920191029-4-R1Operator - Principle665940 | Corbiere and Sons Contracting35920191029-4-R1Operator - Principle665940Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5940 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 359 | 20191029-4-R1 | 53520101 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-10-29 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing between A048-A059 - Rodney walked equipment for float moves. Safety shutdown after 2pm. |  |  | A048-A059 | 0 |  |  | 35 | 43843 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting35920191029-4-R1Labourer - General11715 | Corbiere and Sons Contracting35920191029-4-R1Labourer - General11715Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 359 | 20191029-4-R1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-29 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing between A048-A059 - Rodney walked equipment for float moves. Safety shutdown after 2pm. |  |  | A048-A059 | 0 |  |  | 35 | 43843 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting35920191029-4-R1L.O.A.61260 | Corbiere and Sons Contracting35920191029-4-R1L.O.A.61260Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 360 | 20191029-5-R1 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 6 | HR | 417.6 | 3 |  |  | 4593.6 | 597.168 | 5190.768 | 2019-10-29 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material |  |  |  | 0 |  |  | 35 | 43843 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting36020191029-5-R1Grinder - 4710 Peterson or equal64593.6 | Corbiere and Sons Contracting36020191029-5-R1Grinder - 4710 Peterson or equal64593.6Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4593.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 360 | 20191029-5-R1 | 53520102 | Clearing | 0 | Log Loader | 153 | 6 | HR | 114.75 | 3 |  |  | 1262.25 | 164.0925 | 1426.3425 | 2019-10-29 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material |  |  |  | 0 |  |  | 35 | 43843 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting36020191029-5-R1Log Loader61262.25 | Corbiere and Sons Contracting36020191029-5-R1Log Loader61262.25Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1262.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 360 | 20191029-5-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-29 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material |  |  |  | 0 |  |  | 35 | 43843 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting36020191029-5-R1Light Truck - Pick up10300 | Corbiere and Sons Contracting36020191029-5-R1Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 360 | 20191029-5-R1 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-29 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material |  |  |  | 0 |  |  | 35 | 43843 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting36020191029-5-R1Operator - Principle11990 | Corbiere and Sons Contracting36020191029-5-R1Operator - Principle11990Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 360 | 20191029-5-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-29 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material |  |  |  | 0 |  |  | 35 | 43843 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting36020191029-5-R1L.O.A.1210 | Corbiere and Sons Contracting36020191029-5-R1L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 369 | 20191030-03 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR | 180 | 0 |  |  | 2280 | 296.4 | 2576.4 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing tower A057 then start tower A056 back towards tower A057 and toward tower A055. |  |  | A057, A056, A055 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting36920191030-03Feller Buncher9.52280 | Corbiere and Sons Contracting36920191030-03Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 369 | 20191030-03 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR | 128.25 | 0 |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing tower A057 then start tower A056 back towards tower A057 and toward tower A055. |  |  | A057, A056, A055 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting36920191030-03Skidder 9.51624.5 | Corbiere and Sons Contracting36920191030-03Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 369 | 20191030-03 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing tower A057 then start tower A056 back towards tower A057 and toward tower A055. |  |  | A057, A056, A055 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting36920191030-03Light Truck - Pick up30900 | Corbiere and Sons Contracting36920191030-03Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 369 | 20191030-03 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing tower A057 then start tower A056 back towards tower A057 and toward tower A055. |  |  | A057, A056, A055 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting36920191030-03Foreman4380 | Corbiere and Sons Contracting36920191030-03Foreman4380Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 369 | 20191030-03 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing tower A057 then start tower A056 back towards tower A057 and toward tower A055. |  |  | A057, A056, A055 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting36920191030-03Operator - Principle221980 | Corbiere and Sons Contracting36920191030-03Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 369 | 20191030-03 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing tower A057 then start tower A056 back towards tower A057 and toward tower A055. |  |  | A057, A056, A055 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting36920191030-03L.O.A.3630 | Corbiere and Sons Contracting36920191030-03L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 367 | 20191030-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting36720191030-1Light Truck - Pick up601800 | Corbiere and Sons Contracting36720191030-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 367 | 20191030-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting36720191030-1Project Manager121320 | Corbiere and Sons Contracting36720191030-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 367 | 20191030-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting36720191030-1Superintendent121260 | Corbiere and Sons Contracting36720191030-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 367 | 20191030-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting36720191030-1Project Coordinator12960 | Corbiere and Sons Contracting36720191030-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 367 | 20191030-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting36720191030-1Construction Coordinator12960 | Corbiere and Sons Contracting36720191030-1Construction Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 367 | 20191030-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting36720191030-1Safety Advisor121020 | Corbiere and Sons Contracting36720191030-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 367 | 20191030-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting36720191030-1Project Controls12840 | Corbiere and Sons Contracting36720191030-1Project Controls12840Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 367 | 20191030-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting36720191030-1L.O.A.61260 | Corbiere and Sons Contracting36720191030-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 368 | 20191030-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-10-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 has incorrect rate REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - moved mulcher to MacGregor West, grinder , 1Ex to Mack West. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting36820191030-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting36820191030-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 368 | 20191030-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-10-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 has incorrect rate REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - moved mulcher to MacGregor West, grinder , 1Ex to Mack West. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting36820191030-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting36820191030-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 368 | 20191030-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-10-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 has incorrect rate REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - moved mulcher to MacGregor West, grinder , 1Ex to Mack West. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting36820191030-2-R01Operator - Principle121080 | Corbiere and Sons Contracting36820191030-2-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 368 | 20191030-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-10-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 has incorrect rate REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - moved mulcher to MacGregor West, grinder , 1Ex to Mack West. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting36820191030-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting36820191030-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 368 | 20191030-2-R01 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 24 | HR |  |  |  | 0 | 1800 | 234 | 2034 | 2019-10-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 has incorrect rate REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - moved mulcher to MacGregor West, grinder , 1Ex to Mack West. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting36820191030-2-R01Labourer - Specialized241800 | Corbiere and Sons Contracting36820191030-2-R01Labourer - Specialized241800Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 368 | 20191030-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 has incorrect rate REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - moved mulcher to MacGregor West, grinder , 1Ex to Mack West. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting36820191030-2-R01Labourer - General10650 | Corbiere and Sons Contracting36820191030-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 368 | 20191030-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-30 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader JD 524 has incorrect rate REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - moved mulcher to MacGregor West, grinder , 1Ex to Mack West. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting36820191030-2-R01L.O.A.3630 | Corbiere and Sons Contracting36820191030-2-R01L.O.A.3630Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 370 | 20191030-4-R02 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for skidder. - REVISED 11152019 DK |  |  |  |  | Clearing from A050 |  |  | A050 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting37020191030-4-R02Feller Buncher92160 | Corbiere and Sons Contracting37020191030-4-R02Feller Buncher92160Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 370 | 20191030-4-R02 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for skidder. - REVISED 11152019 DK |  |  |  |  | Clearing from A050 |  |  | A050 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting37020191030-4-R02Skidder 91539 | Corbiere and Sons Contracting37020191030-4-R02Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 370 | 20191030-4-R02 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for skidder. - REVISED 11152019 DK |  |  |  |  | Clearing from A050 |  |  | A050 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting37020191030-4-R02Light Truck - Pick up10300 | Corbiere and Sons Contracting37020191030-4-R02Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 370 | 20191030-4-R02 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for skidder. - REVISED 11152019 DK |  |  |  |  | Clearing from A050 |  |  | A050 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting37020191030-4-R02Operator - Principle221980 | Corbiere and Sons Contracting37020191030-4-R02Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 370 | 20191030-4-R02 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for skidder. - REVISED 11152019 DK |  |  |  |  | Clearing from A050 |  |  | A050 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting37020191030-4-R02L.O.A.2420 | Corbiere and Sons Contracting37020191030-4-R02L.O.A.2420Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 371 | 20191030-5-R01 | 53520101 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A050 and A059 |  |  | A050, A059 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting37120191030-5-R01Brusher91822.5 | Corbiere and Sons Contracting37120191030-5-R01Brusher91822.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 371 | 20191030-5-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 18 | HR | 180 | 0 |  |  | 4320 | 561.6 | 4881.6 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A050 and A059 |  |  | A050, A059 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting37120191030-5-R01Feller Buncher184320 | Corbiere and Sons Contracting37120191030-5-R01Feller Buncher184320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 371 | 20191030-5-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A050 and A059 |  |  | A050, A059 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting37120191030-5-R01Skidder 91539 | Corbiere and Sons Contracting37120191030-5-R01Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 371 | 20191030-5-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A050 and A059 |  |  | A050, A059 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting37120191030-5-R01Light Truck - Pick up30900 | Corbiere and Sons Contracting37120191030-5-R01Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 371 | 20191030-5-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A050 and A059 |  |  | A050, A059 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting37120191030-5-R01Operator - Principle443960 | Corbiere and Sons Contracting37120191030-5-R01Operator - Principle443960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 371 | 20191030-5-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-10-30 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A050 and A059 |  |  | A050, A059 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting37120191030-5-R01L.O.A.4840 | Corbiere and Sons Contracting37120191030-5-R01L.O.A.4840Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 372 | 20191030-6 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-10-30 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material and a scheduled float move to A003 |  |  | A003 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting37220191030-6Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting37220191030-6Grinder - 4710 Peterson or equal95011.2Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 372 | 20191030-6 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-10-30 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material and a scheduled float move to A003 |  |  | A003 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting37220191030-6Log Loader91377 | Corbiere and Sons Contracting37220191030-6Log Loader91377Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 372 | 20191030-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-30 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material and a scheduled float move to A003 |  |  | A003 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting37220191030-6Light Truck - Pick up10300 | Corbiere and Sons Contracting37220191030-6Light Truck - Pick up10300Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 372 | 20191030-6 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-30 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material and a scheduled float move to A003 |  |  | A003 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting37220191030-6Operator - Principle11990 | Corbiere and Sons Contracting37220191030-6Operator - Principle11990Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 372 | 20191030-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-30 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material and a scheduled float move to A003 |  |  | A003 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting37220191030-6L.O.A.1210 | Corbiere and Sons Contracting37220191030-6L.O.A.1210Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 381 | 20191031-02-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-10-31 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader rate is incorrect on LEM; REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting38120191031-02-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting38120191031-02-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 381 | 20191031-02-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-10-31 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader rate is incorrect on LEM; REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting38120191031-02-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting38120191031-02-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 381 | 20191031-02-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-10-31 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader rate is incorrect on LEM; REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting38120191031-02-R01Operator - Principle121080 | Corbiere and Sons Contracting38120191031-02-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 381 | 20191031-02-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-10-31 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader rate is incorrect on LEM; REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting38120191031-02-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting38120191031-02-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 381 | 20191031-02-R01 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 25 | HR |  |  |  | 0 | 1875 | 243.75 | 2118.75 | 2019-10-31 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader rate is incorrect on LEM; REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting38120191031-02-R01Labourer - Specialized251875 | Corbiere and Sons Contracting38120191031-02-R01Labourer - Specialized251875Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1875 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 381 | 20191031-02-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-10-31 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader rate is incorrect on LEM; REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting38120191031-02-R01Labourer - General10650 | Corbiere and Sons Contracting38120191031-02-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 381 | 20191031-02-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-31 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader rate is incorrect on LEM; REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting38120191031-02-R01L.O.A.3630 | Corbiere and Sons Contracting38120191031-02-R01L.O.A.3630Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 380 | 20191031-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting38020191031-1Light Truck - Pick up601800 | Corbiere and Sons Contracting38020191031-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 380 | 20191031-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting38020191031-1Project Manager121320 | Corbiere and Sons Contracting38020191031-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 380 | 20191031-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting38020191031-1Superintendent121260 | Corbiere and Sons Contracting38020191031-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 380 | 20191031-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting38020191031-1Project Coordinator12960 | Corbiere and Sons Contracting38020191031-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 380 | 20191031-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting38020191031-1Construction Coordinator12960 | Corbiere and Sons Contracting38020191031-1Construction Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 380 | 20191031-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting38020191031-1Safety Advisor121020 | Corbiere and Sons Contracting38020191031-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 380 | 20191031-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting38020191031-1Project Controls12840 | Corbiere and Sons Contracting38020191031-1Project Controls12840Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 380 | 20191031-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43792 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting38020191031-1L.O.A.61260 | Corbiere and Sons Contracting38020191031-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 389 | 20191031-10-R01 | 53510112 | Access | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Gravelling and flagging at A027 |  |  | A027 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting38920191031-10-R01Dozer D6 or equal91215 | Corbiere and Sons Contracting38920191031-10-R01Dozer D6 or equal91215Inv#002-R01 | [5 empty] | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 389 | 20191031-10-R01 | 53510112 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Gravelling and flagging at A027 |  |  | A027 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting38920191031-10-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting38920191031-10-R01Light Truck - Pick up10300Inv#002-R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 389 | 20191031-10-R01 | 53510112 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Gravelling and flagging at A027 |  |  | A027 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting38920191031-10-R01Operator - Principle11990 | Corbiere and Sons Contracting38920191031-10-R01Operator - Principle11990Inv#002-R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 389 | 20191031-10-R01 | 53510112 | Access | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Gravelling and flagging at A027 |  |  | A027 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting38920191031-10-R01Labourer - Specialized11825 | Corbiere and Sons Contracting38920191031-10-R01Labourer - Specialized11825Inv#002-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 389 | 20191031-10-R01 | 53510112 | Access | 0 | Labourer - General | 65 | 22 | HR |  |  |  | 0 | 1430 | 185.9 | 1615.9 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Gravelling and flagging at A027 |  |  | A027 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting38920191031-10-R01Labourer - General221430 | Corbiere and Sons Contracting38920191031-10-R01Labourer - General221430Inv#002-R01 | [5 empty] | 1 | 1430 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 389 | 20191031-10-R01 | 53510112 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Gravelling and flagging at A027 |  |  | A027 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting38920191031-10-R01L.O.A.2420 | Corbiere and Sons Contracting38920191031-10-R01L.O.A.2420Inv#002-R01 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 382 | 20191031-3 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR | 180 | 0 |  |  | 2280 | 296.4 | 2576.4 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing tower A055 |  |  |  | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting38220191031-3Feller Buncher9.52280 | Corbiere and Sons Contracting38220191031-3Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 382 | 20191031-3 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR | 128.25 | 0 |  |  | 1624.5 | 211.185 | 1835.685 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing tower A055 |  |  |  | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting38220191031-3Skidder 9.51624.5 | Corbiere and Sons Contracting38220191031-3Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 382 | 20191031-3 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing tower A055 |  |  |  | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting38220191031-3Light Truck - Pick up30900 | Corbiere and Sons Contracting38220191031-3Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 382 | 20191031-3 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing tower A055 |  |  |  | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting38220191031-3Foreman4380 | Corbiere and Sons Contracting38220191031-3Foreman4380Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 382 | 20191031-3 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing tower A055 |  |  |  | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting38220191031-3Operator - Principle221980 | Corbiere and Sons Contracting38220191031-3Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 382 | 20191031-3 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing tower A055 |  |  |  | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting38220191031-3L.O.A.3630 | Corbiere and Sons Contracting38220191031-3L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 383 | 20191031-4-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 18 | HR | 180 | 0 |  |  | 4320 | 561.6 | 4881.6 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A043 westward |  |  |  | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting38320191031-4-R01Feller Buncher184320 | Corbiere and Sons Contracting38320191031-4-R01Feller Buncher184320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 383 | 20191031-4-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A043 westward |  |  |  | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting38320191031-4-R01Skidder 91539 | Corbiere and Sons Contracting38320191031-4-R01Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 383 | 20191031-4-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A043 westward |  |  |  | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting38320191031-4-R01Operator - Principle332970 | Corbiere and Sons Contracting38320191031-4-R01Operator - Principle332970Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 383 | 20191031-4-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A043 westward |  |  |  | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting38320191031-4-R01L.O.A.3630 | Corbiere and Sons Contracting38320191031-4-R01L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 384 | 20191031-5-R01 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A051 and A059 |  |  | A051, A059 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting38420191031-5-R01Feller Buncher92160 | Corbiere and Sons Contracting38420191031-5-R01Feller Buncher92160Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 384 | 20191031-5-R01 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A051 and A059 |  |  | A051, A059 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting38420191031-5-R01Mulcher91845 | Corbiere and Sons Contracting38420191031-5-R01Mulcher91845Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 384 | 20191031-5-R01 | 53520102 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A051 and A059 |  |  | A051, A059 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting38420191031-5-R01Skidder 91539 | Corbiere and Sons Contracting38420191031-5-R01Skidder 91539Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 384 | 20191031-5-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A051 and A059 |  |  | A051, A059 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting38420191031-5-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting38420191031-5-R01Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 384 | 20191031-5-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A051 and A059 |  |  | A051, A059 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting38420191031-5-R01Operator - Principle332970 | Corbiere and Sons Contracting38420191031-5-R01Operator - Principle332970Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 384 | 20191031-5-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A051 and A059 |  |  | A051, A059 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting38420191031-5-R01L.O.A.3630 | Corbiere and Sons Contracting38420191031-5-R01L.O.A.3630Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 385 | 20191031-6 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material and a scheduled float move to A003 |  |  | A003 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting38520191031-6Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting38520191031-6Grinder - 4710 Peterson or equal95011.2Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 385 | 20191031-6 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material and a scheduled float move to A003 |  |  | A003 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting38520191031-6Log Loader91377 | Corbiere and Sons Contracting38520191031-6Log Loader91377Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 385 | 20191031-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material and a scheduled float move to A003 |  |  | A003 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting38520191031-6Light Truck - Pick up10300 | Corbiere and Sons Contracting38520191031-6Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 385 | 20191031-6 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material and a scheduled float move to A003 |  |  | A003 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting38520191031-6Operator - Principle11990 | Corbiere and Sons Contracting38520191031-6Operator - Principle11990Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 385 | 20191031-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-10-31 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material and a scheduled float move to A003 |  |  | A003 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting38520191031-6L.O.A.1210 | Corbiere and Sons Contracting38520191031-6L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 432 | 201911005-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-11-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting432201911005-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting432201911005-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 432 | 201911005-2-R01 | 53520105 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting432201911005-2-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting432201911005-2-R01Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 432 | 201911005-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting432201911005-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting432201911005-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 432 | 201911005-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-11-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting432201911005-2-R01Operator - Principle121080 | Corbiere and Sons Contracting432201911005-2-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 432 | 201911005-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting432201911005-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting432201911005-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 432 | 201911005-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-11-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting432201911005-2-R01Labourer - General10650 | Corbiere and Sons Contracting432201911005-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 432 | 201911005-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting432201911005-2-R01L.O.A.2420 | Corbiere and Sons Contracting432201911005-2-R01L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 393 | 20191101-02-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-11-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader rate is incorrect on LEM; REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting39320191101-02-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting39320191101-02-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 393 | 20191101-02-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader rate is incorrect on LEM; REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting39320191101-02-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting39320191101-02-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 393 | 20191101-02-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-11-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader rate is incorrect on LEM; REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting39320191101-02-R01Operator - Principle121080 | Corbiere and Sons Contracting39320191101-02-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 393 | 20191101-02-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader rate is incorrect on LEM; REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting39320191101-02-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting39320191101-02-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 393 | 20191101-02-R01 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 14 | HR |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader rate is incorrect on LEM; REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting39320191101-02-R01Labourer - Specialized141050 | Corbiere and Sons Contracting39320191101-02-R01Labourer - Specialized141050Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 393 | 20191101-02-R01 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-11-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader rate is incorrect on LEM; REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting39320191101-02-R01Labourer - Specialized11825 | Corbiere and Sons Contracting39320191101-02-R01Labourer - Specialized11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 393 | 20191101-02-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-11-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader rate is incorrect on LEM; REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting39320191101-02-R01Labourer - General10650 | Corbiere and Sons Contracting39320191101-02-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 393 | 20191101-02-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-01 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Loader rate is incorrect on LEM; REVISED 11152019 DK Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting39320191101-02-R01L.O.A.3630 | Corbiere and Sons Contracting39320191101-02-R01L.O.A.3630Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 394 | 20191101-03 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR | 180 | 0 |  |  | 2280 | 296.4 | 2576.4 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing tower A055, cut to river pass A055 and clean up west of tower A056 to orange-black. |  |  | A055, A056 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39420191101-03Feller Buncher9.52280 | Corbiere and Sons Contracting39420191101-03Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 394 | 20191101-03 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR | 128.25 | 0 |  |  | 1624.5 | 211.185 | 1835.685 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing tower A055, cut to river pass A055 and clean up west of tower A056 to orange-black. |  |  | A055, A056 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39420191101-03Skidder 9.51624.5 | Corbiere and Sons Contracting39420191101-03Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 394 | 20191101-03 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing tower A055, cut to river pass A055 and clean up west of tower A056 to orange-black. |  |  | A055, A056 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39420191101-03Light Truck - Pick up30900 | Corbiere and Sons Contracting39420191101-03Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 394 | 20191101-03 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing tower A055, cut to river pass A055 and clean up west of tower A056 to orange-black. |  |  | A055, A056 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39420191101-03Foreman4380 | Corbiere and Sons Contracting39420191101-03Foreman4380Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 394 | 20191101-03 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing tower A055, cut to river pass A055 and clean up west of tower A056 to orange-black. |  |  | A055, A056 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39420191101-03Operator - Principle221980 | Corbiere and Sons Contracting39420191101-03Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 394 | 20191101-03 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing tower A055, cut to river pass A055 and clean up west of tower A056 to orange-black. |  |  | A055, A056 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39420191101-03L.O.A.3630 | Corbiere and Sons Contracting39420191101-03L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 398 | 20191101-06-R02 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A060 |  |  | A060 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39820191101-06-R02Feller Buncher92160 | Corbiere and Sons Contracting39820191101-06-R02Feller Buncher92160Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 398 | 20191101-06-R02 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A060 |  |  | A060 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39820191101-06-R02Skidder 91539 | Corbiere and Sons Contracting39820191101-06-R02Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 398 | 20191101-06-R02 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A060 |  |  | A060 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39820191101-06-R02Light Truck - Pick up20600 | Corbiere and Sons Contracting39820191101-06-R02Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 398 | 20191101-06-R02 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A060 |  |  | A060 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39820191101-06-R02Operator - Principle221980 | Corbiere and Sons Contracting39820191101-06-R02Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 398 | 20191101-06-R02 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A060 |  |  | A060 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39820191101-06-R02L.O.A.2420 | Corbiere and Sons Contracting39820191101-06-R02L.O.A.2420Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 399 | 20191101-07-R01 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material and a scheduled float move to A003 |  |  | A003 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39920191101-07-R01Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting39920191101-07-R01Grinder - 4710 Peterson or equal1810022.4Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 399 | 20191101-07-R01 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material and a scheduled float move to A003 |  |  | A003 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39920191101-07-R01Log Loader182754 | Corbiere and Sons Contracting39920191101-07-R01Log Loader182754Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 399 | 20191101-07-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material and a scheduled float move to A003 |  |  | A003 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39920191101-07-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting39920191101-07-R01Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 399 | 20191101-07-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material and a scheduled float move to A003 |  |  | A003 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39920191101-07-R01Operator - Principle221980 | Corbiere and Sons Contracting39920191101-07-R01Operator - Principle221980Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 399 | 20191101-07-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material and a scheduled float move to A003 |  |  | A003 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39920191101-07-R01L.O.A.2420 | Corbiere and Sons Contracting39920191101-07-R01L.O.A.2420Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 400 | 20191101-08-R01 | 53520102 | Clearing | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finsihed at A019 and moved to A029 |  |  | A019, A029 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting40020191101-08-R01Excavator - 30 ton91255.5 | Corbiere and Sons Contracting40020191101-08-R01Excavator - 30 ton91255.5Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 400 | 20191101-08-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finsihed at A019 and moved to A029 |  |  | A019, A029 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting40020191101-08-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting40020191101-08-R01Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 400 | 20191101-08-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finsihed at A019 and moved to A029 |  |  | A019, A029 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting40020191101-08-R01Operator - Principle11990 | Corbiere and Sons Contracting40020191101-08-R01Operator - Principle11990Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 400 | 20191101-08-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finsihed at A019 and moved to A029 |  |  | A019, A029 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting40020191101-08-R01L.O.A.1210 | Corbiere and Sons Contracting40020191101-08-R01L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 392 | 20191101-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting39220191101-1Light Truck - Pick up601800 | Corbiere and Sons Contracting39220191101-1Light Truck - Pick up601800Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 392 | 20191101-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting39220191101-1Project Manager121320 | Corbiere and Sons Contracting39220191101-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 392 | 20191101-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting39220191101-1Superintendent121260 | Corbiere and Sons Contracting39220191101-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 392 | 20191101-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting39220191101-1Project Coordinator12960 | Corbiere and Sons Contracting39220191101-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 392 | 20191101-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting39220191101-1Construction Coordinator12960 | Corbiere and Sons Contracting39220191101-1Construction Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 392 | 20191101-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting39220191101-1Safety Advisor121020 | Corbiere and Sons Contracting39220191101-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 392 | 20191101-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting39220191101-1Project Controls12840 | Corbiere and Sons Contracting39220191101-1Project Controls12840Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 392 | 20191101-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting39220191101-1L.O.A.61260 | Corbiere and Sons Contracting39220191101-1L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 395 | 20191101-4-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A043 westward |  |  | A043 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39520191101-4-R01Feller Buncher92160 | Corbiere and Sons Contracting39520191101-4-R01Feller Buncher92160Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 395 | 20191101-4-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A043 westward |  |  | A043 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39520191101-4-R01Skidder 91539 | Corbiere and Sons Contracting39520191101-4-R01Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 395 | 20191101-4-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A043 westward |  |  | A043 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39520191101-4-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting39520191101-4-R01Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 395 | 20191101-4-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A043 westward |  |  | A043 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39520191101-4-R01Operator - Principle221980 | Corbiere and Sons Contracting39520191101-4-R01Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 395 | 20191101-4-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A043 westward |  |  | A043 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39520191101-4-R01L.O.A.2420 | Corbiere and Sons Contracting39520191101-4-R01L.O.A.2420Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 397 | 20191101-5-R02 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Error with LEM number date is incorrect. REVISED 11152019 DK |  |  |  |  | Clearing from A054 |  |  | A054 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39720191101-5-R02Feller Buncher92160 | Corbiere and Sons Contracting39720191101-5-R02Feller Buncher92160Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 397 | 20191101-5-R02 | 53520101 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Error with LEM number date is incorrect. REVISED 11152019 DK |  |  |  |  | Clearing from A054 |  |  | A054 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39720191101-5-R02Mulcher91845 | Corbiere and Sons Contracting39720191101-5-R02Mulcher91845Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 397 | 20191101-5-R02 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Error with LEM number date is incorrect. REVISED 11152019 DK |  |  |  |  | Clearing from A054 |  |  | A054 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39720191101-5-R02Operator - Principle221980 | Corbiere and Sons Contracting39720191101-5-R02Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 397 | 20191101-5-R02 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-01 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Error with LEM number date is incorrect. REVISED 11152019 DK |  |  |  |  | Clearing from A054 |  |  | A054 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting39720191101-5-R02L.O.A.2420 | Corbiere and Sons Contracting39720191101-5-R02L.O.A.2420Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 407 | 20191102-02-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-11-02 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting40720191102-02-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting40720191102-02-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 407 | 20191102-02-R01 | 53520105 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-02 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting40720191102-02-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting40720191102-02-R01Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 407 | 20191102-02-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-02 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting40720191102-02-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting40720191102-02-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 407 | 20191102-02-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-11-02 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting40720191102-02-R01Operator - Principle121080 | Corbiere and Sons Contracting40720191102-02-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 407 | 20191102-02-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-02 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting40720191102-02-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting40720191102-02-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 407 | 20191102-02-R01 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 13 | HR |  |  |  | 0 | 975 | 126.75 | 1101.75 | 2019-11-02 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting40720191102-02-R01Labourer - Specialized13975 | Corbiere and Sons Contracting40720191102-02-R01Labourer - Specialized13975Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 407 | 20191102-02-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-11-02 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting40720191102-02-R01Labourer - General10650 | Corbiere and Sons Contracting40720191102-02-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 407 | 20191102-02-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-02 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting40720191102-02-R01L.O.A.2420 | Corbiere and Sons Contracting40720191102-02-R01L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 408 | 20191102-03-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 27 | HR | 180 | 0 |  |  | 6480 | 842.4 | 7322.4 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A060 |  |  | A060 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting40820191102-03-R01Feller Buncher276480 | Corbiere and Sons Contracting40820191102-03-R01Feller Buncher276480Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 6480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 408 | 20191102-03-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A060 |  |  | A060 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting40820191102-03-R01Skidder 183078 | Corbiere and Sons Contracting40820191102-03-R01Skidder 183078Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 408 | 20191102-03-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A060 |  |  | A060 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting40820191102-03-R01Light Truck - Pick up401200 | Corbiere and Sons Contracting40820191102-03-R01Light Truck - Pick up401200Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 408 | 20191102-03-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 55 | HR |  |  |  | 0 | 4950 | 643.5 | 5593.5 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A060 |  |  | A060 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting40820191102-03-R01Operator - Principle554950 | Corbiere and Sons Contracting40820191102-03-R01Operator - Principle554950Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 408 | 20191102-03-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A060 |  |  | A060 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting40820191102-03-R01L.O.A.51050 | Corbiere and Sons Contracting40820191102-03-R01L.O.A.51050Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 409 | 20191102-04-R01 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding - David at A010, Jacob from A008-A009 |  |  | A010, A008-A009 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting40920191102-04-R01Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting40920191102-04-R01Grinder - 4710 Peterson or equal1810022.4Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 409 | 20191102-04-R01 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding - David at A010, Jacob from A008-A009 |  |  | A010, A008-A009 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting40920191102-04-R01Log Loader182754 | Corbiere and Sons Contracting40920191102-04-R01Log Loader182754Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 409 | 20191102-04-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding - David at A010, Jacob from A008-A009 |  |  | A010, A008-A009 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting40920191102-04-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting40920191102-04-R01Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 409 | 20191102-04-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding - David at A010, Jacob from A008-A009 |  |  | A010, A008-A009 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting40920191102-04-R01Operator - Principle221980 | Corbiere and Sons Contracting40920191102-04-R01Operator - Principle221980Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 409 | 20191102-04-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding - David at A010, Jacob from A008-A009 |  |  | A010, A008-A009 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting40920191102-04-R01L.O.A.2420 | Corbiere and Sons Contracting40920191102-04-R01L.O.A.2420Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 412 | 20191102-07-R01 | 53510112 | Access | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Eoor on date - possible error with LOA count. Excavator 30ton has incorrect rate. REVISED 11152019 DK |  |  |  |  | Labourers were fueling and flagging, repairing road from A030-A035 |  |  | A030-A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting41220191102-07-R01Excavator - 30 ton91255.5 | Corbiere and Sons Contracting41220191102-07-R01Excavator - 30 ton91255.5Inv#002-R01 | [5 empty] | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 412 | 20191102-07-R01 | 53510112 | Access | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Eoor on date - possible error with LOA count. Excavator 30ton has incorrect rate. REVISED 11152019 DK |  |  |  |  | Labourers were fueling and flagging, repairing road from A030-A035 |  |  | A030-A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting41220191102-07-R01Excavator - 36 ton91539 | Corbiere and Sons Contracting41220191102-07-R01Excavator - 36 ton91539Inv#002-R01 | [5 empty] | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 412 | 20191102-07-R01 | 53510112 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Eoor on date - possible error with LOA count. Excavator 30ton has incorrect rate. REVISED 11152019 DK |  |  |  |  | Labourers were fueling and flagging, repairing road from A030-A035 |  |  | A030-A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting41220191102-07-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting41220191102-07-R01Light Truck - Pick up10300Inv#002-R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 412 | 20191102-07-R01 | 53510112 | Access | 0 | Operator - Principle | 90 | 27 | HR |  |  |  | 0 | 2430 | 315.9 | 2745.9 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Eoor on date - possible error with LOA count. Excavator 30ton has incorrect rate. REVISED 11152019 DK |  |  |  |  | Labourers were fueling and flagging, repairing road from A030-A035 |  |  | A030-A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting41220191102-07-R01Operator - Principle272430 | Corbiere and Sons Contracting41220191102-07-R01Operator - Principle272430Inv#002-R01 | [5 empty] | 1 | 2430 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 412 | 20191102-07-R01 | 53510112 | Access | 0 | Labourer - Specialized | 75 | 22 | HR |  |  |  | 0 | 1650 | 214.5 | 1864.5 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Eoor on date - possible error with LOA count. Excavator 30ton has incorrect rate. REVISED 11152019 DK |  |  |  |  | Labourers were fueling and flagging, repairing road from A030-A035 |  |  | A030-A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting41220191102-07-R01Labourer - Specialized221650 | Corbiere and Sons Contracting41220191102-07-R01Labourer - Specialized221650Inv#002-R01 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 412 | 20191102-07-R01 | 53510112 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Eoor on date - possible error with LOA count. Excavator 30ton has incorrect rate. REVISED 11152019 DK |  |  |  |  | Labourers were fueling and flagging, repairing road from A030-A035 |  |  | A030-A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting41220191102-07-R01L.O.A.4840 | Corbiere and Sons Contracting41220191102-07-R01L.O.A.4840Inv#002-R01 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 406 | 20191102-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 70 | HR | 22.5 | 0 |  |  | 2100 | 273 | 2373 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting40620191102-1Light Truck - Pick up702100 | Corbiere and Sons Contracting40620191102-1Light Truck - Pick up702100Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 406 | 20191102-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting40620191102-1Project Manager121320 | Corbiere and Sons Contracting40620191102-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 406 | 20191102-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting40620191102-1Superintendent121260 | Corbiere and Sons Contracting40620191102-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 406 | 20191102-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting40620191102-1Project Coordinator12960 | Corbiere and Sons Contracting40620191102-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 406 | 20191102-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting40620191102-1Construction Coordinator12960 | Corbiere and Sons Contracting40620191102-1Construction Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 406 | 20191102-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting40620191102-1Safety Advisor121020 | Corbiere and Sons Contracting40620191102-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 406 | 20191102-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting40620191102-1Project Controls12840 | Corbiere and Sons Contracting40620191102-1Project Controls12840Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 406 | 20191102-1 | 53520101 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting40620191102-1Foreman121140 | Corbiere and Sons Contracting40620191102-1Foreman121140Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 406 | 20191102-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-11-02 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting40620191102-1L.O.A.71470 | Corbiere and Sons Contracting40620191102-1L.O.A.71470Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 414 | 20191103-02-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-11-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting41420191103-02-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting41420191103-02-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 414 | 20191103-02-R01 | 53520105 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting41420191103-02-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting41420191103-02-R01Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 414 | 20191103-02-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting41420191103-02-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting41420191103-02-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 414 | 20191103-02-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting41420191103-02-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting41420191103-02-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 414 | 20191103-02-R01 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 13 | HR |  |  |  | 0 | 975 | 126.75 | 1101.75 | 2019-11-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting41420191103-02-R01Labourer - Specialized13975 | Corbiere and Sons Contracting41420191103-02-R01Labourer - Specialized13975Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 414 | 20191103-02-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting41420191103-02-R01L.O.A.3630 | Corbiere and Sons Contracting41420191103-02-R01L.O.A.3630Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 415 | 20191103-03-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Skidding done at A042 |  |  | A042 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting41520191103-03-R01Skidder 91539 | Corbiere and Sons Contracting41520191103-03-R01Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 415 | 20191103-03-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Skidding done at A042 |  |  | A042 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting41520191103-03-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting41520191103-03-R01Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 415 | 20191103-03-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Skidding done at A042 |  |  | A042 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting41520191103-03-R01Operator - Principle11990 | Corbiere and Sons Contracting41520191103-03-R01Operator - Principle11990Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 415 | 20191103-03-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Skidding done at A042 |  |  | A042 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting41520191103-03-R01L.O.A.1210 | Corbiere and Sons Contracting41520191103-03-R01L.O.A.1210Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 416 | 20191103-04-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 27 | HR | 180 | 0 |  |  | 6480 | 842.4 | 7322.4 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A060 |  |  | A060 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting41620191103-04-R01Feller Buncher276480 | Corbiere and Sons Contracting41620191103-04-R01Feller Buncher276480Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 6480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 416 | 20191103-04-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A060 |  |  | A060 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting41620191103-04-R01Skidder 91539 | Corbiere and Sons Contracting41620191103-04-R01Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 416 | 20191103-04-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A060 |  |  | A060 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting41620191103-04-R01Light Truck - Pick up30900 | Corbiere and Sons Contracting41620191103-04-R01Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 416 | 20191103-04-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A060 |  |  | A060 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting41620191103-04-R01Operator - Principle443960 | Corbiere and Sons Contracting41620191103-04-R01Operator - Principle443960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 416 | 20191103-04-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A060 |  |  | A060 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting41620191103-04-R01L.O.A.4840 | Corbiere and Sons Contracting41620191103-04-R01L.O.A.4840Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 417 | 20191103-05-R01 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material from towers A008-A013. |  |  | A008-A013 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting41720191103-05-R01Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting41720191103-05-R01Grinder - 4710 Peterson or equal1810022.4Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 417 | 20191103-05-R01 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material from towers A008-A013. |  |  | A008-A013 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting41720191103-05-R01Log Loader182754 | Corbiere and Sons Contracting41720191103-05-R01Log Loader182754Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 417 | 20191103-05-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material from towers A008-A013. |  |  | A008-A013 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting41720191103-05-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting41720191103-05-R01Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 417 | 20191103-05-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material from towers A008-A013. |  |  | A008-A013 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting41720191103-05-R01Operator - Principle221980 | Corbiere and Sons Contracting41720191103-05-R01Operator - Principle221980Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 417 | 20191103-05-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | grinding material from towers A008-A013. |  |  | A008-A013 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting41720191103-05-R01L.O.A.2420 | Corbiere and Sons Contracting41720191103-05-R01L.O.A.2420Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 420 | 20191103-08-R02 | 53510112 | Access | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for Excavator 30 ton; REVISED DK 11152019 |  |  |  |  | Labourers were fueling and flagging, repairing road from A030-A035, dozer working at A025 |  |  | A030-A035, A025 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42020191103-08-R02Excavator - 30 ton91255.5 | Corbiere and Sons Contracting42020191103-08-R02Excavator - 30 ton91255.5Inv#002-R01 | [5 empty] | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 420 | 20191103-08-R02 | 53510112 | Access | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for Excavator 30 ton; REVISED DK 11152019 |  |  |  |  | Labourers were fueling and flagging, repairing road from A030-A035, dozer working at A025 |  |  | A030-A035, A025 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42020191103-08-R02Excavator - 36 ton91539 | Corbiere and Sons Contracting42020191103-08-R02Excavator - 36 ton91539Inv#002-R01 | [5 empty] | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 420 | 20191103-08-R02 | 53510112 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for Excavator 30 ton; REVISED DK 11152019 |  |  |  |  | Labourers were fueling and flagging, repairing road from A030-A035, dozer working at A025 |  |  | A030-A035, A025 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42020191103-08-R02Light Truck - Pick up10300 | Corbiere and Sons Contracting42020191103-08-R02Light Truck - Pick up10300Inv#002-R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 420 | 20191103-08-R02 | 53510112 | Access | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for Excavator 30 ton; REVISED DK 11152019 |  |  |  |  | Labourers were fueling and flagging, repairing road from A030-A035, dozer working at A025 |  |  | A030-A035, A025 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42020191103-08-R02Operator - Principle221980 | Corbiere and Sons Contracting42020191103-08-R02Operator - Principle221980Inv#002-R01 | [5 empty] | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 420 | 20191103-08-R02 | 53510112 | Access | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for Excavator 30 ton; REVISED DK 11152019 |  |  |  |  | Labourers were fueling and flagging, repairing road from A030-A035, dozer working at A025 |  |  | A030-A035, A025 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42020191103-08-R02Labourer - Specialized11825 | Corbiere and Sons Contracting42020191103-08-R02Labourer - Specialized11825Inv#002-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 420 | 20191103-08-R02 | 53510112 | Access | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for Excavator 30 ton; REVISED DK 11152019 |  |  |  |  | Labourers were fueling and flagging, repairing road from A030-A035, dozer working at A025 |  |  | A030-A035, A025 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42020191103-08-R02Labourer - General11715 | Corbiere and Sons Contracting42020191103-08-R02Labourer - General11715Inv#002-R01 | [5 empty] | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 420 | 20191103-08-R02 | 53510112 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for Excavator 30 ton; REVISED DK 11152019 |  |  |  |  | Labourers were fueling and flagging, repairing road from A030-A035, dozer working at A025 |  |  | A030-A035, A025 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42020191103-08-R02L.O.A.4840 | Corbiere and Sons Contracting42020191103-08-R02L.O.A.4840Inv#002-R01 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 413 | 20191103-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 70 | HR | 22.5 | 0 |  |  | 2100 | 273 | 2373 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting41320191103-1Light Truck - Pick up702100 | Corbiere and Sons Contracting41320191103-1Light Truck - Pick up702100Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 413 | 20191103-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting41320191103-1Project Manager121320 | Corbiere and Sons Contracting41320191103-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 413 | 20191103-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting41320191103-1Superintendent121260 | Corbiere and Sons Contracting41320191103-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 413 | 20191103-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting41320191103-1Project Coordinator12960 | Corbiere and Sons Contracting41320191103-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 413 | 20191103-1 | 53520101 | Clearing | 0 | Construction Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting41320191103-1Construction Coordinator12960 | Corbiere and Sons Contracting41320191103-1Construction Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 413 | 20191103-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting41320191103-1Safety Advisor121020 | Corbiere and Sons Contracting41320191103-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 413 | 20191103-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 4 | HR |  |  |  | 0 | 280 | 36.4 | 316.4 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting41320191103-1Project Controls4280 | Corbiere and Sons Contracting41320191103-1Project Controls4280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 413 | 20191103-1 | 53520101 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting41320191103-1Foreman121140 | Corbiere and Sons Contracting41320191103-1Foreman121140Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 413 | 20191103-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-11-03 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting41320191103-1L.O.A.71470 | Corbiere and Sons Contracting41320191103-1L.O.A.71470Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 421 | 20191104-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting42120191104-1Light Truck - Pick up501500 | Corbiere and Sons Contracting42120191104-1Light Truck - Pick up501500Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 421 | 20191104-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting42120191104-1Project Manager121320 | Corbiere and Sons Contracting42120191104-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 421 | 20191104-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting42120191104-1Superintendent121260 | Corbiere and Sons Contracting42120191104-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 421 | 20191104-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting42120191104-1Project Coordinator12960 | Corbiere and Sons Contracting42120191104-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 421 | 20191104-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting42120191104-1Safety Advisor121020 | Corbiere and Sons Contracting42120191104-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 421 | 20191104-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting42120191104-1Project Controls12840 | Corbiere and Sons Contracting42120191104-1Project Controls12840Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 421 | 20191104-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting42120191104-1L.O.A.51050 | Corbiere and Sons Contracting42120191104-1L.O.A.51050Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 430 | 20191104-10 | 53510112 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | PTB Logging Inc. Orientation |  |  |  | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting43020191104-10Light Truck - Pick up10300 | Corbiere and Sons Contracting43020191104-10Light Truck - Pick up10300Inv#002-R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 430 | 20191104-10 | 53510112 | Access | 0 | Labourer - Specialized | 75 | 15 | HR |  |  |  | 0 | 1125 | 146.25 | 1271.25 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | PTB Logging Inc. Orientation |  |  |  | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting43020191104-10Labourer - Specialized151125 | Corbiere and Sons Contracting43020191104-10Labourer - Specialized151125Inv#002-R01 | [5 empty] | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 422 | 20191104-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-11-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- Orientations. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting42220191104-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting42220191104-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 422 | 20191104-2-R01 | 53520105 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- Orientations. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting42220191104-2-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting42220191104-2-R01Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 422 | 20191104-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- Orientations. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting42220191104-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting42220191104-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 422 | 20191104-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-11-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- Orientations. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting42220191104-2-R01Operator - Principle121080 | Corbiere and Sons Contracting42220191104-2-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 422 | 20191104-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- Orientations. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting42220191104-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting42220191104-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 422 | 20191104-2-R01 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 24 | HR |  |  |  | 0 | 1800 | 234 | 2034 | 2019-11-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- Orientations. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting42220191104-2-R01Labourer - Specialized241800 | Corbiere and Sons Contracting42220191104-2-R01Labourer - Specialized241800Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 422 | 20191104-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-11-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- Orientations. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting42220191104-2-R01Labourer - General10650 | Corbiere and Sons Contracting42220191104-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 422 | 20191104-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- Orientations. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting42220191104-2-R01L.O.A.4840 | Corbiere and Sons Contracting42220191104-2-R01L.O.A.4840Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 423 | 20191104-3-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 27 | HR | 180 | 0 |  |  | 6480 | 842.4 | 7322.4 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A060-A062 |  |  | A060-A062 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42320191104-3-R01Feller Buncher276480 | Corbiere and Sons Contracting42320191104-3-R01Feller Buncher276480Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 6480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 423 | 20191104-3-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 27 | HR | 128.25 | 0 |  |  | 4617 | 600.21 | 5217.21 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A060-A062 |  |  | A060-A062 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42320191104-3-R01Skidder 274617 | Corbiere and Sons Contracting42320191104-3-R01Skidder 274617Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 423 | 20191104-3-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A060-A062 |  |  | A060-A062 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42320191104-3-R01Light Truck - Pick up30900 | Corbiere and Sons Contracting42320191104-3-R01Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 423 | 20191104-3-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 66 | HR |  |  |  | 0 | 5940 | 772.2 | 6712.2 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A060-A062 |  |  | A060-A062 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42320191104-3-R01Operator - Principle665940 | Corbiere and Sons Contracting42320191104-3-R01Operator - Principle665940Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5940 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 423 | 20191104-3-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A060-A062 |  |  | A060-A062 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42320191104-3-R01L.O.A.61260 | Corbiere and Sons Contracting42320191104-3-R01L.O.A.61260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 424 | 20191104-4-R01 | 53520101 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A003; Delivery of culverts and geo; orientations for hand fallers. |  |  | A003 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42420191104-4-R01Brusher91822.5 | Corbiere and Sons Contracting42420191104-4-R01Brusher91822.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 424 | 20191104-4-R01 | 53520101 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A003; Delivery of culverts and geo; orientations for hand fallers. |  |  | A003 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42420191104-4-R01Mulcher91845 | Corbiere and Sons Contracting42420191104-4-R01Mulcher91845Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 424 | 20191104-4-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A003; Delivery of culverts and geo; orientations for hand fallers. |  |  | A003 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42420191104-4-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting42420191104-4-R01Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 424 | 20191104-4-R01 | 53520101 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A003; Delivery of culverts and geo; orientations for hand fallers. |  |  | A003 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42420191104-4-R01Foreman121140 | Corbiere and Sons Contracting42420191104-4-R01Foreman121140Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 424 | 20191104-4-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A003; Delivery of culverts and geo; orientations for hand fallers. |  |  | A003 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42420191104-4-R01Operator - Principle221980 | Corbiere and Sons Contracting42420191104-4-R01Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 424 | 20191104-4-R01 | 53520101 | Clearing | 0 | Labourer - Specialized | 75 | 25 | HR |  |  |  | 0 | 1875 | 243.75 | 2118.75 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A003; Delivery of culverts and geo; orientations for hand fallers. |  |  | A003 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42420191104-4-R01Labourer - Specialized251875 | Corbiere and Sons Contracting42420191104-4-R01Labourer - Specialized251875Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1875 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 424 | 20191104-4-R01 | 53520101 | Clearing | 0 | Labourer - General | 65 | 16 | HR |  |  |  | 0 | 1040 | 135.2 | 1175.2 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A003; Delivery of culverts and geo; orientations for hand fallers. |  |  | A003 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42420191104-4-R01Labourer - General161040 | Corbiere and Sons Contracting42420191104-4-R01Labourer - General161040Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1040 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 424 | 20191104-4-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A003; Delivery of culverts and geo; orientations for hand fallers. |  |  | A003 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42420191104-4-R01L.O.A.91890 | Corbiere and Sons Contracting42420191104-4-R01L.O.A.91890Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 425 | 20191104-5-R01 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A010, A013, A014 |  |  | A010, A013, A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42520191104-5-R01Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting42520191104-5-R01Grinder - 4710 Peterson or equal1810022.4Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 425 | 20191104-5-R01 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A010, A013, A014 |  |  | A010, A013, A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42520191104-5-R01Log Loader182754 | Corbiere and Sons Contracting42520191104-5-R01Log Loader182754Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 425 | 20191104-5-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A010, A013, A014 |  |  | A010, A013, A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42520191104-5-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting42520191104-5-R01Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 425 | 20191104-5-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A010, A013, A014 |  |  | A010, A013, A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42520191104-5-R01Operator - Principle221980 | Corbiere and Sons Contracting42520191104-5-R01Operator - Principle221980Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 425 | 20191104-5-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A010, A013, A014 |  |  | A010, A013, A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42520191104-5-R01L.O.A.2420 | Corbiere and Sons Contracting42520191104-5-R01L.O.A.2420Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 428 | 20191104-8 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9.5 | HR | 180 | 0 |  |  | 2280 | 296.4 | 2576.4 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North Shore - Clearing Tower A057 west to Orange-Black. |  |  | A057 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42820191104-8Feller Buncher9.52280 | Corbiere and Sons Contracting42820191104-8Feller Buncher9.52280Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 428 | 20191104-8 | 53520101 | Clearing | 0 | Skidder | 171 | 9.5 | HR | 128.25 | 0 |  |  | 1624.5 | 211.185 | 1835.685 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North Shore - Clearing Tower A057 west to Orange-Black. |  |  | A057 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42820191104-8Skidder 9.51624.5 | Corbiere and Sons Contracting42820191104-8Skidder 9.51624.5Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 428 | 20191104-8 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North Shore - Clearing Tower A057 west to Orange-Black. |  |  | A057 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42820191104-8Light Truck - Pick up30900 | Corbiere and Sons Contracting42820191104-8Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 428 | 20191104-8 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North Shore - Clearing Tower A057 west to Orange-Black. |  |  | A057 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42820191104-8Foreman4380 | Corbiere and Sons Contracting42820191104-8Foreman4380Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 428 | 20191104-8 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North Shore - Clearing Tower A057 west to Orange-Black. |  |  | A057 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42820191104-8Operator - Principle221980 | Corbiere and Sons Contracting42820191104-8Operator - Principle221980Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 428 | 20191104-8 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-04 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North Shore - Clearing Tower A057 west to Orange-Black. |  |  | A057 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting42820191104-8L.O.A.3630 | Corbiere and Sons Contracting42820191104-8L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 431 | 20191105-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting43120191105-1Light Truck - Pick up501500 | Corbiere and Sons Contracting43120191105-1Light Truck - Pick up501500Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 431 | 20191105-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting43120191105-1Project Manager121320 | Corbiere and Sons Contracting43120191105-1Project Manager121320Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 431 | 20191105-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting43120191105-1Superintendent121260 | Corbiere and Sons Contracting43120191105-1Superintendent121260Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 431 | 20191105-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting43120191105-1Project Coordinator12960 | Corbiere and Sons Contracting43120191105-1Project Coordinator12960Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 431 | 20191105-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting43120191105-1Safety Advisor121020 | Corbiere and Sons Contracting43120191105-1Safety Advisor121020Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 431 | 20191105-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting43120191105-1Project Controls12840 | Corbiere and Sons Contracting43120191105-1Project Controls12840Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 431 | 20191105-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting43120191105-1L.O.A.51050 | Corbiere and Sons Contracting43120191105-1L.O.A.51050Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 440 | 20191105-10 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 3.5 | HR | 180 | 6 |  |  | 1920 | 249.6 | 2169.6 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North Shore - Clearing tower A061 - shutdown 11am. |  |  | A061 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting44020191105-10Feller Buncher3.51920 | Corbiere and Sons Contracting44020191105-10Feller Buncher3.51920Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1920 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 440 | 20191105-10 | 53520101 | Clearing | 0 | Skidder | 171 | 3.5 | HR | 128.25 | 6 |  |  | 1368 | 177.84 | 1545.84 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North Shore - Clearing tower A061 - shutdown 11am. |  |  | A061 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting44020191105-10Skidder 3.51368 | Corbiere and Sons Contracting44020191105-10Skidder 3.51368Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1368 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 440 | 20191105-10 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North Shore - Clearing tower A061 - shutdown 11am. |  |  | A061 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting44020191105-10Light Truck - Pick up30900 | Corbiere and Sons Contracting44020191105-10Light Truck - Pick up30900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 440 | 20191105-10 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North Shore - Clearing tower A061 - shutdown 11am. |  |  | A061 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting44020191105-10Foreman4380 | Corbiere and Sons Contracting44020191105-10Foreman4380Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 440 | 20191105-10 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 10 | HR |  |  |  | 0 | 900 | 117 | 1017 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North Shore - Clearing tower A061 - shutdown 11am. |  |  | A061 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting44020191105-10Operator - Principle10900 | Corbiere and Sons Contracting44020191105-10Operator - Principle10900Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 440 | 20191105-10 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | North Shore - Clearing tower A061 - shutdown 11am. |  |  | A061 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting44020191105-10L.O.A.3630 | Corbiere and Sons Contracting44020191105-10L.O.A.3630Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 441 | 20191105-11-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Lem number incorrect; REVISED DK 11152019 Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Mount McKay Heavy Equipment - Josh and Blade Collins laid Geo at A025 East and West |  |  | A025 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting44120191105-11-R01L.O.A.4840 | Corbiere and Sons Contracting44120191105-11-R01L.O.A.4840Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 442 | 20191105-12-R01 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 3 | Day |  | 0 |  |  | 360 | 46.8 | 406.8 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | Chainsaw has incorrect rate REVISED 11152019 DK |  |  |  |  | PTB Logging Inc. Starting from landfill site at doing hand falling. . |  |  |  | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting44220191105-12-R01Chainsaw and consummables3360 | Corbiere and Sons Contracting44220191105-12-R01Chainsaw and consummables3360Inv#002-R01 |  |  | WF1-Handfalling |  |  | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 442 | 20191105-12-R01 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | Chainsaw has incorrect rate REVISED 11152019 DK |  |  |  |  | PTB Logging Inc. Starting from landfill site at doing hand falling. . |  |  |  | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting44220191105-12-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting44220191105-12-R01Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 442 | 20191105-12-R01 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 33 | HR |  |  |  | 0 | 2475 | 321.75 | 2796.75 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | Chainsaw has incorrect rate REVISED 11152019 DK |  |  |  |  | PTB Logging Inc. Starting from landfill site at doing hand falling. . |  |  |  | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting44220191105-12-R01Labourer - Specialized332475 | Corbiere and Sons Contracting44220191105-12-R01Labourer - Specialized332475Inv#002-R01 |  |  | WF1-Handfalling |  |  | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 433 | 20191105-3-R02 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for Chainsaw REVISED 11152019 DK |  |  |  |  | General brushing and mulching for cleanup and handfalling done from A005 West to A003. |  |  | A005-A003 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting43320191105-3-R02Brusher91822.5 | Corbiere and Sons Contracting43320191105-3-R02Brusher91822.5Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 433 | 20191105-3-R02 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for Chainsaw REVISED 11152019 DK |  |  |  |  | General brushing and mulching for cleanup and handfalling done from A005 West to A003. |  |  | A005-A003 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting43320191105-3-R02Mulcher91845 | Corbiere and Sons Contracting43320191105-3-R02Mulcher91845Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 433 | 20191105-3-R02 | 53520102 | Clearing | 0 | Chainsaw and consummables | 120 | 6 | Day |  | 0 |  |  | 720 | 93.6 | 813.6 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for Chainsaw REVISED 11152019 DK |  |  |  |  | General brushing and mulching for cleanup and handfalling done from A005 West to A003. |  |  | A005-A003 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting43320191105-3-R02Chainsaw and consummables6720 | Corbiere and Sons Contracting43320191105-3-R02Chainsaw and consummables6720Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 433 | 20191105-3-R02 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for Chainsaw REVISED 11152019 DK |  |  |  |  | General brushing and mulching for cleanup and handfalling done from A005 West to A003. |  |  | A005-A003 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting43320191105-3-R02Light Truck - Pick up20600 | Corbiere and Sons Contracting43320191105-3-R02Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 433 | 20191105-3-R02 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for Chainsaw REVISED 11152019 DK |  |  |  |  | General brushing and mulching for cleanup and handfalling done from A005 West to A003. |  |  | A005-A003 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting43320191105-3-R02Foreman121140 | Corbiere and Sons Contracting43320191105-3-R02Foreman121140Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 433 | 20191105-3-R02 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for Chainsaw REVISED 11152019 DK |  |  |  |  | General brushing and mulching for cleanup and handfalling done from A005 West to A003. |  |  | A005-A003 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting43320191105-3-R02Operator - Principle221980 | Corbiere and Sons Contracting43320191105-3-R02Operator - Principle221980Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 433 | 20191105-3-R02 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 55 | HR |  |  |  | 0 | 4125 | 536.25 | 4661.25 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for Chainsaw REVISED 11152019 DK |  |  |  |  | General brushing and mulching for cleanup and handfalling done from A005 West to A003. |  |  | A005-A003 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting43320191105-3-R02Labourer - Specialized554125 | Corbiere and Sons Contracting43320191105-3-R02Labourer - Specialized554125Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 433 | 20191105-3-R02 | 53520102 | Clearing | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Incorrect rate for Chainsaw REVISED 11152019 DK |  |  |  |  | General brushing and mulching for cleanup and handfalling done from A005 West to A003. |  |  | A005-A003 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting43320191105-3-R02L.O.A.81680 | Corbiere and Sons Contracting43320191105-3-R02L.O.A.81680Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 434 | 20191105-4-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 14 | HR | 180 | 22 |  |  | 7320 | 951.6 | 8271.6 | 2019-11-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 |  | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | Shutdown by MNRF due to missing permits. |  |  |  | 0 |  |  | 12 | 43843 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting43420191105-4-R01Feller Buncher147320 | Corbiere and Sons Contracting43420191105-4-R01Feller Buncher147320Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 7320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 434 | 20191105-4-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 7 | HR | 128.25 | 11 |  |  | 2607.75 | 339.0075 | 2946.7575 | 2019-11-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 |  | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | Shutdown by MNRF due to missing permits. |  |  |  | 0 |  |  | 12 | 43843 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting43420191105-4-R01Skidder 72607.75 | Corbiere and Sons Contracting43420191105-4-R01Skidder 72607.75Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2607.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 434 | 20191105-4-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2019-11-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 |  | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | Shutdown by MNRF due to missing permits. |  |  |  | 0 |  |  | 12 | 43843 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting43420191105-4-R01Light Truck - Pick up401200 | Corbiere and Sons Contracting43420191105-4-R01Light Truck - Pick up401200Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 434 | 20191105-4-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 30 | HR |  |  |  | 0 | 2700 | 351 | 3051 | 2019-11-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 |  | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | Shutdown by MNRF due to missing permits. |  |  |  | 0 |  |  | 12 | 43843 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting43420191105-4-R01Operator - Principle302700 | Corbiere and Sons Contracting43420191105-4-R01Operator - Principle302700Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 434 | 20191105-4-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 |  | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | Shutdown by MNRF due to missing permits. |  |  |  | 0 |  |  | 12 | 43843 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting43420191105-4-R01L.O.A.51050 | Corbiere and Sons Contracting43420191105-4-R01L.O.A.51050Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 435 | 20191105-5-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Skidding in front of Grinders between A010-A014 |  |  | A010-A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting43520191105-5-R01Skidder 91539 | Corbiere and Sons Contracting43520191105-5-R01Skidder 91539Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 435 | 20191105-5-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Skidding in front of Grinders between A010-A014 |  |  | A010-A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting43520191105-5-R01Operator - Principle11990 | Corbiere and Sons Contracting43520191105-5-R01Operator - Principle11990Inv#002-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 435 | 20191105-5-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Skidding in front of Grinders between A010-A014 |  |  | A010-A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting43520191105-5-R01L.O.A.1210 | Corbiere and Sons Contracting43520191105-5-R01L.O.A.1210Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 436 | 20191105-6-R01 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A010, A013 and A014 |  |  | A010, A013, A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting43620191105-6-R01Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting43620191105-6-R01Grinder - 4710 Peterson or equal1810022.4Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 436 | 20191105-6-R01 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A010, A013 and A014 |  |  | A010, A013, A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting43620191105-6-R01Log Loader182754 | Corbiere and Sons Contracting43620191105-6-R01Log Loader182754Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 436 | 20191105-6-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A010, A013 and A014 |  |  | A010, A013, A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting43620191105-6-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting43620191105-6-R01Light Truck - Pick up20600Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 436 | 20191105-6-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A010, A013 and A014 |  |  | A010, A013, A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting43620191105-6-R01Operator - Principle221980 | Corbiere and Sons Contracting43620191105-6-R01Operator - Principle221980Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 436 | 20191105-6-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-05 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A010, A013 and A014 |  |  | A010, A013, A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting43620191105-6-R01L.O.A.2420 | Corbiere and Sons Contracting43620191105-6-R01L.O.A.2420Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 443 | 20191106-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting44320191106-1Light Truck - Pick up501500 | Corbiere and Sons Contracting44320191106-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 443 | 20191106-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting44320191106-1Project Manager121320 | Corbiere and Sons Contracting44320191106-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 443 | 20191106-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting44320191106-1Superintendent121260 | Corbiere and Sons Contracting44320191106-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 443 | 20191106-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting44320191106-1Project Coordinator12960 | Corbiere and Sons Contracting44320191106-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 443 | 20191106-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting44320191106-1Safety Advisor121020 | Corbiere and Sons Contracting44320191106-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 443 | 20191106-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting44320191106-1Project Controls12840 | Corbiere and Sons Contracting44320191106-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 443 | 20191106-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting44320191106-1L.O.A.51050 | Corbiere and Sons Contracting44320191106-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 452 | 20191106-10-R03 | 53520101 | Clearing | 0 | Feller Buncher | 240 |  | HR | 180 | 9 |  |  | 1620 | 210.6 | 1830.6 | 2019-11-06 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | North Shore - Standby - no Permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting45220191106-10-R03Feller Buncher1620 | Corbiere and Sons Contracting45220191106-10-R03Feller Buncher1620Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1620 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 452 | 20191106-10-R03 | 53520101 | Clearing | 0 | Skidder | 171 |  | HR | 128.25 | 9 |  |  | 1154.25 | 150.0525 | 1304.3025 | 2019-11-06 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | North Shore - Standby - no Permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting45220191106-10-R03Skidder 1154.25 | Corbiere and Sons Contracting45220191106-10-R03Skidder 1154.25Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1154.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 452 | 20191106-10-R03 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 |  | HR | 22.5 | 30 |  |  | 675 | 87.75 | 762.75 | 2019-11-06 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | North Shore - Standby - no Permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting45220191106-10-R03Light Truck - Pick up675 | Corbiere and Sons Contracting45220191106-10-R03Light Truck - Pick up675Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 452 | 20191106-10-R03 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-11-06 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | North Shore - Standby - no Permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting45220191106-10-R03Foreman4380 | Corbiere and Sons Contracting45220191106-10-R03Foreman4380Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 452 | 20191106-10-R03 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 8 | HR |  |  |  | 0 | 720 | 93.6 | 813.6 | 2019-11-06 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | North Shore - Standby - no Permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting45220191106-10-R03Operator - Principle8720 | Corbiere and Sons Contracting45220191106-10-R03Operator - Principle8720Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 452 | 20191106-10-R03 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-06 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | North Shore - Standby - no Permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting45220191106-10-R03L.O.A.3630 | Corbiere and Sons Contracting45220191106-10-R03L.O.A.3630Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 454 | 20191106-12-R01 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 3 | Day |  | 0 |  |  | 360 | 46.8 | 406.8 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | Chainsaw has incorrect rate REVISED 11152019 DK |  |  |  |  | PTB Logging Inc. - Hand falling at railway crossing. |  |  |  | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting45420191106-12-R01Chainsaw and consummables3360 | Corbiere and Sons Contracting45420191106-12-R01Chainsaw and consummables3360Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 454 | 20191106-12-R01 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | Chainsaw has incorrect rate REVISED 11152019 DK |  |  |  |  | PTB Logging Inc. - Hand falling at railway crossing. |  |  |  | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting45420191106-12-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting45420191106-12-R01Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 454 | 20191106-12-R01 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 33 | HR |  |  |  | 0 | 2475 | 321.75 | 2796.75 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | Chainsaw has incorrect rate REVISED 11152019 DK |  |  |  |  | PTB Logging Inc. - Hand falling at railway crossing. |  |  |  | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting45420191106-12-R01Labourer - Specialized332475 | Corbiere and Sons Contracting45420191106-12-R01Labourer - Specialized332475Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 444 | 20191106-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-11-06 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves - orientation |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting44420191106-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting44420191106-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 444 | 20191106-2-R01 | 53520105 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-06 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves - orientation |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting44420191106-2-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting44420191106-2-R01Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 444 | 20191106-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-06 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves - orientation |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting44420191106-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting44420191106-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 444 | 20191106-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-11-06 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves - orientation |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting44420191106-2-R01Operator - Principle121080 | Corbiere and Sons Contracting44420191106-2-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 444 | 20191106-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-06 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves - orientation |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting44420191106-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting44420191106-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 444 | 20191106-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-11-06 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves - orientation |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting44420191106-2-R01Labourer - General10650 | Corbiere and Sons Contracting44420191106-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 444 | 20191106-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-06 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves - orientation |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting44420191106-2-R01L.O.A.2420 | Corbiere and Sons Contracting44420191106-2-R01L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 445 | 20191106-3-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 |  | HR | 180 | 36 |  |  | 6480 | 842.4 | 7322.4 | 2019-11-06 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | Shutdown by MNRF due to missing permits. Clinton Robinson worked as a labourer | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting44520191106-3-R01Feller Buncher6480 | Corbiere and Sons Contracting44520191106-3-R01Feller Buncher6480Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 6480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 445 | 20191106-3-R01 | 53520101 | Clearing | 0 | Skidder | 171 |  | HR | 128.25 | 27 |  |  | 3462.75 | 450.1575 | 3912.9075 | 2019-11-06 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | Shutdown by MNRF due to missing permits. Clinton Robinson worked as a labourer | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting44520191106-3-R01Skidder 3462.75 | Corbiere and Sons Contracting44520191106-3-R01Skidder 3462.75Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3462.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 445 | 20191106-3-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 |  | HR | 22.5 | 40 |  |  | 900 | 117 | 1017 | 2019-11-06 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | Shutdown by MNRF due to missing permits. Clinton Robinson worked as a labourer | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting44520191106-3-R01Light Truck - Pick up900 | Corbiere and Sons Contracting44520191106-3-R01Light Truck - Pick up900Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 445 | 20191106-3-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 24 | HR |  |  |  | 0 | 2160 | 280.8 | 2440.8 | 2019-11-06 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | Shutdown by MNRF due to missing permits. Clinton Robinson worked as a labourer | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting44520191106-3-R01Operator - Principle242160 | Corbiere and Sons Contracting44520191106-3-R01Operator - Principle242160Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 445 | 20191106-3-R01 | 53520101 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-11-06 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | Shutdown by MNRF due to missing permits. Clinton Robinson worked as a labourer | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting44520191106-3-R01Labourer - General11715 | Corbiere and Sons Contracting44520191106-3-R01Labourer - General11715Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 445 | 20191106-3-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-06 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | Shutdown by MNRF due to missing permits. Clinton Robinson worked as a labourer | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting44520191106-3-R01L.O.A.61260 | Corbiere and Sons Contracting44520191106-3-R01L.O.A.61260Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 446 | 20191106-4-R01 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A012 |  |  | A012 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting44620191106-4-R01Mulcher91845 | Corbiere and Sons Contracting44620191106-4-R01Mulcher91845Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 446 | 20191106-4-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A012 |  |  | A012 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting44620191106-4-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting44620191106-4-R01Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 446 | 20191106-4-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A012 |  |  | A012 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting44620191106-4-R01Operator - Principle11990 | Corbiere and Sons Contracting44620191106-4-R01Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 446 | 20191106-4-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A012 |  |  | A012 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting44620191106-4-R01L.O.A.1210 | Corbiere and Sons Contracting44620191106-4-R01L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 447 | 20191106-5-R01 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A010, A013, A014 |  |  | A010, A013, A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting44720191106-5-R01Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting44720191106-5-R01Grinder - 4710 Peterson or equal1810022.4Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 447 | 20191106-5-R01 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A010, A013, A014 |  |  | A010, A013, A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting44720191106-5-R01Log Loader182754 | Corbiere and Sons Contracting44720191106-5-R01Log Loader182754Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 447 | 20191106-5-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A010, A013, A014 |  |  | A010, A013, A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting44720191106-5-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting44720191106-5-R01Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 447 | 20191106-5-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A010, A013, A014 |  |  | A010, A013, A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting44720191106-5-R01Operator - Principle221980 | Corbiere and Sons Contracting44720191106-5-R01Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 447 | 20191106-5-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A010, A013, A014 |  |  | A010, A013, A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting44720191106-5-R01L.O.A.2420 | Corbiere and Sons Contracting44720191106-5-R01L.O.A.2420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 451 | 20191106-9-R02 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Chainsaws have incorrect rate; REVISED 11152019 DK |  |  |  |  | Completed to tower A006, Working on Railway Crossing. |  |  | A006 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting45120191106-9-R02Brusher91822.5 | Corbiere and Sons Contracting45120191106-9-R02Brusher91822.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 451 | 20191106-9-R02 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Chainsaws have incorrect rate; REVISED 11152019 DK |  |  |  |  | Completed to tower A006, Working on Railway Crossing. |  |  | A006 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting45120191106-9-R02Mulcher91845 | Corbiere and Sons Contracting45120191106-9-R02Mulcher91845Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 451 | 20191106-9-R02 | 53520102 | Clearing | 0 | Chainsaw and consummables | 120 | 6 | Day |  | 0 |  |  | 720 | 93.6 | 813.6 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Chainsaws have incorrect rate; REVISED 11152019 DK |  |  |  |  | Completed to tower A006, Working on Railway Crossing. |  |  | A006 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting45120191106-9-R02Chainsaw and consummables6720 | Corbiere and Sons Contracting45120191106-9-R02Chainsaw and consummables6720Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 451 | 20191106-9-R02 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Chainsaws have incorrect rate; REVISED 11152019 DK |  |  |  |  | Completed to tower A006, Working on Railway Crossing. |  |  | A006 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting45120191106-9-R02Light Truck - Pick up30900 | Corbiere and Sons Contracting45120191106-9-R02Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 451 | 20191106-9-R02 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Chainsaws have incorrect rate; REVISED 11152019 DK |  |  |  |  | Completed to tower A006, Working on Railway Crossing. |  |  | A006 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting45120191106-9-R02Foreman121140 | Corbiere and Sons Contracting45120191106-9-R02Foreman121140Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 451 | 20191106-9-R02 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Chainsaws have incorrect rate; REVISED 11152019 DK |  |  |  |  | Completed to tower A006, Working on Railway Crossing. |  |  | A006 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting45120191106-9-R02Operator - Principle221980 | Corbiere and Sons Contracting45120191106-9-R02Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 451 | 20191106-9-R02 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 55 | HR |  |  |  | 0 | 4125 | 536.25 | 4661.25 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Chainsaws have incorrect rate; REVISED 11152019 DK |  |  |  |  | Completed to tower A006, Working on Railway Crossing. |  |  | A006 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting45120191106-9-R02Labourer - Specialized554125 | Corbiere and Sons Contracting45120191106-9-R02Labourer - Specialized554125Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 451 | 20191106-9-R02 | 53520102 | Clearing | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2019-11-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Chainsaws have incorrect rate; REVISED 11152019 DK |  |  |  |  | Completed to tower A006, Working on Railway Crossing. |  |  | A006 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting45120191106-9-R02L.O.A.81680 | Corbiere and Sons Contracting45120191106-9-R02L.O.A.81680Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 455 | 20191107-01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting45520191107-01Light Truck - Pick up501500 | Corbiere and Sons Contracting45520191107-01Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 455 | 20191107-01 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting45520191107-01Project Manager121320 | Corbiere and Sons Contracting45520191107-01Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 455 | 20191107-01 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting45520191107-01Superintendent121260 | Corbiere and Sons Contracting45520191107-01Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 455 | 20191107-01 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 11 | HR |  |  |  | 0 | 880 | 114.4 | 994.4 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting45520191107-01Project Coordinator11880 | Corbiere and Sons Contracting45520191107-01Project Coordinator11880Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 455 | 20191107-01 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting45520191107-01Safety Advisor121020 | Corbiere and Sons Contracting45520191107-01Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 455 | 20191107-01 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting45520191107-01Project Controls12840 | Corbiere and Sons Contracting45520191107-01Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 455 | 20191107-01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting45520191107-01L.O.A.51050 | Corbiere and Sons Contracting45520191107-01L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 457 | 20191107-03-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 |  | HR | 180 | 45 |  |  | 8100 | 1053 | 9153 | 2019-11-07 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Light Truck standby rate is incorrect REVISED 11152019 DK | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43853 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting45720191107-03-R01Feller Buncher8100 | Corbiere and Sons Contracting45720191107-03-R01Feller Buncher8100Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 8100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 457 | 20191107-03-R01 | 53520101 | Clearing | 0 | Skidder | 171 |  | HR | 128.25 | 27 |  |  | 3462.75 | 450.1575 | 3912.9075 | 2019-11-07 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Light Truck standby rate is incorrect REVISED 11152019 DK | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43853 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting45720191107-03-R01Skidder 3462.75 | Corbiere and Sons Contracting45720191107-03-R01Skidder 3462.75Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3462.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 457 | 20191107-03-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 |  | HR | 22.5 | 60 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-07 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Light Truck standby rate is incorrect REVISED 11152019 DK | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43853 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting45720191107-03-R01Light Truck - Pick up1350 | Corbiere and Sons Contracting45720191107-03-R01Light Truck - Pick up1350Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 457 | 20191107-03-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 32 | HR |  |  |  | 0 | 2880 | 374.4 | 3254.4 | 2019-11-07 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Light Truck standby rate is incorrect REVISED 11152019 DK | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43853 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting45720191107-03-R01Operator - Principle322880 | Corbiere and Sons Contracting45720191107-03-R01Operator - Principle322880Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2880 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 457 | 20191107-03-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2019-11-07 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Light Truck standby rate is incorrect REVISED 11152019 DK | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43853 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting45720191107-03-R01L.O.A.81680 | Corbiere and Sons Contracting45720191107-03-R01L.O.A.81680Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 460 | 20191107-06 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9.5 | HR | 417.6 | 0 |  |  | 5289.6 | 687.648 | 5977.248 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grindging material at A019 |  |  | A019 | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting46020191107-06Grinder - 4710 Peterson or equal9.55289.6 | Corbiere and Sons Contracting46020191107-06Grinder - 4710 Peterson or equal9.55289.6Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5289.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 460 | 20191107-06 | 53520102 | Clearing | 0 | Log Loader | 153 | 9.5 | HR | 114.75 | 0 |  |  | 1453.5 | 188.955 | 1642.455 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grindging material at A019 |  |  | A019 | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting46020191107-06Log Loader9.51453.5 | Corbiere and Sons Contracting46020191107-06Log Loader9.51453.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1453.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 460 | 20191107-06 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grindging material at A019 |  |  | A019 | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting46020191107-06Light Truck - Pick up10300 | Corbiere and Sons Contracting46020191107-06Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 460 | 20191107-06 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grindging material at A019 |  |  | A019 | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting46020191107-06Operator - Principle11990 | Corbiere and Sons Contracting46020191107-06Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 460 | 20191107-06 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grindging material at A019 |  |  | A019 | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting46020191107-06L.O.A.1210 | Corbiere and Sons Contracting46020191107-06L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 456 | 20191107-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-11-07 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves - orientation Todd Hurdon. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting45620191107-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting45620191107-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 456 | 20191107-2-R01 | 53520105 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-07 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves - orientation Todd Hurdon. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting45620191107-2-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting45620191107-2-R01Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 456 | 20191107-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-07 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves - orientation Todd Hurdon. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting45620191107-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting45620191107-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 456 | 20191107-2-R01 | 53520105 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-11-07 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves - orientation Todd Hurdon. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting45620191107-2-R01Foreman4380 | Corbiere and Sons Contracting45620191107-2-R01Foreman4380Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 456 | 20191107-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-11-07 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves - orientation Todd Hurdon. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting45620191107-2-R01Operator - Principle121080 | Corbiere and Sons Contracting45620191107-2-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 456 | 20191107-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-07 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves - orientation Todd Hurdon. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting45620191107-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting45620191107-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 456 | 20191107-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-11-07 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves - orientation Todd Hurdon. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting45620191107-2-R01Labourer - General10650 | Corbiere and Sons Contracting45620191107-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 456 | 20191107-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-07 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves - orientation Todd Hurdon. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting45620191107-2-R01L.O.A.3630 | Corbiere and Sons Contracting45620191107-2-R01L.O.A.3630Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 458 | 20191107-4-R02 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing between A006-Ao10, Brushing, mulching and hand falling. |  |  | A006-A010 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting45820191107-4-R02Brusher91822.5 | Corbiere and Sons Contracting45820191107-4-R02Brusher91822.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 458 | 20191107-4-R02 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing between A006-Ao10, Brushing, mulching and hand falling. |  |  | A006-A010 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting45820191107-4-R02Mulcher91845 | Corbiere and Sons Contracting45820191107-4-R02Mulcher91845Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 458 | 20191107-4-R02 | 53520102 | Clearing | 0 | Chainsaw and consummables | 120 | 9 | Day |  | 0 |  |  | 1080 | 140.4 | 1220.4 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing between A006-Ao10, Brushing, mulching and hand falling. |  |  | A006-A010 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting45820191107-4-R02Chainsaw and consummables91080 | Corbiere and Sons Contracting45820191107-4-R02Chainsaw and consummables91080Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 458 | 20191107-4-R02 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing between A006-Ao10, Brushing, mulching and hand falling. |  |  | A006-A010 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting45820191107-4-R02Light Truck - Pick up401200 | Corbiere and Sons Contracting45820191107-4-R02Light Truck - Pick up401200Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 458 | 20191107-4-R02 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing between A006-Ao10, Brushing, mulching and hand falling. |  |  | A006-A010 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting45820191107-4-R02Foreman121140 | Corbiere and Sons Contracting45820191107-4-R02Foreman121140Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 458 | 20191107-4-R02 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing between A006-Ao10, Brushing, mulching and hand falling. |  |  | A006-A010 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting45820191107-4-R02Operator - Principle221980 | Corbiere and Sons Contracting45820191107-4-R02Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 458 | 20191107-4-R02 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 83 | HR |  |  |  | 0 | 6225 | 809.25 | 7034.25 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing between A006-Ao10, Brushing, mulching and hand falling. |  |  | A006-A010 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting45820191107-4-R02Labourer - Specialized836225 | Corbiere and Sons Contracting45820191107-4-R02Labourer - Specialized836225Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 6225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 458 | 20191107-4-R02 | 53520102 | Clearing | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing between A006-Ao10, Brushing, mulching and hand falling. |  |  | A006-A010 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting45820191107-4-R02L.O.A.81680 | Corbiere and Sons Contracting45820191107-4-R02L.O.A.81680Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 459 | 20191107-5-R01 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material and mulching at A014 |  |  | A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting45920191107-5-R01Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting45920191107-5-R01Grinder - 4710 Peterson or equal95011.2Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 459 | 20191107-5-R01 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material and mulching at A014 |  |  | A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting45920191107-5-R01Log Loader91377 | Corbiere and Sons Contracting45920191107-5-R01Log Loader91377Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 459 | 20191107-5-R01 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material and mulching at A014 |  |  | A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting45920191107-5-R01Mulcher91845 | Corbiere and Sons Contracting45920191107-5-R01Mulcher91845Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 459 | 20191107-5-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material and mulching at A014 |  |  | A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting45920191107-5-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting45920191107-5-R01Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 459 | 20191107-5-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material and mulching at A014 |  |  | A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting45920191107-5-R01Operator - Principle221980 | Corbiere and Sons Contracting45920191107-5-R01Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 459 | 20191107-5-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-07 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material and mulching at A014 |  |  | A014 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting45920191107-5-R01L.O.A.2420 | Corbiere and Sons Contracting45920191107-5-R01L.O.A.2420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 465 | 20191108-01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Need to create supervision cost code |  |  |  |  | Supervision |  |  | 100 Wolf River Road, Dorion, Ontario P0T 1K0 | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting46520191108-01Light Truck - Pick up501500 | Corbiere and Sons Contracting46520191108-01Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 465 | 20191108-01 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Need to create supervision cost code |  |  |  |  | Supervision |  |  | 100 Wolf River Road, Dorion, Ontario P0T 1K0 | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting46520191108-01Project Manager121320 | Corbiere and Sons Contracting46520191108-01Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 465 | 20191108-01 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Need to create supervision cost code |  |  |  |  | Supervision |  |  | 100 Wolf River Road, Dorion, Ontario P0T 1K0 | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting46520191108-01Superintendent121260 | Corbiere and Sons Contracting46520191108-01Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 465 | 20191108-01 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Need to create supervision cost code |  |  |  |  | Supervision |  |  | 100 Wolf River Road, Dorion, Ontario P0T 1K0 | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting46520191108-01Project Coordinator12960 | Corbiere and Sons Contracting46520191108-01Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 465 | 20191108-01 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Need to create supervision cost code |  |  |  |  | Supervision |  |  | 100 Wolf River Road, Dorion, Ontario P0T 1K0 | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting46520191108-01Safety Advisor121020 | Corbiere and Sons Contracting46520191108-01Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 465 | 20191108-01 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Need to create supervision cost code |  |  |  |  | Supervision |  |  | 100 Wolf River Road, Dorion, Ontario P0T 1K0 | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting46520191108-01Project Controls12840 | Corbiere and Sons Contracting46520191108-01Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 465 | 20191108-01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Need to create supervision cost code |  |  |  |  | Supervision |  |  | 100 Wolf River Road, Dorion, Ontario P0T 1K0 | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting46520191108-01L.O.A.51050 | Corbiere and Sons Contracting46520191108-01L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 469 | 20191108-03-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 |  | HR | 180 | 45 |  |  | 8100 | 1053 | 9153 | 2019-11-08 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | remove 1 feller buncher | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits |  |  | Elderado Road | 0 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting46920191108-03-R01Feller Buncher8100 | Corbiere and Sons Contracting46920191108-03-R01Feller Buncher8100Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 8100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 469 | 20191108-03-R01 | 53520101 | Clearing | 0 | Skidder | 171 |  | HR | 128.25 | 27 |  |  | 3462.75 | 450.1575 | 3912.9075 | 2019-11-08 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | remove 1 feller buncher | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits |  |  | Elderado Road | 0 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting46920191108-03-R01Skidder 3462.75 | Corbiere and Sons Contracting46920191108-03-R01Skidder 3462.75Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3462.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 469 | 20191108-03-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 |  | HR | 22.5 | 40 |  |  | 900 | 117 | 1017 | 2019-11-08 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | remove 1 feller buncher | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits |  |  | Elderado Road | 0 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting46920191108-03-R01Light Truck - Pick up900 | Corbiere and Sons Contracting46920191108-03-R01Light Truck - Pick up900Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 469 | 20191108-03-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 16 | HR |  |  |  | 0 | 1440 | 187.2 | 1627.2 | 2019-11-08 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | remove 1 feller buncher | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits |  |  | Elderado Road | 0 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting46920191108-03-R01Operator - Principle161440 | Corbiere and Sons Contracting46920191108-03-R01Operator - Principle161440Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 469 | 20191108-03-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-08 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | remove 1 feller buncher | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits |  |  | Elderado Road | 0 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting46920191108-03-R01L.O.A.4840 | Corbiere and Sons Contracting46920191108-03-R01L.O.A.4840Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 471 | 20191108-05 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9.5 | HR | 417.6 | 0 |  |  | 5289.6 | 687.648 | 5977.248 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding and Raking at A019-A020 |  |  | Shuniah Road | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting47120191108-05Grinder - 4710 Peterson or equal9.55289.6 | Corbiere and Sons Contracting47120191108-05Grinder - 4710 Peterson or equal9.55289.6Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5289.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 471 | 20191108-05 | 53520102 | Clearing | 0 | Log Loader | 153 | 9.5 | HR | 114.75 | 0 |  |  | 1453.5 | 188.955 | 1642.455 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding and Raking at A019-A020 |  |  | Shuniah Road | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting47120191108-05Log Loader9.51453.5 | Corbiere and Sons Contracting47120191108-05Log Loader9.51453.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1453.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 471 | 20191108-05 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9.5 | HR | 128.25 | 0 |  |  | 1624.5 | 211.185 | 1835.685 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding and Raking at A019-A020 |  |  | Shuniah Road | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting47120191108-05Excavator - 36 ton9.51624.5 | Corbiere and Sons Contracting47120191108-05Excavator - 36 ton9.51624.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 471 | 20191108-05 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding and Raking at A019-A020 |  |  | Shuniah Road | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting47120191108-05Light Truck - Pick up10300 | Corbiere and Sons Contracting47120191108-05Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 471 | 20191108-05 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding and Raking at A019-A020 |  |  | Shuniah Road | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting47120191108-05Operator - Principle221980 | Corbiere and Sons Contracting47120191108-05Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 471 | 20191108-05 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding and Raking at A019-A020 |  |  | Shuniah Road | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting47120191108-05L.O.A.2420 | Corbiere and Sons Contracting47120191108-05L.O.A.2420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 468 | 20191108-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-11-08 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General Yard and equipment maintenance - float moves - orientation |  |  | 100 Wolf River Road, Dorion, Ontario P0T 1K0 | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting46820191108-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting46820191108-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 468 | 20191108-2-R01 | 53520105 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-08 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General Yard and equipment maintenance - float moves - orientation |  |  | 100 Wolf River Road, Dorion, Ontario P0T 1K0 | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting46820191108-2-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting46820191108-2-R01Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 468 | 20191108-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-08 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General Yard and equipment maintenance - float moves - orientation |  |  | 100 Wolf River Road, Dorion, Ontario P0T 1K0 | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting46820191108-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting46820191108-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 468 | 20191108-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 17 | HR |  |  |  | 0 | 1530 | 198.9 | 1728.9 | 2019-11-08 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General Yard and equipment maintenance - float moves - orientation |  |  | 100 Wolf River Road, Dorion, Ontario P0T 1K0 | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting46820191108-2-R01Operator - Principle171530 | Corbiere and Sons Contracting46820191108-2-R01Operator - Principle171530Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1530 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 468 | 20191108-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-08 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General Yard and equipment maintenance - float moves - orientation |  |  | 100 Wolf River Road, Dorion, Ontario P0T 1K0 | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting46820191108-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting46820191108-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 468 | 20191108-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-11-08 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General Yard and equipment maintenance - float moves - orientation |  |  | 100 Wolf River Road, Dorion, Ontario P0T 1K0 | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting46820191108-2-R01Labourer - General10650 | Corbiere and Sons Contracting46820191108-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 468 | 20191108-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-08 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General Yard and equipment maintenance - float moves - orientation |  |  | 100 Wolf River Road, Dorion, Ontario P0T 1K0 | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting46820191108-2-R01L.O.A.3630 | Corbiere and Sons Contracting46820191108-2-R01L.O.A.3630Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 470 | 20191108-4-R01 | 53520102 | Clearing | 0 | Brusher | 202.5 | 21 | HR | 151.88 | 0 |  |  | 4252.5 | 552.825 | 4805.325 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Touch ups and chainsaw workd from A010 to A013 |  |  | MacGregor East | 0 |  |  | 12 | 43814 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting47020191108-4-R01Brusher214252.5 | Corbiere and Sons Contracting47020191108-4-R01Brusher214252.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4252.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 470 | 20191108-4-R01 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Touch ups and chainsaw workd from A010 to A013 |  |  | MacGregor East | 0 |  |  | 12 | 43814 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting47020191108-4-R01Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting47020191108-4-R01Grinder - 4710 Peterson or equal95011.2Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 470 | 20191108-4-R01 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Touch ups and chainsaw workd from A010 to A013 |  |  | MacGregor East | 0 |  |  | 12 | 43814 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting47020191108-4-R01Log Loader91377 | Corbiere and Sons Contracting47020191108-4-R01Log Loader91377Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 470 | 20191108-4-R01 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Touch ups and chainsaw workd from A010 to A013 |  |  | MacGregor East | 0 |  |  | 12 | 43814 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting47020191108-4-R01Mulcher91845 | Corbiere and Sons Contracting47020191108-4-R01Mulcher91845Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 470 | 20191108-4-R01 | 53520102 | Clearing | 0 | Chainsaw and consummables | 120 | 9 | Day |  | 0 |  |  | 1080 | 140.4 | 1220.4 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Touch ups and chainsaw workd from A010 to A013 |  |  | MacGregor East | 0 |  |  | 12 | 43814 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting47020191108-4-R01Chainsaw and consummables91080 | Corbiere and Sons Contracting47020191108-4-R01Chainsaw and consummables91080Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 470 | 20191108-4-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Touch ups and chainsaw workd from A010 to A013 |  |  | MacGregor East | 0 |  |  | 12 | 43814 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting47020191108-4-R01Light Truck - Pick up601800 | Corbiere and Sons Contracting47020191108-4-R01Light Truck - Pick up601800Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 470 | 20191108-4-R01 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Touch ups and chainsaw workd from A010 to A013 |  |  | MacGregor East | 0 |  |  | 12 | 43814 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting47020191108-4-R01Foreman121140 | Corbiere and Sons Contracting47020191108-4-R01Foreman121140Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 470 | 20191108-4-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Touch ups and chainsaw workd from A010 to A013 |  |  | MacGregor East | 0 |  |  | 12 | 43814 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting47020191108-4-R01Operator - Principle443960 | Corbiere and Sons Contracting47020191108-4-R01Operator - Principle443960Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 470 | 20191108-4-R01 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 105 | HR |  |  |  | 0 | 7875 | 1023.75 | 8898.75 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Touch ups and chainsaw workd from A010 to A013 |  |  | MacGregor East | 0 |  |  | 12 | 43814 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting47020191108-4-R01Labourer - Specialized1057875 | Corbiere and Sons Contracting47020191108-4-R01Labourer - Specialized1057875Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 7875 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 470 | 20191108-4-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 12 | DAY |  |  |  | 0 | 2520 | 327.6 | 2847.6 | 2019-11-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Touch ups and chainsaw workd from A010 to A013 |  |  | MacGregor East | 0 |  |  | 12 | 43814 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting47020191108-4-R01L.O.A.122520 | Corbiere and Sons Contracting47020191108-4-R01L.O.A.122520Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2520 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 466 | 20191109-01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 0 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Supervision code needs to be created to capture coding |  |  |  |  | Supervision |  |  | 100 Wolf River Road, Dorion, Ontario P0T 1K0 | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting46620191109-01Light Truck - Pick up501500 | Corbiere and Sons Contracting46620191109-01Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 466 | 20191109-01 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  | 0 | 0 | 1320 | 171.6 | 1491.6 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Supervision code needs to be created to capture coding |  |  |  |  | Supervision |  |  | 100 Wolf River Road, Dorion, Ontario P0T 1K0 | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting46620191109-01Project Manager121320 | Corbiere and Sons Contracting46620191109-01Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 466 | 20191109-01 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  | 0 | 0 | 1260 | 163.8 | 1423.8 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Supervision code needs to be created to capture coding |  |  |  |  | Supervision |  |  | 100 Wolf River Road, Dorion, Ontario P0T 1K0 | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting46620191109-01Superintendent121260 | Corbiere and Sons Contracting46620191109-01Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 466 | 20191109-01 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  | 0 | 0 | 960 | 124.8 | 1084.8 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Supervision code needs to be created to capture coding |  |  |  |  | Supervision |  |  | 100 Wolf River Road, Dorion, Ontario P0T 1K0 | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting46620191109-01Project Coordinator12960 | Corbiere and Sons Contracting46620191109-01Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 466 | 20191109-01 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  | 0 | 0 | 1020 | 132.6 | 1152.6 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Supervision code needs to be created to capture coding |  |  |  |  | Supervision |  |  | 100 Wolf River Road, Dorion, Ontario P0T 1K0 | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting46620191109-01Safety Advisor121020 | Corbiere and Sons Contracting46620191109-01Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 466 | 20191109-01 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  | 0 | 0 | 840 | 109.2 | 949.2 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Supervision code needs to be created to capture coding |  |  |  |  | Supervision |  |  | 100 Wolf River Road, Dorion, Ontario P0T 1K0 | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting46620191109-01Project Controls12840 | Corbiere and Sons Contracting46620191109-01Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 466 | 20191109-01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  | 0 | 0 | 1050 | 136.5 | 1186.5 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Supervision code needs to be created to capture coding |  |  |  |  | Supervision |  |  | 100 Wolf River Road, Dorion, Ontario P0T 1K0 | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting46620191109-01L.O.A.51050 | Corbiere and Sons Contracting46620191109-01L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 477 | 20191109-03-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 |  | HR | 180 | 45 |  |  | 8100 | 1053 | 9153 | 2019-11-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting47720191109-03-R01Feller Buncher8100 | Corbiere and Sons Contracting47720191109-03-R01Feller Buncher8100Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 8100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 477 | 20191109-03-R01 | 53520101 | Clearing | 0 | Skidder | 171 |  | HR | 128.25 | 27 |  |  | 3462.75 | 450.1575 | 3912.9075 | 2019-11-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting47720191109-03-R01Skidder 3462.75 | Corbiere and Sons Contracting47720191109-03-R01Skidder 3462.75Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3462.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 477 | 20191109-03-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 |  | HR | 22.5 | 40 |  |  | 900 | 117 | 1017 | 2019-11-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting47720191109-03-R01Light Truck - Pick up900 | Corbiere and Sons Contracting47720191109-03-R01Light Truck - Pick up900Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 477 | 20191109-03-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 16 | HR |  |  |  | 0 | 1440 | 187.2 | 1627.2 | 2019-11-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting47720191109-03-R01Operator - Principle161440 | Corbiere and Sons Contracting47720191109-03-R01Operator - Principle161440Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 477 | 20191109-03-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-09 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting47720191109-03-R01L.O.A.4840 | Corbiere and Sons Contracting47720191109-03-R01L.O.A.4840Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1031 | 20191109-05-SplitA | 53520102 | Clearing | 0 | L.O.A. | 210 | 0.16476 | DAY |  |  | 0 | 0 | 34.5996 | 4.4979 | 39.0975 | 2019-11-09 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | This LEM was split for invoicing on inv#002 - Sencond part of LEM is labelled SplitB |  |  |  |  | Grinding and Raking at A019-A020 |  |  | Shuniah Road | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting103120191109-05-SplitAL.O.A.0.1647634.5996 | Corbiere and Sons Contracting103120191109-05-SplitAL.O.A.0.1647634.5996Inv#002-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 34.5996 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 479 | 20191109-05-SplitB | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9.5 | HR | 417.6 | 0 |  |  | 5289.6 | 687.648 | 5977.248 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | This LEM was split for invoicing on inv#004 - Sencond part of LEM is labelled SplitA |  |  |  |  | Grinding and Raking at A019-A020 |  |  | Shuniah Road | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting47920191109-05-SplitBGrinder - 4710 Peterson or equal9.55289.6 | Corbiere and Sons Contracting47920191109-05-SplitBGrinder - 4710 Peterson or equal9.55289.6Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5289.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 479 | 20191109-05-SplitB | 53520102 | Clearing | 0 | Log Loader | 153 | 9.5 | HR | 114.75 | 0 |  |  | 1453.5 | 188.955 | 1642.455 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | This LEM was split for invoicing on inv#004 - Sencond part of LEM is labelled SplitA |  |  |  |  | Grinding and Raking at A019-A020 |  |  | Shuniah Road | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting47920191109-05-SplitBLog Loader9.51453.5 | Corbiere and Sons Contracting47920191109-05-SplitBLog Loader9.51453.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1453.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 479 | 20191109-05-SplitB | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | This LEM was split for invoicing on inv#004 - Sencond part of LEM is labelled SplitA |  |  |  |  | Grinding and Raking at A019-A020 |  |  | Shuniah Road | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting47920191109-05-SplitBLight Truck - Pick up10300 | Corbiere and Sons Contracting47920191109-05-SplitBLight Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 479 | 20191109-05-SplitB | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | This LEM was split for invoicing on inv#004 - Sencond part of LEM is labelled SplitA |  |  |  |  | Grinding and Raking at A019-A020 |  |  | Shuniah Road | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting47920191109-05-SplitBOperator - Principle11990 | Corbiere and Sons Contracting47920191109-05-SplitBOperator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 479 | 20191109-05-SplitB | 53520102 | Clearing | 0 | L.O.A. | 210 | 0.83524 | DAY |  |  |  | 0 | 175.4004 | 22.8021 | 198.2025 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | This LEM was split for invoicing on inv#004 - Sencond part of LEM is labelled SplitA |  |  |  |  | Grinding and Raking at A019-A020 |  |  | Shuniah Road | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting47920191109-05-SplitBL.O.A.0.83524175.4004 | Corbiere and Sons Contracting47920191109-05-SplitBL.O.A.0.83524175.4004Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 175.4004 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 480 | 20191109-06-R01 | 53510112 | Access | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow cover overnight; D6 plowing roads from tower A007 to A010, did plowing from highway to A045 near Beck road and back to A009. Raking done at A010 |  |  | MacGregor West | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting48020191109-06-R01Dozer D6 or equal91215 | Corbiere and Sons Contracting48020191109-06-R01Dozer D6 or equal91215Inv#004-R02 | [5 empty] | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 480 | 20191109-06-R01 | 53510112 | Access | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow cover overnight; D6 plowing roads from tower A007 to A010, did plowing from highway to A045 near Beck road and back to A009. Raking done at A010 |  |  | MacGregor West | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting48020191109-06-R01Excavator - 30 ton91255.5 | Corbiere and Sons Contracting48020191109-06-R01Excavator - 30 ton91255.5Inv#004-R02 | [5 empty] | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 480 | 20191109-06-R01 | 53510112 | Access | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow cover overnight; D6 plowing roads from tower A007 to A010, did plowing from highway to A045 near Beck road and back to A009. Raking done at A010 |  |  | MacGregor West | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting48020191109-06-R01Light Truck - Pick up30900 | Corbiere and Sons Contracting48020191109-06-R01Light Truck - Pick up30900Inv#004-R02 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 480 | 20191109-06-R01 | 53510112 | Access | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow cover overnight; D6 plowing roads from tower A007 to A010, did plowing from highway to A045 near Beck road and back to A009. Raking done at A010 |  |  | MacGregor West | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting48020191109-06-R01Foreman121140 | Corbiere and Sons Contracting48020191109-06-R01Foreman121140Inv#004-R02 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 480 | 20191109-06-R01 | 53510112 | Access | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow cover overnight; D6 plowing roads from tower A007 to A010, did plowing from highway to A045 near Beck road and back to A009. Raking done at A010 |  |  | MacGregor West | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting48020191109-06-R01Operator - Principle221980 | Corbiere and Sons Contracting48020191109-06-R01Operator - Principle221980Inv#004-R02 | [5 empty] | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 480 | 20191109-06-R01 | 53510112 | Access | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow cover overnight; D6 plowing roads from tower A007 to A010, did plowing from highway to A045 near Beck road and back to A009. Raking done at A010 |  |  | MacGregor West | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting48020191109-06-R01Labourer - General11715 | Corbiere and Sons Contracting48020191109-06-R01Labourer - General11715Inv#004-R02 | [5 empty] | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 480 | 20191109-06-R01 | 53510112 | Access | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow cover overnight; D6 plowing roads from tower A007 to A010, did plowing from highway to A045 near Beck road and back to A009. Raking done at A010 |  |  | MacGregor West | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting48020191109-06-R01Labourer - General11715 | Corbiere and Sons Contracting48020191109-06-R01Labourer - General11715Inv#004-R02 | [5 empty] | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 480 | 20191109-06-R01 | 53510112 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow cover overnight; D6 plowing roads from tower A007 to A010, did plowing from highway to A045 near Beck road and back to A009. Raking done at A010 |  |  | MacGregor West | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting48020191109-06-R01L.O.A.51050 | Corbiere and Sons Contracting48020191109-06-R01L.O.A.51050Inv#004-R02 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 476 | 20191109-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-11-09 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General Yard and equipment maintenance - float moves |  |  | 100 Wolf River Road, Dorion, Ontario P0T1K0 | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting47620191109-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting47620191109-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 476 | 20191109-2-R01 | 53520105 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-09 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General Yard and equipment maintenance - float moves |  |  | 100 Wolf River Road, Dorion, Ontario P0T1K0 | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting47620191109-2-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting47620191109-2-R01Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 476 | 20191109-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-09 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General Yard and equipment maintenance - float moves |  |  | 100 Wolf River Road, Dorion, Ontario P0T1K0 | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting47620191109-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting47620191109-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 476 | 20191109-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-11-09 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General Yard and equipment maintenance - float moves |  |  | 100 Wolf River Road, Dorion, Ontario P0T1K0 | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting47620191109-2-R01Operator - Principle121080 | Corbiere and Sons Contracting47620191109-2-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 476 | 20191109-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-09 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General Yard and equipment maintenance - float moves |  |  | 100 Wolf River Road, Dorion, Ontario P0T1K0 | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting47620191109-2-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting47620191109-2-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 476 | 20191109-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-11-09 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General Yard and equipment maintenance - float moves |  |  | 100 Wolf River Road, Dorion, Ontario P0T1K0 | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting47620191109-2-R01Labourer - General10650 | Corbiere and Sons Contracting47620191109-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 476 | 20191109-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-09 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General Yard and equipment maintenance - float moves |  |  | 100 Wolf River Road, Dorion, Ontario P0T1K0 | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting47620191109-2-R01L.O.A.2420 | Corbiere and Sons Contracting47620191109-2-R01L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 478 | 20191109-4-R01 | 53520102 | Clearing | 0 | Brusher | 202.5 | 27 | HR | 151.88 | 0 |  |  | 5467.5 | 710.775 | 6178.275 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Touch ups and Chainsaw work from A010 to A013 |  |  | MacGregor East | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting47820191109-4-R01Brusher275467.5 | Corbiere and Sons Contracting47820191109-4-R01Brusher275467.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5467.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 478 | 20191109-4-R01 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Touch ups and Chainsaw work from A010 to A013 |  |  | MacGregor East | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting47820191109-4-R01Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting47820191109-4-R01Grinder - 4710 Peterson or equal95011.2Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 478 | 20191109-4-R01 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Touch ups and Chainsaw work from A010 to A013 |  |  | MacGregor East | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting47820191109-4-R01Log Loader91377 | Corbiere and Sons Contracting47820191109-4-R01Log Loader91377Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 478 | 20191109-4-R01 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Touch ups and Chainsaw work from A010 to A013 |  |  | MacGregor East | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting47820191109-4-R01Mulcher91845 | Corbiere and Sons Contracting47820191109-4-R01Mulcher91845Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 478 | 20191109-4-R01 | 53520102 | Clearing | 0 | Chainsaw and consummables | 120 | 9 | Day |  | 0 |  |  | 1080 | 140.4 | 1220.4 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Touch ups and Chainsaw work from A010 to A013 |  |  | MacGregor East | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting47820191109-4-R01Chainsaw and consummables91080 | Corbiere and Sons Contracting47820191109-4-R01Chainsaw and consummables91080Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 478 | 20191109-4-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Touch ups and Chainsaw work from A010 to A013 |  |  | MacGregor East | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting47820191109-4-R01Light Truck - Pick up601800 | Corbiere and Sons Contracting47820191109-4-R01Light Truck - Pick up601800Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 478 | 20191109-4-R01 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Touch ups and Chainsaw work from A010 to A013 |  |  | MacGregor East | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting47820191109-4-R01Foreman121140 | Corbiere and Sons Contracting47820191109-4-R01Foreman121140Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 478 | 20191109-4-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 55 | HR |  |  |  | 0 | 4950 | 643.5 | 5593.5 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Touch ups and Chainsaw work from A010 to A013 |  |  | MacGregor East | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting47820191109-4-R01Operator - Principle554950 | Corbiere and Sons Contracting47820191109-4-R01Operator - Principle554950Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 478 | 20191109-4-R01 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 83 | HR |  |  |  | 0 | 6225 | 809.25 | 7034.25 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Touch ups and Chainsaw work from A010 to A013 |  |  | MacGregor East | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting47820191109-4-R01Labourer - Specialized836225 | Corbiere and Sons Contracting47820191109-4-R01Labourer - Specialized836225Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 6225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 478 | 20191109-4-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 14 | DAY |  |  |  | 0 | 2940 | 382.2 | 3322.2 | 2019-11-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Touch ups and Chainsaw work from A010 to A013 |  |  | MacGregor East | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting47820191109-4-R01L.O.A.142940 | Corbiere and Sons Contracting47820191109-4-R01L.O.A.142940Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2940 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 467 | 20191110-01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 0 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Supervision Cost Code requires set up |  |  |  |  | Supervision |  |  | 100 Wolf River Road, Dorion, Ontario P0T1K0 | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting46720191110-01Light Truck - Pick up501500 | Corbiere and Sons Contracting46720191110-01Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 467 | 20191110-01 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  | 0 | 0 | 1320 | 171.6 | 1491.6 | 2019-11-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Supervision Cost Code requires set up |  |  |  |  | Supervision |  |  | 100 Wolf River Road, Dorion, Ontario P0T1K0 | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting46720191110-01Project Manager121320 | Corbiere and Sons Contracting46720191110-01Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 467 | 20191110-01 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  | 0 | 0 | 1260 | 163.8 | 1423.8 | 2019-11-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Supervision Cost Code requires set up |  |  |  |  | Supervision |  |  | 100 Wolf River Road, Dorion, Ontario P0T1K0 | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting46720191110-01Superintendent121260 | Corbiere and Sons Contracting46720191110-01Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 467 | 20191110-01 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 13 | HR |  |  | 0 | 0 | 1040 | 135.2 | 1175.2 | 2019-11-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Supervision Cost Code requires set up |  |  |  |  | Supervision |  |  | 100 Wolf River Road, Dorion, Ontario P0T1K0 | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting46720191110-01Project Coordinator131040 | Corbiere and Sons Contracting46720191110-01Project Coordinator131040Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1040 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 467 | 20191110-01 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  | 0 | 0 | 1020 | 132.6 | 1152.6 | 2019-11-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Supervision Cost Code requires set up |  |  |  |  | Supervision |  |  | 100 Wolf River Road, Dorion, Ontario P0T1K0 | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting46720191110-01Safety Advisor121020 | Corbiere and Sons Contracting46720191110-01Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 467 | 20191110-01 | 53520101 | Clearing | 0 | Project Controls | 70 | 6 | HR |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2019-11-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Supervision Cost Code requires set up |  |  |  |  | Supervision |  |  | 100 Wolf River Road, Dorion, Ontario P0T1K0 | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting46720191110-01Project Controls6420 | Corbiere and Sons Contracting46720191110-01Project Controls6420Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 467 | 20191110-01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  | 0 | 0 | 1050 | 136.5 | 1186.5 | 2019-11-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Supervision Cost Code requires set up |  |  |  |  | Supervision |  |  | 100 Wolf River Road, Dorion, Ontario P0T1K0 | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting46720191110-01L.O.A.51050 | Corbiere and Sons Contracting46720191110-01L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 485 | 20191110-03-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 |  | HR | 180 | 36 |  |  | 6480 | 842.4 | 7322.4 | 2019-11-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48520191110-03-R01Feller Buncher6480 | Corbiere and Sons Contracting48520191110-03-R01Feller Buncher6480Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 6480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 485 | 20191110-03-R01 | 53520101 | Clearing | 0 | Skidder | 171 |  | HR | 128.25 | 18 |  |  | 2308.5 | 300.105 | 2608.605 | 2019-11-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48520191110-03-R01Skidder 2308.5 | Corbiere and Sons Contracting48520191110-03-R01Skidder 2308.5Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2308.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 485 | 20191110-03-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 |  | HR | 22.5 | 20 |  |  | 450 | 58.5 | 508.5 | 2019-11-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48520191110-03-R01Light Truck - Pick up450 | Corbiere and Sons Contracting48520191110-03-R01Light Truck - Pick up450Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 485 | 20191110-03-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 8 | HR |  |  |  | 0 | 720 | 93.6 | 813.6 | 2019-11-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48520191110-03-R01Operator - Principle8720 | Corbiere and Sons Contracting48520191110-03-R01Operator - Principle8720Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 485 | 20191110-03-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48520191110-03-R01L.O.A.2420 | Corbiere and Sons Contracting48520191110-03-R01L.O.A.2420Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 488 | 20191110-06 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9.5 | HR | 417.6 | 0 |  |  | 5289.6 | 687.648 | 5977.248 | 2019-11-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A019 |  |  | Shuniah Road | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting48820191110-06Grinder - 4710 Peterson or equal9.55289.6 | Corbiere and Sons Contracting48820191110-06Grinder - 4710 Peterson or equal9.55289.6Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5289.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 488 | 20191110-06 | 53520102 | Clearing | 0 | Log Loader | 153 | 9.5 | HR | 114.75 | 0 |  |  | 1453.5 | 188.955 | 1642.455 | 2019-11-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A019 |  |  | Shuniah Road | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting48820191110-06Log Loader9.51453.5 | Corbiere and Sons Contracting48820191110-06Log Loader9.51453.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1453.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 488 | 20191110-06 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A019 |  |  | Shuniah Road | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting48820191110-06Light Truck - Pick up10300 | Corbiere and Sons Contracting48820191110-06Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 488 | 20191110-06 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A019 |  |  | Shuniah Road | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting48820191110-06Operator - Principle11990 | Corbiere and Sons Contracting48820191110-06Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 488 | 20191110-06 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A019 |  |  | Shuniah Road | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting48820191110-06L.O.A.1210 | Corbiere and Sons Contracting48820191110-06L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 484 | 20191110-2-R02 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 |  |  |  | 891 | 115.83 | 1006.83 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Standby rate for loader is $74.25, ticket is $74.00. Revision required - Corrected Nov 16, 19 - RR Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - Float Moves |  |  | 100 Wolf River Road, Dorion, Ontario, P0T1K0 | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48420191110-2-R02Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting48420191110-2-R02Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 484 | 20191110-2-R02 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Standby rate for loader is $74.25, ticket is $74.00. Revision required - Corrected Nov 16, 19 - RR Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - Float Moves |  |  | 100 Wolf River Road, Dorion, Ontario, P0T1K0 | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48420191110-2-R02Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting48420191110-2-R02Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 484 | 20191110-2-R02 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Standby rate for loader is $74.25, ticket is $74.00. Revision required - Corrected Nov 16, 19 - RR Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - Float Moves |  |  | 100 Wolf River Road, Dorion, Ontario, P0T1K0 | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48420191110-2-R02Operator - Intermdiate11825 | Corbiere and Sons Contracting48420191110-2-R02Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 484 | 20191110-2-R02 | 53520105 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Standby rate for loader is $74.25, ticket is $74.00. Revision required - Corrected Nov 16, 19 - RR Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - Float Moves |  |  | 100 Wolf River Road, Dorion, Ontario, P0T1K0 | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48420191110-2-R02L.O.A.2420 | Corbiere and Sons Contracting48420191110-2-R02L.O.A.2420Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 486 | 20191110-4-R01 | 53520101 | Clearing | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking at Tower A007: DZ working from A009 down to A003 |  |  | MacGregor East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48620191110-4-R01Dozer D6 or equal91215 | Corbiere and Sons Contracting48620191110-4-R01Dozer D6 or equal91215Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 486 | 20191110-4-R01 | 53520101 | Clearing | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking at Tower A007: DZ working from A009 down to A003 |  |  | MacGregor East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48620191110-4-R01Excavator - 30 ton91255.5 | Corbiere and Sons Contracting48620191110-4-R01Excavator - 30 ton91255.5Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 486 | 20191110-4-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking at Tower A007: DZ working from A009 down to A003 |  |  | MacGregor East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48620191110-4-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting48620191110-4-R01Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 486 | 20191110-4-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking at Tower A007: DZ working from A009 down to A003 |  |  | MacGregor East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48620191110-4-R01Operator - Principle221980 | Corbiere and Sons Contracting48620191110-4-R01Operator - Principle221980Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 486 | 20191110-4-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking at Tower A007: DZ working from A009 down to A003 |  |  | MacGregor East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48620191110-4-R01L.O.A.2420 | Corbiere and Sons Contracting48620191110-4-R01L.O.A.2420Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 487 | 20191110-5-R01 | 53520101 | Clearing | 0 | Brusher | 202.5 | 27 | HR | 151.88 | 0 |  |  | 5467.5 | 710.775 | 6178.275 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Chainsaw work finished up to A010 on hillside. Started at A015; skidder, FB and BR's working between A013 and A018. Charlie ran fuel in the AM and then moved onto brushing; Raking at A015 and A016; Grinding at A016 |  |  | MacGregor West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48720191110-5-R01Brusher275467.5 | Corbiere and Sons Contracting48720191110-5-R01Brusher275467.5Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5467.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 487 | 20191110-5-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Chainsaw work finished up to A010 on hillside. Started at A015; skidder, FB and BR's working between A013 and A018. Charlie ran fuel in the AM and then moved onto brushing; Raking at A015 and A016; Grinding at A016 |  |  | MacGregor West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48720191110-5-R01Feller Buncher92160 | Corbiere and Sons Contracting48720191110-5-R01Feller Buncher92160Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 487 | 20191110-5-R01 | 53520101 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Chainsaw work finished up to A010 on hillside. Started at A015; skidder, FB and BR's working between A013 and A018. Charlie ran fuel in the AM and then moved onto brushing; Raking at A015 and A016; Grinding at A016 |  |  | MacGregor West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48720191110-5-R01Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting48720191110-5-R01Grinder - 4710 Peterson or equal95011.2Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 487 | 20191110-5-R01 | 53520101 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Chainsaw work finished up to A010 on hillside. Started at A015; skidder, FB and BR's working between A013 and A018. Charlie ran fuel in the AM and then moved onto brushing; Raking at A015 and A016; Grinding at A016 |  |  | MacGregor West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48720191110-5-R01Log Loader91377 | Corbiere and Sons Contracting48720191110-5-R01Log Loader91377Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 487 | 20191110-5-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Chainsaw work finished up to A010 on hillside. Started at A015; skidder, FB and BR's working between A013 and A018. Charlie ran fuel in the AM and then moved onto brushing; Raking at A015 and A016; Grinding at A016 |  |  | MacGregor West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48720191110-5-R01Skidder 91539 | Corbiere and Sons Contracting48720191110-5-R01Skidder 91539Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 487 | 20191110-5-R01 | 53520101 | Clearing | 0 | Chainsaw and consummables | 120 | 7 | Day |  | 0 |  |  | 840 | 109.2 | 949.2 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Chainsaw work finished up to A010 on hillside. Started at A015; skidder, FB and BR's working between A013 and A018. Charlie ran fuel in the AM and then moved onto brushing; Raking at A015 and A016; Grinding at A016 |  |  | MacGregor West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48720191110-5-R01Chainsaw and consummables7840 | Corbiere and Sons Contracting48720191110-5-R01Chainsaw and consummables7840Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 487 | 20191110-5-R01 | 53520101 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Chainsaw work finished up to A010 on hillside. Started at A015; skidder, FB and BR's working between A013 and A018. Charlie ran fuel in the AM and then moved onto brushing; Raking at A015 and A016; Grinding at A016 |  |  | MacGregor West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48720191110-5-R01Excavator - 36 ton91539 | Corbiere and Sons Contracting48720191110-5-R01Excavator - 36 ton91539Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 487 | 20191110-5-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 70 | HR | 22.5 | 0 |  |  | 2100 | 273 | 2373 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Chainsaw work finished up to A010 on hillside. Started at A015; skidder, FB and BR's working between A013 and A018. Charlie ran fuel in the AM and then moved onto brushing; Raking at A015 and A016; Grinding at A016 |  |  | MacGregor West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48720191110-5-R01Light Truck - Pick up702100 | Corbiere and Sons Contracting48720191110-5-R01Light Truck - Pick up702100Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 487 | 20191110-5-R01 | 53520101 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Chainsaw work finished up to A010 on hillside. Started at A015; skidder, FB and BR's working between A013 and A018. Charlie ran fuel in the AM and then moved onto brushing; Raking at A015 and A016; Grinding at A016 |  |  | MacGregor West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48720191110-5-R01Foreman121140 | Corbiere and Sons Contracting48720191110-5-R01Foreman121140Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 487 | 20191110-5-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 78.5 | HR |  |  |  | 0 | 7065 | 918.45 | 7983.45 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Chainsaw work finished up to A010 on hillside. Started at A015; skidder, FB and BR's working between A013 and A018. Charlie ran fuel in the AM and then moved onto brushing; Raking at A015 and A016; Grinding at A016 |  |  | MacGregor West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48720191110-5-R01Operator - Principle78.57065 | Corbiere and Sons Contracting48720191110-5-R01Operator - Principle78.57065Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 7065 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 487 | 20191110-5-R01 | 53520101 | Clearing | 0 | Labourer - Specialized | 75 | 66 | HR |  |  |  | 0 | 4950 | 643.5 | 5593.5 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Chainsaw work finished up to A010 on hillside. Started at A015; skidder, FB and BR's working between A013 and A018. Charlie ran fuel in the AM and then moved onto brushing; Raking at A015 and A016; Grinding at A016 |  |  | MacGregor West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48720191110-5-R01Labourer - Specialized664950 | Corbiere and Sons Contracting48720191110-5-R01Labourer - Specialized664950Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 487 | 20191110-5-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 14 | DAY |  |  |  | 0 | 2940 | 382.2 | 3322.2 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Chainsaw work finished up to A010 on hillside. Started at A015; skidder, FB and BR's working between A013 and A018. Charlie ran fuel in the AM and then moved onto brushing; Raking at A015 and A016; Grinding at A016 |  |  | MacGregor West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48720191110-5-R01L.O.A.142940 | Corbiere and Sons Contracting48720191110-5-R01L.O.A.142940Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2940 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 489 | 20191110-7-R01 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 18 | HR | 97.88 | 0 |  |  | 2349 | 305.37 | 2654.37 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking from A021 Eastward |  |  | Shuniah Road | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48920191110-7-R01Excavator - 20 ton182349 | Corbiere and Sons Contracting48920191110-7-R01Excavator - 20 ton182349Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2349 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 489 | 20191110-7-R01 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking from A021 Eastward |  |  | Shuniah Road | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48920191110-7-R01Excavator - 36 ton91539 | Corbiere and Sons Contracting48920191110-7-R01Excavator - 36 ton91539Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 489 | 20191110-7-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking from A021 Eastward |  |  | Shuniah Road | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48920191110-7-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting48920191110-7-R01Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 489 | 20191110-7-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking from A021 Eastward |  |  | Shuniah Road | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48920191110-7-R01Operator - Principle332970 | Corbiere and Sons Contracting48920191110-7-R01Operator - Principle332970Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 489 | 20191110-7-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-10 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking from A021 Eastward |  |  | Shuniah Road | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting48920191110-7-R01L.O.A.3630 | Corbiere and Sons Contracting48920191110-7-R01L.O.A.3630Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 492 | 20191111-01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting49220191111-01Light Truck - Pick up501500 | Corbiere and Sons Contracting49220191111-01Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 492 | 20191111-01 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting49220191111-01Project Manager121320 | Corbiere and Sons Contracting49220191111-01Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 492 | 20191111-01 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting49220191111-01Superintendent121260 | Corbiere and Sons Contracting49220191111-01Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 492 | 20191111-01 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting49220191111-01Project Coordinator12960 | Corbiere and Sons Contracting49220191111-01Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 492 | 20191111-01 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting49220191111-01Safety Advisor121020 | Corbiere and Sons Contracting49220191111-01Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 492 | 20191111-01 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting49220191111-01Project Controls12840 | Corbiere and Sons Contracting49220191111-01Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 492 | 20191111-01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting49220191111-01L.O.A.51050 | Corbiere and Sons Contracting49220191111-01L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 494 | 20191111-03-R02 | 53520101 | Clearing | 0 | Feller Buncher | 240 |  | HR | 180 | 45 |  |  | 8100 | 1053 | 9153 | 2019-11-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On standby due to missing permits. |  |  |  | 0 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49420191111-03-R02Feller Buncher8100 | Corbiere and Sons Contracting49420191111-03-R02Feller Buncher8100Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 8100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 494 | 20191111-03-R02 | 53520101 | Clearing | 0 | Skidder | 171 |  | HR | 128.25 | 27 |  |  | 3462.75 | 450.1575 | 3912.9075 | 2019-11-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On standby due to missing permits. |  |  |  | 0 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49420191111-03-R02Skidder 3462.75 | Corbiere and Sons Contracting49420191111-03-R02Skidder 3462.75Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3462.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 494 | 20191111-03-R02 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 |  | HR | 22.5 | 60 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On standby due to missing permits. |  |  |  | 0 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49420191111-03-R02Light Truck - Pick up1350 | Corbiere and Sons Contracting49420191111-03-R02Light Truck - Pick up1350Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 494 | 20191111-03-R02 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 24 | HR |  |  |  | 0 | 2160 | 280.8 | 2440.8 | 2019-11-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On standby due to missing permits. |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49420191111-03-R02Operator - Principle242160 | Corbiere and Sons Contracting49420191111-03-R02Operator - Principle242160Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 494 | 20191111-03-R02 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On standby due to missing permits. |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49420191111-03-R02L.O.A.61260 | Corbiere and Sons Contracting49420191111-03-R02L.O.A.61260Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 496 | 20191111-05 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9.5 | HR | 417.6 | 0 |  |  | 5289.6 | 687.648 | 5977.248 | 2019-11-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Gringing at A019; Joey Day raking. |  |  |  | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting49620191111-05Grinder - 4710 Peterson or equal9.55289.6 | Corbiere and Sons Contracting49620191111-05Grinder - 4710 Peterson or equal9.55289.6Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5289.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 496 | 20191111-05 | 53520102 | Clearing | 0 | Log Loader | 153 | 9.5 | HR | 114.75 | 0 |  |  | 1453.5 | 188.955 | 1642.455 | 2019-11-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Gringing at A019; Joey Day raking. |  |  |  | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting49620191111-05Log Loader9.51453.5 | Corbiere and Sons Contracting49620191111-05Log Loader9.51453.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1453.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 496 | 20191111-05 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9.5 | HR | 128.25 | 0 |  |  | 1624.5 | 211.185 | 1835.685 | 2019-11-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Gringing at A019; Joey Day raking. |  |  |  | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting49620191111-05Excavator - 36 ton9.51624.5 | Corbiere and Sons Contracting49620191111-05Excavator - 36 ton9.51624.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 496 | 20191111-05 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Gringing at A019; Joey Day raking. |  |  |  | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting49620191111-05Light Truck - Pick up10300 | Corbiere and Sons Contracting49620191111-05Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 496 | 20191111-05 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Gringing at A019; Joey Day raking. |  |  |  | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting49620191111-05Operator - Principle221980 | Corbiere and Sons Contracting49620191111-05Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 496 | 20191111-05 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Gringing at A019; Joey Day raking. |  |  |  | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting49620191111-05L.O.A.2420 | Corbiere and Sons Contracting49620191111-05L.O.A.2420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 493 | 20191111-2-R02 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Labour Specialized has incorrect rate - Correct Nov 16, 19 - RR. Revised and approved Jan 8, 2020 - RR |  |  |  |  | Gerneral yard and equipment maintenance - Float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49320191111-2-R02Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting49320191111-2-R02Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 493 | 20191111-2-R02 | 53520105 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Labour Specialized has incorrect rate - Correct Nov 16, 19 - RR. Revised and approved Jan 8, 2020 - RR |  |  |  |  | Gerneral yard and equipment maintenance - Float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49320191111-2-R02Light Truck - Pick up10300 | Corbiere and Sons Contracting49320191111-2-R02Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 493 | 20191111-2-R02 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Labour Specialized has incorrect rate - Correct Nov 16, 19 - RR. Revised and approved Jan 8, 2020 - RR |  |  |  |  | Gerneral yard and equipment maintenance - Float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49320191111-2-R02Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting49320191111-2-R02Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 493 | 20191111-2-R02 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Labour Specialized has incorrect rate - Correct Nov 16, 19 - RR. Revised and approved Jan 8, 2020 - RR |  |  |  |  | Gerneral yard and equipment maintenance - Float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49320191111-2-R02Operator - Principle11990 | Corbiere and Sons Contracting49320191111-2-R02Operator - Principle11990Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 493 | 20191111-2-R02 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Labour Specialized has incorrect rate - Correct Nov 16, 19 - RR. Revised and approved Jan 8, 2020 - RR |  |  |  |  | Gerneral yard and equipment maintenance - Float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49320191111-2-R02Operator - Intermdiate11825 | Corbiere and Sons Contracting49320191111-2-R02Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 493 | 20191111-2-R02 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Labour Specialized has incorrect rate - Correct Nov 16, 19 - RR. Revised and approved Jan 8, 2020 - RR |  |  |  |  | Gerneral yard and equipment maintenance - Float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49320191111-2-R02Labourer - General10650 | Corbiere and Sons Contracting49320191111-2-R02Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 495 | 20191111-4-R01 | 53520102 | Clearing | 0 | Brusher | 202.5 | 18 | HR | 151.88 | 0 |  |  | 3645 | 473.85 | 4118.85 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Grinding material at A016; hand cutting, brushing up at A017. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49520191111-4-R01Brusher183645 | Corbiere and Sons Contracting49520191111-4-R01Brusher183645Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3645 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 495 | 20191111-4-R01 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Grinding material at A016; hand cutting, brushing up at A017. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49520191111-4-R01Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting49520191111-4-R01Grinder - 4710 Peterson or equal95011.2Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 495 | 20191111-4-R01 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Grinding material at A016; hand cutting, brushing up at A017. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49520191111-4-R01Log Loader91377 | Corbiere and Sons Contracting49520191111-4-R01Log Loader91377Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 495 | 20191111-4-R01 | 53520102 | Clearing | 0 | Chainsaw and consummables | 120 | 6 | Day |  | 0 |  |  | 720 | 93.6 | 813.6 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Grinding material at A016; hand cutting, brushing up at A017. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49520191111-4-R01Chainsaw and consummables6720 | Corbiere and Sons Contracting49520191111-4-R01Chainsaw and consummables6720Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 495 | 20191111-4-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Grinding material at A016; hand cutting, brushing up at A017. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49520191111-4-R01Light Truck - Pick up401200 | Corbiere and Sons Contracting49520191111-4-R01Light Truck - Pick up401200Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 495 | 20191111-4-R01 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Grinding material at A016; hand cutting, brushing up at A017. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49520191111-4-R01Foreman121140 | Corbiere and Sons Contracting49520191111-4-R01Foreman121140Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 495 | 20191111-4-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Grinding material at A016; hand cutting, brushing up at A017. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49520191111-4-R01Operator - Principle332970 | Corbiere and Sons Contracting49520191111-4-R01Operator - Principle332970Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 495 | 20191111-4-R01 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 55 | HR |  |  |  | 0 | 4125 | 536.25 | 4661.25 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Grinding material at A016; hand cutting, brushing up at A017. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49520191111-4-R01Labourer - Specialized554125 | Corbiere and Sons Contracting49520191111-4-R01Labourer - Specialized554125Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 495 | 20191111-4-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Grinding material at A016; hand cutting, brushing up at A017. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49520191111-4-R01L.O.A.91890 | Corbiere and Sons Contracting49520191111-4-R01L.O.A.91890Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 497 | 20191111-6-R01 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 3 | Day |  | 0 |  |  | 360 | 46.8 | 406.8 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand cutting at A021 Westward; Raking at A021 West |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49720191111-6-R01Chainsaw and consummables3360 | Corbiere and Sons Contracting49720191111-6-R01Chainsaw and consummables3360Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 497 | 20191111-6-R01 | 53520104 | Clearing | 0 | Excavator - 20 ton | 130.5 | 18 | HR | 97.88 | 0 |  |  | 2349 | 305.37 | 2654.37 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand cutting at A021 Westward; Raking at A021 West |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49720191111-6-R01Excavator - 20 ton182349 | Corbiere and Sons Contracting49720191111-6-R01Excavator - 20 ton182349Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 2349 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 497 | 20191111-6-R01 | 53520104 | Clearing | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand cutting at A021 Westward; Raking at A021 West |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49720191111-6-R01Excavator - 30 ton91255.5 | Corbiere and Sons Contracting49720191111-6-R01Excavator - 30 ton91255.5Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 497 | 20191111-6-R01 | 53520104 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand cutting at A021 Westward; Raking at A021 West |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49720191111-6-R01Excavator - 36 ton91539 | Corbiere and Sons Contracting49720191111-6-R01Excavator - 36 ton91539Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 497 | 20191111-6-R01 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand cutting at A021 Westward; Raking at A021 West |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49720191111-6-R01Light Truck - Pick up30900 | Corbiere and Sons Contracting49720191111-6-R01Light Truck - Pick up30900Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 497 | 20191111-6-R01 | 53520104 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand cutting at A021 Westward; Raking at A021 West |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49720191111-6-R01Operator - Principle443960 | Corbiere and Sons Contracting49720191111-6-R01Operator - Principle443960Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 497 | 20191111-6-R01 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 33 | HR |  |  |  | 0 | 2475 | 321.75 | 2796.75 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand cutting at A021 Westward; Raking at A021 West |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49720191111-6-R01Labourer - Specialized332475 | Corbiere and Sons Contracting49720191111-6-R01Labourer - Specialized332475Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 497 | 20191111-6-R01 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand cutting at A021 Westward; Raking at A021 West |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting49720191111-6-R01L.O.A.4840 | Corbiere and Sons Contracting49720191111-6-R01L.O.A.4840Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 498 | 20191111-7-R01 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking from A035 |  |  | A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting49820191111-7-R01Excavator - 36 ton91539 | Corbiere and Sons Contracting49820191111-7-R01Excavator - 36 ton91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 498 | 20191111-7-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking from A035 |  |  | A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting49820191111-7-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting49820191111-7-R01Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 498 | 20191111-7-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking from A035 |  |  | A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting49820191111-7-R01Operator - Principle11990 | Corbiere and Sons Contracting49820191111-7-R01Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 498 | 20191111-7-R01 | 53520102 | Clearing | 0 | Labourer - General | 65 | 12 | HR |  |  |  | 0 | 780 | 101.4 | 881.4 | 2019-11-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking from A035 |  |  | A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting49820191111-7-R01Labourer - General12780 | Corbiere and Sons Contracting49820191111-7-R01Labourer - General12780Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 780 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 498 | 20191111-7-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking from A035 |  |  | A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting49820191111-7-R01L.O.A.3630 | Corbiere and Sons Contracting49820191111-7-R01L.O.A.3630Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 502 | 20191112-01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting50220191112-01Light Truck - Pick up501500 | Corbiere and Sons Contracting50220191112-01Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 502 | 20191112-01 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting50220191112-01Project Manager121320 | Corbiere and Sons Contracting50220191112-01Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 502 | 20191112-01 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting50220191112-01Superintendent121260 | Corbiere and Sons Contracting50220191112-01Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 502 | 20191112-01 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting50220191112-01Project Coordinator12960 | Corbiere and Sons Contracting50220191112-01Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 502 | 20191112-01 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting50220191112-01Safety Advisor121020 | Corbiere and Sons Contracting50220191112-01Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 502 | 20191112-01 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting50220191112-01Project Controls12840 | Corbiere and Sons Contracting50220191112-01Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 502 | 20191112-01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting50220191112-01L.O.A.51050 | Corbiere and Sons Contracting50220191112-01L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 504 | 20191112-03-R02 | 53520101 | Clearing | 0 | Feller Buncher | 240 |  | HR | 180 | 45 |  |  | 8100 | 1053 | 9153 | 2019-11-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On standby due to missing permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting50420191112-03-R02Feller Buncher8100 | Corbiere and Sons Contracting50420191112-03-R02Feller Buncher8100Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 8100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 504 | 20191112-03-R02 | 53520101 | Clearing | 0 | Skidder | 171 |  | HR | 128.25 | 27 |  |  | 3462.75 | 450.1575 | 3912.9075 | 2019-11-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On standby due to missing permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting50420191112-03-R02Skidder 3462.75 | Corbiere and Sons Contracting50420191112-03-R02Skidder 3462.75Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3462.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 504 | 20191112-03-R02 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 |  | HR | 22.5 | 60 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On standby due to missing permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting50420191112-03-R02Light Truck - Pick up1350 | Corbiere and Sons Contracting50420191112-03-R02Light Truck - Pick up1350Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 504 | 20191112-03-R02 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 24 | HR |  |  |  | 0 | 2160 | 280.8 | 2440.8 | 2019-11-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On standby due to missing permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting50420191112-03-R02Operator - Principle242160 | Corbiere and Sons Contracting50420191112-03-R02Operator - Principle242160Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 504 | 20191112-03-R02 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On standby due to missing permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting50420191112-03-R02L.O.A.61260 | Corbiere and Sons Contracting50420191112-03-R02L.O.A.61260Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 506 | 20191112-05 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9.5 | HR | 417.6 | 0 |  |  | 5289.6 | 687.648 | 5977.248 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A019 |  |  | A019 | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting50620191112-05Grinder - 4710 Peterson or equal9.55289.6 | Corbiere and Sons Contracting50620191112-05Grinder - 4710 Peterson or equal9.55289.6Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5289.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 506 | 20191112-05 | 53520102 | Clearing | 0 | Log Loader | 153 | 9.5 | HR | 114.75 | 0 |  |  | 1453.5 | 188.955 | 1642.455 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A019 |  |  | A019 | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting50620191112-05Log Loader9.51453.5 | Corbiere and Sons Contracting50620191112-05Log Loader9.51453.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1453.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 506 | 20191112-05 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9.5 | HR | 128.25 | 0 |  |  | 1624.5 | 211.185 | 1835.685 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A019 |  |  | A019 | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting50620191112-05Excavator - 36 ton9.51624.5 | Corbiere and Sons Contracting50620191112-05Excavator - 36 ton9.51624.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 506 | 20191112-05 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A019 |  |  | A019 | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting50620191112-05Light Truck - Pick up10300 | Corbiere and Sons Contracting50620191112-05Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 506 | 20191112-05 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A019 |  |  | A019 | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting50620191112-05Operator - Principle221980 | Corbiere and Sons Contracting50620191112-05Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 506 | 20191112-05 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A019 |  |  | A019 | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting50620191112-05L.O.A.2420 | Corbiere and Sons Contracting50620191112-05L.O.A.2420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 507 | 20191112-06 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9.5 | HR | 151.88 | 0 |  |  | 1923.75 | 250.0875 | 2173.8375 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand cutting at A022 Eastward; Grinding at A021; Brushing at A024, raking from A021-A029. |  |  | A022, A021-A029 | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting50720191112-06Brusher9.51923.75 | Corbiere and Sons Contracting50720191112-06Brusher9.51923.75Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1923.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 507 | 20191112-06 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9.5 | HR | 417.6 | 0 |  |  | 5289.6 | 687.648 | 5977.248 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand cutting at A022 Eastward; Grinding at A021; Brushing at A024, raking from A021-A029. |  |  | A022, A021-A029 | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting50720191112-06Grinder - 4710 Peterson or equal9.55289.6 | Corbiere and Sons Contracting50720191112-06Grinder - 4710 Peterson or equal9.55289.6Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5289.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 507 | 20191112-06 | 53520102 | Clearing | 0 | Log Loader | 153 | 9.5 | HR | 114.75 | 0 |  |  | 1453.5 | 188.955 | 1642.455 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand cutting at A022 Eastward; Grinding at A021; Brushing at A024, raking from A021-A029. |  |  | A022, A021-A029 | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting50720191112-06Log Loader9.51453.5 | Corbiere and Sons Contracting50720191112-06Log Loader9.51453.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1453.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 507 | 20191112-06 | 53520102 | Clearing | 0 | Chainsaw and consummables | 120 | 3 | Day |  | 0 |  |  | 360 | 46.8 | 406.8 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand cutting at A022 Eastward; Grinding at A021; Brushing at A024, raking from A021-A029. |  |  | A022, A021-A029 | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting50720191112-06Chainsaw and consummables3360 | Corbiere and Sons Contracting50720191112-06Chainsaw and consummables3360Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 507 | 20191112-06 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 19 | HR | 97.88 | 0 |  |  | 2479.5 | 322.335 | 2801.835 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand cutting at A022 Eastward; Grinding at A021; Brushing at A024, raking from A021-A029. |  |  | A022, A021-A029 | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting50720191112-06Excavator - 20 ton192479.5 | Corbiere and Sons Contracting50720191112-06Excavator - 20 ton192479.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2479.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 507 | 20191112-06 | 53520102 | Clearing | 0 | Excavator - 30 ton | 139.5 | 9.5 | HR | 104.63 | 0 |  |  | 1325.25 | 172.2825 | 1497.5325 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand cutting at A022 Eastward; Grinding at A021; Brushing at A024, raking from A021-A029. |  |  | A022, A021-A029 | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting50720191112-06Excavator - 30 ton9.51325.25 | Corbiere and Sons Contracting50720191112-06Excavator - 30 ton9.51325.25Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1325.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 507 | 20191112-06 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand cutting at A022 Eastward; Grinding at A021; Brushing at A024, raking from A021-A029. |  |  | A022, A021-A029 | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting50720191112-06Light Truck - Pick up501500 | Corbiere and Sons Contracting50720191112-06Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 507 | 20191112-06 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 55 | HR |  |  |  | 0 | 4950 | 643.5 | 5593.5 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand cutting at A022 Eastward; Grinding at A021; Brushing at A024, raking from A021-A029. |  |  | A022, A021-A029 | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting50720191112-06Operator - Principle554950 | Corbiere and Sons Contracting50720191112-06Operator - Principle554950Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 507 | 20191112-06 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 33 | HR |  |  |  | 0 | 2475 | 321.75 | 2796.75 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand cutting at A022 Eastward; Grinding at A021; Brushing at A024, raking from A021-A029. |  |  | A022, A021-A029 | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting50720191112-06Labourer - Specialized332475 | Corbiere and Sons Contracting50720191112-06Labourer - Specialized332475Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 507 | 20191112-06 | 53520102 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand cutting at A022 Eastward; Grinding at A021; Brushing at A024, raking from A021-A029. |  |  | A022, A021-A029 | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting50720191112-06L.O.A.51050 | Corbiere and Sons Contracting50720191112-06L.O.A.51050Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 503 | 20191112-2-R02 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-11-12 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Labourer - specialized has incorrect rate. - Corrected Nov 16, 19 - RR Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment mainetnance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting50320191112-2-R02Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting50320191112-2-R02Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 503 | 20191112-2-R02 | 53520105 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-12 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Labourer - specialized has incorrect rate. - Corrected Nov 16, 19 - RR Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment mainetnance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting50320191112-2-R02Light Truck - Pick up10300 | Corbiere and Sons Contracting50320191112-2-R02Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 503 | 20191112-2-R02 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-12 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Labourer - specialized has incorrect rate. - Corrected Nov 16, 19 - RR Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment mainetnance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting50320191112-2-R02Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting50320191112-2-R02Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 503 | 20191112-2-R02 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-11-12 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Labourer - specialized has incorrect rate. - Corrected Nov 16, 19 - RR Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment mainetnance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting50320191112-2-R02Operator - Principle121080 | Corbiere and Sons Contracting50320191112-2-R02Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 503 | 20191112-2-R02 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-12 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Labourer - specialized has incorrect rate. - Corrected Nov 16, 19 - RR Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment mainetnance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting50320191112-2-R02Operator - Intermdiate11825 | Corbiere and Sons Contracting50320191112-2-R02Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 503 | 20191112-2-R02 | 53520105 | Clearing | 0 | Labourer - General | 65 | 21 | HR |  |  |  | 0 | 1365 | 177.45 | 1542.45 | 2019-11-12 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Labourer - specialized has incorrect rate. - Corrected Nov 16, 19 - RR Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment mainetnance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting50320191112-2-R02Labourer - General211365 | Corbiere and Sons Contracting50320191112-2-R02Labourer - General211365Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1365 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 503 | 20191112-2-R02 | 53520105 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-12 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Labourer - specialized has incorrect rate. - Corrected Nov 16, 19 - RR Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment mainetnance - float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting50320191112-2-R02L.O.A.3630 | Corbiere and Sons Contracting50320191112-2-R02L.O.A.3630Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 505 | 20191112-4-R01 | 53520102 | Clearing | 0 | Brusher | 202.5 | 18 | HR | 151.88 | 0 |  |  | 3645 | 473.85 | 4118.85 | 2019-11-12 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Saw hands doing cutting from A015-A017; 2 saw hands were assigned to Valard yard to do cutting for an entire day. Brushers finishing up to A017. |  |  | A015-A017 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting50520191112-4-R01Brusher183645 | Corbiere and Sons Contracting50520191112-4-R01Brusher183645Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3645 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 505 | 20191112-4-R01 | 53520102 | Clearing | 0 | Chainsaw and consummables | 120 | 7 | Day |  | 0 |  |  | 840 | 109.2 | 949.2 | 2019-11-12 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Saw hands doing cutting from A015-A017; 2 saw hands were assigned to Valard yard to do cutting for an entire day. Brushers finishing up to A017. |  |  | A015-A017 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting50520191112-4-R01Chainsaw and consummables7840 | Corbiere and Sons Contracting50520191112-4-R01Chainsaw and consummables7840Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 505 | 20191112-4-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-12 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Saw hands doing cutting from A015-A017; 2 saw hands were assigned to Valard yard to do cutting for an entire day. Brushers finishing up to A017. |  |  | A015-A017 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting50520191112-4-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting50520191112-4-R01Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 505 | 20191112-4-R01 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-12 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Saw hands doing cutting from A015-A017; 2 saw hands were assigned to Valard yard to do cutting for an entire day. Brushers finishing up to A017. |  |  | A015-A017 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting50520191112-4-R01Foreman121140 | Corbiere and Sons Contracting50520191112-4-R01Foreman121140Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 505 | 20191112-4-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-12 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Saw hands doing cutting from A015-A017; 2 saw hands were assigned to Valard yard to do cutting for an entire day. Brushers finishing up to A017. |  |  | A015-A017 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting50520191112-4-R01Operator - Principle221980 | Corbiere and Sons Contracting50520191112-4-R01Operator - Principle221980Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 505 | 20191112-4-R01 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 66 | HR |  |  |  | 0 | 4950 | 643.5 | 5593.5 | 2019-11-12 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Saw hands doing cutting from A015-A017; 2 saw hands were assigned to Valard yard to do cutting for an entire day. Brushers finishing up to A017. |  |  | A015-A017 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting50520191112-4-R01Labourer - Specialized664950 | Corbiere and Sons Contracting50520191112-4-R01Labourer - Specialized664950Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 505 | 20191112-4-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2019-11-12 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Saw hands doing cutting from A015-A017; 2 saw hands were assigned to Valard yard to do cutting for an entire day. Brushers finishing up to A017. |  |  | A015-A017 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting50520191112-4-R01L.O.A.91890 | Corbiere and Sons Contracting50520191112-4-R01L.O.A.91890Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 508 | 20191112-7-R01 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking A035 east |  |  | A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting50820191112-7-R01Excavator - 36 ton91539 | Corbiere and Sons Contracting50820191112-7-R01Excavator - 36 ton91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 508 | 20191112-7-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking A035 east |  |  | A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting50820191112-7-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting50820191112-7-R01Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 508 | 20191112-7-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking A035 east |  |  | A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting50820191112-7-R01Operator - Principle11990 | Corbiere and Sons Contracting50820191112-7-R01Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 508 | 20191112-7-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking A035 east |  |  | A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting50820191112-7-R01L.O.A.1210 | Corbiere and Sons Contracting50820191112-7-R01L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 512 | 20191113-01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting51220191113-01Light Truck - Pick up501500 | Corbiere and Sons Contracting51220191113-01Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 512 | 20191113-01 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting51220191113-01Project Manager121320 | Corbiere and Sons Contracting51220191113-01Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 512 | 20191113-01 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting51220191113-01Superintendent121260 | Corbiere and Sons Contracting51220191113-01Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 512 | 20191113-01 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting51220191113-01Project Coordinator12960 | Corbiere and Sons Contracting51220191113-01Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 512 | 20191113-01 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting51220191113-01Safety Advisor121020 | Corbiere and Sons Contracting51220191113-01Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 512 | 20191113-01 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting51220191113-01Project Controls12840 | Corbiere and Sons Contracting51220191113-01Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 512 | 20191113-01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting51220191113-01L.O.A.51050 | Corbiere and Sons Contracting51220191113-01L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 514 | 20191113-03-R02 | 53520101 | Clearing | 0 | Feller Buncher | 240 |  | HR | 180 | 45 |  |  | 8100 | 1053 | 9153 | 2019-11-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting51420191113-03-R02Feller Buncher8100 | Corbiere and Sons Contracting51420191113-03-R02Feller Buncher8100Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 8100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 514 | 20191113-03-R02 | 53520101 | Clearing | 0 | Skidder | 171 |  | HR | 128.25 | 27 |  |  | 3462.75 | 450.1575 | 3912.9075 | 2019-11-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting51420191113-03-R02Skidder 3462.75 | Corbiere and Sons Contracting51420191113-03-R02Skidder 3462.75Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3462.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 514 | 20191113-03-R02 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 |  | HR | 22.5 | 60 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting51420191113-03-R02Light Truck - Pick up1350 | Corbiere and Sons Contracting51420191113-03-R02Light Truck - Pick up1350Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 514 | 20191113-03-R02 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 24 | HR |  |  |  | 0 | 2160 | 280.8 | 2440.8 | 2019-11-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting51420191113-03-R02Operator - Principle242160 | Corbiere and Sons Contracting51420191113-03-R02Operator - Principle242160Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 514 | 20191113-03-R02 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits | 1 |  |  | 1 | 43858 | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting51420191113-03-R02L.O.A.61260 | Corbiere and Sons Contracting51420191113-03-R02L.O.A.61260Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 513 | 20191113-2-R02 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-11-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Labourer - specialized has incorrect rate - Corrected Nov 16, 19 - RR Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves - orientations - Dan Pelletier assisted with float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting51320191113-2-R02Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting51320191113-2-R02Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 513 | 20191113-2-R02 | 53520105 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Labourer - specialized has incorrect rate - Corrected Nov 16, 19 - RR Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves - orientations - Dan Pelletier assisted with float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting51320191113-2-R02Light Truck - Pick up10300 | Corbiere and Sons Contracting51320191113-2-R02Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 513 | 20191113-2-R02 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Labourer - specialized has incorrect rate - Corrected Nov 16, 19 - RR Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves - orientations - Dan Pelletier assisted with float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting51320191113-2-R02Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting51320191113-2-R02Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 513 | 20191113-2-R02 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 17 | HR |  |  |  | 0 | 1530 | 198.9 | 1728.9 | 2019-11-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Labourer - specialized has incorrect rate - Corrected Nov 16, 19 - RR Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves - orientations - Dan Pelletier assisted with float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting51320191113-2-R02Operator - Principle171530 | Corbiere and Sons Contracting51320191113-2-R02Operator - Principle171530Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1530 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 513 | 20191113-2-R02 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Labourer - specialized has incorrect rate - Corrected Nov 16, 19 - RR Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves - orientations - Dan Pelletier assisted with float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting51320191113-2-R02Operator - Intermdiate11825 | Corbiere and Sons Contracting51320191113-2-R02Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 513 | 20191113-2-R02 | 53520105 | Clearing | 0 | Labourer - General | 65 | 31 | HR |  |  |  | 0 | 2015 | 261.95 | 2276.95 | 2019-11-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Labourer - specialized has incorrect rate - Corrected Nov 16, 19 - RR Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves - orientations - Dan Pelletier assisted with float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting51320191113-2-R02Labourer - General312015 | Corbiere and Sons Contracting51320191113-2-R02Labourer - General312015Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 2015 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 513 | 20191113-2-R02 | 53520105 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Labourer - specialized has incorrect rate - Corrected Nov 16, 19 - RR Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves - orientations - Dan Pelletier assisted with float moves. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting51320191113-2-R02L.O.A.4840 | Corbiere and Sons Contracting51320191113-2-R02L.O.A.4840Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 515 | 20191113-4-R01 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-11-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A019. |  |  | A019 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting51520191113-4-R01Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting51520191113-4-R01Grinder - 4710 Peterson or equal95011.2Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 515 | 20191113-4-R01 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-11-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A019. |  |  | A019 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting51520191113-4-R01Log Loader91377 | Corbiere and Sons Contracting51520191113-4-R01Log Loader91377Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 515 | 20191113-4-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A019. |  |  | A019 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting51520191113-4-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting51520191113-4-R01Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 515 | 20191113-4-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A019. |  |  | A019 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting51520191113-4-R01Operator - Principle11990 | Corbiere and Sons Contracting51520191113-4-R01Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 515 | 20191113-4-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A019. |  |  | A019 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting51520191113-4-R01L.O.A.1210 | Corbiere and Sons Contracting51520191113-4-R01L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1029 | 20191113-5-R01 | 53520102 | Clearing | 0 | Brusher | 202.5 | 27 | HR | 151.88 | 0 |  |  | 5467.5 | 710.775 | 6178.275 | 2020-01-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022 to A025; Raking from 21 to 29; Brushing from A024 to A029. |  |  | Mackenzie West | 0 |  |  | 36 | 43847 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting102920191113-5-R01Brusher275467.5 | Corbiere and Sons Contracting102920191113-5-R01Brusher275467.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5467.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1029 | 20191113-5-R01 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 9 | Day |  | 0 |  |  | 1080 | 140.4 | 1220.4 | 2020-01-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022 to A025; Raking from 21 to 29; Brushing from A024 to A029. |  |  | Mackenzie West | 0 |  |  | 36 | 43847 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting102920191113-5-R01Chainsaw and consummables91080 | Corbiere and Sons Contracting102920191113-5-R01Chainsaw and consummables91080Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1029 | 20191113-5-R01 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 9 | HR | 97.88 | 0 |  |  | 1174.5 | 152.685 | 1327.185 | 2020-01-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022 to A025; Raking from 21 to 29; Brushing from A024 to A029. |  |  | Mackenzie West | 0 |  |  | 36 | 43847 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting102920191113-5-R01Excavator - 20 ton91174.5 | Corbiere and Sons Contracting102920191113-5-R01Excavator - 20 ton91174.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1174.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1029 | 20191113-5-R01 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 9 | HR | 97.88 | 0 |  |  | 1174.5 | 152.685 | 1327.185 | 2020-01-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022 to A025; Raking from 21 to 29; Brushing from A024 to A029. |  |  | Mackenzie West | 0 |  |  | 36 | 43847 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting102920191113-5-R01Excavator - 20 ton91174.5 | Corbiere and Sons Contracting102920191113-5-R01Excavator - 20 ton91174.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1174.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1029 | 20191113-5-R01 | 53520102 | Clearing | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2020-01-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022 to A025; Raking from 21 to 29; Brushing from A024 to A029. |  |  | Mackenzie West | 0 |  |  | 36 | 43847 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting102920191113-5-R01Excavator - 30 ton91255.5 | Corbiere and Sons Contracting102920191113-5-R01Excavator - 30 ton91255.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1029 | 20191113-5-R01 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022 to A025; Raking from 21 to 29; Brushing from A024 to A029. |  |  | Mackenzie West | 0 |  |  | 36 | 43847 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting102920191113-5-R01Excavator - 36 ton91539 | Corbiere and Sons Contracting102920191113-5-R01Excavator - 36 ton91539Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1029 | 20191113-5-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022 to A025; Raking from 21 to 29; Brushing from A024 to A029. |  |  | Mackenzie West | 0 |  |  | 36 | 43847 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting102920191113-5-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting102920191113-5-R01Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1029 | 20191113-5-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022 to A025; Raking from 21 to 29; Brushing from A024 to A029. |  |  | Mackenzie West | 0 |  |  | 36 | 43847 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting102920191113-5-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting102920191113-5-R01Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1029 | 20191113-5-R01 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2020-01-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022 to A025; Raking from 21 to 29; Brushing from A024 to A029. |  |  | Mackenzie West | 0 |  |  | 36 | 43847 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting102920191113-5-R01Light Truck - Pick up401200 | Corbiere and Sons Contracting102920191113-5-R01Light Truck - Pick up401200Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1029 | 20191113-5-R01 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022 to A025; Raking from 21 to 29; Brushing from A024 to A029. |  |  | Mackenzie West | 0 |  |  | 36 | 43847 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting102920191113-5-R01Foreman121140 | Corbiere and Sons Contracting102920191113-5-R01Foreman121140Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1029 | 20191113-5-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022 to A025; Raking from 21 to 29; Brushing from A024 to A029. |  |  | Mackenzie West | 0 |  |  | 36 | 43847 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting102920191113-5-R01Operator - Principle11990 | Corbiere and Sons Contracting102920191113-5-R01Operator - Principle11990Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1029 | 20191113-5-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 66 | HR |  |  |  | 0 | 5940 | 772.2 | 6712.2 | 2020-01-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022 to A025; Raking from 21 to 29; Brushing from A024 to A029. |  |  | Mackenzie West | 0 |  |  | 36 | 43847 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting102920191113-5-R01Operator - Principle665940 | Corbiere and Sons Contracting102920191113-5-R01Operator - Principle665940Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5940 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1029 | 20191113-5-R01 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 88 | HR |  |  |  | 0 | 6600 | 858 | 7458 | 2020-01-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022 to A025; Raking from 21 to 29; Brushing from A024 to A029. |  |  | Mackenzie West | 0 |  |  | 36 | 43847 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting102920191113-5-R01Labourer - Specialized886600 | Corbiere and Sons Contracting102920191113-5-R01Labourer - Specialized886600Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 6600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1029 | 20191113-5-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-01-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022 to A025; Raking from 21 to 29; Brushing from A024 to A029. |  |  | Mackenzie West | 0 |  |  | 36 | 43847 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting102920191113-5-R01L.O.A.71470 | Corbiere and Sons Contracting102920191113-5-R01L.O.A.71470Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1029 | 20191113-5-R01 | 53520104 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-01-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022 to A025; Raking from 21 to 29; Brushing from A024 to A029. |  |  | Mackenzie West | 0 |  |  | 36 | 43847 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting102920191113-5-R01L.O.A.61260 | Corbiere and Sons Contracting102920191113-5-R01L.O.A.61260Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 517 | 20191113-6-R01 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-11-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking from A035 East |  |  | A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting51720191113-6-R01Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting51720191113-6-R01Grinder - 4710 Peterson or equal95011.2Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 517 | 20191113-6-R01 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-11-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking from A035 East |  |  | A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting51720191113-6-R01Log Loader91377 | Corbiere and Sons Contracting51720191113-6-R01Log Loader91377Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 517 | 20191113-6-R01 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking from A035 East |  |  | A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting51720191113-6-R01Excavator - 36 ton91539 | Corbiere and Sons Contracting51720191113-6-R01Excavator - 36 ton91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 517 | 20191113-6-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking from A035 East |  |  | A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting51720191113-6-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting51720191113-6-R01Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 517 | 20191113-6-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking from A035 East |  |  | A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting51720191113-6-R01Operator - Principle221980 | Corbiere and Sons Contracting51720191113-6-R01Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 517 | 20191113-6-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking from A035 East |  |  | A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting51720191113-6-R01L.O.A.2420 | Corbiere and Sons Contracting51720191113-6-R01L.O.A.2420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 521 | 20191114-01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting52120191114-01Light Truck - Pick up501500 | Corbiere and Sons Contracting52120191114-01Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 521 | 20191114-01 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting52120191114-01Project Manager121320 | Corbiere and Sons Contracting52120191114-01Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 521 | 20191114-01 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting52120191114-01Superintendent121260 | Corbiere and Sons Contracting52120191114-01Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 521 | 20191114-01 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting52120191114-01Project Coordinator12960 | Corbiere and Sons Contracting52120191114-01Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 521 | 20191114-01 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting52120191114-01Safety Advisor121020 | Corbiere and Sons Contracting52120191114-01Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 521 | 20191114-01 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting52120191114-01Project Controls12840 | Corbiere and Sons Contracting52120191114-01Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 521 | 20191114-01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting52120191114-01L.O.A.51050 | Corbiere and Sons Contracting52120191114-01L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 523 | 20191114-03-R02 | 53520101 | Clearing | 0 | Feller Buncher | 240 |  | HR | 180 | 36 |  |  | 6480 | 842.4 | 7322.4 | 2019-11-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standy due to permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting52320191114-03-R02Feller Buncher6480 | Corbiere and Sons Contracting52320191114-03-R02Feller Buncher6480Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 6480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 523 | 20191114-03-R02 | 53520101 | Clearing | 0 | Mulcher | 205 |  | HR | 153.75 | 9 |  |  | 1383.75 | 179.8875 | 1563.6375 | 2019-11-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standy due to permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting52320191114-03-R02Mulcher1383.75 | Corbiere and Sons Contracting52320191114-03-R02Mulcher1383.75Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1383.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 523 | 20191114-03-R02 | 53520101 | Clearing | 0 | Skidder | 171 |  | HR | 128.25 | 27 |  |  | 3462.75 | 450.1575 | 3912.9075 | 2019-11-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standy due to permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting52320191114-03-R02Skidder 3462.75 | Corbiere and Sons Contracting52320191114-03-R02Skidder 3462.75Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3462.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 523 | 20191114-03-R02 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 |  | HR | 22.5 | 50 |  |  | 1125 | 146.25 | 1271.25 | 2019-11-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standy due to permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting52320191114-03-R02Light Truck - Pick up1125 | Corbiere and Sons Contracting52320191114-03-R02Light Truck - Pick up1125Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 523 | 20191114-03-R02 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 24 | HR |  |  |  | 0 | 2160 | 280.8 | 2440.8 | 2019-11-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standy due to permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting52320191114-03-R02Operator - Principle242160 | Corbiere and Sons Contracting52320191114-03-R02Operator - Principle242160Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 523 | 20191114-03-R02 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standy due to permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting52320191114-03-R02L.O.A.61260 | Corbiere and Sons Contracting52320191114-03-R02L.O.A.61260Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 526 | 20191114-06-R01 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and grinding from A030-A035 |  |  | A030-A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52620191114-06-R01Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting52620191114-06-R01Grinder - 4710 Peterson or equal1810022.4Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 526 | 20191114-06-R01 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and grinding from A030-A035 |  |  | A030-A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52620191114-06-R01Log Loader182754 | Corbiere and Sons Contracting52620191114-06-R01Log Loader182754Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 526 | 20191114-06-R01 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and grinding from A030-A035 |  |  | A030-A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52620191114-06-R01Excavator - 36 ton183078 | Corbiere and Sons Contracting52620191114-06-R01Excavator - 36 ton183078Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 526 | 20191114-06-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and grinding from A030-A035 |  |  | A030-A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52620191114-06-R01Light Truck - Pick up501500 | Corbiere and Sons Contracting52620191114-06-R01Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 526 | 20191114-06-R01 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and grinding from A030-A035 |  |  | A030-A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52620191114-06-R01Foreman121140 | Corbiere and Sons Contracting52620191114-06-R01Foreman121140Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 526 | 20191114-06-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and grinding from A030-A035 |  |  | A030-A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52620191114-06-R01Operator - Principle443960 | Corbiere and Sons Contracting52620191114-06-R01Operator - Principle443960Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 526 | 20191114-06-R01 | 53520102 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and grinding from A030-A035 |  |  | A030-A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52620191114-06-R01Labourer - General11715 | Corbiere and Sons Contracting52620191114-06-R01Labourer - General11715Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 526 | 20191114-06-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and grinding from A030-A035 |  |  | A030-A035 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52620191114-06-R01L.O.A.61260 | Corbiere and Sons Contracting52620191114-06-R01L.O.A.61260Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 529 | 20191114-09 | 53520102 | Clearing | 0 | Chainsaw and consummables | 120 | 2 | Day |  | 0 |  |  | 240 | 31.2 | 271.2 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Chainsaw work at railway A048, A049 |  |  | A048, A049 | 0 |  |  | 19 | 43792 | [5 empty] | Bob Grocholski | 01 | Corbiere and Sons Contracting52920191114-09Chainsaw and consummables2240 | Corbiere and Sons Contracting52920191114-09Chainsaw and consummables2240Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 529 | 20191114-09 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Chainsaw work at railway A048, A049 |  |  | A048, A049 | 0 |  |  | 19 | 43792 | [5 empty] | Bob Grocholski | 01 | Corbiere and Sons Contracting52920191114-09Light Truck - Pick up10300 | Corbiere and Sons Contracting52920191114-09Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 529 | 20191114-09 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 22 | HR |  |  |  | 0 | 1650 | 214.5 | 1864.5 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Chainsaw work at railway A048, A049 |  |  | A048, A049 | 0 |  |  | 19 | 43792 | [5 empty] | Bob Grocholski | 01 | Corbiere and Sons Contracting52920191114-09Labourer - Specialized221650 | Corbiere and Sons Contracting52920191114-09Labourer - Specialized221650Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 983 | 20191114-2-R01 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 4 | HR | 94.5 | 5 |  |  | 976.5 | 126.945 | 1103.445 | 2019-12-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard and equipment maintenance- Float moves-Grader did work in yard and then was on SB- Sacha oriented- Sander Truck on SB. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting98320191114-2-R01Grader - Cat 12 to 14 or equal4976.5 | Corbiere and Sons Contracting98320191114-2-R01Grader - Cat 12 to 14 or equal4976.5Inv#005-R01 | [5 empty] | 1 | 976.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 983 | 20191114-2-R01 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-12-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard and equipment maintenance- Float moves-Grader did work in yard and then was on SB- Sacha oriented- Sander Truck on SB. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting98320191114-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting98320191114-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 983 | 20191114-2-R01 | 53510111 | Access | 0 | Sander Truck | 112.5 |  | HR | 84.38 | 9 |  |  | 759.42 | 98.7246 | 858.1446 | 2019-12-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard and equipment maintenance- Float moves-Grader did work in yard and then was on SB- Sacha oriented- Sander Truck on SB. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting98320191114-2-R01Sander Truck759.42 | Corbiere and Sons Contracting98320191114-2-R01Sander Truck759.42Inv#005-R01 | [5 empty] | 1 | 759.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 983 | 20191114-2-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard and equipment maintenance- Float moves-Grader did work in yard and then was on SB- Sacha oriented- Sander Truck on SB. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting98320191114-2-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting98320191114-2-R01Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 983 | 20191114-2-R01 | 53520101 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-12-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard and equipment maintenance- Float moves-Grader did work in yard and then was on SB- Sacha oriented- Sander Truck on SB. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting98320191114-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting98320191114-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 983 | 20191114-2-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 17 | HR |  |  |  | 0 | 1530 | 198.9 | 1728.9 | 2019-12-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard and equipment maintenance- Float moves-Grader did work in yard and then was on SB- Sacha oriented- Sander Truck on SB. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting98320191114-2-R01Operator - Principle171530 | Corbiere and Sons Contracting98320191114-2-R01Operator - Principle171530Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1530 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 983 | 20191114-2-R01 | 53520101 | Clearing | 0 | Operator - Intermdiate | 75 | 16 | HR |  |  | 70 | 0 | 1200 | 156 | 1356 | 2019-12-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard and equipment maintenance- Float moves-Grader did work in yard and then was on SB- Sacha oriented- Sander Truck on SB. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting98320191114-2-R01Operator - Intermdiate161200 | Corbiere and Sons Contracting98320191114-2-R01Operator - Intermdiate161200Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 983 | 20191114-2-R01 | 53520101 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-12-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard and equipment maintenance- Float moves-Grader did work in yard and then was on SB- Sacha oriented- Sander Truck on SB. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting98320191114-2-R01Labourer - General10650 | Corbiere and Sons Contracting98320191114-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 983 | 20191114-2-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-11 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard and equipment maintenance- Float moves-Grader did work in yard and then was on SB- Sacha oriented- Sander Truck on SB. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting98320191114-2-R01L.O.A.4840 | Corbiere and Sons Contracting98320191114-2-R01L.O.A.4840Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 524 | 20191114-4-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finish Clearing from A018-A020 |  |  | A018-A020 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52420191114-4-R01Feller Buncher92160 | Corbiere and Sons Contracting52420191114-4-R01Feller Buncher92160Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 524 | 20191114-4-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finish Clearing from A018-A020 |  |  | A018-A020 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52420191114-4-R01Skidder 91539 | Corbiere and Sons Contracting52420191114-4-R01Skidder 91539Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 524 | 20191114-4-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finish Clearing from A018-A020 |  |  | A018-A020 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52420191114-4-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting52420191114-4-R01Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 524 | 20191114-4-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finish Clearing from A018-A020 |  |  | A018-A020 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52420191114-4-R01Operator - Principle221980 | Corbiere and Sons Contracting52420191114-4-R01Operator - Principle221980Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 524 | 20191114-4-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finish Clearing from A018-A020 |  |  | A018-A020 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52420191114-4-R01L.O.A.1210 | Corbiere and Sons Contracting52420191114-4-R01L.O.A.1210Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 525 | 20191114-5-R01 | 53520102 | Clearing | 0 | Brusher | 202.5 | 27 | HR | 151.88 | 0 |  |  | 5467.5 | 710.775 | 6178.275 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022-A025, raking from A021-A029, brushing from A024-A029 |  |  | A022-A025, A024-A029 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52520191114-5-R01Brusher275467.5 | Corbiere and Sons Contracting52520191114-5-R01Brusher275467.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5467.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 525 | 20191114-5-R01 | 53520102 | Clearing | 0 | Chainsaw and consummables | 120 | 6 | Day |  | 0 |  |  | 720 | 93.6 | 813.6 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022-A025, raking from A021-A029, brushing from A024-A029 |  |  | A022-A025, A024-A029 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52520191114-5-R01Chainsaw and consummables6720 | Corbiere and Sons Contracting52520191114-5-R01Chainsaw and consummables6720Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 525 | 20191114-5-R01 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 18 | HR | 97.88 | 0 |  |  | 2349 | 305.37 | 2654.37 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022-A025, raking from A021-A029, brushing from A024-A029 |  |  | A022-A025, A024-A029 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52520191114-5-R01Excavator - 20 ton182349 | Corbiere and Sons Contracting52520191114-5-R01Excavator - 20 ton182349Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2349 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 525 | 20191114-5-R01 | 53520102 | Clearing | 0 | Excavator - 30 ton | 139.5 | 18 | HR | 104.63 | 0 |  |  | 2511 | 326.43 | 2837.43 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022-A025, raking from A021-A029, brushing from A024-A029 |  |  | A022-A025, A024-A029 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52520191114-5-R01Excavator - 30 ton182511 | Corbiere and Sons Contracting52520191114-5-R01Excavator - 30 ton182511Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2511 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 525 | 20191114-5-R01 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022-A025, raking from A021-A029, brushing from A024-A029 |  |  | A022-A025, A024-A029 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52520191114-5-R01Excavator - 36 ton91539 | Corbiere and Sons Contracting52520191114-5-R01Excavator - 36 ton91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 525 | 20191114-5-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022-A025, raking from A021-A029, brushing from A024-A029 |  |  | A022-A025, A024-A029 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52520191114-5-R01Light Truck - Pick up501500 | Corbiere and Sons Contracting52520191114-5-R01Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 525 | 20191114-5-R01 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022-A025, raking from A021-A029, brushing from A024-A029 |  |  | A022-A025, A024-A029 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52520191114-5-R01Foreman121140 | Corbiere and Sons Contracting52520191114-5-R01Foreman121140Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 525 | 20191114-5-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 88 | HR |  |  |  | 0 | 7920 | 1029.6 | 8949.6 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022-A025, raking from A021-A029, brushing from A024-A029 |  |  | A022-A025, A024-A029 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52520191114-5-R01Operator - Principle887920 | Corbiere and Sons Contracting52520191114-5-R01Operator - Principle887920Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 7920 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 525 | 20191114-5-R01 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 55 | HR |  |  |  | 0 | 4125 | 536.25 | 4661.25 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022-A025, raking from A021-A029, brushing from A024-A029 |  |  | A022-A025, A024-A029 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52520191114-5-R01Labourer - Specialized554125 | Corbiere and Sons Contracting52520191114-5-R01Labourer - Specialized554125Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 525 | 20191114-5-R01 | 53520102 | Clearing | 0 | Labourer - General | 65 | 22 | HR |  |  |  | 0 | 1430 | 185.9 | 1615.9 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022-A025, raking from A021-A029, brushing from A024-A029 |  |  | A022-A025, A024-A029 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52520191114-5-R01Labourer - General221430 | Corbiere and Sons Contracting52520191114-5-R01Labourer - General221430Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1430 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 525 | 20191114-5-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 15 | DAY |  |  |  | 0 | 3150 | 409.5 | 3559.5 | 2019-11-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Saw hands working from A022-A025, raking from A021-A029, brushing from A024-A029 |  |  | A022-A025, A024-A029 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting52520191114-5-R01L.O.A.153150 | Corbiere and Sons Contracting52520191114-5-R01L.O.A.153150Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 530 | 20191115--01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting53020191115--01Light Truck - Pick up501500 | Corbiere and Sons Contracting53020191115--01Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 530 | 20191115--01 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting53020191115--01Project Manager121320 | Corbiere and Sons Contracting53020191115--01Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 530 | 20191115--01 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting53020191115--01Superintendent121260 | Corbiere and Sons Contracting53020191115--01Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 530 | 20191115--01 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting53020191115--01Project Coordinator12960 | Corbiere and Sons Contracting53020191115--01Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 530 | 20191115--01 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting53020191115--01Safety Advisor121020 | Corbiere and Sons Contracting53020191115--01Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 530 | 20191115--01 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting53020191115--01Project Controls12840 | Corbiere and Sons Contracting53020191115--01Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 530 | 20191115--01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting53020191115--01L.O.A.51050 | Corbiere and Sons Contracting53020191115--01L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 532 | 20191115-03-R02 | 53520101 | Clearing | 0 | Feller Buncher | 240 |  | HR | 180 | 36 |  |  | 6480 | 842.4 | 7322.4 | 2019-11-15 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53220191115-03-R02Feller Buncher6480 | Corbiere and Sons Contracting53220191115-03-R02Feller Buncher6480Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 6480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 532 | 20191115-03-R02 | 53520101 | Clearing | 0 | Mulcher | 205 |  | HR | 153.75 | 9 |  |  | 1383.75 | 179.8875 | 1563.6375 | 2019-11-15 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53220191115-03-R02Mulcher1383.75 | Corbiere and Sons Contracting53220191115-03-R02Mulcher1383.75Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1383.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 532 | 20191115-03-R02 | 53520101 | Clearing | 0 | Skidder | 171 |  | HR | 128.25 | 27 |  |  | 3462.75 | 450.1575 | 3912.9075 | 2019-11-15 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53220191115-03-R02Skidder 3462.75 | Corbiere and Sons Contracting53220191115-03-R02Skidder 3462.75Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3462.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 532 | 20191115-03-R02 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 |  | HR | 22.5 | 50 |  |  | 1125 | 146.25 | 1271.25 | 2019-11-15 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53220191115-03-R02Light Truck - Pick up1125 | Corbiere and Sons Contracting53220191115-03-R02Light Truck - Pick up1125Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 532 | 20191115-03-R02 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 24 | HR |  |  |  | 0 | 2160 | 280.8 | 2440.8 | 2019-11-15 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53220191115-03-R02Operator - Principle242160 | Corbiere and Sons Contracting53220191115-03-R02Operator - Principle242160Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 532 | 20191115-03-R02 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-15 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53220191115-03-R02L.O.A.61260 | Corbiere and Sons Contracting53220191115-03-R02L.O.A.61260Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 534 | 20191115-05 | 53520102 | Clearing | 0 | Chainsaw and consummables | 120 | 6 | Day |  | 0 |  |  | 720 | 93.6 | 813.6 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished up hand falling to A029 and carried on Eastward. |  |  |  | 0 |  |  | 8 | 43786 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting53420191115-05Chainsaw and consummables6720 | Corbiere and Sons Contracting53420191115-05Chainsaw and consummables6720Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 534 | 20191115-05 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished up hand falling to A029 and carried on Eastward. |  |  |  | 0 |  |  | 8 | 43786 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting53420191115-05Light Truck - Pick up20600 | Corbiere and Sons Contracting53420191115-05Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 534 | 20191115-05 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished up hand falling to A029 and carried on Eastward. |  |  |  | 0 |  |  | 8 | 43786 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting53420191115-05Foreman121140 | Corbiere and Sons Contracting53420191115-05Foreman121140Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 534 | 20191115-05 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 55 | HR |  |  |  | 0 | 4125 | 536.25 | 4661.25 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished up hand falling to A029 and carried on Eastward. |  |  |  | 0 |  |  | 8 | 43786 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting53420191115-05Labourer - Specialized554125 | Corbiere and Sons Contracting53420191115-05Labourer - Specialized554125Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 534 | 20191115-05 | 53520102 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished up hand falling to A029 and carried on Eastward. |  |  |  | 0 |  |  | 8 | 43786 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting53420191115-05L.O.A.61260 | Corbiere and Sons Contracting53420191115-05L.O.A.61260Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 536 | 20191115-07 | 53520102 | Clearing | 0 | Chainsaw and consummables | 120 | 2 | Day |  | 0 |  |  | 240 | 31.2 | 271.2 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Worked from A045-Ao42. Finished the day by 3pm. |  |  |  | 0 |  |  | 19 | 43792 | [5 empty] | Bob Grocholski | 01 | Corbiere and Sons Contracting53620191115-07Chainsaw and consummables2240 | Corbiere and Sons Contracting53620191115-07Chainsaw and consummables2240Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 536 | 20191115-07 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Worked from A045-Ao42. Finished the day by 3pm. |  |  |  | 0 |  |  | 19 | 43792 | [5 empty] | Bob Grocholski | 01 | Corbiere and Sons Contracting53620191115-07Light Truck - Pick up10300 | Corbiere and Sons Contracting53620191115-07Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 536 | 20191115-07 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 22 | HR |  |  |  | 0 | 1650 | 214.5 | 1864.5 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Worked from A045-Ao42. Finished the day by 3pm. |  |  |  | 0 |  |  | 19 | 43792 | [5 empty] | Bob Grocholski | 01 | Corbiere and Sons Contracting53620191115-07Labourer - Specialized221650 | Corbiere and Sons Contracting53620191115-07Labourer - Specialized221650Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 539 | 20191115-10-R01 | 53510112 | Access | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Widening existing road from A051 to railway crossing.. |  |  | A051 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting53920191115-10-R01Dozer D6 or equal91215 | Corbiere and Sons Contracting53920191115-10-R01Dozer D6 or equal91215Inv#004-R02 | [5 empty] | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 539 | 20191115-10-R01 | 53510112 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Widening existing road from A051 to railway crossing.. |  |  | A051 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting53920191115-10-R01Operator - Principle11990 | Corbiere and Sons Contracting53920191115-10-R01Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 539 | 20191115-10-R01 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Widening existing road from A051 to railway crossing.. |  |  | A051 | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting53920191115-10-R01L.O.A.1210 | Corbiere and Sons Contracting53920191115-10-R01L.O.A.1210Inv#004-R02 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 531 | 20191115-2-R01 | 53520105 | Clearing | 0 | Grader - Cat 12 to 14 or equal | 126 |  | HR | 94.5 | 9.5 |  |  | 897.75 | 116.7075 | 1014.4575 | 2019-11-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- Grader, Sander truck and both operators on SB. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53120191115-2-R01Grader - Cat 12 to 14 or equal897.75 | Corbiere and Sons Contracting53120191115-2-R01Grader - Cat 12 to 14 or equal897.75Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 897.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 531 | 20191115-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-11-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- Grader, Sander truck and both operators on SB. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53120191115-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting53120191115-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 531 | 20191115-2-R01 | 53520105 | Clearing | 0 | Sander Truck | 112.5 |  | HR | 84.38 | 9.5 |  |  | 801.61 | 104.2093 | 905.8193 | 2019-11-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- Grader, Sander truck and both operators on SB. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53120191115-2-R01Sander Truck801.61 | Corbiere and Sons Contracting53120191115-2-R01Sander Truck801.61Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 801.61 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 531 | 20191115-2-R01 | 53520105 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- Grader, Sander truck and both operators on SB. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53120191115-2-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting53120191115-2-R01Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 531 | 20191115-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- Grader, Sander truck and both operators on SB. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53120191115-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting53120191115-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 531 | 20191115-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 16 | HR |  |  |  | 0 | 1440 | 187.2 | 1627.2 | 2019-11-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- Grader, Sander truck and both operators on SB. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53120191115-2-R01Operator - Principle161440 | Corbiere and Sons Contracting53120191115-2-R01Operator - Principle161440Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 531 | 20191115-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 15 | HR |  |  | 70 | 0 | 1125 | 146.25 | 1271.25 | 2019-11-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- Grader, Sander truck and both operators on SB. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53120191115-2-R01Operator - Intermdiate151125 | Corbiere and Sons Contracting53120191115-2-R01Operator - Intermdiate151125Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 531 | 20191115-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-11-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- Grader, Sander truck and both operators on SB. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53120191115-2-R01Labourer - General10650 | Corbiere and Sons Contracting53120191115-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 531 | 20191115-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- Grader, Sander truck and both operators on SB. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53120191115-2-R01L.O.A.4840 | Corbiere and Sons Contracting53120191115-2-R01L.O.A.4840Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 535 | 20191115-6-R01 | 53520102 | Clearing | 0 | Brusher | 202.5 | 27 | HR | 151.88 | 0 |  |  | 5467.5 | 710.775 | 6178.275 | 2019-11-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and grinding from A030-A035, labourers fueld, flagged and cleaned tracks. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53520191115-6-R01Brusher275467.5 | Corbiere and Sons Contracting53520191115-6-R01Brusher275467.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5467.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 535 | 20191115-6-R01 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-11-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and grinding from A030-A035, labourers fueld, flagged and cleaned tracks. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53520191115-6-R01Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting53520191115-6-R01Grinder - 4710 Peterson or equal1810022.4Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 535 | 20191115-6-R01 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-11-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and grinding from A030-A035, labourers fueld, flagged and cleaned tracks. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53520191115-6-R01Log Loader182754 | Corbiere and Sons Contracting53520191115-6-R01Log Loader182754Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 535 | 20191115-6-R01 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 12 | HR | 97.88 | 0 |  |  | 1566 | 203.58 | 1769.58 | 2019-11-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and grinding from A030-A035, labourers fueld, flagged and cleaned tracks. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53520191115-6-R01Excavator - 20 ton121566 | Corbiere and Sons Contracting53520191115-6-R01Excavator - 20 ton121566Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1566 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 535 | 20191115-6-R01 | 53520102 | Clearing | 0 | Excavator - 30 ton | 139.5 | 18 | HR | 104.63 | 0 |  |  | 2511 | 326.43 | 2837.43 | 2019-11-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and grinding from A030-A035, labourers fueld, flagged and cleaned tracks. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53520191115-6-R01Excavator - 30 ton182511 | Corbiere and Sons Contracting53520191115-6-R01Excavator - 30 ton182511Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2511 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 535 | 20191115-6-R01 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 27 | HR | 128.25 | 0 |  |  | 4617 | 600.21 | 5217.21 | 2019-11-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and grinding from A030-A035, labourers fueld, flagged and cleaned tracks. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53520191115-6-R01Excavator - 36 ton274617 | Corbiere and Sons Contracting53520191115-6-R01Excavator - 36 ton274617Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 535 | 20191115-6-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 80 | HR | 22.5 | 0 |  |  | 2400 | 312 | 2712 | 2019-11-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and grinding from A030-A035, labourers fueld, flagged and cleaned tracks. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53520191115-6-R01Light Truck - Pick up802400 | Corbiere and Sons Contracting53520191115-6-R01Light Truck - Pick up802400Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 535 | 20191115-6-R01 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and grinding from A030-A035, labourers fueld, flagged and cleaned tracks. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53520191115-6-R01Foreman121140 | Corbiere and Sons Contracting53520191115-6-R01Foreman121140Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 535 | 20191115-6-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 125 | HR |  |  |  | 0 | 11250 | 1462.5 | 12712.5 | 2019-11-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and grinding from A030-A035, labourers fueld, flagged and cleaned tracks. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53520191115-6-R01Operator - Principle12511250 | Corbiere and Sons Contracting53520191115-6-R01Operator - Principle12511250Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 11250 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 535 | 20191115-6-R01 | 53520102 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-11-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and grinding from A030-A035, labourers fueld, flagged and cleaned tracks. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53520191115-6-R01Labourer - General11715 | Corbiere and Sons Contracting53520191115-6-R01Labourer - General11715Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 535 | 20191115-6-R01 | 53520102 | Clearing | 0 | Labourer - General | 65 | 44 | HR |  |  |  | 0 | 2860 | 371.8 | 3231.8 | 2019-11-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and grinding from A030-A035, labourers fueld, flagged and cleaned tracks. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53520191115-6-R01Labourer - General442860 | Corbiere and Sons Contracting53520191115-6-R01Labourer - General442860Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2860 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 535 | 20191115-6-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 15 | DAY |  |  |  | 0 | 3150 | 409.5 | 3559.5 | 2019-11-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and grinding from A030-A035, labourers fueld, flagged and cleaned tracks. |  |  |  | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting53520191115-6-R01L.O.A.153150 | Corbiere and Sons Contracting53520191115-6-R01L.O.A.153150Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 537 | 20191115-8-R01 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A052 - A054 |  |  |  | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting53720191115-8-R01Feller Buncher92160 | Corbiere and Sons Contracting53720191115-8-R01Feller Buncher92160Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 537 | 20191115-8-R01 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A052 - A054 |  |  |  | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting53720191115-8-R01Skidder 91539 | Corbiere and Sons Contracting53720191115-8-R01Skidder 91539Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 537 | 20191115-8-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A052 - A054 |  |  |  | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting53720191115-8-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting53720191115-8-R01Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 537 | 20191115-8-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A052 - A054 |  |  |  | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting53720191115-8-R01Operator - Principle221980 | Corbiere and Sons Contracting53720191115-8-R01Operator - Principle221980Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 537 | 20191115-8-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A052 - A054 |  |  |  | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting53720191115-8-R01L.O.A.1210 | Corbiere and Sons Contracting53720191115-8-R01L.O.A.1210Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 540 | 20191116-01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-16 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting54020191116-01Light Truck - Pick up501500 | Corbiere and Sons Contracting54020191116-01Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 540 | 20191116-01 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-16 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting54020191116-01Project Manager121320 | Corbiere and Sons Contracting54020191116-01Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 540 | 20191116-01 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-16 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting54020191116-01Superintendent121260 | Corbiere and Sons Contracting54020191116-01Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 540 | 20191116-01 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-16 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting54020191116-01Project Coordinator12960 | Corbiere and Sons Contracting54020191116-01Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 540 | 20191116-01 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-16 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting54020191116-01Safety Advisor121020 | Corbiere and Sons Contracting54020191116-01Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 540 | 20191116-01 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-16 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting54020191116-01Project Controls12840 | Corbiere and Sons Contracting54020191116-01Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 540 | 20191116-01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-16 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43793 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting54020191116-01L.O.A.51050 | Corbiere and Sons Contracting54020191116-01L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 542 | 20191116-03-R02 | 53520101 | Clearing | 0 | Feller Buncher | 240 |  | HR | 180 | 45 |  |  | 8100 | 1053 | 9153 | 2019-11-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54220191116-03-R02Feller Buncher8100 | Corbiere and Sons Contracting54220191116-03-R02Feller Buncher8100Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 8100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 542 | 20191116-03-R02 | 53520101 | Clearing | 0 | Skidder | 171 |  | HR | 128.25 | 36 |  |  | 4617 | 600.21 | 5217.21 | 2019-11-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54220191116-03-R02Skidder 4617 | Corbiere and Sons Contracting54220191116-03-R02Skidder 4617Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 542 | 20191116-03-R02 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 |  | HR | 22.5 | 50 |  |  | 1125 | 146.25 | 1271.25 | 2019-11-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54220191116-03-R02Light Truck - Pick up1125 | Corbiere and Sons Contracting54220191116-03-R02Light Truck - Pick up1125Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 542 | 20191116-03-R02 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 24 | HR |  |  |  | 0 | 2160 | 280.8 | 2440.8 | 2019-11-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54220191116-03-R02Operator - Principle242160 | Corbiere and Sons Contracting54220191116-03-R02Operator - Principle242160Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 542 | 20191116-03-R02 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits |  |  |  | 1 |  | Missing Permit | 35 | 43861 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54220191116-03-R02L.O.A.61260 | Corbiere and Sons Contracting54220191116-03-R02L.O.A.61260Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 544 | 20191116-05-R01 | 53520102 | Clearing | 0 | Brusher | 202.5 | 25.5 | HR | 151.88 | 0 |  |  | 5163.75 | 671.2875 | 5835.0375 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand falling between A032 and A034, raking, brushing, hauling out logs to road for land owner. Labourers fueling, flagging, cleaning tracks. Equipment floated to A046 to continue once completed. |  |  | A032- A034 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54420191116-05-R01Brusher25.55163.75 | Corbiere and Sons Contracting54420191116-05-R01Brusher25.55163.75Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5163.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 544 | 20191116-05-R01 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand falling between A032 and A034, raking, brushing, hauling out logs to road for land owner. Labourers fueling, flagging, cleaning tracks. Equipment floated to A046 to continue once completed. |  |  | A032- A034 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54420191116-05-R01Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting54420191116-05-R01Grinder - 4710 Peterson or equal1810022.4Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 544 | 20191116-05-R01 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand falling between A032 and A034, raking, brushing, hauling out logs to road for land owner. Labourers fueling, flagging, cleaning tracks. Equipment floated to A046 to continue once completed. |  |  | A032- A034 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54420191116-05-R01Log Loader182754 | Corbiere and Sons Contracting54420191116-05-R01Log Loader182754Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 544 | 20191116-05-R01 | 53520102 | Clearing | 0 | Excavator - 30 ton | 139.5 | 18 | HR | 104.63 | 0 |  |  | 2511 | 326.43 | 2837.43 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand falling between A032 and A034, raking, brushing, hauling out logs to road for land owner. Labourers fueling, flagging, cleaning tracks. Equipment floated to A046 to continue once completed. |  |  | A032- A034 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54420191116-05-R01Excavator - 30 ton182511 | Corbiere and Sons Contracting54420191116-05-R01Excavator - 30 ton182511Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2511 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 544 | 20191116-05-R01 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 27 | HR | 128.25 | 0 |  |  | 4617 | 600.21 | 5217.21 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand falling between A032 and A034, raking, brushing, hauling out logs to road for land owner. Labourers fueling, flagging, cleaning tracks. Equipment floated to A046 to continue once completed. |  |  | A032- A034 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54420191116-05-R01Excavator - 36 ton274617 | Corbiere and Sons Contracting54420191116-05-R01Excavator - 36 ton274617Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 544 | 20191116-05-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 100 | HR | 22.5 | 0 |  |  | 3000 | 390 | 3390 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand falling between A032 and A034, raking, brushing, hauling out logs to road for land owner. Labourers fueling, flagging, cleaning tracks. Equipment floated to A046 to continue once completed. |  |  | A032- A034 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54420191116-05-R01Light Truck - Pick up1003000 | Corbiere and Sons Contracting54420191116-05-R01Light Truck - Pick up1003000Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3000 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 544 | 20191116-05-R01 | 53520102 | Clearing | 0 | Foreman | 95 | 24 | HR |  |  |  | 0 | 2280 | 296.4 | 2576.4 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand falling between A032 and A034, raking, brushing, hauling out logs to road for land owner. Labourers fueling, flagging, cleaning tracks. Equipment floated to A046 to continue once completed. |  |  | A032- A034 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54420191116-05-R01Foreman242280 | Corbiere and Sons Contracting54420191116-05-R01Foreman242280Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 544 | 20191116-05-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 110 | HR |  |  |  | 0 | 9900 | 1287 | 11187 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand falling between A032 and A034, raking, brushing, hauling out logs to road for land owner. Labourers fueling, flagging, cleaning tracks. Equipment floated to A046 to continue once completed. |  |  | A032- A034 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54420191116-05-R01Operator - Principle1109900 | Corbiere and Sons Contracting54420191116-05-R01Operator - Principle1109900Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 9900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 544 | 20191116-05-R01 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 55 | HR |  |  |  | 0 | 4125 | 536.25 | 4661.25 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand falling between A032 and A034, raking, brushing, hauling out logs to road for land owner. Labourers fueling, flagging, cleaning tracks. Equipment floated to A046 to continue once completed. |  |  | A032- A034 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54420191116-05-R01Labourer - Specialized554125 | Corbiere and Sons Contracting54420191116-05-R01Labourer - Specialized554125Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 544 | 20191116-05-R01 | 53520102 | Clearing | 0 | Labourer - General | 65 | 49 | HR |  |  |  | 0 | 3185 | 414.05 | 3599.05 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand falling between A032 and A034, raking, brushing, hauling out logs to road for land owner. Labourers fueling, flagging, cleaning tracks. Equipment floated to A046 to continue once completed. |  |  | A032- A034 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54420191116-05-R01Labourer - General493185 | Corbiere and Sons Contracting54420191116-05-R01Labourer - General493185Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3185 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 544 | 20191116-05-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 18 | DAY |  |  |  | 0 | 3780 | 491.4 | 4271.4 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand falling between A032 and A034, raking, brushing, hauling out logs to road for land owner. Labourers fueling, flagging, cleaning tracks. Equipment floated to A046 to continue once completed. |  |  | A032- A034 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54420191116-05-R01L.O.A.183780 | Corbiere and Sons Contracting54420191116-05-R01L.O.A.183780Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3780 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 541 | 20191116-2-R01 | 53520105 | Clearing | 0 | Grader - Cat 12 to 14 or equal | 126 |  | HR | 94.5 | 9.5 |  |  | 897.75 | 116.7075 | 1014.4575 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- grader, sander truck and sander operator or SB, Dan Pelletier assisted in float move, Denis Roy Orientations and the field work with grinder. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54120191116-2-R01Grader - Cat 12 to 14 or equal897.75 | Corbiere and Sons Contracting54120191116-2-R01Grader - Cat 12 to 14 or equal897.75Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 897.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 541 | 20191116-2-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- grader, sander truck and sander operator or SB, Dan Pelletier assisted in float move, Denis Roy Orientations and the field work with grinder. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54120191116-2-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting54120191116-2-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 541 | 20191116-2-R01 | 53520105 | Clearing | 0 | Sander Truck | 112.5 |  | HR | 84.38 | 9.5 |  |  | 801.61 | 104.2093 | 905.8193 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- grader, sander truck and sander operator or SB, Dan Pelletier assisted in float move, Denis Roy Orientations and the field work with grinder. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54120191116-2-R01Sander Truck801.61 | Corbiere and Sons Contracting54120191116-2-R01Sander Truck801.61Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 801.61 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 541 | 20191116-2-R01 | 53520105 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- grader, sander truck and sander operator or SB, Dan Pelletier assisted in float move, Denis Roy Orientations and the field work with grinder. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54120191116-2-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting54120191116-2-R01Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 541 | 20191116-2-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- grader, sander truck and sander operator or SB, Dan Pelletier assisted in float move, Denis Roy Orientations and the field work with grinder. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54120191116-2-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting54120191116-2-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 541 | 20191116-2-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 17 | HR |  |  |  | 0 | 1530 | 198.9 | 1728.9 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- grader, sander truck and sander operator or SB, Dan Pelletier assisted in float move, Denis Roy Orientations and the field work with grinder. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54120191116-2-R01Operator - Principle171530 | Corbiere and Sons Contracting54120191116-2-R01Operator - Principle171530Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1530 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 541 | 20191116-2-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 25 | HR |  |  | 70 | 0 | 1875 | 243.75 | 2118.75 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- grader, sander truck and sander operator or SB, Dan Pelletier assisted in float move, Denis Roy Orientations and the field work with grinder. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54120191116-2-R01Operator - Intermdiate251875 | Corbiere and Sons Contracting54120191116-2-R01Operator - Intermdiate251875Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1875 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 541 | 20191116-2-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- grader, sander truck and sander operator or SB, Dan Pelletier assisted in float move, Denis Roy Orientations and the field work with grinder. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54120191116-2-R01Labourer - General10650 | Corbiere and Sons Contracting54120191116-2-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 541 | 20191116-2-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance - float moves- grader, sander truck and sander operator or SB, Dan Pelletier assisted in float move, Denis Roy Orientations and the field work with grinder. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54120191116-2-R01L.O.A.4840 | Corbiere and Sons Contracting54120191116-2-R01L.O.A.4840Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 545 | 20191116-6-R01 | 53510112 | Access | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Widening road from A044-A043. From 4m to 6m. Labourers installing culverts and cleaning tracks. |  |  | A044-A043 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54520191116-6-R01Excavator - 36 ton91539 | Corbiere and Sons Contracting54520191116-6-R01Excavator - 36 ton91539Inv#005-R01 | [5 empty] | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 545 | 20191116-6-R01 | 53510112 | Access | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Widening road from A044-A043. From 4m to 6m. Labourers installing culverts and cleaning tracks. |  |  | A044-A043 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54520191116-6-R01Light Truck - Pick up20600 | Corbiere and Sons Contracting54520191116-6-R01Light Truck - Pick up20600Inv#005-R01 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 545 | 20191116-6-R01 | 53510112 | Access | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Widening road from A044-A043. From 4m to 6m. Labourers installing culverts and cleaning tracks. |  |  | A044-A043 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54520191116-6-R01Foreman121140 | Corbiere and Sons Contracting54520191116-6-R01Foreman121140Inv#005-R01 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 545 | 20191116-6-R01 | 53510112 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Widening road from A044-A043. From 4m to 6m. Labourers installing culverts and cleaning tracks. |  |  | A044-A043 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54520191116-6-R01Operator - Principle11990 | Corbiere and Sons Contracting54520191116-6-R01Operator - Principle11990Inv#005-R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 545 | 20191116-6-R01 | 53510112 | Access | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Widening road from A044-A043. From 4m to 6m. Labourers installing culverts and cleaning tracks. |  |  | A044-A043 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54520191116-6-R01Labourer - General11715 | Corbiere and Sons Contracting54520191116-6-R01Labourer - General11715Inv#005-R01 | [5 empty] | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 545 | 20191116-6-R01 | 53510112 | Access | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Widening road from A044-A043. From 4m to 6m. Labourers installing culverts and cleaning tracks. |  |  | A044-A043 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54520191116-6-R01Labourer - General11715 | Corbiere and Sons Contracting54520191116-6-R01Labourer - General11715Inv#005-R01 | [5 empty] | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 545 | 20191116-6-R01 | 53510112 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Widening road from A044-A043. From 4m to 6m. Labourers installing culverts and cleaning tracks. |  |  | A044-A043 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54520191116-6-R01L.O.A.4840 | Corbiere and Sons Contracting54520191116-6-R01L.O.A.4840Inv#005-R01 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 546 | 20191116-7-R01 | 53510112 | Access | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Grading road and widening at A053 |  |  | A053 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54620191116-7-R01Dozer D6 or equal91215 | Corbiere and Sons Contracting54620191116-7-R01Dozer D6 or equal91215Inv#005-R01 | [5 empty] | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 546 | 20191116-7-R01 | 53510112 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Grading road and widening at A053 |  |  | A053 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54620191116-7-R01Operator - Principle11990 | Corbiere and Sons Contracting54620191116-7-R01Operator - Principle11990Inv#005-R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 546 | 20191116-7-R01 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Grading road and widening at A053 |  |  | A053 | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54620191116-7-R01L.O.A.1210 | Corbiere and Sons Contracting54620191116-7-R01L.O.A.1210Inv#005-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 548 | 20191117-01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-18 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting54820191117-01Light Truck - Pick up501500 | Corbiere and Sons Contracting54820191117-01Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 548 | 20191117-01 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-18 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting54820191117-01Project Manager121320 | Corbiere and Sons Contracting54820191117-01Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 548 | 20191117-01 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-18 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting54820191117-01Superintendent121260 | Corbiere and Sons Contracting54820191117-01Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 548 | 20191117-01 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-18 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting54820191117-01Project Coordinator12960 | Corbiere and Sons Contracting54820191117-01Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 548 | 20191117-01 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-18 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting54820191117-01Safety Advisor121020 | Corbiere and Sons Contracting54820191117-01Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 548 | 20191117-01 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-18 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting54820191117-01Project Controls12840 | Corbiere and Sons Contracting54820191117-01Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 548 | 20191117-01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-18 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting54820191117-01L.O.A.51050 | Corbiere and Sons Contracting54820191117-01L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 549 | 20191117-02-R01 | 53520101 | Clearing | 0 | Grader - Cat 12 to 14 or equal | 126 |  | HR | 94.5 | 9.5 |  |  | 897.75 | 116.7075 | 1014.4575 | 2019-11-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance-Float moves,-grader and sander truck on SB-Roman Roy orientation and then welding. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54920191117-02-R01Grader - Cat 12 to 14 or equal897.75 | Corbiere and Sons Contracting54920191117-02-R01Grader - Cat 12 to 14 or equal897.75Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 897.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 549 | 20191117-02-R01 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-11-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance-Float moves,-grader and sander truck on SB-Roman Roy orientation and then welding. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54920191117-02-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting54920191117-02-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 549 | 20191117-02-R01 | 53520101 | Clearing | 0 | Sander Truck | 112.5 |  | HR | 84.38 | 9.5 |  |  | 801.61 | 104.2093 | 905.8193 | 2019-11-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance-Float moves,-grader and sander truck on SB-Roman Roy orientation and then welding. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54920191117-02-R01Sander Truck801.61 | Corbiere and Sons Contracting54920191117-02-R01Sander Truck801.61Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 801.61 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 549 | 20191117-02-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance-Float moves,-grader and sander truck on SB-Roman Roy orientation and then welding. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54920191117-02-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting54920191117-02-R01Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 549 | 20191117-02-R01 | 53520101 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance-Float moves,-grader and sander truck on SB-Roman Roy orientation and then welding. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54920191117-02-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting54920191117-02-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 549 | 20191117-02-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-11-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance-Float moves,-grader and sander truck on SB-Roman Roy orientation and then welding. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54920191117-02-R01Operator - Principle121080 | Corbiere and Sons Contracting54920191117-02-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 549 | 20191117-02-R01 | 53520101 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance-Float moves,-grader and sander truck on SB-Roman Roy orientation and then welding. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54920191117-02-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting54920191117-02-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 549 | 20191117-02-R01 | 53520101 | Clearing | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-11-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance-Float moves,-grader and sander truck on SB-Roman Roy orientation and then welding. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54920191117-02-R01Labourer - Specialized11825 | Corbiere and Sons Contracting54920191117-02-R01Labourer - Specialized11825Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 549 | 20191117-02-R01 | 53520101 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-11-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance-Float moves,-grader and sander truck on SB-Roman Roy orientation and then welding. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54920191117-02-R01Labourer - General10650 | Corbiere and Sons Contracting54920191117-02-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 549 | 20191117-02-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | General yard and equipment maintenance-Float moves,-grader and sander truck on SB-Roman Roy orientation and then welding. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting54920191117-02-R01L.O.A.3630 | Corbiere and Sons Contracting54920191117-02-R01L.O.A.3630Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 551 | 20191117-04 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 1 | Day |  | 0 |  |  | 120 | 15.6 | 135.6 | 2019-11-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finish hand felling at A018; Saw hands left at 3pm |  |  |  | 0 |  |  | 8 | 43791 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting55120191117-04Chainsaw and consummables1120 | Corbiere and Sons Contracting55120191117-04Chainsaw and consummables1120Inv#002-R01 |  |  | WF1-Handfalling |  |  | 1 | 120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 551 | 20191117-04 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finish hand felling at A018; Saw hands left at 3pm |  |  |  | 0 |  |  | 8 | 43791 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting55120191117-04Light Truck - Pick up10300 | Corbiere and Sons Contracting55120191117-04Light Truck - Pick up10300Inv#002-R01 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 551 | 20191117-04 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 9 | HR |  |  |  | 0 | 675 | 87.75 | 762.75 | 2019-11-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finish hand felling at A018; Saw hands left at 3pm |  |  |  | 0 |  |  | 8 | 43791 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting55120191117-04Labourer - Specialized9675 | Corbiere and Sons Contracting55120191117-04Labourer - Specialized9675Inv#002-R01 |  |  | WF1-Handfalling |  |  | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 551 | 20191117-04 | 53520104 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-17 | 1 | Inv#002-R01 | 43770 | 81 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finish hand felling at A018; Saw hands left at 3pm |  |  |  | 0 |  |  | 8 | 43791 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting55120191117-04L.O.A.1210 | Corbiere and Sons Contracting55120191117-04L.O.A.1210Inv#002-R01 |  |  | WF1-Handfalling |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 552 | 20191117-05-R03 | 53520101 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-11-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand felling between A032 and A034; Raking, Brushing, Hauling out logs to road for land owner; Labourers, Fueling, Flagging, cleaning tracks; Equipment being floated to Beck Rd.; Hand Fellers finished at 3pm; BR004 down for part of day |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55220191117-05-R03Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting55220191117-05-R03Grinder - 4710 Peterson or equal1810022.4Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 552 | 20191117-05-R03 | 53520101 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-11-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand felling between A032 and A034; Raking, Brushing, Hauling out logs to road for land owner; Labourers, Fueling, Flagging, cleaning tracks; Equipment being floated to Beck Rd.; Hand Fellers finished at 3pm; BR004 down for part of day |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55220191117-05-R03Log Loader182754 | Corbiere and Sons Contracting55220191117-05-R03Log Loader182754Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 552 | 20191117-05-R03 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 3 | Day |  | 0 |  |  | 360 | 46.8 | 406.8 | 2019-11-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand felling between A032 and A034; Raking, Brushing, Hauling out logs to road for land owner; Labourers, Fueling, Flagging, cleaning tracks; Equipment being floated to Beck Rd.; Hand Fellers finished at 3pm; BR004 down for part of day |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55220191117-05-R03Chainsaw and consummables3360 | Corbiere and Sons Contracting55220191117-05-R03Chainsaw and consummables3360Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 552 | 20191117-05-R03 | 53520101 | Clearing | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2019-11-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand felling between A032 and A034; Raking, Brushing, Hauling out logs to road for land owner; Labourers, Fueling, Flagging, cleaning tracks; Equipment being floated to Beck Rd.; Hand Fellers finished at 3pm; BR004 down for part of day |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55220191117-05-R03Excavator - 30 ton91255.5 | Corbiere and Sons Contracting55220191117-05-R03Excavator - 30 ton91255.5Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 552 | 20191117-05-R03 | 53520101 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand felling between A032 and A034; Raking, Brushing, Hauling out logs to road for land owner; Labourers, Fueling, Flagging, cleaning tracks; Equipment being floated to Beck Rd.; Hand Fellers finished at 3pm; BR004 down for part of day |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55220191117-05-R03Excavator - 36 ton91539 | Corbiere and Sons Contracting55220191117-05-R03Excavator - 36 ton91539Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 552 | 20191117-05-R03 | 53520101 | Clearing | 0 | ATV - Side by Side w/ roll bar | 22.5 | 9 | HR | 16.88 | 0 |  |  | 202.5 | 26.325 | 228.825 | 2019-11-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand felling between A032 and A034; Raking, Brushing, Hauling out logs to road for land owner; Labourers, Fueling, Flagging, cleaning tracks; Equipment being floated to Beck Rd.; Hand Fellers finished at 3pm; BR004 down for part of day |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55220191117-05-R03ATV - Side by Side w/ roll bar9202.5 | Corbiere and Sons Contracting55220191117-05-R03ATV - Side by Side w/ roll bar9202.5Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 202.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 552 | 20191117-05-R03 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 80 | HR | 22.5 | 0 |  |  | 2400 | 312 | 2712 | 2019-11-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand felling between A032 and A034; Raking, Brushing, Hauling out logs to road for land owner; Labourers, Fueling, Flagging, cleaning tracks; Equipment being floated to Beck Rd.; Hand Fellers finished at 3pm; BR004 down for part of day |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55220191117-05-R03Light Truck - Pick up802400 | Corbiere and Sons Contracting55220191117-05-R03Light Truck - Pick up802400Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 552 | 20191117-05-R03 | 53520101 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand felling between A032 and A034; Raking, Brushing, Hauling out logs to road for land owner; Labourers, Fueling, Flagging, cleaning tracks; Equipment being floated to Beck Rd.; Hand Fellers finished at 3pm; BR004 down for part of day |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55220191117-05-R03Foreman121140 | Corbiere and Sons Contracting55220191117-05-R03Foreman121140Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 552 | 20191117-05-R03 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 77 | HR |  |  |  | 0 | 6930 | 900.9 | 7830.9 | 2019-11-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand felling between A032 and A034; Raking, Brushing, Hauling out logs to road for land owner; Labourers, Fueling, Flagging, cleaning tracks; Equipment being floated to Beck Rd.; Hand Fellers finished at 3pm; BR004 down for part of day |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55220191117-05-R03Operator - Principle776930 | Corbiere and Sons Contracting55220191117-05-R03Operator - Principle776930Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 6930 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 552 | 20191117-05-R03 | 53520101 | Clearing | 0 | Labourer - Specialized | 75 | 27 | HR |  |  |  | 0 | 2025 | 263.25 | 2288.25 | 2019-11-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand felling between A032 and A034; Raking, Brushing, Hauling out logs to road for land owner; Labourers, Fueling, Flagging, cleaning tracks; Equipment being floated to Beck Rd.; Hand Fellers finished at 3pm; BR004 down for part of day |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55220191117-05-R03Labourer - Specialized272025 | Corbiere and Sons Contracting55220191117-05-R03Labourer - Specialized272025Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2025 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 552 | 20191117-05-R03 | 53520101 | Clearing | 0 | Labourer - General | 65 | 55 | HR |  |  |  | 0 | 3575 | 464.75 | 4039.75 | 2019-11-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand felling between A032 and A034; Raking, Brushing, Hauling out logs to road for land owner; Labourers, Fueling, Flagging, cleaning tracks; Equipment being floated to Beck Rd.; Hand Fellers finished at 3pm; BR004 down for part of day |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55220191117-05-R03Labourer - General553575 | Corbiere and Sons Contracting55220191117-05-R03Labourer - General553575Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 552 | 20191117-05-R03 | 53520101 | Clearing | 0 | L.O.A. | 210 | 13 | DAY |  |  |  | 0 | 2730 | 354.9 | 3084.9 | 2019-11-17 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand felling between A032 and A034; Raking, Brushing, Hauling out logs to road for land owner; Labourers, Fueling, Flagging, cleaning tracks; Equipment being floated to Beck Rd.; Hand Fellers finished at 3pm; BR004 down for part of day |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55220191117-05-R03L.O.A.132730 | Corbiere and Sons Contracting55220191117-05-R03L.O.A.132730Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2730 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 553 | 20191117-06-R01 | 53520102 | Clearing | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2019-11-17 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking on ROW from A045 to A042 |  |  | Beck West | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting55320191117-06-R01Excavator - 30 ton91255.5 | Corbiere and Sons Contracting55320191117-06-R01Excavator - 30 ton91255.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 553 | 20191117-06-R01 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-17 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking on ROW from A045 to A042 |  |  | Beck West | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting55320191117-06-R01Excavator - 36 ton91539 | Corbiere and Sons Contracting55320191117-06-R01Excavator - 36 ton91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 553 | 20191117-06-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-17 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking on ROW from A045 to A042 |  |  | Beck West | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting55320191117-06-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting55320191117-06-R01Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 553 | 20191117-06-R01 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-17 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking on ROW from A045 to A042 |  |  | Beck West | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting55320191117-06-R01Foreman121140 | Corbiere and Sons Contracting55320191117-06-R01Foreman121140Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 553 | 20191117-06-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-17 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking on ROW from A045 to A042 |  |  | Beck West | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting55320191117-06-R01Operator - Principle221980 | Corbiere and Sons Contracting55320191117-06-R01Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 553 | 20191117-06-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-17 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking on ROW from A045 to A042 |  |  | Beck West | 0 |  |  | 34 | 43813 | [5 empty] | Tim Taggart | 01 | Corbiere and Sons Contracting55320191117-06-R01L.O.A.3630 | Corbiere and Sons Contracting55320191117-06-R01L.O.A.3630Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 556 | 20191118-01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-18 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting55620191118-01Light Truck - Pick up501500 | Corbiere and Sons Contracting55620191118-01Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 556 | 20191118-01 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-18 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting55620191118-01Project Manager121320 | Corbiere and Sons Contracting55620191118-01Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 556 | 20191118-01 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-18 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting55620191118-01Superintendent121260 | Corbiere and Sons Contracting55620191118-01Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 556 | 20191118-01 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-18 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting55620191118-01Project Coordinator12960 | Corbiere and Sons Contracting55620191118-01Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 556 | 20191118-01 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-18 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting55620191118-01Safety Advisor121020 | Corbiere and Sons Contracting55620191118-01Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 556 | 20191118-01 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-18 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting55620191118-01Project Controls12840 | Corbiere and Sons Contracting55620191118-01Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 556 | 20191118-01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  |  | 1050 | 136.5 | 1186.5 | 2019-11-18 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting55620191118-01L.O.A.51050 | Corbiere and Sons Contracting55620191118-01L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 558 | 20191118-03-R02 | 53520101 | Clearing | 0 | Feller Buncher | 240 |  | HR | 180 | 45 |  |  | 8100 | 1053 | 9153 | 2019-11-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits. | 1 |  |  | 1 | 43863 | Missing Permit | 35 | 43863 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55820191118-03-R02Feller Buncher8100 | Corbiere and Sons Contracting55820191118-03-R02Feller Buncher8100Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 8100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 558 | 20191118-03-R02 | 53520101 | Clearing | 0 | Skidder | 171 |  | HR | 128.25 | 36 |  |  | 4617 | 600.21 | 5217.21 | 2019-11-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits. | 1 |  |  | 1 | 43863 | Missing Permit | 35 | 43863 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55820191118-03-R02Skidder 4617 | Corbiere and Sons Contracting55820191118-03-R02Skidder 4617Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 558 | 20191118-03-R02 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 |  | HR | 22.5 | 50 |  |  | 1125 | 146.25 | 1271.25 | 2019-11-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits. | 1 |  |  | 1 | 43863 | Missing Permit | 35 | 43863 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55820191118-03-R02Light Truck - Pick up1125 | Corbiere and Sons Contracting55820191118-03-R02Light Truck - Pick up1125Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 558 | 20191118-03-R02 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 20 | HR |  |  |  | 0 | 1800 | 234 | 2034 | 2019-11-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits. | 1 |  |  | 1 | 43863 | Missing Permit | 35 | 43863 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55820191118-03-R02Operator - Principle201800 | Corbiere and Sons Contracting55820191118-03-R02Operator - Principle201800Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 558 | 20191118-03-R02 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits. | 1 |  |  | 1 | 43863 | Missing Permit | 35 | 43863 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55820191118-03-R02L.O.A.51050 | Corbiere and Sons Contracting55820191118-03-R02L.O.A.51050Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 559 | 20191118-04-R01 | 53520101 | Clearing | 0 | Mulcher | 205 | 4 | HR | 153.75 | 5 |  |  | 1588.75 | 206.5375 | 1795.2875 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand Felling at MacKenzie River and unmarked wetlands, A035; Spreading chips at A030; Hauling spruce logs; Labourers fueling, flagging, spotting, cleaning tracks; Mulcher on SB for afternoon; |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55920191118-04-R01Mulcher41588.75 | Corbiere and Sons Contracting55920191118-04-R01Mulcher41588.75Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1588.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 559 | 20191118-04-R01 | 53520101 | Clearing | 0 | Chainsaw and consummables | 120 | 4 | Day |  | 0 |  |  | 480 | 62.4 | 542.4 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand Felling at MacKenzie River and unmarked wetlands, A035; Spreading chips at A030; Hauling spruce logs; Labourers fueling, flagging, spotting, cleaning tracks; Mulcher on SB for afternoon; |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55920191118-04-R01Chainsaw and consummables4480 | Corbiere and Sons Contracting55920191118-04-R01Chainsaw and consummables4480Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 559 | 20191118-04-R01 | 53520101 | Clearing | 0 | Excavator - 20 ton | 130.5 | 9 | HR | 97.88 | 0 |  |  | 1174.5 | 152.685 | 1327.185 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand Felling at MacKenzie River and unmarked wetlands, A035; Spreading chips at A030; Hauling spruce logs; Labourers fueling, flagging, spotting, cleaning tracks; Mulcher on SB for afternoon; |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55920191118-04-R01Excavator - 20 ton91174.5 | Corbiere and Sons Contracting55920191118-04-R01Excavator - 20 ton91174.5Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1174.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 559 | 20191118-04-R01 | 53520101 | Clearing | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand Felling at MacKenzie River and unmarked wetlands, A035; Spreading chips at A030; Hauling spruce logs; Labourers fueling, flagging, spotting, cleaning tracks; Mulcher on SB for afternoon; |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55920191118-04-R01Excavator - 30 ton91255.5 | Corbiere and Sons Contracting55920191118-04-R01Excavator - 30 ton91255.5Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 559 | 20191118-04-R01 | 53520101 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand Felling at MacKenzie River and unmarked wetlands, A035; Spreading chips at A030; Hauling spruce logs; Labourers fueling, flagging, spotting, cleaning tracks; Mulcher on SB for afternoon; |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55920191118-04-R01Excavator - 36 ton91539 | Corbiere and Sons Contracting55920191118-04-R01Excavator - 36 ton91539Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 559 | 20191118-04-R01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 70 | HR | 22.5 | 0 |  |  | 2100 | 273 | 2373 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand Felling at MacKenzie River and unmarked wetlands, A035; Spreading chips at A030; Hauling spruce logs; Labourers fueling, flagging, spotting, cleaning tracks; Mulcher on SB for afternoon; |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55920191118-04-R01Light Truck - Pick up702100 | Corbiere and Sons Contracting55920191118-04-R01Light Truck - Pick up702100Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 559 | 20191118-04-R01 | 53520101 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand Felling at MacKenzie River and unmarked wetlands, A035; Spreading chips at A030; Hauling spruce logs; Labourers fueling, flagging, spotting, cleaning tracks; Mulcher on SB for afternoon; |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55920191118-04-R01Foreman121140 | Corbiere and Sons Contracting55920191118-04-R01Foreman121140Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 559 | 20191118-04-R01 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 38 | HR |  |  |  | 0 | 3420 | 444.6 | 3864.6 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand Felling at MacKenzie River and unmarked wetlands, A035; Spreading chips at A030; Hauling spruce logs; Labourers fueling, flagging, spotting, cleaning tracks; Mulcher on SB for afternoon; |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55920191118-04-R01Operator - Principle383420 | Corbiere and Sons Contracting55920191118-04-R01Operator - Principle383420Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 559 | 20191118-04-R01 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 44 | HR |  |  |  | 0 | 3300 | 429 | 3729 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand Felling at MacKenzie River and unmarked wetlands, A035; Spreading chips at A030; Hauling spruce logs; Labourers fueling, flagging, spotting, cleaning tracks; Mulcher on SB for afternoon; |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55920191118-04-R01Labourer - Specialized443300 | Corbiere and Sons Contracting55920191118-04-R01Labourer - Specialized443300Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 3300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 559 | 20191118-04-R01 | 53520101 | Clearing | 0 | Labourer - General | 65 | 66 | HR |  |  |  | 0 | 4290 | 557.7 | 4847.7 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand Felling at MacKenzie River and unmarked wetlands, A035; Spreading chips at A030; Hauling spruce logs; Labourers fueling, flagging, spotting, cleaning tracks; Mulcher on SB for afternoon; |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55920191118-04-R01Labourer - General664290 | Corbiere and Sons Contracting55920191118-04-R01Labourer - General664290Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4290 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 559 | 20191118-04-R01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 11 | DAY |  |  |  | 0 | 2310 | 300.3 | 2610.3 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Hand Felling at MacKenzie River and unmarked wetlands, A035; Spreading chips at A030; Hauling spruce logs; Labourers fueling, flagging, spotting, cleaning tracks; Mulcher on SB for afternoon; |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting55920191118-04-R01L.O.A.112310 | Corbiere and Sons Contracting55920191118-04-R01L.O.A.112310Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 560 | 20191118-05-R01 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and Brushing on ROW from A045 to A042; Labourers, flagging, fueling, spotting, cleaning tracks; Grinding at A045 and A046 |  |  | Beck West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56020191118-05-R01Brusher91822.5 | Corbiere and Sons Contracting56020191118-05-R01Brusher91822.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 560 | 20191118-05-R01 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and Brushing on ROW from A045 to A042; Labourers, flagging, fueling, spotting, cleaning tracks; Grinding at A045 and A046 |  |  | Beck West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56020191118-05-R01Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting56020191118-05-R01Grinder - 4710 Peterson or equal1810022.4Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 560 | 20191118-05-R01 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and Brushing on ROW from A045 to A042; Labourers, flagging, fueling, spotting, cleaning tracks; Grinding at A045 and A046 |  |  | Beck West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56020191118-05-R01Log Loader182754 | Corbiere and Sons Contracting56020191118-05-R01Log Loader182754Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 560 | 20191118-05-R01 | 53520102 | Clearing | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and Brushing on ROW from A045 to A042; Labourers, flagging, fueling, spotting, cleaning tracks; Grinding at A045 and A046 |  |  | Beck West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56020191118-05-R01Excavator - 30 ton91255.5 | Corbiere and Sons Contracting56020191118-05-R01Excavator - 30 ton91255.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 560 | 20191118-05-R01 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 27 | HR | 128.25 | 0 |  |  | 4617 | 600.21 | 5217.21 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and Brushing on ROW from A045 to A042; Labourers, flagging, fueling, spotting, cleaning tracks; Grinding at A045 and A046 |  |  | Beck West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56020191118-05-R01Excavator - 36 ton274617 | Corbiere and Sons Contracting56020191118-05-R01Excavator - 36 ton274617Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 560 | 20191118-05-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and Brushing on ROW from A045 to A042; Labourers, flagging, fueling, spotting, cleaning tracks; Grinding at A045 and A046 |  |  | Beck West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56020191118-05-R01Light Truck - Pick up501500 | Corbiere and Sons Contracting56020191118-05-R01Light Truck - Pick up501500Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 560 | 20191118-05-R01 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and Brushing on ROW from A045 to A042; Labourers, flagging, fueling, spotting, cleaning tracks; Grinding at A045 and A046 |  |  | Beck West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56020191118-05-R01Foreman121140 | Corbiere and Sons Contracting56020191118-05-R01Foreman121140Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 560 | 20191118-05-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 77 | HR |  |  |  | 0 | 6930 | 900.9 | 7830.9 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and Brushing on ROW from A045 to A042; Labourers, flagging, fueling, spotting, cleaning tracks; Grinding at A045 and A046 |  |  | Beck West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56020191118-05-R01Operator - Principle776930 | Corbiere and Sons Contracting56020191118-05-R01Operator - Principle776930Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 6930 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 560 | 20191118-05-R01 | 53520102 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and Brushing on ROW from A045 to A042; Labourers, flagging, fueling, spotting, cleaning tracks; Grinding at A045 and A046 |  |  | Beck West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56020191118-05-R01Labourer - General11715 | Corbiere and Sons Contracting56020191118-05-R01Labourer - General11715Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 560 | 20191118-05-R01 | 53520102 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and Brushing on ROW from A045 to A042; Labourers, flagging, fueling, spotting, cleaning tracks; Grinding at A045 and A046 |  |  | Beck West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56020191118-05-R01Labourer - General11715 | Corbiere and Sons Contracting56020191118-05-R01Labourer - General11715Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 560 | 20191118-05-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Raking and Brushing on ROW from A045 to A042; Labourers, flagging, fueling, spotting, cleaning tracks; Grinding at A045 and A046 |  |  | Beck West | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56020191118-05-R01L.O.A.91890 | Corbiere and Sons Contracting56020191118-05-R01L.O.A.91890Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 562 | 20191118-07-R01 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Grader floated to Elderado and then began work |  |  | Eldorado | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56220191118-07-R01Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting56220191118-07-R01Grader - Cat 12 to 14 or equal91134Inv#005-R01 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 562 | 20191118-07-R01 | 53510112 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Grader floated to Elderado and then began work |  |  | Eldorado | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56220191118-07-R01Operator - Principle11990 | Corbiere and Sons Contracting56220191118-07-R01Operator - Principle11990Inv#005-R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 562 | 20191118-07-R01 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-18 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | All Season Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Grader floated to Elderado and then began work |  |  | Eldorado | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56220191118-07-R01L.O.A.1210 | Corbiere and Sons Contracting56220191118-07-R01L.O.A.1210Inv#005-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 563 | 20191119-01 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-19 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting56320191119-01Light Truck - Pick up501500 | Corbiere and Sons Contracting56320191119-01Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 563 | 20191119-01 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-19 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting56320191119-01Project Manager121320 | Corbiere and Sons Contracting56320191119-01Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 563 | 20191119-01 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-19 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting56320191119-01Superintendent121260 | Corbiere and Sons Contracting56320191119-01Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 563 | 20191119-01 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-19 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting56320191119-01Project Coordinator12960 | Corbiere and Sons Contracting56320191119-01Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 563 | 20191119-01 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-19 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting56320191119-01Safety Advisor121020 | Corbiere and Sons Contracting56320191119-01Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 563 | 20191119-01 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-19 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting56320191119-01Project Controls12840 | Corbiere and Sons Contracting56320191119-01Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 563 | 20191119-01 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-19 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting56320191119-01L.O.A.51050 | Corbiere and Sons Contracting56320191119-01L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 564 | 20191119-02-R01 | 53520105 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | Activity-Warehouse-General yard and equipmnet maintenance- Float moves-Sander on SB- Roman Roy Welding. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56420191119-02-R01Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting56420191119-02-R01Loader JD 524 to 624 or equal9891Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 564 | 20191119-02-R01 | 53520105 | Clearing | 0 | Sander Truck | 112.5 |  | HR | 84.38 | 9.5 |  |  | 801.61 | 104.2093 | 905.8193 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | Activity-Warehouse-General yard and equipmnet maintenance- Float moves-Sander on SB- Roman Roy Welding. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56420191119-02-R01Sander Truck801.61 | Corbiere and Sons Contracting56420191119-02-R01Sander Truck801.61Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 801.61 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 564 | 20191119-02-R01 | 53520105 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | Activity-Warehouse-General yard and equipmnet maintenance- Float moves-Sander on SB- Roman Roy Welding. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56420191119-02-R01Light Truck - Pick up10300 | Corbiere and Sons Contracting56420191119-02-R01Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 564 | 20191119-02-R01 | 53520105 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | Activity-Warehouse-General yard and equipmnet maintenance- Float moves-Sander on SB- Roman Roy Welding. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56420191119-02-R01Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting56420191119-02-R01Tractor Trailer - 60 Ton101350Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 564 | 20191119-02-R01 | 53520105 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | Activity-Warehouse-General yard and equipmnet maintenance- Float moves-Sander on SB- Roman Roy Welding. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56420191119-02-R01Operator - Principle121080 | Corbiere and Sons Contracting56420191119-02-R01Operator - Principle121080Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 564 | 20191119-02-R01 | 53520105 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | Activity-Warehouse-General yard and equipmnet maintenance- Float moves-Sander on SB- Roman Roy Welding. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56420191119-02-R01Operator - Intermdiate11825 | Corbiere and Sons Contracting56420191119-02-R01Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 564 | 20191119-02-R01 | 53520105 | Clearing | 0 | Labourer - Specialized | 75 | 13 | HR |  |  |  | 0 | 975 | 126.75 | 1101.75 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | Activity-Warehouse-General yard and equipmnet maintenance- Float moves-Sander on SB- Roman Roy Welding. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56420191119-02-R01Labourer - Specialized13975 | Corbiere and Sons Contracting56420191119-02-R01Labourer - Specialized13975Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 564 | 20191119-02-R01 | 53520105 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | Activity-Warehouse-General yard and equipmnet maintenance- Float moves-Sander on SB- Roman Roy Welding. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56420191119-02-R01Labourer - General10650 | Corbiere and Sons Contracting56420191119-02-R01Labourer - General10650Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 564 | 20191119-02-R01 | 53520105 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Camp Prep Costs |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and approved Jan 8, 2020 - RR |  |  |  |  | Activity-Warehouse-General yard and equipmnet maintenance- Float moves-Sander on SB- Roman Roy Welding. |  |  |  | 0 |  |  | 35 | 43838 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56420191119-02-R01L.O.A.3630 | Corbiere and Sons Contracting56420191119-02-R01L.O.A.3630Inv#005-R01 |  |  | WF1-Indirects |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 565 | 20191119-03-R2 | 53520101 | Clearing | 0 | Feller Buncher | 240 |  | HR | 180 | 45 |  |  | 8100 | 1053 | 9153 | 2019-11-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits. | 1 |  |  | 1 | 43863 | Missing Permit | 35 | 43863 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56520191119-03-R2Feller Buncher8100 | Corbiere and Sons Contracting56520191119-03-R2Feller Buncher8100Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 8100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 565 | 20191119-03-R2 | 53520101 | Clearing | 0 | Skidder | 171 |  | HR | 128.25 | 36 |  |  | 4617 | 600.21 | 5217.21 | 2019-11-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits. | 1 |  |  | 1 | 43863 | Missing Permit | 35 | 43863 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56520191119-03-R2Skidder 4617 | Corbiere and Sons Contracting56520191119-03-R2Skidder 4617Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 565 | 20191119-03-R2 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 |  | HR | 22.5 | 50 |  |  | 1125 | 146.25 | 1271.25 | 2019-11-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits. | 1 |  |  | 1 | 43863 | Missing Permit | 35 | 43863 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56520191119-03-R2Light Truck - Pick up1125 | Corbiere and Sons Contracting56520191119-03-R2Light Truck - Pick up1125Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 565 | 20191119-03-R2 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 20 | HR |  |  |  | 0 | 1800 | 234 | 2034 | 2019-11-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits. | 1 |  |  | 1 | 43863 | Missing Permit | 35 | 43863 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56520191119-03-R2Operator - Principle201800 | Corbiere and Sons Contracting56520191119-03-R2Operator - Principle201800Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 565 | 20191119-03-R2 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 11 | Approved | ROW INTERNAL - STANDBY MISSING PERMITS SEPT 23 - NOV 21, 2019 | 9011 | On Standby due to missing permits. | 1 |  |  | 1 | 43863 | Missing Permit | 35 | 43863 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56520191119-03-R2L.O.A.51050 | Corbiere and Sons Contracting56520191119-03-R2L.O.A.51050Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 566 | 20191119-04-R01 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Labourers: Fueled, Flagged, moved fuel tank, cleaned garbage on ROW at all structures from A010 to A035; Raking, Mulching and Brushing from A030 to A035 |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56620191119-04-R01Brusher91822.5 | Corbiere and Sons Contracting56620191119-04-R01Brusher91822.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 566 | 20191119-04-R01 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Labourers: Fueled, Flagged, moved fuel tank, cleaned garbage on ROW at all structures from A010 to A035; Raking, Mulching and Brushing from A030 to A035 |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56620191119-04-R01Mulcher91845 | Corbiere and Sons Contracting56620191119-04-R01Mulcher91845Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 566 | 20191119-04-R01 | 53520102 | Clearing | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Labourers: Fueled, Flagged, moved fuel tank, cleaned garbage on ROW at all structures from A010 to A035; Raking, Mulching and Brushing from A030 to A035 |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56620191119-04-R01Excavator - 30 ton91255.5 | Corbiere and Sons Contracting56620191119-04-R01Excavator - 30 ton91255.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 566 | 20191119-04-R01 | 53520102 | Clearing | 0 | Grader - Cat 12 to 14 or equal | 126 | 8 | HR | 94.5 | 0 |  |  | 1008 | 131.04 | 1139.04 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Labourers: Fueled, Flagged, moved fuel tank, cleaned garbage on ROW at all structures from A010 to A035; Raking, Mulching and Brushing from A030 to A035 |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56620191119-04-R01Grader - Cat 12 to 14 or equal81008 | Corbiere and Sons Contracting56620191119-04-R01Grader - Cat 12 to 14 or equal81008Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1008 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 566 | 20191119-04-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Labourers: Fueled, Flagged, moved fuel tank, cleaned garbage on ROW at all structures from A010 to A035; Raking, Mulching and Brushing from A030 to A035 |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56620191119-04-R01Light Truck - Pick up401200 | Corbiere and Sons Contracting56620191119-04-R01Light Truck - Pick up401200Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 566 | 20191119-04-R01 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Labourers: Fueled, Flagged, moved fuel tank, cleaned garbage on ROW at all structures from A010 to A035; Raking, Mulching and Brushing from A030 to A035 |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56620191119-04-R01Foreman121140 | Corbiere and Sons Contracting56620191119-04-R01Foreman121140Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 566 | 20191119-04-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Labourers: Fueled, Flagged, moved fuel tank, cleaned garbage on ROW at all structures from A010 to A035; Raking, Mulching and Brushing from A030 to A035 |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56620191119-04-R01Operator - Principle443960 | Corbiere and Sons Contracting56620191119-04-R01Operator - Principle443960Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 566 | 20191119-04-R01 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Labourers: Fueled, Flagged, moved fuel tank, cleaned garbage on ROW at all structures from A010 to A035; Raking, Mulching and Brushing from A030 to A035 |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56620191119-04-R01Labourer - Specialized11825 | Corbiere and Sons Contracting56620191119-04-R01Labourer - Specialized11825Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 566 | 20191119-04-R01 | 53520102 | Clearing | 0 | Labourer - General | 65 | 55 | HR |  |  |  | 0 | 3575 | 464.75 | 4039.75 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Labourers: Fueled, Flagged, moved fuel tank, cleaned garbage on ROW at all structures from A010 to A035; Raking, Mulching and Brushing from A030 to A035 |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56620191119-04-R01Labourer - General553575 | Corbiere and Sons Contracting56620191119-04-R01Labourer - General553575Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 566 | 20191119-04-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Labourers: Fueled, Flagged, moved fuel tank, cleaned garbage on ROW at all structures from A010 to A035; Raking, Mulching and Brushing from A030 to A035 |  |  | MacKenzie East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56620191119-04-R01L.O.A.91890 | Corbiere and Sons Contracting56620191119-04-R01L.O.A.91890Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 567 | 20191119-05 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 19 | HR | 417.6 | 0 |  |  | 10579.2 | 1375.296 | 11954.496 | 2019-11-19 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material A044 and A045 |  |  | Beck West | 0 | [10 empty] | 01 | Corbiere and Sons Contracting56720191119-05Grinder - 4710 Peterson or equal1910579.2 | Corbiere and Sons Contracting56720191119-05Grinder - 4710 Peterson or equal1910579.2Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10579.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 567 | 20191119-05 | 53520102 | Clearing | 0 | Log Loader | 153 | 19 | HR | 114.75 | 0 |  |  | 2907 | 377.91 | 3284.91 | 2019-11-19 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material A044 and A045 |  |  | Beck West | 0 | [10 empty] | 01 | Corbiere and Sons Contracting56720191119-05Log Loader192907 | Corbiere and Sons Contracting56720191119-05Log Loader192907Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2907 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 567 | 20191119-05 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-19 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material A044 and A045 |  |  | Beck West | 0 | [10 empty] | 01 | Corbiere and Sons Contracting56720191119-05Light Truck - Pick up20600 | Corbiere and Sons Contracting56720191119-05Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 567 | 20191119-05 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-19 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material A044 and A045 |  |  | Beck West | 0 | [10 empty] | 01 | Corbiere and Sons Contracting56720191119-05Operator - Principle221980 | Corbiere and Sons Contracting56720191119-05Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 567 | 20191119-05 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-19 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material A044 and A045 |  |  | Beck West | 0 | [10 empty] | 01 | Corbiere and Sons Contracting56720191119-05L.O.A.2420 | Corbiere and Sons Contracting56720191119-05L.O.A.2420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 568 | 20191119-06-R01 | 53520102 | Clearing | 0 | Chainsaw and consummables | 120 | 4 | Day |  | 0 |  |  | 480 | 62.4 | 542.4 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Finished cutting whips and stumps to A049 and on both sides of River; Raking from A045 to A054 |  |  | Beck East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56820191119-06-R01Chainsaw and consummables4480 | Corbiere and Sons Contracting56820191119-06-R01Chainsaw and consummables4480Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 568 | 20191119-06-R01 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 9 | HR | 97.88 | 0 |  |  | 1174.5 | 152.685 | 1327.185 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Finished cutting whips and stumps to A049 and on both sides of River; Raking from A045 to A054 |  |  | Beck East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56820191119-06-R01Excavator - 20 ton91174.5 | Corbiere and Sons Contracting56820191119-06-R01Excavator - 20 ton91174.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1174.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 568 | 20191119-06-R01 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Finished cutting whips and stumps to A049 and on both sides of River; Raking from A045 to A054 |  |  | Beck East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56820191119-06-R01Excavator - 36 ton91539 | Corbiere and Sons Contracting56820191119-06-R01Excavator - 36 ton91539Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 568 | 20191119-06-R01 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Finished cutting whips and stumps to A049 and on both sides of River; Raking from A045 to A054 |  |  | Beck East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56820191119-06-R01Light Truck - Pick up401200 | Corbiere and Sons Contracting56820191119-06-R01Light Truck - Pick up401200Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 568 | 20191119-06-R01 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Finished cutting whips and stumps to A049 and on both sides of River; Raking from A045 to A054 |  |  | Beck East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56820191119-06-R01Operator - Principle221980 | Corbiere and Sons Contracting56820191119-06-R01Operator - Principle221980Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 568 | 20191119-06-R01 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 44 | HR |  |  |  | 0 | 3300 | 429 | 3729 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Finished cutting whips and stumps to A049 and on both sides of River; Raking from A045 to A054 |  |  | Beck East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56820191119-06-R01Labourer - Specialized443300 | Corbiere and Sons Contracting56820191119-06-R01Labourer - Specialized443300Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 568 | 20191119-06-R01 | 53520102 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Revised and Approved Jan 6, 2020 - RR |  |  |  |  | Finished cutting whips and stumps to A049 and on both sides of River; Raking from A045 to A054 |  |  | Beck East | 0 |  |  | 35 | 43836 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting56820191119-06-R01L.O.A.61260 | Corbiere and Sons Contracting56820191119-06-R01L.O.A.61260Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 570 | 20191120-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting57020191120-1Light Truck - Pick up501500 | Corbiere and Sons Contracting57020191120-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 570 | 20191120-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting57020191120-1Project Manager121320 | Corbiere and Sons Contracting57020191120-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 570 | 20191120-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting57020191120-1Superintendent121260 | Corbiere and Sons Contracting57020191120-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 570 | 20191120-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting57020191120-1Project Coordinator12960 | Corbiere and Sons Contracting57020191120-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 570 | 20191120-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting57020191120-1Safety Advisor121020 | Corbiere and Sons Contracting57020191120-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 570 | 20191120-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting57020191120-1Project Controls12840 | Corbiere and Sons Contracting57020191120-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 570 | 20191120-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Supervision |  |  |  | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting57020191120-1L.O.A.51050 | Corbiere and Sons Contracting57020191120-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 575 | 20191120-2-R3 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-11-24 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Yard care and maintenance of equipment; Wesley was float driver; Robert helped mechanics get downed equipment back up and running. |  |  | General yard maintenance and equipment repair | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting57520191120-2-R3Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting57520191120-2-R3Loader JD 524 to 624 or equal9891Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 575 | 20191120-2-R3 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-24 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Yard care and maintenance of equipment; Wesley was float driver; Robert helped mechanics get downed equipment back up and running. |  |  | General yard maintenance and equipment repair | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting57520191120-2-R3Light Truck - Pick up10300 | Corbiere and Sons Contracting57520191120-2-R3Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 575 | 20191120-2-R3 | 53520101 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-24 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Yard care and maintenance of equipment; Wesley was float driver; Robert helped mechanics get downed equipment back up and running. |  |  | General yard maintenance and equipment repair | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting57520191120-2-R3Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting57520191120-2-R3Tractor Trailer - 60 Ton101350Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 575 | 20191120-2-R3 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-11-24 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Yard care and maintenance of equipment; Wesley was float driver; Robert helped mechanics get downed equipment back up and running. |  |  | General yard maintenance and equipment repair | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting57520191120-2-R3Operator - Principle121080 | Corbiere and Sons Contracting57520191120-2-R3Operator - Principle121080Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 575 | 20191120-2-R3 | 53520101 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-24 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Yard care and maintenance of equipment; Wesley was float driver; Robert helped mechanics get downed equipment back up and running. |  |  | General yard maintenance and equipment repair | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting57520191120-2-R3Operator - Intermdiate11825 | Corbiere and Sons Contracting57520191120-2-R3Operator - Intermdiate11825Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 575 | 20191120-2-R3 | 53520101 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-11-24 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Yard care and maintenance of equipment; Wesley was float driver; Robert helped mechanics get downed equipment back up and running. |  |  | General yard maintenance and equipment repair | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting57520191120-2-R3Labourer - General10650 | Corbiere and Sons Contracting57520191120-2-R3Labourer - General10650Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 575 | 20191120-2-R3 | 53520101 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-11-24 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Yard care and maintenance of equipment; Wesley was float driver; Robert helped mechanics get downed equipment back up and running. |  |  | General yard maintenance and equipment repair | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting57520191120-2-R3Labourer - General11715 | Corbiere and Sons Contracting57520191120-2-R3Labourer - General11715Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 575 | 20191120-2-R3 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-24 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Yard care and maintenance of equipment; Wesley was float driver; Robert helped mechanics get downed equipment back up and running. |  |  | General yard maintenance and equipment repair | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting57520191120-2-R3L.O.A.3630 | Corbiere and Sons Contracting57520191120-2-R3L.O.A.3630Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 572 | 20191120-3-R1 | 53520101 | Clearing | 0 | Brusher | 202.5 | 3.5 | HR | 151.88 | 0 |  |  | 708.75 | 92.1375 | 800.8875 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling from A048 to A051; Cutting whips, stumps; Cutting trees in wetland, bucking into 7' Lengths; Raking, Ditching, Installing Culverts, Labourers Cleaning Tracks, picking up garbage |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57220191120-3-R1Brusher3.5708.75 | Corbiere and Sons Contracting57220191120-3-R1Brusher3.5708.75Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 708.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 572 | 20191120-3-R1 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling from A048 to A051; Cutting whips, stumps; Cutting trees in wetland, bucking into 7' Lengths; Raking, Ditching, Installing Culverts, Labourers Cleaning Tracks, picking up garbage |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57220191120-3-R1Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting57220191120-3-R1Grinder - 4710 Peterson or equal1810022.4Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 572 | 20191120-3-R1 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling from A048 to A051; Cutting whips, stumps; Cutting trees in wetland, bucking into 7' Lengths; Raking, Ditching, Installing Culverts, Labourers Cleaning Tracks, picking up garbage |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57220191120-3-R1Log Loader182754 | Corbiere and Sons Contracting57220191120-3-R1Log Loader182754Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 572 | 20191120-3-R1 | 53520102 | Clearing | 0 | Chainsaw and consummables | 120 | 3 | Day |  | 0 |  |  | 360 | 46.8 | 406.8 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling from A048 to A051; Cutting whips, stumps; Cutting trees in wetland, bucking into 7' Lengths; Raking, Ditching, Installing Culverts, Labourers Cleaning Tracks, picking up garbage |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57220191120-3-R1Chainsaw and consummables3360 | Corbiere and Sons Contracting57220191120-3-R1Chainsaw and consummables3360Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 572 | 20191120-3-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling from A048 to A051; Cutting whips, stumps; Cutting trees in wetland, bucking into 7' Lengths; Raking, Ditching, Installing Culverts, Labourers Cleaning Tracks, picking up garbage |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57220191120-3-R1Light Truck - Pick up30900 | Corbiere and Sons Contracting57220191120-3-R1Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 572 | 20191120-3-R1 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling from A048 to A051; Cutting whips, stumps; Cutting trees in wetland, bucking into 7' Lengths; Raking, Ditching, Installing Culverts, Labourers Cleaning Tracks, picking up garbage |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57220191120-3-R1Light Truck - Pick up20600 | Corbiere and Sons Contracting57220191120-3-R1Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 572 | 20191120-3-R1 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling from A048 to A051; Cutting whips, stumps; Cutting trees in wetland, bucking into 7' Lengths; Raking, Ditching, Installing Culverts, Labourers Cleaning Tracks, picking up garbage |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57220191120-3-R1Foreman4380 | Corbiere and Sons Contracting57220191120-3-R1Foreman4380Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 572 | 20191120-3-R1 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling from A048 to A051; Cutting whips, stumps; Cutting trees in wetland, bucking into 7' Lengths; Raking, Ditching, Installing Culverts, Labourers Cleaning Tracks, picking up garbage |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57220191120-3-R1Operator - Principle443960 | Corbiere and Sons Contracting57220191120-3-R1Operator - Principle443960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 572 | 20191120-3-R1 | 53520101 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling from A048 to A051; Cutting whips, stumps; Cutting trees in wetland, bucking into 7' Lengths; Raking, Ditching, Installing Culverts, Labourers Cleaning Tracks, picking up garbage |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57220191120-3-R1Operator - Intermdiate11825 | Corbiere and Sons Contracting57220191120-3-R1Operator - Intermdiate11825Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 572 | 20191120-3-R1 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 33 | HR |  |  |  | 0 | 2475 | 321.75 | 2796.75 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling from A048 to A051; Cutting whips, stumps; Cutting trees in wetland, bucking into 7' Lengths; Raking, Ditching, Installing Culverts, Labourers Cleaning Tracks, picking up garbage |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57220191120-3-R1Labourer - Specialized332475 | Corbiere and Sons Contracting57220191120-3-R1Labourer - Specialized332475Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 572 | 20191120-3-R1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling from A048 to A051; Cutting whips, stumps; Cutting trees in wetland, bucking into 7' Lengths; Raking, Ditching, Installing Culverts, Labourers Cleaning Tracks, picking up garbage |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57220191120-3-R1L.O.A.4840 | Corbiere and Sons Contracting57220191120-3-R1L.O.A.4840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 572 | 20191120-3-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling from A048 to A051; Cutting whips, stumps; Cutting trees in wetland, bucking into 7' Lengths; Raking, Ditching, Installing Culverts, Labourers Cleaning Tracks, picking up garbage |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57220191120-3-R1L.O.A.2420 | Corbiere and Sons Contracting57220191120-3-R1L.O.A.2420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 572 | 20191120-3-R1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling from A048 to A051; Cutting whips, stumps; Cutting trees in wetland, bucking into 7' Lengths; Raking, Ditching, Installing Culverts, Labourers Cleaning Tracks, picking up garbage |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57220191120-3-R1L.O.A.3630 | Corbiere and Sons Contracting57220191120-3-R1L.O.A.3630Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 574 | 20191120-4-R1 | 53520101 | Clearing | 0 | Brusher | 202.5 | 3.5 | HR | 151.88 | 0 |  |  | 708.75 | 92.1375 | 800.8875 | 2019-11-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, spotting, fueling, hauling Geo; Dylan and Wade left at 12:30; Raking from A057 to A061 |  |  | A057 to A061; | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57420191120-4-R1Brusher3.5708.75 | Corbiere and Sons Contracting57420191120-4-R1Brusher3.5708.75Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 708.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 574 | 20191120-4-R1 | 53520101 | Clearing | 0 | Dozer D6 or equal | 135 | 4 | HR | 101.25 | 0 |  |  | 540 | 70.2 | 610.2 | 2019-11-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, spotting, fueling, hauling Geo; Dylan and Wade left at 12:30; Raking from A057 to A061 |  |  | A057 to A061; | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57420191120-4-R1Dozer D6 or equal4540 | Corbiere and Sons Contracting57420191120-4-R1Dozer D6 or equal4540Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 540 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 574 | 20191120-4-R1 | 53520101 | Clearing | 0 | Excavator - 20 ton | 130.5 | 7.5 | HR | 97.88 | 0 |  |  | 978.75 | 127.2375 | 1105.9875 | 2019-11-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, spotting, fueling, hauling Geo; Dylan and Wade left at 12:30; Raking from A057 to A061 |  |  | A057 to A061; | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57420191120-4-R1Excavator - 20 ton7.5978.75 | Corbiere and Sons Contracting57420191120-4-R1Excavator - 20 ton7.5978.75Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 978.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 574 | 20191120-4-R1 | 53520101 | Clearing | 0 | Excavator - 30 ton | 139.5 | 6 | HR | 104.63 | 0 |  |  | 837 | 108.81 | 945.81 | 2019-11-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, spotting, fueling, hauling Geo; Dylan and Wade left at 12:30; Raking from A057 to A061 |  |  | A057 to A061; | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57420191120-4-R1Excavator - 30 ton6837 | Corbiere and Sons Contracting57420191120-4-R1Excavator - 30 ton6837Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 837 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 574 | 20191120-4-R1 | 53520101 | Clearing | 0 | Excavator - 36 ton | 171 | 4.5 | HR | 128.25 | 0 |  |  | 769.5 | 100.035 | 869.535 | 2019-11-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, spotting, fueling, hauling Geo; Dylan and Wade left at 12:30; Raking from A057 to A061 |  |  | A057 to A061; | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57420191120-4-R1Excavator - 36 ton4.5769.5 | Corbiere and Sons Contracting57420191120-4-R1Excavator - 36 ton4.5769.5Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 769.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 574 | 20191120-4-R1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-11-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, spotting, fueling, hauling Geo; Dylan and Wade left at 12:30; Raking from A057 to A061 |  |  | A057 to A061; | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57420191120-4-R1Light Truck - Pick up601800 | Corbiere and Sons Contracting57420191120-4-R1Light Truck - Pick up601800Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 574 | 20191120-4-R1 | 53520101 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, spotting, fueling, hauling Geo; Dylan and Wade left at 12:30; Raking from A057 to A061 |  |  | A057 to A061; | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57420191120-4-R1Foreman121140 | Corbiere and Sons Contracting57420191120-4-R1Foreman121140Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 574 | 20191120-4-R1 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-11-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, spotting, fueling, hauling Geo; Dylan and Wade left at 12:30; Raking from A057 to A061 |  |  | A057 to A061; | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57420191120-4-R1Operator - Principle443960 | Corbiere and Sons Contracting57420191120-4-R1Operator - Principle443960Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 574 | 20191120-4-R1 | 53520101 | Clearing | 0 | Labourer - General | 65 | 42 | HR |  |  |  | 0 | 2730 | 354.9 | 3084.9 | 2019-11-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, spotting, fueling, hauling Geo; Dylan and Wade left at 12:30; Raking from A057 to A061 |  |  | A057 to A061; | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57420191120-4-R1Labourer - General422730 | Corbiere and Sons Contracting57420191120-4-R1Labourer - General422730Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2730 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 574 | 20191120-4-R1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2019-11-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, spotting, fueling, hauling Geo; Dylan and Wade left at 12:30; Raking from A057 to A061 |  |  | A057 to A061; | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57420191120-4-R1L.O.A.81680 | Corbiere and Sons Contracting57420191120-4-R1L.O.A.81680Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1595 | 20191120-5 | 53520102 | Clearing | 0 | Feller Buncher | 240 |  | HR | 180 | 45 |  |  | 8100 | 1053 | 9153 | 2019-11-20 | 1 | INV#024 | 43953 | 90 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | No BackUp provided LEM not approved yet |  | Approved |  |  | All FB's, SKD's and Mulcher on standby waiting for permits: Sander Truck and Grader requested by Valard but not needed in field today today on standby | 1 |  |  | 0 | 43795 |  | 40 | 43948 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting159520191120-5Feller Buncher8100 | Corbiere and Sons Contracting159520191120-5Feller Buncher8100INV#024 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 8100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1595 | 20191120-5 | 53520102 | Clearing | 0 | Mulcher | 205 |  | HR | 153.75 | 9 |  |  | 1383.75 | 179.8875 | 1563.6375 | 2019-11-20 | 1 | INV#024 | 43953 | 90 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | No BackUp provided LEM not approved yet |  | Approved |  |  | All FB's, SKD's and Mulcher on standby waiting for permits: Sander Truck and Grader requested by Valard but not needed in field today today on standby | 1 |  |  | 0 | 43795 |  | 40 | 43948 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting159520191120-5Mulcher1383.75 | Corbiere and Sons Contracting159520191120-5Mulcher1383.75INV#024 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1383.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1595 | 20191120-5 | 53520102 | Clearing | 0 | Skidder | 171 |  | HR | 128.25 | 36 |  |  | 4617 | 600.21 | 5217.21 | 2019-11-20 | 1 | INV#024 | 43953 | 90 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | No BackUp provided LEM not approved yet |  | Approved |  |  | All FB's, SKD's and Mulcher on standby waiting for permits: Sander Truck and Grader requested by Valard but not needed in field today today on standby | 1 |  |  | 0 | 43795 |  | 40 | 43948 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting159520191120-5Skidder 4617 | Corbiere and Sons Contracting159520191120-5Skidder 4617INV#024 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1595 | 20191120-5 | 53520102 | Clearing | 0 | Grader - Cat 12 to 14 or equal | 126 |  | HR | 94.5 | 9 |  |  | 850.5 | 110.565 | 961.065 | 2019-11-20 | 1 | INV#024 | 43953 | 90 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | No BackUp provided LEM not approved yet |  | Approved |  |  | All FB's, SKD's and Mulcher on standby waiting for permits: Sander Truck and Grader requested by Valard but not needed in field today today on standby | 1 |  |  | 0 | 43795 |  | 40 | 43948 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting159520191120-5Grader - Cat 12 to 14 or equal850.5 | Corbiere and Sons Contracting159520191120-5Grader - Cat 12 to 14 or equal850.5INV#024 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 850.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1595 | 20191120-5 | 53520102 | Clearing | 0 | Sander Truck | 112.5 |  | HR | 84.38 | 9 |  |  | 759.42 | 98.7246 | 858.1446 | 2019-11-20 | 1 | INV#024 | 43953 | 90 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | No BackUp provided LEM not approved yet |  | Approved |  |  | All FB's, SKD's and Mulcher on standby waiting for permits: Sander Truck and Grader requested by Valard but not needed in field today today on standby | 1 |  |  | 0 | 43795 |  | 40 | 43948 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting159520191120-5Sander Truck759.42 | Corbiere and Sons Contracting159520191120-5Sander Truck759.42INV#024 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 759.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1595 | 20191120-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 |  | HR | 22.5 | 50 |  |  | 1125 | 146.25 | 1271.25 | 2019-11-20 | 1 | INV#024 | 43953 | 90 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | No BackUp provided LEM not approved yet |  | Approved |  |  | All FB's, SKD's and Mulcher on standby waiting for permits: Sander Truck and Grader requested by Valard but not needed in field today today on standby | 1 |  |  | 0 | 43795 |  | 40 | 43948 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting159520191120-5Light Truck - Pick up1125 | Corbiere and Sons Contracting159520191120-5Light Truck - Pick up1125INV#024 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1595 | 20191120-5 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2019-11-20 | 1 | INV#024 | 43953 | 90 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | No BackUp provided LEM not approved yet |  | Approved |  |  | All FB's, SKD's and Mulcher on standby waiting for permits: Sander Truck and Grader requested by Valard but not needed in field today today on standby | 1 |  |  | 0 | 43795 |  | 40 | 43948 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting159520191120-5Foreman4380 | Corbiere and Sons Contracting159520191120-5Foreman4380INV#024 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1595 | 20191120-5 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 24 | HR |  |  |  | 0 | 2160 | 280.8 | 2440.8 | 2019-11-20 | 1 | INV#024 | 43953 | 90 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | No BackUp provided LEM not approved yet |  | Approved |  |  | All FB's, SKD's and Mulcher on standby waiting for permits: Sander Truck and Grader requested by Valard but not needed in field today today on standby | 1 |  |  | 0 | 43795 |  | 40 | 43948 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting159520191120-5Operator - Principle242160 | Corbiere and Sons Contracting159520191120-5Operator - Principle242160INV#024 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1595 | 20191120-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-11-20 | 1 | INV#024 | 43953 | 90 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | No BackUp provided LEM not approved yet |  | Approved |  |  | All FB's, SKD's and Mulcher on standby waiting for permits: Sander Truck and Grader requested by Valard but not needed in field today today on standby | 1 |  |  | 0 | 43795 |  | 40 | 43948 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting159520191120-5L.O.A.71470 | Corbiere and Sons Contracting159520191120-5L.O.A.71470INV#024 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 571 | 20191121-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting57120191121-1Light Truck - Pick up501500 | Corbiere and Sons Contracting57120191121-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 571 | 20191121-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting57120191121-1Project Manager121320 | Corbiere and Sons Contracting57120191121-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 571 | 20191121-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting57120191121-1Superintendent121260 | Corbiere and Sons Contracting57120191121-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 571 | 20191121-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting57120191121-1Project Coordinator12960 | Corbiere and Sons Contracting57120191121-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 571 | 20191121-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting57120191121-1Safety Advisor121020 | Corbiere and Sons Contracting57120191121-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 571 | 20191121-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting57120191121-1Project Controls12840 | Corbiere and Sons Contracting57120191121-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 571 | 20191121-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting57120191121-1L.O.A.51050 | Corbiere and Sons Contracting57120191121-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 576 | 20191121-2-R1 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 74.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2019-11-24 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Plowing of yard, welding, equipment repairs and general yard maintenance |  |  | General yard and equipment maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting57620191121-2-R1Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting57620191121-2-R1Loader JD 524 to 624 or equal5495Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 576 | 20191121-2-R1 | 53520101 | Clearing | 0 | Sander Truck | 112.5 | 5 | HR | 84.38 |  |  |  | 562.5 | 73.125 | 635.625 | 2019-11-24 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Plowing of yard, welding, equipment repairs and general yard maintenance |  |  | General yard and equipment maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting57620191121-2-R1Sander Truck5562.5 | Corbiere and Sons Contracting57620191121-2-R1Sander Truck5562.5Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 562.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 576 | 20191121-2-R1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-24 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Plowing of yard, welding, equipment repairs and general yard maintenance |  |  | General yard and equipment maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting57620191121-2-R1Light Truck - Pick up10300 | Corbiere and Sons Contracting57620191121-2-R1Light Truck - Pick up10300Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 576 | 20191121-2-R1 | 53520101 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-24 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Plowing of yard, welding, equipment repairs and general yard maintenance |  |  | General yard and equipment maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting57620191121-2-R1Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting57620191121-2-R1Tractor Trailer - 60 Ton101350Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 576 | 20191121-2-R1 | 53520101 | Clearing | 0 | Operator - Intermdiate | 75 | 28 | HR |  |  | 70 | 0 | 2100 | 273 | 2373 | 2019-11-24 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Plowing of yard, welding, equipment repairs and general yard maintenance |  |  | General yard and equipment maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting57620191121-2-R1Operator - Intermdiate282100 | Corbiere and Sons Contracting57620191121-2-R1Operator - Intermdiate282100Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 576 | 20191121-2-R1 | 53520101 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-11-24 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Plowing of yard, welding, equipment repairs and general yard maintenance |  |  | General yard and equipment maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting57620191121-2-R1Labourer - General10650 | Corbiere and Sons Contracting57620191121-2-R1Labourer - General10650Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 576 | 20191121-2-R1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-24 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Plowing of yard, welding, equipment repairs and general yard maintenance |  |  | General yard and equipment maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting57620191121-2-R1L.O.A.3630 | Corbiere and Sons Contracting57620191121-2-R1L.O.A.3630Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 573 | 20191121-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 2.5 | HR | 151.88 | 0 |  |  | 506.25 | 65.8125 | 572.0625 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; Mulcher on SB; 1 DZ on SB; Labourers fueling, running tools, shovelling, Cleaning Tracks; Building Road, Raking; Brushing all between A057 and A060 |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57320191121-3Brusher2.5506.25 | Corbiere and Sons Contracting57320191121-3Brusher2.5506.25Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 506.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 573 | 20191121-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; Mulcher on SB; 1 DZ on SB; Labourers fueling, running tools, shovelling, Cleaning Tracks; Building Road, Raking; Brushing all between A057 and A060 |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57320191121-3Brusher91822.5 | Corbiere and Sons Contracting57320191121-3Brusher91822.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 573 | 20191121-3 | 53520101 | Clearing | 0 | Feller Buncher | 240 |  | HR | 180 | 45 |  |  | 8100 | 1053 | 9153 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; Mulcher on SB; 1 DZ on SB; Labourers fueling, running tools, shovelling, Cleaning Tracks; Building Road, Raking; Brushing all between A057 and A060 |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57320191121-3Feller Buncher8100 | Corbiere and Sons Contracting57320191121-3Feller Buncher8100Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 8100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 573 | 20191121-3 | 53520101 | Clearing | 0 | Skidder | 171 |  | HR | 128.25 | 36 |  |  | 4617 | 600.21 | 5217.21 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; Mulcher on SB; 1 DZ on SB; Labourers fueling, running tools, shovelling, Cleaning Tracks; Building Road, Raking; Brushing all between A057 and A060 |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57320191121-3Skidder 4617 | Corbiere and Sons Contracting57320191121-3Skidder 4617Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 573 | 20191121-3 | 53520101 | Clearing | 0 | Dozer D6 or equal | 135 |  | HR | 101.25 | 9 |  |  | 911.25 | 118.4625 | 1029.7125 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; Mulcher on SB; 1 DZ on SB; Labourers fueling, running tools, shovelling, Cleaning Tracks; Building Road, Raking; Brushing all between A057 and A060 |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57320191121-3Dozer D6 or equal911.25 | Corbiere and Sons Contracting57320191121-3Dozer D6 or equal911.25Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 911.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 573 | 20191121-3 | 53520102 | Clearing | 0 | Excavator - 30 ton | 139.5 | 7.5 | HR | 104.63 | 0 |  |  | 1046.25 | 136.0125 | 1182.2625 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; Mulcher on SB; 1 DZ on SB; Labourers fueling, running tools, shovelling, Cleaning Tracks; Building Road, Raking; Brushing all between A057 and A060 |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57320191121-3Excavator - 30 ton7.51046.25 | Corbiere and Sons Contracting57320191121-3Excavator - 30 ton7.51046.25Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1046.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 573 | 20191121-3 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 3 | HR | 128.25 | 0 |  |  | 513 | 66.69 | 579.69 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; Mulcher on SB; 1 DZ on SB; Labourers fueling, running tools, shovelling, Cleaning Tracks; Building Road, Raking; Brushing all between A057 and A060 |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57320191121-3Excavator - 36 ton3513 | Corbiere and Sons Contracting57320191121-3Excavator - 36 ton3513Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 513 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 573 | 20191121-3 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 7.5 | HR | 94.5 | 0 |  |  | 945 | 122.85 | 1067.85 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; Mulcher on SB; 1 DZ on SB; Labourers fueling, running tools, shovelling, Cleaning Tracks; Building Road, Raking; Brushing all between A057 and A060 |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57320191121-3Grader - Cat 12 to 14 or equal7.5945 | Corbiere and Sons Contracting57320191121-3Grader - Cat 12 to 14 or equal7.5945Inv#004-R02 | [5 empty] | 1 | 945 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 573 | 20191121-3 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; Mulcher on SB; 1 DZ on SB; Labourers fueling, running tools, shovelling, Cleaning Tracks; Building Road, Raking; Brushing all between A057 and A060 |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57320191121-3Light Truck - Pick up10300 | Corbiere and Sons Contracting57320191121-3Light Truck - Pick up10300Inv#004-R02 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 573 | 20191121-3 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 |  | HR | 22.5 | 50 |  |  | 1125 | 146.25 | 1271.25 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; Mulcher on SB; 1 DZ on SB; Labourers fueling, running tools, shovelling, Cleaning Tracks; Building Road, Raking; Brushing all between A057 and A060 |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57320191121-3Light Truck - Pick up1125 | Corbiere and Sons Contracting57320191121-3Light Truck - Pick up1125Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 573 | 20191121-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; Mulcher on SB; 1 DZ on SB; Labourers fueling, running tools, shovelling, Cleaning Tracks; Building Road, Raking; Brushing all between A057 and A060 |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57320191121-3Light Truck - Pick up10300 | Corbiere and Sons Contracting57320191121-3Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 573 | 20191121-3 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; Mulcher on SB; 1 DZ on SB; Labourers fueling, running tools, shovelling, Cleaning Tracks; Building Road, Raking; Brushing all between A057 and A060 |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57320191121-3Foreman4380 | Corbiere and Sons Contracting57320191121-3Foreman4380Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 573 | 20191121-3 | 53520102 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  |  | 0 | 570 | 74.1 | 644.1 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; Mulcher on SB; 1 DZ on SB; Labourers fueling, running tools, shovelling, Cleaning Tracks; Building Road, Raking; Brushing all between A057 and A060 |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57320191121-3Foreman6570 | Corbiere and Sons Contracting57320191121-3Foreman6570Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 573 | 20191121-3 | 53510111 | Access | 0 | Operator - Principle | 90 | 13 | HR |  |  |  | 0 | 1170 | 152.1 | 1322.1 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; Mulcher on SB; 1 DZ on SB; Labourers fueling, running tools, shovelling, Cleaning Tracks; Building Road, Raking; Brushing all between A057 and A060 |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57320191121-3Operator - Principle131170 | Corbiere and Sons Contracting57320191121-3Operator - Principle131170Inv#004-R02 | [5 empty] | 1 | 1170 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 573 | 20191121-3 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 28 | HR |  |  |  | 0 | 2520 | 327.6 | 2847.6 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; Mulcher on SB; 1 DZ on SB; Labourers fueling, running tools, shovelling, Cleaning Tracks; Building Road, Raking; Brushing all between A057 and A060 |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57320191121-3Operator - Principle282520 | Corbiere and Sons Contracting57320191121-3Operator - Principle282520Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2520 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 573 | 20191121-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 36 | HR |  |  |  | 0 | 3240 | 421.2 | 3661.2 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; Mulcher on SB; 1 DZ on SB; Labourers fueling, running tools, shovelling, Cleaning Tracks; Building Road, Raking; Brushing all between A057 and A060 |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57320191121-3Operator - Principle363240 | Corbiere and Sons Contracting57320191121-3Operator - Principle363240Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 573 | 20191121-3 | 53520102 | Clearing | 0 | Labourer - General | 65 | 20 | HR |  |  |  | 0 | 1300 | 169 | 1469 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; Mulcher on SB; 1 DZ on SB; Labourers fueling, running tools, shovelling, Cleaning Tracks; Building Road, Raking; Brushing all between A057 and A060 |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57320191121-3Labourer - General201300 | Corbiere and Sons Contracting57320191121-3Labourer - General201300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 573 | 20191121-3 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; Mulcher on SB; 1 DZ on SB; Labourers fueling, running tools, shovelling, Cleaning Tracks; Building Road, Raking; Brushing all between A057 and A060 |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57320191121-3L.O.A.1210 | Corbiere and Sons Contracting57320191121-3L.O.A.1210Inv#004-R02 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 573 | 20191121-3 | 53520101 | Clearing | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; Mulcher on SB; 1 DZ on SB; Labourers fueling, running tools, shovelling, Cleaning Tracks; Building Road, Raking; Brushing all between A057 and A060 |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57320191121-3L.O.A.81680 | Corbiere and Sons Contracting57320191121-3L.O.A.81680Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 573 | 20191121-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; Mulcher on SB; 1 DZ on SB; Labourers fueling, running tools, shovelling, Cleaning Tracks; Building Road, Raking; Brushing all between A057 and A060 |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting57320191121-3L.O.A.3630 | Corbiere and Sons Contracting57320191121-3L.O.A.3630Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 577 | 20191121-4-R1 | 53520102 | Clearing | 0 | Brusher | 202.5 | 5 | HR | 151.88 | 0 |  |  | 1012.5 | 131.625 | 1144.125 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling for trees that were over hanging after snowfall; Cutting from A049 to A052; Raking, plowing, Installing Culverts; Grinding of Material; Labourers Cleaning tracks, picking up garbage. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57720191121-4-R1Brusher51012.5 | Corbiere and Sons Contracting57720191121-4-R1Brusher51012.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1012.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 577 | 20191121-4-R1 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 14 | HR | 417.6 | 3 |  |  | 9048 | 1176.24 | 10224.24 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling for trees that were over hanging after snowfall; Cutting from A049 to A052; Raking, plowing, Installing Culverts; Grinding of Material; Labourers Cleaning tracks, picking up garbage. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57720191121-4-R1Grinder - 4710 Peterson or equal149048 | Corbiere and Sons Contracting57720191121-4-R1Grinder - 4710 Peterson or equal149048Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 9048 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 577 | 20191121-4-R1 | 53520102 | Clearing | 0 | Log Loader | 153 | 14 | HR | 114.75 | 3 |  |  | 2486.25 | 323.2125 | 2809.4625 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling for trees that were over hanging after snowfall; Cutting from A049 to A052; Raking, plowing, Installing Culverts; Grinding of Material; Labourers Cleaning tracks, picking up garbage. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57720191121-4-R1Log Loader142486.25 | Corbiere and Sons Contracting57720191121-4-R1Log Loader142486.25Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2486.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 577 | 20191121-4-R1 | 53520101 | Clearing | 0 | Chainsaw and consummables | 120 | 4 | Day |  | 0 |  |  | 480 | 62.4 | 542.4 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling for trees that were over hanging after snowfall; Cutting from A049 to A052; Raking, plowing, Installing Culverts; Grinding of Material; Labourers Cleaning tracks, picking up garbage. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57720191121-4-R1Chainsaw and consummables4480 | Corbiere and Sons Contracting57720191121-4-R1Chainsaw and consummables4480Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 577 | 20191121-4-R1 | 53520102 | Clearing | 0 | Excavator - 30 ton | 139.5 | 7 | HR | 104.63 | 0 |  |  | 976.5 | 126.945 | 1103.445 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling for trees that were over hanging after snowfall; Cutting from A049 to A052; Raking, plowing, Installing Culverts; Grinding of Material; Labourers Cleaning tracks, picking up garbage. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57720191121-4-R1Excavator - 30 ton7976.5 | Corbiere and Sons Contracting57720191121-4-R1Excavator - 30 ton7976.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 976.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 577 | 20191121-4-R1 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 7 | HR | 128.25 | 0 |  |  | 1197 | 155.61 | 1352.61 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling for trees that were over hanging after snowfall; Cutting from A049 to A052; Raking, plowing, Installing Culverts; Grinding of Material; Labourers Cleaning tracks, picking up garbage. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57720191121-4-R1Excavator - 36 ton71197 | Corbiere and Sons Contracting57720191121-4-R1Excavator - 36 ton71197Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1197 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 577 | 20191121-4-R1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 |  |  |  | 600 | 78 | 678 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling for trees that were over hanging after snowfall; Cutting from A049 to A052; Raking, plowing, Installing Culverts; Grinding of Material; Labourers Cleaning tracks, picking up garbage. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57720191121-4-R1Light Truck - Pick up20600 | Corbiere and Sons Contracting57720191121-4-R1Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 577 | 20191121-4-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling for trees that were over hanging after snowfall; Cutting from A049 to A052; Raking, plowing, Installing Culverts; Grinding of Material; Labourers Cleaning tracks, picking up garbage. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57720191121-4-R1Light Truck - Pick up30900 | Corbiere and Sons Contracting57720191121-4-R1Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 577 | 20191121-4-R1 | 53520102 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  |  | 0 | 570 | 74.1 | 644.1 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling for trees that were over hanging after snowfall; Cutting from A049 to A052; Raking, plowing, Installing Culverts; Grinding of Material; Labourers Cleaning tracks, picking up garbage. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57720191121-4-R1Foreman6570 | Corbiere and Sons Contracting57720191121-4-R1Foreman6570Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 577 | 20191121-4-R1 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling for trees that were over hanging after snowfall; Cutting from A049 to A052; Raking, plowing, Installing Culverts; Grinding of Material; Labourers Cleaning tracks, picking up garbage. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57720191121-4-R1Operator - Principle11990 | Corbiere and Sons Contracting57720191121-4-R1Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 577 | 20191121-4-R1 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 72 | HR |  |  |  | 0 | 6480 | 842.4 | 7322.4 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling for trees that were over hanging after snowfall; Cutting from A049 to A052; Raking, plowing, Installing Culverts; Grinding of Material; Labourers Cleaning tracks, picking up garbage. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57720191121-4-R1Operator - Principle726480 | Corbiere and Sons Contracting57720191121-4-R1Operator - Principle726480Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 6480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 577 | 20191121-4-R1 | 53520101 | Clearing | 0 | Labourer - Specialized | 75 | 44 | HR |  |  |  | 0 | 3300 | 429 | 3729 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling for trees that were over hanging after snowfall; Cutting from A049 to A052; Raking, plowing, Installing Culverts; Grinding of Material; Labourers Cleaning tracks, picking up garbage. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57720191121-4-R1Labourer - Specialized443300 | Corbiere and Sons Contracting57720191121-4-R1Labourer - Specialized443300Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 577 | 20191121-4-R1 | 53520102 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling for trees that were over hanging after snowfall; Cutting from A049 to A052; Raking, plowing, Installing Culverts; Grinding of Material; Labourers Cleaning tracks, picking up garbage. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57720191121-4-R1Labourer - General10650 | Corbiere and Sons Contracting57720191121-4-R1Labourer - General10650Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 577 | 20191121-4-R1 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling for trees that were over hanging after snowfall; Cutting from A049 to A052; Raking, plowing, Installing Culverts; Grinding of Material; Labourers Cleaning tracks, picking up garbage. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57720191121-4-R1L.O.A.1210 | Corbiere and Sons Contracting57720191121-4-R1L.O.A.1210Inv#004-R02 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 577 | 20191121-4-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2019-11-24 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling for trees that were over hanging after snowfall; Cutting from A049 to A052; Raking, plowing, Installing Culverts; Grinding of Material; Labourers Cleaning tracks, picking up garbage. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting57720191121-4-R1L.O.A.102100 | Corbiere and Sons Contracting57720191121-4-R1L.O.A.102100Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 578 | 20191122-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting57820191122-1Light Truck - Pick up501500 | Corbiere and Sons Contracting57820191122-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 578 | 20191122-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting57820191122-1Project Manager121320 | Corbiere and Sons Contracting57820191122-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 578 | 20191122-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting57820191122-1Superintendent121260 | Corbiere and Sons Contracting57820191122-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 578 | 20191122-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting57820191122-1Project Coordinator12960 | Corbiere and Sons Contracting57820191122-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 578 | 20191122-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting57820191122-1Safety Advisor121020 | Corbiere and Sons Contracting57820191122-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 578 | 20191122-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting57820191122-1Project Controls12840 | Corbiere and Sons Contracting57820191122-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 578 | 20191122-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43795 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting57820191122-1L.O.A.51050 | Corbiere and Sons Contracting57820191122-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 579 | 20191122-2-R1 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 74.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2019-11-25 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance, Float Truck Broke down at noon; Wes O'Connor aided with LTL trucks who came in to help with floats |  |  | General yard and equipment maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting57920191122-2-R1Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting57920191122-2-R1Loader JD 524 to 624 or equal5495Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 579 | 20191122-2-R1 | 53520101 | Clearing | 0 | Sander Truck | 112.5 | 5 | HR | 84.38 |  |  |  | 562.5 | 73.125 | 635.625 | 2019-11-25 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance, Float Truck Broke down at noon; Wes O'Connor aided with LTL trucks who came in to help with floats |  |  | General yard and equipment maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting57920191122-2-R1Sander Truck5562.5 | Corbiere and Sons Contracting57920191122-2-R1Sander Truck5562.5Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 562.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 579 | 20191122-2-R1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-25 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance, Float Truck Broke down at noon; Wes O'Connor aided with LTL trucks who came in to help with floats |  |  | General yard and equipment maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting57920191122-2-R1Light Truck - Pick up10300 | Corbiere and Sons Contracting57920191122-2-R1Light Truck - Pick up10300Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 579 | 20191122-2-R1 | 53520101 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 5 | HR | 101.25 | 0 |  |  | 675 | 87.75 | 762.75 | 2019-11-25 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance, Float Truck Broke down at noon; Wes O'Connor aided with LTL trucks who came in to help with floats |  |  | General yard and equipment maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting57920191122-2-R1Tractor Trailer - 60 Ton5675 | Corbiere and Sons Contracting57920191122-2-R1Tractor Trailer - 60 Ton5675Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 579 | 20191122-2-R1 | 53520101 | Clearing | 0 | Operator - Intermdiate | 75 | 25 | HR |  |  | 70 | 0 | 1875 | 243.75 | 2118.75 | 2019-11-25 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance, Float Truck Broke down at noon; Wes O'Connor aided with LTL trucks who came in to help with floats |  |  | General yard and equipment maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting57920191122-2-R1Operator - Intermdiate251875 | Corbiere and Sons Contracting57920191122-2-R1Operator - Intermdiate251875Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1875 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 579 | 20191122-2-R1 | 53520101 | Clearing | 0 | Labourer - General | 65 | 21 | HR |  |  |  | 0 | 1365 | 177.45 | 1542.45 | 2019-11-25 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance, Float Truck Broke down at noon; Wes O'Connor aided with LTL trucks who came in to help with floats |  |  | General yard and equipment maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting57920191122-2-R1Labourer - General211365 | Corbiere and Sons Contracting57920191122-2-R1Labourer - General211365Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1365 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 579 | 20191122-2-R1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-25 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance, Float Truck Broke down at noon; Wes O'Connor aided with LTL trucks who came in to help with floats |  |  | General yard and equipment maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting57920191122-2-R1L.O.A.4840 | Corbiere and Sons Contracting57920191122-2-R1L.O.A.4840Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 8.5 | HR | 151.88 | 0 |  |  | 1721.25 | 223.7625 | 1945.0125 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3Brusher8.51721.25 | Corbiere and Sons Contracting58020191122-3Brusher8.51721.25Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1721.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53520102 | Clearing | 0 | Feller Buncher | 240 |  | HR | 180 | 45 |  |  | 8100 | 1053 | 9153 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3Feller Buncher8100 | Corbiere and Sons Contracting58020191122-3Feller Buncher8100Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 8100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53520102 | Clearing | 0 | Mulcher | 205 |  | HR | 153.75 | 9 |  |  | 1383.75 | 179.8875 | 1563.6375 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3Mulcher1383.75 | Corbiere and Sons Contracting58020191122-3Mulcher1383.75Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1383.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53520102 | Clearing | 0 | Skidder | 171 |  | HR | 128.25 | 36 |  |  | 4617 | 600.21 | 5217.21 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3Skidder 4617 | Corbiere and Sons Contracting58020191122-3Skidder 4617Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53520102 | Clearing | 0 | Dozer D6 or equal | 135 | 8.5 | HR | 101.25 | 0 |  |  | 1147.5 | 149.175 | 1296.675 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3Dozer D6 or equal8.51147.5 | Corbiere and Sons Contracting58020191122-3Dozer D6 or equal8.51147.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1147.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53520102 | Clearing | 0 | Excavator - 30 ton | 139.5 | 8.5 | HR | 104.63 | 0 |  |  | 1185.75 | 154.1475 | 1339.8975 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3Excavator - 30 ton8.51185.75 | Corbiere and Sons Contracting58020191122-3Excavator - 30 ton8.51185.75Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1185.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 11 | HR | 94.5 | 0 |  |  | 1386 | 180.18 | 1566.18 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3Grader - Cat 12 to 14 or equal111386 | Corbiere and Sons Contracting58020191122-3Grader - Cat 12 to 14 or equal111386Inv#004-R02 | [5 empty] | 1 | 1386 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3Light Truck - Pick up20600 | Corbiere and Sons Contracting58020191122-3Light Truck - Pick up20600Inv#004-R02 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 |  | HR | 22.5 | 50 |  |  | 1125 | 146.25 | 1271.25 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3Light Truck - Pick up1125 | Corbiere and Sons Contracting58020191122-3Light Truck - Pick up1125Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3Light Truck - Pick up30900 | Corbiere and Sons Contracting58020191122-3Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53510111 | Access | 0 | Foreman | 95 | 6 | HR |  |  |  | 0 | 570 | 74.1 | 644.1 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3Foreman6570 | Corbiere and Sons Contracting58020191122-3Foreman6570Inv#004-R02 | [5 empty] | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3Foreman4380 | Corbiere and Sons Contracting58020191122-3Foreman4380Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53520102 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  |  | 0 | 570 | 74.1 | 644.1 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3Foreman6570 | Corbiere and Sons Contracting58020191122-3Foreman6570Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53510111 | Access | 0 | Operator - Principle | 90 | 23 | HR |  |  |  | 0 | 2070 | 269.1 | 2339.1 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3Operator - Principle232070 | Corbiere and Sons Contracting58020191122-3Operator - Principle232070Inv#004-R02 | [5 empty] | 1 | 2070 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 20 | HR |  |  |  | 0 | 1800 | 234 | 2034 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3Operator - Principle201800 | Corbiere and Sons Contracting58020191122-3Operator - Principle201800Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3Operator - Principle11990 | Corbiere and Sons Contracting58020191122-3Operator - Principle11990Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3Operator - Principle443960 | Corbiere and Sons Contracting58020191122-3Operator - Principle443960Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53510111 | Access | 0 | Labourer - Specialized | 75 | 5 | HR |  |  |  | 0 | 375 | 48.75 | 423.75 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3Labourer - Specialized5375 | Corbiere and Sons Contracting58020191122-3Labourer - Specialized5375Inv#004-R02 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53510111 | Access | 0 | Labourer - General | 65 | 19 | HR |  |  |  | 0 | 1235 | 160.55 | 1395.55 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3Labourer - General191235 | Corbiere and Sons Contracting58020191122-3Labourer - General191235Inv#004-R02 | [5 empty] | 1 | 1235 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53520102 | Clearing | 0 | Labourer - General | 65 | 4 | HR |  |  |  | 0 | 260 | 33.8 | 293.8 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3Labourer - General4260 | Corbiere and Sons Contracting58020191122-3Labourer - General4260Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53510111 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3L.O.A.51050 | Corbiere and Sons Contracting58020191122-3L.O.A.51050Inv#004-R02 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53520101 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3L.O.A.71470 | Corbiere and Sons Contracting58020191122-3L.O.A.71470Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 580 | 20191122-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | All Feller Bunchers and Skidders on SB; No Permits; Mulcher on SB; Attempted to move to A116 but couldn't make it up hill; Mike, Lionel, Robert out all day waiting for FBs to get to windfarm; |  |  | Eldorado | 0 |  |  | 8 | 43795 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58020191122-3L.O.A.3630 | Corbiere and Sons Contracting58020191122-3L.O.A.3630Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 581 | 20191122-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling at A051 to A052 and also at Valard yard; Raking from A049 to A051 and from A053 to A052; Brushing both sides of rail tracks at A053; Culverts Installed on Beck Rd. from Hwy 9 |  |  | Beck Road East | 0 |  |  | 10 | 43795 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58120191122-4Brusher91822.5 | Corbiere and Sons Contracting58120191122-4Brusher91822.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 581 | 20191122-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 12.5 | HR | 417.6 | 5.5 |  |  | 9256.8 | 1203.384 | 10460.184 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling at A051 to A052 and also at Valard yard; Raking from A049 to A051 and from A053 to A052; Brushing both sides of rail tracks at A053; Culverts Installed on Beck Rd. from Hwy 9 |  |  | Beck Road East | 0 |  |  | 10 | 43795 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58120191122-4Grinder - 4710 Peterson or equal12.59256.8 | Corbiere and Sons Contracting58120191122-4Grinder - 4710 Peterson or equal12.59256.8Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 9256.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 581 | 20191122-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 25 | HR | 114.75 | 3 |  |  | 4169.25 | 542.0025 | 4711.2525 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling at A051 to A052 and also at Valard yard; Raking from A049 to A051 and from A053 to A052; Brushing both sides of rail tracks at A053; Culverts Installed on Beck Rd. from Hwy 9 |  |  | Beck Road East | 0 |  |  | 10 | 43795 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58120191122-4Log Loader254169.25 | Corbiere and Sons Contracting58120191122-4Log Loader254169.25Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4169.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 581 | 20191122-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 4 | Day |  | 0 |  |  | 480 | 62.4 | 542.4 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling at A051 to A052 and also at Valard yard; Raking from A049 to A051 and from A053 to A052; Brushing both sides of rail tracks at A053; Culverts Installed on Beck Rd. from Hwy 9 |  |  | Beck Road East | 0 |  |  | 10 | 43795 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58120191122-4Chainsaw and consummables4480 | Corbiere and Sons Contracting58120191122-4Chainsaw and consummables4480Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 581 | 20191122-4 | 53510111 | Access | 0 | Dozer D6 or equal | 135 |  | HR | 101.25 | 9 |  |  | 911.25 | 118.4625 | 1029.7125 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling at A051 to A052 and also at Valard yard; Raking from A049 to A051 and from A053 to A052; Brushing both sides of rail tracks at A053; Culverts Installed on Beck Rd. from Hwy 9 |  |  | Beck Road East | 0 |  |  | 10 | 43795 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58120191122-4Dozer D6 or equal911.25 | Corbiere and Sons Contracting58120191122-4Dozer D6 or equal911.25Inv#004-R02 | [5 empty] | 1 | 911.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 581 | 20191122-4 | 53520102 | Clearing | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling at A051 to A052 and also at Valard yard; Raking from A049 to A051 and from A053 to A052; Brushing both sides of rail tracks at A053; Culverts Installed on Beck Rd. from Hwy 9 |  |  | Beck Road East | 0 |  |  | 10 | 43795 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58120191122-4Excavator - 30 ton91255.5 | Corbiere and Sons Contracting58120191122-4Excavator - 30 ton91255.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 581 | 20191122-4 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 |  | HR | 128.25 | 9 |  |  | 1154.25 | 150.0525 | 1304.3025 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling at A051 to A052 and also at Valard yard; Raking from A049 to A051 and from A053 to A052; Brushing both sides of rail tracks at A053; Culverts Installed on Beck Rd. from Hwy 9 |  |  | Beck Road East | 0 |  |  | 10 | 43795 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58120191122-4Excavator - 36 ton1154.25 | Corbiere and Sons Contracting58120191122-4Excavator - 36 ton1154.25Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1154.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 581 | 20191122-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling at A051 to A052 and also at Valard yard; Raking from A049 to A051 and from A053 to A052; Brushing both sides of rail tracks at A053; Culverts Installed on Beck Rd. from Hwy 9 |  |  | Beck Road East | 0 |  |  | 10 | 43795 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58120191122-4Light Truck - Pick up30900 | Corbiere and Sons Contracting58120191122-4Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 581 | 20191122-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling at A051 to A052 and also at Valard yard; Raking from A049 to A051 and from A053 to A052; Brushing both sides of rail tracks at A053; Culverts Installed on Beck Rd. from Hwy 9 |  |  | Beck Road East | 0 |  |  | 10 | 43795 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58120191122-4Light Truck - Pick up20600 | Corbiere and Sons Contracting58120191122-4Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 581 | 20191122-4 | 53520102 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  |  | 0 | 570 | 74.1 | 644.1 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling at A051 to A052 and also at Valard yard; Raking from A049 to A051 and from A053 to A052; Brushing both sides of rail tracks at A053; Culverts Installed on Beck Rd. from Hwy 9 |  |  | Beck Road East | 0 |  |  | 10 | 43795 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58120191122-4Foreman6570 | Corbiere and Sons Contracting58120191122-4Foreman6570Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 581 | 20191122-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 4 | HR |  |  |  | 0 | 360 | 46.8 | 406.8 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling at A051 to A052 and also at Valard yard; Raking from A049 to A051 and from A053 to A052; Brushing both sides of rail tracks at A053; Culverts Installed on Beck Rd. from Hwy 9 |  |  | Beck Road East | 0 |  |  | 10 | 43795 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58120191122-4Operator - Principle4360 | Corbiere and Sons Contracting58120191122-4Operator - Principle4360Inv#004-R02 | [5 empty] | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 581 | 20191122-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 48 | HR |  |  |  | 0 | 4320 | 561.6 | 4881.6 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling at A051 to A052 and also at Valard yard; Raking from A049 to A051 and from A053 to A052; Brushing both sides of rail tracks at A053; Culverts Installed on Beck Rd. from Hwy 9 |  |  | Beck Road East | 0 |  |  | 10 | 43795 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58120191122-4Operator - Principle484320 | Corbiere and Sons Contracting58120191122-4Operator - Principle484320Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 581 | 20191122-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 40 | HR |  |  |  | 0 | 3000 | 390 | 3390 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling at A051 to A052 and also at Valard yard; Raking from A049 to A051 and from A053 to A052; Brushing both sides of rail tracks at A053; Culverts Installed on Beck Rd. from Hwy 9 |  |  | Beck Road East | 0 |  |  | 10 | 43795 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58120191122-4Labourer - Specialized403000 | Corbiere and Sons Contracting58120191122-4Labourer - Specialized403000Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 3000 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 581 | 20191122-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling at A051 to A052 and also at Valard yard; Raking from A049 to A051 and from A053 to A052; Brushing both sides of rail tracks at A053; Culverts Installed on Beck Rd. from Hwy 9 |  |  | Beck Road East | 0 |  |  | 10 | 43795 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58120191122-4L.O.A.51050 | Corbiere and Sons Contracting58120191122-4L.O.A.51050Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 581 | 20191122-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-25 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Hand Felling at A051 to A052 and also at Valard yard; Raking from A049 to A051 and from A053 to A052; Brushing both sides of rail tracks at A053; Culverts Installed on Beck Rd. from Hwy 9 |  |  | Beck Road East | 0 |  |  | 10 | 43795 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58120191122-4L.O.A.4840 | Corbiere and Sons Contracting58120191122-4L.O.A.4840Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 582 | 20191123-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting58220191123-1Light Truck - Pick up501500 | Corbiere and Sons Contracting58220191123-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 582 | 20191123-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting58220191123-1Project Manager121320 | Corbiere and Sons Contracting58220191123-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 582 | 20191123-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting58220191123-1Superintendent121260 | Corbiere and Sons Contracting58220191123-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 582 | 20191123-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting58220191123-1Project Coordinator12960 | Corbiere and Sons Contracting58220191123-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 582 | 20191123-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting58220191123-1Safety Advisor121020 | Corbiere and Sons Contracting58220191123-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 582 | 20191123-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting58220191123-1Project Controls12840 | Corbiere and Sons Contracting58220191123-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 582 | 20191123-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting58220191123-1L.O.A.51050 | Corbiere and Sons Contracting58220191123-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 583 | 20191123-2-R1 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 74.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance; Float Truck broke down at 12:30; Orientation; Sander on SB; |  |  | Yard Maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting58320191123-2-R1Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting58320191123-2-R1Loader JD 524 to 624 or equal5495Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 583 | 20191123-2-R1 | 53520101 | Clearing | 0 | Sander Truck | 112.5 | 5 | HR | 84.38 |  |  |  | 562.5 | 73.125 | 635.625 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance; Float Truck broke down at 12:30; Orientation; Sander on SB; |  |  | Yard Maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting58320191123-2-R1Sander Truck5562.5 | Corbiere and Sons Contracting58320191123-2-R1Sander Truck5562.5Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 562.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 583 | 20191123-2-R1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance; Float Truck broke down at 12:30; Orientation; Sander on SB; |  |  | Yard Maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting58320191123-2-R1Light Truck - Pick up10300 | Corbiere and Sons Contracting58320191123-2-R1Light Truck - Pick up10300Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 583 | 20191123-2-R1 | 53520101 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 5 | HR | 101.25 | 0 |  |  | 675 | 87.75 | 762.75 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance; Float Truck broke down at 12:30; Orientation; Sander on SB; |  |  | Yard Maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting58320191123-2-R1Tractor Trailer - 60 Ton5675 | Corbiere and Sons Contracting58320191123-2-R1Tractor Trailer - 60 Ton5675Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 583 | 20191123-2-R1 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 5 | HR |  |  |  | 0 | 450 | 58.5 | 508.5 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance; Float Truck broke down at 12:30; Orientation; Sander on SB; |  |  | Yard Maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting58320191123-2-R1Operator - Principle5450 | Corbiere and Sons Contracting58320191123-2-R1Operator - Principle5450Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 583 | 20191123-2-R1 | 53520101 | Clearing | 0 | Operator - Intermdiate | 75 | 20 | HR |  |  | 70 | 0 | 1500 | 195 | 1695 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance; Float Truck broke down at 12:30; Orientation; Sander on SB; |  |  | Yard Maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting58320191123-2-R1Operator - Intermdiate201500 | Corbiere and Sons Contracting58320191123-2-R1Operator - Intermdiate201500Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 583 | 20191123-2-R1 | 53520101 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance; Float Truck broke down at 12:30; Orientation; Sander on SB; |  |  | Yard Maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting58320191123-2-R1Labourer - General10650 | Corbiere and Sons Contracting58320191123-2-R1Labourer - General10650Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 583 | 20191123-2-R1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance; Float Truck broke down at 12:30; Orientation; Sander on SB; |  |  | Yard Maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting58320191123-2-R1L.O.A.3630 | Corbiere and Sons Contracting58320191123-2-R1L.O.A.3630Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 584 | 20191123-3 | 53520102 | Clearing | 0 | Brusher | 202.5 |  | HR | 151.88 | 9 |  |  | 1366.92 | 177.6996 | 1544.6196 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fueling, flagging for Valard, float moves; Raking and fixing of AU2 road; Grading of Eldorado and then moved to Ouimet rd. |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58420191123-3Brusher1366.92 | Corbiere and Sons Contracting58420191123-3Brusher1366.92Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1366.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 584 | 20191123-3 | 53520102 | Clearing | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fueling, flagging for Valard, float moves; Raking and fixing of AU2 road; Grading of Eldorado and then moved to Ouimet rd. |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58420191123-3Excavator - 30 ton91255.5 | Corbiere and Sons Contracting58420191123-3Excavator - 30 ton91255.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 584 | 20191123-3 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 |  | HR | 128.25 | 9 |  |  | 1154.25 | 150.0525 | 1304.3025 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fueling, flagging for Valard, float moves; Raking and fixing of AU2 road; Grading of Eldorado and then moved to Ouimet rd. |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58420191123-3Excavator - 36 ton1154.25 | Corbiere and Sons Contracting58420191123-3Excavator - 36 ton1154.25Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1154.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 584 | 20191123-3 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fueling, flagging for Valard, float moves; Raking and fixing of AU2 road; Grading of Eldorado and then moved to Ouimet rd. |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58420191123-3Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting58420191123-3Grader - Cat 12 to 14 or equal91134Inv#004-R02 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 584 | 20191123-3 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fueling, flagging for Valard, float moves; Raking and fixing of AU2 road; Grading of Eldorado and then moved to Ouimet rd. |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58420191123-3Light Truck - Pick up10300 | Corbiere and Sons Contracting58420191123-3Light Truck - Pick up10300Inv#004-R02 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 584 | 20191123-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fueling, flagging for Valard, float moves; Raking and fixing of AU2 road; Grading of Eldorado and then moved to Ouimet rd. |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58420191123-3Light Truck - Pick up10300 | Corbiere and Sons Contracting58420191123-3Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 584 | 20191123-3 | 53510111 | Access | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fueling, flagging for Valard, float moves; Raking and fixing of AU2 road; Grading of Eldorado and then moved to Ouimet rd. |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58420191123-3Foreman4380 | Corbiere and Sons Contracting58420191123-3Foreman4380Inv#004-R02 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 584 | 20191123-3 | 53520102 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fueling, flagging for Valard, float moves; Raking and fixing of AU2 road; Grading of Eldorado and then moved to Ouimet rd. |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58420191123-3Foreman4380 | Corbiere and Sons Contracting58420191123-3Foreman4380Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 584 | 20191123-3 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fueling, flagging for Valard, float moves; Raking and fixing of AU2 road; Grading of Eldorado and then moved to Ouimet rd. |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58420191123-3Operator - Principle11990 | Corbiere and Sons Contracting58420191123-3Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 584 | 20191123-3 | 53510111 | Access | 0 | Labourer - Specialized | 75 | 3 | HR |  |  |  | 0 | 225 | 29.25 | 254.25 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fueling, flagging for Valard, float moves; Raking and fixing of AU2 road; Grading of Eldorado and then moved to Ouimet rd. |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58420191123-3Labourer - Specialized3225 | Corbiere and Sons Contracting58420191123-3Labourer - Specialized3225Inv#004-R02 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 584 | 20191123-3 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 4 | HR |  |  |  | 0 | 300 | 39 | 339 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fueling, flagging for Valard, float moves; Raking and fixing of AU2 road; Grading of Eldorado and then moved to Ouimet rd. |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58420191123-3Labourer - Specialized4300 | Corbiere and Sons Contracting58420191123-3Labourer - Specialized4300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 584 | 20191123-3 | 53520102 | Clearing | 0 | Labourer - General | 65 | 6 | HR |  |  |  | 0 | 390 | 50.7 | 440.7 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fueling, flagging for Valard, float moves; Raking and fixing of AU2 road; Grading of Eldorado and then moved to Ouimet rd. |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58420191123-3Labourer - General6390 | Corbiere and Sons Contracting58420191123-3Labourer - General6390Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 390 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 584 | 20191123-3 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fueling, flagging for Valard, float moves; Raking and fixing of AU2 road; Grading of Eldorado and then moved to Ouimet rd. |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58420191123-3L.O.A.1210 | Corbiere and Sons Contracting58420191123-3L.O.A.1210Inv#004-R02 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 584 | 20191123-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fueling, flagging for Valard, float moves; Raking and fixing of AU2 road; Grading of Eldorado and then moved to Ouimet rd. |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58420191123-3L.O.A.1210 | Corbiere and Sons Contracting58420191123-3L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 585 | 20191123-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at wetland between A051 and A052 |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58520191123-4Brusher91822.5 | Corbiere and Sons Contracting58520191123-4Brusher91822.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 585 | 20191123-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 16.5 | HR | 417.6 | 1.5 |  |  | 9813.6 | 1275.768 | 11089.368 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at wetland between A051 and A052 |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58520191123-4Grinder - 4710 Peterson or equal16.59813.6 | Corbiere and Sons Contracting58520191123-4Grinder - 4710 Peterson or equal16.59813.6Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 9813.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 585 | 20191123-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at wetland between A051 and A052 |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58520191123-4Log Loader182754 | Corbiere and Sons Contracting58520191123-4Log Loader182754Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 585 | 20191123-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 5 | Day |  | 0 |  |  | 600 | 78 | 678 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at wetland between A051 and A052 |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58520191123-4Chainsaw and consummables5600 | Corbiere and Sons Contracting58520191123-4Chainsaw and consummables5600Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 585 | 20191123-4 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 10 | HR | 101.25 | 9 |  |  | 2261.25 | 293.9625 | 2555.2125 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at wetland between A051 and A052 |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58520191123-4Dozer D6 or equal102261.25 | Corbiere and Sons Contracting58520191123-4Dozer D6 or equal102261.25Inv#004-R02 | [5 empty] | 1 | 2261.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 585 | 20191123-4 | 53520102 | Clearing | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at wetland between A051 and A052 |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58520191123-4Excavator - 30 ton91255.5 | Corbiere and Sons Contracting58520191123-4Excavator - 30 ton91255.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 585 | 20191123-4 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 4.5 | HR | 128.25 | 0 |  |  | 769.5 | 100.035 | 869.535 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at wetland between A051 and A052 |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58520191123-4Excavator - 36 ton4.5769.5 | Corbiere and Sons Contracting58520191123-4Excavator - 36 ton4.5769.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 769.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 585 | 20191123-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at wetland between A051 and A052 |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58520191123-4Light Truck - Pick up30900 | Corbiere and Sons Contracting58520191123-4Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 585 | 20191123-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at wetland between A051 and A052 |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58520191123-4Light Truck - Pick up20600 | Corbiere and Sons Contracting58520191123-4Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 585 | 20191123-4 | 53520102 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  |  | 0 | 570 | 74.1 | 644.1 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at wetland between A051 and A052 |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58520191123-4Foreman6570 | Corbiere and Sons Contracting58520191123-4Foreman6570Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 585 | 20191123-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 19 | HR |  |  |  | 0 | 1710 | 222.3 | 1932.3 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at wetland between A051 and A052 |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58520191123-4Operator - Principle191710 | Corbiere and Sons Contracting58520191123-4Operator - Principle191710Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1710 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 585 | 20191123-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at wetland between A051 and A052 |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58520191123-4Operator - Principle11990 | Corbiere and Sons Contracting58520191123-4Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 585 | 20191123-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at wetland between A051 and A052 |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58520191123-4Operator - Principle221980 | Corbiere and Sons Contracting58520191123-4Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 585 | 20191123-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 55 | HR |  |  |  | 0 | 4125 | 536.25 | 4661.25 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at wetland between A051 and A052 |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58520191123-4Labourer - Specialized554125 | Corbiere and Sons Contracting58520191123-4Labourer - Specialized554125Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 4125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 585 | 20191123-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at wetland between A051 and A052 |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58520191123-4L.O.A.61260 | Corbiere and Sons Contracting58520191123-4L.O.A.61260Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 585 | 20191123-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at wetland between A051 and A052 |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting58520191123-4L.O.A.51050 | Corbiere and Sons Contracting58520191123-4L.O.A.51050Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 586 | 20191123-5-R1 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 36 | HR | 180 | 9 |  |  | 10260 | 1333.8 | 11593.8 | 2019-11-27 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves of Feller Bunchers and Skidders - Mulcher on SB; Required to walk in equipment 8.8 KMs from base of hill; Cutting W of A116, Cutting E of A111; Skidders at A111; |  |  | Wind Farm | 0 |  |  | 40 | 43967 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting58620191123-5-R1Feller Buncher3610260 | Corbiere and Sons Contracting58620191123-5-R1Feller Buncher3610260INV#027 |  |  | WF1-Merchantable Clearing |  |  | 1 | 10260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 586 | 20191123-5-R1 | 53520101 | Clearing | 0 | Mulcher | 205 |  | HR | 153.75 | 9 |  |  | 1383.75 | 179.8875 | 1563.6375 | 2019-11-27 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves of Feller Bunchers and Skidders - Mulcher on SB; Required to walk in equipment 8.8 KMs from base of hill; Cutting W of A116, Cutting E of A111; Skidders at A111; |  |  | Wind Farm | 0 |  |  | 40 | 43967 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting58620191123-5-R1Mulcher1383.75 | Corbiere and Sons Contracting58620191123-5-R1Mulcher1383.75INV#027 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1383.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 586 | 20191123-5-R1 | 53520101 | Clearing | 0 | Skidder | 171 | 18 | HR | 128.25 | 18 |  |  | 5386.5 | 700.245 | 6086.745 | 2019-11-27 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves of Feller Bunchers and Skidders - Mulcher on SB; Required to walk in equipment 8.8 KMs from base of hill; Cutting W of A116, Cutting E of A111; Skidders at A111; |  |  | Wind Farm | 0 |  |  | 40 | 43967 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting58620191123-5-R1Skidder 185386.5 | Corbiere and Sons Contracting58620191123-5-R1Skidder 185386.5INV#027 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5386.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 586 | 20191123-5-R1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-11-27 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves of Feller Bunchers and Skidders - Mulcher on SB; Required to walk in equipment 8.8 KMs from base of hill; Cutting W of A116, Cutting E of A111; Skidders at A111; |  |  | Wind Farm | 0 |  |  | 40 | 43967 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting58620191123-5-R1Light Truck - Pick up601800 | Corbiere and Sons Contracting58620191123-5-R1Light Truck - Pick up601800INV#027 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 586 | 20191123-5-R1 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-11-27 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves of Feller Bunchers and Skidders - Mulcher on SB; Required to walk in equipment 8.8 KMs from base of hill; Cutting W of A116, Cutting E of A111; Skidders at A111; |  |  | Wind Farm | 0 |  |  | 40 | 43967 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting58620191123-5-R1Foreman4380 | Corbiere and Sons Contracting58620191123-5-R1Foreman4380INV#027 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 586 | 20191123-5-R1 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 74 | HR |  |  |  | 0 | 6660 | 865.8 | 7525.8 | 2019-11-27 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves of Feller Bunchers and Skidders - Mulcher on SB; Required to walk in equipment 8.8 KMs from base of hill; Cutting W of A116, Cutting E of A111; Skidders at A111; |  |  | Wind Farm | 0 |  |  | 40 | 43967 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting58620191123-5-R1Operator - Principle746660 | Corbiere and Sons Contracting58620191123-5-R1Operator - Principle746660INV#027 |  |  | WF1-Merchantable Clearing |  |  | 1 | 6660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 586 | 20191123-5-R1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-11-27 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves of Feller Bunchers and Skidders - Mulcher on SB; Required to walk in equipment 8.8 KMs from base of hill; Cutting W of A116, Cutting E of A111; Skidders at A111; |  |  | Wind Farm | 0 |  |  | 40 | 43967 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting58620191123-5-R1L.O.A.71470 | Corbiere and Sons Contracting58620191123-5-R1L.O.A.71470INV#027 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 587 | 20191124-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting58720191124-1Light Truck - Pick up501500 | Corbiere and Sons Contracting58720191124-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 587 | 20191124-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting58720191124-1Project Manager121320 | Corbiere and Sons Contracting58720191124-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 587 | 20191124-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting58720191124-1Superintendent121260 | Corbiere and Sons Contracting58720191124-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 587 | 20191124-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting58720191124-1Project Coordinator12960 | Corbiere and Sons Contracting58720191124-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 587 | 20191124-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting58720191124-1Safety Advisor121020 | Corbiere and Sons Contracting58720191124-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 587 | 20191124-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting58720191124-1Project Controls12840 | Corbiere and Sons Contracting58720191124-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 587 | 20191124-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting58720191124-1L.O.A.51050 | Corbiere and Sons Contracting58720191124-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 588 | 20191124-2-R1 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 74.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves; Buncher from Beck to Ouimet Road, Valard EX from Shuniah to Beck, Valard EX from MacKenzie to Beck, 2 skidders from Eldorado to Ouimet Canyon; Yard care |  |  | Yard Maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting58820191124-2-R1Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting58820191124-2-R1Loader JD 524 to 624 or equal5495Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 588 | 20191124-2-R1 | 53520101 | Clearing | 0 | Sander Truck | 112.5 | 5 | HR | 84.38 |  |  |  | 562.5 | 73.125 | 635.625 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves; Buncher from Beck to Ouimet Road, Valard EX from Shuniah to Beck, Valard EX from MacKenzie to Beck, 2 skidders from Eldorado to Ouimet Canyon; Yard care |  |  | Yard Maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting58820191124-2-R1Sander Truck5562.5 | Corbiere and Sons Contracting58820191124-2-R1Sander Truck5562.5Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 562.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 588 | 20191124-2-R1 | 53520101 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves; Buncher from Beck to Ouimet Road, Valard EX from Shuniah to Beck, Valard EX from MacKenzie to Beck, 2 skidders from Eldorado to Ouimet Canyon; Yard care |  |  | Yard Maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting58820191124-2-R1Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting58820191124-2-R1Tractor Trailer - 60 Ton101350Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 588 | 20191124-2-R1 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 0 | HR |  |  |  | 0 | 0 | 0 | 0 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves; Buncher from Beck to Ouimet Road, Valard EX from Shuniah to Beck, Valard EX from MacKenzie to Beck, 2 skidders from Eldorado to Ouimet Canyon; Yard care |  |  | Yard Maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting58820191124-2-R1Operator - Principle00 | Corbiere and Sons Contracting58820191124-2-R1Operator - Principle00Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 0 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 588 | 20191124-2-R1 | 53520101 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves; Buncher from Beck to Ouimet Road, Valard EX from Shuniah to Beck, Valard EX from MacKenzie to Beck, 2 skidders from Eldorado to Ouimet Canyon; Yard care |  |  | Yard Maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting58820191124-2-R1Operator - Intermdiate11825 | Corbiere and Sons Contracting58820191124-2-R1Operator - Intermdiate11825Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 588 | 20191124-2-R1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves; Buncher from Beck to Ouimet Road, Valard EX from Shuniah to Beck, Valard EX from MacKenzie to Beck, 2 skidders from Eldorado to Ouimet Canyon; Yard care |  |  | Yard Maintenance | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting58820191124-2-R1L.O.A.2420 | Corbiere and Sons Contracting58820191124-2-R1L.O.A.2420Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 589 | 20191124-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 2.5 | HR | 151.88 | 0 |  |  | 506.25 | 65.8125 | 572.0625 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers Flagging for Valard and Corbiere float moves; fueling, culverts; Rd. Building and Raking at A055 and A056; Brushing at AU2 Access Road; |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58920191124-3Brusher2.5506.25 | Corbiere and Sons Contracting58920191124-3Brusher2.5506.25Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 506.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 589 | 20191124-3 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers Flagging for Valard and Corbiere float moves; fueling, culverts; Rd. Building and Raking at A055 and A056; Brushing at AU2 Access Road; |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58920191124-3Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting58920191124-3Grader - Cat 12 to 14 or equal91134Inv#004-R02 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 589 | 20191124-3 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers Flagging for Valard and Corbiere float moves; fueling, culverts; Rd. Building and Raking at A055 and A056; Brushing at AU2 Access Road; |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58920191124-3Light Truck - Pick up10300 | Corbiere and Sons Contracting58920191124-3Light Truck - Pick up10300Inv#004-R02 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 589 | 20191124-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers Flagging for Valard and Corbiere float moves; fueling, culverts; Rd. Building and Raking at A055 and A056; Brushing at AU2 Access Road; |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58920191124-3Light Truck - Pick up20600 | Corbiere and Sons Contracting58920191124-3Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 589 | 20191124-3 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  |  | 380 | 49.4 | 429.4 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers Flagging for Valard and Corbiere float moves; fueling, culverts; Rd. Building and Raking at A055 and A056; Brushing at AU2 Access Road; |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58920191124-3Foreman4380 | Corbiere and Sons Contracting58920191124-3Foreman4380Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 589 | 20191124-3 | 53520102 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers Flagging for Valard and Corbiere float moves; fueling, culverts; Rd. Building and Raking at A055 and A056; Brushing at AU2 Access Road; |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58920191124-3Foreman4380 | Corbiere and Sons Contracting58920191124-3Foreman4380Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 589 | 20191124-3 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers Flagging for Valard and Corbiere float moves; fueling, culverts; Rd. Building and Raking at A055 and A056; Brushing at AU2 Access Road; |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58920191124-3Operator - Principle11990 | Corbiere and Sons Contracting58920191124-3Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 589 | 20191124-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers Flagging for Valard and Corbiere float moves; fueling, culverts; Rd. Building and Raking at A055 and A056; Brushing at AU2 Access Road; |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58920191124-3Operator - Principle11990 | Corbiere and Sons Contracting58920191124-3Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 589 | 20191124-3 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 5 | HR |  |  |  | 0 | 375 | 48.75 | 423.75 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers Flagging for Valard and Corbiere float moves; fueling, culverts; Rd. Building and Raking at A055 and A056; Brushing at AU2 Access Road; |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58920191124-3Labourer - Specialized5375 | Corbiere and Sons Contracting58920191124-3Labourer - Specialized5375Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 589 | 20191124-3 | 53520101 | Clearing | 0 | Labourer - General | 65 | 33 | HR |  |  |  | 0 | 2145 | 278.85 | 2423.85 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers Flagging for Valard and Corbiere float moves; fueling, culverts; Rd. Building and Raking at A055 and A056; Brushing at AU2 Access Road; |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58920191124-3Labourer - General332145 | Corbiere and Sons Contracting58920191124-3Labourer - General332145Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2145 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 589 | 20191124-3 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers Flagging for Valard and Corbiere float moves; fueling, culverts; Rd. Building and Raking at A055 and A056; Brushing at AU2 Access Road; |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58920191124-3L.O.A.1210 | Corbiere and Sons Contracting58920191124-3L.O.A.1210Inv#004-R02 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 589 | 20191124-3 | 53520101 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers Flagging for Valard and Corbiere float moves; fueling, culverts; Rd. Building and Raking at A055 and A056; Brushing at AU2 Access Road; |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58920191124-3L.O.A.1210 | Corbiere and Sons Contracting58920191124-3L.O.A.1210Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 589 | 20191124-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers Flagging for Valard and Corbiere float moves; fueling, culverts; Rd. Building and Raking at A055 and A056; Brushing at AU2 Access Road; |  |  | Eldorado Road | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting58920191124-3L.O.A.2420 | Corbiere and Sons Contracting58920191124-3L.O.A.2420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 590 | 20191124-4 | 53520101 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling between A051 and A052; Grinding material at towers A047 to A054; Raking West from A053; Brushing from A053; Building of Access Road at A048; Charlie started at 6am and fueled trucks |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59020191124-4Brusher91822.5 | Corbiere and Sons Contracting59020191124-4Brusher91822.5Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 590 | 20191124-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling between A051 and A052; Grinding material at towers A047 to A054; Raking West from A053; Brushing from A053; Building of Access Road at A048; Charlie started at 6am and fueled trucks |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59020191124-4Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting59020191124-4Grinder - 4710 Peterson or equal1810022.4Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 590 | 20191124-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling between A051 and A052; Grinding material at towers A047 to A054; Raking West from A053; Brushing from A053; Building of Access Road at A048; Charlie started at 6am and fueled trucks |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59020191124-4Log Loader182754 | Corbiere and Sons Contracting59020191124-4Log Loader182754Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 590 | 20191124-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 6 | Day |  | 0 |  |  | 720 | 93.6 | 813.6 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling between A051 and A052; Grinding material at towers A047 to A054; Raking West from A053; Brushing from A053; Building of Access Road at A048; Charlie started at 6am and fueled trucks |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59020191124-4Chainsaw and consummables6720 | Corbiere and Sons Contracting59020191124-4Chainsaw and consummables6720Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 590 | 20191124-4 | 53520102 | Clearing | 0 | Excavator - 30 ton | 139.5 | 7 | HR | 104.63 | 0 |  |  | 976.5 | 126.945 | 1103.445 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling between A051 and A052; Grinding material at towers A047 to A054; Raking West from A053; Brushing from A053; Building of Access Road at A048; Charlie started at 6am and fueled trucks |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59020191124-4Excavator - 30 ton7976.5 | Corbiere and Sons Contracting59020191124-4Excavator - 30 ton7976.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 976.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 590 | 20191124-4 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling between A051 and A052; Grinding material at towers A047 to A054; Raking West from A053; Brushing from A053; Building of Access Road at A048; Charlie started at 6am and fueled trucks |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59020191124-4Excavator - 36 ton91539 | Corbiere and Sons Contracting59020191124-4Excavator - 36 ton91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 590 | 20191124-4 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling between A051 and A052; Grinding material at towers A047 to A054; Raking West from A053; Brushing from A053; Building of Access Road at A048; Charlie started at 6am and fueled trucks |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59020191124-4Light Truck - Pick up10300 | Corbiere and Sons Contracting59020191124-4Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 590 | 20191124-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling between A051 and A052; Grinding material at towers A047 to A054; Raking West from A053; Brushing from A053; Building of Access Road at A048; Charlie started at 6am and fueled trucks |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59020191124-4Light Truck - Pick up20600 | Corbiere and Sons Contracting59020191124-4Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 590 | 20191124-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling between A051 and A052; Grinding material at towers A047 to A054; Raking West from A053; Brushing from A053; Building of Access Road at A048; Charlie started at 6am and fueled trucks |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59020191124-4Light Truck - Pick up30900 | Corbiere and Sons Contracting59020191124-4Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 590 | 20191124-4 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling between A051 and A052; Grinding material at towers A047 to A054; Raking West from A053; Brushing from A053; Building of Access Road at A048; Charlie started at 6am and fueled trucks |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59020191124-4Foreman121140 | Corbiere and Sons Contracting59020191124-4Foreman121140Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 590 | 20191124-4 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 6 | HR |  |  |  | 0 | 540 | 70.2 | 610.2 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling between A051 and A052; Grinding material at towers A047 to A054; Raking West from A053; Brushing from A053; Building of Access Road at A048; Charlie started at 6am and fueled trucks |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59020191124-4Operator - Principle6540 | Corbiere and Sons Contracting59020191124-4Operator - Principle6540Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 540 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 590 | 20191124-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling between A051 and A052; Grinding material at towers A047 to A054; Raking West from A053; Brushing from A053; Building of Access Road at A048; Charlie started at 6am and fueled trucks |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59020191124-4Operator - Principle221980 | Corbiere and Sons Contracting59020191124-4Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 590 | 20191124-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 20.5 | HR |  |  |  | 0 | 1845 | 239.85 | 2084.85 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling between A051 and A052; Grinding material at towers A047 to A054; Raking West from A053; Brushing from A053; Building of Access Road at A048; Charlie started at 6am and fueled trucks |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59020191124-4Operator - Principle20.51845 | Corbiere and Sons Contracting59020191124-4Operator - Principle20.51845Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 590 | 20191124-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 55 | HR |  |  |  | 0 | 4125 | 536.25 | 4661.25 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling between A051 and A052; Grinding material at towers A047 to A054; Raking West from A053; Brushing from A053; Building of Access Road at A048; Charlie started at 6am and fueled trucks |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59020191124-4Labourer - Specialized554125 | Corbiere and Sons Contracting59020191124-4Labourer - Specialized554125Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 4125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 590 | 20191124-4 | 53520101 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling between A051 and A052; Grinding material at towers A047 to A054; Raking West from A053; Brushing from A053; Building of Access Road at A048; Charlie started at 6am and fueled trucks |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59020191124-4L.O.A.1210 | Corbiere and Sons Contracting59020191124-4L.O.A.1210Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 590 | 20191124-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling between A051 and A052; Grinding material at towers A047 to A054; Raking West from A053; Brushing from A053; Building of Access Road at A048; Charlie started at 6am and fueled trucks |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59020191124-4L.O.A.3630 | Corbiere and Sons Contracting59020191124-4L.O.A.3630Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 590 | 20191124-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling between A051 and A052; Grinding material at towers A047 to A054; Raking West from A053; Brushing from A053; Building of Access Road at A048; Charlie started at 6am and fueled trucks |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59020191124-4L.O.A.61260 | Corbiere and Sons Contracting59020191124-4L.O.A.61260Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 591 | 20191124-5-R1 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 18 | HR | 180 | 0 |  |  | 4320 | 561.6 | 4881.6 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Finish cutting from A116 to A115 into retainment area; Cutting from A111 Westward into retainment area; Float move for Lionel Roy and then walked into A107 |  |  | Wind Farm | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting59120191124-5-R1Feller Buncher184320 | Corbiere and Sons Contracting59120191124-5-R1Feller Buncher184320Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 591 | 20191124-5-R1 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 18 | HR | 180 | 0 |  |  | 4320 | 561.6 | 4881.6 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Finish cutting from A116 to A115 into retainment area; Cutting from A111 Westward into retainment area; Float move for Lionel Roy and then walked into A107 |  |  | Wind Farm | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting59120191124-5-R1Feller Buncher184320 | Corbiere and Sons Contracting59120191124-5-R1Feller Buncher184320Inv#069 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 591 | 20191124-5-R1 | 53520102 | Clearing | 0 | Mulcher | 205 |  | HR | 153.75 | 9 |  |  | 1383.75 | 179.8875 | 1563.6375 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Finish cutting from A116 to A115 into retainment area; Cutting from A111 Westward into retainment area; Float move for Lionel Roy and then walked into A107 |  |  | Wind Farm | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting59120191124-5-R1Mulcher1383.75 | Corbiere and Sons Contracting59120191124-5-R1Mulcher1383.75Inv#069 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1383.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 591 | 20191124-5-R1 | 53520102 | Clearing | 0 | Skidder | 171 |  | HR | 128.25 | 9 |  |  | 1154.25 | 150.0525 | 1304.3025 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Finish cutting from A116 to A115 into retainment area; Cutting from A111 Westward into retainment area; Float move for Lionel Roy and then walked into A107 |  |  | Wind Farm | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting59120191124-5-R1Skidder 1154.25 | Corbiere and Sons Contracting59120191124-5-R1Skidder 1154.25Inv#069 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1154.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 591 | 20191124-5-R1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Finish cutting from A116 to A115 into retainment area; Cutting from A111 Westward into retainment area; Float move for Lionel Roy and then walked into A107 |  |  | Wind Farm | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting59120191124-5-R1Light Truck - Pick up20600 | Corbiere and Sons Contracting59120191124-5-R1Light Truck - Pick up20600Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 591 | 20191124-5-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Finish cutting from A116 to A115 into retainment area; Cutting from A111 Westward into retainment area; Float move for Lionel Roy and then walked into A107 |  |  | Wind Farm | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting59120191124-5-R1Light Truck - Pick up10300 | Corbiere and Sons Contracting59120191124-5-R1Light Truck - Pick up10300Inv#069 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 591 | 20191124-5-R1 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 30 | HR |  |  |  | 0 | 2700 | 351 | 3051 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Finish cutting from A116 to A115 into retainment area; Cutting from A111 Westward into retainment area; Float move for Lionel Roy and then walked into A107 |  |  | Wind Farm | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting59120191124-5-R1Operator - Principle302700 | Corbiere and Sons Contracting59120191124-5-R1Operator - Principle302700Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 591 | 20191124-5-R1 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Finish cutting from A116 to A115 into retainment area; Cutting from A111 Westward into retainment area; Float move for Lionel Roy and then walked into A107 |  |  | Wind Farm | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting59120191124-5-R1Operator - Principle332970 | Corbiere and Sons Contracting59120191124-5-R1Operator - Principle332970Inv#069 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 591 | 20191124-5-R1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Finish cutting from A116 to A115 into retainment area; Cutting from A111 Westward into retainment area; Float move for Lionel Roy and then walked into A107 |  |  | Wind Farm | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting59120191124-5-R1L.O.A.3630 | Corbiere and Sons Contracting59120191124-5-R1L.O.A.3630Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 591 | 20191124-5-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Finish cutting from A116 to A115 into retainment area; Cutting from A111 Westward into retainment area; Float move for Lionel Roy and then walked into A107 |  |  | Wind Farm | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting59120191124-5-R1L.O.A.3630 | Corbiere and Sons Contracting59120191124-5-R1L.O.A.3630Inv#069 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 592 | 20191125-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting59220191125-1Light Truck - Pick up501500 | Corbiere and Sons Contracting59220191125-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 592 | 20191125-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting59220191125-1Project Manager121320 | Corbiere and Sons Contracting59220191125-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 592 | 20191125-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting59220191125-1Superintendent121260 | Corbiere and Sons Contracting59220191125-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 592 | 20191125-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting59220191125-1Project Coordinator12960 | Corbiere and Sons Contracting59220191125-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 592 | 20191125-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting59220191125-1Safety Advisor121020 | Corbiere and Sons Contracting59220191125-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 592 | 20191125-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting59220191125-1Project Controls12840 | Corbiere and Sons Contracting59220191125-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 592 | 20191125-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting59220191125-1L.O.A.51050 | Corbiere and Sons Contracting59220191125-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 593 | 20191125-2-R1 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 74.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Truck down all day; Yard Maintenance |  |  |  | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting59320191125-2-R1Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting59320191125-2-R1Loader JD 524 to 624 or equal5495Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 593 | 20191125-2-R1 | 53520101 | Clearing | 0 | Sander Truck | 112.5 | 5 | HR | 84.38 |  |  |  | 562.5 | 73.125 | 635.625 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Truck down all day; Yard Maintenance |  |  |  | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting59320191125-2-R1Sander Truck5562.5 | Corbiere and Sons Contracting59320191125-2-R1Sander Truck5562.5Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 562.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 593 | 20191125-2-R1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Truck down all day; Yard Maintenance |  |  |  | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting59320191125-2-R1Light Truck - Pick up10300 | Corbiere and Sons Contracting59320191125-2-R1Light Truck - Pick up10300Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 593 | 20191125-2-R1 | 53520101 | Clearing | 0 | Operator - Intermdiate | 75 | 12 | HR |  |  | 70 | 0 | 900 | 117 | 1017 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Truck down all day; Yard Maintenance |  |  |  | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting59320191125-2-R1Operator - Intermdiate12900 | Corbiere and Sons Contracting59320191125-2-R1Operator - Intermdiate12900Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 593 | 20191125-2-R1 | 53520101 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Truck down all day; Yard Maintenance |  |  |  | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting59320191125-2-R1Labourer - General10650 | Corbiere and Sons Contracting59320191125-2-R1Labourer - General10650Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 593 | 20191125-2-R1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-27 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Truck down all day; Yard Maintenance |  |  |  | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting59320191125-2-R1L.O.A.1210 | Corbiere and Sons Contracting59320191125-2-R1L.O.A.1210Inv#069 |  |  | WF1-Merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 594 | 20191125-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers fueled equipment, escorted grader, installed culverts; Raking, Brushing, Building Rd, stripping of ROW, Grading, all at A055 Westard and Eastward |  |  | Eldorado - A055 | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59420191125-3Brusher91822.5 | Corbiere and Sons Contracting59420191125-3Brusher91822.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 594 | 20191125-3 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 5 | HR | 101.25 | 0 |  |  | 675 | 87.75 | 762.75 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers fueled equipment, escorted grader, installed culverts; Raking, Brushing, Building Rd, stripping of ROW, Grading, all at A055 Westard and Eastward |  |  | Eldorado - A055 | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59420191125-3Dozer D6 or equal5675 | Corbiere and Sons Contracting59420191125-3Dozer D6 or equal5675Inv#004-R02 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 594 | 20191125-3 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers fueled equipment, escorted grader, installed culverts; Raking, Brushing, Building Rd, stripping of ROW, Grading, all at A055 Westard and Eastward |  |  | Eldorado - A055 | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59420191125-3Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting59420191125-3Grader - Cat 12 to 14 or equal91134Inv#004-R02 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 594 | 20191125-3 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers fueled equipment, escorted grader, installed culverts; Raking, Brushing, Building Rd, stripping of ROW, Grading, all at A055 Westard and Eastward |  |  | Eldorado - A055 | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59420191125-3Light Truck - Pick up10300 | Corbiere and Sons Contracting59420191125-3Light Truck - Pick up10300Inv#004-R02 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 594 | 20191125-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers fueled equipment, escorted grader, installed culverts; Raking, Brushing, Building Rd, stripping of ROW, Grading, all at A055 Westard and Eastward |  |  | Eldorado - A055 | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59420191125-3Light Truck - Pick up20600 | Corbiere and Sons Contracting59420191125-3Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 594 | 20191125-3 | 53510111 | Access | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers fueled equipment, escorted grader, installed culverts; Raking, Brushing, Building Rd, stripping of ROW, Grading, all at A055 Westard and Eastward |  |  | Eldorado - A055 | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59420191125-3Foreman4380 | Corbiere and Sons Contracting59420191125-3Foreman4380Inv#004-R02 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 594 | 20191125-3 | 53520102 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers fueled equipment, escorted grader, installed culverts; Raking, Brushing, Building Rd, stripping of ROW, Grading, all at A055 Westard and Eastward |  |  | Eldorado - A055 | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59420191125-3Foreman4380 | Corbiere and Sons Contracting59420191125-3Foreman4380Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 594 | 20191125-3 | 53510111 | Access | 0 | Operator - Principle | 90 | 6.5 | HR |  |  |  | 0 | 585 | 76.05 | 661.05 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers fueled equipment, escorted grader, installed culverts; Raking, Brushing, Building Rd, stripping of ROW, Grading, all at A055 Westard and Eastward |  |  | Eldorado - A055 | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59420191125-3Operator - Principle6.5585 | Corbiere and Sons Contracting59420191125-3Operator - Principle6.5585Inv#004-R02 | [5 empty] | 1 | 585 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 594 | 20191125-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers fueled equipment, escorted grader, installed culverts; Raking, Brushing, Building Rd, stripping of ROW, Grading, all at A055 Westard and Eastward |  |  | Eldorado - A055 | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59420191125-3Operator - Principle11990 | Corbiere and Sons Contracting59420191125-3Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 594 | 20191125-3 | 53510111 | Access | 0 | Labourer - Specialized | 75 | 4 | HR |  |  |  | 0 | 300 | 39 | 339 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers fueled equipment, escorted grader, installed culverts; Raking, Brushing, Building Rd, stripping of ROW, Grading, all at A055 Westard and Eastward |  |  | Eldorado - A055 | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59420191125-3Labourer - Specialized4300 | Corbiere and Sons Contracting59420191125-3Labourer - Specialized4300Inv#004-R02 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 594 | 20191125-3 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 4 | HR |  |  |  | 0 | 300 | 39 | 339 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers fueled equipment, escorted grader, installed culverts; Raking, Brushing, Building Rd, stripping of ROW, Grading, all at A055 Westard and Eastward |  |  | Eldorado - A055 | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59420191125-3Labourer - Specialized4300 | Corbiere and Sons Contracting59420191125-3Labourer - Specialized4300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 594 | 20191125-3 | 53520102 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers fueled equipment, escorted grader, installed culverts; Raking, Brushing, Building Rd, stripping of ROW, Grading, all at A055 Westard and Eastward |  |  | Eldorado - A055 | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59420191125-3Labourer - General11715 | Corbiere and Sons Contracting59420191125-3Labourer - General11715Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 594 | 20191125-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers fueled equipment, escorted grader, installed culverts; Raking, Brushing, Building Rd, stripping of ROW, Grading, all at A055 Westard and Eastward |  |  | Eldorado - A055 | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59420191125-3L.O.A.1210 | Corbiere and Sons Contracting59420191125-3L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 595 | 20191125-4 | 53520101 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A052; 1 crew left at 11:30; Grinding at A049 and A054 and then float moved; Snow removal by dozer; ROW road finished into A051; Culvert Installation; 2 Exs walked out to end of Beck Rd. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59520191125-4Brusher91822.5 | Corbiere and Sons Contracting59520191125-4Brusher91822.5Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 595 | 20191125-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A052; 1 crew left at 11:30; Grinding at A049 and A054 and then float moved; Snow removal by dozer; ROW road finished into A051; Culvert Installation; 2 Exs walked out to end of Beck Rd. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59520191125-4Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting59520191125-4Grinder - 4710 Peterson or equal1810022.4Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 595 | 20191125-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A052; 1 crew left at 11:30; Grinding at A049 and A054 and then float moved; Snow removal by dozer; ROW road finished into A051; Culvert Installation; 2 Exs walked out to end of Beck Rd. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59520191125-4Log Loader182754 | Corbiere and Sons Contracting59520191125-4Log Loader182754Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 595 | 20191125-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 8 | Day |  | 0 |  |  | 960 | 124.8 | 1084.8 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A052; 1 crew left at 11:30; Grinding at A049 and A054 and then float moved; Snow removal by dozer; ROW road finished into A051; Culvert Installation; 2 Exs walked out to end of Beck Rd. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59520191125-4Chainsaw and consummables8960 | Corbiere and Sons Contracting59520191125-4Chainsaw and consummables8960Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 595 | 20191125-4 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 5 | HR | 101.25 | 0 |  |  | 675 | 87.75 | 762.75 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A052; 1 crew left at 11:30; Grinding at A049 and A054 and then float moved; Snow removal by dozer; ROW road finished into A051; Culvert Installation; 2 Exs walked out to end of Beck Rd. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59520191125-4Dozer D6 or equal5675 | Corbiere and Sons Contracting59520191125-4Dozer D6 or equal5675Inv#004-R02 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 595 | 20191125-4 | 53520101 | Clearing | 0 | Excavator - 36 ton | 171 | 13 | HR | 128.25 | 0 |  |  | 2223 | 288.99 | 2511.99 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A052; 1 crew left at 11:30; Grinding at A049 and A054 and then float moved; Snow removal by dozer; ROW road finished into A051; Culvert Installation; 2 Exs walked out to end of Beck Rd. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59520191125-4Excavator - 36 ton132223 | Corbiere and Sons Contracting59520191125-4Excavator - 36 ton132223Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2223 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 595 | 20191125-4 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A052; 1 crew left at 11:30; Grinding at A049 and A054 and then float moved; Snow removal by dozer; ROW road finished into A051; Culvert Installation; 2 Exs walked out to end of Beck Rd. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59520191125-4Light Truck - Pick up10300 | Corbiere and Sons Contracting59520191125-4Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 595 | 20191125-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A052; 1 crew left at 11:30; Grinding at A049 and A054 and then float moved; Snow removal by dozer; ROW road finished into A051; Culvert Installation; 2 Exs walked out to end of Beck Rd. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59520191125-4Light Truck - Pick up20600 | Corbiere and Sons Contracting59520191125-4Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 595 | 20191125-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A052; 1 crew left at 11:30; Grinding at A049 and A054 and then float moved; Snow removal by dozer; ROW road finished into A051; Culvert Installation; 2 Exs walked out to end of Beck Rd. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59520191125-4Light Truck - Pick up30900 | Corbiere and Sons Contracting59520191125-4Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 595 | 20191125-4 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A052; 1 crew left at 11:30; Grinding at A049 and A054 and then float moved; Snow removal by dozer; ROW road finished into A051; Culvert Installation; 2 Exs walked out to end of Beck Rd. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59520191125-4Foreman121140 | Corbiere and Sons Contracting59520191125-4Foreman121140Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 595 | 20191125-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 6 | HR |  |  |  | 0 | 540 | 70.2 | 610.2 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A052; 1 crew left at 11:30; Grinding at A049 and A054 and then float moved; Snow removal by dozer; ROW road finished into A051; Culvert Installation; 2 Exs walked out to end of Beck Rd. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59520191125-4Operator - Principle6540 | Corbiere and Sons Contracting59520191125-4Operator - Principle6540Inv#004-R02 | [5 empty] | 1 | 540 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 595 | 20191125-4 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 27 | HR |  |  |  | 0 | 2430 | 315.9 | 2745.9 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A052; 1 crew left at 11:30; Grinding at A049 and A054 and then float moved; Snow removal by dozer; ROW road finished into A051; Culvert Installation; 2 Exs walked out to end of Beck Rd. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59520191125-4Operator - Principle272430 | Corbiere and Sons Contracting59520191125-4Operator - Principle272430Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2430 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 595 | 20191125-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A052; 1 crew left at 11:30; Grinding at A049 and A054 and then float moved; Snow removal by dozer; ROW road finished into A051; Culvert Installation; 2 Exs walked out to end of Beck Rd. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59520191125-4Operator - Principle221980 | Corbiere and Sons Contracting59520191125-4Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 595 | 20191125-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 53 | HR |  |  |  | 0 | 3975 | 516.75 | 4491.75 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A052; 1 crew left at 11:30; Grinding at A049 and A054 and then float moved; Snow removal by dozer; ROW road finished into A051; Culvert Installation; 2 Exs walked out to end of Beck Rd. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59520191125-4Labourer - Specialized533975 | Corbiere and Sons Contracting59520191125-4Labourer - Specialized533975Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 3975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 595 | 20191125-4 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A052; 1 crew left at 11:30; Grinding at A049 and A054 and then float moved; Snow removal by dozer; ROW road finished into A051; Culvert Installation; 2 Exs walked out to end of Beck Rd. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59520191125-4L.O.A.1210 | Corbiere and Sons Contracting59520191125-4L.O.A.1210Inv#004-R02 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 595 | 20191125-4 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A052; 1 crew left at 11:30; Grinding at A049 and A054 and then float moved; Snow removal by dozer; ROW road finished into A051; Culvert Installation; 2 Exs walked out to end of Beck Rd. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59520191125-4L.O.A.3630 | Corbiere and Sons Contracting59520191125-4L.O.A.3630Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 595 | 20191125-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A052; 1 crew left at 11:30; Grinding at A049 and A054 and then float moved; Snow removal by dozer; ROW road finished into A051; Culvert Installation; 2 Exs walked out to end of Beck Rd. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59520191125-4L.O.A.2420 | Corbiere and Sons Contracting59520191125-4L.O.A.2420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 595 | 20191125-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A052; 1 crew left at 11:30; Grinding at A049 and A054 and then float moved; Snow removal by dozer; ROW road finished into A051; Culvert Installation; 2 Exs walked out to end of Beck Rd. |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59520191125-4L.O.A.81680 | Corbiere and Sons Contracting59520191125-4L.O.A.81680Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 596 | 20191125-5 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 27 | HR | 180 | 0 |  |  | 6480 | 842.4 | 7322.4 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished clearing from A111 to A115; Walked 1 Skidder amd 2 FBs to A105; Walked 1 SKD to A102; Cut road access road into A105; Walked CAT 545 SKD from base of hill |  |  | Wind Farm | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59620191125-5Feller Buncher276480 | Corbiere and Sons Contracting59620191125-5Feller Buncher276480Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 6480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 596 | 20191125-5 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 18 | HR | 180 | 0 |  |  | 4320 | 561.6 | 4881.6 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished clearing from A111 to A115; Walked 1 Skidder amd 2 FBs to A105; Walked 1 SKD to A102; Cut road access road into A105; Walked CAT 545 SKD from base of hill |  |  | Wind Farm | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59620191125-5Feller Buncher184320 | Corbiere and Sons Contracting59620191125-5Feller Buncher184320Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 596 | 20191125-5 | 53520101 | Clearing | 0 | Mulcher | 205 |  | HR | 153.75 | 9 |  |  | 1383.75 | 179.8875 | 1563.6375 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished clearing from A111 to A115; Walked 1 Skidder amd 2 FBs to A105; Walked 1 SKD to A102; Cut road access road into A105; Walked CAT 545 SKD from base of hill |  |  | Wind Farm | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59620191125-5Mulcher1383.75 | Corbiere and Sons Contracting59620191125-5Mulcher1383.75Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1383.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 596 | 20191125-5 | 53520101 | Clearing | 0 | Skidder | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished clearing from A111 to A115; Walked 1 Skidder amd 2 FBs to A105; Walked 1 SKD to A102; Cut road access road into A105; Walked CAT 545 SKD from base of hill |  |  | Wind Farm | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59620191125-5Skidder 183078 | Corbiere and Sons Contracting59620191125-5Skidder 183078Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 596 | 20191125-5 | 53520102 | Clearing | 0 | Skidder | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished clearing from A111 to A115; Walked 1 Skidder amd 2 FBs to A105; Walked 1 SKD to A102; Cut road access road into A105; Walked CAT 545 SKD from base of hill |  |  | Wind Farm | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59620191125-5Skidder 183078 | Corbiere and Sons Contracting59620191125-5Skidder 183078Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 596 | 20191125-5 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished clearing from A111 to A115; Walked 1 Skidder amd 2 FBs to A105; Walked 1 SKD to A102; Cut road access road into A105; Walked CAT 545 SKD from base of hill |  |  | Wind Farm | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59620191125-5Light Truck - Pick up401200 | Corbiere and Sons Contracting59620191125-5Light Truck - Pick up401200Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 596 | 20191125-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished clearing from A111 to A115; Walked 1 Skidder amd 2 FBs to A105; Walked 1 SKD to A102; Cut road access road into A105; Walked CAT 545 SKD from base of hill |  |  | Wind Farm | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59620191125-5Light Truck - Pick up20600 | Corbiere and Sons Contracting59620191125-5Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 596 | 20191125-5 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished clearing from A111 to A115; Walked 1 Skidder amd 2 FBs to A105; Walked 1 SKD to A102; Cut road access road into A105; Walked CAT 545 SKD from base of hill |  |  | Wind Farm | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59620191125-5Foreman4380 | Corbiere and Sons Contracting59620191125-5Foreman4380Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 596 | 20191125-5 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 50 | HR |  |  |  | 0 | 4500 | 585 | 5085 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished clearing from A111 to A115; Walked 1 Skidder amd 2 FBs to A105; Walked 1 SKD to A102; Cut road access road into A105; Walked CAT 545 SKD from base of hill |  |  | Wind Farm | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59620191125-5Operator - Principle504500 | Corbiere and Sons Contracting59620191125-5Operator - Principle504500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 596 | 20191125-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 37 | HR |  |  |  | 0 | 3330 | 432.9 | 3762.9 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished clearing from A111 to A115; Walked 1 Skidder amd 2 FBs to A105; Walked 1 SKD to A102; Cut road access road into A105; Walked CAT 545 SKD from base of hill |  |  | Wind Farm | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59620191125-5Operator - Principle373330 | Corbiere and Sons Contracting59620191125-5Operator - Principle373330Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3330 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 596 | 20191125-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished clearing from A111 to A115; Walked 1 Skidder amd 2 FBs to A105; Walked 1 SKD to A102; Cut road access road into A105; Walked CAT 545 SKD from base of hill |  |  | Wind Farm | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59620191125-5L.O.A.51050 | Corbiere and Sons Contracting59620191125-5L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 596 | 20191125-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-27 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished clearing from A111 to A115; Walked 1 Skidder amd 2 FBs to A105; Walked 1 SKD to A102; Cut road access road into A105; Walked CAT 545 SKD from base of hill |  |  | Wind Farm | 0 |  |  | 8 | 43802 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting59620191125-5L.O.A.4840 | Corbiere and Sons Contracting59620191125-5L.O.A.4840Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 597 | 20191126-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting59720191126-1Light Truck - Pick up501500 | Corbiere and Sons Contracting59720191126-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 597 | 20191126-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting59720191126-1Project Manager121320 | Corbiere and Sons Contracting59720191126-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 597 | 20191126-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting59720191126-1Superintendent121260 | Corbiere and Sons Contracting59720191126-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 597 | 20191126-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting59720191126-1Project Coordinator12960 | Corbiere and Sons Contracting59720191126-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 597 | 20191126-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting59720191126-1Safety Advisor121020 | Corbiere and Sons Contracting59720191126-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 597 | 20191126-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting59720191126-1Project Controls12840 | Corbiere and Sons Contracting59720191126-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 597 | 20191126-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting59720191126-1L.O.A.51050 | Corbiere and Sons Contracting59720191126-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 598 | 20191126-2-R2 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-11-28 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Float Moves: SKD, EX336, Mulcher; Running for parts, plowing of yard and general upkeep |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting59820191126-2-R2Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting59820191126-2-R2Loader JD 524 to 624 or equal9891Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 598 | 20191126-2-R2 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-28 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Float Moves: SKD, EX336, Mulcher; Running for parts, plowing of yard and general upkeep |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting59820191126-2-R2Light Truck - Pick up10300 | Corbiere and Sons Contracting59820191126-2-R2Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 598 | 20191126-2-R2 | 53520101 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2019-11-28 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Float Moves: SKD, EX336, Mulcher; Running for parts, plowing of yard and general upkeep |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting59820191126-2-R2Tractor Trailer - 60 Ton91215 | Corbiere and Sons Contracting59820191126-2-R2Tractor Trailer - 60 Ton91215Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 598 | 20191126-2-R2 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-11-28 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Float Moves: SKD, EX336, Mulcher; Running for parts, plowing of yard and general upkeep |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting59820191126-2-R2Operator - Principle121080 | Corbiere and Sons Contracting59820191126-2-R2Operator - Principle121080Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 598 | 20191126-2-R2 | 53520101 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-28 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Float Moves: SKD, EX336, Mulcher; Running for parts, plowing of yard and general upkeep |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting59820191126-2-R2Operator - Intermdiate11825 | Corbiere and Sons Contracting59820191126-2-R2Operator - Intermdiate11825Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 598 | 20191126-2-R2 | 53520101 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-11-28 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Float Moves: SKD, EX336, Mulcher; Running for parts, plowing of yard and general upkeep |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting59820191126-2-R2Labourer - General10650 | Corbiere and Sons Contracting59820191126-2-R2Labourer - General10650Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 598 | 20191126-2-R2 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-28 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Float Moves: SKD, EX336, Mulcher; Running for parts, plowing of yard and general upkeep |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting59820191126-2-R2L.O.A.2420 | Corbiere and Sons Contracting59820191126-2-R2L.O.A.2420Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 599 | 20191126-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers; Fueling, escorting floats, checking fire extinguishers; Donald Johnson Raking at A060 with 210 Link Belt; Brushing at A055; Grader working from Macgregor across all segments to wind farm |  |  |  | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59920191126-3Brusher91822.5 | Corbiere and Sons Contracting59920191126-3Brusher91822.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 599 | 20191126-3 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 4 | HR | 101.25 | 5 |  |  | 1046.25 | 136.0125 | 1182.2625 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers; Fueling, escorting floats, checking fire extinguishers; Donald Johnson Raking at A060 with 210 Link Belt; Brushing at A055; Grader working from Macgregor across all segments to wind farm |  |  |  | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59920191126-3Dozer D6 or equal41046.25 | Corbiere and Sons Contracting59920191126-3Dozer D6 or equal41046.25Inv#004-R02 | [5 empty] | 1 | 1046.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 599 | 20191126-3 | 53520102 | Clearing | 0 | Excavator - 30 ton | 139.5 |  | HR | 104.63 | 9 |  |  | 941.67 | 122.4171 | 1064.0871 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers; Fueling, escorting floats, checking fire extinguishers; Donald Johnson Raking at A060 with 210 Link Belt; Brushing at A055; Grader working from Macgregor across all segments to wind farm |  |  |  | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59920191126-3Excavator - 30 ton941.67 | Corbiere and Sons Contracting59920191126-3Excavator - 30 ton941.67Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 941.67 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 599 | 20191126-3 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 |  | HR | 128.25 | 9 |  |  | 1154.25 | 150.0525 | 1304.3025 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers; Fueling, escorting floats, checking fire extinguishers; Donald Johnson Raking at A060 with 210 Link Belt; Brushing at A055; Grader working from Macgregor across all segments to wind farm |  |  |  | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59920191126-3Excavator - 36 ton1154.25 | Corbiere and Sons Contracting59920191126-3Excavator - 36 ton1154.25Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1154.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 599 | 20191126-3 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers; Fueling, escorting floats, checking fire extinguishers; Donald Johnson Raking at A060 with 210 Link Belt; Brushing at A055; Grader working from Macgregor across all segments to wind farm |  |  |  | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59920191126-3Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting59920191126-3Grader - Cat 12 to 14 or equal91134Inv#004-R02 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 599 | 20191126-3 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers; Fueling, escorting floats, checking fire extinguishers; Donald Johnson Raking at A060 with 210 Link Belt; Brushing at A055; Grader working from Macgregor across all segments to wind farm |  |  |  | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59920191126-3Light Truck - Pick up10300 | Corbiere and Sons Contracting59920191126-3Light Truck - Pick up10300Inv#004-R02 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 599 | 20191126-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers; Fueling, escorting floats, checking fire extinguishers; Donald Johnson Raking at A060 with 210 Link Belt; Brushing at A055; Grader working from Macgregor across all segments to wind farm |  |  |  | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59920191126-3Light Truck - Pick up30900 | Corbiere and Sons Contracting59920191126-3Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 599 | 20191126-3 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers; Fueling, escorting floats, checking fire extinguishers; Donald Johnson Raking at A060 with 210 Link Belt; Brushing at A055; Grader working from Macgregor across all segments to wind farm |  |  |  | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59920191126-3Foreman121140 | Corbiere and Sons Contracting59920191126-3Foreman121140Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 599 | 20191126-3 | 53510111 | Access | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers; Fueling, escorting floats, checking fire extinguishers; Donald Johnson Raking at A060 with 210 Link Belt; Brushing at A055; Grader working from Macgregor across all segments to wind farm |  |  |  | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59920191126-3Operator - Principle221980 | Corbiere and Sons Contracting59920191126-3Operator - Principle221980Inv#004-R02 | [5 empty] | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 599 | 20191126-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 26 | HR |  |  |  | 0 | 2340 | 304.2 | 2644.2 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers; Fueling, escorting floats, checking fire extinguishers; Donald Johnson Raking at A060 with 210 Link Belt; Brushing at A055; Grader working from Macgregor across all segments to wind farm |  |  |  | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59920191126-3Operator - Principle262340 | Corbiere and Sons Contracting59920191126-3Operator - Principle262340Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2340 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 599 | 20191126-3 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 4 | HR |  |  | 70 | 0 | 300 | 39 | 339 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers; Fueling, escorting floats, checking fire extinguishers; Donald Johnson Raking at A060 with 210 Link Belt; Brushing at A055; Grader working from Macgregor across all segments to wind farm |  |  |  | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59920191126-3Operator - Intermdiate4300 | Corbiere and Sons Contracting59920191126-3Operator - Intermdiate4300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 599 | 20191126-3 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 7 | HR |  |  |  | 0 | 525 | 68.25 | 593.25 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers; Fueling, escorting floats, checking fire extinguishers; Donald Johnson Raking at A060 with 210 Link Belt; Brushing at A055; Grader working from Macgregor across all segments to wind farm |  |  |  | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59920191126-3Labourer - Specialized7525 | Corbiere and Sons Contracting59920191126-3Labourer - Specialized7525Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 599 | 20191126-3 | 53510111 | Access | 0 | Labourer - General | 65 | 6 | HR |  |  |  | 0 | 390 | 50.7 | 440.7 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers; Fueling, escorting floats, checking fire extinguishers; Donald Johnson Raking at A060 with 210 Link Belt; Brushing at A055; Grader working from Macgregor across all segments to wind farm |  |  |  | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59920191126-3Labourer - General6390 | Corbiere and Sons Contracting59920191126-3Labourer - General6390Inv#004-R02 | [5 empty] | 1 | 390 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 599 | 20191126-3 | 53510111 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers; Fueling, escorting floats, checking fire extinguishers; Donald Johnson Raking at A060 with 210 Link Belt; Brushing at A055; Grader working from Macgregor across all segments to wind farm |  |  |  | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59920191126-3L.O.A.3630 | Corbiere and Sons Contracting59920191126-3L.O.A.3630Inv#004-R02 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 599 | 20191126-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers; Fueling, escorting floats, checking fire extinguishers; Donald Johnson Raking at A060 with 210 Link Belt; Brushing at A055; Grader working from Macgregor across all segments to wind farm |  |  |  | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting59920191126-3L.O.A.4840 | Corbiere and Sons Contracting59920191126-3L.O.A.4840Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 600 | 20191126-4 | 53520101 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60020191126-4Brusher91822.5 | Corbiere and Sons Contracting60020191126-4Brusher91822.5Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 600 | 20191126-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60020191126-4Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting60020191126-4Grinder - 4710 Peterson or equal1810022.4Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 600 | 20191126-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60020191126-4Log Loader182754 | Corbiere and Sons Contracting60020191126-4Log Loader182754Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 600 | 20191126-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 9 | Day |  | 0 |  |  | 1080 | 140.4 | 1220.4 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60020191126-4Chainsaw and consummables91080 | Corbiere and Sons Contracting60020191126-4Chainsaw and consummables91080Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 600 | 20191126-4 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 6 | HR | 101.25 | 0 |  |  | 810 | 105.3 | 915.3 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60020191126-4Dozer D6 or equal6810 | Corbiere and Sons Contracting60020191126-4Dozer D6 or equal6810Inv#004-R02 | [5 empty] | 1 | 810 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 600 | 20191126-4 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60020191126-4Light Truck - Pick up10300 | Corbiere and Sons Contracting60020191126-4Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 600 | 20191126-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60020191126-4Light Truck - Pick up20600 | Corbiere and Sons Contracting60020191126-4Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 600 | 20191126-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60020191126-4Light Truck - Pick up30900 | Corbiere and Sons Contracting60020191126-4Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 600 | 20191126-4 | 53510111 | Access | 0 | Foreman | 95 | 6 | HR |  |  |  | 0 | 570 | 74.1 | 644.1 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60020191126-4Foreman6570 | Corbiere and Sons Contracting60020191126-4Foreman6570Inv#004-R02 | [5 empty] | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 600 | 20191126-4 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60020191126-4Foreman121140 | Corbiere and Sons Contracting60020191126-4Foreman121140Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 600 | 20191126-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 7 | HR |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60020191126-4Operator - Principle7630 | Corbiere and Sons Contracting60020191126-4Operator - Principle7630Inv#004-R02 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 600 | 20191126-4 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60020191126-4Operator - Principle11990 | Corbiere and Sons Contracting60020191126-4Operator - Principle11990Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 600 | 20191126-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60020191126-4Operator - Principle221980 | Corbiere and Sons Contracting60020191126-4Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 600 | 20191126-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 88 | HR |  |  |  | 0 | 6600 | 858 | 7458 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60020191126-4Labourer - Specialized886600 | Corbiere and Sons Contracting60020191126-4Labourer - Specialized886600Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 6600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 600 | 20191126-4 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60020191126-4L.O.A.2420 | Corbiere and Sons Contracting60020191126-4L.O.A.2420Inv#004-R02 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 600 | 20191126-4 | 53520101 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60020191126-4L.O.A.1210 | Corbiere and Sons Contracting60020191126-4L.O.A.1210Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 600 | 20191126-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60020191126-4L.O.A.2420 | Corbiere and Sons Contracting60020191126-4L.O.A.2420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 600 | 20191126-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60020191126-4L.O.A.91890 | Corbiere and Sons Contracting60020191126-4L.O.A.91890Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 601 | 20191126-5 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 6 | HR | 180 | 0 |  |  | 1440 | 187.2 | 1627.2 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished at A108 to A107; Move to A101 East; Finish at A105 West and Move to A101; New Access cut out at A01 and Access Rd. into A102 and A103 |  |  | Wind Farm | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60120191126-5Feller Buncher61440 | Corbiere and Sons Contracting60120191126-5Feller Buncher61440Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 601 | 20191126-5 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 39 | HR | 180 | 0 |  |  | 9360 | 1216.8 | 10576.8 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished at A108 to A107; Move to A101 East; Finish at A105 West and Move to A101; New Access cut out at A01 and Access Rd. into A102 and A103 |  |  | Wind Farm | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60120191126-5Feller Buncher399360 | Corbiere and Sons Contracting60120191126-5Feller Buncher399360Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 9360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 601 | 20191126-5 | 53520102 | Clearing | 0 | Mulcher | 205 |  | HR | 153.75 | 9 |  |  | 1383.75 | 179.8875 | 1563.6375 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished at A108 to A107; Move to A101 East; Finish at A105 West and Move to A101; New Access cut out at A01 and Access Rd. into A102 and A103 |  |  | Wind Farm | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60120191126-5Mulcher1383.75 | Corbiere and Sons Contracting60120191126-5Mulcher1383.75Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1383.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 601 | 20191126-5 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished at A108 to A107; Move to A101 East; Finish at A105 West and Move to A101; New Access cut out at A01 and Access Rd. into A102 and A103 |  |  | Wind Farm | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60120191126-5Skidder 91539 | Corbiere and Sons Contracting60120191126-5Skidder 91539Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 601 | 20191126-5 | 53520102 | Clearing | 0 | Skidder | 171 | 27 | HR | 128.25 | 0 |  |  | 4617 | 600.21 | 5217.21 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished at A108 to A107; Move to A101 East; Finish at A105 West and Move to A101; New Access cut out at A01 and Access Rd. into A102 and A103 |  |  | Wind Farm | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60120191126-5Skidder 274617 | Corbiere and Sons Contracting60120191126-5Skidder 274617Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 601 | 20191126-5 | 53510111 | Access | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished at A108 to A107; Move to A101 East; Finish at A105 West and Move to A101; New Access cut out at A01 and Access Rd. into A102 and A103 |  |  | Wind Farm | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60120191126-5Excavator - 36 ton91539 | Corbiere and Sons Contracting60120191126-5Excavator - 36 ton91539Inv#004-R02 | [5 empty] | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 601 | 20191126-5 | 53510111 | Access | 0 | Sander Truck | 112.5 | 7.5 | HR | 84.38 | 1.5 |  |  | 970.32 | 126.1416 | 1096.4616 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished at A108 to A107; Move to A101 East; Finish at A105 West and Move to A101; New Access cut out at A01 and Access Rd. into A102 and A103 |  |  | Wind Farm | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60120191126-5Sander Truck7.5970.32 | Corbiere and Sons Contracting60120191126-5Sander Truck7.5970.32Inv#004-R02 | [5 empty] | 1 | 970.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 601 | 20191126-5 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished at A108 to A107; Move to A101 East; Finish at A105 West and Move to A101; New Access cut out at A01 and Access Rd. into A102 and A103 |  |  | Wind Farm | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60120191126-5Light Truck - Pick up20600 | Corbiere and Sons Contracting60120191126-5Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 601 | 20191126-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished at A108 to A107; Move to A101 East; Finish at A105 West and Move to A101; New Access cut out at A01 and Access Rd. into A102 and A103 |  |  | Wind Farm | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60120191126-5Light Truck - Pick up10300 | Corbiere and Sons Contracting60120191126-5Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 601 | 20191126-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished at A108 to A107; Move to A101 East; Finish at A105 West and Move to A101; New Access cut out at A01 and Access Rd. into A102 and A103 |  |  | Wind Farm | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60120191126-5Light Truck - Pick up20600 | Corbiere and Sons Contracting60120191126-5Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 601 | 20191126-5 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished at A108 to A107; Move to A101 East; Finish at A105 West and Move to A101; New Access cut out at A01 and Access Rd. into A102 and A103 |  |  | Wind Farm | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60120191126-5Operator - Principle11990 | Corbiere and Sons Contracting60120191126-5Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 601 | 20191126-5 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 17 | HR |  |  |  | 0 | 1530 | 198.9 | 1728.9 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished at A108 to A107; Move to A101 East; Finish at A105 West and Move to A101; New Access cut out at A01 and Access Rd. into A102 and A103 |  |  | Wind Farm | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60120191126-5Operator - Principle171530 | Corbiere and Sons Contracting60120191126-5Operator - Principle171530Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1530 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 601 | 20191126-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 86 | HR |  |  |  | 0 | 7740 | 1006.2 | 8746.2 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished at A108 to A107; Move to A101 East; Finish at A105 West and Move to A101; New Access cut out at A01 and Access Rd. into A102 and A103 |  |  | Wind Farm | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60120191126-5Operator - Principle867740 | Corbiere and Sons Contracting60120191126-5Operator - Principle867740Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 7740 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 601 | 20191126-5 | 53510111 | Access | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished at A108 to A107; Move to A101 East; Finish at A105 West and Move to A101; New Access cut out at A01 and Access Rd. into A102 and A103 |  |  | Wind Farm | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60120191126-5Operator - Intermdiate11825 | Corbiere and Sons Contracting60120191126-5Operator - Intermdiate11825Inv#004-R02 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 601 | 20191126-5 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished at A108 to A107; Move to A101 East; Finish at A105 West and Move to A101; New Access cut out at A01 and Access Rd. into A102 and A103 |  |  | Wind Farm | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60120191126-5L.O.A.2420 | Corbiere and Sons Contracting60120191126-5L.O.A.2420Inv#004-R02 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 601 | 20191126-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished at A108 to A107; Move to A101 East; Finish at A105 West and Move to A101; New Access cut out at A01 and Access Rd. into A102 and A103 |  |  | Wind Farm | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60120191126-5L.O.A.3630 | Corbiere and Sons Contracting60120191126-5L.O.A.3630Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 601 | 20191126-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished at A108 to A107; Move to A101 East; Finish at A105 West and Move to A101; New Access cut out at A01 and Access Rd. into A102 and A103 |  |  | Wind Farm | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60120191126-5L.O.A.61260 | Corbiere and Sons Contracting60120191126-5L.O.A.61260Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 602 | 20191127-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting60220191127-1Light Truck - Pick up501500 | Corbiere and Sons Contracting60220191127-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 602 | 20191127-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting60220191127-1Project Manager121320 | Corbiere and Sons Contracting60220191127-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 602 | 20191127-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting60220191127-1Superintendent121260 | Corbiere and Sons Contracting60220191127-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 602 | 20191127-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting60220191127-1Project Coordinator12960 | Corbiere and Sons Contracting60220191127-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 602 | 20191127-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting60220191127-1Safety Advisor121020 | Corbiere and Sons Contracting60220191127-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 602 | 20191127-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting60220191127-1Project Controls12840 | Corbiere and Sons Contracting60220191127-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 602 | 20191127-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting60220191127-1L.O.A.51050 | Corbiere and Sons Contracting60220191127-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 603 | 20191127-2-R2 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-11-28 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Float Moves; Buncher with Rake from yard to Ouimet; 2 Exs from beck and Eldorado to Ouimet; Mechanics; Rakes, 336EX, Float Truck; Welding: 5th wheel and back racks on trucks; Loader used for sand |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting60320191127-2-R2Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting60320191127-2-R2Loader JD 524 to 624 or equal9891Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 603 | 20191127-2-R2 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-28 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Float Moves; Buncher with Rake from yard to Ouimet; 2 Exs from beck and Eldorado to Ouimet; Mechanics; Rakes, 336EX, Float Truck; Welding: 5th wheel and back racks on trucks; Loader used for sand |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting60320191127-2-R2Light Truck - Pick up10300 | Corbiere and Sons Contracting60320191127-2-R2Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 603 | 20191127-2-R2 | 53520101 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-11-28 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Float Moves; Buncher with Rake from yard to Ouimet; 2 Exs from beck and Eldorado to Ouimet; Mechanics; Rakes, 336EX, Float Truck; Welding: 5th wheel and back racks on trucks; Loader used for sand |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting60320191127-2-R2Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting60320191127-2-R2Tractor Trailer - 60 Ton101350Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 603 | 20191127-2-R2 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-11-28 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Float Moves; Buncher with Rake from yard to Ouimet; 2 Exs from beck and Eldorado to Ouimet; Mechanics; Rakes, 336EX, Float Truck; Welding: 5th wheel and back racks on trucks; Loader used for sand |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting60320191127-2-R2Operator - Principle121080 | Corbiere and Sons Contracting60320191127-2-R2Operator - Principle121080Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 603 | 20191127-2-R2 | 53520101 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-28 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Float Moves; Buncher with Rake from yard to Ouimet; 2 Exs from beck and Eldorado to Ouimet; Mechanics; Rakes, 336EX, Float Truck; Welding: 5th wheel and back racks on trucks; Loader used for sand |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting60320191127-2-R2Operator - Intermdiate11825 | Corbiere and Sons Contracting60320191127-2-R2Operator - Intermdiate11825Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 603 | 20191127-2-R2 | 53520101 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-11-28 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Float Moves; Buncher with Rake from yard to Ouimet; 2 Exs from beck and Eldorado to Ouimet; Mechanics; Rakes, 336EX, Float Truck; Welding: 5th wheel and back racks on trucks; Loader used for sand |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting60320191127-2-R2Labourer - General10650 | Corbiere and Sons Contracting60320191127-2-R2Labourer - General10650Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 603 | 20191127-2-R2 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-28 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Float Moves; Buncher with Rake from yard to Ouimet; 2 Exs from beck and Eldorado to Ouimet; Mechanics; Rakes, 336EX, Float Truck; Welding: 5th wheel and back racks on trucks; Loader used for sand |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting60320191127-2-R2L.O.A.2420 | Corbiere and Sons Contracting60320191127-2-R2L.O.A.2420Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 604 | 20191127-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Spotting, fueling, escorting floats, cleaning tracks; Gravelling at A056; Brushing at A055-A056; Raking at A061; Dozer at A055; COREX004 moved from Eldorado to Wind Farm; EX5 stop after Gravel |  |  | Eldorado - A055 to A079 | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60420191127-3Brusher91822.5 | Corbiere and Sons Contracting60420191127-3Brusher91822.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 604 | 20191127-3 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 9 | HR | 97.88 | 0 |  |  | 1174.5 | 152.685 | 1327.185 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Spotting, fueling, escorting floats, cleaning tracks; Gravelling at A056; Brushing at A055-A056; Raking at A061; Dozer at A055; COREX004 moved from Eldorado to Wind Farm; EX5 stop after Gravel |  |  | Eldorado - A055 to A079 | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60420191127-3Excavator - 20 ton91174.5 | Corbiere and Sons Contracting60420191127-3Excavator - 20 ton91174.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1174.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 604 | 20191127-3 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Spotting, fueling, escorting floats, cleaning tracks; Gravelling at A056; Brushing at A055-A056; Raking at A061; Dozer at A055; COREX004 moved from Eldorado to Wind Farm; EX5 stop after Gravel |  |  | Eldorado - A055 to A079 | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60420191127-3Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting60420191127-3Grader - Cat 12 to 14 or equal91134Inv#004-R02 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 604 | 20191127-3 | 53510111 | Access | 0 | Sander Truck | 112.5 | 9 | HR | 84.38 | 0 |  |  | 1012.5 | 131.625 | 1144.125 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Spotting, fueling, escorting floats, cleaning tracks; Gravelling at A056; Brushing at A055-A056; Raking at A061; Dozer at A055; COREX004 moved from Eldorado to Wind Farm; EX5 stop after Gravel |  |  | Eldorado - A055 to A079 | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60420191127-3Sander Truck91012.5 | Corbiere and Sons Contracting60420191127-3Sander Truck91012.5Inv#004-R02 | [5 empty] | 1 | 1012.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 604 | 20191127-3 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Spotting, fueling, escorting floats, cleaning tracks; Gravelling at A056; Brushing at A055-A056; Raking at A061; Dozer at A055; COREX004 moved from Eldorado to Wind Farm; EX5 stop after Gravel |  |  | Eldorado - A055 to A079 | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60420191127-3Light Truck - Pick up10300 | Corbiere and Sons Contracting60420191127-3Light Truck - Pick up10300Inv#004-R02 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 604 | 20191127-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Spotting, fueling, escorting floats, cleaning tracks; Gravelling at A056; Brushing at A055-A056; Raking at A061; Dozer at A055; COREX004 moved from Eldorado to Wind Farm; EX5 stop after Gravel |  |  | Eldorado - A055 to A079 | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60420191127-3Light Truck - Pick up20600 | Corbiere and Sons Contracting60420191127-3Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 604 | 20191127-3 | 53520102 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Spotting, fueling, escorting floats, cleaning tracks; Gravelling at A056; Brushing at A055-A056; Raking at A061; Dozer at A055; COREX004 moved from Eldorado to Wind Farm; EX5 stop after Gravel |  |  | Eldorado - A055 to A079 | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60420191127-3Foreman4380 | Corbiere and Sons Contracting60420191127-3Foreman4380Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 604 | 20191127-3 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Spotting, fueling, escorting floats, cleaning tracks; Gravelling at A056; Brushing at A055-A056; Raking at A061; Dozer at A055; COREX004 moved from Eldorado to Wind Farm; EX5 stop after Gravel |  |  | Eldorado - A055 to A079 | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60420191127-3Operator - Principle11990 | Corbiere and Sons Contracting60420191127-3Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 604 | 20191127-3 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Spotting, fueling, escorting floats, cleaning tracks; Gravelling at A056; Brushing at A055-A056; Raking at A061; Dozer at A055; COREX004 moved from Eldorado to Wind Farm; EX5 stop after Gravel |  |  | Eldorado - A055 to A079 | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60420191127-3Operator - Principle11990 | Corbiere and Sons Contracting60420191127-3Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 604 | 20191127-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Spotting, fueling, escorting floats, cleaning tracks; Gravelling at A056; Brushing at A055-A056; Raking at A061; Dozer at A055; COREX004 moved from Eldorado to Wind Farm; EX5 stop after Gravel |  |  | Eldorado - A055 to A079 | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60420191127-3Operator - Principle11990 | Corbiere and Sons Contracting60420191127-3Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 604 | 20191127-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Spotting, fueling, escorting floats, cleaning tracks; Gravelling at A056; Brushing at A055-A056; Raking at A061; Dozer at A055; COREX004 moved from Eldorado to Wind Farm; EX5 stop after Gravel |  |  | Eldorado - A055 to A079 | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60420191127-3Operator - Principle11990 | Corbiere and Sons Contracting60420191127-3Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 604 | 20191127-3 | 53520102 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Spotting, fueling, escorting floats, cleaning tracks; Gravelling at A056; Brushing at A055-A056; Raking at A061; Dozer at A055; COREX004 moved from Eldorado to Wind Farm; EX5 stop after Gravel |  |  | Eldorado - A055 to A079 | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60420191127-3Labourer - General11715 | Corbiere and Sons Contracting60420191127-3Labourer - General11715Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 604 | 20191127-3 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Spotting, fueling, escorting floats, cleaning tracks; Gravelling at A056; Brushing at A055-A056; Raking at A061; Dozer at A055; COREX004 moved from Eldorado to Wind Farm; EX5 stop after Gravel |  |  | Eldorado - A055 to A079 | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60420191127-3L.O.A.2420 | Corbiere and Sons Contracting60420191127-3L.O.A.2420Inv#004-R02 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 604 | 20191127-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Spotting, fueling, escorting floats, cleaning tracks; Gravelling at A056; Brushing at A055-A056; Raking at A061; Dozer at A055; COREX004 moved from Eldorado to Wind Farm; EX5 stop after Gravel |  |  | Eldorado - A055 to A079 | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60420191127-3L.O.A.3630 | Corbiere and Sons Contracting60420191127-3L.O.A.3630Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 605 | 20191127-4 | 53520101 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; Gravelling shut down at 1PM; EX and DZ on SB; Nick Morin in pit with EX002 loading and prepping |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60520191127-4Brusher91822.5 | Corbiere and Sons Contracting60520191127-4Brusher91822.5Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 605 | 20191127-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; Gravelling shut down at 1PM; EX and DZ on SB; Nick Morin in pit with EX002 loading and prepping |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60520191127-4Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting60520191127-4Grinder - 4710 Peterson or equal1810022.4Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 605 | 20191127-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; Gravelling shut down at 1PM; EX and DZ on SB; Nick Morin in pit with EX002 loading and prepping |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60520191127-4Log Loader182754 | Corbiere and Sons Contracting60520191127-4Log Loader182754Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 605 | 20191127-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 9 | Day |  | 0 |  |  | 1080 | 140.4 | 1220.4 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; Gravelling shut down at 1PM; EX and DZ on SB; Nick Morin in pit with EX002 loading and prepping |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60520191127-4Chainsaw and consummables91080 | Corbiere and Sons Contracting60520191127-4Chainsaw and consummables91080Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 605 | 20191127-4 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; Gravelling shut down at 1PM; EX and DZ on SB; Nick Morin in pit with EX002 loading and prepping |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60520191127-4Light Truck - Pick up10300 | Corbiere and Sons Contracting60520191127-4Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 605 | 20191127-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; Gravelling shut down at 1PM; EX and DZ on SB; Nick Morin in pit with EX002 loading and prepping |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60520191127-4Light Truck - Pick up20600 | Corbiere and Sons Contracting60520191127-4Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 605 | 20191127-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; Gravelling shut down at 1PM; EX and DZ on SB; Nick Morin in pit with EX002 loading and prepping |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60520191127-4Light Truck - Pick up30900 | Corbiere and Sons Contracting60520191127-4Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 605 | 20191127-4 | 53520101 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  |  | 0 | 570 | 74.1 | 644.1 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; Gravelling shut down at 1PM; EX and DZ on SB; Nick Morin in pit with EX002 loading and prepping |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60520191127-4Foreman6570 | Corbiere and Sons Contracting60520191127-4Foreman6570Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 605 | 20191127-4 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; Gravelling shut down at 1PM; EX and DZ on SB; Nick Morin in pit with EX002 loading and prepping |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60520191127-4Foreman121140 | Corbiere and Sons Contracting60520191127-4Foreman121140Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 605 | 20191127-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 6 | HR |  |  |  | 0 | 540 | 70.2 | 610.2 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; Gravelling shut down at 1PM; EX and DZ on SB; Nick Morin in pit with EX002 loading and prepping |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60520191127-4Operator - Principle6540 | Corbiere and Sons Contracting60520191127-4Operator - Principle6540Inv#004-R02 | [5 empty] | 1 | 540 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 605 | 20191127-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; Gravelling shut down at 1PM; EX and DZ on SB; Nick Morin in pit with EX002 loading and prepping |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60520191127-4Operator - Principle332970 | Corbiere and Sons Contracting60520191127-4Operator - Principle332970Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 605 | 20191127-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 68 | HR |  |  |  | 0 | 5100 | 663 | 5763 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; Gravelling shut down at 1PM; EX and DZ on SB; Nick Morin in pit with EX002 loading and prepping |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60520191127-4Labourer - Specialized685100 | Corbiere and Sons Contracting60520191127-4Labourer - Specialized685100Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 5100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 605 | 20191127-4 | 53520101 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; Gravelling shut down at 1PM; EX and DZ on SB; Nick Morin in pit with EX002 loading and prepping |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60520191127-4L.O.A.1210 | Corbiere and Sons Contracting60520191127-4L.O.A.1210Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 605 | 20191127-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; Gravelling shut down at 1PM; EX and DZ on SB; Nick Morin in pit with EX002 loading and prepping |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60520191127-4L.O.A.3630 | Corbiere and Sons Contracting60520191127-4L.O.A.3630Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 605 | 20191127-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A055 and from A054 to A042; Complete from A054 to Creek; Grinding from A049 to A050; Gravelling shut down at 1PM; EX and DZ on SB; Nick Morin in pit with EX002 loading and prepping |  |  | Beck Road East | 0 |  |  | 10 | 43797 | [5 empty] | Robert Grocholski | 01 | Corbiere and Sons Contracting60520191127-4L.O.A.91890 | Corbiere and Sons Contracting60520191127-4L.O.A.91890Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 606 | 20191127-5 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 27 | HR | 180 | 0 |  |  | 6480 | 842.4 | 7322.4 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Pat walked in with MUL and started at A111 W; Raking from A116 W; Skidders seperating wood; Feller Bunchers Cut Access into A098 and start at A094 |  |  | Wind Farm | 0 |  |  | 36 | 43797 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60620191127-5Feller Buncher276480 | Corbiere and Sons Contracting60620191127-5Feller Buncher276480Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 6480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 606 | 20191127-5 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Pat walked in with MUL and started at A111 W; Raking from A116 W; Skidders seperating wood; Feller Bunchers Cut Access into A098 and start at A094 |  |  | Wind Farm | 0 |  |  | 36 | 43797 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60620191127-5Feller Buncher92160 | Corbiere and Sons Contracting60620191127-5Feller Buncher92160Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 606 | 20191127-5 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Pat walked in with MUL and started at A111 W; Raking from A116 W; Skidders seperating wood; Feller Bunchers Cut Access into A098 and start at A094 |  |  | Wind Farm | 0 |  |  | 36 | 43797 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60620191127-5Mulcher91845 | Corbiere and Sons Contracting60620191127-5Mulcher91845Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 606 | 20191127-5 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Pat walked in with MUL and started at A111 W; Raking from A116 W; Skidders seperating wood; Feller Bunchers Cut Access into A098 and start at A094 |  |  | Wind Farm | 0 |  |  | 36 | 43797 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60620191127-5Skidder 91539 | Corbiere and Sons Contracting60620191127-5Skidder 91539Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 606 | 20191127-5 | 53520102 | Clearing | 0 | Skidder | 171 | 27 | HR | 128.25 | 0 |  |  | 4617 | 600.21 | 5217.21 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Pat walked in with MUL and started at A111 W; Raking from A116 W; Skidders seperating wood; Feller Bunchers Cut Access into A098 and start at A094 |  |  | Wind Farm | 0 |  |  | 36 | 43797 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60620191127-5Skidder 274617 | Corbiere and Sons Contracting60620191127-5Skidder 274617Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 606 | 20191127-5 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Pat walked in with MUL and started at A111 W; Raking from A116 W; Skidders seperating wood; Feller Bunchers Cut Access into A098 and start at A094 |  |  | Wind Farm | 0 |  |  | 36 | 43797 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60620191127-5Excavator - 36 ton91539 | Corbiere and Sons Contracting60620191127-5Excavator - 36 ton91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 606 | 20191127-5 | 53520102 | Clearing | 0 | Excavator - 50 ton | 189 | 9 | HR | 141.75 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Pat walked in with MUL and started at A111 W; Raking from A116 W; Skidders seperating wood; Feller Bunchers Cut Access into A098 and start at A094 |  |  | Wind Farm | 0 |  |  | 36 | 43797 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60620191127-5Excavator - 50 ton91701 | Corbiere and Sons Contracting60620191127-5Excavator - 50 ton91701Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1701 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 606 | 20191127-5 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Pat walked in with MUL and started at A111 W; Raking from A116 W; Skidders seperating wood; Feller Bunchers Cut Access into A098 and start at A094 |  |  | Wind Farm | 0 |  |  | 36 | 43797 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60620191127-5Light Truck - Pick up20600 | Corbiere and Sons Contracting60620191127-5Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 606 | 20191127-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Pat walked in with MUL and started at A111 W; Raking from A116 W; Skidders seperating wood; Feller Bunchers Cut Access into A098 and start at A094 |  |  | Wind Farm | 0 |  |  | 36 | 43797 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60620191127-5Light Truck - Pick up30900 | Corbiere and Sons Contracting60620191127-5Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 606 | 20191127-5 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Pat walked in with MUL and started at A111 W; Raking from A116 W; Skidders seperating wood; Feller Bunchers Cut Access into A098 and start at A094 |  |  | Wind Farm | 0 |  |  | 36 | 43797 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60620191127-5Operator - Principle443960 | Corbiere and Sons Contracting60620191127-5Operator - Principle443960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 606 | 20191127-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 77 | HR |  |  |  | 0 | 6930 | 900.9 | 7830.9 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Pat walked in with MUL and started at A111 W; Raking from A116 W; Skidders seperating wood; Feller Bunchers Cut Access into A098 and start at A094 |  |  | Wind Farm | 0 |  |  | 36 | 43797 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60620191127-5Operator - Principle776930 | Corbiere and Sons Contracting60620191127-5Operator - Principle776930Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 6930 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 606 | 20191127-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Pat walked in with MUL and started at A111 W; Raking from A116 W; Skidders seperating wood; Feller Bunchers Cut Access into A098 and start at A094 |  |  | Wind Farm | 0 |  |  | 36 | 43797 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60620191127-5L.O.A.4840 | Corbiere and Sons Contracting60620191127-5L.O.A.4840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 606 | 20191127-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-28 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Pat walked in with MUL and started at A111 W; Raking from A116 W; Skidders seperating wood; Feller Bunchers Cut Access into A098 and start at A094 |  |  | Wind Farm | 0 |  |  | 36 | 43797 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60620191127-5L.O.A.61260 | Corbiere and Sons Contracting60620191127-5L.O.A.61260Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 607 | 20191128-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting60720191128-1Light Truck - Pick up501500 | Corbiere and Sons Contracting60720191128-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 607 | 20191128-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting60720191128-1Project Manager121320 | Corbiere and Sons Contracting60720191128-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 607 | 20191128-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting60720191128-1Superintendent121260 | Corbiere and Sons Contracting60720191128-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 607 | 20191128-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting60720191128-1Project Coordinator12960 | Corbiere and Sons Contracting60720191128-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 607 | 20191128-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting60720191128-1Safety Advisor121020 | Corbiere and Sons Contracting60720191128-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 607 | 20191128-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting60720191128-1Project Controls12840 | Corbiere and Sons Contracting60720191128-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 607 | 20191128-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting60720191128-1L.O.A.51050 | Corbiere and Sons Contracting60720191128-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 608 | 20191128-2-R2 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-11-29 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | clean oil tanks; Float moves: Grinder and LL; Ernest Orientation. |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting60820191128-2-R2Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting60820191128-2-R2Loader JD 524 to 624 or equal9891Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 608 | 20191128-2-R2 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-29 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | clean oil tanks; Float moves: Grinder and LL; Ernest Orientation. |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting60820191128-2-R2Light Truck - Pick up10300 | Corbiere and Sons Contracting60820191128-2-R2Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 608 | 20191128-2-R2 | 53520101 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2019-11-29 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | clean oil tanks; Float moves: Grinder and LL; Ernest Orientation. |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting60820191128-2-R2Tractor Trailer - 60 Ton91215 | Corbiere and Sons Contracting60820191128-2-R2Tractor Trailer - 60 Ton91215Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 608 | 20191128-2-R2 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-11-29 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | clean oil tanks; Float moves: Grinder and LL; Ernest Orientation. |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting60820191128-2-R2Operator - Principle121080 | Corbiere and Sons Contracting60820191128-2-R2Operator - Principle121080Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 608 | 20191128-2-R2 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 5 | HR |  |  |  | 0 | 450 | 58.5 | 508.5 | 2019-11-29 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | clean oil tanks; Float moves: Grinder and LL; Ernest Orientation. |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting60820191128-2-R2Operator - Principle5450 | Corbiere and Sons Contracting60820191128-2-R2Operator - Principle5450Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 608 | 20191128-2-R2 | 53520101 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-29 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | clean oil tanks; Float moves: Grinder and LL; Ernest Orientation. |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting60820191128-2-R2Operator - Intermdiate11825 | Corbiere and Sons Contracting60820191128-2-R2Operator - Intermdiate11825Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 608 | 20191128-2-R2 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-29 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | clean oil tanks; Float moves: Grinder and LL; Ernest Orientation. |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting60820191128-2-R2L.O.A.3630 | Corbiere and Sons Contracting60820191128-2-R2L.O.A.3630Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 609 | 20191128-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs Gravelling from A55-57; Brusher at A057; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60920191128-3Brusher91822.5 | Corbiere and Sons Contracting60920191128-3Brusher91822.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 609 | 20191128-3 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 9 | HR | 97.88 | 0 |  |  | 1174.5 | 152.685 | 1327.185 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs Gravelling from A55-57; Brusher at A057; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60920191128-3Excavator - 20 ton91174.5 | Corbiere and Sons Contracting60920191128-3Excavator - 20 ton91174.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1174.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 609 | 20191128-3 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs Gravelling from A55-57; Brusher at A057; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60920191128-3Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting60920191128-3Grader - Cat 12 to 14 or equal91134Inv#004-R02 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 609 | 20191128-3 | 53510111 | Access | 0 | Sander Truck | 112.5 | 10 | HR | 84.38 | 0 |  |  | 1125 | 146.25 | 1271.25 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs Gravelling from A55-57; Brusher at A057; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60920191128-3Sander Truck101125 | Corbiere and Sons Contracting60920191128-3Sander Truck101125Inv#004-R02 | [5 empty] | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 609 | 20191128-3 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs Gravelling from A55-57; Brusher at A057; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60920191128-3Light Truck - Pick up10300 | Corbiere and Sons Contracting60920191128-3Light Truck - Pick up10300Inv#004-R02 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 609 | 20191128-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs Gravelling from A55-57; Brusher at A057; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60920191128-3Light Truck - Pick up10300 | Corbiere and Sons Contracting60920191128-3Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 609 | 20191128-3 | 53520102 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs Gravelling from A55-57; Brusher at A057; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60920191128-3Foreman4380 | Corbiere and Sons Contracting60920191128-3Foreman4380Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 609 | 20191128-3 | 53510111 | Access | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs Gravelling from A55-57; Brusher at A057; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60920191128-3Operator - Principle221980 | Corbiere and Sons Contracting60920191128-3Operator - Principle221980Inv#004-R02 | [5 empty] | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 609 | 20191128-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs Gravelling from A55-57; Brusher at A057; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60920191128-3Operator - Principle221980 | Corbiere and Sons Contracting60920191128-3Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 609 | 20191128-3 | 53510111 | Access | 0 | Labourer - Specialized | 75 | 6 | HR |  |  |  | 0 | 450 | 58.5 | 508.5 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs Gravelling from A55-57; Brusher at A057; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60920191128-3Labourer - Specialized6450 | Corbiere and Sons Contracting60920191128-3Labourer - Specialized6450Inv#004-R02 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 609 | 20191128-3 | 53510111 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs Gravelling from A55-57; Brusher at A057; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60920191128-3L.O.A.3630 | Corbiere and Sons Contracting60920191128-3L.O.A.3630Inv#004-R02 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 609 | 20191128-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs Gravelling from A55-57; Brusher at A057; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting60920191128-3L.O.A.2420 | Corbiere and Sons Contracting60920191128-3L.O.A.2420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 610 | 20191128-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A056; Griding from A050-A051 and then Float Moved to A058; Nick in Pit; 2 Exs Gravelling, 1 EX roughing up hill for trucks and spreading gravel; EX001 serviced at 2pm; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61020191128-4Brusher91822.5 | Corbiere and Sons Contracting61020191128-4Brusher91822.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 610 | 20191128-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A056; Griding from A050-A051 and then Float Moved to A058; Nick in Pit; 2 Exs Gravelling, 1 EX roughing up hill for trucks and spreading gravel; EX001 serviced at 2pm; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61020191128-4Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting61020191128-4Grinder - 4710 Peterson or equal1810022.4Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 610 | 20191128-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A056; Griding from A050-A051 and then Float Moved to A058; Nick in Pit; 2 Exs Gravelling, 1 EX roughing up hill for trucks and spreading gravel; EX001 serviced at 2pm; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61020191128-4Log Loader182754 | Corbiere and Sons Contracting61020191128-4Log Loader182754Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 610 | 20191128-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 9 | Day |  | 0 |  |  | 1080 | 140.4 | 1220.4 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A056; Griding from A050-A051 and then Float Moved to A058; Nick in Pit; 2 Exs Gravelling, 1 EX roughing up hill for trucks and spreading gravel; EX001 serviced at 2pm; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61020191128-4Chainsaw and consummables91080 | Corbiere and Sons Contracting61020191128-4Chainsaw and consummables91080Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 610 | 20191128-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A056; Griding from A050-A051 and then Float Moved to A058; Nick in Pit; 2 Exs Gravelling, 1 EX roughing up hill for trucks and spreading gravel; EX001 serviced at 2pm; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61020191128-4Light Truck - Pick up20600 | Corbiere and Sons Contracting61020191128-4Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 610 | 20191128-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A056; Griding from A050-A051 and then Float Moved to A058; Nick in Pit; 2 Exs Gravelling, 1 EX roughing up hill for trucks and spreading gravel; EX001 serviced at 2pm; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61020191128-4Light Truck - Pick up10300 | Corbiere and Sons Contracting61020191128-4Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 610 | 20191128-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A056; Griding from A050-A051 and then Float Moved to A058; Nick in Pit; 2 Exs Gravelling, 1 EX roughing up hill for trucks and spreading gravel; EX001 serviced at 2pm; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61020191128-4Light Truck - Pick up30900 | Corbiere and Sons Contracting61020191128-4Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 610 | 20191128-4 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A056; Griding from A050-A051 and then Float Moved to A058; Nick in Pit; 2 Exs Gravelling, 1 EX roughing up hill for trucks and spreading gravel; EX001 serviced at 2pm; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61020191128-4Foreman121140 | Corbiere and Sons Contracting61020191128-4Foreman121140Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 610 | 20191128-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A056; Griding from A050-A051 and then Float Moved to A058; Nick in Pit; 2 Exs Gravelling, 1 EX roughing up hill for trucks and spreading gravel; EX001 serviced at 2pm; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61020191128-4Operator - Principle332970 | Corbiere and Sons Contracting61020191128-4Operator - Principle332970Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 610 | 20191128-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 88 | HR |  |  |  | 0 | 6600 | 858 | 7458 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A056; Griding from A050-A051 and then Float Moved to A058; Nick in Pit; 2 Exs Gravelling, 1 EX roughing up hill for trucks and spreading gravel; EX001 serviced at 2pm; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61020191128-4Labourer - Specialized886600 | Corbiere and Sons Contracting61020191128-4Labourer - Specialized886600Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 6600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 610 | 20191128-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A056; Griding from A050-A051 and then Float Moved to A058; Nick in Pit; 2 Exs Gravelling, 1 EX roughing up hill for trucks and spreading gravel; EX001 serviced at 2pm; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61020191128-4L.O.A.3630 | Corbiere and Sons Contracting61020191128-4L.O.A.3630Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 610 | 20191128-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A042 to A056; Griding from A050-A051 and then Float Moved to A058; Nick in Pit; 2 Exs Gravelling, 1 EX roughing up hill for trucks and spreading gravel; EX001 serviced at 2pm; |  |  | Eldorado | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61020191128-4L.O.A.91890 | Corbiere and Sons Contracting61020191128-4L.O.A.91890Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 611 | 20191128-5 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 18 | HR | 180 | 0 |  |  | 4320 | 561.6 | 4881.6 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking finished at A116 W and then Walked to A111; ROW Rd Building finished at A116 and then moved to A111; Mulcher A111 W down to A106; FBs and SKDs from 101 to 106; down to A094 |  |  | Wind Farm | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61120191128-5Feller Buncher184320 | Corbiere and Sons Contracting61120191128-5Feller Buncher184320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 611 | 20191128-5 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 27 | HR | 180 | 0 |  |  | 6480 | 842.4 | 7322.4 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking finished at A116 W and then Walked to A111; ROW Rd Building finished at A116 and then moved to A111; Mulcher A111 W down to A106; FBs and SKDs from 101 to 106; down to A094 |  |  | Wind Farm | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61120191128-5Feller Buncher276480 | Corbiere and Sons Contracting61120191128-5Feller Buncher276480Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 6480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 611 | 20191128-5 | 53520102 | Clearing | 0 | Mulcher | 205 | 4 | HR | 153.75 | 0 |  |  | 820 | 106.6 | 926.6 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking finished at A116 W and then Walked to A111; ROW Rd Building finished at A116 and then moved to A111; Mulcher A111 W down to A106; FBs and SKDs from 101 to 106; down to A094 |  |  | Wind Farm | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61120191128-5Mulcher4820 | Corbiere and Sons Contracting61120191128-5Mulcher4820Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 820 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 611 | 20191128-5 | 53520101 | Clearing | 0 | Skidder | 171 | 13 | HR | 128.25 | 0 |  |  | 2223 | 288.99 | 2511.99 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking finished at A116 W and then Walked to A111; ROW Rd Building finished at A116 and then moved to A111; Mulcher A111 W down to A106; FBs and SKDs from 101 to 106; down to A094 |  |  | Wind Farm | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61120191128-5Skidder 132223 | Corbiere and Sons Contracting61120191128-5Skidder 132223Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2223 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 611 | 20191128-5 | 53520102 | Clearing | 0 | Skidder | 171 | 14 | HR | 128.25 | 0 |  |  | 2394 | 311.22 | 2705.22 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking finished at A116 W and then Walked to A111; ROW Rd Building finished at A116 and then moved to A111; Mulcher A111 W down to A106; FBs and SKDs from 101 to 106; down to A094 |  |  | Wind Farm | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61120191128-5Skidder 142394 | Corbiere and Sons Contracting61120191128-5Skidder 142394Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2394 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 611 | 20191128-5 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking finished at A116 W and then Walked to A111; ROW Rd Building finished at A116 and then moved to A111; Mulcher A111 W down to A106; FBs and SKDs from 101 to 106; down to A094 |  |  | Wind Farm | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61120191128-5Excavator - 36 ton91539 | Corbiere and Sons Contracting61120191128-5Excavator - 36 ton91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 611 | 20191128-5 | 53520102 | Clearing | 0 | Excavator - 50 ton | 189 | 9 | HR | 141.75 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking finished at A116 W and then Walked to A111; ROW Rd Building finished at A116 and then moved to A111; Mulcher A111 W down to A106; FBs and SKDs from 101 to 106; down to A094 |  |  | Wind Farm | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61120191128-5Excavator - 50 ton91701 | Corbiere and Sons Contracting61120191128-5Excavator - 50 ton91701Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1701 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 611 | 20191128-5 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking finished at A116 W and then Walked to A111; ROW Rd Building finished at A116 and then moved to A111; Mulcher A111 W down to A106; FBs and SKDs from 101 to 106; down to A094 |  |  | Wind Farm | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61120191128-5Light Truck - Pick up10300 | Corbiere and Sons Contracting61120191128-5Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 611 | 20191128-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking finished at A116 W and then Walked to A111; ROW Rd Building finished at A116 and then moved to A111; Mulcher A111 W down to A106; FBs and SKDs from 101 to 106; down to A094 |  |  | Wind Farm | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61120191128-5Light Truck - Pick up401200 | Corbiere and Sons Contracting61120191128-5Light Truck - Pick up401200Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 611 | 20191128-5 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 38 | HR |  |  |  | 0 | 3420 | 444.6 | 3864.6 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking finished at A116 W and then Walked to A111; ROW Rd Building finished at A116 and then moved to A111; Mulcher A111 W down to A106; FBs and SKDs from 101 to 106; down to A094 |  |  | Wind Farm | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61120191128-5Operator - Principle383420 | Corbiere and Sons Contracting61120191128-5Operator - Principle383420Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 611 | 20191128-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 77 | HR |  |  |  | 0 | 6930 | 900.9 | 7830.9 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking finished at A116 W and then Walked to A111; ROW Rd Building finished at A116 and then moved to A111; Mulcher A111 W down to A106; FBs and SKDs from 101 to 106; down to A094 |  |  | Wind Farm | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61120191128-5Operator - Principle776930 | Corbiere and Sons Contracting61120191128-5Operator - Principle776930Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 6930 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 611 | 20191128-5 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking finished at A116 W and then Walked to A111; ROW Rd Building finished at A116 and then moved to A111; Mulcher A111 W down to A106; FBs and SKDs from 101 to 106; down to A094 |  |  | Wind Farm | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61120191128-5Operator - Intermdiate11825 | Corbiere and Sons Contracting61120191128-5Operator - Intermdiate11825Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 611 | 20191128-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking finished at A116 W and then Walked to A111; ROW Rd Building finished at A116 and then moved to A111; Mulcher A111 W down to A106; FBs and SKDs from 101 to 106; down to A094 |  |  | Wind Farm | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61120191128-5L.O.A.3630 | Corbiere and Sons Contracting61120191128-5L.O.A.3630Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 611 | 20191128-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-11-29 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking finished at A116 W and then Walked to A111; ROW Rd Building finished at A116 and then moved to A111; Mulcher A111 W down to A106; FBs and SKDs from 101 to 106; down to A094 |  |  | Wind Farm | 0 |  |  | 36 | 43798 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61120191128-5L.O.A.71470 | Corbiere and Sons Contracting61120191128-5L.O.A.71470Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 613 | 20191129-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting61320191129-1Light Truck - Pick up501500 | Corbiere and Sons Contracting61320191129-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 613 | 20191129-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting61320191129-1Project Manager121320 | Corbiere and Sons Contracting61320191129-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 613 | 20191129-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting61320191129-1Superintendent121260 | Corbiere and Sons Contracting61320191129-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 613 | 20191129-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting61320191129-1Project Coordinator12960 | Corbiere and Sons Contracting61320191129-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 613 | 20191129-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting61320191129-1Safety Advisor121020 | Corbiere and Sons Contracting61320191129-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 613 | 20191129-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting61320191129-1Project Controls12840 | Corbiere and Sons Contracting61320191129-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 613 | 20191129-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting61320191129-1L.O.A.51050 | Corbiere and Sons Contracting61320191129-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 614 | 20191129-2-R2 | 53520101 | Clearing | 0 | Grader - Cat 12 to 14 or equal | 126 | 6 | HR | 94.5 | 0 |  |  | 756 | 98.28 | 854.28 | 2019-11-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Eddy Moved Grader from Thunder Bay to Eldorado; Float Truck moved, Brusher from Beck to Eldorado, Grinder and LL to Windfarm; |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting61420191129-2-R2Grader - Cat 12 to 14 or equal6756 | Corbiere and Sons Contracting61420191129-2-R2Grader - Cat 12 to 14 or equal6756Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 756 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 614 | 20191129-2-R2 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-11-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Eddy Moved Grader from Thunder Bay to Eldorado; Float Truck moved, Brusher from Beck to Eldorado, Grinder and LL to Windfarm; |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting61420191129-2-R2Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting61420191129-2-R2Loader JD 524 to 624 or equal9891Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 614 | 20191129-2-R2 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Eddy Moved Grader from Thunder Bay to Eldorado; Float Truck moved, Brusher from Beck to Eldorado, Grinder and LL to Windfarm; |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting61420191129-2-R2Light Truck - Pick up10300 | Corbiere and Sons Contracting61420191129-2-R2Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 614 | 20191129-2-R2 | 53520101 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2019-11-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Eddy Moved Grader from Thunder Bay to Eldorado; Float Truck moved, Brusher from Beck to Eldorado, Grinder and LL to Windfarm; |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting61420191129-2-R2Tractor Trailer - 60 Ton91215 | Corbiere and Sons Contracting61420191129-2-R2Tractor Trailer - 60 Ton91215Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 614 | 20191129-2-R2 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-11-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Eddy Moved Grader from Thunder Bay to Eldorado; Float Truck moved, Brusher from Beck to Eldorado, Grinder and LL to Windfarm; |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting61420191129-2-R2Operator - Principle121080 | Corbiere and Sons Contracting61420191129-2-R2Operator - Principle121080Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 614 | 20191129-2-R2 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 8 | HR |  |  |  | 0 | 720 | 93.6 | 813.6 | 2019-11-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Eddy Moved Grader from Thunder Bay to Eldorado; Float Truck moved, Brusher from Beck to Eldorado, Grinder and LL to Windfarm; |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting61420191129-2-R2Operator - Principle8720 | Corbiere and Sons Contracting61420191129-2-R2Operator - Principle8720Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 614 | 20191129-2-R2 | 53520101 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-11-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Eddy Moved Grader from Thunder Bay to Eldorado; Float Truck moved, Brusher from Beck to Eldorado, Grinder and LL to Windfarm; |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting61420191129-2-R2Operator - Intermdiate11825 | Corbiere and Sons Contracting61420191129-2-R2Operator - Intermdiate11825Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 614 | 20191129-2-R2 | 53520101 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-11-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Eddy Moved Grader from Thunder Bay to Eldorado; Float Truck moved, Brusher from Beck to Eldorado, Grinder and LL to Windfarm; |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting61420191129-2-R2Labourer - General10650 | Corbiere and Sons Contracting61420191129-2-R2Labourer - General10650Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 614 | 20191129-2-R2 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-11-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Eddy Moved Grader from Thunder Bay to Eldorado; Float Truck moved, Brusher from Beck to Eldorado, Grinder and LL to Windfarm; |  |  | General yard Maintenance, Float Moves; equipment | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting61420191129-2-R2L.O.A.3630 | Corbiere and Sons Contracting61420191129-2-R2L.O.A.3630Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 615 | 20191129-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs and DZ Gravelling from A55-57; Brusher between A058 and A061; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61520191129-3Brusher91822.5 | Corbiere and Sons Contracting61520191129-3Brusher91822.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 615 | 20191129-3 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 9 | HR | 97.88 | 0 |  |  | 1174.5 | 152.685 | 1327.185 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs and DZ Gravelling from A55-57; Brusher between A058 and A061; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61520191129-3Excavator - 20 ton91174.5 | Corbiere and Sons Contracting61520191129-3Excavator - 20 ton91174.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1174.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 615 | 20191129-3 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs and DZ Gravelling from A55-57; Brusher between A058 and A061; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61520191129-3Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting61520191129-3Grader - Cat 12 to 14 or equal91134Inv#004-R02 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 615 | 20191129-3 | 53510111 | Access | 0 | Sander Truck | 112.5 | 10.5 | HR | 84.38 | 0 |  |  | 1181.25 | 153.5625 | 1334.8125 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs and DZ Gravelling from A55-57; Brusher between A058 and A061; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61520191129-3Sander Truck10.51181.25 | Corbiere and Sons Contracting61520191129-3Sander Truck10.51181.25Inv#004-R02 | [5 empty] | 1 | 1181.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 615 | 20191129-3 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs and DZ Gravelling from A55-57; Brusher between A058 and A061; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61520191129-3Light Truck - Pick up10300 | Corbiere and Sons Contracting61520191129-3Light Truck - Pick up10300Inv#004-R02 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 615 | 20191129-3 | 53510111 | Access | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs and DZ Gravelling from A55-57; Brusher between A058 and A061; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61520191129-3Foreman4380 | Corbiere and Sons Contracting61520191129-3Foreman4380Inv#004-R02 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 615 | 20191129-3 | 53520101 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs and DZ Gravelling from A55-57; Brusher between A058 and A061; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61520191129-3Foreman4380 | Corbiere and Sons Contracting61520191129-3Foreman4380Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 615 | 20191129-3 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs and DZ Gravelling from A55-57; Brusher between A058 and A061; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61520191129-3Operator - Principle11990 | Corbiere and Sons Contracting61520191129-3Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 615 | 20191129-3 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs and DZ Gravelling from A55-57; Brusher between A058 and A061; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61520191129-3Operator - Principle11990 | Corbiere and Sons Contracting61520191129-3Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 615 | 20191129-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs and DZ Gravelling from A55-57; Brusher between A058 and A061; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61520191129-3Operator - Principle11990 | Corbiere and Sons Contracting61520191129-3Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 615 | 20191129-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs and DZ Gravelling from A55-57; Brusher between A058 and A061; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61520191129-3Operator - Principle11990 | Corbiere and Sons Contracting61520191129-3Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 615 | 20191129-3 | 53510111 | Access | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs and DZ Gravelling from A55-57; Brusher between A058 and A061; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61520191129-3Labourer - Specialized11825 | Corbiere and Sons Contracting61520191129-3Labourer - Specialized11825Inv#004-R02 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 615 | 20191129-3 | 53510111 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs and DZ Gravelling from A55-57; Brusher between A058 and A061; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61520191129-3L.O.A.4840 | Corbiere and Sons Contracting61520191129-3L.O.A.4840Inv#004-R02 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 615 | 20191129-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers: Fueling, Flagging, Spotting; Exs and DZ Gravelling from A55-57; Brusher between A058 and A061; Raking from A061-A062; Sanding and Grading across Segments; |  |  | Eldorado | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61520191129-3L.O.A.2420 | Corbiere and Sons Contracting61520191129-3L.O.A.2420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 616 | 20191129-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A055-A056; Grinding at A048-A056; Gravel Spread, Geo, Raking; Nick working in pit; Charlie and Brusher floated to windfarm |  |  | Beck East | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61620191129-4Brusher91822.5 | Corbiere and Sons Contracting61620191129-4Brusher91822.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 616 | 20191129-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A055-A056; Grinding at A048-A056; Gravel Spread, Geo, Raking; Nick working in pit; Charlie and Brusher floated to windfarm |  |  | Beck East | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61620191129-4Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting61620191129-4Grinder - 4710 Peterson or equal1810022.4Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 616 | 20191129-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A055-A056; Grinding at A048-A056; Gravel Spread, Geo, Raking; Nick working in pit; Charlie and Brusher floated to windfarm |  |  | Beck East | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61620191129-4Log Loader182754 | Corbiere and Sons Contracting61620191129-4Log Loader182754Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 616 | 20191129-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 9 | Day |  | 0 |  |  | 1080 | 140.4 | 1220.4 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A055-A056; Grinding at A048-A056; Gravel Spread, Geo, Raking; Nick working in pit; Charlie and Brusher floated to windfarm |  |  | Beck East | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61620191129-4Chainsaw and consummables91080 | Corbiere and Sons Contracting61620191129-4Chainsaw and consummables91080Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 616 | 20191129-4 | 53520102 | Clearing | 0 | Excavator - 30 ton | 139.5 | 5 | HR | 104.63 | 0 |  |  | 697.5 | 90.675 | 788.175 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A055-A056; Grinding at A048-A056; Gravel Spread, Geo, Raking; Nick working in pit; Charlie and Brusher floated to windfarm |  |  | Beck East | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61620191129-4Excavator - 30 ton5697.5 | Corbiere and Sons Contracting61620191129-4Excavator - 30 ton5697.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 697.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 616 | 20191129-4 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A055-A056; Grinding at A048-A056; Gravel Spread, Geo, Raking; Nick working in pit; Charlie and Brusher floated to windfarm |  |  | Beck East | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61620191129-4Excavator - 36 ton91539 | Corbiere and Sons Contracting61620191129-4Excavator - 36 ton91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 616 | 20191129-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A055-A056; Grinding at A048-A056; Gravel Spread, Geo, Raking; Nick working in pit; Charlie and Brusher floated to windfarm |  |  | Beck East | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61620191129-4Light Truck - Pick up20600 | Corbiere and Sons Contracting61620191129-4Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 616 | 20191129-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A055-A056; Grinding at A048-A056; Gravel Spread, Geo, Raking; Nick working in pit; Charlie and Brusher floated to windfarm |  |  | Beck East | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61620191129-4Light Truck - Pick up10300 | Corbiere and Sons Contracting61620191129-4Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 616 | 20191129-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A055-A056; Grinding at A048-A056; Gravel Spread, Geo, Raking; Nick working in pit; Charlie and Brusher floated to windfarm |  |  | Beck East | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61620191129-4Light Truck - Pick up30900 | Corbiere and Sons Contracting61620191129-4Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 616 | 20191129-4 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A055-A056; Grinding at A048-A056; Gravel Spread, Geo, Raking; Nick working in pit; Charlie and Brusher floated to windfarm |  |  | Beck East | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61620191129-4Foreman121140 | Corbiere and Sons Contracting61620191129-4Foreman121140Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 616 | 20191129-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 50 | HR |  |  |  | 0 | 4500 | 585 | 5085 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A055-A056; Grinding at A048-A056; Gravel Spread, Geo, Raking; Nick working in pit; Charlie and Brusher floated to windfarm |  |  | Beck East | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61620191129-4Operator - Principle504500 | Corbiere and Sons Contracting61620191129-4Operator - Principle504500Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 616 | 20191129-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 88 | HR |  |  |  | 0 | 6600 | 858 | 7458 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A055-A056; Grinding at A048-A056; Gravel Spread, Geo, Raking; Nick working in pit; Charlie and Brusher floated to windfarm |  |  | Beck East | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61620191129-4Labourer - Specialized886600 | Corbiere and Sons Contracting61620191129-4Labourer - Specialized886600Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 6600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 616 | 20191129-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A055-A056; Grinding at A048-A056; Gravel Spread, Geo, Raking; Nick working in pit; Charlie and Brusher floated to windfarm |  |  | Beck East | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61620191129-4L.O.A.51050 | Corbiere and Sons Contracting61620191129-4L.O.A.51050Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 616 | 20191129-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A055-A056; Grinding at A048-A056; Gravel Spread, Geo, Raking; Nick working in pit; Charlie and Brusher floated to windfarm |  |  | Beck East | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61620191129-4L.O.A.91890 | Corbiere and Sons Contracting61620191129-4L.O.A.91890Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 617 | 20191129-5 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 18 | HR | 180 | 0 |  |  | 4320 | 561.6 | 4881.6 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Cutting at A105 E, Skidding at A102 W, Finished at A093-A095 and moved to A088; Raking to A111 W and E; Brusher at A116 West; |  |  | Wind Farm | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61720191129-5Feller Buncher184320 | Corbiere and Sons Contracting61720191129-5Feller Buncher184320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 617 | 20191129-5 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 27 | HR | 180 | 0 |  |  | 6480 | 842.4 | 7322.4 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Cutting at A105 E, Skidding at A102 W, Finished at A093-A095 and moved to A088; Raking to A111 W and E; Brusher at A116 West; |  |  | Wind Farm | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61720191129-5Feller Buncher276480 | Corbiere and Sons Contracting61720191129-5Feller Buncher276480Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 6480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 617 | 20191129-5 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Cutting at A105 E, Skidding at A102 W, Finished at A093-A095 and moved to A088; Raking to A111 W and E; Brusher at A116 West; |  |  | Wind Farm | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61720191129-5Skidder 91539 | Corbiere and Sons Contracting61720191129-5Skidder 91539Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 617 | 20191129-5 | 53520102 | Clearing | 0 | Skidder | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Cutting at A105 E, Skidding at A102 W, Finished at A093-A095 and moved to A088; Raking to A111 W and E; Brusher at A116 West; |  |  | Wind Farm | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61720191129-5Skidder 183078 | Corbiere and Sons Contracting61720191129-5Skidder 183078Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 617 | 20191129-5 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 7 | HR | 128.25 | 0 |  |  | 1197 | 155.61 | 1352.61 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Cutting at A105 E, Skidding at A102 W, Finished at A093-A095 and moved to A088; Raking to A111 W and E; Brusher at A116 West; |  |  | Wind Farm | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61720191129-5Excavator - 36 ton71197 | Corbiere and Sons Contracting61720191129-5Excavator - 36 ton71197Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1197 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 617 | 20191129-5 | 53520102 | Clearing | 0 | Excavator - 50 ton | 189 | 9 | HR | 141.75 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Cutting at A105 E, Skidding at A102 W, Finished at A093-A095 and moved to A088; Raking to A111 W and E; Brusher at A116 West; |  |  | Wind Farm | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61720191129-5Excavator - 50 ton91701 | Corbiere and Sons Contracting61720191129-5Excavator - 50 ton91701Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1701 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 617 | 20191129-5 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Cutting at A105 E, Skidding at A102 W, Finished at A093-A095 and moved to A088; Raking to A111 W and E; Brusher at A116 West; |  |  | Wind Farm | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61720191129-5Light Truck - Pick up10300 | Corbiere and Sons Contracting61720191129-5Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 617 | 20191129-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Cutting at A105 E, Skidding at A102 W, Finished at A093-A095 and moved to A088; Raking to A111 W and E; Brusher at A116 West; |  |  | Wind Farm | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61720191129-5Light Truck - Pick up401200 | Corbiere and Sons Contracting61720191129-5Light Truck - Pick up401200Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 617 | 20191129-5 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Cutting at A105 E, Skidding at A102 W, Finished at A093-A095 and moved to A088; Raking to A111 W and E; Brusher at A116 West; |  |  | Wind Farm | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61720191129-5Operator - Principle221980 | Corbiere and Sons Contracting61720191129-5Operator - Principle221980Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 617 | 20191129-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 99 | HR |  |  |  | 0 | 8910 | 1158.3 | 10068.3 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Cutting at A105 E, Skidding at A102 W, Finished at A093-A095 and moved to A088; Raking to A111 W and E; Brusher at A116 West; |  |  | Wind Farm | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61720191129-5Operator - Principle998910 | Corbiere and Sons Contracting61720191129-5Operator - Principle998910Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 8910 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 617 | 20191129-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Cutting at A105 E, Skidding at A102 W, Finished at A093-A095 and moved to A088; Raking to A111 W and E; Brusher at A116 West; |  |  | Wind Farm | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61720191129-5L.O.A.2420 | Corbiere and Sons Contracting61720191129-5L.O.A.2420Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 617 | 20191129-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-11-30 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Cutting at A105 E, Skidding at A102 W, Finished at A093-A095 and moved to A088; Raking to A111 W and E; Brusher at A116 West; |  |  | Wind Farm | 0 |  |  | 36 | 43799 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting61720191129-5L.O.A.61260 | Corbiere and Sons Contracting61720191129-5L.O.A.61260Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 618 | 20191130-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting61820191130-1Light Truck - Pick up501500 | Corbiere and Sons Contracting61820191130-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 618 | 20191130-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting61820191130-1Project Manager121320 | Corbiere and Sons Contracting61820191130-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 618 | 20191130-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting61820191130-1Superintendent121260 | Corbiere and Sons Contracting61820191130-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 618 | 20191130-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting61820191130-1Project Coordinator12960 | Corbiere and Sons Contracting61820191130-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 618 | 20191130-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting61820191130-1Safety Advisor121020 | Corbiere and Sons Contracting61820191130-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 618 | 20191130-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting61820191130-1Project Controls12840 | Corbiere and Sons Contracting61820191130-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 618 | 20191130-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting61820191130-1L.O.A.51050 | Corbiere and Sons Contracting61820191130-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 619 | 20191130-2-R2 | 53520102 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-12-01 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Float Moves: DZ to Pit; |  |  | Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting61920191130-2-R2Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting61920191130-2-R2Loader JD 524 to 624 or equal9891Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 619 | 20191130-2-R2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-01 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Float Moves: DZ to Pit; |  |  | Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting61920191130-2-R2Light Truck - Pick up10300 | Corbiere and Sons Contracting61920191130-2-R2Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 619 | 20191130-2-R2 | 53520102 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2019-12-01 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Float Moves: DZ to Pit; |  |  | Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting61920191130-2-R2Tractor Trailer - 60 Ton91215 | Corbiere and Sons Contracting61920191130-2-R2Tractor Trailer - 60 Ton91215Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 619 | 20191130-2-R2 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 | 2019-12-01 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Float Moves: DZ to Pit; |  |  | Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting61920191130-2-R2Operator - Principle121080 | Corbiere and Sons Contracting61920191130-2-R2Operator - Principle121080Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 619 | 20191130-2-R2 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-12-01 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Float Moves: DZ to Pit; |  |  | Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting61920191130-2-R2Operator - Intermdiate11825 | Corbiere and Sons Contracting61920191130-2-R2Operator - Intermdiate11825Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 619 | 20191130-2-R2 | 53520101 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-12-01 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Float Moves: DZ to Pit; |  |  | Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting61920191130-2-R2Labourer - General10650 | Corbiere and Sons Contracting61920191130-2-R2Labourer - General10650Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 619 | 20191130-2-R2 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-01 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Float Moves: DZ to Pit; |  |  | Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting61920191130-2-R2L.O.A.2420 | Corbiere and Sons Contracting61920191130-2-R2L.O.A.2420Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 620 | 20191130-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A055 to A057; Handfelling completed at A055; Brushing from A062 to A064; Glen, Culvert and Gravelling A061; DZ Gravelling from A055 to A061; Sander Truck working all Segments |  |  | Eldorado | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62020191130-3Brusher91822.5 | Corbiere and Sons Contracting62020191130-3Brusher91822.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 620 | 20191130-3 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A055 to A057; Handfelling completed at A055; Brushing from A062 to A064; Glen, Culvert and Gravelling A061; DZ Gravelling from A055 to A061; Sander Truck working all Segments |  |  | Eldorado | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62020191130-3Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting62020191130-3Grinder - 4710 Peterson or equal95011.2Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 620 | 20191130-3 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A055 to A057; Handfelling completed at A055; Brushing from A062 to A064; Glen, Culvert and Gravelling A061; DZ Gravelling from A055 to A061; Sander Truck working all Segments |  |  | Eldorado | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62020191130-3Log Loader91377 | Corbiere and Sons Contracting62020191130-3Log Loader91377Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 620 | 20191130-3 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 6 | Day |  | 0 |  |  | 720 | 93.6 | 813.6 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A055 to A057; Handfelling completed at A055; Brushing from A062 to A064; Glen, Culvert and Gravelling A061; DZ Gravelling from A055 to A061; Sander Truck working all Segments |  |  | Eldorado | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62020191130-3Chainsaw and consummables6720 | Corbiere and Sons Contracting62020191130-3Chainsaw and consummables6720Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 620 | 20191130-3 | 53510111 | Access | 0 | Sander Truck | 112.5 | 11 | HR | 84.38 | 0 |  |  | 1237.5 | 160.875 | 1398.375 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A055 to A057; Handfelling completed at A055; Brushing from A062 to A064; Glen, Culvert and Gravelling A061; DZ Gravelling from A055 to A061; Sander Truck working all Segments |  |  | Eldorado | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62020191130-3Sander Truck111237.5 | Corbiere and Sons Contracting62020191130-3Sander Truck111237.5Inv#004-R02 | [5 empty] | 1 | 1237.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 620 | 20191130-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A055 to A057; Handfelling completed at A055; Brushing from A062 to A064; Glen, Culvert and Gravelling A061; DZ Gravelling from A055 to A061; Sander Truck working all Segments |  |  | Eldorado | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62020191130-3Light Truck - Pick up10300 | Corbiere and Sons Contracting62020191130-3Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 620 | 20191130-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A055 to A057; Handfelling completed at A055; Brushing from A062 to A064; Glen, Culvert and Gravelling A061; DZ Gravelling from A055 to A061; Sander Truck working all Segments |  |  | Eldorado | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62020191130-3Light Truck - Pick up10300 | Corbiere and Sons Contracting62020191130-3Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 620 | 20191130-3 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A055 to A057; Handfelling completed at A055; Brushing from A062 to A064; Glen, Culvert and Gravelling A061; DZ Gravelling from A055 to A061; Sander Truck working all Segments |  |  | Eldorado | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62020191130-3Light Truck - Pick up20600 | Corbiere and Sons Contracting62020191130-3Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 620 | 20191130-3 | 53520102 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A055 to A057; Handfelling completed at A055; Brushing from A062 to A064; Glen, Culvert and Gravelling A061; DZ Gravelling from A055 to A061; Sander Truck working all Segments |  |  | Eldorado | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62020191130-3Foreman4380 | Corbiere and Sons Contracting62020191130-3Foreman4380Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 620 | 20191130-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A055 to A057; Handfelling completed at A055; Brushing from A062 to A064; Glen, Culvert and Gravelling A061; DZ Gravelling from A055 to A061; Sander Truck working all Segments |  |  | Eldorado | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62020191130-3Foreman121140 | Corbiere and Sons Contracting62020191130-3Foreman121140Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 620 | 20191130-3 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A055 to A057; Handfelling completed at A055; Brushing from A062 to A064; Glen, Culvert and Gravelling A061; DZ Gravelling from A055 to A061; Sander Truck working all Segments |  |  | Eldorado | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62020191130-3Operator - Principle11990 | Corbiere and Sons Contracting62020191130-3Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 620 | 20191130-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A055 to A057; Handfelling completed at A055; Brushing from A062 to A064; Glen, Culvert and Gravelling A061; DZ Gravelling from A055 to A061; Sander Truck working all Segments |  |  | Eldorado | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62020191130-3Operator - Principle11990 | Corbiere and Sons Contracting62020191130-3Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 620 | 20191130-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A055 to A057; Handfelling completed at A055; Brushing from A062 to A064; Glen, Culvert and Gravelling A061; DZ Gravelling from A055 to A061; Sander Truck working all Segments |  |  | Eldorado | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62020191130-3Operator - Principle11990 | Corbiere and Sons Contracting62020191130-3Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 620 | 20191130-3 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 55 | HR |  |  |  | 0 | 4125 | 536.25 | 4661.25 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A055 to A057; Handfelling completed at A055; Brushing from A062 to A064; Glen, Culvert and Gravelling A061; DZ Gravelling from A055 to A061; Sander Truck working all Segments |  |  | Eldorado | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62020191130-3Labourer - Specialized554125 | Corbiere and Sons Contracting62020191130-3Labourer - Specialized554125Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 4125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 620 | 20191130-3 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A055 to A057; Handfelling completed at A055; Brushing from A062 to A064; Glen, Culvert and Gravelling A061; DZ Gravelling from A055 to A061; Sander Truck working all Segments |  |  | Eldorado | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62020191130-3L.O.A.1210 | Corbiere and Sons Contracting62020191130-3L.O.A.1210Inv#004-R02 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 620 | 20191130-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A055 to A057; Handfelling completed at A055; Brushing from A062 to A064; Glen, Culvert and Gravelling A061; DZ Gravelling from A055 to A061; Sander Truck working all Segments |  |  | Eldorado | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62020191130-3L.O.A.2420 | Corbiere and Sons Contracting62020191130-3L.O.A.2420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 620 | 20191130-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A055 to A057; Handfelling completed at A055; Brushing from A062 to A064; Glen, Culvert and Gravelling A061; DZ Gravelling from A055 to A061; Sander Truck working all Segments |  |  | Eldorado | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62020191130-3L.O.A.61260 | Corbiere and Sons Contracting62020191130-3L.O.A.61260Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 621 | 20191130-4 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 4 | HR | 128.25 | 0 |  |  | 684 | 88.92 | 772.92 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Work between A043 and A042; Stockpiling gravel loads to finalize approach; Concrete block were leveled; EX and DZ were loading trucks at pit and stripping area for better material |  |  | Beck Road and Gravel Pit | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62120191130-4Excavator - 36 ton4684 | Corbiere and Sons Contracting62120191130-4Excavator - 36 ton4684Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 684 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 621 | 20191130-4 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 5 | HR | 128.25 | 0 |  |  | 855 | 111.15 | 966.15 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Work between A043 and A042; Stockpiling gravel loads to finalize approach; Concrete block were leveled; EX and DZ were loading trucks at pit and stripping area for better material |  |  | Beck Road and Gravel Pit | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62120191130-4Excavator - 36 ton5855 | Corbiere and Sons Contracting62120191130-4Excavator - 36 ton5855Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 855 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 621 | 20191130-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Work between A043 and A042; Stockpiling gravel loads to finalize approach; Concrete block were leveled; EX and DZ were loading trucks at pit and stripping area for better material |  |  | Beck Road and Gravel Pit | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62120191130-4Light Truck - Pick up10300 | Corbiere and Sons Contracting62120191130-4Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 621 | 20191130-4 | 53510111 | Access | 0 | Foreman | 95 | 5 | HR |  |  |  | 0 | 475 | 61.75 | 536.75 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Work between A043 and A042; Stockpiling gravel loads to finalize approach; Concrete block were leveled; EX and DZ were loading trucks at pit and stripping area for better material |  |  | Beck Road and Gravel Pit | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62120191130-4Foreman5475 | Corbiere and Sons Contracting62120191130-4Foreman5475Inv#004-R02 | [5 empty] | 1 | 475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 621 | 20191130-4 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 5 | HR |  |  |  | 0 | 450 | 58.5 | 508.5 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Work between A043 and A042; Stockpiling gravel loads to finalize approach; Concrete block were leveled; EX and DZ were loading trucks at pit and stripping area for better material |  |  | Beck Road and Gravel Pit | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62120191130-4Operator - Principle5450 | Corbiere and Sons Contracting62120191130-4Operator - Principle5450Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 621 | 20191130-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 4 | HR |  |  |  | 0 | 360 | 46.8 | 406.8 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Work between A043 and A042; Stockpiling gravel loads to finalize approach; Concrete block were leveled; EX and DZ were loading trucks at pit and stripping area for better material |  |  | Beck Road and Gravel Pit | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62120191130-4Operator - Principle4360 | Corbiere and Sons Contracting62120191130-4Operator - Principle4360Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 621 | 20191130-4 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Work between A043 and A042; Stockpiling gravel loads to finalize approach; Concrete block were leveled; EX and DZ were loading trucks at pit and stripping area for better material |  |  | Beck Road and Gravel Pit | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62120191130-4L.O.A.1210 | Corbiere and Sons Contracting62120191130-4L.O.A.1210Inv#004-R02 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 621 | 20191130-4 | 53520101 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Work between A043 and A042; Stockpiling gravel loads to finalize approach; Concrete block were leveled; EX and DZ were loading trucks at pit and stripping area for better material |  |  | Beck Road and Gravel Pit | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62120191130-4L.O.A.1210 | Corbiere and Sons Contracting62120191130-4L.O.A.1210Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 621 | 20191130-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Work between A043 and A042; Stockpiling gravel loads to finalize approach; Concrete block were leveled; EX and DZ were loading trucks at pit and stripping area for better material |  |  | Beck Road and Gravel Pit | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62120191130-4L.O.A.1210 | Corbiere and Sons Contracting62120191130-4L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 622 | 20191130-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grading from A099 to A087 and Eldorado; Cutting and Skidding from A090 to A087; Raking from A111 E and both A116 Eastward and Westward; Brushing at A116; Log Loader and Grinder Walked into A115 |  |  | Clearing and Winter Maintenance | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62220191130-5Brusher91822.5 | Corbiere and Sons Contracting62220191130-5Brusher91822.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 622 | 20191130-5 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 36 | HR | 180 | 0 |  |  | 8640 | 1123.2 | 9763.2 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grading from A099 to A087 and Eldorado; Cutting and Skidding from A090 to A087; Raking from A111 E and both A116 Eastward and Westward; Brushing at A116; Log Loader and Grinder Walked into A115 |  |  | Clearing and Winter Maintenance | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62220191130-5Feller Buncher368640 | Corbiere and Sons Contracting62220191130-5Feller Buncher368640Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 8640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 622 | 20191130-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grading from A099 to A087 and Eldorado; Cutting and Skidding from A090 to A087; Raking from A111 E and both A116 Eastward and Westward; Brushing at A116; Log Loader and Grinder Walked into A115 |  |  | Clearing and Winter Maintenance | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62220191130-5Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting62220191130-5Grinder - 4710 Peterson or equal95011.2Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 622 | 20191130-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grading from A099 to A087 and Eldorado; Cutting and Skidding from A090 to A087; Raking from A111 E and both A116 Eastward and Westward; Brushing at A116; Log Loader and Grinder Walked into A115 |  |  | Clearing and Winter Maintenance | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62220191130-5Log Loader91377 | Corbiere and Sons Contracting62220191130-5Log Loader91377Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 622 | 20191130-5 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grading from A099 to A087 and Eldorado; Cutting and Skidding from A090 to A087; Raking from A111 E and both A116 Eastward and Westward; Brushing at A116; Log Loader and Grinder Walked into A115 |  |  | Clearing and Winter Maintenance | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62220191130-5Mulcher91845 | Corbiere and Sons Contracting62220191130-5Mulcher91845Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 622 | 20191130-5 | 53520102 | Clearing | 0 | Skidder | 171 | 22 | HR | 128.25 | 0 |  |  | 3762 | 489.06 | 4251.06 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grading from A099 to A087 and Eldorado; Cutting and Skidding from A090 to A087; Raking from A111 E and both A116 Eastward and Westward; Brushing at A116; Log Loader and Grinder Walked into A115 |  |  | Clearing and Winter Maintenance | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62220191130-5Skidder 223762 | Corbiere and Sons Contracting62220191130-5Skidder 223762Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3762 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 622 | 20191130-5 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grading from A099 to A087 and Eldorado; Cutting and Skidding from A090 to A087; Raking from A111 E and both A116 Eastward and Westward; Brushing at A116; Log Loader and Grinder Walked into A115 |  |  | Clearing and Winter Maintenance | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62220191130-5Excavator - 36 ton183078 | Corbiere and Sons Contracting62220191130-5Excavator - 36 ton183078Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 622 | 20191130-5 | 53520102 | Clearing | 0 | Excavator - 50 ton | 189 | 9 | HR | 141.75 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grading from A099 to A087 and Eldorado; Cutting and Skidding from A090 to A087; Raking from A111 E and both A116 Eastward and Westward; Brushing at A116; Log Loader and Grinder Walked into A115 |  |  | Clearing and Winter Maintenance | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62220191130-5Excavator - 50 ton91701 | Corbiere and Sons Contracting62220191130-5Excavator - 50 ton91701Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1701 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 622 | 20191130-5 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 18 | HR | 94.5 | 0 |  |  | 2268 | 294.84 | 2562.84 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grading from A099 to A087 and Eldorado; Cutting and Skidding from A090 to A087; Raking from A111 E and both A116 Eastward and Westward; Brushing at A116; Log Loader and Grinder Walked into A115 |  |  | Clearing and Winter Maintenance | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62220191130-5Grader - Cat 12 to 14 or equal182268 | Corbiere and Sons Contracting62220191130-5Grader - Cat 12 to 14 or equal182268Inv#004-R02 | [5 empty] | 1 | 2268 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 622 | 20191130-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grading from A099 to A087 and Eldorado; Cutting and Skidding from A090 to A087; Raking from A111 E and both A116 Eastward and Westward; Brushing at A116; Log Loader and Grinder Walked into A115 |  |  | Clearing and Winter Maintenance | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62220191130-5Light Truck - Pick up10300 | Corbiere and Sons Contracting62220191130-5Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 622 | 20191130-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 45 | HR | 22.5 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grading from A099 to A087 and Eldorado; Cutting and Skidding from A090 to A087; Raking from A111 E and both A116 Eastward and Westward; Brushing at A116; Log Loader and Grinder Walked into A115 |  |  | Clearing and Winter Maintenance | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62220191130-5Light Truck - Pick up451350 | Corbiere and Sons Contracting62220191130-5Light Truck - Pick up451350Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 622 | 20191130-5 | 53510111 | Access | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grading from A099 to A087 and Eldorado; Cutting and Skidding from A090 to A087; Raking from A111 E and both A116 Eastward and Westward; Brushing at A116; Log Loader and Grinder Walked into A115 |  |  | Clearing and Winter Maintenance | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62220191130-5Operator - Principle221980 | Corbiere and Sons Contracting62220191130-5Operator - Principle221980Inv#004-R02 | [5 empty] | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 622 | 20191130-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 143 | HR |  |  |  | 0 | 12870 | 1673.1 | 14543.1 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grading from A099 to A087 and Eldorado; Cutting and Skidding from A090 to A087; Raking from A111 E and both A116 Eastward and Westward; Brushing at A116; Log Loader and Grinder Walked into A115 |  |  | Clearing and Winter Maintenance | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62220191130-5Operator - Principle14312870 | Corbiere and Sons Contracting62220191130-5Operator - Principle14312870Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 12870 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 622 | 20191130-5 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grading from A099 to A087 and Eldorado; Cutting and Skidding from A090 to A087; Raking from A111 E and both A116 Eastward and Westward; Brushing at A116; Log Loader and Grinder Walked into A115 |  |  | Clearing and Winter Maintenance | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62220191130-5L.O.A.2420 | Corbiere and Sons Contracting62220191130-5L.O.A.2420Inv#004-R02 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 622 | 20191130-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 12 | DAY |  |  |  | 0 | 2520 | 327.6 | 2847.6 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grading from A099 to A087 and Eldorado; Cutting and Skidding from A090 to A087; Raking from A111 E and both A116 Eastward and Westward; Brushing at A116; Log Loader and Grinder Walked into A115 |  |  | Clearing and Winter Maintenance | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62220191130-5L.O.A.122520 | Corbiere and Sons Contracting62220191130-5L.O.A.122520Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2520 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 623 | 20191130-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 22 | HR | 22.5 | 0 |  |  | 660 | 85.8 | 745.8 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | 3 Operators and 1 labourer went out after hours to ensure all equipment was fully fueled and ready for the following day - Please note that I have billed all their time as General Labourers |  |  | Fueling-All Segments were equipment was located | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62320191130-6Light Truck - Pick up22660 | Corbiere and Sons Contracting62320191130-6Light Truck - Pick up22660Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 623 | 20191130-6 | 53520102 | Clearing | 0 | Labourer - General | 65 | 22 | HR |  |  |  | 0 | 1430 | 185.9 | 1615.9 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | 3 Operators and 1 labourer went out after hours to ensure all equipment was fully fueled and ready for the following day - Please note that I have billed all their time as General Labourers |  |  | Fueling-All Segments were equipment was located | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62320191130-6Labourer - General221430 | Corbiere and Sons Contracting62320191130-6Labourer - General221430Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1430 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 623 | 20191130-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-01 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | 3 Operators and 1 labourer went out after hours to ensure all equipment was fully fueled and ready for the following day - Please note that I have billed all their time as General Labourers |  |  | Fueling-All Segments were equipment was located | 0 |  |  | 36 | 43801 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting62320191130-6L.O.A.1210 | Corbiere and Sons Contracting62320191130-6L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 690 | 20191210-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting69020191210-1Light Truck - Pick up501500 | Corbiere and Sons Contracting69020191210-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 690 | 20191210-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting69020191210-1Project Manager121320 | Corbiere and Sons Contracting69020191210-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 690 | 20191210-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting69020191210-1Superintendent121260 | Corbiere and Sons Contracting69020191210-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 690 | 20191210-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting69020191210-1Project Coordinator12960 | Corbiere and Sons Contracting69020191210-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 690 | 20191210-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting69020191210-1Safety Advisor121020 | Corbiere and Sons Contracting69020191210-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 690 | 20191210-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting69020191210-1Project Controls12840 | Corbiere and Sons Contracting69020191210-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 690 | 20191210-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting69020191210-1L.O.A.51050 | Corbiere and Sons Contracting69020191210-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 691 | 20191210-2-R3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Austin working on Grader, Mulcher and the CAT Buncher, cole worked on Brusher, Equipment was being worked on early morning and late night trying to get running in the cold. |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting69120191210-2-R3Light Truck - Pick up10300 | Corbiere and Sons Contracting69120191210-2-R3Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 691 | 20191210-2-R3 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2019-12-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Austin working on Grader, Mulcher and the CAT Buncher, cole worked on Brusher, Equipment was being worked on early morning and late night trying to get running in the cold. |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting69120191210-2-R3Operator - Apprentice10600 | Corbiere and Sons Contracting69120191210-2-R3Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 691 | 20191210-2-R3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Austin working on Grader, Mulcher and the CAT Buncher, cole worked on Brusher, Equipment was being worked on early morning and late night trying to get running in the cold. |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting69120191210-2-R3L.O.A.1210 | Corbiere and Sons Contracting69120191210-2-R3L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 691 | 20191210-2-R3 | 53520102 | Clearing | 0 | Warehouse Supervisor | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2019-12-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Austin working on Grader, Mulcher and the CAT Buncher, cole worked on Brusher, Equipment was being worked on early morning and late night trying to get running in the cold. |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting69120191210-2-R3Warehouse Supervisor12900 | Corbiere and Sons Contracting69120191210-2-R3Warehouse Supervisor12900Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 692 | 20191210-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing - Handfelling, brusher and feller working at landowners property, 3 labourers flagging and spotting. Float moved Feller Buncher and Brusher to this location for the work. |  |  | MacKenzie East - A030-A035 | 0 |  |  | 17 | 43814 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting69220191210-3Brusher91822.5 | Corbiere and Sons Contracting69220191210-3Brusher91822.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 692 | 20191210-3 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 4 | HR | 180 | 0 |  |  | 960 | 124.8 | 1084.8 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing - Handfelling, brusher and feller working at landowners property, 3 labourers flagging and spotting. Float moved Feller Buncher and Brusher to this location for the work. |  |  | MacKenzie East - A030-A035 | 0 |  |  | 17 | 43814 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting69220191210-3Feller Buncher4960 | Corbiere and Sons Contracting69220191210-3Feller Buncher4960Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 692 | 20191210-3 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 2 | Day |  | 0 |  |  | 240 | 31.2 | 271.2 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing - Handfelling, brusher and feller working at landowners property, 3 labourers flagging and spotting. Float moved Feller Buncher and Brusher to this location for the work. |  |  | MacKenzie East - A030-A035 | 0 |  |  | 17 | 43814 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting69220191210-3Chainsaw and consummables2240 | Corbiere and Sons Contracting69220191210-3Chainsaw and consummables2240Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 692 | 20191210-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing - Handfelling, brusher and feller working at landowners property, 3 labourers flagging and spotting. Float moved Feller Buncher and Brusher to this location for the work. |  |  | MacKenzie East - A030-A035 | 0 |  |  | 17 | 43814 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting69220191210-3Light Truck - Pick up10300 | Corbiere and Sons Contracting69220191210-3Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 692 | 20191210-3 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing - Handfelling, brusher and feller working at landowners property, 3 labourers flagging and spotting. Float moved Feller Buncher and Brusher to this location for the work. |  |  | MacKenzie East - A030-A035 | 0 |  |  | 17 | 43814 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting69220191210-3Light Truck - Pick up10300 | Corbiere and Sons Contracting69220191210-3Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 692 | 20191210-3 | 53520102 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing - Handfelling, brusher and feller working at landowners property, 3 labourers flagging and spotting. Float moved Feller Buncher and Brusher to this location for the work. |  |  | MacKenzie East - A030-A035 | 0 |  |  | 17 | 43814 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting69220191210-3Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting69220191210-3Tractor Trailer - 60 Ton101350Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 692 | 20191210-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 15 | HR |  |  |  | 0 | 1350 | 175.5 | 1525.5 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing - Handfelling, brusher and feller working at landowners property, 3 labourers flagging and spotting. Float moved Feller Buncher and Brusher to this location for the work. |  |  | MacKenzie East - A030-A035 | 0 |  |  | 17 | 43814 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting69220191210-3Operator - Principle151350 | Corbiere and Sons Contracting69220191210-3Operator - Principle151350Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 692 | 20191210-3 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing - Handfelling, brusher and feller working at landowners property, 3 labourers flagging and spotting. Float moved Feller Buncher and Brusher to this location for the work. |  |  | MacKenzie East - A030-A035 | 0 |  |  | 17 | 43814 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting69220191210-3Operator - Intermdiate11825 | Corbiere and Sons Contracting69220191210-3Operator - Intermdiate11825Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 692 | 20191210-3 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing - Handfelling, brusher and feller working at landowners property, 3 labourers flagging and spotting. Float moved Feller Buncher and Brusher to this location for the work. |  |  | MacKenzie East - A030-A035 | 0 |  |  | 17 | 43814 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting69220191210-3Labourer - Specialized11825 | Corbiere and Sons Contracting69220191210-3Labourer - Specialized11825Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 692 | 20191210-3 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 22 | HR |  |  |  | 0 | 1650 | 214.5 | 1864.5 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing - Handfelling, brusher and feller working at landowners property, 3 labourers flagging and spotting. Float moved Feller Buncher and Brusher to this location for the work. |  |  | MacKenzie East - A030-A035 | 0 |  |  | 17 | 43814 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting69220191210-3Labourer - Specialized221650 | Corbiere and Sons Contracting69220191210-3Labourer - Specialized221650Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 692 | 20191210-3 | 53520102 | Clearing | 0 | Labourer - General | 65 | 22 | HR |  |  |  | 0 | 1430 | 185.9 | 1615.9 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing - Handfelling, brusher and feller working at landowners property, 3 labourers flagging and spotting. Float moved Feller Buncher and Brusher to this location for the work. |  |  | MacKenzie East - A030-A035 | 0 |  |  | 17 | 43814 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting69220191210-3Labourer - General221430 | Corbiere and Sons Contracting69220191210-3Labourer - General221430Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1430 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 692 | 20191210-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing - Handfelling, brusher and feller working at landowners property, 3 labourers flagging and spotting. Float moved Feller Buncher and Brusher to this location for the work. |  |  | MacKenzie East - A030-A035 | 0 |  |  | 17 | 43814 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting69220191210-3L.O.A.61260 | Corbiere and Sons Contracting69220191210-3L.O.A.61260Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 692 | 20191210-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing - Handfelling, brusher and feller working at landowners property, 3 labourers flagging and spotting. Float moved Feller Buncher and Brusher to this location for the work. |  |  | MacKenzie East - A030-A035 | 0 |  |  | 17 | 43814 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting69220191210-3L.O.A.2420 | Corbiere and Sons Contracting69220191210-3L.O.A.2420Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 694 | 20191210-5 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 7 | Day |  | 0 |  |  | 840 | 109.2 | 949.2 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling |  |  | Beck Road East A047-A054 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69420191210-5Chainsaw and consummables7840 | Corbiere and Sons Contracting69420191210-5Chainsaw and consummables7840Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 694 | 20191210-5 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling |  |  | Beck Road East A047-A054 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69420191210-5Light Truck - Pick up20600 | Corbiere and Sons Contracting69420191210-5Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 694 | 20191210-5 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling |  |  | Beck Road East A047-A054 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69420191210-5Foreman121140 | Corbiere and Sons Contracting69420191210-5Foreman121140Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 694 | 20191210-5 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 66 | HR |  |  |  | 0 | 4950 | 643.5 | 5593.5 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling |  |  | Beck Road East A047-A054 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69420191210-5Labourer - Specialized664950 | Corbiere and Sons Contracting69420191210-5Labourer - Specialized664950Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 694 | 20191210-5 | 53520104 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling |  |  | Beck Road East A047-A054 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69420191210-5L.O.A.71470 | Corbiere and Sons Contracting69420191210-5L.O.A.71470Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 14 | HR | 180 | 0 |  |  | 3360 | 436.8 | 3796.8 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Feller Buncher143360 | Corbiere and Sons Contracting69520191210-6Feller Buncher143360Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting69520191210-6Grinder - 4710 Peterson or equal1810022.4Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Log Loader182754 | Corbiere and Sons Contracting69520191210-6Log Loader182754Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520102 | Clearing | 0 | Mulcher | 205 | 4 | HR | 153.75 | 0 |  |  | 820 | 106.6 | 926.6 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Mulcher4820 | Corbiere and Sons Contracting69520191210-6Mulcher4820Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 820 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520101 | Clearing | 0 | Skidder | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Skidder 183078 | Corbiere and Sons Contracting69520191210-6Skidder 183078Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520102 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Skidder 91539 | Corbiere and Sons Contracting69520191210-6Skidder 91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 5 | Day |  | 0 |  |  | 600 | 78 | 678 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Chainsaw and consummables5600 | Corbiere and Sons Contracting69520191210-6Chainsaw and consummables5600Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 9 | HR | 97.88 | 0 |  |  | 1174.5 | 152.685 | 1327.185 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Excavator - 20 ton91174.5 | Corbiere and Sons Contracting69520191210-6Excavator - 20 ton91174.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1174.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Excavator - 36 ton91539 | Corbiere and Sons Contracting69520191210-6Excavator - 36 ton91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 18 | HR | 94.5 | 0 |  |  | 2268 | 294.84 | 2562.84 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Grader - Cat 12 to 14 or equal182268 | Corbiere and Sons Contracting69520191210-6Grader - Cat 12 to 14 or equal182268Inv#004-R02 | [5 empty] | 1 | 2268 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 10 | HR | 74.25 | 0 |  |  | 990 | 128.7 | 1118.7 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Loader JD 524 to 624 or equal10990 | Corbiere and Sons Contracting69520191210-6Loader JD 524 to 624 or equal10990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53510111 | Access | 0 | Sander Truck | 112.5 | 3 | HR | 84.38 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Sander Truck3337.5 | Corbiere and Sons Contracting69520191210-6Sander Truck3337.5Inv#004-R02 | [5 empty] | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Light Truck - Pick up20600 | Corbiere and Sons Contracting69520191210-6Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Light Truck - Pick up20600 | Corbiere and Sons Contracting69520191210-6Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Light Truck - Pick up20600 | Corbiere and Sons Contracting69520191210-6Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Light Truck - Pick up20600 | Corbiere and Sons Contracting69520191210-6Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Light Truck - Pick up20600 | Corbiere and Sons Contracting69520191210-6Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Light Truck - Pick up20600 | Corbiere and Sons Contracting69520191210-6Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Light Truck - Pick up10300 | Corbiere and Sons Contracting69520191210-6Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Foreman121140 | Corbiere and Sons Contracting69520191210-6Foreman121140Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Foreman121140 | Corbiere and Sons Contracting69520191210-6Foreman121140Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53510111 | Access | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Operator - Principle332970 | Corbiere and Sons Contracting69520191210-6Operator - Principle332970Inv#004-R02 | [5 empty] | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Operator - Principle332970 | Corbiere and Sons Contracting69520191210-6Operator - Principle332970Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Operator - Principle221980 | Corbiere and Sons Contracting69520191210-6Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 88 | HR |  |  |  | 0 | 7920 | 1029.6 | 8949.6 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Operator - Principle887920 | Corbiere and Sons Contracting69520191210-6Operator - Principle887920Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 7920 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 44 | HR |  |  |  | 0 | 3300 | 429 | 3729 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Labourer - Specialized443300 | Corbiere and Sons Contracting69520191210-6Labourer - Specialized443300Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 3300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520102 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6Labourer - General11715 | Corbiere and Sons Contracting69520191210-6Labourer - General11715Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53510111 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6L.O.A.3630 | Corbiere and Sons Contracting69520191210-6L.O.A.3630Inv#004-R02 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6L.O.A.2420 | Corbiere and Sons Contracting69520191210-6L.O.A.2420Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 13 | DAY |  |  |  | 0 | 2730 | 354.9 | 3084.9 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6L.O.A.132730 | Corbiere and Sons Contracting69520191210-6L.O.A.132730Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2730 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 695 | 20191210-6 | 53520104 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A099 and A105; Installing Culverts at A109-A110; Rd. Building at A105-104 and at A109-A110, Labourers rolling out GEO; Handfelling at A101 and A102; FBs and SKDs clearing at A97 and A098; Raking and Mulching at A094-A095; Graders clearing all access roads; 3 Orientations; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69520191210-6L.O.A.61260 | Corbiere and Sons Contracting69520191210-6L.O.A.61260Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 696 | 20191210-7 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at Tower B012, grader opened up Dorion Cutoff and opened up Cavern Lake Rd. Sander Truck work Dorion and Cavern Lake Rd. |  |  | Fish Hatchery A128-B017 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69620191210-7Feller Buncher92160 | Corbiere and Sons Contracting69620191210-7Feller Buncher92160Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 696 | 20191210-7 | 53520102 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at Tower B012, grader opened up Dorion Cutoff and opened up Cavern Lake Rd. Sander Truck work Dorion and Cavern Lake Rd. |  |  | Fish Hatchery A128-B017 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69620191210-7Skidder 91539 | Corbiere and Sons Contracting69620191210-7Skidder 91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 696 | 20191210-7 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at Tower B012, grader opened up Dorion Cutoff and opened up Cavern Lake Rd. Sander Truck work Dorion and Cavern Lake Rd. |  |  | Fish Hatchery A128-B017 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69620191210-7Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting69620191210-7Grader - Cat 12 to 14 or equal91134Inv#004-R02 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 696 | 20191210-7 | 53510111 | Access | 0 | Sander Truck | 112.5 | 10.5 | HR | 84.38 | 0 |  |  | 1181.25 | 153.5625 | 1334.8125 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at Tower B012, grader opened up Dorion Cutoff and opened up Cavern Lake Rd. Sander Truck work Dorion and Cavern Lake Rd. |  |  | Fish Hatchery A128-B017 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69620191210-7Sander Truck10.51181.25 | Corbiere and Sons Contracting69620191210-7Sander Truck10.51181.25Inv#004-R02 | [5 empty] | 1 | 1181.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 696 | 20191210-7 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at Tower B012, grader opened up Dorion Cutoff and opened up Cavern Lake Rd. Sander Truck work Dorion and Cavern Lake Rd. |  |  | Fish Hatchery A128-B017 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69620191210-7Light Truck - Pick up10300 | Corbiere and Sons Contracting69620191210-7Light Truck - Pick up10300Inv#004-R02 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 696 | 20191210-7 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at Tower B012, grader opened up Dorion Cutoff and opened up Cavern Lake Rd. Sander Truck work Dorion and Cavern Lake Rd. |  |  | Fish Hatchery A128-B017 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69620191210-7Light Truck - Pick up30900 | Corbiere and Sons Contracting69620191210-7Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 696 | 20191210-7 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at Tower B012, grader opened up Dorion Cutoff and opened up Cavern Lake Rd. Sander Truck work Dorion and Cavern Lake Rd. |  |  | Fish Hatchery A128-B017 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69620191210-7Foreman121140 | Corbiere and Sons Contracting69620191210-7Foreman121140Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 696 | 20191210-7 | 53510111 | Access | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at Tower B012, grader opened up Dorion Cutoff and opened up Cavern Lake Rd. Sander Truck work Dorion and Cavern Lake Rd. |  |  | Fish Hatchery A128-B017 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69620191210-7Operator - Principle221980 | Corbiere and Sons Contracting69620191210-7Operator - Principle221980Inv#004-R02 | [5 empty] | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 696 | 20191210-7 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at Tower B012, grader opened up Dorion Cutoff and opened up Cavern Lake Rd. Sander Truck work Dorion and Cavern Lake Rd. |  |  | Fish Hatchery A128-B017 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69620191210-7Operator - Principle221980 | Corbiere and Sons Contracting69620191210-7Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 696 | 20191210-7 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at Tower B012, grader opened up Dorion Cutoff and opened up Cavern Lake Rd. Sander Truck work Dorion and Cavern Lake Rd. |  |  | Fish Hatchery A128-B017 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69620191210-7L.O.A.2420 | Corbiere and Sons Contracting69620191210-7L.O.A.2420Inv#004-R02 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 696 | 20191210-7 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at Tower B012, grader opened up Dorion Cutoff and opened up Cavern Lake Rd. Sander Truck work Dorion and Cavern Lake Rd. |  |  | Fish Hatchery A128-B017 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69620191210-7L.O.A.3630 | Corbiere and Sons Contracting69620191210-7L.O.A.3630Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 697 | 20191210-8 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Night Shift Fuelling across all segments that equipment is located |  |  | All segments | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69720191210-8Light Truck - Pick up20600 | Corbiere and Sons Contracting69720191210-8Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 697 | 20191210-8 | 53520102 | Clearing | 0 | Labourer - General | 65 | 24 | HR |  |  |  | 0 | 1560 | 202.8 | 1762.8 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Night Shift Fuelling across all segments that equipment is located |  |  | All segments | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69720191210-8Labourer - General241560 | Corbiere and Sons Contracting69720191210-8Labourer - General241560Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 697 | 20191210-8 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-10 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Night Shift Fuelling across all segments that equipment is located |  |  | All segments | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting69720191210-8L.O.A.1210 | Corbiere and Sons Contracting69720191210-8L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 624 | 2019121-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6242019121-1Light Truck - Pick up501500 | Corbiere and Sons Contracting6242019121-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 624 | 2019121-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6242019121-1Project Manager121320 | Corbiere and Sons Contracting6242019121-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 624 | 2019121-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6242019121-1Superintendent121260 | Corbiere and Sons Contracting6242019121-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 624 | 2019121-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6242019121-1Project Coordinator12960 | Corbiere and Sons Contracting6242019121-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 624 | 2019121-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6242019121-1Safety Advisor121020 | Corbiere and Sons Contracting6242019121-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 624 | 2019121-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6242019121-1Project Controls12840 | Corbiere and Sons Contracting6242019121-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 624 | 2019121-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6242019121-1L.O.A.51050 | Corbiere and Sons Contracting6242019121-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 698 | 20191211-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting69820191211-1Light Truck - Pick up501500 | Corbiere and Sons Contracting69820191211-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 698 | 20191211-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting69820191211-1Project Manager121320 | Corbiere and Sons Contracting69820191211-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 698 | 20191211-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting69820191211-1Superintendent121260 | Corbiere and Sons Contracting69820191211-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 698 | 20191211-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting69820191211-1Project Coordinator12960 | Corbiere and Sons Contracting69820191211-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 698 | 20191211-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting69820191211-1Safety Advisor121020 | Corbiere and Sons Contracting69820191211-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 698 | 20191211-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting69820191211-1Project Controls12840 | Corbiere and Sons Contracting69820191211-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 698 | 20191211-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting69820191211-1L.O.A.51050 | Corbiere and Sons Contracting69820191211-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 699 | 20191211-2-R3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-11 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | labourers started all equipment in field, worked on keeping them running throughout the day, |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting69920191211-2-R3Light Truck - Pick up10300 | Corbiere and Sons Contracting69920191211-2-R3Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 699 | 20191211-2-R3 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2019-12-11 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | labourers started all equipment in field, worked on keeping them running throughout the day, |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting69920191211-2-R3Operator - Apprentice10600 | Corbiere and Sons Contracting69920191211-2-R3Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 699 | 20191211-2-R3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-11 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | labourers started all equipment in field, worked on keeping them running throughout the day, |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting69920191211-2-R3L.O.A.1210 | Corbiere and Sons Contracting69920191211-2-R3L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 699 | 20191211-2-R3 | 53520102 | Clearing | 0 | Warehouse Supervisor | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2019-12-11 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | labourers started all equipment in field, worked on keeping them running throughout the day, |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting69920191211-2-R3Warehouse Supervisor12900 | Corbiere and Sons Contracting69920191211-2-R3Warehouse Supervisor12900Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 700 | 20191211-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 3 | HR | 151.88 | 0 |  |  | 607.5 | 78.975 | 686.475 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at Landowner's property |  |  | Mackenzie East A030-A035 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70020191211-3Brusher3607.5 | Corbiere and Sons Contracting70020191211-3Brusher3607.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 607.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 700 | 20191211-3 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 3 | HR | 180 | 0 |  |  | 720 | 93.6 | 813.6 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at Landowner's property |  |  | Mackenzie East A030-A035 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70020191211-3Feller Buncher3720 | Corbiere and Sons Contracting70020191211-3Feller Buncher3720Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 700 | 20191211-3 | 53520102 | Clearing | 0 | Chainsaw and consummables | 120 | 2 | Day |  | 0 |  |  | 240 | 31.2 | 271.2 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at Landowner's property |  |  | Mackenzie East A030-A035 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70020191211-3Chainsaw and consummables2240 | Corbiere and Sons Contracting70020191211-3Chainsaw and consummables2240Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 700 | 20191211-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at Landowner's property |  |  | Mackenzie East A030-A035 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70020191211-3Light Truck - Pick up30900 | Corbiere and Sons Contracting70020191211-3Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 700 | 20191211-3 | 53520102 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at Landowner's property |  |  | Mackenzie East A030-A035 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70020191211-3Foreman4380 | Corbiere and Sons Contracting70020191211-3Foreman4380Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 700 | 20191211-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 8 | HR |  |  |  | 0 | 720 | 93.6 | 813.6 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at Landowner's property |  |  | Mackenzie East A030-A035 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70020191211-3Operator - Principle8720 | Corbiere and Sons Contracting70020191211-3Operator - Principle8720Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 700 | 20191211-3 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 12 | HR |  |  |  | 0 | 900 | 117 | 1017 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at Landowner's property |  |  | Mackenzie East A030-A035 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70020191211-3Labourer - Specialized12900 | Corbiere and Sons Contracting70020191211-3Labourer - Specialized12900Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 700 | 20191211-3 | 53520102 | Clearing | 0 | Labourer - General | 65 | 4 | HR |  |  |  | 0 | 260 | 33.8 | 293.8 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at Landowner's property |  |  | Mackenzie East A030-A035 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70020191211-3Labourer - General4260 | Corbiere and Sons Contracting70020191211-3Labourer - General4260Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 700 | 20191211-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at Landowner's property |  |  | Mackenzie East A030-A035 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70020191211-3L.O.A.71470 | Corbiere and Sons Contracting70020191211-3L.O.A.71470Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 701 | 20191211-4 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 6 | HR | 180 | 0 |  |  | 1440 | 187.2 | 1627.2 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | 1 EX, 1DZ working at KB pit, 1 EX at Pearl Pit, FB and SKD clearing towards pipeline crossing, 1 EX gravelling on Beck. |  |  | Beck Road West A036-A046 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70120191211-4Feller Buncher61440 | Corbiere and Sons Contracting70120191211-4Feller Buncher61440Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 701 | 20191211-4 | 53520102 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | 1 EX, 1DZ working at KB pit, 1 EX at Pearl Pit, FB and SKD clearing towards pipeline crossing, 1 EX gravelling on Beck. |  |  | Beck Road West A036-A046 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70120191211-4Skidder 91539 | Corbiere and Sons Contracting70120191211-4Skidder 91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 701 | 20191211-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 18 | HR |  |  |  | 0 | 1620 | 210.6 | 1830.6 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | 1 EX, 1DZ working at KB pit, 1 EX at Pearl Pit, FB and SKD clearing towards pipeline crossing, 1 EX gravelling on Beck. |  |  | Beck Road West A036-A046 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70120191211-4Operator - Principle181620 | Corbiere and Sons Contracting70120191211-4Operator - Principle181620Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1620 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 701 | 20191211-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | 1 EX, 1DZ working at KB pit, 1 EX at Pearl Pit, FB and SKD clearing towards pipeline crossing, 1 EX gravelling on Beck. |  |  | Beck Road West A036-A046 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70120191211-4L.O.A.1210 | Corbiere and Sons Contracting70120191211-4L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 15 | HR | 151.88 | 0 |  |  | 3037.5 | 394.875 | 3432.375 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Brusher153037.5 | Corbiere and Sons Contracting70420191211-5Brusher153037.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3037.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Feller Buncher92160 | Corbiere and Sons Contracting70420191211-5Feller Buncher92160Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Feller Buncher92160 | Corbiere and Sons Contracting70420191211-5Feller Buncher92160Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting70420191211-5Grinder - 4710 Peterson or equal1810022.4Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Log Loader182754 | Corbiere and Sons Contracting70420191211-5Log Loader182754Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Mulcher91845 | Corbiere and Sons Contracting70420191211-5Mulcher91845Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Skidder 91539 | Corbiere and Sons Contracting70420191211-5Skidder 91539Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520102 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Skidder 91539 | Corbiere and Sons Contracting70420191211-5Skidder 91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 5 | Day |  | 0 |  |  | 600 | 78 | 678 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Chainsaw and consummables5600 | Corbiere and Sons Contracting70420191211-5Chainsaw and consummables5600Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 8 | Day |  | 0 |  |  | 960 | 124.8 | 1084.8 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Chainsaw and consummables8960 | Corbiere and Sons Contracting70420191211-5Chainsaw and consummables8960Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 9 | HR | 97.88 | 0 |  |  | 1174.5 | 152.685 | 1327.185 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Excavator - 20 ton91174.5 | Corbiere and Sons Contracting70420191211-5Excavator - 20 ton91174.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1174.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Excavator - 36 ton91539 | Corbiere and Sons Contracting70420191211-5Excavator - 36 ton91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520102 | Clearing | 0 | Excavator - 50 ton | 189 | 9 | HR | 141.75 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Excavator - 50 ton91701 | Corbiere and Sons Contracting70420191211-5Excavator - 50 ton91701Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1701 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 20 | HR | 94.5 | 0 |  |  | 2520 | 327.6 | 2847.6 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Grader - Cat 12 to 14 or equal202520 | Corbiere and Sons Contracting70420191211-5Grader - Cat 12 to 14 or equal202520Inv#004-R02 | [5 empty] | 1 | 2520 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting70420191211-5Loader JD 524 to 624 or equal9891Inv#004-R02 | [5 empty] | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Light Truck - Pick up10300 | Corbiere and Sons Contracting70420191211-5Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Light Truck - Pick up20600 | Corbiere and Sons Contracting70420191211-5Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Light Truck - Pick up10300 | Corbiere and Sons Contracting70420191211-5Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Light Truck - Pick up601800 | Corbiere and Sons Contracting70420191211-5Light Truck - Pick up601800Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Light Truck - Pick up20600 | Corbiere and Sons Contracting70420191211-5Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Light Truck - Pick up30900 | Corbiere and Sons Contracting70420191211-5Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520102 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 11 | HR | 101.25 | 0 |  |  | 1485 | 193.05 | 1678.05 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Tractor Trailer - 60 Ton111485 | Corbiere and Sons Contracting70420191211-5Tractor Trailer - 60 Ton111485Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1485 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520102 | Clearing | 0 | Foreman | 95 | 8 | HR |  |  |  | 0 | 760 | 98.8 | 858.8 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Foreman8760 | Corbiere and Sons Contracting70420191211-5Foreman8760Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 760 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520104 | Clearing | 0 | Foreman | 95 | 24 | HR |  |  |  | 0 | 2280 | 296.4 | 2576.4 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Foreman242280 | Corbiere and Sons Contracting70420191211-5Foreman242280Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Operator - Principle11990 | Corbiere and Sons Contracting70420191211-5Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Operator - Principle11990 | Corbiere and Sons Contracting70420191211-5Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Operator - Principle221980 | Corbiere and Sons Contracting70420191211-5Operator - Principle221980Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Operator - Principle221980 | Corbiere and Sons Contracting70420191211-5Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Operator - Principle11990 | Corbiere and Sons Contracting70420191211-5Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 84 | HR |  |  |  | 0 | 7560 | 982.8 | 8542.8 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Operator - Principle847560 | Corbiere and Sons Contracting70420191211-5Operator - Principle847560Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 7560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Operator - Intermdiate11825 | Corbiere and Sons Contracting70420191211-5Operator - Intermdiate11825Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 135 | HR |  |  |  | 0 | 10125 | 1316.25 | 11441.25 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Labourer - Specialized13510125 | Corbiere and Sons Contracting70420191211-5Labourer - Specialized13510125Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 10125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53510111 | Access | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Labourer - General11715 | Corbiere and Sons Contracting70420191211-5Labourer - General11715Inv#004-R02 | [5 empty] | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520102 | Clearing | 0 | Labourer - General | 65 | 6 | HR |  |  |  | 0 | 390 | 50.7 | 440.7 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5Labourer - General6390 | Corbiere and Sons Contracting70420191211-5Labourer - General6390Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 390 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53510111 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5L.O.A.3630 | Corbiere and Sons Contracting70420191211-5L.O.A.3630Inv#004-R02 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5L.O.A.2420 | Corbiere and Sons Contracting70420191211-5L.O.A.2420Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5L.O.A.102100 | Corbiere and Sons Contracting70420191211-5L.O.A.102100Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 704 | 20191211-5 | 53520104 | Clearing | 0 | L.O.A. | 210 | 13 | DAY |  |  |  | 0 | 2730 | 354.9 | 3084.9 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A102; Handfelling from A101 to A106 and then down to A095; Labourers were flagging, escorting, spotting, installing culverts and geo; Evan and Leonard grading across all ouimet canyon access roads; FB and BR float moved; Road Building ad gravelling from A103-A105 and A109-A110; FBs and SKDs working from A116 Eastward; Raking going on from A094-A095 and from A087 |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70420191211-5L.O.A.132730 | Corbiere and Sons Contracting70420191211-5L.O.A.132730Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 2730 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 702 | 20191211-6-R1 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from B012, sanding and grading across all access roads in Fish Hatchery. |  |  |  | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70220191211-6-R1Feller Buncher92160 | Corbiere and Sons Contracting70220191211-6-R1Feller Buncher92160Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 702 | 20191211-6-R1 | 53520102 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from B012, sanding and grading across all access roads in Fish Hatchery. |  |  |  | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70220191211-6-R1Skidder 91539 | Corbiere and Sons Contracting70220191211-6-R1Skidder 91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 702 | 20191211-6-R1 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 4.5 | HR | 101.25 | 0 |  |  | 607.5 | 78.975 | 686.475 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from B012, sanding and grading across all access roads in Fish Hatchery. |  |  |  | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70220191211-6-R1Dozer D6 or equal4.5607.5 | Corbiere and Sons Contracting70220191211-6-R1Dozer D6 or equal4.5607.5Inv#004-R02 | [5 empty] | 1 | 607.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 702 | 20191211-6-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from B012, sanding and grading across all access roads in Fish Hatchery. |  |  |  | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70220191211-6-R1Light Truck - Pick up30900 | Corbiere and Sons Contracting70220191211-6-R1Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 702 | 20191211-6-R1 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from B012, sanding and grading across all access roads in Fish Hatchery. |  |  |  | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70220191211-6-R1Foreman121140 | Corbiere and Sons Contracting70220191211-6-R1Foreman121140Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 702 | 20191211-6-R1 | 53510111 | Access | 0 | Operator - Principle | 90 | 6 | HR |  |  |  | 0 | 540 | 70.2 | 610.2 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from B012, sanding and grading across all access roads in Fish Hatchery. |  |  |  | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70220191211-6-R1Operator - Principle6540 | Corbiere and Sons Contracting70220191211-6-R1Operator - Principle6540Inv#004-R02 | [5 empty] | 1 | 540 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 702 | 20191211-6-R1 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from B012, sanding and grading across all access roads in Fish Hatchery. |  |  |  | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70220191211-6-R1Operator - Principle221980 | Corbiere and Sons Contracting70220191211-6-R1Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 702 | 20191211-6-R1 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from B012, sanding and grading across all access roads in Fish Hatchery. |  |  |  | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70220191211-6-R1L.O.A.1210 | Corbiere and Sons Contracting70220191211-6-R1L.O.A.1210Inv#004-R02 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 702 | 20191211-6-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from B012, sanding and grading across all access roads in Fish Hatchery. |  |  |  | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70220191211-6-R1L.O.A.3630 | Corbiere and Sons Contracting70220191211-6-R1L.O.A.3630Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 702 | 20191211-6-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from B012, sanding and grading across all access roads in Fish Hatchery. |  |  |  | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70220191211-6-R1L.O.A.2420 | Corbiere and Sons Contracting70220191211-6-R1L.O.A.2420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 703 | 20191211-7 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Night Shift Fuelling |  |  | All Segments | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70320191211-7Light Truck - Pick up20600 | Corbiere and Sons Contracting70320191211-7Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 703 | 20191211-7 | 53520102 | Clearing | 0 | Labourer - General | 65 | 24 | HR |  |  |  | 0 | 1560 | 202.8 | 1762.8 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Night Shift Fuelling |  |  | All Segments | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70320191211-7Labourer - General241560 | Corbiere and Sons Contracting70320191211-7Labourer - General241560Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 703 | 20191211-7 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-11 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Night Shift Fuelling |  |  | All Segments | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70320191211-7L.O.A.1210 | Corbiere and Sons Contracting70320191211-7L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 705 | 20191212-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting70520191212-1Light Truck - Pick up501500 | Corbiere and Sons Contracting70520191212-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 705 | 20191212-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting70520191212-1Project Manager121320 | Corbiere and Sons Contracting70520191212-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 705 | 20191212-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting70520191212-1Superintendent121260 | Corbiere and Sons Contracting70520191212-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 705 | 20191212-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting70520191212-1Project Coordinator12960 | Corbiere and Sons Contracting70520191212-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 705 | 20191212-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting70520191212-1Safety Advisor121020 | Corbiere and Sons Contracting70520191212-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 705 | 20191212-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting70520191212-1Project Controls12840 | Corbiere and Sons Contracting70520191212-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 705 | 20191212-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting70520191212-1L.O.A.51050 | Corbiere and Sons Contracting70520191212-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 706 | 20191212-2-R3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-12 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Cold weather causing lots of equipment issues; Track put back on mulcher, fixed 460 Link Belt, weld on bucket, worked on 329 Track, CAT Buncher, new Excavators and Dozer that just arrived to prep to move into field; |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting70620191212-2-R3Light Truck - Pick up10300 | Corbiere and Sons Contracting70620191212-2-R3Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 706 | 20191212-2-R3 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2019-12-12 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Cold weather causing lots of equipment issues; Track put back on mulcher, fixed 460 Link Belt, weld on bucket, worked on 329 Track, CAT Buncher, new Excavators and Dozer that just arrived to prep to move into field; |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting70620191212-2-R3Operator - Apprentice10600 | Corbiere and Sons Contracting70620191212-2-R3Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 706 | 20191212-2-R3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-12 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Cold weather causing lots of equipment issues; Track put back on mulcher, fixed 460 Link Belt, weld on bucket, worked on 329 Track, CAT Buncher, new Excavators and Dozer that just arrived to prep to move into field; |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting70620191212-2-R3L.O.A.1210 | Corbiere and Sons Contracting70620191212-2-R3L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 706 | 20191212-2-R3 | 53520102 | Clearing | 0 | Warehouse Supervisor | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2019-12-12 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Cold weather causing lots of equipment issues; Track put back on mulcher, fixed 460 Link Belt, weld on bucket, worked on 329 Track, CAT Buncher, new Excavators and Dozer that just arrived to prep to move into field; |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting70620191212-2-R3Warehouse Supervisor12900 | Corbiere and Sons Contracting70620191212-2-R3Warehouse Supervisor12900Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 707 | 20191212-3 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing to pipeline crossing; EX gravelling towards pipeline crossing; 1 EX and 1 DZ at KB Pit; 1 EX at Pearl Pit; |  |  |  | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70720191212-3Feller Buncher92160 | Corbiere and Sons Contracting70720191212-3Feller Buncher92160Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 707 | 20191212-3 | 53520102 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing to pipeline crossing; EX gravelling towards pipeline crossing; 1 EX and 1 DZ at KB Pit; 1 EX at Pearl Pit; |  |  |  | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70720191212-3Skidder 91539 | Corbiere and Sons Contracting70720191212-3Skidder 91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 707 | 20191212-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing to pipeline crossing; EX gravelling towards pipeline crossing; 1 EX and 1 DZ at KB Pit; 1 EX at Pearl Pit; |  |  |  | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70720191212-3Light Truck - Pick up10300 | Corbiere and Sons Contracting70720191212-3Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 707 | 20191212-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing to pipeline crossing; EX gravelling towards pipeline crossing; 1 EX and 1 DZ at KB Pit; 1 EX at Pearl Pit; |  |  |  | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70720191212-3Operator - Principle221980 | Corbiere and Sons Contracting70720191212-3Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 707 | 20191212-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing to pipeline crossing; EX gravelling towards pipeline crossing; 1 EX and 1 DZ at KB Pit; 1 EX at Pearl Pit; |  |  |  | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70720191212-3L.O.A.2420 | Corbiere and Sons Contracting70720191212-3L.O.A.2420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 16 | HR | 151.88 | 0 |  |  | 3240 | 421.2 | 3661.2 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Brusher163240 | Corbiere and Sons Contracting71020191212-4Brusher163240Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 23 | HR | 180 | 0 |  |  | 5520 | 717.6 | 6237.6 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Feller Buncher235520 | Corbiere and Sons Contracting71020191212-4Feller Buncher235520Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5520 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting71020191212-4Grinder - 4710 Peterson or equal1810022.4Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Log Loader182754 | Corbiere and Sons Contracting71020191212-4Log Loader182754Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Mulcher91845 | Corbiere and Sons Contracting71020191212-4Mulcher91845Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Skidder 91539 | Corbiere and Sons Contracting71020191212-4Skidder 91539Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53520102 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Skidder 91539 | Corbiere and Sons Contracting71020191212-4Skidder 91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 15 | Day |  | 0 |  |  | 1800 | 234 | 2034 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Chainsaw and consummables151800 | Corbiere and Sons Contracting71020191212-4Chainsaw and consummables151800Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 9 | HR | 97.88 | 0 |  |  | 1174.5 | 152.685 | 1327.185 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Excavator - 20 ton91174.5 | Corbiere and Sons Contracting71020191212-4Excavator - 20 ton91174.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1174.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Excavator - 36 ton91539 | Corbiere and Sons Contracting71020191212-4Excavator - 36 ton91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53520102 | Clearing | 0 | Excavator - 50 ton | 189 | 9 | HR | 141.75 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Excavator - 50 ton91701 | Corbiere and Sons Contracting71020191212-4Excavator - 50 ton91701Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1701 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 20 | HR | 94.5 | 0 |  |  | 2520 | 327.6 | 2847.6 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Grader - Cat 12 to 14 or equal202520 | Corbiere and Sons Contracting71020191212-4Grader - Cat 12 to 14 or equal202520Inv#004-R02 | [5 empty] | 1 | 2520 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting71020191212-4Loader JD 524 to 624 or equal9891Inv#004-R02 | [5 empty] | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Light Truck - Pick up20600 | Corbiere and Sons Contracting71020191212-4Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 70 | HR | 22.5 | 0 |  |  | 2100 | 273 | 2373 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Light Truck - Pick up702100 | Corbiere and Sons Contracting71020191212-4Light Truck - Pick up702100Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Light Truck - Pick up601800 | Corbiere and Sons Contracting71020191212-4Light Truck - Pick up601800Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53510111 | Access | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Foreman4380 | Corbiere and Sons Contracting71020191212-4Foreman4380Inv#004-R02 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53520102 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Foreman4380 | Corbiere and Sons Contracting71020191212-4Foreman4380Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53520104 | Clearing | 0 | Foreman | 95 | 24 | HR |  |  |  | 0 | 2280 | 296.4 | 2576.4 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Foreman242280 | Corbiere and Sons Contracting71020191212-4Foreman242280Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Operator - Principle221980 | Corbiere and Sons Contracting71020191212-4Operator - Principle221980Inv#004-R02 | [5 empty] | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 55 | HR |  |  |  | 0 | 4950 | 643.5 | 5593.5 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Operator - Principle554950 | Corbiere and Sons Contracting71020191212-4Operator - Principle554950Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 88 | HR |  |  |  | 0 | 7920 | 1029.6 | 8949.6 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Operator - Principle887920 | Corbiere and Sons Contracting71020191212-4Operator - Principle887920Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 7920 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 143 | HR |  |  |  | 0 | 10725 | 1394.25 | 12119.25 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Labourer - Specialized14310725 | Corbiere and Sons Contracting71020191212-4Labourer - Specialized14310725Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 10725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53510111 | Access | 0 | Labourer - General | 65 | 5 | HR |  |  |  | 0 | 325 | 42.25 | 367.25 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4Labourer - General5325 | Corbiere and Sons Contracting71020191212-4Labourer - General5325Inv#004-R02 | [5 empty] | 1 | 325 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53510111 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4L.O.A.3630 | Corbiere and Sons Contracting71020191212-4L.O.A.3630Inv#004-R02 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4L.O.A.51050 | Corbiere and Sons Contracting71020191212-4L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4L.O.A.81680 | Corbiere and Sons Contracting71020191212-4L.O.A.81680Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 710 | 20191212-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 15 | DAY |  |  |  | 0 | 3150 | 409.5 | 3559.5 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinders working from A102-A103; Handfelling from A093-A095 and at A106; FBs and SKDs working at A116 E into A117; Raking, Brushing and Mulching happening at A090 down to A087 East; Gravelling and Rd. Building from A109-A110 and from A102 to A103; Labourers Fuelling, laying GEO, cleaning tracks, escorting float moves; Grading all access roads in Ouimet Canyon and accross most other segments at Valards request; |  |  | Wind Farm - A80 to A117 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71020191212-4L.O.A.153150 | Corbiere and Sons Contracting71020191212-4L.O.A.153150Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 3150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 708 | 20191212-5 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators road building from B011-B012, clearing at B011 and B013 |  |  | Fish Hatchery A128-B017 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70820191212-5Feller Buncher92160 | Corbiere and Sons Contracting70820191212-5Feller Buncher92160Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 708 | 20191212-5 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators road building from B011-B012, clearing at B011 and B013 |  |  | Fish Hatchery A128-B017 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70820191212-5Skidder 91539 | Corbiere and Sons Contracting70820191212-5Skidder 91539Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 708 | 20191212-5 | 53510111 | Access | 0 | Sander Truck | 112.5 | 9 | HR | 84.38 | 0 |  |  | 1012.5 | 131.625 | 1144.125 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators road building from B011-B012, clearing at B011 and B013 |  |  | Fish Hatchery A128-B017 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70820191212-5Sander Truck91012.5 | Corbiere and Sons Contracting70820191212-5Sander Truck91012.5Inv#004-R02 | [5 empty] | 1 | 1012.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 708 | 20191212-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators road building from B011-B012, clearing at B011 and B013 |  |  | Fish Hatchery A128-B017 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70820191212-5Light Truck - Pick up20600 | Corbiere and Sons Contracting70820191212-5Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 708 | 20191212-5 | 53520101 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators road building from B011-B012, clearing at B011 and B013 |  |  | Fish Hatchery A128-B017 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70820191212-5Foreman121140 | Corbiere and Sons Contracting70820191212-5Foreman121140Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 708 | 20191212-5 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators road building from B011-B012, clearing at B011 and B013 |  |  | Fish Hatchery A128-B017 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70820191212-5Operator - Principle11990 | Corbiere and Sons Contracting70820191212-5Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 708 | 20191212-5 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators road building from B011-B012, clearing at B011 and B013 |  |  | Fish Hatchery A128-B017 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70820191212-5Operator - Principle221980 | Corbiere and Sons Contracting70820191212-5Operator - Principle221980Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 708 | 20191212-5 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators road building from B011-B012, clearing at B011 and B013 |  |  | Fish Hatchery A128-B017 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70820191212-5L.O.A.1210 | Corbiere and Sons Contracting70820191212-5L.O.A.1210Inv#004-R02 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 708 | 20191212-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators road building from B011-B012, clearing at B011 and B013 |  |  | Fish Hatchery A128-B017 | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70820191212-5L.O.A.3630 | Corbiere and Sons Contracting70820191212-5L.O.A.3630Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 709 | 20191212-6 | 53520102 | Clearing | 1 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling all equipment in field overnight |  |  | All Areas | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70920191212-6Light Truck - Pick up20600 | Corbiere and Sons Contracting70920191212-6Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 709 | 20191212-6 | 53520102 | Clearing | 1 | Labourer - General | 65 | 24 | HR |  |  |  | 0 | 1560 | 202.8 | 1762.8 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling all equipment in field overnight |  |  | All Areas | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70920191212-6Labourer - General241560 | Corbiere and Sons Contracting70920191212-6Labourer - General241560Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 709 | 20191212-6 | 53520102 | Clearing | 1 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-12 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling all equipment in field overnight |  |  | All Areas | 0 |  |  | 37 | 43814 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting70920191212-6L.O.A.1210 | Corbiere and Sons Contracting70920191212-6L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 625 | 2019121-2-R1 | 53520102 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2019-12-03 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance; Float Moves, DZ from Eldorado to Pearl pit; Welded mount on brusher head, install hydraulic line on shovel at Canyon Rd; Servicing of equipment; Fuel Truck, BR head, Rake |  |  | Welding/Equipment Repairs/Float moves | 0 |  |  | 40 | 43967 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting6252019121-2-R1Tractor Trailer - 60 Ton91215 | Corbiere and Sons Contracting6252019121-2-R1Tractor Trailer - 60 Ton91215INV#027 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 625 | 2019121-2-R1 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-12-03 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance; Float Moves, DZ from Eldorado to Pearl pit; Welded mount on brusher head, install hydraulic line on shovel at Canyon Rd; Servicing of equipment; Fuel Truck, BR head, Rake |  |  | Welding/Equipment Repairs/Float moves | 0 |  |  | 40 | 43967 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting6252019121-2-R1Operator - Intermdiate11825 | Corbiere and Sons Contracting6252019121-2-R1Operator - Intermdiate11825INV#027 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 625 | 2019121-2-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-03 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance; Float Moves, DZ from Eldorado to Pearl pit; Welded mount on brusher head, install hydraulic line on shovel at Canyon Rd; Servicing of equipment; Fuel Truck, BR head, Rake |  |  | Welding/Equipment Repairs/Float moves | 0 |  |  | 40 | 43967 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting6252019121-2-R1L.O.A.1210 | Corbiere and Sons Contracting6252019121-2-R1L.O.A.1210INV#027 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 711 | 20191213-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting71120191213-1Light Truck - Pick up501500 | Corbiere and Sons Contracting71120191213-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 711 | 20191213-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting71120191213-1Project Manager121320 | Corbiere and Sons Contracting71120191213-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 711 | 20191213-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting71120191213-1Superintendent121260 | Corbiere and Sons Contracting71120191213-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 711 | 20191213-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting71120191213-1Project Coordinator12960 | Corbiere and Sons Contracting71120191213-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 711 | 20191213-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting71120191213-1Safety Advisor121020 | Corbiere and Sons Contracting71120191213-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 711 | 20191213-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting71120191213-1Project Controls12840 | Corbiere and Sons Contracting71120191213-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 711 | 20191213-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting71120191213-1L.O.A.51050 | Corbiere and Sons Contracting71120191213-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 712 | 20191213-2-R2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Replace hose on 336, weld grousers on mulcher, teeth for mulcher, greasing of equipment in field, starting of equipment in field due to cold. |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting71220191213-2-R2Light Truck - Pick up10300 | Corbiere and Sons Contracting71220191213-2-R2Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 712 | 20191213-2-R2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2019-12-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Replace hose on 336, weld grousers on mulcher, teeth for mulcher, greasing of equipment in field, starting of equipment in field due to cold. |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting71220191213-2-R2Operator - Apprentice10600 | Corbiere and Sons Contracting71220191213-2-R2Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 712 | 20191213-2-R2 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Replace hose on 336, weld grousers on mulcher, teeth for mulcher, greasing of equipment in field, starting of equipment in field due to cold. |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting71220191213-2-R2L.O.A.1210 | Corbiere and Sons Contracting71220191213-2-R2L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 712 | 20191213-2-R2 | 53520102 | Clearing | 0 | Warehouse Supervisor | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2019-12-13 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Replace hose on 336, weld grousers on mulcher, teeth for mulcher, greasing of equipment in field, starting of equipment in field due to cold. |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting71220191213-2-R2Warehouse Supervisor12900 | Corbiere and Sons Contracting71220191213-2-R2Warehouse Supervisor12900Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 713 | 20191213-3 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Continue clearing from A040 West; Road Gravelling and Gravel loading from pits. |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71320191213-3Feller Buncher92160 | Corbiere and Sons Contracting71320191213-3Feller Buncher92160Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 713 | 20191213-3 | 53520102 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Continue clearing from A040 West; Road Gravelling and Gravel loading from pits. |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71320191213-3Skidder 91539 | Corbiere and Sons Contracting71320191213-3Skidder 91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 713 | 20191213-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Continue clearing from A040 West; Road Gravelling and Gravel loading from pits. |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71320191213-3Light Truck - Pick up10300 | Corbiere and Sons Contracting71320191213-3Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 713 | 20191213-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Continue clearing from A040 West; Road Gravelling and Gravel loading from pits. |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71320191213-3L.O.A.2420 | Corbiere and Sons Contracting71320191213-3L.O.A.2420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 18 | HR | 151.88 | 0 |  |  | 3645 | 473.85 | 4118.85 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Brusher183645 | Corbiere and Sons Contracting71420191213-4Brusher183645Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3645 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 16 | HR | 180 | 0 |  |  | 3840 | 499.2 | 4339.2 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Feller Buncher163840 | Corbiere and Sons Contracting71420191213-4Feller Buncher163840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Feller Buncher92160 | Corbiere and Sons Contracting71420191213-4Feller Buncher92160Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting71420191213-4Grinder - 4710 Peterson or equal1810022.4Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Log Loader182754 | Corbiere and Sons Contracting71420191213-4Log Loader182754Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Mulcher91845 | Corbiere and Sons Contracting71420191213-4Mulcher91845Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Skidder 91539 | Corbiere and Sons Contracting71420191213-4Skidder 91539Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520102 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Skidder 91539 | Corbiere and Sons Contracting71420191213-4Skidder 91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 15 | Day |  | 0 |  |  | 1800 | 234 | 2034 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Chainsaw and consummables151800 | Corbiere and Sons Contracting71420191213-4Chainsaw and consummables151800Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 9 | HR | 97.88 | 0 |  |  | 1174.5 | 152.685 | 1327.185 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Excavator - 20 ton91174.5 | Corbiere and Sons Contracting71420191213-4Excavator - 20 ton91174.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1174.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Excavator - 36 ton91539 | Corbiere and Sons Contracting71420191213-4Excavator - 36 ton91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520102 | Clearing | 0 | Excavator - 50 ton | 189 | 9 | HR | 141.75 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Excavator - 50 ton91701 | Corbiere and Sons Contracting71420191213-4Excavator - 50 ton91701Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1701 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 18 | HR | 94.5 | 0 |  |  | 2268 | 294.84 | 2562.84 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Grader - Cat 12 to 14 or equal182268 | Corbiere and Sons Contracting71420191213-4Grader - Cat 12 to 14 or equal182268Inv#004-R02 | [5 empty] | 1 | 2268 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting71420191213-4Loader JD 524 to 624 or equal9891Inv#004-R02 | [5 empty] | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53510111 | Access | 0 | Sander Truck | 112.5 | 6 | HR | 84.38 | 0 |  |  | 675 | 87.75 | 762.75 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Sander Truck6675 | Corbiere and Sons Contracting71420191213-4Sander Truck6675Inv#004-R02 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Light Truck - Pick up10300 | Corbiere and Sons Contracting71420191213-4Light Truck - Pick up10300Inv#004-R02 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Light Truck - Pick up10300 | Corbiere and Sons Contracting71420191213-4Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 70 | HR | 22.5 | 0 |  |  | 2100 | 273 | 2373 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Light Truck - Pick up702100 | Corbiere and Sons Contracting71420191213-4Light Truck - Pick up702100Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Light Truck - Pick up601800 | Corbiere and Sons Contracting71420191213-4Light Truck - Pick up601800Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53510111 | Access | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Foreman4380 | Corbiere and Sons Contracting71420191213-4Foreman4380Inv#004-R02 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520102 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Foreman4380 | Corbiere and Sons Contracting71420191213-4Foreman4380Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520104 | Clearing | 0 | Foreman | 95 | 24 | HR |  |  |  | 0 | 2280 | 296.4 | 2576.4 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Foreman242280 | Corbiere and Sons Contracting71420191213-4Foreman242280Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 29 | HR |  |  |  | 0 | 2610 | 339.3 | 2949.3 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Operator - Principle292610 | Corbiere and Sons Contracting71420191213-4Operator - Principle292610Inv#004-R02 | [5 empty] | 1 | 2610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 37 | HR |  |  |  | 0 | 3330 | 432.9 | 3762.9 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Operator - Principle373330 | Corbiere and Sons Contracting71420191213-4Operator - Principle373330Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3330 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 110 | HR |  |  |  | 0 | 9900 | 1287 | 11187 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Operator - Principle1109900 | Corbiere and Sons Contracting71420191213-4Operator - Principle1109900Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 9900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 8 | HR |  |  | 70 | 0 | 600 | 78 | 678 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Operator - Intermdiate8600 | Corbiere and Sons Contracting71420191213-4Operator - Intermdiate8600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 143 | HR |  |  |  | 0 | 10725 | 1394.25 | 12119.25 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Labourer - Specialized14310725 | Corbiere and Sons Contracting71420191213-4Labourer - Specialized14310725Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 10725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53510111 | Access | 0 | Labourer - General | 65 | 6.5 | HR |  |  |  | 0 | 422.5 | 54.925 | 477.425 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4Labourer - General6.5422.5 | Corbiere and Sons Contracting71420191213-4Labourer - General6.5422.5Inv#004-R02 | [5 empty] | 1 | 422.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53510111 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4L.O.A.51050 | Corbiere and Sons Contracting71420191213-4L.O.A.51050Inv#004-R02 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4L.O.A.4840 | Corbiere and Sons Contracting71420191213-4L.O.A.4840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4L.O.A.102100 | Corbiere and Sons Contracting71420191213-4L.O.A.102100Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 714 | 20191213-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 15 | DAY |  |  |  | 0 | 3150 | 409.5 | 3559.5 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A094 and A111; Handfelling from A090, A093-A095 and at A105-A106; Road Building from A098-A099, A102-A105 and A109-A110; Culverts installed a A101; Brusher and Mulchers clearing up to A086 East; Raking hoes and Rakes; FBs and SKDs working at A116-A117; |  |  |  | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71420191213-4L.O.A.153150 | Corbiere and Sons Contracting71420191213-4L.O.A.153150Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 3150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 715 | 20191213-5 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | FB and SKD working at B013; Exs and DZ worked between B011 and B013 |  |  | Fish Hatchery A128-B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting71520191213-5Feller Buncher92160 | Corbiere and Sons Contracting71520191213-5Feller Buncher92160Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 715 | 20191213-5 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | FB and SKD working at B013; Exs and DZ worked between B011 and B013 |  |  | Fish Hatchery A128-B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting71520191213-5Skidder 91539 | Corbiere and Sons Contracting71520191213-5Skidder 91539Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 715 | 20191213-5 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | FB and SKD working at B013; Exs and DZ worked between B011 and B013 |  |  | Fish Hatchery A128-B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting71520191213-5Light Truck - Pick up20600 | Corbiere and Sons Contracting71520191213-5Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 715 | 20191213-5 | 53520101 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | FB and SKD working at B013; Exs and DZ worked between B011 and B013 |  |  | Fish Hatchery A128-B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting71520191213-5Foreman121140 | Corbiere and Sons Contracting71520191213-5Foreman121140Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 715 | 20191213-5 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | FB and SKD working at B013; Exs and DZ worked between B011 and B013 |  |  | Fish Hatchery A128-B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting71520191213-5Operator - Principle221980 | Corbiere and Sons Contracting71520191213-5Operator - Principle221980Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 715 | 20191213-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-12-13 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | FB and SKD working at B013; Exs and DZ worked between B011 and B013 |  |  | Fish Hatchery A128-B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting71520191213-5L.O.A.3630 | Corbiere and Sons Contracting71520191213-5L.O.A.3630Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 716 | 20191213-6 | 53520102 | Clearing | 1 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Night shift Fuelling |  |  | All Areas | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71620191213-6Light Truck - Pick up20600 | Corbiere and Sons Contracting71620191213-6Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 716 | 20191213-6 | 53520102 | Clearing | 1 | Labourer - General | 65 | 24 | HR |  |  |  | 0 | 1560 | 202.8 | 1762.8 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Night shift Fuelling |  |  | All Areas | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71620191213-6Labourer - General241560 | Corbiere and Sons Contracting71620191213-6Labourer - General241560Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 716 | 20191213-6 | 53520102 | Clearing | 1 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-13 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Night shift Fuelling |  |  | All Areas | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71620191213-6L.O.A.1210 | Corbiere and Sons Contracting71620191213-6L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 985 | 20191213-8 | 53510111 | Access | 0 | Sander Truck | 112.5 | 10.5 | HR | 84.38 | 0 |  |  | 1181.25 | 153.5625 | 1334.8125 | 2020-01-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Sander Truck working across access roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting98520191213-8Sander Truck10.51181.25 | Corbiere and Sons Contracting98520191213-8Sander Truck10.51181.25Inv#006R01 | [5 empty] | 1 | 1181.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 985 | 20191213-8 | 53510111 | Access | 0 | Operator - Principle | 90 | 10.5 | HR |  |  |  | 0 | 945 | 122.85 | 1067.85 | 2020-01-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Sander Truck working across access roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting98520191213-8Operator - Principle10.5945 | Corbiere and Sons Contracting98520191213-8Operator - Principle10.5945Inv#006R01 | [5 empty] | 1 | 945 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 985 | 20191213-8 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Sander Truck working across access roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting98520191213-8L.O.A.1210 | Corbiere and Sons Contracting98520191213-8L.O.A.1210Inv#006R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 717 | 20191214-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting71720191214-1Light Truck - Pick up501500 | Corbiere and Sons Contracting71720191214-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 717 | 20191214-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting71720191214-1Project Manager121320 | Corbiere and Sons Contracting71720191214-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 717 | 20191214-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting71720191214-1Superintendent121260 | Corbiere and Sons Contracting71720191214-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 717 | 20191214-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting71720191214-1Project Coordinator12960 | Corbiere and Sons Contracting71720191214-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 717 | 20191214-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting71720191214-1Safety Advisor121020 | Corbiere and Sons Contracting71720191214-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 717 | 20191214-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting71720191214-1Project Controls12840 | Corbiere and Sons Contracting71720191214-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 717 | 20191214-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43816 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting71720191214-1L.O.A.51050 | Corbiere and Sons Contracting71720191214-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 718 | 20191214-2-R2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Starting of equipment in field; Hose on EX009; Wled Grousers; Weld bucket on EX009; Prep DZ003; field calls; CAT Buncher repairs; Hitachi 3336; |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting71820191214-2-R2Light Truck - Pick up10300 | Corbiere and Sons Contracting71820191214-2-R2Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 718 | 20191214-2-R2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2019-12-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Starting of equipment in field; Hose on EX009; Wled Grousers; Weld bucket on EX009; Prep DZ003; field calls; CAT Buncher repairs; Hitachi 3336; |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting71820191214-2-R2Operator - Apprentice10600 | Corbiere and Sons Contracting71820191214-2-R2Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 718 | 20191214-2-R2 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Starting of equipment in field; Hose on EX009; Wled Grousers; Weld bucket on EX009; Prep DZ003; field calls; CAT Buncher repairs; Hitachi 3336; |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting71820191214-2-R2L.O.A.1210 | Corbiere and Sons Contracting71820191214-2-R2L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 718 | 20191214-2-R2 | 53520102 | Clearing | 0 | Warehouse Supervisor | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2019-12-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Starting of equipment in field; Hose on EX009; Wled Grousers; Weld bucket on EX009; Prep DZ003; field calls; CAT Buncher repairs; Hitachi 3336; |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting71820191214-2-R2Warehouse Supervisor12900 | Corbiere and Sons Contracting71820191214-2-R2Warehouse Supervisor12900Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 719 | 20191214-3 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Continue Road Gravel from A040 West; Cutting at A039 Westward; 1 EX at each pit and 1 DZ and KB pit; |  |  | Beck Road West A036-A046 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71920191214-3Feller Buncher92160 | Corbiere and Sons Contracting71920191214-3Feller Buncher92160Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 719 | 20191214-3 | 53520102 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Continue Road Gravel from A040 West; Cutting at A039 Westward; 1 EX at each pit and 1 DZ and KB pit; |  |  | Beck Road West A036-A046 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71920191214-3Skidder 91539 | Corbiere and Sons Contracting71920191214-3Skidder 91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 719 | 20191214-3 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Continue Road Gravel from A040 West; Cutting at A039 Westward; 1 EX at each pit and 1 DZ and KB pit; |  |  | Beck Road West A036-A046 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71920191214-3Operator - Principle11990 | Corbiere and Sons Contracting71920191214-3Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 719 | 20191214-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Continue Road Gravel from A040 West; Cutting at A039 Westward; 1 EX at each pit and 1 DZ and KB pit; |  |  | Beck Road West A036-A046 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71920191214-3Operator - Principle221980 | Corbiere and Sons Contracting71920191214-3Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 719 | 20191214-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Continue Road Gravel from A040 West; Cutting at A039 Westward; 1 EX at each pit and 1 DZ and KB pit; |  |  | Beck Road West A036-A046 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting71920191214-3L.O.A.2420 | Corbiere and Sons Contracting71920191214-3L.O.A.2420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 722 | 20191214-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 27 | HR | 151.88 | 0 |  |  | 5467.5 | 710.775 | 6178.275 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111, A094, A095 and A090; Handfelling at A093-A095, A106, A109-A111; Raking and Brushing at both A086 and A082; Rd. Building and Gravelling from A109-A110, A101-A100, and from A098 to A095; Installing culverts at A101; Labourers Rolling GEO, cleaning tracks, fuelling, escorting, flagging, spotting; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72220191214-4Brusher275467.5 | Corbiere and Sons Contracting72220191214-4Brusher275467.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5467.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 722 | 20191214-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111, A094, A095 and A090; Handfelling at A093-A095, A106, A109-A111; Raking and Brushing at both A086 and A082; Rd. Building and Gravelling from A109-A110, A101-A100, and from A098 to A095; Installing culverts at A101; Labourers Rolling GEO, cleaning tracks, fuelling, escorting, flagging, spotting; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72220191214-4Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting72220191214-4Grinder - 4710 Peterson or equal1810022.4Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 722 | 20191214-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111, A094, A095 and A090; Handfelling at A093-A095, A106, A109-A111; Raking and Brushing at both A086 and A082; Rd. Building and Gravelling from A109-A110, A101-A100, and from A098 to A095; Installing culverts at A101; Labourers Rolling GEO, cleaning tracks, fuelling, escorting, flagging, spotting; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72220191214-4Log Loader182754 | Corbiere and Sons Contracting72220191214-4Log Loader182754Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 722 | 20191214-4 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111, A094, A095 and A090; Handfelling at A093-A095, A106, A109-A111; Raking and Brushing at both A086 and A082; Rd. Building and Gravelling from A109-A110, A101-A100, and from A098 to A095; Installing culverts at A101; Labourers Rolling GEO, cleaning tracks, fuelling, escorting, flagging, spotting; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72220191214-4Mulcher91845 | Corbiere and Sons Contracting72220191214-4Mulcher91845Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 722 | 20191214-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 13 | Day |  | 0 |  |  | 1560 | 202.8 | 1762.8 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111, A094, A095 and A090; Handfelling at A093-A095, A106, A109-A111; Raking and Brushing at both A086 and A082; Rd. Building and Gravelling from A109-A110, A101-A100, and from A098 to A095; Installing culverts at A101; Labourers Rolling GEO, cleaning tracks, fuelling, escorting, flagging, spotting; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72220191214-4Chainsaw and consummables131560 | Corbiere and Sons Contracting72220191214-4Chainsaw and consummables131560Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 722 | 20191214-4 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 7 | HR | 97.88 | 0 |  |  | 913.5 | 118.755 | 1032.255 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111, A094, A095 and A090; Handfelling at A093-A095, A106, A109-A111; Raking and Brushing at both A086 and A082; Rd. Building and Gravelling from A109-A110, A101-A100, and from A098 to A095; Installing culverts at A101; Labourers Rolling GEO, cleaning tracks, fuelling, escorting, flagging, spotting; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72220191214-4Excavator - 20 ton7913.5 | Corbiere and Sons Contracting72220191214-4Excavator - 20 ton7913.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 913.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 722 | 20191214-4 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111, A094, A095 and A090; Handfelling at A093-A095, A106, A109-A111; Raking and Brushing at both A086 and A082; Rd. Building and Gravelling from A109-A110, A101-A100, and from A098 to A095; Installing culverts at A101; Labourers Rolling GEO, cleaning tracks, fuelling, escorting, flagging, spotting; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72220191214-4Excavator - 36 ton91539 | Corbiere and Sons Contracting72220191214-4Excavator - 36 ton91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 722 | 20191214-4 | 53520102 | Clearing | 0 | Excavator - 50 ton | 189 | 9 | HR | 141.75 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111, A094, A095 and A090; Handfelling at A093-A095, A106, A109-A111; Raking and Brushing at both A086 and A082; Rd. Building and Gravelling from A109-A110, A101-A100, and from A098 to A095; Installing culverts at A101; Labourers Rolling GEO, cleaning tracks, fuelling, escorting, flagging, spotting; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72220191214-4Excavator - 50 ton91701 | Corbiere and Sons Contracting72220191214-4Excavator - 50 ton91701Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1701 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 722 | 20191214-4 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 17 | HR | 94.5 | 0 |  |  | 2142 | 278.46 | 2420.46 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111, A094, A095 and A090; Handfelling at A093-A095, A106, A109-A111; Raking and Brushing at both A086 and A082; Rd. Building and Gravelling from A109-A110, A101-A100, and from A098 to A095; Installing culverts at A101; Labourers Rolling GEO, cleaning tracks, fuelling, escorting, flagging, spotting; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72220191214-4Grader - Cat 12 to 14 or equal172142 | Corbiere and Sons Contracting72220191214-4Grader - Cat 12 to 14 or equal172142Inv#004-R02 | [5 empty] | 1 | 2142 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 722 | 20191214-4 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 10 | HR | 74.25 | 0 |  |  | 990 | 128.7 | 1118.7 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111, A094, A095 and A090; Handfelling at A093-A095, A106, A109-A111; Raking and Brushing at both A086 and A082; Rd. Building and Gravelling from A109-A110, A101-A100, and from A098 to A095; Installing culverts at A101; Labourers Rolling GEO, cleaning tracks, fuelling, escorting, flagging, spotting; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72220191214-4Loader JD 524 to 624 or equal10990 | Corbiere and Sons Contracting72220191214-4Loader JD 524 to 624 or equal10990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 722 | 20191214-4 | 53510111 | Access | 0 | Sander Truck | 112.5 | 9 | HR | 84.38 | 0 |  |  | 1012.5 | 131.625 | 1144.125 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111, A094, A095 and A090; Handfelling at A093-A095, A106, A109-A111; Raking and Brushing at both A086 and A082; Rd. Building and Gravelling from A109-A110, A101-A100, and from A098 to A095; Installing culverts at A101; Labourers Rolling GEO, cleaning tracks, fuelling, escorting, flagging, spotting; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72220191214-4Sander Truck91012.5 | Corbiere and Sons Contracting72220191214-4Sander Truck91012.5Inv#004-R02 | [5 empty] | 1 | 1012.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 722 | 20191214-4 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111, A094, A095 and A090; Handfelling at A093-A095, A106, A109-A111; Raking and Brushing at both A086 and A082; Rd. Building and Gravelling from A109-A110, A101-A100, and from A098 to A095; Installing culverts at A101; Labourers Rolling GEO, cleaning tracks, fuelling, escorting, flagging, spotting; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72220191214-4Light Truck - Pick up10300 | Corbiere and Sons Contracting72220191214-4Light Truck - Pick up10300Inv#004-R02 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 722 | 20191214-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111, A094, A095 and A090; Handfelling at A093-A095, A106, A109-A111; Raking and Brushing at both A086 and A082; Rd. Building and Gravelling from A109-A110, A101-A100, and from A098 to A095; Installing culverts at A101; Labourers Rolling GEO, cleaning tracks, fuelling, escorting, flagging, spotting; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72220191214-4Light Truck - Pick up601800 | Corbiere and Sons Contracting72220191214-4Light Truck - Pick up601800Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 722 | 20191214-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111, A094, A095 and A090; Handfelling at A093-A095, A106, A109-A111; Raking and Brushing at both A086 and A082; Rd. Building and Gravelling from A109-A110, A101-A100, and from A098 to A095; Installing culverts at A101; Labourers Rolling GEO, cleaning tracks, fuelling, escorting, flagging, spotting; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72220191214-4Light Truck - Pick up501500 | Corbiere and Sons Contracting72220191214-4Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 722 | 20191214-4 | 53510111 | Access | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111, A094, A095 and A090; Handfelling at A093-A095, A106, A109-A111; Raking and Brushing at both A086 and A082; Rd. Building and Gravelling from A109-A110, A101-A100, and from A098 to A095; Installing culverts at A101; Labourers Rolling GEO, cleaning tracks, fuelling, escorting, flagging, spotting; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72220191214-4Foreman4380 | Corbiere and Sons Contracting72220191214-4Foreman4380Inv#004-R02 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 722 | 20191214-4 | 53520104 | Clearing | 0 | Foreman | 95 | 24 | HR |  |  |  | 0 | 2280 | 296.4 | 2576.4 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111, A094, A095 and A090; Handfelling at A093-A095, A106, A109-A111; Raking and Brushing at both A086 and A082; Rd. Building and Gravelling from A109-A110, A101-A100, and from A098 to A095; Installing culverts at A101; Labourers Rolling GEO, cleaning tracks, fuelling, escorting, flagging, spotting; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72220191214-4Foreman242280 | Corbiere and Sons Contracting72220191214-4Foreman242280Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 722 | 20191214-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 29 | HR |  |  |  | 0 | 2610 | 339.3 | 2949.3 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111, A094, A095 and A090; Handfelling at A093-A095, A106, A109-A111; Raking and Brushing at both A086 and A082; Rd. Building and Gravelling from A109-A110, A101-A100, and from A098 to A095; Installing culverts at A101; Labourers Rolling GEO, cleaning tracks, fuelling, escorting, flagging, spotting; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72220191214-4Operator - Principle292610 | Corbiere and Sons Contracting72220191214-4Operator - Principle292610Inv#004-R02 | [5 empty] | 1 | 2610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 722 | 20191214-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 97 | HR |  |  |  | 0 | 8730 | 1134.9 | 9864.9 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111, A094, A095 and A090; Handfelling at A093-A095, A106, A109-A111; Raking and Brushing at both A086 and A082; Rd. Building and Gravelling from A109-A110, A101-A100, and from A098 to A095; Installing culverts at A101; Labourers Rolling GEO, cleaning tracks, fuelling, escorting, flagging, spotting; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72220191214-4Operator - Principle978730 | Corbiere and Sons Contracting72220191214-4Operator - Principle978730Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 8730 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 722 | 20191214-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 121 | HR |  |  |  | 0 | 9075 | 1179.75 | 10254.75 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111, A094, A095 and A090; Handfelling at A093-A095, A106, A109-A111; Raking and Brushing at both A086 and A082; Rd. Building and Gravelling from A109-A110, A101-A100, and from A098 to A095; Installing culverts at A101; Labourers Rolling GEO, cleaning tracks, fuelling, escorting, flagging, spotting; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72220191214-4Labourer - Specialized1219075 | Corbiere and Sons Contracting72220191214-4Labourer - Specialized1219075Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 9075 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 722 | 20191214-4 | 53510111 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111, A094, A095 and A090; Handfelling at A093-A095, A106, A109-A111; Raking and Brushing at both A086 and A082; Rd. Building and Gravelling from A109-A110, A101-A100, and from A098 to A095; Installing culverts at A101; Labourers Rolling GEO, cleaning tracks, fuelling, escorting, flagging, spotting; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72220191214-4L.O.A.4840 | Corbiere and Sons Contracting72220191214-4L.O.A.4840Inv#004-R02 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 722 | 20191214-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111, A094, A095 and A090; Handfelling at A093-A095, A106, A109-A111; Raking and Brushing at both A086 and A082; Rd. Building and Gravelling from A109-A110, A101-A100, and from A098 to A095; Installing culverts at A101; Labourers Rolling GEO, cleaning tracks, fuelling, escorting, flagging, spotting; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72220191214-4L.O.A.91890 | Corbiere and Sons Contracting72220191214-4L.O.A.91890Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 722 | 20191214-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 13 | DAY |  |  |  | 0 | 2730 | 354.9 | 3084.9 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111, A094, A095 and A090; Handfelling at A093-A095, A106, A109-A111; Raking and Brushing at both A086 and A082; Rd. Building and Gravelling from A109-A110, A101-A100, and from A098 to A095; Installing culverts at A101; Labourers Rolling GEO, cleaning tracks, fuelling, escorting, flagging, spotting; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72220191214-4L.O.A.132730 | Corbiere and Sons Contracting72220191214-4L.O.A.132730Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 2730 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 720 | 20191214-5 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 18 | HR | 180 | 0 |  |  | 4320 | 561.6 | 4881.6 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A120 East |  |  | Wolf Lake Road A118-A127 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72020191214-5Feller Buncher184320 | Corbiere and Sons Contracting72020191214-5Feller Buncher184320Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 720 | 20191214-5 | 53520102 | Clearing | 0 | Skidder | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A120 East |  |  | Wolf Lake Road A118-A127 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72020191214-5Skidder 183078 | Corbiere and Sons Contracting72020191214-5Skidder 183078Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 720 | 20191214-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A120 East |  |  | Wolf Lake Road A118-A127 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72020191214-5Light Truck - Pick up30900 | Corbiere and Sons Contracting72020191214-5Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 720 | 20191214-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 48 | HR |  |  |  | 0 | 4320 | 561.6 | 4881.6 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A120 East |  |  | Wolf Lake Road A118-A127 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72020191214-5Operator - Principle484320 | Corbiere and Sons Contracting72020191214-5Operator - Principle484320Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 720 | 20191214-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A120 East |  |  | Wolf Lake Road A118-A127 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72020191214-5L.O.A.4840 | Corbiere and Sons Contracting72020191214-5L.O.A.4840Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 721 | 20191214-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling of all equipment in field overnight |  |  | All Areas | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72120191214-6Light Truck - Pick up20600 | Corbiere and Sons Contracting72120191214-6Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 721 | 20191214-6 | 53520102 | Clearing | 0 | Labourer - General | 65 | 24 | HR |  |  |  | 0 | 1560 | 202.8 | 1762.8 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling of all equipment in field overnight |  |  | All Areas | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72120191214-6Labourer - General241560 | Corbiere and Sons Contracting72120191214-6Labourer - General241560Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 721 | 20191214-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-14 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling of all equipment in field overnight |  |  | All Areas | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72120191214-6L.O.A.1210 | Corbiere and Sons Contracting72120191214-6L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 731 | 20191214-7 | 53510111 | Access | 0 | Sander Truck | 112.5 | 8 | HR | 84.38 | 0 |  |  | 900 | 117 | 1017 | 2019-12-14 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Sander off access road A090 |  |  | Wind Farm | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting73120191214-7Sander Truck8900 | Corbiere and Sons Contracting73120191214-7Sander Truck8900Inv#005-R01 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 731 | 20191214-7 | 53510111 | Access | 0 | Operator - Principle | 90 | 8 | HR |  |  |  | 0 | 720 | 93.6 | 813.6 | 2019-12-14 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Sander off access road A090 |  |  | Wind Farm | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting73120191214-7Operator - Principle8720 | Corbiere and Sons Contracting73120191214-7Operator - Principle8720Inv#005-R01 | [5 empty] | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 731 | 20191214-7 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-14 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Sander off access road A090 |  |  | Wind Farm | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting73120191214-7L.O.A.1210 | Corbiere and Sons Contracting73120191214-7L.O.A.1210Inv#005-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 986 | 20191214-9 | 53510111 | Access | 0 | Sander Truck | 112.5 | 10.5 | HR | 84.38 | 0 |  |  | 1181.25 | 153.5625 | 1334.8125 | 2020-01-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Sander Truck working across access roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting98620191214-9Sander Truck10.51181.25 | Corbiere and Sons Contracting98620191214-9Sander Truck10.51181.25Inv#006R01 | [5 empty] | 1 | 1181.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 986 | 20191214-9 | 53510111 | Access | 0 | Operator - Principle | 90 | 10.5 | HR |  |  |  | 0 | 945 | 122.85 | 1067.85 | 2020-01-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Sander Truck working across access roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting98620191214-9Operator - Principle10.5945 | Corbiere and Sons Contracting98620191214-9Operator - Principle10.5945Inv#006R01 | [5 empty] | 1 | 945 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 986 | 20191214-9 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Sander Truck working across access roads |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting98620191214-9L.O.A.1210 | Corbiere and Sons Contracting98620191214-9L.O.A.1210Inv#006R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 627 | 2019121-4-R1 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A057; Handfelling done to A59.5; Arnold and Kye Orientation and Site walk to organize plan; Install Culverts, Fueling, Cleaning Tracks,;DZ and Ex at pearl pit loading trucks and stripping for gravel; Building Access Road to A061; Brushing from A061 to A062; Sander Truck Working accross all segments; BR004 and FWFN Ex floated to Windfarm |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6272019121-4-R1Brusher91822.5 | Corbiere and Sons Contracting6272019121-4-R1Brusher91822.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 627 | 2019121-4-R1 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A057; Handfelling done to A59.5; Arnold and Kye Orientation and Site walk to organize plan; Install Culverts, Fueling, Cleaning Tracks,;DZ and Ex at pearl pit loading trucks and stripping for gravel; Building Access Road to A061; Brushing from A061 to A062; Sander Truck Working accross all segments; BR004 and FWFN Ex floated to Windfarm |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6272019121-4-R1Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting6272019121-4-R1Grinder - 4710 Peterson or equal95011.2Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 627 | 2019121-4-R1 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A057; Handfelling done to A59.5; Arnold and Kye Orientation and Site walk to organize plan; Install Culverts, Fueling, Cleaning Tracks,;DZ and Ex at pearl pit loading trucks and stripping for gravel; Building Access Road to A061; Brushing from A061 to A062; Sander Truck Working accross all segments; BR004 and FWFN Ex floated to Windfarm |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6272019121-4-R1Log Loader91377 | Corbiere and Sons Contracting6272019121-4-R1Log Loader91377Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 627 | 2019121-4-R1 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 5 | Day |  | 0 |  |  | 600 | 78 | 678 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A057; Handfelling done to A59.5; Arnold and Kye Orientation and Site walk to organize plan; Install Culverts, Fueling, Cleaning Tracks,;DZ and Ex at pearl pit loading trucks and stripping for gravel; Building Access Road to A061; Brushing from A061 to A062; Sander Truck Working accross all segments; BR004 and FWFN Ex floated to Windfarm |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6272019121-4-R1Chainsaw and consummables5600 | Corbiere and Sons Contracting6272019121-4-R1Chainsaw and consummables5600Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 627 | 2019121-4-R1 | 53510111 | Access | 0 | Sander Truck | 112.5 | 10 | HR | 84.38 | 0 |  |  | 1125 | 146.25 | 1271.25 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A057; Handfelling done to A59.5; Arnold and Kye Orientation and Site walk to organize plan; Install Culverts, Fueling, Cleaning Tracks,;DZ and Ex at pearl pit loading trucks and stripping for gravel; Building Access Road to A061; Brushing from A061 to A062; Sander Truck Working accross all segments; BR004 and FWFN Ex floated to Windfarm |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6272019121-4-R1Sander Truck101125 | Corbiere and Sons Contracting6272019121-4-R1Sander Truck101125Inv#004-R02 | [5 empty] | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 627 | 2019121-4-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A057; Handfelling done to A59.5; Arnold and Kye Orientation and Site walk to organize plan; Install Culverts, Fueling, Cleaning Tracks,;DZ and Ex at pearl pit loading trucks and stripping for gravel; Building Access Road to A061; Brushing from A061 to A062; Sander Truck Working accross all segments; BR004 and FWFN Ex floated to Windfarm |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6272019121-4-R1Light Truck - Pick up10300 | Corbiere and Sons Contracting6272019121-4-R1Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 627 | 2019121-4-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A057; Handfelling done to A59.5; Arnold and Kye Orientation and Site walk to organize plan; Install Culverts, Fueling, Cleaning Tracks,;DZ and Ex at pearl pit loading trucks and stripping for gravel; Building Access Road to A061; Brushing from A061 to A062; Sander Truck Working accross all segments; BR004 and FWFN Ex floated to Windfarm |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6272019121-4-R1Light Truck - Pick up20600 | Corbiere and Sons Contracting6272019121-4-R1Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 627 | 2019121-4-R1 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A057; Handfelling done to A59.5; Arnold and Kye Orientation and Site walk to organize plan; Install Culverts, Fueling, Cleaning Tracks,;DZ and Ex at pearl pit loading trucks and stripping for gravel; Building Access Road to A061; Brushing from A061 to A062; Sander Truck Working accross all segments; BR004 and FWFN Ex floated to Windfarm |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6272019121-4-R1Light Truck - Pick up30900 | Corbiere and Sons Contracting6272019121-4-R1Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 627 | 2019121-4-R1 | 53520104 | Clearing | 0 | Foreman | 95 | 24 | HR |  |  |  | 0 | 2280 | 296.4 | 2576.4 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A057; Handfelling done to A59.5; Arnold and Kye Orientation and Site walk to organize plan; Install Culverts, Fueling, Cleaning Tracks,;DZ and Ex at pearl pit loading trucks and stripping for gravel; Building Access Road to A061; Brushing from A061 to A062; Sander Truck Working accross all segments; BR004 and FWFN Ex floated to Windfarm |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6272019121-4-R1Foreman242280 | Corbiere and Sons Contracting6272019121-4-R1Foreman242280Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 627 | 2019121-4-R1 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A057; Handfelling done to A59.5; Arnold and Kye Orientation and Site walk to organize plan; Install Culverts, Fueling, Cleaning Tracks,;DZ and Ex at pearl pit loading trucks and stripping for gravel; Building Access Road to A061; Brushing from A061 to A062; Sander Truck Working accross all segments; BR004 and FWFN Ex floated to Windfarm |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6272019121-4-R1Operator - Principle11990 | Corbiere and Sons Contracting6272019121-4-R1Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 627 | 2019121-4-R1 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A057; Handfelling done to A59.5; Arnold and Kye Orientation and Site walk to organize plan; Install Culverts, Fueling, Cleaning Tracks,;DZ and Ex at pearl pit loading trucks and stripping for gravel; Building Access Road to A061; Brushing from A061 to A062; Sander Truck Working accross all segments; BR004 and FWFN Ex floated to Windfarm |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6272019121-4-R1Operator - Principle221980 | Corbiere and Sons Contracting6272019121-4-R1Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 627 | 2019121-4-R1 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 55 | HR |  |  |  | 0 | 4125 | 536.25 | 4661.25 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A057; Handfelling done to A59.5; Arnold and Kye Orientation and Site walk to organize plan; Install Culverts, Fueling, Cleaning Tracks,;DZ and Ex at pearl pit loading trucks and stripping for gravel; Building Access Road to A061; Brushing from A061 to A062; Sander Truck Working accross all segments; BR004 and FWFN Ex floated to Windfarm |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6272019121-4-R1Labourer - Specialized554125 | Corbiere and Sons Contracting6272019121-4-R1Labourer - Specialized554125Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 4125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 627 | 2019121-4-R1 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A057; Handfelling done to A59.5; Arnold and Kye Orientation and Site walk to organize plan; Install Culverts, Fueling, Cleaning Tracks,;DZ and Ex at pearl pit loading trucks and stripping for gravel; Building Access Road to A061; Brushing from A061 to A062; Sander Truck Working accross all segments; BR004 and FWFN Ex floated to Windfarm |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6272019121-4-R1L.O.A.1210 | Corbiere and Sons Contracting6272019121-4-R1L.O.A.1210Inv#004-R02 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 627 | 2019121-4-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A057; Handfelling done to A59.5; Arnold and Kye Orientation and Site walk to organize plan; Install Culverts, Fueling, Cleaning Tracks,;DZ and Ex at pearl pit loading trucks and stripping for gravel; Building Access Road to A061; Brushing from A061 to A062; Sander Truck Working accross all segments; BR004 and FWFN Ex floated to Windfarm |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6272019121-4-R1L.O.A.2420 | Corbiere and Sons Contracting6272019121-4-R1L.O.A.2420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 627 | 2019121-4-R1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A057; Handfelling done to A59.5; Arnold and Kye Orientation and Site walk to organize plan; Install Culverts, Fueling, Cleaning Tracks,;DZ and Ex at pearl pit loading trucks and stripping for gravel; Building Access Road to A061; Brushing from A061 to A062; Sander Truck Working accross all segments; BR004 and FWFN Ex floated to Windfarm |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6272019121-4-R1L.O.A.71470 | Corbiere and Sons Contracting6272019121-4-R1L.O.A.71470Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 723 | 20191215-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting72320191215-1Light Truck - Pick up501500 | Corbiere and Sons Contracting72320191215-1Light Truck - Pick up501500Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 723 | 20191215-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting72320191215-1Project Manager121320 | Corbiere and Sons Contracting72320191215-1Project Manager121320Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 723 | 20191215-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting72320191215-1Superintendent121260 | Corbiere and Sons Contracting72320191215-1Superintendent121260Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 723 | 20191215-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting72320191215-1Project Coordinator12960 | Corbiere and Sons Contracting72320191215-1Project Coordinator12960Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 723 | 20191215-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting72320191215-1Safety Advisor121020 | Corbiere and Sons Contracting72320191215-1Safety Advisor121020Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 723 | 20191215-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting72320191215-1Project Controls12840 | Corbiere and Sons Contracting72320191215-1Project Controls12840Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 723 | 20191215-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting72320191215-1L.O.A.51050 | Corbiere and Sons Contracting72320191215-1L.O.A.51050Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 724 | 20191215-2-R2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Welding Grousers on mulcher, starting equipment in field, repairs to 822 buncher, JD Grader, mulcher. |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting72420191215-2-R2Light Truck - Pick up10300 | Corbiere and Sons Contracting72420191215-2-R2Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 724 | 20191215-2-R2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2019-12-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Welding Grousers on mulcher, starting equipment in field, repairs to 822 buncher, JD Grader, mulcher. |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting72420191215-2-R2Operator - Apprentice10600 | Corbiere and Sons Contracting72420191215-2-R2Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 724 | 20191215-2-R2 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Welding Grousers on mulcher, starting equipment in field, repairs to 822 buncher, JD Grader, mulcher. |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting72420191215-2-R2L.O.A.1210 | Corbiere and Sons Contracting72420191215-2-R2L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 724 | 20191215-2-R2 | 53520102 | Clearing | 0 | Warehouse Supervisor | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2019-12-15 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Welding Grousers on mulcher, starting equipment in field, repairs to 822 buncher, JD Grader, mulcher. |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting72420191215-2-R2Warehouse Supervisor12900 | Corbiere and Sons Contracting72420191215-2-R2Warehouse Supervisor12900Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 725 | 20191215-3 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 6 | HR | 180 | 0 |  |  | 1440 | 187.2 | 1627.2 | 2019-12-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A039 Westward, gravelling at A040 and work from the Pits. |  |  | Beck Road West - A036-A046 | 0 |  |  | 17 | 43816 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting72520191215-3Feller Buncher61440 | Corbiere and Sons Contracting72520191215-3Feller Buncher61440Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 725 | 20191215-3 | 53520102 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A039 Westward, gravelling at A040 and work from the Pits. |  |  | Beck Road West - A036-A046 | 0 |  |  | 17 | 43816 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting72520191215-3Skidder 91539 | Corbiere and Sons Contracting72520191215-3Skidder 91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 725 | 20191215-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A039 Westward, gravelling at A040 and work from the Pits. |  |  | Beck Road West - A036-A046 | 0 |  |  | 17 | 43816 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting72520191215-3Light Truck - Pick up10300 | Corbiere and Sons Contracting72520191215-3Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 725 | 20191215-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A039 Westward, gravelling at A040 and work from the Pits. |  |  | Beck Road West - A036-A046 | 0 |  |  | 17 | 43816 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting72520191215-3Operator - Principle221980 | Corbiere and Sons Contracting72520191215-3Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 725 | 20191215-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing at A039 Westward, gravelling at A040 and work from the Pits. |  |  | Beck Road West - A036-A046 | 0 |  |  | 17 | 43816 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting72520191215-3L.O.A.2420 | Corbiere and Sons Contracting72520191215-3L.O.A.2420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 726 | 20191215-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 27 | HR | 151.88 | 0 |  |  | 5467.5 | 710.775 | 6178.275 | 2019-12-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and Raking at A076 both Eastward and Westward |  |  | Eldorado Road A055-A079 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72620191215-4Brusher275467.5 | Corbiere and Sons Contracting72620191215-4Brusher275467.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5467.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 726 | 20191215-4 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-12-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and Raking at A076 both Eastward and Westward |  |  | Eldorado Road A055-A079 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72620191215-4Mulcher91845 | Corbiere and Sons Contracting72620191215-4Mulcher91845Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 726 | 20191215-4 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and Raking at A076 both Eastward and Westward |  |  | Eldorado Road A055-A079 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72620191215-4Excavator - 36 ton91539 | Corbiere and Sons Contracting72620191215-4Excavator - 36 ton91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 726 | 20191215-4 | 53520102 | Clearing | 0 | Excavator - 50 ton | 189 | 9 | HR | 141.75 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2019-12-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and Raking at A076 both Eastward and Westward |  |  | Eldorado Road A055-A079 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72620191215-4Excavator - 50 ton91701 | Corbiere and Sons Contracting72620191215-4Excavator - 50 ton91701Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1701 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 726 | 20191215-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and Raking at A076 both Eastward and Westward |  |  | Eldorado Road A055-A079 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72620191215-4Light Truck - Pick up30900 | Corbiere and Sons Contracting72620191215-4Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 726 | 20191215-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 66 | HR |  |  |  | 0 | 5940 | 772.2 | 6712.2 | 2019-12-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and Raking at A076 both Eastward and Westward |  |  | Eldorado Road A055-A079 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72620191215-4Operator - Principle665940 | Corbiere and Sons Contracting72620191215-4Operator - Principle665940Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5940 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 726 | 20191215-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-12-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and Raking at A076 both Eastward and Westward |  |  | Eldorado Road A055-A079 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72620191215-4L.O.A.51050 | Corbiere and Sons Contracting72620191215-4L.O.A.51050Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 727 | 20191215-5-R1 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111-A106 and A094-A095; Handfelling at A089 and A093-A095; Gravelling and Road prepping from A091-A092; EX and DZ float moved to A098; Sanding all access roads; Labourers cleaning tracks, laying GEO, gathering bridge componants; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43817 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72720191215-5-R1Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting72720191215-5-R1Grinder - 4710 Peterson or equal1810022.4Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 727 | 20191215-5-R1 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111-A106 and A094-A095; Handfelling at A089 and A093-A095; Gravelling and Road prepping from A091-A092; EX and DZ float moved to A098; Sanding all access roads; Labourers cleaning tracks, laying GEO, gathering bridge componants; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43817 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72720191215-5-R1Log Loader182754 | Corbiere and Sons Contracting72720191215-5-R1Log Loader182754Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 727 | 20191215-5-R1 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 11 | Day |  | 0 |  |  | 1320 | 171.6 | 1491.6 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111-A106 and A094-A095; Handfelling at A089 and A093-A095; Gravelling and Road prepping from A091-A092; EX and DZ float moved to A098; Sanding all access roads; Labourers cleaning tracks, laying GEO, gathering bridge componants; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43817 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72720191215-5-R1Chainsaw and consummables111320 | Corbiere and Sons Contracting72720191215-5-R1Chainsaw and consummables111320Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 727 | 20191215-5-R1 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111-A106 and A094-A095; Handfelling at A089 and A093-A095; Gravelling and Road prepping from A091-A092; EX and DZ float moved to A098; Sanding all access roads; Labourers cleaning tracks, laying GEO, gathering bridge componants; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43817 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72720191215-5-R1Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting72720191215-5-R1Grader - Cat 12 to 14 or equal91134Inv#005-R01 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 727 | 20191215-5-R1 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 10 | HR | 74.25 | 0 |  |  | 990 | 128.7 | 1118.7 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111-A106 and A094-A095; Handfelling at A089 and A093-A095; Gravelling and Road prepping from A091-A092; EX and DZ float moved to A098; Sanding all access roads; Labourers cleaning tracks, laying GEO, gathering bridge componants; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43817 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72720191215-5-R1Loader JD 524 to 624 or equal10990 | Corbiere and Sons Contracting72720191215-5-R1Loader JD 524 to 624 or equal10990Inv#005-R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 727 | 20191215-5-R1 | 53510111 | Access | 0 | Sander Truck | 112.5 | 11 | HR | 84.38 | 0 |  |  | 1237.5 | 160.875 | 1398.375 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111-A106 and A094-A095; Handfelling at A089 and A093-A095; Gravelling and Road prepping from A091-A092; EX and DZ float moved to A098; Sanding all access roads; Labourers cleaning tracks, laying GEO, gathering bridge componants; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43817 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72720191215-5-R1Sander Truck111237.5 | Corbiere and Sons Contracting72720191215-5-R1Sander Truck111237.5Inv#005-R01 | [5 empty] | 1 | 1237.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 727 | 20191215-5-R1 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111-A106 and A094-A095; Handfelling at A089 and A093-A095; Gravelling and Road prepping from A091-A092; EX and DZ float moved to A098; Sanding all access roads; Labourers cleaning tracks, laying GEO, gathering bridge componants; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43817 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72720191215-5-R1Light Truck - Pick up10300 | Corbiere and Sons Contracting72720191215-5-R1Light Truck - Pick up10300Inv#005-R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 727 | 20191215-5-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111-A106 and A094-A095; Handfelling at A089 and A093-A095; Gravelling and Road prepping from A091-A092; EX and DZ float moved to A098; Sanding all access roads; Labourers cleaning tracks, laying GEO, gathering bridge componants; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43817 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72720191215-5-R1Light Truck - Pick up20600 | Corbiere and Sons Contracting72720191215-5-R1Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 727 | 20191215-5-R1 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111-A106 and A094-A095; Handfelling at A089 and A093-A095; Gravelling and Road prepping from A091-A092; EX and DZ float moved to A098; Sanding all access roads; Labourers cleaning tracks, laying GEO, gathering bridge componants; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43817 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72720191215-5-R1Light Truck - Pick up501500 | Corbiere and Sons Contracting72720191215-5-R1Light Truck - Pick up501500Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 727 | 20191215-5-R1 | 53510111 | Access | 0 | Tractor Trailer - 60 Ton | 135 | 11 | HR | 101.25 | 0 |  |  | 1485 | 193.05 | 1678.05 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111-A106 and A094-A095; Handfelling at A089 and A093-A095; Gravelling and Road prepping from A091-A092; EX and DZ float moved to A098; Sanding all access roads; Labourers cleaning tracks, laying GEO, gathering bridge componants; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43817 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72720191215-5-R1Tractor Trailer - 60 Ton111485 | Corbiere and Sons Contracting72720191215-5-R1Tractor Trailer - 60 Ton111485Inv#005-R01 | [5 empty] | 1 | 1485 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 727 | 20191215-5-R1 | 53510111 | Access | 0 | Foreman | 95 | 6 | HR |  |  |  | 0 | 570 | 74.1 | 644.1 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111-A106 and A094-A095; Handfelling at A089 and A093-A095; Gravelling and Road prepping from A091-A092; EX and DZ float moved to A098; Sanding all access roads; Labourers cleaning tracks, laying GEO, gathering bridge componants; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43817 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72720191215-5-R1Foreman6570 | Corbiere and Sons Contracting72720191215-5-R1Foreman6570Inv#005-R01 | [5 empty] | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 727 | 20191215-5-R1 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111-A106 and A094-A095; Handfelling at A089 and A093-A095; Gravelling and Road prepping from A091-A092; EX and DZ float moved to A098; Sanding all access roads; Labourers cleaning tracks, laying GEO, gathering bridge componants; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43817 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72720191215-5-R1Foreman121140 | Corbiere and Sons Contracting72720191215-5-R1Foreman121140Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 727 | 20191215-5-R1 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111-A106 and A094-A095; Handfelling at A089 and A093-A095; Gravelling and Road prepping from A091-A092; EX and DZ float moved to A098; Sanding all access roads; Labourers cleaning tracks, laying GEO, gathering bridge componants; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43817 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72720191215-5-R1Foreman121140 | Corbiere and Sons Contracting72720191215-5-R1Foreman121140Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 727 | 20191215-5-R1 | 53510111 | Access | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111-A106 and A094-A095; Handfelling at A089 and A093-A095; Gravelling and Road prepping from A091-A092; EX and DZ float moved to A098; Sanding all access roads; Labourers cleaning tracks, laying GEO, gathering bridge componants; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43817 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72720191215-5-R1Operator - Principle221980 | Corbiere and Sons Contracting72720191215-5-R1Operator - Principle221980Inv#005-R01 | [5 empty] | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 727 | 20191215-5-R1 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111-A106 and A094-A095; Handfelling at A089 and A093-A095; Gravelling and Road prepping from A091-A092; EX and DZ float moved to A098; Sanding all access roads; Labourers cleaning tracks, laying GEO, gathering bridge componants; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43817 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72720191215-5-R1Operator - Principle221980 | Corbiere and Sons Contracting72720191215-5-R1Operator - Principle221980Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 727 | 20191215-5-R1 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 44 | HR |  |  |  | 0 | 3300 | 429 | 3729 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111-A106 and A094-A095; Handfelling at A089 and A093-A095; Gravelling and Road prepping from A091-A092; EX and DZ float moved to A098; Sanding all access roads; Labourers cleaning tracks, laying GEO, gathering bridge componants; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43817 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72720191215-5-R1Labourer - Specialized443300 | Corbiere and Sons Contracting72720191215-5-R1Labourer - Specialized443300Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 3300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 727 | 20191215-5-R1 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 55 | HR |  |  |  | 0 | 4125 | 536.25 | 4661.25 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111-A106 and A094-A095; Handfelling at A089 and A093-A095; Gravelling and Road prepping from A091-A092; EX and DZ float moved to A098; Sanding all access roads; Labourers cleaning tracks, laying GEO, gathering bridge componants; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43817 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72720191215-5-R1Labourer - Specialized554125 | Corbiere and Sons Contracting72720191215-5-R1Labourer - Specialized554125Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 4125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 727 | 20191215-5-R1 | 53510111 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111-A106 and A094-A095; Handfelling at A089 and A093-A095; Gravelling and Road prepping from A091-A092; EX and DZ float moved to A098; Sanding all access roads; Labourers cleaning tracks, laying GEO, gathering bridge componants; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43817 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72720191215-5-R1L.O.A.3630 | Corbiere and Sons Contracting72720191215-5-R1L.O.A.3630Inv#005-R01 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 727 | 20191215-5-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111-A106 and A094-A095; Handfelling at A089 and A093-A095; Gravelling and Road prepping from A091-A092; EX and DZ float moved to A098; Sanding all access roads; Labourers cleaning tracks, laying GEO, gathering bridge componants; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43817 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72720191215-5-R1L.O.A.2420 | Corbiere and Sons Contracting72720191215-5-R1L.O.A.2420Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 727 | 20191215-5-R1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 11 | DAY |  |  |  | 0 | 2310 | 300.3 | 2610.3 | 2019-12-15 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A111-A106 and A094-A095; Handfelling at A089 and A093-A095; Gravelling and Road prepping from A091-A092; EX and DZ float moved to A098; Sanding all access roads; Labourers cleaning tracks, laying GEO, gathering bridge componants; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43817 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72720191215-5-R1L.O.A.112310 | Corbiere and Sons Contracting72720191215-5-R1L.O.A.112310Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 728 | 20191215-6 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 27 | HR | 180 | 0 |  |  | 6480 | 842.4 | 7322.4 | 2019-12-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Cutting from A122-A124 |  |  | Wolf Lake Road A118-A127 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72820191215-6Feller Buncher276480 | Corbiere and Sons Contracting72820191215-6Feller Buncher276480Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 6480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 728 | 20191215-6 | 53520102 | Clearing | 0 | Skidder | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2019-12-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Cutting from A122-A124 |  |  | Wolf Lake Road A118-A127 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72820191215-6Skidder 183078 | Corbiere and Sons Contracting72820191215-6Skidder 183078Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 728 | 20191215-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Cutting from A122-A124 |  |  | Wolf Lake Road A118-A127 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72820191215-6Light Truck - Pick up30900 | Corbiere and Sons Contracting72820191215-6Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 728 | 20191215-6 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 55 | HR |  |  |  | 0 | 4950 | 643.5 | 5593.5 | 2019-12-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Cutting from A122-A124 |  |  | Wolf Lake Road A118-A127 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72820191215-6Operator - Principle554950 | Corbiere and Sons Contracting72820191215-6Operator - Principle554950Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 728 | 20191215-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Cutting from A122-A124 |  |  | Wolf Lake Road A118-A127 | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72820191215-6L.O.A.4840 | Corbiere and Sons Contracting72820191215-6L.O.A.4840Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 729 | 20191215-7 | 53520102 | Clearing | 1 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling of Equipment overnight at all areas where equipment is located in field. |  |  | all areas | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72920191215-7Light Truck - Pick up20600 | Corbiere and Sons Contracting72920191215-7Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 729 | 20191215-7 | 53520102 | Clearing | 1 | Labourer - General | 65 | 24 | HR |  |  |  | 0 | 1560 | 202.8 | 1762.8 | 2019-12-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling of Equipment overnight at all areas where equipment is located in field. |  |  | all areas | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72920191215-7Labourer - General241560 | Corbiere and Sons Contracting72920191215-7Labourer - General241560Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 729 | 20191215-7 | 53520102 | Clearing | 1 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-15 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling of Equipment overnight at all areas where equipment is located in field. |  |  | all areas | 0 |  |  | 37 | 43816 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting72920191215-7L.O.A.1210 | Corbiere and Sons Contracting72920191215-7L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 628 | 2019121-5-R1 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A115-A111; MUL broke down at 1 PM; Gravelling at A111; Raking and Brushing between A109 and A111; Feller Bunchers and Skidders from A090 to A087 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6282019121-5-R1Brusher91822.5 | Corbiere and Sons Contracting6282019121-5-R1Brusher91822.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 628 | 2019121-5-R1 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 36 | HR | 180 | 0 |  |  | 8640 | 1123.2 | 9763.2 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A115-A111; MUL broke down at 1 PM; Gravelling at A111; Raking and Brushing between A109 and A111; Feller Bunchers and Skidders from A090 to A087 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6282019121-5-R1Feller Buncher368640 | Corbiere and Sons Contracting6282019121-5-R1Feller Buncher368640Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 8640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 628 | 2019121-5-R1 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A115-A111; MUL broke down at 1 PM; Gravelling at A111; Raking and Brushing between A109 and A111; Feller Bunchers and Skidders from A090 to A087 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6282019121-5-R1Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting6282019121-5-R1Grinder - 4710 Peterson or equal95011.2Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 628 | 2019121-5-R1 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A115-A111; MUL broke down at 1 PM; Gravelling at A111; Raking and Brushing between A109 and A111; Feller Bunchers and Skidders from A090 to A087 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6282019121-5-R1Log Loader91377 | Corbiere and Sons Contracting6282019121-5-R1Log Loader91377Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 628 | 2019121-5-R1 | 53520102 | Clearing | 0 | Mulcher | 205 | 5 | HR | 153.75 | 0 |  |  | 1025 | 133.25 | 1158.25 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A115-A111; MUL broke down at 1 PM; Gravelling at A111; Raking and Brushing between A109 and A111; Feller Bunchers and Skidders from A090 to A087 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6282019121-5-R1Mulcher51025 | Corbiere and Sons Contracting6282019121-5-R1Mulcher51025Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1025 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 628 | 2019121-5-R1 | 53520102 | Clearing | 0 | Skidder | 171 | 27 | HR | 128.25 | 0 |  |  | 4617 | 600.21 | 5217.21 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A115-A111; MUL broke down at 1 PM; Gravelling at A111; Raking and Brushing between A109 and A111; Feller Bunchers and Skidders from A090 to A087 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6282019121-5-R1Skidder 274617 | Corbiere and Sons Contracting6282019121-5-R1Skidder 274617Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 628 | 2019121-5-R1 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A115-A111; MUL broke down at 1 PM; Gravelling at A111; Raking and Brushing between A109 and A111; Feller Bunchers and Skidders from A090 to A087 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6282019121-5-R1Excavator - 36 ton91539 | Corbiere and Sons Contracting6282019121-5-R1Excavator - 36 ton91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 628 | 2019121-5-R1 | 53520102 | Clearing | 0 | Excavator - 50 ton | 189 | 9 | HR | 141.75 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A115-A111; MUL broke down at 1 PM; Gravelling at A111; Raking and Brushing between A109 and A111; Feller Bunchers and Skidders from A090 to A087 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6282019121-5-R1Excavator - 50 ton91701 | Corbiere and Sons Contracting6282019121-5-R1Excavator - 50 ton91701Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1701 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 628 | 2019121-5-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A115-A111; MUL broke down at 1 PM; Gravelling at A111; Raking and Brushing between A109 and A111; Feller Bunchers and Skidders from A090 to A087 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6282019121-5-R1Light Truck - Pick up10300 | Corbiere and Sons Contracting6282019121-5-R1Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 628 | 2019121-5-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A115-A111; MUL broke down at 1 PM; Gravelling at A111; Raking and Brushing between A109 and A111; Feller Bunchers and Skidders from A090 to A087 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6282019121-5-R1Light Truck - Pick up401200 | Corbiere and Sons Contracting6282019121-5-R1Light Truck - Pick up401200Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 628 | 2019121-5-R1 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 110 | HR |  |  |  | 0 | 9900 | 1287 | 11187 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A115-A111; MUL broke down at 1 PM; Gravelling at A111; Raking and Brushing between A109 and A111; Feller Bunchers and Skidders from A090 to A087 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6282019121-5-R1Operator - Principle1109900 | Corbiere and Sons Contracting6282019121-5-R1Operator - Principle1109900Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 9900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 628 | 2019121-5-R1 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A115-A111; MUL broke down at 1 PM; Gravelling at A111; Raking and Brushing between A109 and A111; Feller Bunchers and Skidders from A090 to A087 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6282019121-5-R1Operator - Intermdiate11825 | Corbiere and Sons Contracting6282019121-5-R1Operator - Intermdiate11825Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 628 | 2019121-5-R1 | 53520102 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A115-A111; MUL broke down at 1 PM; Gravelling at A111; Raking and Brushing between A109 and A111; Feller Bunchers and Skidders from A090 to A087 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6282019121-5-R1Labourer - General11715 | Corbiere and Sons Contracting6282019121-5-R1Labourer - General11715Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 628 | 2019121-5-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding at A115-A111; MUL broke down at 1 PM; Gravelling at A111; Raking and Brushing between A109 and A111; Feller Bunchers and Skidders from A090 to A087 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6282019121-5-R1L.O.A.102100 | Corbiere and Sons Contracting6282019121-5-R1L.O.A.102100Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 949 | 2019121-6 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 |  | HR | 94.5 | 18 |  |  | 1701 | 221.13 | 1922.13 | 2019-12-03 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Standby-Ticket 2019121-5 + 2019121-4 |  |  |  | 0 |  |  | 12 | 43843 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting9492019121-6Grader - Cat 12 to 14 or equal1701 | Corbiere and Sons Contracting9492019121-6Grader - Cat 12 to 14 or equal1701Inv#006R01 | [5 empty] | 1 | 1701 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 732 | 20191216-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting73220191216-1Light Truck - Pick up501500 | Corbiere and Sons Contracting73220191216-1Light Truck - Pick up501500Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 732 | 20191216-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting73220191216-1Project Manager121320 | Corbiere and Sons Contracting73220191216-1Project Manager121320Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 732 | 20191216-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting73220191216-1Superintendent121260 | Corbiere and Sons Contracting73220191216-1Superintendent121260Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 732 | 20191216-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting73220191216-1Project Coordinator12960 | Corbiere and Sons Contracting73220191216-1Project Coordinator12960Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 732 | 20191216-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting73220191216-1Safety Advisor121020 | Corbiere and Sons Contracting73220191216-1Safety Advisor121020Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 732 | 20191216-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting73220191216-1Project Controls12840 | Corbiere and Sons Contracting73220191216-1Project Controls12840Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 732 | 20191216-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting73220191216-1L.O.A.51050 | Corbiere and Sons Contracting73220191216-1L.O.A.51050Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 733 | 20191216-2-R2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-16 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Greasing of Equipment, parts running, repairs to grader, service truck, welding. |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting73320191216-2-R2Light Truck - Pick up10300 | Corbiere and Sons Contracting73320191216-2-R2Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 733 | 20191216-2-R2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2019-12-16 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Greasing of Equipment, parts running, repairs to grader, service truck, welding. |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting73320191216-2-R2Operator - Apprentice10600 | Corbiere and Sons Contracting73320191216-2-R2Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 733 | 20191216-2-R2 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-16 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Greasing of Equipment, parts running, repairs to grader, service truck, welding. |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting73320191216-2-R2L.O.A.1210 | Corbiere and Sons Contracting73320191216-2-R2L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 733 | 20191216-2-R2 | 53520102 | Clearing | 0 | Warehouse Supervisor | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2019-12-16 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Greasing of Equipment, parts running, repairs to grader, service truck, welding. |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting73320191216-2-R2Warehouse Supervisor12900 | Corbiere and Sons Contracting73320191216-2-R2Warehouse Supervisor12900Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 734 | 20191216-3 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-16 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Gravelling and road building from A039; clearing down to A037; gravel loading at both pits. |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting73420191216-3Feller Buncher92160 | Corbiere and Sons Contracting73420191216-3Feller Buncher92160Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 734 | 20191216-3 | 53520102 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-16 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Gravelling and road building from A039; clearing down to A037; gravel loading at both pits. |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting73420191216-3Skidder 91539 | Corbiere and Sons Contracting73420191216-3Skidder 91539Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 734 | 20191216-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-16 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Gravelling and road building from A039; clearing down to A037; gravel loading at both pits. |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting73420191216-3Light Truck - Pick up10300 | Corbiere and Sons Contracting73420191216-3Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 734 | 20191216-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-16 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Gravelling and road building from A039; clearing down to A037; gravel loading at both pits. |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting73420191216-3Operator - Principle221980 | Corbiere and Sons Contracting73420191216-3Operator - Principle221980Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 734 | 20191216-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-16 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Gravelling and road building from A039; clearing down to A037; gravel loading at both pits. |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting73420191216-3L.O.A.2420 | Corbiere and Sons Contracting73420191216-3L.O.A.2420Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 735 | 20191216-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 27 | HR | 151.88 | 0 |  |  | 5467.5 | 710.775 | 6178.275 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and raking from A073-A071 and then started walking out to A080 to end of shift. |  | Eldorado A055-A079 |  | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73520191216-4Brusher275467.5 | Corbiere and Sons Contracting73520191216-4Brusher275467.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5467.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 735 | 20191216-4 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and raking from A073-A071 and then started walking out to A080 to end of shift. |  | Eldorado A055-A079 |  | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73520191216-4Mulcher91845 | Corbiere and Sons Contracting73520191216-4Mulcher91845Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 735 | 20191216-4 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and raking from A073-A071 and then started walking out to A080 to end of shift. |  | Eldorado A055-A079 |  | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73520191216-4Excavator - 36 ton91539 | Corbiere and Sons Contracting73520191216-4Excavator - 36 ton91539Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 735 | 20191216-4 | 53520102 | Clearing | 0 | Excavator - 50 ton | 189 | 9 | HR | 141.75 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and raking from A073-A071 and then started walking out to A080 to end of shift. |  | Eldorado A055-A079 |  | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73520191216-4Excavator - 50 ton91701 | Corbiere and Sons Contracting73520191216-4Excavator - 50 ton91701Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1701 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 735 | 20191216-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and raking from A073-A071 and then started walking out to A080 to end of shift. |  | Eldorado A055-A079 |  | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73520191216-4Light Truck - Pick up30900 | Corbiere and Sons Contracting73520191216-4Light Truck - Pick up30900Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 735 | 20191216-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 66 | HR |  |  |  | 0 | 5940 | 772.2 | 6712.2 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and raking from A073-A071 and then started walking out to A080 to end of shift. |  | Eldorado A055-A079 |  | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73520191216-4Operator - Principle665940 | Corbiere and Sons Contracting73520191216-4Operator - Principle665940Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5940 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 735 | 20191216-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Brushing and raking from A073-A071 and then started walking out to A080 to end of shift. |  | Eldorado A055-A079 |  | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73520191216-4L.O.A.61260 | Corbiere and Sons Contracting73520191216-4L.O.A.61260Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting73920191216-5Grinder - 4710 Peterson or equal95011.2Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting73920191216-5Grinder - 4710 Peterson or equal95011.2Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Log Loader91377 | Corbiere and Sons Contracting73920191216-5Log Loader91377Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Log Loader91377 | Corbiere and Sons Contracting73920191216-5Log Loader91377Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 14 | Day |  | 0 |  |  | 1680 | 218.4 | 1898.4 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Chainsaw and consummables141680 | Corbiere and Sons Contracting73920191216-5Chainsaw and consummables141680Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 9 | HR | 97.88 | 0 |  |  | 1174.5 | 152.685 | 1327.185 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Excavator - 20 ton91174.5 | Corbiere and Sons Contracting73920191216-5Excavator - 20 ton91174.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1174.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 18 | HR | 94.5 | 0 |  |  | 2268 | 294.84 | 2562.84 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Grader - Cat 12 to 14 or equal182268 | Corbiere and Sons Contracting73920191216-5Grader - Cat 12 to 14 or equal182268Inv#005-R01 | [5 empty] | 1 | 2268 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 10 | HR | 74.25 | 0 |  |  | 990 | 128.7 | 1118.7 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Loader JD 524 to 624 or equal10990 | Corbiere and Sons Contracting73920191216-5Loader JD 524 to 624 or equal10990Inv#005-R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53510111 | Access | 0 | Sander Truck | 112.5 | 11 | HR | 84.38 | 0 |  |  | 1237.5 | 160.875 | 1398.375 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Sander Truck111237.5 | Corbiere and Sons Contracting73920191216-5Sander Truck111237.5Inv#005-R01 | [5 empty] | 1 | 1237.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Light Truck - Pick up10300 | Corbiere and Sons Contracting73920191216-5Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Light Truck - Pick up10300 | Corbiere and Sons Contracting73920191216-5Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Light Truck - Pick up10300 | Corbiere and Sons Contracting73920191216-5Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 60 | HR | 22.5 | 0 |  |  | 1800 | 234 | 2034 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Light Truck - Pick up601800 | Corbiere and Sons Contracting73920191216-5Light Truck - Pick up601800Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53520102 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 11 | HR | 101.25 | 0 |  |  | 1485 | 193.05 | 1678.05 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Tractor Trailer - 60 Ton111485 | Corbiere and Sons Contracting73920191216-5Tractor Trailer - 60 Ton111485Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1485 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Foreman121140 | Corbiere and Sons Contracting73920191216-5Foreman121140Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Foreman121140 | Corbiere and Sons Contracting73920191216-5Foreman121140Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53510111 | Access | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Operator - Principle332970 | Corbiere and Sons Contracting73920191216-5Operator - Principle332970Inv#005-R01 | [5 empty] | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Operator - Principle221980 | Corbiere and Sons Contracting73920191216-5Operator - Principle221980Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Operator - Principle11990 | Corbiere and Sons Contracting73920191216-5Operator - Principle11990Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Operator - Intermdiate11825 | Corbiere and Sons Contracting73920191216-5Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 22 | HR |  |  |  | 0 | 1650 | 214.5 | 1864.5 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Labourer - Specialized221650 | Corbiere and Sons Contracting73920191216-5Labourer - Specialized221650Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 33 | HR |  |  |  | 0 | 2475 | 321.75 | 2796.75 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Labourer - Specialized332475 | Corbiere and Sons Contracting73920191216-5Labourer - Specialized332475Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 77 | HR |  |  |  | 0 | 5775 | 750.75 | 6525.75 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5Labourer - Specialized775775 | Corbiere and Sons Contracting73920191216-5Labourer - Specialized775775Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 5775 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53510111 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5L.O.A.3630 | Corbiere and Sons Contracting73920191216-5L.O.A.3630Inv#005-R01 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5L.O.A.4840 | Corbiere and Sons Contracting73920191216-5L.O.A.4840Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 739 | 20191216-5 | 53520104 | Clearing | 0 | L.O.A. | 210 | 14 | DAY |  |  |  | 0 | 2940 | 382.2 | 3322.2 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A090, A094-A095; Handfelling done from A089-A093; Bridge Installation at A098; Rd. Building and Gravelling at A091, A092, A098 and from A100-A101; Labourers spotting trucks; cleaning tracks, laying GEO, installing culvert; Log Loader and Grinder float moved; Grading and Sanding accross access roads; |  |  | Wind Farm A080-A117 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73920191216-5L.O.A.142940 | Corbiere and Sons Contracting73920191216-5L.O.A.142940Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 2940 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 736 | 20191216-6 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 18 | HR | 180 | 0 |  |  | 4320 | 561.6 | 4881.6 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A122 into A124 |  |  | Wolf Lake Road - A118-A127 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73620191216-6Feller Buncher184320 | Corbiere and Sons Contracting73620191216-6Feller Buncher184320Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 736 | 20191216-6 | 53520101 | Clearing | 0 | Skidder | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A122 into A124 |  |  | Wolf Lake Road - A118-A127 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73620191216-6Skidder 183078 | Corbiere and Sons Contracting73620191216-6Skidder 183078Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 736 | 20191216-6 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A122 into A124 |  |  | Wolf Lake Road - A118-A127 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73620191216-6Light Truck - Pick up30900 | Corbiere and Sons Contracting73620191216-6Light Truck - Pick up30900Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 736 | 20191216-6 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A122 into A124 |  |  | Wolf Lake Road - A118-A127 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73620191216-6Operator - Principle443960 | Corbiere and Sons Contracting73620191216-6Operator - Principle443960Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 736 | 20191216-6 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A122 into A124 |  |  | Wolf Lake Road - A118-A127 | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73620191216-6L.O.A.3630 | Corbiere and Sons Contracting73620191216-6L.O.A.3630Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 737 | 20191216-7 | 53520102 | Clearing | 0 | Brusher | 202.5 | 1 | HR | 151.88 | 0 |  |  | 202.5 | 26.325 | 228.825 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Road building at B012-B013; FB and SKD working at B006-B007; DZ widening road from B001-B005; raking and brushing from B012-B013; 2 orientations. |  |  | Fish Hatchery Road A128-B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting73720191216-7Brusher1202.5 | Corbiere and Sons Contracting73720191216-7Brusher1202.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 202.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 737 | 20191216-7 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Road building at B012-B013; FB and SKD working at B006-B007; DZ widening road from B001-B005; raking and brushing from B012-B013; 2 orientations. |  |  | Fish Hatchery Road A128-B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting73720191216-7Feller Buncher92160 | Corbiere and Sons Contracting73720191216-7Feller Buncher92160Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 737 | 20191216-7 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Road building at B012-B013; FB and SKD working at B006-B007; DZ widening road from B001-B005; raking and brushing from B012-B013; 2 orientations. |  |  | Fish Hatchery Road A128-B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting73720191216-7Skidder 91539 | Corbiere and Sons Contracting73720191216-7Skidder 91539Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 737 | 20191216-7 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 2 | HR | 128.25 | 0 |  |  | 342 | 44.46 | 386.46 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Road building at B012-B013; FB and SKD working at B006-B007; DZ widening road from B001-B005; raking and brushing from B012-B013; 2 orientations. |  |  | Fish Hatchery Road A128-B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting73720191216-7Excavator - 36 ton2342 | Corbiere and Sons Contracting73720191216-7Excavator - 36 ton2342Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 342 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 737 | 20191216-7 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton | 13.5 | 2 | HR | 10.13 | 0 |  |  | 27 | 3.51 | 30.51 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Road building at B012-B013; FB and SKD working at B006-B007; DZ widening road from B001-B005; raking and brushing from B012-B013; 2 orientations. |  |  | Fish Hatchery Road A128-B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting73720191216-7Excavator Thumb - 30 - 50 ton227 | Corbiere and Sons Contracting73720191216-7Excavator Thumb - 30 - 50 ton227Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 27 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 737 | 20191216-7 | 53520101 | Clearing | 0 | Grader - Cat 12 to 14 or equal | 126 | 6 | HR | 94.5 | 0 |  |  | 756 | 98.28 | 854.28 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Road building at B012-B013; FB and SKD working at B006-B007; DZ widening road from B001-B005; raking and brushing from B012-B013; 2 orientations. |  |  | Fish Hatchery Road A128-B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting73720191216-7Grader - Cat 12 to 14 or equal6756 | Corbiere and Sons Contracting73720191216-7Grader - Cat 12 to 14 or equal6756Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 756 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 737 | 20191216-7 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Road building at B012-B013; FB and SKD working at B006-B007; DZ widening road from B001-B005; raking and brushing from B012-B013; 2 orientations. |  |  | Fish Hatchery Road A128-B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting73720191216-7Light Truck - Pick up20600 | Corbiere and Sons Contracting73720191216-7Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 737 | 20191216-7 | 53520101 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Road building at B012-B013; FB and SKD working at B006-B007; DZ widening road from B001-B005; raking and brushing from B012-B013; 2 orientations. |  |  | Fish Hatchery Road A128-B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting73720191216-7Foreman121140 | Corbiere and Sons Contracting73720191216-7Foreman121140Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 737 | 20191216-7 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Road building at B012-B013; FB and SKD working at B006-B007; DZ widening road from B001-B005; raking and brushing from B012-B013; 2 orientations. |  |  | Fish Hatchery Road A128-B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting73720191216-7Operator - Principle221980 | Corbiere and Sons Contracting73720191216-7Operator - Principle221980Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 737 | 20191216-7 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Road building at B012-B013; FB and SKD working at B006-B007; DZ widening road from B001-B005; raking and brushing from B012-B013; 2 orientations. |  |  | Fish Hatchery Road A128-B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting73720191216-7Operator - Principle11990 | Corbiere and Sons Contracting73720191216-7Operator - Principle11990Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 737 | 20191216-7 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Road building at B012-B013; FB and SKD working at B006-B007; DZ widening road from B001-B005; raking and brushing from B012-B013; 2 orientations. |  |  | Fish Hatchery Road A128-B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting73720191216-7L.O.A.3630 | Corbiere and Sons Contracting73720191216-7L.O.A.3630Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 737 | 20191216-7 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Road building at B012-B013; FB and SKD working at B006-B007; DZ widening road from B001-B005; raking and brushing from B012-B013; 2 orientations. |  |  | Fish Hatchery Road A128-B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting73720191216-7L.O.A.2420 | Corbiere and Sons Contracting73720191216-7L.O.A.2420Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 738 | 20191216-8 | 53520102 | Clearing | 1 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fueling of equipment in field overnight |  |  |  | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73820191216-8Light Truck - Pick up20600 | Corbiere and Sons Contracting73820191216-8Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 738 | 20191216-8 | 53520102 | Clearing | 1 | Labourer - General | 65 | 24 | HR |  |  |  | 0 | 1560 | 202.8 | 1762.8 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fueling of equipment in field overnight |  |  |  | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73820191216-8Labourer - General241560 | Corbiere and Sons Contracting73820191216-8Labourer - General241560Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 738 | 20191216-8 | 53520102 | Clearing | 1 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-16 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fueling of equipment in field overnight |  |  |  | 0 |  |  | 37 | 43818 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting73820191216-8L.O.A.1210 | Corbiere and Sons Contracting73820191216-8L.O.A.1210Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 740 | 20191217-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting74020191217-1Light Truck - Pick up501500 | Corbiere and Sons Contracting74020191217-1Light Truck - Pick up501500Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 740 | 20191217-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting74020191217-1Project Manager121320 | Corbiere and Sons Contracting74020191217-1Project Manager121320Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 740 | 20191217-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting74020191217-1Superintendent121260 | Corbiere and Sons Contracting74020191217-1Superintendent121260Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 740 | 20191217-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting74020191217-1Project Coordinator12960 | Corbiere and Sons Contracting74020191217-1Project Coordinator12960Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 740 | 20191217-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting74020191217-1Safety Advisor121020 | Corbiere and Sons Contracting74020191217-1Safety Advisor121020Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 740 | 20191217-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting74020191217-1Project Controls12840 | Corbiere and Sons Contracting74020191217-1Project Controls12840Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 740 | 20191217-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting74020191217-1L.O.A.51050 | Corbiere and Sons Contracting74020191217-1L.O.A.51050Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 742 | 20191217-2-R3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-19 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Wash new 350 Linkbelt; Run Parts; Work on Grader, 350 Hitachi, JD Mulcher, welding of Sandtruck; |  |  | General Yard Maintenance and Equipment Repair | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting74220191217-2-R3Light Truck - Pick up10300 | Corbiere and Sons Contracting74220191217-2-R3Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 742 | 20191217-2-R3 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2019-12-19 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Wash new 350 Linkbelt; Run Parts; Work on Grader, 350 Hitachi, JD Mulcher, welding of Sandtruck; |  |  | General Yard Maintenance and Equipment Repair | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting74220191217-2-R3Operator - Apprentice10600 | Corbiere and Sons Contracting74220191217-2-R3Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 742 | 20191217-2-R3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-19 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Wash new 350 Linkbelt; Run Parts; Work on Grader, 350 Hitachi, JD Mulcher, welding of Sandtruck; |  |  | General Yard Maintenance and Equipment Repair | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting74220191217-2-R3L.O.A.1210 | Corbiere and Sons Contracting74220191217-2-R3L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 742 | 20191217-2-R3 | 53520102 | Clearing | 0 | Warehouse Supervisor | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2019-12-19 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Wash new 350 Linkbelt; Run Parts; Work on Grader, 350 Hitachi, JD Mulcher, welding of Sandtruck; |  |  | General Yard Maintenance and Equipment Repair | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting74220191217-2-R3Warehouse Supervisor12900 | Corbiere and Sons Contracting74220191217-2-R3Warehouse Supervisor12900Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 743 | 20191217-3 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-19 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourer laying GEO, installing silt fencing, cleaning tracks; Clearing at A038; Loading Gravel trucks at pits; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting74320191217-3Feller Buncher92160 | Corbiere and Sons Contracting74320191217-3Feller Buncher92160Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 743 | 20191217-3 | 53520102 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-19 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourer laying GEO, installing silt fencing, cleaning tracks; Clearing at A038; Loading Gravel trucks at pits; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting74320191217-3Skidder 91539 | Corbiere and Sons Contracting74320191217-3Skidder 91539Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 743 | 20191217-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-19 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourer laying GEO, installing silt fencing, cleaning tracks; Clearing at A038; Loading Gravel trucks at pits; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting74320191217-3Light Truck - Pick up10300 | Corbiere and Sons Contracting74320191217-3Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 743 | 20191217-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-19 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourer laying GEO, installing silt fencing, cleaning tracks; Clearing at A038; Loading Gravel trucks at pits; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting74320191217-3Operator - Principle11990 | Corbiere and Sons Contracting74320191217-3Operator - Principle11990Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 743 | 20191217-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-19 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourer laying GEO, installing silt fencing, cleaning tracks; Clearing at A038; Loading Gravel trucks at pits; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting74320191217-3Operator - Principle11990 | Corbiere and Sons Contracting74320191217-3Operator - Principle11990Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 743 | 20191217-3 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-12-19 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourer laying GEO, installing silt fencing, cleaning tracks; Clearing at A038; Loading Gravel trucks at pits; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting74320191217-3L.O.A.3630 | Corbiere and Sons Contracting74320191217-3L.O.A.3630Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 743 | 20191217-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-19 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourer laying GEO, installing silt fencing, cleaning tracks; Clearing at A038; Loading Gravel trucks at pits; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting74320191217-3L.O.A.2420 | Corbiere and Sons Contracting74320191217-3L.O.A.2420Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 744 | 20191217-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 21 | HR | 151.88 | 0 |  |  | 4252.5 | 552.825 | 4805.325 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and Brushing at A072-A073 |  |  | Eldorado - A055 to A079 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting74420191217-4Brusher214252.5 | Corbiere and Sons Contracting74420191217-4Brusher214252.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4252.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 744 | 20191217-4 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and Brushing at A072-A073 |  |  | Eldorado - A055 to A079 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting74420191217-4Excavator - 36 ton91539 | Corbiere and Sons Contracting74420191217-4Excavator - 36 ton91539Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 744 | 20191217-4 | 53520102 | Clearing | 0 | Excavator - 50 ton | 189 | 9 | HR | 141.75 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and Brushing at A072-A073 |  |  | Eldorado - A055 to A079 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting74420191217-4Excavator - 50 ton91701 | Corbiere and Sons Contracting74420191217-4Excavator - 50 ton91701Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1701 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 744 | 20191217-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and Brushing at A072-A073 |  |  | Eldorado - A055 to A079 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting74420191217-4Light Truck - Pick up30900 | Corbiere and Sons Contracting74420191217-4Light Truck - Pick up30900Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 744 | 20191217-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 55 | HR |  |  |  | 0 | 4950 | 643.5 | 5593.5 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and Brushing at A072-A073 |  |  | Eldorado - A055 to A079 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting74420191217-4Operator - Principle554950 | Corbiere and Sons Contracting74420191217-4Operator - Principle554950Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 744 | 20191217-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and Brushing at A072-A073 |  |  | Eldorado - A055 to A079 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting74420191217-4L.O.A.51050 | Corbiere and Sons Contracting74420191217-4L.O.A.51050Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 18 | HR | 151.88 | 0 |  |  | 3645 | 473.85 | 4118.85 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Brusher183645 | Corbiere and Sons Contracting74520191217-5Brusher183645Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3645 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting74520191217-5Grinder - 4710 Peterson or equal95011.2Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting74520191217-5Grinder - 4710 Peterson or equal95011.2Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Log Loader91377 | Corbiere and Sons Contracting74520191217-5Log Loader91377Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Log Loader91377 | Corbiere and Sons Contracting74520191217-5Log Loader91377Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 6 | Day |  | 0 |  |  | 720 | 93.6 | 813.6 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Chainsaw and consummables6720 | Corbiere and Sons Contracting74520191217-5Chainsaw and consummables6720Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 7 | Day |  | 0 |  |  | 840 | 109.2 | 949.2 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Chainsaw and consummables7840 | Corbiere and Sons Contracting74520191217-5Chainsaw and consummables7840Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Excavator - 36 ton91539 | Corbiere and Sons Contracting74520191217-5Excavator - 36 ton91539Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520102 | Clearing | 0 | Excavator - 50 ton | 189 | 9 | HR | 141.75 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Excavator - 50 ton91701 | Corbiere and Sons Contracting74520191217-5Excavator - 50 ton91701Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1701 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting74520191217-5Grader - Cat 12 to 14 or equal91134Inv#005-R01 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 10 | HR | 74.25 | 0 |  |  | 990 | 128.7 | 1118.7 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Loader JD 524 to 624 or equal10990 | Corbiere and Sons Contracting74520191217-5Loader JD 524 to 624 or equal10990Inv#005-R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53510111 | Access | 0 | Sander Truck | 112.5 | 10 | HR | 84.38 | 0 |  |  | 1125 | 146.25 | 1271.25 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Sander Truck101125 | Corbiere and Sons Contracting74520191217-5Sander Truck101125Inv#005-R01 | [5 empty] | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Light Truck - Pick up10300 | Corbiere and Sons Contracting74520191217-5Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Light Truck - Pick up10300 | Corbiere and Sons Contracting74520191217-5Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Light Truck - Pick up30900 | Corbiere and Sons Contracting74520191217-5Light Truck - Pick up30900Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Light Truck - Pick up30900 | Corbiere and Sons Contracting74520191217-5Light Truck - Pick up30900Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Light Truck - Pick up30900 | Corbiere and Sons Contracting74520191217-5Light Truck - Pick up30900Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53510111 | Access | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting74520191217-5Tractor Trailer - 60 Ton101350Inv#005-R01 | [5 empty] | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53510111 | Access | 0 | Foreman | 95 | 3 | HR |  |  |  | 0 | 285 | 37.05 | 322.05 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Foreman3285 | Corbiere and Sons Contracting74520191217-5Foreman3285Inv#005-R01 | [5 empty] | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Foreman121140 | Corbiere and Sons Contracting74520191217-5Foreman121140Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Foreman121140 | Corbiere and Sons Contracting74520191217-5Foreman121140Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53510111 | Access | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Operator - Principle221980 | Corbiere and Sons Contracting74520191217-5Operator - Principle221980Inv#005-R01 | [5 empty] | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Operator - Principle221980 | Corbiere and Sons Contracting74520191217-5Operator - Principle221980Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Operator - Principle443960 | Corbiere and Sons Contracting74520191217-5Operator - Principle443960Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Operator - Intermdiate11825 | Corbiere and Sons Contracting74520191217-5Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 22 | HR |  |  |  | 0 | 1650 | 214.5 | 1864.5 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Labourer - Specialized221650 | Corbiere and Sons Contracting74520191217-5Labourer - Specialized221650Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 33 | HR |  |  |  | 0 | 2475 | 321.75 | 2796.75 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Labourer - Specialized332475 | Corbiere and Sons Contracting74520191217-5Labourer - Specialized332475Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 66 | HR |  |  |  | 0 | 4950 | 643.5 | 5593.5 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5Labourer - Specialized664950 | Corbiere and Sons Contracting74520191217-5Labourer - Specialized664950Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53510111 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5L.O.A.3630 | Corbiere and Sons Contracting74520191217-5L.O.A.3630Inv#005-R01 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5L.O.A.61260 | Corbiere and Sons Contracting74520191217-5L.O.A.61260Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 745 | 20191217-5 | 53520104 | Clearing | 0 | L.O.A. | 210 | 13 | DAY |  |  |  | 0 | 2730 | 354.9 | 3084.9 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of material at A085 and A082; Handfelling at A093-A094, and A087-A089; DZ widening at A101-A100 and then down to A093-A095; Pat working on bridge build up at A098; Gravelling from A090-A092 and A102; Road Preppings from A093 up to A098; Loader starting in pit; Labourers flagging for trucks and working with D6 on gravel push outs; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74520191217-5L.O.A.132730 | Corbiere and Sons Contracting74520191217-5L.O.A.132730Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 2730 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1594 | 20191217-6-R1 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 27 | HR | 180 | 0 |  |  | 6480 | 842.4 | 7322.4 | 2019-12-17 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  |  | 0 |  |  | 0 | 43819 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting159420191217-6-R1Feller Buncher276480 | Corbiere and Sons Contracting159420191217-6-R1Feller Buncher276480Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 6480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1594 | 20191217-6-R1 | 53520102 | Clearing | 0 | Skidder | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2019-12-17 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  |  | 0 |  |  | 0 | 43819 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting159420191217-6-R1Skidder 183078 | Corbiere and Sons Contracting159420191217-6-R1Skidder 183078Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1594 | 20191217-6-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-17 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  |  | 0 |  |  | 0 | 43819 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting159420191217-6-R1Light Truck - Pick up30900 | Corbiere and Sons Contracting159420191217-6-R1Light Truck - Pick up30900Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1594 | 20191217-6-R1 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 55 | HR |  |  |  | 0 | 4950 | 643.5 | 5593.5 | 2019-12-17 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  |  | 0 |  |  | 0 | 43819 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting159420191217-6-R1Operator - Principle554950 | Corbiere and Sons Contracting159420191217-6-R1Operator - Principle554950Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1594 | 20191217-6-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-17 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  |  | 0 |  |  | 0 | 43819 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting159420191217-6-R1L.O.A.4840 | Corbiere and Sons Contracting159420191217-6-R1L.O.A.4840Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 748 | 20191217-7 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Installing Bridge at B006; FB and SKD working at B007; DZ working at B006; EX and BR raking and brushing at B011; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting74820191217-7Brusher91822.5 | Corbiere and Sons Contracting74820191217-7Brusher91822.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 748 | 20191217-7 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Installing Bridge at B006; FB and SKD working at B007; DZ working at B006; EX and BR raking and brushing at B011; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting74820191217-7Feller Buncher92160 | Corbiere and Sons Contracting74820191217-7Feller Buncher92160Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 748 | 20191217-7 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Installing Bridge at B006; FB and SKD working at B007; DZ working at B006; EX and BR raking and brushing at B011; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting74820191217-7Skidder 91539 | Corbiere and Sons Contracting74820191217-7Skidder 91539Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 748 | 20191217-7 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Installing Bridge at B006; FB and SKD working at B007; DZ working at B006; EX and BR raking and brushing at B011; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting74820191217-7Excavator - 36 ton91539 | Corbiere and Sons Contracting74820191217-7Excavator - 36 ton91539Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 748 | 20191217-7 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton | 13.5 | 9 | HR | 10.13 | 0 |  |  | 121.5 | 15.795 | 137.295 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Installing Bridge at B006; FB and SKD working at B007; DZ working at B006; EX and BR raking and brushing at B011; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting74820191217-7Excavator Thumb - 30 - 50 ton9121.5 | Corbiere and Sons Contracting74820191217-7Excavator Thumb - 30 - 50 ton9121.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 121.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 748 | 20191217-7 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Installing Bridge at B006; FB and SKD working at B007; DZ working at B006; EX and BR raking and brushing at B011; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting74820191217-7Light Truck - Pick up501500 | Corbiere and Sons Contracting74820191217-7Light Truck - Pick up501500Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 748 | 20191217-7 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Installing Bridge at B006; FB and SKD working at B007; DZ working at B006; EX and BR raking and brushing at B011; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting74820191217-7Operator - Principle11990 | Corbiere and Sons Contracting74820191217-7Operator - Principle11990Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 748 | 20191217-7 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Installing Bridge at B006; FB and SKD working at B007; DZ working at B006; EX and BR raking and brushing at B011; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting74820191217-7Operator - Principle11990 | Corbiere and Sons Contracting74820191217-7Operator - Principle11990Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 748 | 20191217-7 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Installing Bridge at B006; FB and SKD working at B007; DZ working at B006; EX and BR raking and brushing at B011; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting74820191217-7Operator - Principle11990 | Corbiere and Sons Contracting74820191217-7Operator - Principle11990Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 748 | 20191217-7 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Installing Bridge at B006; FB and SKD working at B007; DZ working at B006; EX and BR raking and brushing at B011; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting74820191217-7Operator - Principle11990 | Corbiere and Sons Contracting74820191217-7Operator - Principle11990Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 748 | 20191217-7 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Installing Bridge at B006; FB and SKD working at B007; DZ working at B006; EX and BR raking and brushing at B011; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting74820191217-7L.O.A.2420 | Corbiere and Sons Contracting74820191217-7L.O.A.2420Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 748 | 20191217-7 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Installing Bridge at B006; FB and SKD working at B007; DZ working at B006; EX and BR raking and brushing at B011; |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting74820191217-7L.O.A.2420 | Corbiere and Sons Contracting74820191217-7L.O.A.2420Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 749 | 20191217-8 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Night Shift Fuelling |  |  | All Segments where equipment is located | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74920191217-8Light Truck - Pick up20600 | Corbiere and Sons Contracting74920191217-8Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 749 | 20191217-8 | 53520102 | Clearing | 0 | Labourer - General | 65 | 24 | HR |  |  |  | 0 | 1560 | 202.8 | 1762.8 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Night Shift Fuelling |  |  | All Segments where equipment is located | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74920191217-8Labourer - General241560 | Corbiere and Sons Contracting74920191217-8Labourer - General241560Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 749 | 20191217-8 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-19 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Night Shift Fuelling |  |  | All Segments where equipment is located | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting74920191217-8L.O.A.1210 | Corbiere and Sons Contracting74920191217-8L.O.A.1210Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 750 | 20191218-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 0 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting75020191218-1Light Truck - Pick up501500 | Corbiere and Sons Contracting75020191218-1Light Truck - Pick up501500Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 750 | 20191218-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  | 0 | 0 | 1320 | 171.6 | 1491.6 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting75020191218-1Project Manager121320 | Corbiere and Sons Contracting75020191218-1Project Manager121320Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 750 | 20191218-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  | 0 | 0 | 1260 | 163.8 | 1423.8 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting75020191218-1Superintendent121260 | Corbiere and Sons Contracting75020191218-1Superintendent121260Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 750 | 20191218-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  | 0 | 0 | 960 | 124.8 | 1084.8 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting75020191218-1Project Coordinator12960 | Corbiere and Sons Contracting75020191218-1Project Coordinator12960Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 750 | 20191218-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  | 0 | 0 | 1020 | 132.6 | 1152.6 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting75020191218-1Safety Advisor121020 | Corbiere and Sons Contracting75020191218-1Safety Advisor121020Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 750 | 20191218-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  | 0 | 0 | 840 | 109.2 | 949.2 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting75020191218-1Project Controls12840 | Corbiere and Sons Contracting75020191218-1Project Controls12840Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 750 | 20191218-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  | 0 | 0 | 1050 | 136.5 | 1186.5 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting75020191218-1L.O.A.51050 | Corbiere and Sons Contracting75020191218-1L.O.A.51050Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 751 | 20191218-2-R2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-20 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting75120191218-2-R2Light Truck - Pick up10300 | Corbiere and Sons Contracting75120191218-2-R2Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 751 | 20191218-2-R2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2019-12-20 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting75120191218-2-R2Operator - Apprentice10600 | Corbiere and Sons Contracting75120191218-2-R2Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 751 | 20191218-2-R2 | 53520102 | Clearing | 0 | L.O.A. | 210 | 0 | DAY |  |  |  | 0 | 0 | 0 | 0 | 2019-12-20 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting75120191218-2-R2L.O.A.00 | Corbiere and Sons Contracting75120191218-2-R2L.O.A.00Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 0 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 752 | 20191218-3 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 3 | HR | 180 | 0 |  |  | 720 | 93.6 | 813.6 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Exs working at Gravel pits; Clearing at A037 going West; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 8 | 43819 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting75220191218-3Feller Buncher3720 | Corbiere and Sons Contracting75220191218-3Feller Buncher3720Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 752 | 20191218-3 | 53520102 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Exs working at Gravel pits; Clearing at A037 going West; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 8 | 43819 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting75220191218-3Skidder 91539 | Corbiere and Sons Contracting75220191218-3Skidder 91539Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 752 | 20191218-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Exs working at Gravel pits; Clearing at A037 going West; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 8 | 43819 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting75220191218-3Light Truck - Pick up10300 | Corbiere and Sons Contracting75220191218-3Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 752 | 20191218-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 35 | HR |  |  |  | 0 | 3150 | 409.5 | 3559.5 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Exs working at Gravel pits; Clearing at A037 going West; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 8 | 43819 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting75220191218-3Operator - Principle353150 | Corbiere and Sons Contracting75220191218-3Operator - Principle353150Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 752 | 20191218-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Exs working at Gravel pits; Clearing at A037 going West; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 8 | 43819 | [5 empty] | Gord Pidcock | 01 | Corbiere and Sons Contracting75220191218-3L.O.A.51050 | Corbiere and Sons Contracting75220191218-3L.O.A.51050Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 753 | 20191218-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 18 | HR | 151.88 | 0 |  |  | 3645 | 473.85 | 4118.85 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finishing Brushing from A076-A072 and then start walking equipment to A082-A084; |  |  | Eldorado - A055 to A079 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75320191218-4Brusher183645 | Corbiere and Sons Contracting75320191218-4Brusher183645Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3645 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 753 | 20191218-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finishing Brushing from A076-A072 and then start walking equipment to A082-A084; |  |  | Eldorado - A055 to A079 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75320191218-4Light Truck - Pick up10300 | Corbiere and Sons Contracting75320191218-4Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 753 | 20191218-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finishing Brushing from A076-A072 and then start walking equipment to A082-A084; |  |  | Eldorado - A055 to A079 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75320191218-4Operator - Principle221980 | Corbiere and Sons Contracting75320191218-4Operator - Principle221980Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 753 | 20191218-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finishing Brushing from A076-A072 and then start walking equipment to A082-A084; |  |  | Eldorado - A055 to A079 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75320191218-4L.O.A.2420 | Corbiere and Sons Contracting75320191218-4L.O.A.2420Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5Brusher91822.5 | Corbiere and Sons Contracting75420191218-5Brusher91822.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53520102 | Clearing | 0 | Mulcher | 205 | 4 | HR | 153.75 | 0 |  |  | 820 | 106.6 | 926.6 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5Mulcher4820 | Corbiere and Sons Contracting75420191218-5Mulcher4820Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 820 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 8 | Day |  | 0 |  |  | 960 | 124.8 | 1084.8 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5Chainsaw and consummables8960 | Corbiere and Sons Contracting75420191218-5Chainsaw and consummables8960Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 6 | Day |  | 0 |  |  | 720 | 93.6 | 813.6 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5Chainsaw and consummables6720 | Corbiere and Sons Contracting75420191218-5Chainsaw and consummables6720Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 9 | HR | 97.88 | 0 |  |  | 1174.5 | 152.685 | 1327.185 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5Excavator - 20 ton91174.5 | Corbiere and Sons Contracting75420191218-5Excavator - 20 ton91174.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1174.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5Excavator - 36 ton91539 | Corbiere and Sons Contracting75420191218-5Excavator - 36 ton91539Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53520102 | Clearing | 0 | Excavator - 50 ton | 189 | 7 | HR | 141.75 | 0 |  |  | 1323 | 171.99 | 1494.99 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5Excavator - 50 ton71323 | Corbiere and Sons Contracting75420191218-5Excavator - 50 ton71323Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1323 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 6 | HR | 74.25 | 0 |  |  | 594 | 77.22 | 671.22 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5Loader JD 524 to 624 or equal6594 | Corbiere and Sons Contracting75420191218-5Loader JD 524 to 624 or equal6594Inv#005-R01 | [5 empty] | 1 | 594 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53510111 | Access | 0 | Sander Truck | 112.5 | 11 | HR | 84.38 | 0 |  |  | 1237.5 | 160.875 | 1398.375 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5Sander Truck111237.5 | Corbiere and Sons Contracting75420191218-5Sander Truck111237.5Inv#005-R01 | [5 empty] | 1 | 1237.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5Light Truck - Pick up20600 | Corbiere and Sons Contracting75420191218-5Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5Light Truck - Pick up20600 | Corbiere and Sons Contracting75420191218-5Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5Light Truck - Pick up20600 | Corbiere and Sons Contracting75420191218-5Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5Light Truck - Pick up30900 | Corbiere and Sons Contracting75420191218-5Light Truck - Pick up30900Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5Light Truck - Pick up30900 | Corbiere and Sons Contracting75420191218-5Light Truck - Pick up30900Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5Foreman121140 | Corbiere and Sons Contracting75420191218-5Foreman121140Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5Foreman121140 | Corbiere and Sons Contracting75420191218-5Foreman121140Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5Operator - Principle11990 | Corbiere and Sons Contracting75420191218-5Operator - Principle11990Inv#005-R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 8 | HR |  |  |  | 0 | 720 | 93.6 | 813.6 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5Operator - Principle8720 | Corbiere and Sons Contracting75420191218-5Operator - Principle8720Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5Operator - Principle11990 | Corbiere and Sons Contracting75420191218-5Operator - Principle11990Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 64 | HR |  |  |  | 0 | 5760 | 748.8 | 6508.8 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5Operator - Principle645760 | Corbiere and Sons Contracting75420191218-5Operator - Principle645760Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5760 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 99 | HR |  |  |  | 0 | 7425 | 965.25 | 8390.25 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5Labourer - Specialized997425 | Corbiere and Sons Contracting75420191218-5Labourer - Specialized997425Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 7425 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 33 | HR |  |  |  | 0 | 2475 | 321.75 | 2796.75 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5Labourer - Specialized332475 | Corbiere and Sons Contracting75420191218-5Labourer - Specialized332475Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5L.O.A.1210 | Corbiere and Sons Contracting75420191218-5L.O.A.1210Inv#005-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 11 | DAY |  |  |  | 0 | 2310 | 300.3 | 2610.3 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5L.O.A.112310 | Corbiere and Sons Contracting75420191218-5L.O.A.112310Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 754 | 20191218-5 | 53520104 | Clearing | 0 | L.O.A. | 210 | 14 | DAY |  |  |  | 0 | 2940 | 382.2 | 3322.2 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Couldn't get the grinders running in the cold weather, operators waited at site and then sent home; Handfelling from A089 to A091-A093; Finished Prepping road at A090, installed culvert and moved down to A088; Gravelling, Road Prepping and Building from A87-A092; Labourers laying out GEO, flagging, spotting. 4 New Operators in Orientations, Finish Brushing at A080-A081 and move to A082-A084; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75420191218-5L.O.A.142940 | Corbiere and Sons Contracting75420191218-5L.O.A.142940Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 2940 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 760 | 20191218-6 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 24 | HR | 180 | 0 |  |  | 5760 | 748.8 | 6508.8 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Cut road into A124; Cut Across Wet Land into A126 to A127 |  |  | Wolf Lake Road - A118 to A127 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting76020191218-6Feller Buncher245760 | Corbiere and Sons Contracting76020191218-6Feller Buncher245760Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5760 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 760 | 20191218-6 | 53520102 | Clearing | 0 | Skidder | 171 | 17 | HR | 128.25 | 0 |  |  | 2907 | 377.91 | 3284.91 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Cut road into A124; Cut Across Wet Land into A126 to A127 |  |  | Wolf Lake Road - A118 to A127 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting76020191218-6Skidder 172907 | Corbiere and Sons Contracting76020191218-6Skidder 172907Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2907 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 760 | 20191218-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Cut road into A124; Cut Across Wet Land into A126 to A127 |  |  | Wolf Lake Road - A118 to A127 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting76020191218-6Light Truck - Pick up30900 | Corbiere and Sons Contracting76020191218-6Light Truck - Pick up30900Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 760 | 20191218-6 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 55 | HR |  |  |  | 0 | 4950 | 643.5 | 5593.5 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Cut road into A124; Cut Across Wet Land into A126 to A127 |  |  | Wolf Lake Road - A118 to A127 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting76020191218-6Operator - Principle554950 | Corbiere and Sons Contracting76020191218-6Operator - Principle554950Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 760 | 20191218-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Cut road into A124; Cut Across Wet Land into A126 to A127 |  |  | Wolf Lake Road - A118 to A127 | 0 | [10 empty] | 01 | Corbiere and Sons Contracting76020191218-6L.O.A.4840 | Corbiere and Sons Contracting76020191218-6L.O.A.4840Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 757 | 20191218-7 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | 3 Exs Road Building from B006 to B007; FB and SKD working from B007-B008; DZ clearing snow from B005-B006; Brusher working at B011; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting75720191218-7Brusher91822.5 | Corbiere and Sons Contracting75720191218-7Brusher91822.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 757 | 20191218-7 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | 3 Exs Road Building from B006 to B007; FB and SKD working from B007-B008; DZ clearing snow from B005-B006; Brusher working at B011; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting75720191218-7Feller Buncher92160 | Corbiere and Sons Contracting75720191218-7Feller Buncher92160Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 757 | 20191218-7 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | 3 Exs Road Building from B006 to B007; FB and SKD working from B007-B008; DZ clearing snow from B005-B006; Brusher working at B011; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting75720191218-7Skidder 91539 | Corbiere and Sons Contracting75720191218-7Skidder 91539Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 757 | 20191218-7 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 4 | HR | 128.25 | 0 |  |  | 684 | 88.92 | 772.92 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | 3 Exs Road Building from B006 to B007; FB and SKD working from B007-B008; DZ clearing snow from B005-B006; Brusher working at B011; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting75720191218-7Excavator - 36 ton4684 | Corbiere and Sons Contracting75720191218-7Excavator - 36 ton4684Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 684 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 757 | 20191218-7 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton | 13.5 | 4 | HR | 10.13 | 0 |  |  | 54 | 7.02 | 61.02 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | 3 Exs Road Building from B006 to B007; FB and SKD working from B007-B008; DZ clearing snow from B005-B006; Brusher working at B011; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting75720191218-7Excavator Thumb - 30 - 50 ton454 | Corbiere and Sons Contracting75720191218-7Excavator Thumb - 30 - 50 ton454Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 757 | 20191218-7 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | 3 Exs Road Building from B006 to B007; FB and SKD working from B007-B008; DZ clearing snow from B005-B006; Brusher working at B011; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting75720191218-7Light Truck - Pick up20600 | Corbiere and Sons Contracting75720191218-7Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 757 | 20191218-7 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | 3 Exs Road Building from B006 to B007; FB and SKD working from B007-B008; DZ clearing snow from B005-B006; Brusher working at B011; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting75720191218-7Light Truck - Pick up20600 | Corbiere and Sons Contracting75720191218-7Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 757 | 20191218-7 | 53520101 | Clearing | 0 | Foreman | 95 | 1 | HR |  |  |  | 0 | 95 | 12.35 | 107.35 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | 3 Exs Road Building from B006 to B007; FB and SKD working from B007-B008; DZ clearing snow from B005-B006; Brusher working at B011; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting75720191218-7Foreman195 | Corbiere and Sons Contracting75720191218-7Foreman195Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 757 | 20191218-7 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | 3 Exs Road Building from B006 to B007; FB and SKD working from B007-B008; DZ clearing snow from B005-B006; Brusher working at B011; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting75720191218-7Operator - Principle221980 | Corbiere and Sons Contracting75720191218-7Operator - Principle221980Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 757 | 20191218-7 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 20 | HR |  |  |  | 0 | 1800 | 234 | 2034 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | 3 Exs Road Building from B006 to B007; FB and SKD working from B007-B008; DZ clearing snow from B005-B006; Brusher working at B011; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting75720191218-7Operator - Principle201800 | Corbiere and Sons Contracting75720191218-7Operator - Principle201800Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 757 | 20191218-7 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | 3 Exs Road Building from B006 to B007; FB and SKD working from B007-B008; DZ clearing snow from B005-B006; Brusher working at B011; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting75720191218-7L.O.A.2420 | Corbiere and Sons Contracting75720191218-7L.O.A.2420Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 757 | 20191218-7 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | 3 Exs Road Building from B006 to B007; FB and SKD working from B007-B008; DZ clearing snow from B005-B006; Brusher working at B011; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43837 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting75720191218-7L.O.A.1210 | Corbiere and Sons Contracting75720191218-7L.O.A.1210Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 758 | 20191218-8 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Night Shift Fuelling from 5:30PM to 5:30AM |  |  | All Segments where Equipment is Located | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75820191218-8Light Truck - Pick up20600 | Corbiere and Sons Contracting75820191218-8Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 758 | 20191218-8 | 53520102 | Clearing | 0 | Labourer - General | 65 | 24 | HR |  |  |  | 0 | 1560 | 202.8 | 1762.8 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Night Shift Fuelling from 5:30PM to 5:30AM |  |  | All Segments where Equipment is Located | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75820191218-8Labourer - General241560 | Corbiere and Sons Contracting75820191218-8Labourer - General241560Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 758 | 20191218-8 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-20 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Night Shift Fuelling from 5:30PM to 5:30AM |  |  | All Segments where Equipment is Located | 0 |  |  | 37 | 43833 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting75820191218-8L.O.A.1210 | Corbiere and Sons Contracting75820191218-8L.O.A.1210Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 759 | 20191218-9-R1 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 10 | HR | 94.5 |  |  |  | 1260 | 163.8 | 1423.8 | 2019-12-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | 2 Graders on Standby as was directed by Valard not to come in |  |  |  | 0 |  |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting75920191218-9-R1Grader - Cat 12 to 14 or equal101260 | Corbiere and Sons Contracting75920191218-9-R1Grader - Cat 12 to 14 or equal101260Inv#007-R01 | [5 empty] | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 761 | 20191219-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 0 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76120191219-1Light Truck - Pick up501500 | Corbiere and Sons Contracting76120191219-1Light Truck - Pick up501500Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 761 | 20191219-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  | 0 | 0 | 1320 | 171.6 | 1491.6 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76120191219-1Project Manager121320 | Corbiere and Sons Contracting76120191219-1Project Manager121320Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 761 | 20191219-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  | 0 | 0 | 1260 | 163.8 | 1423.8 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76120191219-1Superintendent121260 | Corbiere and Sons Contracting76120191219-1Superintendent121260Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 761 | 20191219-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  | 0 | 0 | 960 | 124.8 | 1084.8 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76120191219-1Project Coordinator12960 | Corbiere and Sons Contracting76120191219-1Project Coordinator12960Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 761 | 20191219-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  | 0 | 0 | 1020 | 132.6 | 1152.6 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76120191219-1Safety Advisor121020 | Corbiere and Sons Contracting76120191219-1Safety Advisor121020Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 761 | 20191219-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  | 0 | 0 | 840 | 109.2 | 949.2 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76120191219-1Project Controls12840 | Corbiere and Sons Contracting76120191219-1Project Controls12840Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 761 | 20191219-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  | 0 | 0 | 1050 | 136.5 | 1186.5 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76120191219-1L.O.A.51050 | Corbiere and Sons Contracting76120191219-1L.O.A.51050Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 762 | 20191219-2-R2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 0 | 0 |  |  | 300 | 39 | 339 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Worked on JD Rake, prep D5 to bring out to site, fix Dump Truck; Roman Welded Thumb on to EX012 (350); Work on both Log Loaders in field to keep them running; |  |  | General Yard Maintenance and Equipment Repairs | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting76220191219-2-R2Light Truck - Pick up10300 | Corbiere and Sons Contracting76220191219-2-R2Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 762 | 20191219-2-R2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  | 0 | 0 | 600 | 78 | 678 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Worked on JD Rake, prep D5 to bring out to site, fix Dump Truck; Roman Welded Thumb on to EX012 (350); Work on both Log Loaders in field to keep them running; |  |  | General Yard Maintenance and Equipment Repairs | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting76220191219-2-R2Operator - Apprentice10600 | Corbiere and Sons Contracting76220191219-2-R2Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 763 | 20191219-3 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 0 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Gravelling and Road Building from A041; Loading of Gravel Trucks at Pits; Clearing from A036 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76320191219-3Feller Buncher92160 | Corbiere and Sons Contracting76320191219-3Feller Buncher92160Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 763 | 20191219-3 | 53520102 | Clearing | 0 | Skidder | 171 | 9 | HR | 0 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Gravelling and Road Building from A041; Loading of Gravel Trucks at Pits; Clearing from A036 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76320191219-3Skidder 91539 | Corbiere and Sons Contracting76320191219-3Skidder 91539Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 763 | 20191219-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 0 | 0 |  |  | 300 | 39 | 339 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Gravelling and Road Building from A041; Loading of Gravel Trucks at Pits; Clearing from A036 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76320191219-3Light Truck - Pick up10300 | Corbiere and Sons Contracting76320191219-3Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 763 | 20191219-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  | 0 | 0 | 1980 | 257.4 | 2237.4 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Gravelling and Road Building from A041; Loading of Gravel Trucks at Pits; Clearing from A036 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76320191219-3Operator - Principle221980 | Corbiere and Sons Contracting76320191219-3Operator - Principle221980Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 763 | 20191219-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Gravelling and Road Building from A041; Loading of Gravel Trucks at Pits; Clearing from A036 |  |  | Beck Road West - A036 to A046 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76320191219-3L.O.A.1210 | Corbiere and Sons Contracting76320191219-3L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 21 | HR | 151.88 | 0 |  |  | 4252.5 | 552.825 | 4805.325 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Brusher214252.5 | Corbiere and Sons Contracting76420191219-4Brusher214252.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4252.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 7 | HR | 417.6 | 0 |  |  | 3897.6 | 506.688 | 4404.288 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Grinder - 4710 Peterson or equal73897.6 | Corbiere and Sons Contracting76420191219-4Grinder - 4710 Peterson or equal73897.6Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3897.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting76420191219-4Grinder - 4710 Peterson or equal95011.2Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 7 | HR | 114.75 | 0 |  |  | 1071 | 139.23 | 1210.23 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Log Loader71071 | Corbiere and Sons Contracting76420191219-4Log Loader71071Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1071 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Log Loader91377 | Corbiere and Sons Contracting76420191219-4Log Loader91377Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Mulcher91845 | Corbiere and Sons Contracting76420191219-4Mulcher91845Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 5 | Day |  | 0 |  |  | 600 | 78 | 678 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Chainsaw and consummables5600 | Corbiere and Sons Contracting76420191219-4Chainsaw and consummables5600Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 7 | Day |  | 0 |  |  | 840 | 109.2 | 949.2 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Chainsaw and consummables7840 | Corbiere and Sons Contracting76420191219-4Chainsaw and consummables7840Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 9 | HR | 97.88 | 0 |  |  | 1174.5 | 152.685 | 1327.185 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Excavator - 20 ton91174.5 | Corbiere and Sons Contracting76420191219-4Excavator - 20 ton91174.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1174.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Excavator - 36 ton91539 | Corbiere and Sons Contracting76420191219-4Excavator - 36 ton91539Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520102 | Clearing | 0 | Excavator - 50 ton | 189 | 9 | HR | 141.75 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Excavator - 50 ton91701 | Corbiere and Sons Contracting76420191219-4Excavator - 50 ton91701Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1701 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 15 | HR | 94.5 | 0 |  |  | 1890 | 245.7 | 2135.7 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Grader - Cat 12 to 14 or equal151890 | Corbiere and Sons Contracting76420191219-4Grader - Cat 12 to 14 or equal151890Inv#006R01 | [5 empty] | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 10 | HR | 74.25 | 0 |  |  | 990 | 128.7 | 1118.7 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Loader JD 524 to 624 or equal10990 | Corbiere and Sons Contracting76420191219-4Loader JD 524 to 624 or equal10990Inv#006R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53510111 | Access | 0 | Sander Truck | 112.5 | 11 | HR | 84.38 | 0 |  |  | 1237.5 | 160.875 | 1398.375 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Sander Truck111237.5 | Corbiere and Sons Contracting76420191219-4Sander Truck111237.5Inv#006R01 | [5 empty] | 1 | 1237.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Light Truck - Pick up10300 | Corbiere and Sons Contracting76420191219-4Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Light Truck - Pick up10300 | Corbiere and Sons Contracting76420191219-4Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Light Truck - Pick up30900 | Corbiere and Sons Contracting76420191219-4Light Truck - Pick up30900Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Light Truck - Pick up30900 | Corbiere and Sons Contracting76420191219-4Light Truck - Pick up30900Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Light Truck - Pick up20600 | Corbiere and Sons Contracting76420191219-4Light Truck - Pick up20600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Light Truck - Pick up30900 | Corbiere and Sons Contracting76420191219-4Light Truck - Pick up30900Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Light Truck - Pick up30900 | Corbiere and Sons Contracting76420191219-4Light Truck - Pick up30900Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520104 | Clearing | 0 | Foreman | 95 | 24 | HR |  |  |  | 0 | 2280 | 296.4 | 2576.4 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Foreman242280 | Corbiere and Sons Contracting76420191219-4Foreman242280Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 29 | HR |  |  |  | 0 | 2610 | 339.3 | 2949.3 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Operator - Principle292610 | Corbiere and Sons Contracting76420191219-4Operator - Principle292610Inv#006R01 | [5 empty] | 1 | 2610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Operator - Principle221980 | Corbiere and Sons Contracting76420191219-4Operator - Principle221980Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Operator - Principle443960 | Corbiere and Sons Contracting76420191219-4Operator - Principle443960Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Operator - Principle11990 | Corbiere and Sons Contracting76420191219-4Operator - Principle11990Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 110 | HR |  |  |  | 0 | 8250 | 1072.5 | 9322.5 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4Labourer - Specialized1108250 | Corbiere and Sons Contracting76420191219-4Labourer - Specialized1108250Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 8250 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53510111 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4L.O.A.3630 | Corbiere and Sons Contracting76420191219-4L.O.A.3630Inv#006R01 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4L.O.A.71470 | Corbiere and Sons Contracting76420191219-4L.O.A.71470Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 764 | 20191219-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 12 | DAY |  |  |  | 0 | 2520 | 327.6 | 2847.6 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A083-A085, A089 and A093; Rd Building from A087-A088, Gravelling with DZ from A091-A093; Loader working in Pit; Labourers cleaning tracks, rolling out GEO; Finish Brushing at A082 and then start walking towards A116; Grading access roads in Ouimet Canyon; Sanding all Access Roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76420191219-4L.O.A.122520 | Corbiere and Sons Contracting76420191219-4L.O.A.122520Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 2520 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 765 | 20191219-5 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A123 to A127; Walking out to be float moved in the morning; John Corbiere, new foreman did Orientation and then went out with Reg for sitre specific training; |  |  | Wolf Lake Road - A118 to A128 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76520191219-5Feller Buncher92160 | Corbiere and Sons Contracting76520191219-5Feller Buncher92160Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 765 | 20191219-5 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 18 | HR | 180 | 0 |  |  | 4320 | 561.6 | 4881.6 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A123 to A127; Walking out to be float moved in the morning; John Corbiere, new foreman did Orientation and then went out with Reg for sitre specific training; |  |  | Wolf Lake Road - A118 to A128 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76520191219-5Feller Buncher184320 | Corbiere and Sons Contracting76520191219-5Feller Buncher184320Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 765 | 20191219-5 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A123 to A127; Walking out to be float moved in the morning; John Corbiere, new foreman did Orientation and then went out with Reg for sitre specific training; |  |  | Wolf Lake Road - A118 to A128 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76520191219-5Skidder 91539 | Corbiere and Sons Contracting76520191219-5Skidder 91539Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 765 | 20191219-5 | 53520102 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A123 to A127; Walking out to be float moved in the morning; John Corbiere, new foreman did Orientation and then went out with Reg for sitre specific training; |  |  | Wolf Lake Road - A118 to A128 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76520191219-5Skidder 91539 | Corbiere and Sons Contracting76520191219-5Skidder 91539Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 765 | 20191219-5 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A123 to A127; Walking out to be float moved in the morning; John Corbiere, new foreman did Orientation and then went out with Reg for sitre specific training; |  |  | Wolf Lake Road - A118 to A128 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76520191219-5Light Truck - Pick up10300 | Corbiere and Sons Contracting76520191219-5Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 765 | 20191219-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A123 to A127; Walking out to be float moved in the morning; John Corbiere, new foreman did Orientation and then went out with Reg for sitre specific training; |  |  | Wolf Lake Road - A118 to A128 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76520191219-5Light Truck - Pick up20600 | Corbiere and Sons Contracting76520191219-5Light Truck - Pick up20600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 765 | 20191219-5 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A123 to A127; Walking out to be float moved in the morning; John Corbiere, new foreman did Orientation and then went out with Reg for sitre specific training; |  |  | Wolf Lake Road - A118 to A128 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76520191219-5Foreman121140 | Corbiere and Sons Contracting76520191219-5Foreman121140Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 765 | 20191219-5 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A123 to A127; Walking out to be float moved in the morning; John Corbiere, new foreman did Orientation and then went out with Reg for sitre specific training; |  |  | Wolf Lake Road - A118 to A128 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76520191219-5Operator - Principle221980 | Corbiere and Sons Contracting76520191219-5Operator - Principle221980Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 765 | 20191219-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A123 to A127; Walking out to be float moved in the morning; John Corbiere, new foreman did Orientation and then went out with Reg for sitre specific training; |  |  | Wolf Lake Road - A118 to A128 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76520191219-5Operator - Principle332970 | Corbiere and Sons Contracting76520191219-5Operator - Principle332970Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 765 | 20191219-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A123 to A127; Walking out to be float moved in the morning; John Corbiere, new foreman did Orientation and then went out with Reg for sitre specific training; |  |  | Wolf Lake Road - A118 to A128 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76520191219-5L.O.A.2420 | Corbiere and Sons Contracting76520191219-5L.O.A.2420Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 765 | 20191219-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A123 to A127; Walking out to be float moved in the morning; John Corbiere, new foreman did Orientation and then went out with Reg for sitre specific training; |  |  | Wolf Lake Road - A118 to A128 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76520191219-5L.O.A.3630 | Corbiere and Sons Contracting76520191219-5L.O.A.3630Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 766 | 20191219-6 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Road Building from B006 to B009; Clearing from B007-B009; DZ working from B005-B006; Brusher working from B006; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76620191219-6Brusher91822.5 | Corbiere and Sons Contracting76620191219-6Brusher91822.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 766 | 20191219-6 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Road Building from B006 to B009; Clearing from B007-B009; DZ working from B005-B006; Brusher working from B006; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76620191219-6Feller Buncher92160 | Corbiere and Sons Contracting76620191219-6Feller Buncher92160Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 766 | 20191219-6 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Road Building from B006 to B009; Clearing from B007-B009; DZ working from B005-B006; Brusher working from B006; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76620191219-6Skidder 91539 | Corbiere and Sons Contracting76620191219-6Skidder 91539Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 766 | 20191219-6 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Road Building from B006 to B009; Clearing from B007-B009; DZ working from B005-B006; Brusher working from B006; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76620191219-6Light Truck - Pick up20600 | Corbiere and Sons Contracting76620191219-6Light Truck - Pick up20600Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 766 | 20191219-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Road Building from B006 to B009; Clearing from B007-B009; DZ working from B005-B006; Brusher working from B006; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76620191219-6Light Truck - Pick up20600 | Corbiere and Sons Contracting76620191219-6Light Truck - Pick up20600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 766 | 20191219-6 | 53520101 | Clearing | 0 | Foreman | 95 | 1 | HR |  |  |  | 0 | 95 | 12.35 | 107.35 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Road Building from B006 to B009; Clearing from B007-B009; DZ working from B005-B006; Brusher working from B006; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76620191219-6Foreman195 | Corbiere and Sons Contracting76620191219-6Foreman195Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 766 | 20191219-6 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Road Building from B006 to B009; Clearing from B007-B009; DZ working from B005-B006; Brusher working from B006; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76620191219-6Operator - Principle221980 | Corbiere and Sons Contracting76620191219-6Operator - Principle221980Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 766 | 20191219-6 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Road Building from B006 to B009; Clearing from B007-B009; DZ working from B005-B006; Brusher working from B006; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76620191219-6Operator - Principle11990 | Corbiere and Sons Contracting76620191219-6Operator - Principle11990Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 766 | 20191219-6 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Road Building from B006 to B009; Clearing from B007-B009; DZ working from B005-B006; Brusher working from B006; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76620191219-6L.O.A.2420 | Corbiere and Sons Contracting76620191219-6L.O.A.2420Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 766 | 20191219-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Road Building from B006 to B009; Clearing from B007-B009; DZ working from B005-B006; Brusher working from B006; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76620191219-6L.O.A.1210 | Corbiere and Sons Contracting76620191219-6L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 767 | 20191219-7 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-21 | 1 | Inv#069 | 44144 | 123 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 16 | Approved | ROW Internal tracking - Fueling Corbiere Equipment | 9016 | Fuelling of equipment overnight; 5:30PM to 5:30AM |  |  | Night Shift Fuelling-All segments where equipment is located | 0 |  |  | 51 | 44146 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting76720191219-7Light Truck - Pick up20600 | Corbiere and Sons Contracting76720191219-7Light Truck - Pick up20600Inv#069 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 767 | 20191219-7 | 53520102 | Clearing | 0 | Labourer - General | 65 | 24 | HR |  |  |  | 0 | 1560 | 202.8 | 1762.8 | 2019-12-21 | 1 | Inv#069 | 44144 | 123 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 16 | Approved | ROW Internal tracking - Fueling Corbiere Equipment | 9016 | Fuelling of equipment overnight; 5:30PM to 5:30AM |  |  | Night Shift Fuelling-All segments where equipment is located | 0 |  |  | 51 | 44146 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting76720191219-7Labourer - General241560 | Corbiere and Sons Contracting76720191219-7Labourer - General241560Inv#069 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 767 | 20191219-7 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-21 | 1 | Inv#069 | 44144 | 123 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 16 | Approved | ROW Internal tracking - Fueling Corbiere Equipment | 9016 | Fuelling of equipment overnight; 5:30PM to 5:30AM |  |  | Night Shift Fuelling-All segments where equipment is located | 0 |  |  | 51 | 44146 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting76720191219-7L.O.A.1210 | Corbiere and Sons Contracting76720191219-7L.O.A.1210Inv#069 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 768 | 20191220-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 0 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76820191220-1Light Truck - Pick up501500 | Corbiere and Sons Contracting76820191220-1Light Truck - Pick up501500Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 768 | 20191220-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  | 0 | 0 | 1320 | 171.6 | 1491.6 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76820191220-1Project Manager121320 | Corbiere and Sons Contracting76820191220-1Project Manager121320Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 768 | 20191220-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  | 0 | 0 | 1260 | 163.8 | 1423.8 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76820191220-1Superintendent121260 | Corbiere and Sons Contracting76820191220-1Superintendent121260Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 768 | 20191220-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  | 0 | 0 | 960 | 124.8 | 1084.8 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76820191220-1Project Coordinator12960 | Corbiere and Sons Contracting76820191220-1Project Coordinator12960Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 768 | 20191220-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  | 0 | 0 | 1020 | 132.6 | 1152.6 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76820191220-1Safety Advisor121020 | Corbiere and Sons Contracting76820191220-1Safety Advisor121020Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 768 | 20191220-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  | 0 | 0 | 840 | 109.2 | 949.2 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76820191220-1Project Controls12840 | Corbiere and Sons Contracting76820191220-1Project Controls12840Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 768 | 20191220-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  | 0 | 0 | 1050 | 136.5 | 1186.5 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting76820191220-1L.O.A.51050 | Corbiere and Sons Contracting76820191220-1L.O.A.51050Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 769 | 20191220-2-R2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Worked on motor of one of the Brushers, prepping new EX350 to send out to field, welding grousers, fix grader that went down; General shop duties, parts running; |  |  | General Yard Maintenance and Equipment Repair | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting76920191220-2-R2Light Truck - Pick up10300 | Corbiere and Sons Contracting76920191220-2-R2Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 769 | 20191220-2-R2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Worked on motor of one of the Brushers, prepping new EX350 to send out to field, welding grousers, fix grader that went down; General shop duties, parts running; |  |  | General Yard Maintenance and Equipment Repair | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting76920191220-2-R2Operator - Apprentice10600 | Corbiere and Sons Contracting76920191220-2-R2Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 769 | 20191220-2-R2 | 53520102 | Clearing | 0 | L.O.A. | 210 | 0 | DAY |  |  |  | 0 | 0 | 0 | 0 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Worked on motor of one of the Brushers, prepping new EX350 to send out to field, welding grousers, fix grader that went down; General shop duties, parts running; |  |  | General Yard Maintenance and Equipment Repair | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting76920191220-2-R2L.O.A.00 | Corbiere and Sons Contracting76920191220-2-R2L.O.A.00Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 0 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 27 | HR | 151.88 | 0 |  |  | 5467.5 | 710.775 | 6178.275 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Brusher275467.5 | Corbiere and Sons Contracting77120191220-4Brusher275467.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5467.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting77120191220-4Grinder - 4710 Peterson or equal95011.2Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting77120191220-4Grinder - 4710 Peterson or equal95011.2Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Log Loader91377 | Corbiere and Sons Contracting77120191220-4Log Loader91377Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Log Loader91377 | Corbiere and Sons Contracting77120191220-4Log Loader91377Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Mulcher91845 | Corbiere and Sons Contracting77120191220-4Mulcher91845Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 5 | Day |  | 0 |  |  | 600 | 78 | 678 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Chainsaw and consummables5600 | Corbiere and Sons Contracting77120191220-4Chainsaw and consummables5600Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 8 | Day |  | 0 |  |  | 960 | 124.8 | 1084.8 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Chainsaw and consummables8960 | Corbiere and Sons Contracting77120191220-4Chainsaw and consummables8960Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 9 | HR | 97.88 | 0 |  |  | 1174.5 | 152.685 | 1327.185 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Excavator - 20 ton91174.5 | Corbiere and Sons Contracting77120191220-4Excavator - 20 ton91174.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1174.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520102 | Clearing | 0 | Excavator - 50 ton | 189 | 9 | HR | 141.75 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Excavator - 50 ton91701 | Corbiere and Sons Contracting77120191220-4Excavator - 50 ton91701Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1701 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 5 | HR | 94.5 | 0 |  |  | 630 | 81.9 | 711.9 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Grader - Cat 12 to 14 or equal5630 | Corbiere and Sons Contracting77120191220-4Grader - Cat 12 to 14 or equal5630Inv#006R01 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 6 | HR | 74.25 | 0 |  |  | 594 | 77.22 | 671.22 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Loader JD 524 to 624 or equal6594 | Corbiere and Sons Contracting77120191220-4Loader JD 524 to 624 or equal6594Inv#006R01 | [5 empty] | 1 | 594 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53510111 | Access | 0 | Sander Truck | 112.5 | 11 | HR | 84.38 | 0 |  |  | 1237.5 | 160.875 | 1398.375 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Sander Truck111237.5 | Corbiere and Sons Contracting77120191220-4Sander Truck111237.5Inv#006R01 | [5 empty] | 1 | 1237.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Light Truck - Pick up10300 | Corbiere and Sons Contracting77120191220-4Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Light Truck - Pick up10300 | Corbiere and Sons Contracting77120191220-4Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Light Truck - Pick up10300 | Corbiere and Sons Contracting77120191220-4Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Light Truck - Pick up30900 | Corbiere and Sons Contracting77120191220-4Light Truck - Pick up30900Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Light Truck - Pick up30900 | Corbiere and Sons Contracting77120191220-4Light Truck - Pick up30900Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Light Truck - Pick up30900 | Corbiere and Sons Contracting77120191220-4Light Truck - Pick up30900Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53510111 | Access | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting77120191220-4Tractor Trailer - 60 Ton101350Inv#006R01 | [5 empty] | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Foreman121140 | Corbiere and Sons Contracting77120191220-4Foreman121140Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Foreman121140 | Corbiere and Sons Contracting77120191220-4Foreman121140Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 6 | HR |  |  |  | 0 | 540 | 70.2 | 610.2 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Operator - Principle6540 | Corbiere and Sons Contracting77120191220-4Operator - Principle6540Inv#006R01 | [5 empty] | 1 | 540 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Operator - Principle11990 | Corbiere and Sons Contracting77120191220-4Operator - Principle11990Inv#006R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Operator - Principle221980 | Corbiere and Sons Contracting77120191220-4Operator - Principle221980Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Operator - Principle332970 | Corbiere and Sons Contracting77120191220-4Operator - Principle332970Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Operator - Principle221980 | Corbiere and Sons Contracting77120191220-4Operator - Principle221980Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Operator - Principle11990 | Corbiere and Sons Contracting77120191220-4Operator - Principle11990Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Labourer - Specialized11825 | Corbiere and Sons Contracting77120191220-4Labourer - Specialized11825Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 33 | HR |  |  |  | 0 | 2475 | 321.75 | 2796.75 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Labourer - Specialized332475 | Corbiere and Sons Contracting77120191220-4Labourer - Specialized332475Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 77 | HR |  |  |  | 0 | 5775 | 750.75 | 6525.75 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Labourer - Specialized775775 | Corbiere and Sons Contracting77120191220-4Labourer - Specialized775775Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 5775 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520102 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4Labourer - General11715 | Corbiere and Sons Contracting77120191220-4Labourer - General11715Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4L.O.A.2420 | Corbiere and Sons Contracting77120191220-4L.O.A.2420Inv#006R01 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4L.O.A.91890 | Corbiere and Sons Contracting77120191220-4L.O.A.91890Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 771 | 20191220-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 13 | DAY |  |  |  | 0 | 2730 | 354.9 | 3084.9 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A082 and A085; Handfelling from A080-A082 and A084-A085; Raking from A117, sanding and grading of Ouimet Canyon; Raking and Brushing at A086 and at A117; Road Building from A082, A085, up to A088-A093 and at A115-A116; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77120191220-4L.O.A.132730 | Corbiere and Sons Contracting77120191220-4L.O.A.132730Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 2730 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 772 | 20191220-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 5 | HR | 151.88 | 0 |  |  | 1012.5 | 131.625 | 1144.125 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Feller Bunchers and Skidders starting at A132; 3 Exs and 1 DZ road building from B008 to B009; FB and SKD clearing from B008 to B009; Brusher at B009; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77220191220-5Brusher51012.5 | Corbiere and Sons Contracting77220191220-5Brusher51012.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1012.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 772 | 20191220-5 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Feller Bunchers and Skidders starting at A132; 3 Exs and 1 DZ road building from B008 to B009; FB and SKD clearing from B008 to B009; Brusher at B009; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77220191220-5Feller Buncher92160 | Corbiere and Sons Contracting77220191220-5Feller Buncher92160Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 772 | 20191220-5 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 36 | HR | 180 | 0 |  |  | 8640 | 1123.2 | 9763.2 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Feller Bunchers and Skidders starting at A132; 3 Exs and 1 DZ road building from B008 to B009; FB and SKD clearing from B008 to B009; Brusher at B009; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77220191220-5Feller Buncher368640 | Corbiere and Sons Contracting77220191220-5Feller Buncher368640Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 8640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 772 | 20191220-5 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Feller Bunchers and Skidders starting at A132; 3 Exs and 1 DZ road building from B008 to B009; FB and SKD clearing from B008 to B009; Brusher at B009; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77220191220-5Skidder 91539 | Corbiere and Sons Contracting77220191220-5Skidder 91539Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 772 | 20191220-5 | 53520102 | Clearing | 0 | Skidder | 171 | 27 | HR | 128.25 | 0 |  |  | 4617 | 600.21 | 5217.21 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Feller Bunchers and Skidders starting at A132; 3 Exs and 1 DZ road building from B008 to B009; FB and SKD clearing from B008 to B009; Brusher at B009; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77220191220-5Skidder 274617 | Corbiere and Sons Contracting77220191220-5Skidder 274617Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 772 | 20191220-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Feller Bunchers and Skidders starting at A132; 3 Exs and 1 DZ road building from B008 to B009; FB and SKD clearing from B008 to B009; Brusher at B009; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77220191220-5Light Truck - Pick up30900 | Corbiere and Sons Contracting77220191220-5Light Truck - Pick up30900Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 772 | 20191220-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Feller Bunchers and Skidders starting at A132; 3 Exs and 1 DZ road building from B008 to B009; FB and SKD clearing from B008 to B009; Brusher at B009; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77220191220-5Light Truck - Pick up401200 | Corbiere and Sons Contracting77220191220-5Light Truck - Pick up401200Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 772 | 20191220-5 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Feller Bunchers and Skidders starting at A132; 3 Exs and 1 DZ road building from B008 to B009; FB and SKD clearing from B008 to B009; Brusher at B009; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77220191220-5Foreman121140 | Corbiere and Sons Contracting77220191220-5Foreman121140Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 772 | 20191220-5 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Feller Bunchers and Skidders starting at A132; 3 Exs and 1 DZ road building from B008 to B009; FB and SKD clearing from B008 to B009; Brusher at B009; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77220191220-5Operator - Principle221980 | Corbiere and Sons Contracting77220191220-5Operator - Principle221980Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 772 | 20191220-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 77 | HR |  |  |  | 0 | 6930 | 900.9 | 7830.9 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Feller Bunchers and Skidders starting at A132; 3 Exs and 1 DZ road building from B008 to B009; FB and SKD clearing from B008 to B009; Brusher at B009; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77220191220-5Operator - Principle776930 | Corbiere and Sons Contracting77220191220-5Operator - Principle776930Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 6930 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 772 | 20191220-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 7 | HR |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Feller Bunchers and Skidders starting at A132; 3 Exs and 1 DZ road building from B008 to B009; FB and SKD clearing from B008 to B009; Brusher at B009; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77220191220-5Operator - Principle7630 | Corbiere and Sons Contracting77220191220-5Operator - Principle7630Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 772 | 20191220-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Feller Bunchers and Skidders starting at A132; 3 Exs and 1 DZ road building from B008 to B009; FB and SKD clearing from B008 to B009; Brusher at B009; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77220191220-5L.O.A.2420 | Corbiere and Sons Contracting77220191220-5L.O.A.2420Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 772 | 20191220-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-12-21 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Feller Bunchers and Skidders starting at A132; 3 Exs and 1 DZ road building from B008 to B009; FB and SKD clearing from B008 to B009; Brusher at B009; |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting77220191220-5L.O.A.71470 | Corbiere and Sons Contracting77220191220-5L.O.A.71470Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 773 | 20191220-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-21 | 1 | Inv#069 | 44144 | 123 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 16 | Approved | ROW Internal tracking - Fueling Corbiere Equipment | 9016 | Fuelling of equipment overnight; 5:30PM to 5:30AM |  |  | Night Shift Fuelling-All segments where equipment is located | 0 |  |  | 51 | 44146 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting77320191220-6Light Truck - Pick up20600 | Corbiere and Sons Contracting77320191220-6Light Truck - Pick up20600Inv#069 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 773 | 20191220-6 | 53520102 | Clearing | 0 | Labourer - General | 65 | 24 | HR |  |  |  | 0 | 1560 | 202.8 | 1762.8 | 2019-12-21 | 1 | Inv#069 | 44144 | 123 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 16 | Approved | ROW Internal tracking - Fueling Corbiere Equipment | 9016 | Fuelling of equipment overnight; 5:30PM to 5:30AM |  |  | Night Shift Fuelling-All segments where equipment is located | 0 |  |  | 51 | 44146 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting77320191220-6Labourer - General241560 | Corbiere and Sons Contracting77320191220-6Labourer - General241560Inv#069 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 773 | 20191220-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-21 | 1 | Inv#069 | 44144 | 123 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 16 | Approved | ROW Internal tracking - Fueling Corbiere Equipment | 9016 | Fuelling of equipment overnight; 5:30PM to 5:30AM |  |  | Night Shift Fuelling-All segments where equipment is located | 0 |  |  | 51 | 44146 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting77320191220-6L.O.A.1210 | Corbiere and Sons Contracting77320191220-6L.O.A.1210Inv#069 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 629 | 2019122-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6292019122-1Light Truck - Pick up501500 | Corbiere and Sons Contracting6292019122-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 629 | 2019122-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6292019122-1Project Manager121320 | Corbiere and Sons Contracting6292019122-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 629 | 2019122-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6292019122-1Superintendent121260 | Corbiere and Sons Contracting6292019122-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 629 | 2019122-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6292019122-1Project Coordinator12960 | Corbiere and Sons Contracting6292019122-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 629 | 2019122-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6292019122-1Safety Advisor121020 | Corbiere and Sons Contracting6292019122-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 629 | 2019122-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6292019122-1Project Controls12840 | Corbiere and Sons Contracting6292019122-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 629 | 2019122-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-12-03 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6292019122-1L.O.A.51050 | Corbiere and Sons Contracting6292019122-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 775 | 20191221-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting77520191221-1Light Truck - Pick up501500 | Corbiere and Sons Contracting77520191221-1Light Truck - Pick up501500Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 775 | 20191221-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting77520191221-1Project Manager121320 | Corbiere and Sons Contracting77520191221-1Project Manager121320Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 775 | 20191221-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting77520191221-1Superintendent121260 | Corbiere and Sons Contracting77520191221-1Superintendent121260Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 775 | 20191221-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting77520191221-1Project Coordinator12960 | Corbiere and Sons Contracting77520191221-1Project Coordinator12960Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 775 | 20191221-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting77520191221-1Safety Advisor121020 | Corbiere and Sons Contracting77520191221-1Safety Advisor121020Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 775 | 20191221-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting77520191221-1Project Controls12840 | Corbiere and Sons Contracting77520191221-1Project Controls12840Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 775 | 20191221-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting77520191221-1L.O.A.51050 | Corbiere and Sons Contracting77520191221-1L.O.A.51050Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 776 | 20191221-2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard maintenance |  |  | Yard Maintenance | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting77620191221-2Light Truck - Pick up10300 | Corbiere and Sons Contracting77620191221-2Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 776 | 20191221-2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard maintenance |  |  | Yard Maintenance | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting77620191221-2Operator - Apprentice10600 | Corbiere and Sons Contracting77620191221-2Operator - Apprentice10600Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 27 | HR | 151.88 | 0 |  |  | 5467.5 | 710.775 | 6178.275 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Brusher275467.5 | Corbiere and Sons Contracting77820191221-4Brusher275467.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5467.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting77820191221-4Grinder - 4710 Peterson or equal95011.2Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting77820191221-4Grinder - 4710 Peterson or equal95011.2Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Log Loader91377 | Corbiere and Sons Contracting77820191221-4Log Loader91377Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Log Loader91377 | Corbiere and Sons Contracting77820191221-4Log Loader91377Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Mulcher91845 | Corbiere and Sons Contracting77820191221-4Mulcher91845Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 3 | Day |  | 0 |  |  | 360 | 46.8 | 406.8 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Chainsaw and consummables3360 | Corbiere and Sons Contracting77820191221-4Chainsaw and consummables3360Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 5 | Day |  | 0 |  |  | 600 | 78 | 678 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Chainsaw and consummables5600 | Corbiere and Sons Contracting77820191221-4Chainsaw and consummables5600Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Excavator - 36 ton91539 | Corbiere and Sons Contracting77820191221-4Excavator - 36 ton91539Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Excavator - 36 ton91539 | Corbiere and Sons Contracting77820191221-4Excavator - 36 ton91539Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520102 | Clearing | 0 | Excavator - 50 ton | 189 | 9 | HR | 141.75 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Excavator - 50 ton91701 | Corbiere and Sons Contracting77820191221-4Excavator - 50 ton91701Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1701 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 10 | HR | 94.5 | 0 |  |  | 1260 | 163.8 | 1423.8 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Grader - Cat 12 to 14 or equal101260 | Corbiere and Sons Contracting77820191221-4Grader - Cat 12 to 14 or equal101260Inv#005-R01 | [5 empty] | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 6 | HR | 74.25 | 0 |  |  | 594 | 77.22 | 671.22 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Loader JD 524 to 624 or equal6594 | Corbiere and Sons Contracting77820191221-4Loader JD 524 to 624 or equal6594Inv#005-R01 | [5 empty] | 1 | 594 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53510111 | Access | 0 | Sander Truck | 112.5 | 10 | HR | 84.38 | 0 |  |  | 1125 | 146.25 | 1271.25 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Sander Truck101125 | Corbiere and Sons Contracting77820191221-4Sander Truck101125Inv#005-R01 | [5 empty] | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Light Truck - Pick up10300 | Corbiere and Sons Contracting77820191221-4Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Light Truck - Pick up10300 | Corbiere and Sons Contracting77820191221-4Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Light Truck - Pick up30900 | Corbiere and Sons Contracting77820191221-4Light Truck - Pick up30900Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Light Truck - Pick up20600 | Corbiere and Sons Contracting77820191221-4Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Light Truck - Pick up10300 | Corbiere and Sons Contracting77820191221-4Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Light Truck - Pick up30900 | Corbiere and Sons Contracting77820191221-4Light Truck - Pick up30900Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53510111 | Access | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting77820191221-4Tractor Trailer - 60 Ton101350Inv#005-R01 | [5 empty] | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53510111 | Access | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Foreman4380 | Corbiere and Sons Contracting77820191221-4Foreman4380Inv#005-R01 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Foreman121140 | Corbiere and Sons Contracting77820191221-4Foreman121140Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Foreman121140 | Corbiere and Sons Contracting77820191221-4Foreman121140Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Operator - Principle11990 | Corbiere and Sons Contracting77820191221-4Operator - Principle11990Inv#005-R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Operator - Principle11990 | Corbiere and Sons Contracting77820191221-4Operator - Principle11990Inv#005-R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Operator - Principle11990 | Corbiere and Sons Contracting77820191221-4Operator - Principle11990Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Operator - Principle11990 | Corbiere and Sons Contracting77820191221-4Operator - Principle11990Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 77 | HR |  |  |  | 0 | 6930 | 900.9 | 7830.9 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Operator - Principle776930 | Corbiere and Sons Contracting77820191221-4Operator - Principle776930Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 6930 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Operator - Principle11990 | Corbiere and Sons Contracting77820191221-4Operator - Principle11990Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Operator - Intermdiate11825 | Corbiere and Sons Contracting77820191221-4Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 22 | HR |  |  |  | 0 | 1650 | 214.5 | 1864.5 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Labourer - Specialized221650 | Corbiere and Sons Contracting77820191221-4Labourer - Specialized221650Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 44 | HR |  |  |  | 0 | 3300 | 429 | 3729 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4Labourer - Specialized443300 | Corbiere and Sons Contracting77820191221-4Labourer - Specialized443300Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 3300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53510111 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4L.O.A.3630 | Corbiere and Sons Contracting77820191221-4L.O.A.3630Inv#005-R01 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4L.O.A.102100 | Corbiere and Sons Contracting77820191221-4L.O.A.102100Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 778 | 20191221-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material from A082 to A085; Handfelling at A093; Finish Brushing and Raking at A116 East; Road Building from A090 to A091 and from A080-A081; Raking at A112; Grading and Sanding across several access roads; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 2 | 43852 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77820191221-4L.O.A.81680 | Corbiere and Sons Contracting77820191221-4L.O.A.81680Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 779 | 20191221-5 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 36 | HR | 180 | 0 |  |  | 8640 | 1123.2 | 9763.2 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A131 to A133 |  |  | Fish Hatchery - A129 to B017 | 0 |  |  | 2 | 43821 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77920191221-5Feller Buncher368640 | Corbiere and Sons Contracting77920191221-5Feller Buncher368640Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 8640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 779 | 20191221-5 | 53520102 | Clearing | 0 | Skidder | 171 | 27 | HR | 128.25 | 0 |  |  | 4617 | 600.21 | 5217.21 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A131 to A133 |  |  | Fish Hatchery - A129 to B017 | 0 |  |  | 2 | 43821 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77920191221-5Skidder 274617 | Corbiere and Sons Contracting77920191221-5Skidder 274617Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 779 | 20191221-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A131 to A133 |  |  | Fish Hatchery - A129 to B017 | 0 |  |  | 2 | 43821 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77920191221-5Light Truck - Pick up401200 | Corbiere and Sons Contracting77920191221-5Light Truck - Pick up401200Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 779 | 20191221-5 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A131 to A133 |  |  | Fish Hatchery - A129 to B017 | 0 |  |  | 2 | 43821 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77920191221-5Foreman121140 | Corbiere and Sons Contracting77920191221-5Foreman121140Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 779 | 20191221-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 77 | HR |  |  |  | 0 | 6930 | 900.9 | 7830.9 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A131 to A133 |  |  | Fish Hatchery - A129 to B017 | 0 |  |  | 2 | 43821 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77920191221-5Operator - Principle776930 | Corbiere and Sons Contracting77920191221-5Operator - Principle776930Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 6930 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 779 | 20191221-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A131 to A133 |  |  | Fish Hatchery - A129 to B017 | 0 |  |  | 2 | 43821 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting77920191221-5L.O.A.61260 | Corbiere and Sons Contracting77920191221-5L.O.A.61260Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 780 | 20191221-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling of equipment in the field overnight |  |  | Night Shift Fuelling-All segments where equipment located | 0 |  |  | 2 | 43821 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting78020191221-6Light Truck - Pick up20600 | Corbiere and Sons Contracting78020191221-6Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 780 | 20191221-6 | 53520102 | Clearing | 0 | Labourer - General | 65 | 24 | HR |  |  |  | 0 | 1560 | 202.8 | 1762.8 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling of equipment in the field overnight |  |  | Night Shift Fuelling-All segments where equipment located | 0 |  |  | 2 | 43821 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting78020191221-6Labourer - General241560 | Corbiere and Sons Contracting78020191221-6Labourer - General241560Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 780 | 20191221-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling of equipment in the field overnight |  |  | Night Shift Fuelling-All segments where equipment located | 0 |  |  | 2 | 43821 | [5 empty] | Terrance Bob | 01 | Corbiere and Sons Contracting78020191221-6L.O.A.1210 | Corbiere and Sons Contracting78020191221-6L.O.A.1210Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 782 | 20191222-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting78220191222-1Light Truck - Pick up20600 | Corbiere and Sons Contracting78220191222-1Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 782 | 20191222-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting78220191222-1Project Manager121320 | Corbiere and Sons Contracting78220191222-1Project Manager121320Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 782 | 20191222-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting78220191222-1Project Controls12840 | Corbiere and Sons Contracting78220191222-1Project Controls12840Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 782 | 20191222-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting78220191222-1L.O.A.2420 | Corbiere and Sons Contracting78220191222-1L.O.A.2420Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 783 | 20191222-2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard maintenance |  |  | Yard Maintenance | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting78320191222-2Light Truck - Pick up10300 | Corbiere and Sons Contracting78320191222-2Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 783 | 20191222-2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard maintenance |  |  | Yard Maintenance | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting78320191222-2Operator - Apprentice10600 | Corbiere and Sons Contracting78320191222-2Operator - Apprentice10600Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 783 | 20191222-2 | 53520102 | Clearing | 0 | Labourer - General | 65 | 12 | HR |  |  |  | 0 | 780 | 101.4 | 881.4 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard maintenance |  |  | Yard Maintenance | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting78320191222-2Labourer - General12780 | Corbiere and Sons Contracting78320191222-2Labourer - General12780Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 780 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 783 | 20191222-2 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard maintenance |  |  | Yard Maintenance | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting78320191222-2L.O.A.1210 | Corbiere and Sons Contracting78320191222-2L.O.A.1210Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 630 | 2019122-2-R2 | 53520102 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 74.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2019-12-03 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance; Sean Levens ran loader to fill sand truck and taking care of all other yard duties |  |  | Welding/Equipment Repairs | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting6302019122-2-R2Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting6302019122-2-R2Loader JD 524 to 624 or equal5495Inv#069 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 630 | 2019122-2-R2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 |  |  |  | 300 | 39 | 339 | 2019-12-03 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance; Sean Levens ran loader to fill sand truck and taking care of all other yard duties |  |  | Welding/Equipment Repairs | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting6302019122-2-R2Light Truck - Pick up10300 | Corbiere and Sons Contracting6302019122-2-R2Light Truck - Pick up10300Inv#069 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 630 | 2019122-2-R2 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 12 | HR |  |  | 70 | 0 | 900 | 117 | 1017 | 2019-12-03 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance; Sean Levens ran loader to fill sand truck and taking care of all other yard duties |  |  | Welding/Equipment Repairs | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting6302019122-2-R2Operator - Intermdiate12900 | Corbiere and Sons Contracting6302019122-2-R2Operator - Intermdiate12900Inv#069 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 630 | 2019122-2-R2 | 53520102 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 | 2019-12-03 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance; Sean Levens ran loader to fill sand truck and taking care of all other yard duties |  |  | Welding/Equipment Repairs | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting6302019122-2-R2Labourer - General10650 | Corbiere and Sons Contracting6302019122-2-R2Labourer - General10650Inv#069 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 630 | 2019122-2-R2 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-03 | 1 | Inv#069 | 44144 | 123 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance; Sean Levens ran loader to fill sand truck and taking care of all other yard duties |  |  | Welding/Equipment Repairs | 0 |  |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 01 | Corbiere and Sons Contracting6302019122-2-R2L.O.A.1210 | Corbiere and Sons Contracting6302019122-2-R2L.O.A.1210Inv#069 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 784 | 20191223-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting78420191223-1Light Truck - Pick up20600 | Corbiere and Sons Contracting78420191223-1Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 784 | 20191223-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting78420191223-1Project Manager121320 | Corbiere and Sons Contracting78420191223-1Project Manager121320Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 784 | 20191223-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting78420191223-1Project Controls12840 | Corbiere and Sons Contracting78420191223-1Project Controls12840Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 784 | 20191223-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting78420191223-1L.O.A.2420 | Corbiere and Sons Contracting78420191223-1L.O.A.2420Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 785 | 20191223-2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard maintenance |  |  | Yard Maintenance | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting78520191223-2Light Truck - Pick up10300 | Corbiere and Sons Contracting78520191223-2Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 785 | 20191223-2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2020-01-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard maintenance |  |  | Yard Maintenance | 0 |  |  | 35 | 43835 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting78520191223-2Operator - Apprentice10600 | Corbiere and Sons Contracting78520191223-2Operator - Apprentice10600Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 632 | 2019122-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling completed to A061 and then moved to A111; Grinding at A059; Labourers: Fueling, spotting, cleaning tracks, verifying Fire Extinguishers; Float Truck: 1 BR from yard to Wind farm, 1 BR from Eldorado to Wind farm, 210 link belt from Eldorado to windfarm; Sander Truck worked across all segments; Gravelling, Rd. Building and Brushing all at A061 |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43803 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6322019122-4Brusher91822.5 | Corbiere and Sons Contracting6322019122-4Brusher91822.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 632 | 2019122-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling completed to A061 and then moved to A111; Grinding at A059; Labourers: Fueling, spotting, cleaning tracks, verifying Fire Extinguishers; Float Truck: 1 BR from yard to Wind farm, 1 BR from Eldorado to Wind farm, 210 link belt from Eldorado to windfarm; Sander Truck worked across all segments; Gravelling, Rd. Building and Brushing all at A061 |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43803 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6322019122-4Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting6322019122-4Grinder - 4710 Peterson or equal95011.2Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 632 | 2019122-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling completed to A061 and then moved to A111; Grinding at A059; Labourers: Fueling, spotting, cleaning tracks, verifying Fire Extinguishers; Float Truck: 1 BR from yard to Wind farm, 1 BR from Eldorado to Wind farm, 210 link belt from Eldorado to windfarm; Sander Truck worked across all segments; Gravelling, Rd. Building and Brushing all at A061 |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43803 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6322019122-4Log Loader91377 | Corbiere and Sons Contracting6322019122-4Log Loader91377Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 632 | 2019122-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 10 | Day |  | 0 |  |  | 1200 | 156 | 1356 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling completed to A061 and then moved to A111; Grinding at A059; Labourers: Fueling, spotting, cleaning tracks, verifying Fire Extinguishers; Float Truck: 1 BR from yard to Wind farm, 1 BR from Eldorado to Wind farm, 210 link belt from Eldorado to windfarm; Sander Truck worked across all segments; Gravelling, Rd. Building and Brushing all at A061 |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43803 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6322019122-4Chainsaw and consummables101200 | Corbiere and Sons Contracting6322019122-4Chainsaw and consummables101200Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 632 | 2019122-4 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 9 | HR | 97.88 | 0 |  |  | 1174.5 | 152.685 | 1327.185 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling completed to A061 and then moved to A111; Grinding at A059; Labourers: Fueling, spotting, cleaning tracks, verifying Fire Extinguishers; Float Truck: 1 BR from yard to Wind farm, 1 BR from Eldorado to Wind farm, 210 link belt from Eldorado to windfarm; Sander Truck worked across all segments; Gravelling, Rd. Building and Brushing all at A061 |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43803 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6322019122-4Excavator - 20 ton91174.5 | Corbiere and Sons Contracting6322019122-4Excavator - 20 ton91174.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1174.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 632 | 2019122-4 | 53510111 | Access | 0 | Sander Truck | 112.5 | 11 | HR | 84.38 | 0 |  |  | 1237.5 | 160.875 | 1398.375 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling completed to A061 and then moved to A111; Grinding at A059; Labourers: Fueling, spotting, cleaning tracks, verifying Fire Extinguishers; Float Truck: 1 BR from yard to Wind farm, 1 BR from Eldorado to Wind farm, 210 link belt from Eldorado to windfarm; Sander Truck worked across all segments; Gravelling, Rd. Building and Brushing all at A061 |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43803 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6322019122-4Sander Truck111237.5 | Corbiere and Sons Contracting6322019122-4Sander Truck111237.5Inv#005-R01 | [5 empty] | 1 | 1237.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 632 | 2019122-4 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling completed to A061 and then moved to A111; Grinding at A059; Labourers: Fueling, spotting, cleaning tracks, verifying Fire Extinguishers; Float Truck: 1 BR from yard to Wind farm, 1 BR from Eldorado to Wind farm, 210 link belt from Eldorado to windfarm; Sander Truck worked across all segments; Gravelling, Rd. Building and Brushing all at A061 |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43803 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6322019122-4Light Truck - Pick up10300 | Corbiere and Sons Contracting6322019122-4Light Truck - Pick up10300Inv#005-R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 632 | 2019122-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling completed to A061 and then moved to A111; Grinding at A059; Labourers: Fueling, spotting, cleaning tracks, verifying Fire Extinguishers; Float Truck: 1 BR from yard to Wind farm, 1 BR from Eldorado to Wind farm, 210 link belt from Eldorado to windfarm; Sander Truck worked across all segments; Gravelling, Rd. Building and Brushing all at A061 |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43803 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6322019122-4Light Truck - Pick up10300 | Corbiere and Sons Contracting6322019122-4Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 632 | 2019122-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling completed to A061 and then moved to A111; Grinding at A059; Labourers: Fueling, spotting, cleaning tracks, verifying Fire Extinguishers; Float Truck: 1 BR from yard to Wind farm, 1 BR from Eldorado to Wind farm, 210 link belt from Eldorado to windfarm; Sander Truck worked across all segments; Gravelling, Rd. Building and Brushing all at A061 |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43803 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6322019122-4Light Truck - Pick up20600 | Corbiere and Sons Contracting6322019122-4Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 632 | 2019122-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling completed to A061 and then moved to A111; Grinding at A059; Labourers: Fueling, spotting, cleaning tracks, verifying Fire Extinguishers; Float Truck: 1 BR from yard to Wind farm, 1 BR from Eldorado to Wind farm, 210 link belt from Eldorado to windfarm; Sander Truck worked across all segments; Gravelling, Rd. Building and Brushing all at A061 |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43803 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6322019122-4Light Truck - Pick up401200 | Corbiere and Sons Contracting6322019122-4Light Truck - Pick up401200Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 632 | 2019122-4 | 53520102 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 11 | HR | 101.25 | 0 |  |  | 1485 | 193.05 | 1678.05 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling completed to A061 and then moved to A111; Grinding at A059; Labourers: Fueling, spotting, cleaning tracks, verifying Fire Extinguishers; Float Truck: 1 BR from yard to Wind farm, 1 BR from Eldorado to Wind farm, 210 link belt from Eldorado to windfarm; Sander Truck worked across all segments; Gravelling, Rd. Building and Brushing all at A061 |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43803 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6322019122-4Tractor Trailer - 60 Ton111485 | Corbiere and Sons Contracting6322019122-4Tractor Trailer - 60 Ton111485Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1485 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 632 | 2019122-4 | 53520104 | Clearing | 0 | Foreman | 95 | 23 | HR |  |  |  | 0 | 2185 | 284.05 | 2469.05 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling completed to A061 and then moved to A111; Grinding at A059; Labourers: Fueling, spotting, cleaning tracks, verifying Fire Extinguishers; Float Truck: 1 BR from yard to Wind farm, 1 BR from Eldorado to Wind farm, 210 link belt from Eldorado to windfarm; Sander Truck worked across all segments; Gravelling, Rd. Building and Brushing all at A061 |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43803 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6322019122-4Foreman232185 | Corbiere and Sons Contracting6322019122-4Foreman232185Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 2185 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 632 | 2019122-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling completed to A061 and then moved to A111; Grinding at A059; Labourers: Fueling, spotting, cleaning tracks, verifying Fire Extinguishers; Float Truck: 1 BR from yard to Wind farm, 1 BR from Eldorado to Wind farm, 210 link belt from Eldorado to windfarm; Sander Truck worked across all segments; Gravelling, Rd. Building and Brushing all at A061 |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43803 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6322019122-4Operator - Principle332970 | Corbiere and Sons Contracting6322019122-4Operator - Principle332970Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 632 | 2019122-4 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling completed to A061 and then moved to A111; Grinding at A059; Labourers: Fueling, spotting, cleaning tracks, verifying Fire Extinguishers; Float Truck: 1 BR from yard to Wind farm, 1 BR from Eldorado to Wind farm, 210 link belt from Eldorado to windfarm; Sander Truck worked across all segments; Gravelling, Rd. Building and Brushing all at A061 |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43803 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6322019122-4Operator - Intermdiate11825 | Corbiere and Sons Contracting6322019122-4Operator - Intermdiate11825Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 632 | 2019122-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 88 | HR |  |  |  | 0 | 6600 | 858 | 7458 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling completed to A061 and then moved to A111; Grinding at A059; Labourers: Fueling, spotting, cleaning tracks, verifying Fire Extinguishers; Float Truck: 1 BR from yard to Wind farm, 1 BR from Eldorado to Wind farm, 210 link belt from Eldorado to windfarm; Sander Truck worked across all segments; Gravelling, Rd. Building and Brushing all at A061 |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43803 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6322019122-4Labourer - Specialized886600 | Corbiere and Sons Contracting6322019122-4Labourer - Specialized886600Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 6600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 632 | 2019122-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling completed to A061 and then moved to A111; Grinding at A059; Labourers: Fueling, spotting, cleaning tracks, verifying Fire Extinguishers; Float Truck: 1 BR from yard to Wind farm, 1 BR from Eldorado to Wind farm, 210 link belt from Eldorado to windfarm; Sander Truck worked across all segments; Gravelling, Rd. Building and Brushing all at A061 |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43803 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6322019122-4L.O.A.4840 | Corbiere and Sons Contracting6322019122-4L.O.A.4840Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 632 | 2019122-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling completed to A061 and then moved to A111; Grinding at A059; Labourers: Fueling, spotting, cleaning tracks, verifying Fire Extinguishers; Float Truck: 1 BR from yard to Wind farm, 1 BR from Eldorado to Wind farm, 210 link belt from Eldorado to windfarm; Sander Truck worked across all segments; Gravelling, Rd. Building and Brushing all at A061 |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43803 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6322019122-4L.O.A.102100 | Corbiere and Sons Contracting6322019122-4L.O.A.102100Inv#005-R01 |  |  | WF1-Handfalling |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 633 | 2019122-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A112; Dan Pelletier, Orientation for TDG; Finished cutting at A086 E, Need Bridge to finish at A085; Move from A086 to A082; Finish cutting at A091 East; Gravelling at A111 East; Brusher at A111 East; Rakes and Exs at A102 to A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6332019122-5Brusher91822.5 | Corbiere and Sons Contracting6332019122-5Brusher91822.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 633 | 2019122-5 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 18 | HR | 180 | 0 |  |  | 4320 | 561.6 | 4881.6 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A112; Dan Pelletier, Orientation for TDG; Finished cutting at A086 E, Need Bridge to finish at A085; Move from A086 to A082; Finish cutting at A091 East; Gravelling at A111 East; Brusher at A111 East; Rakes and Exs at A102 to A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6332019122-5Feller Buncher184320 | Corbiere and Sons Contracting6332019122-5Feller Buncher184320Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 633 | 2019122-5 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 18 | HR | 180 | 0 |  |  | 4320 | 561.6 | 4881.6 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A112; Dan Pelletier, Orientation for TDG; Finished cutting at A086 E, Need Bridge to finish at A085; Move from A086 to A082; Finish cutting at A091 East; Gravelling at A111 East; Brusher at A111 East; Rakes and Exs at A102 to A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6332019122-5Feller Buncher184320 | Corbiere and Sons Contracting6332019122-5Feller Buncher184320Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 633 | 2019122-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A112; Dan Pelletier, Orientation for TDG; Finished cutting at A086 E, Need Bridge to finish at A085; Move from A086 to A082; Finish cutting at A091 East; Gravelling at A111 East; Brusher at A111 East; Rakes and Exs at A102 to A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6332019122-5Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting6332019122-5Grinder - 4710 Peterson or equal95011.2Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 633 | 2019122-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A112; Dan Pelletier, Orientation for TDG; Finished cutting at A086 E, Need Bridge to finish at A085; Move from A086 to A082; Finish cutting at A091 East; Gravelling at A111 East; Brusher at A111 East; Rakes and Exs at A102 to A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6332019122-5Log Loader91377 | Corbiere and Sons Contracting6332019122-5Log Loader91377Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 633 | 2019122-5 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A112; Dan Pelletier, Orientation for TDG; Finished cutting at A086 E, Need Bridge to finish at A085; Move from A086 to A082; Finish cutting at A091 East; Gravelling at A111 East; Brusher at A111 East; Rakes and Exs at A102 to A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6332019122-5Mulcher91845 | Corbiere and Sons Contracting6332019122-5Mulcher91845Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 633 | 2019122-5 | 53520101 | Clearing | 0 | Skidder | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A112; Dan Pelletier, Orientation for TDG; Finished cutting at A086 E, Need Bridge to finish at A085; Move from A086 to A082; Finish cutting at A091 East; Gravelling at A111 East; Brusher at A111 East; Rakes and Exs at A102 to A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6332019122-5Skidder 183078 | Corbiere and Sons Contracting6332019122-5Skidder 183078Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 633 | 2019122-5 | 53520102 | Clearing | 0 | Skidder | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A112; Dan Pelletier, Orientation for TDG; Finished cutting at A086 E, Need Bridge to finish at A085; Move from A086 to A082; Finish cutting at A091 East; Gravelling at A111 East; Brusher at A111 East; Rakes and Exs at A102 to A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6332019122-5Skidder 183078 | Corbiere and Sons Contracting6332019122-5Skidder 183078Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 633 | 2019122-5 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A112; Dan Pelletier, Orientation for TDG; Finished cutting at A086 E, Need Bridge to finish at A085; Move from A086 to A082; Finish cutting at A091 East; Gravelling at A111 East; Brusher at A111 East; Rakes and Exs at A102 to A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6332019122-5Excavator - 36 ton91539 | Corbiere and Sons Contracting6332019122-5Excavator - 36 ton91539Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 633 | 2019122-5 | 53520102 | Clearing | 0 | Excavator - 50 ton | 189 | 9 | HR | 141.75 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A112; Dan Pelletier, Orientation for TDG; Finished cutting at A086 E, Need Bridge to finish at A085; Move from A086 to A082; Finish cutting at A091 East; Gravelling at A111 East; Brusher at A111 East; Rakes and Exs at A102 to A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6332019122-5Excavator - 50 ton91701 | Corbiere and Sons Contracting6332019122-5Excavator - 50 ton91701Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1701 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 633 | 2019122-5 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A112; Dan Pelletier, Orientation for TDG; Finished cutting at A086 E, Need Bridge to finish at A085; Move from A086 to A082; Finish cutting at A091 East; Gravelling at A111 East; Brusher at A111 East; Rakes and Exs at A102 to A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6332019122-5Light Truck - Pick up30900 | Corbiere and Sons Contracting6332019122-5Light Truck - Pick up30900Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 633 | 2019122-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A112; Dan Pelletier, Orientation for TDG; Finished cutting at A086 E, Need Bridge to finish at A085; Move from A086 to A082; Finish cutting at A091 East; Gravelling at A111 East; Brusher at A111 East; Rakes and Exs at A102 to A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6332019122-5Light Truck - Pick up10300 | Corbiere and Sons Contracting6332019122-5Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 633 | 2019122-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A112; Dan Pelletier, Orientation for TDG; Finished cutting at A086 E, Need Bridge to finish at A085; Move from A086 to A082; Finish cutting at A091 East; Gravelling at A111 East; Brusher at A111 East; Rakes and Exs at A102 to A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6332019122-5Light Truck - Pick up20600 | Corbiere and Sons Contracting6332019122-5Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 633 | 2019122-5 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A112; Dan Pelletier, Orientation for TDG; Finished cutting at A086 E, Need Bridge to finish at A085; Move from A086 to A082; Finish cutting at A091 East; Gravelling at A111 East; Brusher at A111 East; Rakes and Exs at A102 to A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6332019122-5Operator - Principle443960 | Corbiere and Sons Contracting6332019122-5Operator - Principle443960Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 633 | 2019122-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 88 | HR |  |  |  | 0 | 7920 | 1029.6 | 8949.6 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A112; Dan Pelletier, Orientation for TDG; Finished cutting at A086 E, Need Bridge to finish at A085; Move from A086 to A082; Finish cutting at A091 East; Gravelling at A111 East; Brusher at A111 East; Rakes and Exs at A102 to A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6332019122-5Operator - Principle887920 | Corbiere and Sons Contracting6332019122-5Operator - Principle887920Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 7920 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 633 | 2019122-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A112; Dan Pelletier, Orientation for TDG; Finished cutting at A086 E, Need Bridge to finish at A085; Move from A086 to A082; Finish cutting at A091 East; Gravelling at A111 East; Brusher at A111 East; Rakes and Exs at A102 to A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6332019122-5Operator - Principle11990 | Corbiere and Sons Contracting6332019122-5Operator - Principle11990Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 633 | 2019122-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 5 | HR |  |  |  | 0 | 450 | 58.5 | 508.5 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A112; Dan Pelletier, Orientation for TDG; Finished cutting at A086 E, Need Bridge to finish at A085; Move from A086 to A082; Finish cutting at A091 East; Gravelling at A111 East; Brusher at A111 East; Rakes and Exs at A102 to A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6332019122-5Operator - Principle5450 | Corbiere and Sons Contracting6332019122-5Operator - Principle5450Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 633 | 2019122-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 16 | DAY |  |  |  | 0 | 3360 | 436.8 | 3796.8 | 2019-12-03 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material at A112; Dan Pelletier, Orientation for TDG; Finished cutting at A086 E, Need Bridge to finish at A085; Move from A086 to A082; Finish cutting at A091 East; Gravelling at A111 East; Brusher at A111 East; Rakes and Exs at A102 to A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43802 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6332019122-5L.O.A.163360 | Corbiere and Sons Contracting6332019122-5L.O.A.163360Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 786 | 20191227-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting78620191227-1Light Truck - Pick up30900 | Corbiere and Sons Contracting78620191227-1Light Truck - Pick up30900Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 786 | 20191227-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting78620191227-1Project Manager121320 | Corbiere and Sons Contracting78620191227-1Project Manager121320Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 786 | 20191227-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting78620191227-1Project Coordinator12960 | Corbiere and Sons Contracting78620191227-1Project Coordinator12960Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 786 | 20191227-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting78620191227-1Project Controls12840 | Corbiere and Sons Contracting78620191227-1Project Controls12840Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 786 | 20191227-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting78620191227-1L.O.A.3630 | Corbiere and Sons Contracting78620191227-1L.O.A.3630Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 787 | 20191227-2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard maintenance |  |  | Yard Maintenance | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting78720191227-2Light Truck - Pick up10300 | Corbiere and Sons Contracting78720191227-2Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 787 | 20191227-2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard maintenance |  |  | Yard Maintenance | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting78720191227-2Operator - Apprentice10600 | Corbiere and Sons Contracting78720191227-2Operator - Apprentice10600Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 889 | 20191227-3 | 53510111 | Access | 0 | Sander Truck | 112.5 | 9 | HR | 84.38 | 0 |  |  | 1012.5 | 131.625 | 1144.125 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Sander Truck working across all segments |  |  | All Segments | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting88920191227-3Sander Truck91012.5 | Corbiere and Sons Contracting88920191227-3Sander Truck91012.5Inv#006R01 | [5 empty] | 1 | 1012.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 889 | 20191227-3 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Sander Truck working across all segments |  |  | All Segments | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting88920191227-3Operator - Principle11990 | Corbiere and Sons Contracting88920191227-3Operator - Principle11990Inv#006R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 889 | 20191227-3 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Sander Truck working across all segments |  |  | All Segments | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting88920191227-3L.O.A.1210 | Corbiere and Sons Contracting88920191227-3L.O.A.1210Inv#006R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 788 | 20191228-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting78820191228-1Light Truck - Pick up30900 | Corbiere and Sons Contracting78820191228-1Light Truck - Pick up30900Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 788 | 20191228-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting78820191228-1Project Manager121320 | Corbiere and Sons Contracting78820191228-1Project Manager121320Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 788 | 20191228-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting78820191228-1Superintendent121260 | Corbiere and Sons Contracting78820191228-1Superintendent121260Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 788 | 20191228-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting78820191228-1Project Coordinator12960 | Corbiere and Sons Contracting78820191228-1Project Coordinator12960Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 788 | 20191228-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting78820191228-1L.O.A.3630 | Corbiere and Sons Contracting78820191228-1L.O.A.3630Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 789 | 20191228-2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard maintenance |  |  | General yard maintenance | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting78920191228-2Light Truck - Pick up10300 | Corbiere and Sons Contracting78920191228-2Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 789 | 20191228-2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard maintenance |  |  | General yard maintenance | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting78920191228-2Operator - Apprentice10600 | Corbiere and Sons Contracting78920191228-2Operator - Apprentice10600Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 790 | 20191228-3 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 13 | HR | 94.5 | 0 |  |  | 1638 | 212.94 | 1850.94 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Crew showed up to work but there was an access amount of snow, sent home. Graders went out; |  |  |  | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79020191228-3Grader - Cat 12 to 14 or equal131638 | Corbiere and Sons Contracting79020191228-3Grader - Cat 12 to 14 or equal131638Inv#005-R01 | [5 empty] | 1 | 1638 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 790 | 20191228-3 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Crew showed up to work but there was an access amount of snow, sent home. Graders went out; |  |  |  | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79020191228-3Light Truck - Pick up20600 | Corbiere and Sons Contracting79020191228-3Light Truck - Pick up20600Inv#005-R01 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 790 | 20191228-3 | 53510111 | Access | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Crew showed up to work but there was an access amount of snow, sent home. Graders went out; |  |  |  | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79020191228-3Operator - Principle443960 | Corbiere and Sons Contracting79020191228-3Operator - Principle443960Inv#005-R01 | [5 empty] | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 790 | 20191228-3 | 53510111 | Access | 0 | Labourer - Specialized | 75 | 4 | HR |  |  |  | 0 | 300 | 39 | 339 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Crew showed up to work but there was an access amount of snow, sent home. Graders went out; |  |  |  | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79020191228-3Labourer - Specialized4300 | Corbiere and Sons Contracting79020191228-3Labourer - Specialized4300Inv#005-R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 790 | 20191228-3 | 53510111 | Access | 0 | Labourer - General | 65 | 8 | HR |  |  |  | 0 | 520 | 67.6 | 587.6 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Crew showed up to work but there was an access amount of snow, sent home. Graders went out; |  |  |  | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79020191228-3Labourer - General8520 | Corbiere and Sons Contracting79020191228-3Labourer - General8520Inv#005-R01 | [5 empty] | 1 | 520 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 790 | 20191228-3 | 53510111 | Access | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Crew showed up to work but there was an access amount of snow, sent home. Graders went out; |  |  |  | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79020191228-3L.O.A.91890 | Corbiere and Sons Contracting79020191228-3L.O.A.91890Inv#005-R01 | [5 empty] | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 792 | 20191228-5-R1 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 8 | HR | 101.25 | 0 |  |  | 1080 | 140.4 | 1220.4 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grader and Sander working across all access roads |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79220191228-5-R1Dozer D6 or equal81080 | Corbiere and Sons Contracting79220191228-5-R1Dozer D6 or equal81080Inv#005-R01 | [5 empty] | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 792 | 20191228-5-R1 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 7 | HR | 94.5 | 0 |  |  | 882 | 114.66 | 996.66 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grader and Sander working across all access roads |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79220191228-5-R1Grader - Cat 12 to 14 or equal7882 | Corbiere and Sons Contracting79220191228-5-R1Grader - Cat 12 to 14 or equal7882Inv#005-R01 | [5 empty] | 1 | 882 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 792 | 20191228-5-R1 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 24 | HR | 22.5 | 0 |  |  | 720 | 93.6 | 813.6 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grader and Sander working across all access roads |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79220191228-5-R1Light Truck - Pick up24720 | Corbiere and Sons Contracting79220191228-5-R1Light Truck - Pick up24720Inv#005-R01 | [5 empty] | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 792 | 20191228-5-R1 | 53510111 | Access | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grader and Sander working across all access roads |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79220191228-5-R1Foreman4380 | Corbiere and Sons Contracting79220191228-5-R1Foreman4380Inv#005-R01 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 792 | 20191228-5-R1 | 53510111 | Access | 0 | Operator - Principle | 90 | 19 | HR |  |  |  | 0 | 1710 | 222.3 | 1932.3 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grader and Sander working across all access roads |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79220191228-5-R1Operator - Principle191710 | Corbiere and Sons Contracting79220191228-5-R1Operator - Principle191710Inv#005-R01 | [5 empty] | 1 | 1710 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 792 | 20191228-5-R1 | 53510111 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grader and Sander working across all access roads |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79220191228-5-R1L.O.A.3630 | Corbiere and Sons Contracting79220191228-5-R1L.O.A.3630Inv#005-R01 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 890 | 20191228-6 | 53510111 | Access | 0 | Sander Truck | 112.5 | 9 | HR | 84.38 | 0 |  |  | 1012.5 | 131.625 | 1144.125 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Sander Truck working across all Segments |  |  | All Segments Where Required | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting89020191228-6Sander Truck91012.5 | Corbiere and Sons Contracting89020191228-6Sander Truck91012.5Inv#006R01 | [5 empty] | 1 | 1012.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 890 | 20191228-6 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Sander Truck working across all Segments |  |  | All Segments Where Required | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting89020191228-6Operator - Principle11990 | Corbiere and Sons Contracting89020191228-6Operator - Principle11990Inv#006R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 890 | 20191228-6 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Sander Truck working across all Segments |  |  | All Segments Where Required | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting89020191228-6L.O.A.1210 | Corbiere and Sons Contracting89020191228-6L.O.A.1210Inv#006R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 793 | 20191229-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79320191229-1Light Truck - Pick up30900 | Corbiere and Sons Contracting79320191229-1Light Truck - Pick up30900Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 793 | 20191229-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79320191229-1Project Manager121320 | Corbiere and Sons Contracting79320191229-1Project Manager121320Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 793 | 20191229-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79320191229-1Superintendent121260 | Corbiere and Sons Contracting79320191229-1Superintendent121260Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 793 | 20191229-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79320191229-1Project Coordinator12960 | Corbiere and Sons Contracting79320191229-1Project Coordinator12960Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 793 | 20191229-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79320191229-1L.O.A.3630 | Corbiere and Sons Contracting79320191229-1L.O.A.3630Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 794 | 20191229-2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard maintenance |  |  | General yard maintenance | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79420191229-2Light Truck - Pick up10300 | Corbiere and Sons Contracting79420191229-2Light Truck - Pick up10300Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 794 | 20191229-2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard maintenance |  |  | General yard maintenance | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79420191229-2Operator - Apprentice10600 | Corbiere and Sons Contracting79420191229-2Operator - Apprentice10600Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 795 | 20191229-3 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Removal |  |  | Wind Farm and various access roads | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79520191229-3Dozer D6 or equal91215 | Corbiere and Sons Contracting79520191229-3Dozer D6 or equal91215Inv#005-R01 | [5 empty] | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 795 | 20191229-3 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Removal |  |  | Wind Farm and various access roads | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79520191229-3Dozer D6 or equal91215 | Corbiere and Sons Contracting79520191229-3Dozer D6 or equal91215Inv#005-R01 | [5 empty] | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 795 | 20191229-3 | 53510111 | Access | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Removal |  |  | Wind Farm and various access roads | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79520191229-3Excavator - 36 ton91539 | Corbiere and Sons Contracting79520191229-3Excavator - 36 ton91539Inv#005-R01 | [5 empty] | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 795 | 20191229-3 | 53510111 | Access | 0 | Excavator - 50 ton | 189 | 9 | HR | 141.75 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Removal |  |  | Wind Farm and various access roads | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79520191229-3Excavator - 50 ton91701 | Corbiere and Sons Contracting79520191229-3Excavator - 50 ton91701Inv#005-R01 | [5 empty] | 1 | 1701 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 795 | 20191229-3 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Removal |  |  | Wind Farm and various access roads | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79520191229-3Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting79520191229-3Grader - Cat 12 to 14 or equal91134Inv#005-R01 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 795 | 20191229-3 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Removal |  |  | Wind Farm and various access roads | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79520191229-3Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting79520191229-3Grader - Cat 12 to 14 or equal91134Inv#005-R01 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 795 | 20191229-3 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Removal |  |  | Wind Farm and various access roads | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79520191229-3Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting79520191229-3Loader JD 524 to 624 or equal9891Inv#005-R01 | [5 empty] | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 795 | 20191229-3 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Removal |  |  | Wind Farm and various access roads | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79520191229-3Light Truck - Pick up401200 | Corbiere and Sons Contracting79520191229-3Light Truck - Pick up401200Inv#005-R01 | [5 empty] | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 795 | 20191229-3 | 53510111 | Access | 0 | Operator - Principle | 90 | 77 | HR |  |  |  | 0 | 6930 | 900.9 | 7830.9 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Removal |  |  | Wind Farm and various access roads | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79520191229-3Operator - Principle776930 | Corbiere and Sons Contracting79520191229-3Operator - Principle776930Inv#005-R01 | [5 empty] | 1 | 6930 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 795 | 20191229-3 | 53510111 | Access | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Removal |  |  | Wind Farm and various access roads | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79520191229-3Labourer - Specialized11825 | Corbiere and Sons Contracting79520191229-3Labourer - Specialized11825Inv#005-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 795 | 20191229-3 | 53510111 | Access | 0 | Labourer - General | 65 | 22 | HR |  |  |  | 0 | 1430 | 185.9 | 1615.9 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Removal |  |  | Wind Farm and various access roads | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79520191229-3Labourer - General221430 | Corbiere and Sons Contracting79520191229-3Labourer - General221430Inv#005-R01 | [5 empty] | 1 | 1430 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 795 | 20191229-3 | 53510111 | Access | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Removal |  |  | Wind Farm and various access roads | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79520191229-3L.O.A.91890 | Corbiere and Sons Contracting79520191229-3L.O.A.91890Inv#005-R01 | [5 empty] | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 796 | 20191229-4 | 53520102 | Clearing | 0 | Mechanics Truck | 55 | 10 | HR | 41.25 | 0 |  |  | 550 | 71.5 | 621.5 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Equipment Repair; Worked on Sander Truck at Ouimet Canyon |  |  | Ouimet Canyon-Equipment Repair | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79620191229-4Mechanics Truck10550 | Corbiere and Sons Contracting79620191229-4Mechanics Truck10550Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 550 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 796 | 20191229-4 | 53520102 | Clearing | 0 | Mechanic | 90 | 10 | HR |  |  |  | 0 | 900 | 117 | 1017 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Equipment Repair; Worked on Sander Truck at Ouimet Canyon |  |  | Ouimet Canyon-Equipment Repair | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79620191229-4Mechanic10900 | Corbiere and Sons Contracting79620191229-4Mechanic10900Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 796 | 20191229-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-04 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Equipment Repair; Worked on Sander Truck at Ouimet Canyon |  |  | Ouimet Canyon-Equipment Repair | 0 |  |  | 36 | 43835 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79620191229-4L.O.A.1210 | Corbiere and Sons Contracting79620191229-4L.O.A.1210Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 797 | 20191229-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-EX-01, NS-EX-02, NS-EX-04 raked and piled towers B007-B009, Feller Buncher NS-FB-01 finalized clearing between towers 08 & 09, with skidder NS-SK-01 assisted piling, mobilized to B006 and cleared roadline to B004 - Tractor NS-DZ-03 completed clearing snow and widening roadline to tower A132, cleared to B009 began assisting build to within 100m of B005 - NS-BR-01 continued to open up Cavern Road access via mulching 2m width 400m beyond culvert installation |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79720191229-5Brusher91822.5 | Corbiere and Sons Contracting79720191229-5Brusher91822.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 797 | 20191229-5 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-EX-01, NS-EX-02, NS-EX-04 raked and piled towers B007-B009, Feller Buncher NS-FB-01 finalized clearing between towers 08 & 09, with skidder NS-SK-01 assisted piling, mobilized to B006 and cleared roadline to B004 - Tractor NS-DZ-03 completed clearing snow and widening roadline to tower A132, cleared to B009 began assisting build to within 100m of B005 - NS-BR-01 continued to open up Cavern Road access via mulching 2m width 400m beyond culvert installation |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79720191229-5Feller Buncher92160 | Corbiere and Sons Contracting79720191229-5Feller Buncher92160Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 797 | 20191229-5 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-EX-01, NS-EX-02, NS-EX-04 raked and piled towers B007-B009, Feller Buncher NS-FB-01 finalized clearing between towers 08 & 09, with skidder NS-SK-01 assisted piling, mobilized to B006 and cleared roadline to B004 - Tractor NS-DZ-03 completed clearing snow and widening roadline to tower A132, cleared to B009 began assisting build to within 100m of B005 - NS-BR-01 continued to open up Cavern Road access via mulching 2m width 400m beyond culvert installation |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79720191229-5Skidder 91539 | Corbiere and Sons Contracting79720191229-5Skidder 91539Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 797 | 20191229-5 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 8 | HR | 101.25 | 0 |  |  | 1080 | 140.4 | 1220.4 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-EX-01, NS-EX-02, NS-EX-04 raked and piled towers B007-B009, Feller Buncher NS-FB-01 finalized clearing between towers 08 & 09, with skidder NS-SK-01 assisted piling, mobilized to B006 and cleared roadline to B004 - Tractor NS-DZ-03 completed clearing snow and widening roadline to tower A132, cleared to B009 began assisting build to within 100m of B005 - NS-BR-01 continued to open up Cavern Road access via mulching 2m width 400m beyond culvert installation |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79720191229-5Dozer D6 or equal81080 | Corbiere and Sons Contracting79720191229-5Dozer D6 or equal81080Inv#006R01 | [5 empty] | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 797 | 20191229-5 | 53520102 | Clearing | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-EX-01, NS-EX-02, NS-EX-04 raked and piled towers B007-B009, Feller Buncher NS-FB-01 finalized clearing between towers 08 & 09, with skidder NS-SK-01 assisted piling, mobilized to B006 and cleared roadline to B004 - Tractor NS-DZ-03 completed clearing snow and widening roadline to tower A132, cleared to B009 began assisting build to within 100m of B005 - NS-BR-01 continued to open up Cavern Road access via mulching 2m width 400m beyond culvert installation |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79720191229-5Excavator - 30 ton91255.5 | Corbiere and Sons Contracting79720191229-5Excavator - 30 ton91255.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 797 | 20191229-5 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-EX-01, NS-EX-02, NS-EX-04 raked and piled towers B007-B009, Feller Buncher NS-FB-01 finalized clearing between towers 08 & 09, with skidder NS-SK-01 assisted piling, mobilized to B006 and cleared roadline to B004 - Tractor NS-DZ-03 completed clearing snow and widening roadline to tower A132, cleared to B009 began assisting build to within 100m of B005 - NS-BR-01 continued to open up Cavern Road access via mulching 2m width 400m beyond culvert installation |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79720191229-5Excavator - 36 ton91539 | Corbiere and Sons Contracting79720191229-5Excavator - 36 ton91539Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 797 | 20191229-5 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-EX-01, NS-EX-02, NS-EX-04 raked and piled towers B007-B009, Feller Buncher NS-FB-01 finalized clearing between towers 08 & 09, with skidder NS-SK-01 assisted piling, mobilized to B006 and cleared roadline to B004 - Tractor NS-DZ-03 completed clearing snow and widening roadline to tower A132, cleared to B009 began assisting build to within 100m of B005 - NS-BR-01 continued to open up Cavern Road access via mulching 2m width 400m beyond culvert installation |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79720191229-5Excavator - 36 ton91539 | Corbiere and Sons Contracting79720191229-5Excavator - 36 ton91539Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 797 | 20191229-5 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton | 13.5 | 9 | HR | 10.13 | 0 |  |  | 121.5 | 15.795 | 137.295 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-EX-01, NS-EX-02, NS-EX-04 raked and piled towers B007-B009, Feller Buncher NS-FB-01 finalized clearing between towers 08 & 09, with skidder NS-SK-01 assisted piling, mobilized to B006 and cleared roadline to B004 - Tractor NS-DZ-03 completed clearing snow and widening roadline to tower A132, cleared to B009 began assisting build to within 100m of B005 - NS-BR-01 continued to open up Cavern Road access via mulching 2m width 400m beyond culvert installation |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79720191229-5Excavator Thumb - 30 - 50 ton9121.5 | Corbiere and Sons Contracting79720191229-5Excavator Thumb - 30 - 50 ton9121.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 121.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 797 | 20191229-5 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton | 13.5 | 9 | HR | 10.13 | 0 |  |  | 121.5 | 15.795 | 137.295 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-EX-01, NS-EX-02, NS-EX-04 raked and piled towers B007-B009, Feller Buncher NS-FB-01 finalized clearing between towers 08 & 09, with skidder NS-SK-01 assisted piling, mobilized to B006 and cleared roadline to B004 - Tractor NS-DZ-03 completed clearing snow and widening roadline to tower A132, cleared to B009 began assisting build to within 100m of B005 - NS-BR-01 continued to open up Cavern Road access via mulching 2m width 400m beyond culvert installation |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79720191229-5Excavator Thumb - 30 - 50 ton9121.5 | Corbiere and Sons Contracting79720191229-5Excavator Thumb - 30 - 50 ton9121.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 121.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 797 | 20191229-5 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton | 13.5 | 9 | HR | 10.13 | 0 |  |  | 121.5 | 15.795 | 137.295 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-EX-01, NS-EX-02, NS-EX-04 raked and piled towers B007-B009, Feller Buncher NS-FB-01 finalized clearing between towers 08 & 09, with skidder NS-SK-01 assisted piling, mobilized to B006 and cleared roadline to B004 - Tractor NS-DZ-03 completed clearing snow and widening roadline to tower A132, cleared to B009 began assisting build to within 100m of B005 - NS-BR-01 continued to open up Cavern Road access via mulching 2m width 400m beyond culvert installation |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79720191229-5Excavator Thumb - 30 - 50 ton9121.5 | Corbiere and Sons Contracting79720191229-5Excavator Thumb - 30 - 50 ton9121.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 121.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 797 | 20191229-5 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-EX-01, NS-EX-02, NS-EX-04 raked and piled towers B007-B009, Feller Buncher NS-FB-01 finalized clearing between towers 08 & 09, with skidder NS-SK-01 assisted piling, mobilized to B006 and cleared roadline to B004 - Tractor NS-DZ-03 completed clearing snow and widening roadline to tower A132, cleared to B009 began assisting build to within 100m of B005 - NS-BR-01 continued to open up Cavern Road access via mulching 2m width 400m beyond culvert installation |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79720191229-5Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting79720191229-5Grader - Cat 12 to 14 or equal91134Inv#006R01 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 797 | 20191229-5 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-EX-01, NS-EX-02, NS-EX-04 raked and piled towers B007-B009, Feller Buncher NS-FB-01 finalized clearing between towers 08 & 09, with skidder NS-SK-01 assisted piling, mobilized to B006 and cleared roadline to B004 - Tractor NS-DZ-03 completed clearing snow and widening roadline to tower A132, cleared to B009 began assisting build to within 100m of B005 - NS-BR-01 continued to open up Cavern Road access via mulching 2m width 400m beyond culvert installation |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79720191229-5Light Truck - Pick up20600 | Corbiere and Sons Contracting79720191229-5Light Truck - Pick up20600Inv#006R01 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 797 | 20191229-5 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-EX-01, NS-EX-02, NS-EX-04 raked and piled towers B007-B009, Feller Buncher NS-FB-01 finalized clearing between towers 08 & 09, with skidder NS-SK-01 assisted piling, mobilized to B006 and cleared roadline to B004 - Tractor NS-DZ-03 completed clearing snow and widening roadline to tower A132, cleared to B009 began assisting build to within 100m of B005 - NS-BR-01 continued to open up Cavern Road access via mulching 2m width 400m beyond culvert installation |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79720191229-5Light Truck - Pick up30900 | Corbiere and Sons Contracting79720191229-5Light Truck - Pick up30900Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 797 | 20191229-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-EX-01, NS-EX-02, NS-EX-04 raked and piled towers B007-B009, Feller Buncher NS-FB-01 finalized clearing between towers 08 & 09, with skidder NS-SK-01 assisted piling, mobilized to B006 and cleared roadline to B004 - Tractor NS-DZ-03 completed clearing snow and widening roadline to tower A132, cleared to B009 began assisting build to within 100m of B005 - NS-BR-01 continued to open up Cavern Road access via mulching 2m width 400m beyond culvert installation |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79720191229-5Light Truck - Pick up30900 | Corbiere and Sons Contracting79720191229-5Light Truck - Pick up30900Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 797 | 20191229-5 | 53510111 | Access | 0 | Foreman | 95 | 1 | HR |  |  |  | 0 | 95 | 12.35 | 107.35 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-EX-01, NS-EX-02, NS-EX-04 raked and piled towers B007-B009, Feller Buncher NS-FB-01 finalized clearing between towers 08 & 09, with skidder NS-SK-01 assisted piling, mobilized to B006 and cleared roadline to B004 - Tractor NS-DZ-03 completed clearing snow and widening roadline to tower A132, cleared to B009 began assisting build to within 100m of B005 - NS-BR-01 continued to open up Cavern Road access via mulching 2m width 400m beyond culvert installation |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79720191229-5Foreman195 | Corbiere and Sons Contracting79720191229-5Foreman195Inv#006R01 | [5 empty] | 1 | 95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 797 | 20191229-5 | 53520101 | Clearing | 0 | Foreman | 95 | 7 | HR |  |  |  | 0 | 665 | 86.45 | 751.45 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-EX-01, NS-EX-02, NS-EX-04 raked and piled towers B007-B009, Feller Buncher NS-FB-01 finalized clearing between towers 08 & 09, with skidder NS-SK-01 assisted piling, mobilized to B006 and cleared roadline to B004 - Tractor NS-DZ-03 completed clearing snow and widening roadline to tower A132, cleared to B009 began assisting build to within 100m of B005 - NS-BR-01 continued to open up Cavern Road access via mulching 2m width 400m beyond culvert installation |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79720191229-5Foreman7665 | Corbiere and Sons Contracting79720191229-5Foreman7665Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 665 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 797 | 20191229-5 | 53510111 | Access | 0 | Operator - Principle | 90 | 20 | HR |  |  |  | 0 | 1800 | 234 | 2034 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-EX-01, NS-EX-02, NS-EX-04 raked and piled towers B007-B009, Feller Buncher NS-FB-01 finalized clearing between towers 08 & 09, with skidder NS-SK-01 assisted piling, mobilized to B006 and cleared roadline to B004 - Tractor NS-DZ-03 completed clearing snow and widening roadline to tower A132, cleared to B009 began assisting build to within 100m of B005 - NS-BR-01 continued to open up Cavern Road access via mulching 2m width 400m beyond culvert installation |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79720191229-5Operator - Principle201800 | Corbiere and Sons Contracting79720191229-5Operator - Principle201800Inv#006R01 | [5 empty] | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 797 | 20191229-5 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-EX-01, NS-EX-02, NS-EX-04 raked and piled towers B007-B009, Feller Buncher NS-FB-01 finalized clearing between towers 08 & 09, with skidder NS-SK-01 assisted piling, mobilized to B006 and cleared roadline to B004 - Tractor NS-DZ-03 completed clearing snow and widening roadline to tower A132, cleared to B009 began assisting build to within 100m of B005 - NS-BR-01 continued to open up Cavern Road access via mulching 2m width 400m beyond culvert installation |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79720191229-5Operator - Principle221980 | Corbiere and Sons Contracting79720191229-5Operator - Principle221980Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 797 | 20191229-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-EX-01, NS-EX-02, NS-EX-04 raked and piled towers B007-B009, Feller Buncher NS-FB-01 finalized clearing between towers 08 & 09, with skidder NS-SK-01 assisted piling, mobilized to B006 and cleared roadline to B004 - Tractor NS-DZ-03 completed clearing snow and widening roadline to tower A132, cleared to B009 began assisting build to within 100m of B005 - NS-BR-01 continued to open up Cavern Road access via mulching 2m width 400m beyond culvert installation |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79720191229-5Operator - Principle443960 | Corbiere and Sons Contracting79720191229-5Operator - Principle443960Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 797 | 20191229-5 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-EX-01, NS-EX-02, NS-EX-04 raked and piled towers B007-B009, Feller Buncher NS-FB-01 finalized clearing between towers 08 & 09, with skidder NS-SK-01 assisted piling, mobilized to B006 and cleared roadline to B004 - Tractor NS-DZ-03 completed clearing snow and widening roadline to tower A132, cleared to B009 began assisting build to within 100m of B005 - NS-BR-01 continued to open up Cavern Road access via mulching 2m width 400m beyond culvert installation |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79720191229-5L.O.A.1210 | Corbiere and Sons Contracting79720191229-5L.O.A.1210Inv#006R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 797 | 20191229-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-EX-01, NS-EX-02, NS-EX-04 raked and piled towers B007-B009, Feller Buncher NS-FB-01 finalized clearing between towers 08 & 09, with skidder NS-SK-01 assisted piling, mobilized to B006 and cleared roadline to B004 - Tractor NS-DZ-03 completed clearing snow and widening roadline to tower A132, cleared to B009 began assisting build to within 100m of B005 - NS-BR-01 continued to open up Cavern Road access via mulching 2m width 400m beyond culvert installation |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79720191229-5L.O.A.2420 | Corbiere and Sons Contracting79720191229-5L.O.A.2420Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 797 | 20191229-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-EX-01, NS-EX-02, NS-EX-04 raked and piled towers B007-B009, Feller Buncher NS-FB-01 finalized clearing between towers 08 & 09, with skidder NS-SK-01 assisted piling, mobilized to B006 and cleared roadline to B004 - Tractor NS-DZ-03 completed clearing snow and widening roadline to tower A132, cleared to B009 began assisting build to within 100m of B005 - NS-BR-01 continued to open up Cavern Road access via mulching 2m width 400m beyond culvert installation |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79720191229-5L.O.A.4840 | Corbiere and Sons Contracting79720191229-5L.O.A.4840Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 891 | 20191229-6 | 53510111 | Access | 0 | Sander Truck | 112.5 | 3 | HR | 84.38 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Sander Truck broke down after 3 hours |  |  | All Segments where Required | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting89120191229-6Sander Truck3337.5 | Corbiere and Sons Contracting89120191229-6Sander Truck3337.5Inv#006R01 | [5 empty] | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 891 | 20191229-6 | 53510111 | Access | 0 | Operator - Principle | 90 | 4 | HR |  |  |  | 0 | 360 | 46.8 | 406.8 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Sander Truck broke down after 3 hours |  |  | All Segments where Required | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting89120191229-6Operator - Principle4360 | Corbiere and Sons Contracting89120191229-6Operator - Principle4360Inv#006R01 | [5 empty] | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 891 | 20191229-6 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-07 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Sander Truck broke down after 3 hours |  |  | All Segments where Required | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting89120191229-6L.O.A.1210 | Corbiere and Sons Contracting89120191229-6L.O.A.1210Inv#006R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 798 | 20191230-1 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 7.5 | HR | 22.5 | 0 |  |  | 225 | 29.25 | 254.25 | 2019-12-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79820191230-1Light Truck - Pick up7.5225 | Corbiere and Sons Contracting79820191230-1Light Truck - Pick up7.5225Inv#006R01 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 798 | 20191230-1 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 2.5 | HR | 22.5 | 0 |  |  | 75 | 9.75 | 84.75 | 2019-12-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79820191230-1Light Truck - Pick up2.575 | Corbiere and Sons Contracting79820191230-1Light Truck - Pick up2.575Inv#006R01 | [5 empty] | 1 | 75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 798 | 20191230-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 7.5 | HR | 22.5 | 0 |  |  | 225 | 29.25 | 254.25 | 2019-12-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79820191230-1Light Truck - Pick up7.5225 | Corbiere and Sons Contracting79820191230-1Light Truck - Pick up7.5225Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 798 | 20191230-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 2.5 | HR | 22.5 | 0 |  |  | 75 | 9.75 | 84.75 | 2019-12-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79820191230-1Light Truck - Pick up2.575 | Corbiere and Sons Contracting79820191230-1Light Truck - Pick up2.575Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 798 | 20191230-1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 7.5 | HR | 22.5 | 0 |  |  | 225 | 29.25 | 254.25 | 2019-12-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79820191230-1Light Truck - Pick up7.5225 | Corbiere and Sons Contracting79820191230-1Light Truck - Pick up7.5225Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 798 | 20191230-1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 2.5 | HR | 22.5 | 0 |  |  | 75 | 9.75 | 84.75 | 2019-12-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79820191230-1Light Truck - Pick up2.575 | Corbiere and Sons Contracting79820191230-1Light Truck - Pick up2.575Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 798 | 20191230-1 | 53510111 | Access | 0 | Project Manager | 110 | 3 | HR |  |  | 110 | 0 | 330 | 42.9 | 372.9 | 2019-12-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79820191230-1Project Manager3330 | Corbiere and Sons Contracting79820191230-1Project Manager3330Inv#006R01 | [5 empty] | 1 | 330 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 798 | 20191230-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 3 | HR |  |  | 110 | 0 | 330 | 42.9 | 372.9 | 2019-12-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79820191230-1Project Manager3330 | Corbiere and Sons Contracting79820191230-1Project Manager3330Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 330 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 798 | 20191230-1 | 53520102 | Clearing | 0 | Project Manager | 110 | 3 | HR |  |  | 110 | 0 | 330 | 42.9 | 372.9 | 2019-12-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79820191230-1Project Manager3330 | Corbiere and Sons Contracting79820191230-1Project Manager3330Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 330 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 798 | 20191230-1 | 53510111 | Access | 0 | Superintendent | 105 | 3 | HR |  |  | 105 | 0 | 315 | 40.95 | 355.95 | 2019-12-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79820191230-1Superintendent3315 | Corbiere and Sons Contracting79820191230-1Superintendent3315Inv#006R01 | [5 empty] | 1 | 315 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 798 | 20191230-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 3 | HR |  |  | 105 | 0 | 315 | 40.95 | 355.95 | 2019-12-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79820191230-1Superintendent3315 | Corbiere and Sons Contracting79820191230-1Superintendent3315Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 315 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 798 | 20191230-1 | 53520102 | Clearing | 0 | Superintendent | 105 | 3 | HR |  |  | 105 | 0 | 315 | 40.95 | 355.95 | 2019-12-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79820191230-1Superintendent3315 | Corbiere and Sons Contracting79820191230-1Superintendent3315Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 315 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 798 | 20191230-1 | 53510111 | Access | 0 | Project Coordinator | 80 | 3 | HR |  |  | 80 | 0 | 240 | 31.2 | 271.2 | 2019-12-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79820191230-1Project Coordinator3240 | Corbiere and Sons Contracting79820191230-1Project Coordinator3240Inv#006R01 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 798 | 20191230-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 3 | HR |  |  | 80 | 0 | 240 | 31.2 | 271.2 | 2019-12-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79820191230-1Project Coordinator3240 | Corbiere and Sons Contracting79820191230-1Project Coordinator3240Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 798 | 20191230-1 | 53520102 | Clearing | 0 | Project Coordinator | 80 | 3 | HR |  |  | 80 | 0 | 240 | 31.2 | 271.2 | 2019-12-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79820191230-1Project Coordinator3240 | Corbiere and Sons Contracting79820191230-1Project Coordinator3240Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 798 | 20191230-1 | 53510111 | Access | 0 | Project Controls | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2019-12-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79820191230-1Project Controls3210 | Corbiere and Sons Contracting79820191230-1Project Controls3210Inv#006R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 798 | 20191230-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2019-12-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79820191230-1Project Controls3210 | Corbiere and Sons Contracting79820191230-1Project Controls3210Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 798 | 20191230-1 | 53520102 | Clearing | 0 | Project Controls | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2019-12-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79820191230-1Project Controls3210 | Corbiere and Sons Contracting79820191230-1Project Controls3210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 798 | 20191230-1 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79820191230-1L.O.A.1210 | Corbiere and Sons Contracting79820191230-1L.O.A.1210Inv#006R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 798 | 20191230-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79820191230-1L.O.A.1210 | Corbiere and Sons Contracting79820191230-1L.O.A.1210Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 798 | 20191230-1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-30 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79820191230-1L.O.A.1210 | Corbiere and Sons Contracting79820191230-1L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 799 | 20191230-2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard maintenance |  |  | General yard maintenance | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79920191230-2Light Truck - Pick up10300 | Corbiere and Sons Contracting79920191230-2Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 799 | 20191230-2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard maintenance |  |  | General yard maintenance | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting79920191230-2Operator - Apprentice10600 | Corbiere and Sons Contracting79920191230-2Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 800 | 20191230-3-R1 | 53510111 | Access | 0 | Dozer - D5 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2020-01-05 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Wind Farm and various access roads-Snow Removal |  |  | Wind Farm and various access roads-Snow Removal | 0 |  |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting80020191230-3-R1Dozer - D5 or equal9891 | Corbiere and Sons Contracting80020191230-3-R1Dozer - D5 or equal9891Inv#022 | [5 empty] | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 800 | 20191230-3-R1 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2020-01-05 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Wind Farm and various access roads-Snow Removal |  |  | Wind Farm and various access roads-Snow Removal | 0 |  |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting80020191230-3-R1Dozer D6 or equal91215 | Corbiere and Sons Contracting80020191230-3-R1Dozer D6 or equal91215Inv#022 | [5 empty] | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 800 | 20191230-3-R1 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2020-01-05 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Wind Farm and various access roads-Snow Removal |  |  | Wind Farm and various access roads-Snow Removal | 0 |  |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting80020191230-3-R1Dozer D6 or equal91215 | Corbiere and Sons Contracting80020191230-3-R1Dozer D6 or equal91215Inv#022 | [5 empty] | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 800 | 20191230-3-R1 | 53510111 | Access | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-05 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Wind Farm and various access roads-Snow Removal |  |  | Wind Farm and various access roads-Snow Removal | 0 |  |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting80020191230-3-R1Excavator - 36 ton91539 | Corbiere and Sons Contracting80020191230-3-R1Excavator - 36 ton91539Inv#022 | [5 empty] | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 800 | 20191230-3-R1 | 53510111 | Access | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-05 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Wind Farm and various access roads-Snow Removal |  |  | Wind Farm and various access roads-Snow Removal | 0 |  |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting80020191230-3-R1Excavator - 36 ton91539 | Corbiere and Sons Contracting80020191230-3-R1Excavator - 36 ton91539Inv#022 | [5 empty] | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 800 | 20191230-3-R1 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 18 | HR | 94.5 | 0 |  |  | 2268 | 294.84 | 2562.84 | 2020-01-05 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Wind Farm and various access roads-Snow Removal |  |  | Wind Farm and various access roads-Snow Removal | 0 |  |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting80020191230-3-R1Grader - Cat 12 to 14 or equal182268 | Corbiere and Sons Contracting80020191230-3-R1Grader - Cat 12 to 14 or equal182268Inv#022 | [5 empty] | 1 | 2268 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 800 | 20191230-3-R1 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2020-01-05 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Wind Farm and various access roads-Snow Removal |  |  | Wind Farm and various access roads-Snow Removal | 0 |  |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting80020191230-3-R1Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting80020191230-3-R1Loader JD 524 to 624 or equal9891Inv#022 | [5 empty] | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 800 | 20191230-3-R1 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2020-01-05 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Wind Farm and various access roads-Snow Removal |  |  | Wind Farm and various access roads-Snow Removal | 0 |  |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting80020191230-3-R1Light Truck - Pick up401200 | Corbiere and Sons Contracting80020191230-3-R1Light Truck - Pick up401200Inv#022 | [5 empty] | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 800 | 20191230-3-R1 | 53510111 | Access | 0 | Operator - Principle | 90 | 88 | HR |  |  |  | 0 | 7920 | 1029.6 | 8949.6 | 2020-01-05 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Wind Farm and various access roads-Snow Removal |  |  | Wind Farm and various access roads-Snow Removal | 0 |  |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting80020191230-3-R1Operator - Principle887920 | Corbiere and Sons Contracting80020191230-3-R1Operator - Principle887920Inv#022 | [5 empty] | 1 | 7920 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 800 | 20191230-3-R1 | 53510111 | Access | 0 | Labourer - General | 65 | 22 | HR |  |  |  | 0 | 1430 | 185.9 | 1615.9 | 2020-01-05 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Wind Farm and various access roads-Snow Removal |  |  | Wind Farm and various access roads-Snow Removal | 0 |  |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting80020191230-3-R1Labourer - General221430 | Corbiere and Sons Contracting80020191230-3-R1Labourer - General221430Inv#022 | [5 empty] | 1 | 1430 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 800 | 20191230-3-R1 | 53510111 | Access | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2020-01-05 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Wind Farm and various access roads-Snow Removal |  |  | Wind Farm and various access roads-Snow Removal | 0 |  |  | 40 | 43934 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting80020191230-3-R1L.O.A.91890 | Corbiere and Sons Contracting80020191230-3-R1L.O.A.91890Inv#022 | [5 empty] | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 802 | 20191230-4 | 53510111 | Access | 0 | Mechanics Truck | 55 | 10 | HR | 41.25 | 0 |  |  | 550 | 71.5 | 621.5 | 2020-01-05 |  |  |  |  | 1 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 13 | Rejected | Rejected Mechanic Charges - Resubmitted on new LEMS | 9014 | Equipment Repair-Continuing repairs to Sander Truck/Service Truck and ran for necessary parts |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting80220191230-4Mechanics Truck10550 | Corbiere and Sons Contracting80220191230-4Mechanics Truck10550 | [5 empty] | 1 | 550 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 802 | 20191230-4 | 53510111 | Access | 0 | Mechanic | 90 | 10 | HR |  |  |  | 0 | 900 | 117 | 1017 | 2020-01-05 |  |  |  |  | 1 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 13 | Rejected | Rejected Mechanic Charges - Resubmitted on new LEMS | 9014 | Equipment Repair-Continuing repairs to Sander Truck/Service Truck and ran for necessary parts |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting80220191230-4Mechanic10900 | Corbiere and Sons Contracting80220191230-4Mechanic10900 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 802 | 20191230-4 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-05 |  |  |  |  | 1 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 13 | Rejected | Rejected Mechanic Charges - Resubmitted on new LEMS | 9014 | Equipment Repair-Continuing repairs to Sander Truck/Service Truck and ran for necessary parts |  |  |  | 0 | [10 empty] | 01 | Corbiere and Sons Contracting80220191230-4L.O.A.1210 | Corbiere and Sons Contracting80220191230-4L.O.A.1210 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5Brusher91822.5 | Corbiere and Sons Contracting80320191230-5Brusher91822.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5Feller Buncher92160 | Corbiere and Sons Contracting80320191230-5Feller Buncher92160Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5Skidder 91539 | Corbiere and Sons Contracting80320191230-5Skidder 91539Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5Dozer D6 or equal91215 | Corbiere and Sons Contracting80320191230-5Dozer D6 or equal91215Inv#005-R01 | [5 empty] | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53520102 | Clearing | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5Excavator - 30 ton91255.5 | Corbiere and Sons Contracting80320191230-5Excavator - 30 ton91255.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5Excavator - 36 ton91539 | Corbiere and Sons Contracting80320191230-5Excavator - 36 ton91539Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5Excavator - 36 ton91539 | Corbiere and Sons Contracting80320191230-5Excavator - 36 ton91539Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton | 13.5 | 9 | HR | 10.13 | 0 |  |  | 121.5 | 15.795 | 137.295 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5Excavator Thumb - 30 - 50 ton9121.5 | Corbiere and Sons Contracting80320191230-5Excavator Thumb - 30 - 50 ton9121.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 121.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton | 13.5 | 9 | HR | 10.13 | 0 |  |  | 121.5 | 15.795 | 137.295 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5Excavator Thumb - 30 - 50 ton9121.5 | Corbiere and Sons Contracting80320191230-5Excavator Thumb - 30 - 50 ton9121.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 121.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton | 13.5 | 9 | HR | 10.13 | 0 |  |  | 121.5 | 15.795 | 137.295 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5Excavator Thumb - 30 - 50 ton9121.5 | Corbiere and Sons Contracting80320191230-5Excavator Thumb - 30 - 50 ton9121.5Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 121.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting80320191230-5Grader - Cat 12 to 14 or equal91134Inv#005-R01 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5Light Truck - Pick up20600 | Corbiere and Sons Contracting80320191230-5Light Truck - Pick up20600Inv#005-R01 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5Light Truck - Pick up30900 | Corbiere and Sons Contracting80320191230-5Light Truck - Pick up30900Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5Light Truck - Pick up20600 | Corbiere and Sons Contracting80320191230-5Light Truck - Pick up20600Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53510111 | Access | 0 | Foreman | 95 | 1 | HR |  |  |  | 0 | 95 | 12.35 | 107.35 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5Foreman195 | Corbiere and Sons Contracting80320191230-5Foreman195Inv#005-R01 | [5 empty] | 1 | 95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53520101 | Clearing | 0 | Foreman | 95 | 9 | HR |  |  |  | 0 | 855 | 111.15 | 966.15 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5Foreman9855 | Corbiere and Sons Contracting80320191230-5Foreman9855Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 855 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53520102 | Clearing | 0 | Foreman | 95 | 2 | HR |  |  |  | 0 | 190 | 24.7 | 214.7 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5Foreman2190 | Corbiere and Sons Contracting80320191230-5Foreman2190Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5Operator - Principle11990 | Corbiere and Sons Contracting80320191230-5Operator - Principle11990Inv#005-R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5Operator - Principle221980 | Corbiere and Sons Contracting80320191230-5Operator - Principle221980Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5Operator - Principle443960 | Corbiere and Sons Contracting80320191230-5Operator - Principle443960Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5L.O.A.1210 | Corbiere and Sons Contracting80320191230-5L.O.A.1210Inv#005-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5L.O.A.2420 | Corbiere and Sons Contracting80320191230-5L.O.A.2420Inv#005-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 803 | 20191230-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-05 | 1 | Inv#005-R01 | 43841 | 83 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | NS-FB-01 cut Row B006 to B004 -NS-SK-01 Tower B004- Grader NS-GR-01 Wolf Lake Drive and Cavern Road-NS-Ex-01 Raking B006 to B007 -NS-EX-02 racking between Towers B008 to B006 - NS-EX-04 Racking Tower B006 to B007 - NS-BR-01 Brushing Cavern Road. |  |  | Fish Hatchery Road - A128 - B017 | 0 |  |  | 36 | 43836 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80320191230-5L.O.A.51050 | Corbiere and Sons Contracting80320191230-5L.O.A.51050Inv#005-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 635 | 2019123-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6352019123-1Light Truck - Pick up501500 | Corbiere and Sons Contracting6352019123-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 635 | 2019123-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6352019123-1Project Manager121320 | Corbiere and Sons Contracting6352019123-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 635 | 2019123-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6352019123-1Superintendent121260 | Corbiere and Sons Contracting6352019123-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 635 | 2019123-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6352019123-1Project Coordinator12960 | Corbiere and Sons Contracting6352019123-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 635 | 2019123-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6352019123-1Safety Advisor121020 | Corbiere and Sons Contracting6352019123-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 635 | 2019123-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6352019123-1Project Controls12840 | Corbiere and Sons Contracting6352019123-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 635 | 2019123-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Supervision | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6352019123-1L.O.A.51050 | Corbiere and Sons Contracting6352019123-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 804 | 20191231-1 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-31 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80420191231-1Light Truck - Pick up10300 | Corbiere and Sons Contracting80420191231-1Light Truck - Pick up10300Inv#006R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 804 | 20191231-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-31 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80420191231-1Light Truck - Pick up10300 | Corbiere and Sons Contracting80420191231-1Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 804 | 20191231-1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-31 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80420191231-1Light Truck - Pick up10300 | Corbiere and Sons Contracting80420191231-1Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 804 | 20191231-1 | 53510111 | Access | 0 | Project Manager | 110 | 3 | HR |  |  | 110 | 0 | 330 | 42.9 | 372.9 | 2019-12-31 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80420191231-1Project Manager3330 | Corbiere and Sons Contracting80420191231-1Project Manager3330Inv#006R01 | [5 empty] | 1 | 330 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 804 | 20191231-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 3 | HR |  |  | 110 | 0 | 330 | 42.9 | 372.9 | 2019-12-31 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80420191231-1Project Manager3330 | Corbiere and Sons Contracting80420191231-1Project Manager3330Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 330 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 804 | 20191231-1 | 53520102 | Clearing | 0 | Project Manager | 110 | 3 | HR |  |  | 110 | 0 | 330 | 42.9 | 372.9 | 2019-12-31 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80420191231-1Project Manager3330 | Corbiere and Sons Contracting80420191231-1Project Manager3330Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 330 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 804 | 20191231-1 | 53510111 | Access | 0 | Superintendent | 105 | 3 | HR |  |  | 105 | 0 | 315 | 40.95 | 355.95 | 2019-12-31 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80420191231-1Superintendent3315 | Corbiere and Sons Contracting80420191231-1Superintendent3315Inv#006R01 | [5 empty] | 1 | 315 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 804 | 20191231-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 3 | HR |  |  | 105 | 0 | 315 | 40.95 | 355.95 | 2019-12-31 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80420191231-1Superintendent3315 | Corbiere and Sons Contracting80420191231-1Superintendent3315Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 315 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 804 | 20191231-1 | 53520102 | Clearing | 0 | Superintendent | 105 | 3 | HR |  |  | 105 | 0 | 315 | 40.95 | 355.95 | 2019-12-31 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80420191231-1Superintendent3315 | Corbiere and Sons Contracting80420191231-1Superintendent3315Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 315 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 804 | 20191231-1 | 53510111 | Access | 0 | Project Coordinator | 80 | 3 | HR |  |  | 80 | 0 | 240 | 31.2 | 271.2 | 2019-12-31 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80420191231-1Project Coordinator3240 | Corbiere and Sons Contracting80420191231-1Project Coordinator3240Inv#006R01 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 804 | 20191231-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 3 | HR |  |  | 80 | 0 | 240 | 31.2 | 271.2 | 2019-12-31 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80420191231-1Project Coordinator3240 | Corbiere and Sons Contracting80420191231-1Project Coordinator3240Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 804 | 20191231-1 | 53520102 | Clearing | 0 | Project Coordinator | 80 | 3 | HR |  |  | 80 | 0 | 240 | 31.2 | 271.2 | 2019-12-31 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80420191231-1Project Coordinator3240 | Corbiere and Sons Contracting80420191231-1Project Coordinator3240Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 804 | 20191231-1 | 53510111 | Access | 0 | Project Controls | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2019-12-31 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80420191231-1Project Controls3210 | Corbiere and Sons Contracting80420191231-1Project Controls3210Inv#006R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 804 | 20191231-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2019-12-31 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80420191231-1Project Controls3210 | Corbiere and Sons Contracting80420191231-1Project Controls3210Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 804 | 20191231-1 | 53520102 | Clearing | 0 | Project Controls | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2019-12-31 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80420191231-1Project Controls3210 | Corbiere and Sons Contracting80420191231-1Project Controls3210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 804 | 20191231-1 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-31 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80420191231-1L.O.A.1210 | Corbiere and Sons Contracting80420191231-1L.O.A.1210Inv#006R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 804 | 20191231-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-31 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80420191231-1L.O.A.1210 | Corbiere and Sons Contracting80420191231-1L.O.A.1210Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 804 | 20191231-1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-31 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510107,53510111,53520101,53520102 - these codes had cost on the given day |  |  |  |  | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80420191231-1L.O.A.1210 | Corbiere and Sons Contracting80420191231-1L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 805 | 20191231-2 | 53520102 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 6 | HR | 74.25 | 0 |  |  | 594 | 77.22 | 671.22 | 2020-01-05 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance |  |  | General yard maintenance | 0 |  |  | 36 | 43852 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80520191231-2Loader JD 524 to 624 or equal6594 | Corbiere and Sons Contracting80520191231-2Loader JD 524 to 624 or equal6594INV#027 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 594 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 805 | 20191231-2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-05 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance |  |  | General yard maintenance | 0 |  |  | 36 | 43852 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80520191231-2Light Truck - Pick up10300 | Corbiere and Sons Contracting80520191231-2Light Truck - Pick up10300INV#027 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 805 | 20191231-2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2020-01-05 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | General yard maintenance |  |  | General yard maintenance | 0 |  |  | 36 | 43852 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80520191231-2Operator - Apprentice10600 | Corbiere and Sons Contracting80520191231-2Operator - Apprentice10600INV#027 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 806 | 20191231-3-R2 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Removal-Wind Farm and various access roads |  |  | Snow Removal-Wind Farm and various access roads | 0 |  |  | 36 | 43834 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80620191231-3-R2Dozer D6 or equal91215 | Corbiere and Sons Contracting80620191231-3-R2Dozer D6 or equal91215Inv#006R01 | [5 empty] | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 806 | 20191231-3-R2 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Removal-Wind Farm and various access roads |  |  | Snow Removal-Wind Farm and various access roads | 0 |  |  | 36 | 43834 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80620191231-3-R2Dozer D6 or equal91215 | Corbiere and Sons Contracting80620191231-3-R2Dozer D6 or equal91215Inv#006R01 | [5 empty] | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 806 | 20191231-3-R2 | 53510111 | Access | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Removal-Wind Farm and various access roads |  |  | Snow Removal-Wind Farm and various access roads | 0 |  |  | 36 | 43834 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80620191231-3-R2Excavator - 36 ton91539 | Corbiere and Sons Contracting80620191231-3-R2Excavator - 36 ton91539Inv#006R01 | [5 empty] | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 806 | 20191231-3-R2 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 18 | HR | 94.5 | 0 |  |  | 2268 | 294.84 | 2562.84 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Removal-Wind Farm and various access roads |  |  | Snow Removal-Wind Farm and various access roads | 0 |  |  | 36 | 43834 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80620191231-3-R2Grader - Cat 12 to 14 or equal182268 | Corbiere and Sons Contracting80620191231-3-R2Grader - Cat 12 to 14 or equal182268Inv#006R01 | [5 empty] | 1 | 2268 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 806 | 20191231-3-R2 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Removal-Wind Farm and various access roads |  |  | Snow Removal-Wind Farm and various access roads | 0 |  |  | 36 | 43834 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80620191231-3-R2Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting80620191231-3-R2Loader JD 524 to 624 or equal9891Inv#006R01 | [5 empty] | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 806 | 20191231-3-R2 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Removal-Wind Farm and various access roads |  |  | Snow Removal-Wind Farm and various access roads | 0 |  |  | 36 | 43834 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80620191231-3-R2Light Truck - Pick up401200 | Corbiere and Sons Contracting80620191231-3-R2Light Truck - Pick up401200Inv#006R01 | [5 empty] | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 806 | 20191231-3-R2 | 53510111 | Access | 0 | Operator - Principle | 90 | 66 | HR |  |  |  | 0 | 5940 | 772.2 | 6712.2 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Removal-Wind Farm and various access roads |  |  | Snow Removal-Wind Farm and various access roads | 0 |  |  | 36 | 43834 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80620191231-3-R2Operator - Principle665940 | Corbiere and Sons Contracting80620191231-3-R2Operator - Principle665940Inv#006R01 | [5 empty] | 1 | 5940 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 806 | 20191231-3-R2 | 53510111 | Access | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Removal-Wind Farm and various access roads |  |  | Snow Removal-Wind Farm and various access roads | 0 |  |  | 36 | 43834 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80620191231-3-R2Labourer - Specialized11825 | Corbiere and Sons Contracting80620191231-3-R2Labourer - Specialized11825Inv#006R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 806 | 20191231-3-R2 | 53510111 | Access | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Removal-Wind Farm and various access roads |  |  | Snow Removal-Wind Farm and various access roads | 0 |  |  | 36 | 43834 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80620191231-3-R2Labourer - General11715 | Corbiere and Sons Contracting80620191231-3-R2Labourer - General11715Inv#006R01 | [5 empty] | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 806 | 20191231-3-R2 | 53510111 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Snow Removal-Wind Farm and various access roads |  |  | Snow Removal-Wind Farm and various access roads | 0 |  |  | 36 | 43834 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting80620191231-3-R2L.O.A.71470 | Corbiere and Sons Contracting80620191231-3-R2L.O.A.71470Inv#006R01 | [5 empty] | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 636 | 2019123-2-R2 | 53520102 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 |  | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Yard Maintenance |  |  | Welding/Equipment Repairs | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6362019123-2-R2Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting6362019123-2-R2Loader JD 524 to 624 or equal9891Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 636 | 2019123-2-R2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 |  | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Yard Maintenance |  |  | Welding/Equipment Repairs | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6362019123-2-R2Light Truck - Pick up10300 | Corbiere and Sons Contracting6362019123-2-R2Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 636 | 2019123-2-R2 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 |  | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Yard Maintenance |  |  | Welding/Equipment Repairs | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6362019123-2-R2Operator - Principle121080 | Corbiere and Sons Contracting6362019123-2-R2Operator - Principle121080Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 636 | 2019123-2-R2 | 53520102 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 |  | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Yard Maintenance |  |  | Welding/Equipment Repairs | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6362019123-2-R2Labourer - General10650 | Corbiere and Sons Contracting6362019123-2-R2Labourer - General10650Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 636 | 2019123-2-R2 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 |  | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Yard Maintenance |  |  | Welding/Equipment Repairs | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6362019123-2-R2L.O.A.1210 | Corbiere and Sons Contracting6362019123-2-R2L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 638 | 2019123-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, fuelling, installing culverts, and spotting; DZ002 gravelled at A061 and then was floated to Wind Farm; EX5 gravelled and installed culverts; EX001 at pit loading gravel trucks; Float truck moved DZ2 to wind farm, DZ1 from Pearl Pit to KB lake Pit, moved FB from A091 to A042; Handfelling at A061 and for new saw hands did orientation. |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6382019123-4Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting6382019123-4Grinder - 4710 Peterson or equal95011.2Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 638 | 2019123-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, fuelling, installing culverts, and spotting; DZ002 gravelled at A061 and then was floated to Wind Farm; EX5 gravelled and installed culverts; EX001 at pit loading gravel trucks; Float truck moved DZ2 to wind farm, DZ1 from Pearl Pit to KB lake Pit, moved FB from A091 to A042; Handfelling at A061 and for new saw hands did orientation. |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6382019123-4Log Loader91377 | Corbiere and Sons Contracting6382019123-4Log Loader91377Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 638 | 2019123-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 2 | Day |  | 0 |  |  | 240 | 31.2 | 271.2 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, fuelling, installing culverts, and spotting; DZ002 gravelled at A061 and then was floated to Wind Farm; EX5 gravelled and installed culverts; EX001 at pit loading gravel trucks; Float truck moved DZ2 to wind farm, DZ1 from Pearl Pit to KB lake Pit, moved FB from A091 to A042; Handfelling at A061 and for new saw hands did orientation. |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6382019123-4Chainsaw and consummables2240 | Corbiere and Sons Contracting6382019123-4Chainsaw and consummables2240Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 638 | 2019123-4 | 53510111 | Access | 0 | Sander Truck | 112.5 | 11 | HR | 84.38 | 0 |  |  | 1237.5 | 160.875 | 1398.375 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, fuelling, installing culverts, and spotting; DZ002 gravelled at A061 and then was floated to Wind Farm; EX5 gravelled and installed culverts; EX001 at pit loading gravel trucks; Float truck moved DZ2 to wind farm, DZ1 from Pearl Pit to KB lake Pit, moved FB from A091 to A042; Handfelling at A061 and for new saw hands did orientation. |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6382019123-4Sander Truck111237.5 | Corbiere and Sons Contracting6382019123-4Sander Truck111237.5Inv#004-R02 | [5 empty] | 1 | 1237.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 638 | 2019123-4 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, fuelling, installing culverts, and spotting; DZ002 gravelled at A061 and then was floated to Wind Farm; EX5 gravelled and installed culverts; EX001 at pit loading gravel trucks; Float truck moved DZ2 to wind farm, DZ1 from Pearl Pit to KB lake Pit, moved FB from A091 to A042; Handfelling at A061 and for new saw hands did orientation. |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6382019123-4Light Truck - Pick up10300 | Corbiere and Sons Contracting6382019123-4Light Truck - Pick up10300Inv#004-R02 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 638 | 2019123-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, fuelling, installing culverts, and spotting; DZ002 gravelled at A061 and then was floated to Wind Farm; EX5 gravelled and installed culverts; EX001 at pit loading gravel trucks; Float truck moved DZ2 to wind farm, DZ1 from Pearl Pit to KB lake Pit, moved FB from A091 to A042; Handfelling at A061 and for new saw hands did orientation. |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6382019123-4Light Truck - Pick up10300 | Corbiere and Sons Contracting6382019123-4Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 638 | 2019123-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, fuelling, installing culverts, and spotting; DZ002 gravelled at A061 and then was floated to Wind Farm; EX5 gravelled and installed culverts; EX001 at pit loading gravel trucks; Float truck moved DZ2 to wind farm, DZ1 from Pearl Pit to KB lake Pit, moved FB from A091 to A042; Handfelling at A061 and for new saw hands did orientation. |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6382019123-4Light Truck - Pick up10300 | Corbiere and Sons Contracting6382019123-4Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 638 | 2019123-4 | 53510111 | Access | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, fuelling, installing culverts, and spotting; DZ002 gravelled at A061 and then was floated to Wind Farm; EX5 gravelled and installed culverts; EX001 at pit loading gravel trucks; Float truck moved DZ2 to wind farm, DZ1 from Pearl Pit to KB lake Pit, moved FB from A091 to A042; Handfelling at A061 and for new saw hands did orientation. |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6382019123-4Foreman4380 | Corbiere and Sons Contracting6382019123-4Foreman4380Inv#004-R02 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 638 | 2019123-4 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, fuelling, installing culverts, and spotting; DZ002 gravelled at A061 and then was floated to Wind Farm; EX5 gravelled and installed culverts; EX001 at pit loading gravel trucks; Float truck moved DZ2 to wind farm, DZ1 from Pearl Pit to KB lake Pit, moved FB from A091 to A042; Handfelling at A061 and for new saw hands did orientation. |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6382019123-4Foreman121140 | Corbiere and Sons Contracting6382019123-4Foreman121140Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 638 | 2019123-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, fuelling, installing culverts, and spotting; DZ002 gravelled at A061 and then was floated to Wind Farm; EX5 gravelled and installed culverts; EX001 at pit loading gravel trucks; Float truck moved DZ2 to wind farm, DZ1 from Pearl Pit to KB lake Pit, moved FB from A091 to A042; Handfelling at A061 and for new saw hands did orientation. |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6382019123-4Operator - Principle11990 | Corbiere and Sons Contracting6382019123-4Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 638 | 2019123-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, fuelling, installing culverts, and spotting; DZ002 gravelled at A061 and then was floated to Wind Farm; EX5 gravelled and installed culverts; EX001 at pit loading gravel trucks; Float truck moved DZ2 to wind farm, DZ1 from Pearl Pit to KB lake Pit, moved FB from A091 to A042; Handfelling at A061 and for new saw hands did orientation. |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6382019123-4Operator - Principle11990 | Corbiere and Sons Contracting6382019123-4Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 638 | 2019123-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, fuelling, installing culverts, and spotting; DZ002 gravelled at A061 and then was floated to Wind Farm; EX5 gravelled and installed culverts; EX001 at pit loading gravel trucks; Float truck moved DZ2 to wind farm, DZ1 from Pearl Pit to KB lake Pit, moved FB from A091 to A042; Handfelling at A061 and for new saw hands did orientation. |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6382019123-4Labourer - Specialized11825 | Corbiere and Sons Contracting6382019123-4Labourer - Specialized11825Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 638 | 2019123-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 20 | HR |  |  |  | 0 | 1500 | 195 | 1695 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, fuelling, installing culverts, and spotting; DZ002 gravelled at A061 and then was floated to Wind Farm; EX5 gravelled and installed culverts; EX001 at pit loading gravel trucks; Float truck moved DZ2 to wind farm, DZ1 from Pearl Pit to KB lake Pit, moved FB from A091 to A042; Handfelling at A061 and for new saw hands did orientation. |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6382019123-4Labourer - Specialized201500 | Corbiere and Sons Contracting6382019123-4Labourer - Specialized201500Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 638 | 2019123-4 | 53510111 | Access | 0 | Labourer - General | 65 | 3 | HR |  |  |  | 0 | 195 | 25.35 | 220.35 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, fuelling, installing culverts, and spotting; DZ002 gravelled at A061 and then was floated to Wind Farm; EX5 gravelled and installed culverts; EX001 at pit loading gravel trucks; Float truck moved DZ2 to wind farm, DZ1 from Pearl Pit to KB lake Pit, moved FB from A091 to A042; Handfelling at A061 and for new saw hands did orientation. |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6382019123-4Labourer - General3195 | Corbiere and Sons Contracting6382019123-4Labourer - General3195Inv#004-R02 | [5 empty] | 1 | 195 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 638 | 2019123-4 | 53510111 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, fuelling, installing culverts, and spotting; DZ002 gravelled at A061 and then was floated to Wind Farm; EX5 gravelled and installed culverts; EX001 at pit loading gravel trucks; Float truck moved DZ2 to wind farm, DZ1 from Pearl Pit to KB lake Pit, moved FB from A091 to A042; Handfelling at A061 and for new saw hands did orientation. |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6382019123-4L.O.A.3630 | Corbiere and Sons Contracting6382019123-4L.O.A.3630Inv#004-R02 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 638 | 2019123-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, fuelling, installing culverts, and spotting; DZ002 gravelled at A061 and then was floated to Wind Farm; EX5 gravelled and installed culverts; EX001 at pit loading gravel trucks; Float truck moved DZ2 to wind farm, DZ1 from Pearl Pit to KB lake Pit, moved FB from A091 to A042; Handfelling at A061 and for new saw hands did orientation. |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6382019123-4L.O.A.1210 | Corbiere and Sons Contracting6382019123-4L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 638 | 2019123-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers were flagging, fuelling, installing culverts, and spotting; DZ002 gravelled at A061 and then was floated to Wind Farm; EX5 gravelled and installed culverts; EX001 at pit loading gravel trucks; Float truck moved DZ2 to wind farm, DZ1 from Pearl Pit to KB lake Pit, moved FB from A091 to A042; Handfelling at A061 and for new saw hands did orientation. |  |  | Eldorado Road - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6382019123-4L.O.A.61260 | Corbiere and Sons Contracting6382019123-4L.O.A.61260Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 18 | HR | 151.88 | 0 |  |  | 3645 | 473.85 | 4118.85 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5Brusher183645 | Corbiere and Sons Contracting6392019123-5Brusher183645Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3645 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 36 | HR | 180 | 0 |  |  | 8640 | 1123.2 | 9763.2 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5Feller Buncher368640 | Corbiere and Sons Contracting6392019123-5Feller Buncher368640Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 8640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520101 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting6392019123-5Grinder - 4710 Peterson or equal95011.2Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5Log Loader91377 | Corbiere and Sons Contracting6392019123-5Log Loader91377Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520102 | Clearing | 0 | Mulcher | 205 | 3 | HR | 153.75 | 0 |  |  | 615 | 79.95 | 694.95 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5Mulcher3615 | Corbiere and Sons Contracting6392019123-5Mulcher3615Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 615 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520101 | Clearing | 0 | Skidder | 171 | 36 | HR | 128.25 | 0 |  |  | 6156 | 800.28 | 6956.28 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5Skidder 366156 | Corbiere and Sons Contracting6392019123-5Skidder 366156Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 6156 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 8 | Day |  | 0 |  |  | 960 | 124.8 | 1084.8 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5Chainsaw and consummables8960 | Corbiere and Sons Contracting6392019123-5Chainsaw and consummables8960Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 9 | HR | 97.88 | 0 |  |  | 1174.5 | 152.685 | 1327.185 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5Excavator - 20 ton91174.5 | Corbiere and Sons Contracting6392019123-5Excavator - 20 ton91174.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1174.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520102 | Clearing | 0 | Excavator - 50 ton | 189 | 9 | HR | 141.75 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5Excavator - 50 ton91701 | Corbiere and Sons Contracting6392019123-5Excavator - 50 ton91701Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1701 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5Light Truck - Pick up30900 | Corbiere and Sons Contracting6392019123-5Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5Light Truck - Pick up10300 | Corbiere and Sons Contracting6392019123-5Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5Light Truck - Pick up401200 | Corbiere and Sons Contracting6392019123-5Light Truck - Pick up401200Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5Light Truck - Pick up30900 | Corbiere and Sons Contracting6392019123-5Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5Foreman121140 | Corbiere and Sons Contracting6392019123-5Foreman121140Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 33 | HR |  |  |  | 0 | 2970 | 386.1 | 3356.1 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5Operator - Principle332970 | Corbiere and Sons Contracting6392019123-5Operator - Principle332970Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2970 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5Operator - Principle221980 | Corbiere and Sons Contracting6392019123-5Operator - Principle221980Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5Operator - Principle11990 | Corbiere and Sons Contracting6392019123-5Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 4 | HR |  |  |  | 0 | 360 | 46.8 | 406.8 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5Operator - Principle4360 | Corbiere and Sons Contracting6392019123-5Operator - Principle4360Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5Operator - Principle221980 | Corbiere and Sons Contracting6392019123-5Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 77 | HR |  |  |  | 0 | 6930 | 900.9 | 7830.9 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5Operator - Principle776930 | Corbiere and Sons Contracting6392019123-5Operator - Principle776930Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 6930 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 77 | HR |  |  |  | 0 | 5775 | 750.75 | 6525.75 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5Labourer - Specialized775775 | Corbiere and Sons Contracting6392019123-5Labourer - Specialized775775Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 5775 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5L.O.A.51050 | Corbiere and Sons Contracting6392019123-5L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5L.O.A.102100 | Corbiere and Sons Contracting6392019123-5L.O.A.102100Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 639 | 2019123-5 | 53520104 | Clearing | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding from A112; Handfelling from A114 to A115; 4 FBs and 3 SKDs cutting at A082 East, finishing access into ROW; DZ and Exs working on road gravelling at A111; Exs Raking at A102; 1 FB and 1 SKD walked out to be floated to A042; Pat Steinberg ran Mulcher for part of day and DZ for rest; All Brushers working between A109 and A111. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6392019123-5L.O.A.81680 | Corbiere and Sons Contracting6392019123-5L.O.A.81680Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 640 | 2019123-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling at night |  |  | Across all segments (Most of equipment at WindFarm) | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6402019123-6Light Truck - Pick up20600 | Corbiere and Sons Contracting6402019123-6Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 640 | 2019123-6 | 53520102 | Clearing | 0 | Labourer - General | 65 | 27 | HR |  |  |  | 0 | 1755 | 228.15 | 1983.15 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling at night |  |  | Across all segments (Most of equipment at WindFarm) | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6402019123-6Labourer - General271755 | Corbiere and Sons Contracting6402019123-6Labourer - General271755Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1755 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 640 | 2019123-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling at night |  |  | Across all segments (Most of equipment at WindFarm) | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6402019123-6L.O.A.1210 | Corbiere and Sons Contracting6402019123-6L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 641 | 2019123-7 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 |  | HR | 94.5 | 9 |  |  | 850.5 | 110.565 | 961.065 | 2019-12-06 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | No Work for 2 Graders; Both on SB for the day |  |  | Standby | 0 |  |  | 12 | 43843 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6412019123-7Grader - Cat 12 to 14 or equal850.5 | Corbiere and Sons Contracting6412019123-7Grader - Cat 12 to 14 or equal850.5Inv#006R01 | [5 empty] | 1 | 850.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 641 | 2019123-7 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 |  | HR | 94.5 | 9 |  |  | 850.5 | 110.565 | 961.065 | 2019-12-06 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | No Work for 2 Graders; Both on SB for the day |  |  | Standby | 0 |  |  | 12 | 43843 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6412019123-7Grader - Cat 12 to 14 or equal850.5 | Corbiere and Sons Contracting6412019123-7Grader - Cat 12 to 14 or equal850.5Inv#006R01 | [5 empty] | 1 | 850.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 642 | 2019124-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 0 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6422019124-1Light Truck - Pick up501500 | Corbiere and Sons Contracting6422019124-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 642 | 2019124-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  | 0 | 0 | 1320 | 171.6 | 1491.6 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6422019124-1Project Manager121320 | Corbiere and Sons Contracting6422019124-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 642 | 2019124-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  | 0 | 0 | 1260 | 163.8 | 1423.8 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6422019124-1Superintendent121260 | Corbiere and Sons Contracting6422019124-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 642 | 2019124-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  | 0 | 0 | 960 | 124.8 | 1084.8 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6422019124-1Project Coordinator12960 | Corbiere and Sons Contracting6422019124-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 642 | 2019124-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  | 0 | 0 | 1020 | 132.6 | 1152.6 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6422019124-1Safety Advisor121020 | Corbiere and Sons Contracting6422019124-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 642 | 2019124-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  | 0 | 0 | 840 | 109.2 | 949.2 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6422019124-1Project Controls12840 | Corbiere and Sons Contracting6422019124-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 642 | 2019124-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  | 0 | 0 | 1050 | 136.5 | 1186.5 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6422019124-1L.O.A.51050 | Corbiere and Sons Contracting6422019124-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 650 | 2019124-2-R2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 0 | 0 |  |  | 300 | 39 | 339 |  | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenance Bradley work on SKD fixing hose; Sean cleaned up shop and set up bins for disposal; Jack running for parts and supplies throughout the day |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6502019124-2-R2Light Truck - Pick up10300 | Corbiere and Sons Contracting6502019124-2-R2Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 650 | 2019124-2-R2 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 12 | HR |  |  |  | 0 | 1080 | 140.4 | 1220.4 |  | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenance Bradley work on SKD fixing hose; Sean cleaned up shop and set up bins for disposal; Jack running for parts and supplies throughout the day |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6502019124-2-R2Operator - Principle121080 | Corbiere and Sons Contracting6502019124-2-R2Operator - Principle121080Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 650 | 2019124-2-R2 | 53520102 | Clearing | 0 | Labourer - General | 65 | 10 | HR |  |  |  | 0 | 650 | 84.5 | 734.5 |  | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenance Bradley work on SKD fixing hose; Sean cleaned up shop and set up bins for disposal; Jack running for parts and supplies throughout the day |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6502019124-2-R2Labourer - General10650 | Corbiere and Sons Contracting6502019124-2-R2Labourer - General10650Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 650 | 2019124-2-R2 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 |  | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenance Bradley work on SKD fixing hose; Sean cleaned up shop and set up bins for disposal; Jack running for parts and supplies throughout the day |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6502019124-2-R2L.O.A.1210 | Corbiere and Sons Contracting6502019124-2-R2L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 644 | 2019124-3 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Lifted and bolted 9M Bridge Together; Cutting of brush from A042 to A041; Piled rush and built exit ramp; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43807 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting6442019124-3Feller Buncher92160 | Corbiere and Sons Contracting6442019124-3Feller Buncher92160Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 644 | 2019124-3 | 53520102 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Lifted and bolted 9M Bridge Together; Cutting of brush from A042 to A041; Piled rush and built exit ramp; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43807 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting6442019124-3Skidder 91539 | Corbiere and Sons Contracting6442019124-3Skidder 91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 644 | 2019124-3 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 7 | HR | 128.25 | 0 |  |  | 1197 | 155.61 | 1352.61 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Lifted and bolted 9M Bridge Together; Cutting of brush from A042 to A041; Piled rush and built exit ramp; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43807 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting6442019124-3Excavator - 36 ton71197 | Corbiere and Sons Contracting6442019124-3Excavator - 36 ton71197Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1197 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 644 | 2019124-3 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 7 | HR | 128.25 | 0 |  |  | 1197 | 155.61 | 1352.61 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Lifted and bolted 9M Bridge Together; Cutting of brush from A042 to A041; Piled rush and built exit ramp; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43807 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting6442019124-3Excavator - 36 ton71197 | Corbiere and Sons Contracting6442019124-3Excavator - 36 ton71197Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1197 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 644 | 2019124-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Lifted and bolted 9M Bridge Together; Cutting of brush from A042 to A041; Piled rush and built exit ramp; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43807 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting6442019124-3Light Truck - Pick up20600 | Corbiere and Sons Contracting6442019124-3Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 644 | 2019124-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Lifted and bolted 9M Bridge Together; Cutting of brush from A042 to A041; Piled rush and built exit ramp; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43807 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting6442019124-3Light Truck - Pick up20600 | Corbiere and Sons Contracting6442019124-3Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 644 | 2019124-3 | 53520102 | Clearing | 0 | Foreman | 95 | 10 | HR |  |  |  | 0 | 950 | 123.5 | 1073.5 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Lifted and bolted 9M Bridge Together; Cutting of brush from A042 to A041; Piled rush and built exit ramp; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43807 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting6442019124-3Foreman10950 | Corbiere and Sons Contracting6442019124-3Foreman10950Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 644 | 2019124-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 9 | HR |  |  |  | 0 | 810 | 105.3 | 915.3 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Lifted and bolted 9M Bridge Together; Cutting of brush from A042 to A041; Piled rush and built exit ramp; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43807 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting6442019124-3Operator - Principle9810 | Corbiere and Sons Contracting6442019124-3Operator - Principle9810Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 810 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 644 | 2019124-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 9 | HR |  |  |  | 0 | 810 | 105.3 | 915.3 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Lifted and bolted 9M Bridge Together; Cutting of brush from A042 to A041; Piled rush and built exit ramp; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43807 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting6442019124-3Operator - Principle9810 | Corbiere and Sons Contracting6442019124-3Operator - Principle9810Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 810 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 644 | 2019124-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Lifted and bolted 9M Bridge Together; Cutting of brush from A042 to A041; Piled rush and built exit ramp; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43807 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting6442019124-3Operator - Principle221980 | Corbiere and Sons Contracting6442019124-3Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 644 | 2019124-3 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 10 | HR |  |  |  | 0 | 750 | 97.5 | 847.5 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Lifted and bolted 9M Bridge Together; Cutting of brush from A042 to A041; Piled rush and built exit ramp; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43807 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting6442019124-3Labourer - Specialized10750 | Corbiere and Sons Contracting6442019124-3Labourer - Specialized10750Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 644 | 2019124-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Lifted and bolted 9M Bridge Together; Cutting of brush from A042 to A041; Piled rush and built exit ramp; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43807 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting6442019124-3L.O.A.2420 | Corbiere and Sons Contracting6442019124-3L.O.A.2420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 645 | 2019124-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A060; Handfelling; Cutting Birch Logs at A060 for 5 hours; Labourers installing culverts, fuelling, hauling and laying GEO; Gravelling and Raking at A061 W; EX1 loading trucks at Pit; Sander Truck worked across all segments; Float Moves, EX001 to KB pit; SKD from A091 to A042; EX from Eldorado to Wind Farm. |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6452019124-4Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting6452019124-4Grinder - 4710 Peterson or equal95011.2Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 645 | 2019124-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A060; Handfelling; Cutting Birch Logs at A060 for 5 hours; Labourers installing culverts, fuelling, hauling and laying GEO; Gravelling and Raking at A061 W; EX1 loading trucks at Pit; Sander Truck worked across all segments; Float Moves, EX001 to KB pit; SKD from A091 to A042; EX from Eldorado to Wind Farm. |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6452019124-4Log Loader91377 | Corbiere and Sons Contracting6452019124-4Log Loader91377Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 645 | 2019124-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 7 | Day |  | 0 |  |  | 840 | 109.2 | 949.2 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A060; Handfelling; Cutting Birch Logs at A060 for 5 hours; Labourers installing culverts, fuelling, hauling and laying GEO; Gravelling and Raking at A061 W; EX1 loading trucks at Pit; Sander Truck worked across all segments; Float Moves, EX001 to KB pit; SKD from A091 to A042; EX from Eldorado to Wind Farm. |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6452019124-4Chainsaw and consummables7840 | Corbiere and Sons Contracting6452019124-4Chainsaw and consummables7840Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 645 | 2019124-4 | 53510111 | Access | 0 | Grader - Cat 16 to 18 or equal | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A060; Handfelling; Cutting Birch Logs at A060 for 5 hours; Labourers installing culverts, fuelling, hauling and laying GEO; Gravelling and Raking at A061 W; EX1 loading trucks at Pit; Sander Truck worked across all segments; Float Moves, EX001 to KB pit; SKD from A091 to A042; EX from Eldorado to Wind Farm. |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6452019124-4Grader - Cat 16 to 18 or equal91539 | Corbiere and Sons Contracting6452019124-4Grader - Cat 16 to 18 or equal91539Inv#004-R02 | [5 empty] | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 645 | 2019124-4 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A060; Handfelling; Cutting Birch Logs at A060 for 5 hours; Labourers installing culverts, fuelling, hauling and laying GEO; Gravelling and Raking at A061 W; EX1 loading trucks at Pit; Sander Truck worked across all segments; Float Moves, EX001 to KB pit; SKD from A091 to A042; EX from Eldorado to Wind Farm. |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6452019124-4Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting6452019124-4Loader JD 524 to 624 or equal9891Inv#004-R02 | [5 empty] | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 645 | 2019124-4 | 53510111 | Access | 0 | Sander Truck | 112.5 | 11 | HR | 84.38 | 0 |  |  | 1237.5 | 160.875 | 1398.375 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A060; Handfelling; Cutting Birch Logs at A060 for 5 hours; Labourers installing culverts, fuelling, hauling and laying GEO; Gravelling and Raking at A061 W; EX1 loading trucks at Pit; Sander Truck worked across all segments; Float Moves, EX001 to KB pit; SKD from A091 to A042; EX from Eldorado to Wind Farm. |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6452019124-4Sander Truck111237.5 | Corbiere and Sons Contracting6452019124-4Sander Truck111237.5Inv#004-R02 | [5 empty] | 1 | 1237.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 645 | 2019124-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A060; Handfelling; Cutting Birch Logs at A060 for 5 hours; Labourers installing culverts, fuelling, hauling and laying GEO; Gravelling and Raking at A061 W; EX1 loading trucks at Pit; Sander Truck worked across all segments; Float Moves, EX001 to KB pit; SKD from A091 to A042; EX from Eldorado to Wind Farm. |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6452019124-4Light Truck - Pick up10300 | Corbiere and Sons Contracting6452019124-4Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 645 | 2019124-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A060; Handfelling; Cutting Birch Logs at A060 for 5 hours; Labourers installing culverts, fuelling, hauling and laying GEO; Gravelling and Raking at A061 W; EX1 loading trucks at Pit; Sander Truck worked across all segments; Float Moves, EX001 to KB pit; SKD from A091 to A042; EX from Eldorado to Wind Farm. |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6452019124-4Light Truck - Pick up10300 | Corbiere and Sons Contracting6452019124-4Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 645 | 2019124-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A060; Handfelling; Cutting Birch Logs at A060 for 5 hours; Labourers installing culverts, fuelling, hauling and laying GEO; Gravelling and Raking at A061 W; EX1 loading trucks at Pit; Sander Truck worked across all segments; Float Moves, EX001 to KB pit; SKD from A091 to A042; EX from Eldorado to Wind Farm. |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6452019124-4Light Truck - Pick up10300 | Corbiere and Sons Contracting6452019124-4Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 645 | 2019124-4 | 53520102 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 4 | HR | 101.25 | 0 |  |  | 540 | 70.2 | 610.2 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A060; Handfelling; Cutting Birch Logs at A060 for 5 hours; Labourers installing culverts, fuelling, hauling and laying GEO; Gravelling and Raking at A061 W; EX1 loading trucks at Pit; Sander Truck worked across all segments; Float Moves, EX001 to KB pit; SKD from A091 to A042; EX from Eldorado to Wind Farm. |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6452019124-4Tractor Trailer - 60 Ton4540 | Corbiere and Sons Contracting6452019124-4Tractor Trailer - 60 Ton4540Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 540 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 645 | 2019124-4 | 53510111 | Access | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A060; Handfelling; Cutting Birch Logs at A060 for 5 hours; Labourers installing culverts, fuelling, hauling and laying GEO; Gravelling and Raking at A061 W; EX1 loading trucks at Pit; Sander Truck worked across all segments; Float Moves, EX001 to KB pit; SKD from A091 to A042; EX from Eldorado to Wind Farm. |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6452019124-4Foreman121140 | Corbiere and Sons Contracting6452019124-4Foreman121140Inv#004-R02 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 645 | 2019124-4 | 53520104 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  |  | 0 | 570 | 74.1 | 644.1 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A060; Handfelling; Cutting Birch Logs at A060 for 5 hours; Labourers installing culverts, fuelling, hauling and laying GEO; Gravelling and Raking at A061 W; EX1 loading trucks at Pit; Sander Truck worked across all segments; Float Moves, EX001 to KB pit; SKD from A091 to A042; EX from Eldorado to Wind Farm. |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6452019124-4Foreman6570 | Corbiere and Sons Contracting6452019124-4Foreman6570Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 645 | 2019124-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A060; Handfelling; Cutting Birch Logs at A060 for 5 hours; Labourers installing culverts, fuelling, hauling and laying GEO; Gravelling and Raking at A061 W; EX1 loading trucks at Pit; Sander Truck worked across all segments; Float Moves, EX001 to KB pit; SKD from A091 to A042; EX from Eldorado to Wind Farm. |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6452019124-4Operator - Principle11990 | Corbiere and Sons Contracting6452019124-4Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 645 | 2019124-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A060; Handfelling; Cutting Birch Logs at A060 for 5 hours; Labourers installing culverts, fuelling, hauling and laying GEO; Gravelling and Raking at A061 W; EX1 loading trucks at Pit; Sander Truck worked across all segments; Float Moves, EX001 to KB pit; SKD from A091 to A042; EX from Eldorado to Wind Farm. |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6452019124-4Operator - Principle11990 | Corbiere and Sons Contracting6452019124-4Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 645 | 2019124-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A060; Handfelling; Cutting Birch Logs at A060 for 5 hours; Labourers installing culverts, fuelling, hauling and laying GEO; Gravelling and Raking at A061 W; EX1 loading trucks at Pit; Sander Truck worked across all segments; Float Moves, EX001 to KB pit; SKD from A091 to A042; EX from Eldorado to Wind Farm. |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6452019124-4Operator - Principle11990 | Corbiere and Sons Contracting6452019124-4Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 645 | 2019124-4 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 4 | HR |  |  | 70 | 0 | 300 | 39 | 339 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A060; Handfelling; Cutting Birch Logs at A060 for 5 hours; Labourers installing culverts, fuelling, hauling and laying GEO; Gravelling and Raking at A061 W; EX1 loading trucks at Pit; Sander Truck worked across all segments; Float Moves, EX001 to KB pit; SKD from A091 to A042; EX from Eldorado to Wind Farm. |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6452019124-4Operator - Intermdiate4300 | Corbiere and Sons Contracting6452019124-4Operator - Intermdiate4300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 645 | 2019124-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 30 | HR |  |  |  | 0 | 2250 | 292.5 | 2542.5 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A060; Handfelling; Cutting Birch Logs at A060 for 5 hours; Labourers installing culverts, fuelling, hauling and laying GEO; Gravelling and Raking at A061 W; EX1 loading trucks at Pit; Sander Truck worked across all segments; Float Moves, EX001 to KB pit; SKD from A091 to A042; EX from Eldorado to Wind Farm. |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6452019124-4Labourer - Specialized302250 | Corbiere and Sons Contracting6452019124-4Labourer - Specialized302250Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 2250 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 645 | 2019124-4 | 53520102 | Clearing | 0 | Labourer - General | 65 | 4 | HR |  |  |  | 0 | 260 | 33.8 | 293.8 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A060; Handfelling; Cutting Birch Logs at A060 for 5 hours; Labourers installing culverts, fuelling, hauling and laying GEO; Gravelling and Raking at A061 W; EX1 loading trucks at Pit; Sander Truck worked across all segments; Float Moves, EX001 to KB pit; SKD from A091 to A042; EX from Eldorado to Wind Farm. |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6452019124-4Labourer - General4260 | Corbiere and Sons Contracting6452019124-4Labourer - General4260Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 645 | 2019124-4 | 53510111 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A060; Handfelling; Cutting Birch Logs at A060 for 5 hours; Labourers installing culverts, fuelling, hauling and laying GEO; Gravelling and Raking at A061 W; EX1 loading trucks at Pit; Sander Truck worked across all segments; Float Moves, EX001 to KB pit; SKD from A091 to A042; EX from Eldorado to Wind Farm. |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6452019124-4L.O.A.3630 | Corbiere and Sons Contracting6452019124-4L.O.A.3630Inv#004-R02 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 645 | 2019124-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A060; Handfelling; Cutting Birch Logs at A060 for 5 hours; Labourers installing culverts, fuelling, hauling and laying GEO; Gravelling and Raking at A061 W; EX1 loading trucks at Pit; Sander Truck worked across all segments; Float Moves, EX001 to KB pit; SKD from A091 to A042; EX from Eldorado to Wind Farm. |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6452019124-4L.O.A.1210 | Corbiere and Sons Contracting6452019124-4L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 645 | 2019124-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding of Material at A060; Handfelling; Cutting Birch Logs at A060 for 5 hours; Labourers installing culverts, fuelling, hauling and laying GEO; Gravelling and Raking at A061 W; EX1 loading trucks at Pit; Sander Truck worked across all segments; Float Moves, EX001 to KB pit; SKD from A091 to A042; EX from Eldorado to Wind Farm. |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6452019124-4L.O.A.71470 | Corbiere and Sons Contracting6452019124-4L.O.A.71470Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 646 | 2019124-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 27 | HR | 151.88 | 0 |  |  | 5467.5 | 710.775 | 6178.275 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A108 to A111; Grinding of Material at A113; FBs and SKDs all working between A082 and A080; Had to talk between to towers; Brush work all between towers A107 and A110; EXs installing culvert at A110 and building access ramp at A108-A107; Culvert Install and Rd. Building at A104-A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6462019124-5Brusher275467.5 | Corbiere and Sons Contracting6462019124-5Brusher275467.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5467.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 646 | 2019124-5 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 36 | HR | 180 | 0 |  |  | 8640 | 1123.2 | 9763.2 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A108 to A111; Grinding of Material at A113; FBs and SKDs all working between A082 and A080; Had to talk between to towers; Brush work all between towers A107 and A110; EXs installing culvert at A110 and building access ramp at A108-A107; Culvert Install and Rd. Building at A104-A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6462019124-5Feller Buncher368640 | Corbiere and Sons Contracting6462019124-5Feller Buncher368640Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 8640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 646 | 2019124-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A108 to A111; Grinding of Material at A113; FBs and SKDs all working between A082 and A080; Had to talk between to towers; Brush work all between towers A107 and A110; EXs installing culvert at A110 and building access ramp at A108-A107; Culvert Install and Rd. Building at A104-A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6462019124-5Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting6462019124-5Grinder - 4710 Peterson or equal95011.2Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 646 | 2019124-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A108 to A111; Grinding of Material at A113; FBs and SKDs all working between A082 and A080; Had to talk between to towers; Brush work all between towers A107 and A110; EXs installing culvert at A110 and building access ramp at A108-A107; Culvert Install and Rd. Building at A104-A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6462019124-5Log Loader91377 | Corbiere and Sons Contracting6462019124-5Log Loader91377Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 646 | 2019124-5 | 53520102 | Clearing | 0 | Skidder | 171 | 27 | HR | 128.25 | 0 |  |  | 4617 | 600.21 | 5217.21 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A108 to A111; Grinding of Material at A113; FBs and SKDs all working between A082 and A080; Had to talk between to towers; Brush work all between towers A107 and A110; EXs installing culvert at A110 and building access ramp at A108-A107; Culvert Install and Rd. Building at A104-A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6462019124-5Skidder 274617 | Corbiere and Sons Contracting6462019124-5Skidder 274617Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 646 | 2019124-5 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 8 | Day |  | 0 |  |  | 960 | 124.8 | 1084.8 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A108 to A111; Grinding of Material at A113; FBs and SKDs all working between A082 and A080; Had to talk between to towers; Brush work all between towers A107 and A110; EXs installing culvert at A110 and building access ramp at A108-A107; Culvert Install and Rd. Building at A104-A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6462019124-5Chainsaw and consummables8960 | Corbiere and Sons Contracting6462019124-5Chainsaw and consummables8960Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 646 | 2019124-5 | 53520102 | Clearing | 0 | Excavator - 50 ton | 189 | 9 | HR | 141.75 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A108 to A111; Grinding of Material at A113; FBs and SKDs all working between A082 and A080; Had to talk between to towers; Brush work all between towers A107 and A110; EXs installing culvert at A110 and building access ramp at A108-A107; Culvert Install and Rd. Building at A104-A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6462019124-5Excavator - 50 ton91701 | Corbiere and Sons Contracting6462019124-5Excavator - 50 ton91701Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1701 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 646 | 2019124-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A108 to A111; Grinding of Material at A113; FBs and SKDs all working between A082 and A080; Had to talk between to towers; Brush work all between towers A107 and A110; EXs installing culvert at A110 and building access ramp at A108-A107; Culvert Install and Rd. Building at A104-A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6462019124-5Light Truck - Pick up10300 | Corbiere and Sons Contracting6462019124-5Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 646 | 2019124-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A108 to A111; Grinding of Material at A113; FBs and SKDs all working between A082 and A080; Had to talk between to towers; Brush work all between towers A107 and A110; EXs installing culvert at A110 and building access ramp at A108-A107; Culvert Install and Rd. Building at A104-A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6462019124-5Light Truck - Pick up401200 | Corbiere and Sons Contracting6462019124-5Light Truck - Pick up401200Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 646 | 2019124-5 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A108 to A111; Grinding of Material at A113; FBs and SKDs all working between A082 and A080; Had to talk between to towers; Brush work all between towers A107 and A110; EXs installing culvert at A110 and building access ramp at A108-A107; Culvert Install and Rd. Building at A104-A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6462019124-5Light Truck - Pick up10300 | Corbiere and Sons Contracting6462019124-5Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 646 | 2019124-5 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A108 to A111; Grinding of Material at A113; FBs and SKDs all working between A082 and A080; Had to talk between to towers; Brush work all between towers A107 and A110; EXs installing culvert at A110 and building access ramp at A108-A107; Culvert Install and Rd. Building at A104-A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6462019124-5Light Truck - Pick up30900 | Corbiere and Sons Contracting6462019124-5Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 646 | 2019124-5 | 53520104 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  |  | 0 | 570 | 74.1 | 644.1 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A108 to A111; Grinding of Material at A113; FBs and SKDs all working between A082 and A080; Had to talk between to towers; Brush work all between towers A107 and A110; EXs installing culvert at A110 and building access ramp at A108-A107; Culvert Install and Rd. Building at A104-A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6462019124-5Foreman6570 | Corbiere and Sons Contracting6462019124-5Foreman6570Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 646 | 2019124-5 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A108 to A111; Grinding of Material at A113; FBs and SKDs all working between A082 and A080; Had to talk between to towers; Brush work all between towers A107 and A110; EXs installing culvert at A110 and building access ramp at A108-A107; Culvert Install and Rd. Building at A104-A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6462019124-5Foreman121140 | Corbiere and Sons Contracting6462019124-5Foreman121140Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 646 | 2019124-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A108 to A111; Grinding of Material at A113; FBs and SKDs all working between A082 and A080; Had to talk between to towers; Brush work all between towers A107 and A110; EXs installing culvert at A110 and building access ramp at A108-A107; Culvert Install and Rd. Building at A104-A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6462019124-5Operator - Principle11990 | Corbiere and Sons Contracting6462019124-5Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 646 | 2019124-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 121 | HR |  |  |  | 0 | 10890 | 1415.7 | 12305.7 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A108 to A111; Grinding of Material at A113; FBs and SKDs all working between A082 and A080; Had to talk between to towers; Brush work all between towers A107 and A110; EXs installing culvert at A110 and building access ramp at A108-A107; Culvert Install and Rd. Building at A104-A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6462019124-5Operator - Principle12110890 | Corbiere and Sons Contracting6462019124-5Operator - Principle12110890Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 646 | 2019124-5 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 36 | HR |  |  |  | 0 | 2700 | 351 | 3051 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A108 to A111; Grinding of Material at A113; FBs and SKDs all working between A082 and A080; Had to talk between to towers; Brush work all between towers A107 and A110; EXs installing culvert at A110 and building access ramp at A108-A107; Culvert Install and Rd. Building at A104-A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6462019124-5Labourer - Specialized362700 | Corbiere and Sons Contracting6462019124-5Labourer - Specialized362700Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 2700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 646 | 2019124-5 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 77 | HR |  |  |  | 0 | 5775 | 750.75 | 6525.75 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A108 to A111; Grinding of Material at A113; FBs and SKDs all working between A082 and A080; Had to talk between to towers; Brush work all between towers A107 and A110; EXs installing culvert at A110 and building access ramp at A108-A107; Culvert Install and Rd. Building at A104-A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6462019124-5Labourer - Specialized775775 | Corbiere and Sons Contracting6462019124-5Labourer - Specialized775775Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 5775 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 646 | 2019124-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A108 to A111; Grinding of Material at A113; FBs and SKDs all working between A082 and A080; Had to talk between to towers; Brush work all between towers A107 and A110; EXs installing culvert at A110 and building access ramp at A108-A107; Culvert Install and Rd. Building at A104-A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6462019124-5L.O.A.102100 | Corbiere and Sons Contracting6462019124-5L.O.A.102100Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 646 | 2019124-5 | 53520104 | Clearing | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A108 to A111; Grinding of Material at A113; FBs and SKDs all working between A082 and A080; Had to talk between to towers; Brush work all between towers A107 and A110; EXs installing culvert at A110 and building access ramp at A108-A107; Culvert Install and Rd. Building at A104-A105; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6462019124-5L.O.A.91890 | Corbiere and Sons Contracting6462019124-5L.O.A.91890Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 647 | 2019124-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling equipment in field across all segments |  |  | Night Shift Fuelling Across all segments | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6472019124-6Light Truck - Pick up20600 | Corbiere and Sons Contracting6472019124-6Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 647 | 2019124-6 | 53520102 | Clearing | 0 | Labourer - General | 65 | 24 | HR |  |  |  | 0 | 1560 | 202.8 | 1762.8 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling equipment in field across all segments |  |  | Night Shift Fuelling Across all segments | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6472019124-6Labourer - General241560 | Corbiere and Sons Contracting6472019124-6Labourer - General241560Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 647 | 2019124-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling equipment in field across all segments |  |  | Night Shift Fuelling Across all segments | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6472019124-6L.O.A.1210 | Corbiere and Sons Contracting6472019124-6L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 648 | 2019124-7 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 |  | HR | 94.5 | 9 |  |  | 850.5 | 110.565 | 961.065 | 2019-12-06 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | No Work for 1 of the Graders; Standby for the day |  |  | Standby | 0 |  |  | 12 | 43843 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6482019124-7Grader - Cat 12 to 14 or equal850.5 | Corbiere and Sons Contracting6482019124-7Grader - Cat 12 to 14 or equal850.5Inv#006R01 | [5 empty] | 1 | 850.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 649 | 2019125-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 0 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6492019125-1Light Truck - Pick up501500 | Corbiere and Sons Contracting6492019125-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 649 | 2019125-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  | 0 | 0 | 1320 | 171.6 | 1491.6 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6492019125-1Project Manager121320 | Corbiere and Sons Contracting6492019125-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 649 | 2019125-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  | 0 | 0 | 1260 | 163.8 | 1423.8 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6492019125-1Superintendent121260 | Corbiere and Sons Contracting6492019125-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 649 | 2019125-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  | 0 | 0 | 960 | 124.8 | 1084.8 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6492019125-1Project Coordinator12960 | Corbiere and Sons Contracting6492019125-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 649 | 2019125-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  | 0 | 0 | 1020 | 132.6 | 1152.6 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6492019125-1Safety Advisor121020 | Corbiere and Sons Contracting6492019125-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 649 | 2019125-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  | 0 | 0 | 840 | 109.2 | 949.2 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6492019125-1Project Controls12840 | Corbiere and Sons Contracting6492019125-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 649 | 2019125-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  | 0 | 0 | 1050 | 136.5 | 1186.5 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6492019125-1L.O.A.51050 | Corbiere and Sons Contracting6492019125-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 643 | 2019125-2-R2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 0 | 0 |  |  | 300 | 39 | 339 |  | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Labourer ran for parts; Sean took care of all other general yard maintenance and organization |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6432019125-2-R2Light Truck - Pick up10300 | Corbiere and Sons Contracting6432019125-2-R2Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 643 | 2019125-2-R2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 |  | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Labourer ran for parts; Sean took care of all other general yard maintenance and organization |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6432019125-2-R2Operator - Apprentice10600 | Corbiere and Sons Contracting6432019125-2-R2Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 643 | 2019125-2-R2 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 |  | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Labourer ran for parts; Sean took care of all other general yard maintenance and organization |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6432019125-2-R2L.O.A.1210 | Corbiere and Sons Contracting6432019125-2-R2L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 643 | 2019125-2-R2 | 53520102 | Clearing | 0 | Warehouse Supervisor | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 |  | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Labourer ran for parts; Sean took care of all other general yard maintenance and organization |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6432019125-2-R2Warehouse Supervisor12900 | Corbiere and Sons Contracting6432019125-2-R2Warehouse Supervisor12900Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 651 | 2019125-3 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX002 built turning pad and brush matted from A042 to A041; Rd. Building with existing material at A041; Culvert installation; Clearing from A041 to A040; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43807 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting6512019125-3Feller Buncher92160 | Corbiere and Sons Contracting6512019125-3Feller Buncher92160Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 651 | 2019125-3 | 53520102 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX002 built turning pad and brush matted from A042 to A041; Rd. Building with existing material at A041; Culvert installation; Clearing from A041 to A040; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43807 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting6512019125-3Skidder 91539 | Corbiere and Sons Contracting6512019125-3Skidder 91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 651 | 2019125-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX002 built turning pad and brush matted from A042 to A041; Rd. Building with existing material at A041; Culvert installation; Clearing from A041 to A040; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43807 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting6512019125-3Light Truck - Pick up20600 | Corbiere and Sons Contracting6512019125-3Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 651 | 2019125-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX002 built turning pad and brush matted from A042 to A041; Rd. Building with existing material at A041; Culvert installation; Clearing from A041 to A040; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43807 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting6512019125-3Operator - Principle11990 | Corbiere and Sons Contracting6512019125-3Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 651 | 2019125-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX002 built turning pad and brush matted from A042 to A041; Rd. Building with existing material at A041; Culvert installation; Clearing from A041 to A040; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43807 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting6512019125-3Operator - Principle11990 | Corbiere and Sons Contracting6512019125-3Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 651 | 2019125-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX002 built turning pad and brush matted from A042 to A041; Rd. Building with existing material at A041; Culvert installation; Clearing from A041 to A040; |  |  | Beck Road West - A036 to A046 | 0 |  |  | 37 | 43807 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting6512019125-3L.O.A.2420 | Corbiere and Sons Contracting6512019125-3L.O.A.2420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 27 | HR | 151.88 | 0 |  |  | 5467.5 | 710.775 | 6178.275 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Brusher275467.5 | Corbiere and Sons Contracting6522019125-4Brusher275467.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5467.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Feller Buncher92160 | Corbiere and Sons Contracting6522019125-4Feller Buncher92160Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 27 | HR | 180 | 0 |  |  | 6480 | 842.4 | 7322.4 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Feller Buncher276480 | Corbiere and Sons Contracting6522019125-4Feller Buncher276480Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 6480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting6522019125-4Grinder - 4710 Peterson or equal95011.2Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting6522019125-4Grinder - 4710 Peterson or equal95011.2Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Log Loader91377 | Corbiere and Sons Contracting6522019125-4Log Loader91377Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Log Loader91377 | Corbiere and Sons Contracting6522019125-4Log Loader91377Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Mulcher91845 | Corbiere and Sons Contracting6522019125-4Mulcher91845Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520101 | Clearing | 0 | Skidder | 171 | 10 | HR | 128.25 | 0 |  |  | 1710 | 222.3 | 1932.3 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Skidder 101710 | Corbiere and Sons Contracting6522019125-4Skidder 101710Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1710 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | Skidder | 171 | 20 | HR | 128.25 | 0 |  |  | 3420 | 444.6 | 3864.6 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Skidder 203420 | Corbiere and Sons Contracting6522019125-4Skidder 203420Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 15 | Day |  | 0 |  |  | 1800 | 234 | 2034 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Chainsaw and consummables151800 | Corbiere and Sons Contracting6522019125-4Chainsaw and consummables151800Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 9 | HR | 97.88 | 0 |  |  | 1174.5 | 152.685 | 1327.185 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Excavator - 20 ton91174.5 | Corbiere and Sons Contracting6522019125-4Excavator - 20 ton91174.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1174.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 2 | HR | 128.25 | 0 |  |  | 342 | 44.46 | 386.46 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Excavator - 36 ton2342 | Corbiere and Sons Contracting6522019125-4Excavator - 36 ton2342Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 342 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 4 | HR | 128.25 | 0 |  |  | 684 | 88.92 | 772.92 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Excavator - 36 ton4684 | Corbiere and Sons Contracting6522019125-4Excavator - 36 ton4684Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 684 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting6522019125-4Grader - Cat 12 to 14 or equal91134Inv#004-R02 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53510111 | Access | 0 | Sander Truck | 112.5 | 10 | HR | 84.38 | 0 |  |  | 1125 | 146.25 | 1271.25 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Sander Truck101125 | Corbiere and Sons Contracting6522019125-4Sander Truck101125Inv#004-R02 | [5 empty] | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Light Truck - Pick up10300 | Corbiere and Sons Contracting6522019125-4Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Light Truck - Pick up10300 | Corbiere and Sons Contracting6522019125-4Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Light Truck - Pick up10300 | Corbiere and Sons Contracting6522019125-4Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Light Truck - Pick up30900 | Corbiere and Sons Contracting6522019125-4Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Light Truck - Pick up10300 | Corbiere and Sons Contracting6522019125-4Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Light Truck - Pick up501500 | Corbiere and Sons Contracting6522019125-4Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 11 | HR | 101.25 | 0 |  |  | 1485 | 193.05 | 1678.05 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Tractor Trailer - 60 Ton111485 | Corbiere and Sons Contracting6522019125-4Tractor Trailer - 60 Ton111485Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1485 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Foreman121140 | Corbiere and Sons Contracting6522019125-4Foreman121140Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Foreman121140 | Corbiere and Sons Contracting6522019125-4Foreman121140Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Operator - Principle11990 | Corbiere and Sons Contracting6522019125-4Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Operator - Principle11990 | Corbiere and Sons Contracting6522019125-4Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 24 | HR |  |  |  | 0 | 2160 | 280.8 | 2440.8 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Operator - Principle242160 | Corbiere and Sons Contracting6522019125-4Operator - Principle242160Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 121 | HR |  |  |  | 0 | 10890 | 1415.7 | 12305.7 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Operator - Principle12110890 | Corbiere and Sons Contracting6522019125-4Operator - Principle12110890Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Operator - Principle11990 | Corbiere and Sons Contracting6522019125-4Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Operator - Principle11990 | Corbiere and Sons Contracting6522019125-4Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Operator - Intermdiate11825 | Corbiere and Sons Contracting6522019125-4Operator - Intermdiate11825Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 66 | HR |  |  |  | 0 | 4950 | 643.5 | 5593.5 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Labourer - Specialized664950 | Corbiere and Sons Contracting6522019125-4Labourer - Specialized664950Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 77 | HR |  |  |  | 0 | 5775 | 750.75 | 6525.75 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Labourer - Specialized775775 | Corbiere and Sons Contracting6522019125-4Labourer - Specialized775775Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 5775 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | Labourer - General | 65 | 5 | HR |  |  |  | 0 | 325 | 42.25 | 367.25 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4Labourer - General5325 | Corbiere and Sons Contracting6522019125-4Labourer - General5325Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 325 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4L.O.A.2420 | Corbiere and Sons Contracting6522019125-4L.O.A.2420Inv#004-R02 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4L.O.A.2420 | Corbiere and Sons Contracting6522019125-4L.O.A.2420Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 12 | DAY |  |  |  | 0 | 2520 | 327.6 | 2847.6 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4L.O.A.122520 | Corbiere and Sons Contracting6522019125-4L.O.A.122520Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2520 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 652 | 2019125-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 15 | DAY |  |  |  | 0 | 3150 | 409.5 | 3559.5 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | EX5 building Rd with gravel trucks from A105-104; EX3 Building from A108 to A107 except for 2 hours of raking; Tim working with dizer at A111-112; Labourers rolling out geo and backing up trucks; Grinding of material at A108 and A112; Handfelling at A107-109; FBs and SKDs cutting in access at A080; MUL at A101; Brushers finishing between A105 and A107; Grader doing road access from A080 to A077; Nick and Alain at pit; Sander Truck along access roads; Float Moves: Fuel Tank, Grinder, Log Loader; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6522019125-4L.O.A.153150 | Corbiere and Sons Contracting6522019125-4L.O.A.153150Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 3150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 653 | 2019125-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers going to equipment across all segments to fuel over night |  |  | Night Shift Fuelling | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6532019125-5Light Truck - Pick up20600 | Corbiere and Sons Contracting6532019125-5Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 653 | 2019125-5 | 53520102 | Clearing | 0 | Labourer - General | 65 | 24 | HR |  |  |  | 0 | 1560 | 202.8 | 1762.8 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers going to equipment across all segments to fuel over night |  |  | Night Shift Fuelling | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6532019125-5Labourer - General241560 | Corbiere and Sons Contracting6532019125-5Labourer - General241560Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 653 | 2019125-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Labourers going to equipment across all segments to fuel over night |  |  | Night Shift Fuelling | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6532019125-5L.O.A.1210 | Corbiere and Sons Contracting6532019125-5L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 654 | 2019125-6 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 |  | HR | 94.5 | 9 |  |  | 850.5 | 110.565 | 961.065 | 2019-12-06 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | 2nd Grader requested by Valard but no work for today. Standby. |  |  | Wind Farm | 0 |  |  | 12 | 43843 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6542019125-6Grader - Cat 12 to 14 or equal850.5 | Corbiere and Sons Contracting6542019125-6Grader - Cat 12 to 14 or equal850.5Inv#006R01 | [5 empty] | 1 | 850.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 656 | 2019126-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 0 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6562019126-1Light Truck - Pick up501500 | Corbiere and Sons Contracting6562019126-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 656 | 2019126-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  | 0 | 0 | 1320 | 171.6 | 1491.6 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6562019126-1Project Manager121320 | Corbiere and Sons Contracting6562019126-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 656 | 2019126-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  | 0 | 0 | 1260 | 163.8 | 1423.8 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6562019126-1Superintendent121260 | Corbiere and Sons Contracting6562019126-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 656 | 2019126-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  | 0 | 0 | 960 | 124.8 | 1084.8 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6562019126-1Project Coordinator12960 | Corbiere and Sons Contracting6562019126-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 656 | 2019126-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  | 0 | 0 | 1020 | 132.6 | 1152.6 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6562019126-1Safety Advisor121020 | Corbiere and Sons Contracting6562019126-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 656 | 2019126-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  | 0 | 0 | 840 | 109.2 | 949.2 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6562019126-1Project Controls12840 | Corbiere and Sons Contracting6562019126-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 656 | 2019126-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  | 0 | 0 | 1050 | 136.5 | 1186.5 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6562019126-1L.O.A.51050 | Corbiere and Sons Contracting6562019126-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 657 | 2019126-2-R2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 0 | 0 |  |  | 300 | 39 | 339 | 2019-12-06 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Sean and Jack looked after all warehouse necessities and activites; |  |  | Yard Maintenance and Equipment Repair | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6572019126-2-R2Light Truck - Pick up10300 | Corbiere and Sons Contracting6572019126-2-R2Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 657 | 2019126-2-R2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  | 0 | 0 | 600 | 78 | 678 | 2019-12-06 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Sean and Jack looked after all warehouse necessities and activites; |  |  | Yard Maintenance and Equipment Repair | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6572019126-2-R2Operator - Apprentice10600 | Corbiere and Sons Contracting6572019126-2-R2Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 657 | 2019126-2-R2 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2019-12-06 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Sean and Jack looked after all warehouse necessities and activites; |  |  | Yard Maintenance and Equipment Repair | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6572019126-2-R2L.O.A.1210 | Corbiere and Sons Contracting6572019126-2-R2L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 657 | 2019126-2-R2 | 53520102 | Clearing | 0 | Warehouse Supervisor | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2019-12-06 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Sean and Jack looked after all warehouse necessities and activites; |  |  | Yard Maintenance and Equipment Repair | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6572019126-2-R2Warehouse Supervisor12900 | Corbiere and Sons Contracting6572019126-2-R2Warehouse Supervisor12900Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 658 | 2019126-3 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Building Access Road to creek crossing at A040; Finish cutting from A040 to A042 |  |  | Beck Road W - A036 to A046 | 0 |  |  | 37 | 43807 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting6582019126-3Feller Buncher92160 | Corbiere and Sons Contracting6582019126-3Feller Buncher92160Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 658 | 2019126-3 | 53520102 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Building Access Road to creek crossing at A040; Finish cutting from A040 to A042 |  |  | Beck Road W - A036 to A046 | 0 |  |  | 37 | 43807 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting6582019126-3Skidder 91539 | Corbiere and Sons Contracting6582019126-3Skidder 91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 658 | 2019126-3 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Building Access Road to creek crossing at A040; Finish cutting from A040 to A042 |  |  | Beck Road W - A036 to A046 | 0 |  |  | 37 | 43807 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting6582019126-3Light Truck - Pick up20600 | Corbiere and Sons Contracting6582019126-3Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 658 | 2019126-3 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Building Access Road to creek crossing at A040; Finish cutting from A040 to A042 |  |  | Beck Road W - A036 to A046 | 0 |  |  | 37 | 43807 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting6582019126-3Operator - Principle221980 | Corbiere and Sons Contracting6582019126-3Operator - Principle221980Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 18 | HR | 151.88 | 0 |  |  | 3645 | 473.85 | 4118.85 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Brusher183645 | Corbiere and Sons Contracting6592019126-4Brusher183645Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3645 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 36 | HR | 180 | 0 |  |  | 8640 | 1123.2 | 9763.2 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Feller Buncher368640 | Corbiere and Sons Contracting6592019126-4Feller Buncher368640Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 8640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting6592019126-4Grinder - 4710 Peterson or equal1810022.4Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Log Loader182754 | Corbiere and Sons Contracting6592019126-4Log Loader182754Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Mulcher91845 | Corbiere and Sons Contracting6592019126-4Mulcher91845Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520102 | Clearing | 0 | Skidder | 171 | 27 | HR | 128.25 | 0 |  |  | 4617 | 600.21 | 5217.21 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Skidder 274617 | Corbiere and Sons Contracting6592019126-4Skidder 274617Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 7 | Day |  | 0 |  |  | 840 | 109.2 | 949.2 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Chainsaw and consummables7840 | Corbiere and Sons Contracting6592019126-4Chainsaw and consummables7840Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 8 | Day |  | 0 |  |  | 960 | 124.8 | 1084.8 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Chainsaw and consummables8960 | Corbiere and Sons Contracting6592019126-4Chainsaw and consummables8960Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 9 | HR | 97.88 | 0 |  |  | 1174.5 | 152.685 | 1327.185 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Excavator - 20 ton91174.5 | Corbiere and Sons Contracting6592019126-4Excavator - 20 ton91174.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1174.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Excavator - 36 ton91539 | Corbiere and Sons Contracting6592019126-4Excavator - 36 ton91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 10 | HR | 74.25 | 0 |  |  | 990 | 128.7 | 1118.7 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Loader JD 524 to 624 or equal10990 | Corbiere and Sons Contracting6592019126-4Loader JD 524 to 624 or equal10990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53510111 | Access | 0 | Sander Truck | 112.5 | 11 | HR | 84.38 | 0 |  |  | 1237.5 | 160.875 | 1398.375 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Sander Truck111237.5 | Corbiere and Sons Contracting6592019126-4Sander Truck111237.5Inv#004-R02 | [5 empty] | 1 | 1237.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Light Truck - Pick up10300 | Corbiere and Sons Contracting6592019126-4Light Truck - Pick up10300Inv#004-R02 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Light Truck - Pick up10300 | Corbiere and Sons Contracting6592019126-4Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 |  |  |  | 300 | 39 | 339 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Light Truck - Pick up10300 | Corbiere and Sons Contracting6592019126-4Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Light Truck - Pick up401200 | Corbiere and Sons Contracting6592019126-4Light Truck - Pick up401200Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Light Truck - Pick up10300 | Corbiere and Sons Contracting6592019126-4Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Light Truck - Pick up20600 | Corbiere and Sons Contracting6592019126-4Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Light Truck - Pick up30900 | Corbiere and Sons Contracting6592019126-4Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520102 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 11 | HR | 101.25 | 0 |  |  | 1485 | 193.05 | 1678.05 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Tractor Trailer - 60 Ton111485 | Corbiere and Sons Contracting6592019126-4Tractor Trailer - 60 Ton111485Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1485 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520102 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  |  | 0 | 380 | 49.4 | 429.4 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Foreman4380 | Corbiere and Sons Contracting6592019126-4Foreman4380Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520104 | Clearing | 0 | Foreman | 95 | 24 | HR |  |  |  | 0 | 2280 | 296.4 | 2576.4 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Foreman242280 | Corbiere and Sons Contracting6592019126-4Foreman242280Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Operator - Principle11990 | Corbiere and Sons Contracting6592019126-4Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 139 | HR |  |  |  | 0 | 12510 | 1626.3 | 14136.3 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Operator - Principle13912510 | Corbiere and Sons Contracting6592019126-4Operator - Principle13912510Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 12510 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Operator - Principle11990 | Corbiere and Sons Contracting6592019126-4Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Operator - Principle11990 | Corbiere and Sons Contracting6592019126-4Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Operator - Intermdiate11825 | Corbiere and Sons Contracting6592019126-4Operator - Intermdiate11825Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520102 | Clearing | 0 | Labourer - Specialized | 75 | 6 | HR |  |  |  | 0 | 450 | 58.5 | 508.5 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Labourer - Specialized6450 | Corbiere and Sons Contracting6592019126-4Labourer - Specialized6450Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 143 | HR |  |  |  | 0 | 10725 | 1394.25 | 12119.25 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Labourer - Specialized14310725 | Corbiere and Sons Contracting6592019126-4Labourer - Specialized14310725Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 10725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520102 | Clearing | 0 | Labourer - General | 65 | 6 | HR |  |  |  | 0 | 390 | 50.7 | 440.7 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4Labourer - General6390 | Corbiere and Sons Contracting6592019126-4Labourer - General6390Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 390 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4L.O.A.1210 | Corbiere and Sons Contracting6592019126-4L.O.A.1210Inv#004-R02 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 15 | DAY |  |  |  | 0 | 3150 | 409.5 | 3559.5 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4L.O.A.153150 | Corbiere and Sons Contracting6592019126-4L.O.A.153150Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 659 | 2019126-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 14 | DAY |  |  |  | 0 | 2940 | 382.2 | 3322.2 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A110 to A105; Grinders working at A112 and A108; FBs and SKDs work at A080 and walk to A076(3KMs); Brushers finishing at A105 W; Move to A102-103; Grader worked on access road from A099 to A071; Road Building at A104 and A107; DZ working from A112' Labourers laying out Geo and prepping installation; EX001 and DZ001 working at KB Pit; Raking at A101 going Westward; |  |  |  | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6592019126-4L.O.A.142940 | Corbiere and Sons Contracting6592019126-4L.O.A.142940Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 2940 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 660 | 2019126-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling of equipment in field |  |  | Night Shift Fuelling | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6602019126-5Light Truck - Pick up20600 | Corbiere and Sons Contracting6602019126-5Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 660 | 2019126-5 | 53520102 | Clearing | 0 | Labourer - General | 65 | 23 | HR |  |  |  | 0 | 1495 | 194.35 | 1689.35 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling of equipment in field |  |  | Night Shift Fuelling | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6602019126-5Labourer - General231495 | Corbiere and Sons Contracting6602019126-5Labourer - General231495Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 660 | 2019126-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-06 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling of equipment in field |  |  | Night Shift Fuelling | 0 |  |  | 36 | 43806 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6602019126-5L.O.A.1210 | Corbiere and Sons Contracting6602019126-5L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 661 | 2019126-6 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 |  | HR | 94.5 | 9 |  |  | 850.5 | 110.565 | 961.065 | 2019-12-06 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | 2nd Grader requested by Valard but no work for today. Standby. |  |  | Standby-Windfarm | 0 |  |  | 12 | 43843 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6612019126-6Grader - Cat 12 to 14 or equal850.5 | Corbiere and Sons Contracting6612019126-6Grader - Cat 12 to 14 or equal850.5Inv#006R01 | [5 empty] | 1 | 850.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 662 | 2019127-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 0 | 0 |  |  | 1500 | 195 | 1695 |  | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6622019127-1Light Truck - Pick up501500 | Corbiere and Sons Contracting6622019127-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 662 | 2019127-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  | 0 | 0 | 1320 | 171.6 | 1491.6 |  | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6622019127-1Project Manager121320 | Corbiere and Sons Contracting6622019127-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 662 | 2019127-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  | 0 | 0 | 1260 | 163.8 | 1423.8 |  | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6622019127-1Superintendent121260 | Corbiere and Sons Contracting6622019127-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 662 | 2019127-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  | 0 | 0 | 960 | 124.8 | 1084.8 |  | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6622019127-1Project Coordinator12960 | Corbiere and Sons Contracting6622019127-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 662 | 2019127-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  | 0 | 0 | 1020 | 132.6 | 1152.6 |  | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6622019127-1Safety Advisor121020 | Corbiere and Sons Contracting6622019127-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 662 | 2019127-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  | 0 | 0 | 840 | 109.2 | 949.2 |  | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6622019127-1Project Controls12840 | Corbiere and Sons Contracting6622019127-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 662 | 2019127-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  | 0 | 0 | 1050 | 136.5 | 1186.5 |  | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6622019127-1L.O.A.51050 | Corbiere and Sons Contracting6622019127-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 664 | 2019127-2-R2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 0 | 0 |  |  | 300 | 39 | 339 | 2019-12-08 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Yard Maintenance, Running for parts |  |  | General Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6642019127-2-R2Light Truck - Pick up10300 | Corbiere and Sons Contracting6642019127-2-R2Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 664 | 2019127-2-R2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  | 0 | 0 | 600 | 78 | 678 | 2019-12-08 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Yard Maintenance, Running for parts |  |  | General Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6642019127-2-R2Operator - Apprentice10600 | Corbiere and Sons Contracting6642019127-2-R2Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 664 | 2019127-2-R2 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2019-12-08 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Yard Maintenance, Running for parts |  |  | General Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6642019127-2-R2L.O.A.1210 | Corbiere and Sons Contracting6642019127-2-R2L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 664 | 2019127-2-R2 | 53520102 | Clearing | 0 | Warehouse Supervisor | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2019-12-08 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Yard Maintenance, Running for parts |  |  | General Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6642019127-2-R2Warehouse Supervisor12900 | Corbiere and Sons Contracting6642019127-2-R2Warehouse Supervisor12900Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 666 | 2019127-4 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 34 | HR | 180 | 0 |  |  | 8160 | 1060.8 | 9220.8 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing continued at A075 |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6662019127-4Feller Buncher348160 | Corbiere and Sons Contracting6662019127-4Feller Buncher348160Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 8160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 666 | 2019127-4 | 53520102 | Clearing | 0 | Skidder | 171 | 27 | HR | 128.25 | 0 |  |  | 4617 | 600.21 | 5217.21 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing continued at A075 |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6662019127-4Skidder 274617 | Corbiere and Sons Contracting6662019127-4Skidder 274617Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 666 | 2019127-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing continued at A075 |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6662019127-4Light Truck - Pick up30900 | Corbiere and Sons Contracting6662019127-4Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 666 | 2019127-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 77 | HR |  |  |  | 0 | 6930 | 900.9 | 7830.9 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing continued at A075 |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6662019127-4Operator - Principle776930 | Corbiere and Sons Contracting6662019127-4Operator - Principle776930Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 6930 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 18 | HR | 151.88 | 0 |  |  | 3645 | 473.85 | 4118.85 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5Brusher183645 | Corbiere and Sons Contracting6672019127-5Brusher183645Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3645 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting6672019127-5Grinder - 4710 Peterson or equal1810022.4Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5Log Loader182754 | Corbiere and Sons Contracting6672019127-5Log Loader182754Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5Mulcher91845 | Corbiere and Sons Contracting6672019127-5Mulcher91845Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 12 | Day |  | 0 |  |  | 1440 | 187.2 | 1627.2 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5Chainsaw and consummables121440 | Corbiere and Sons Contracting6672019127-5Chainsaw and consummables121440Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 2.5 | HR | 97.88 | 0 |  |  | 326.25 | 42.4125 | 368.6625 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5Excavator - 20 ton2.5326.25 | Corbiere and Sons Contracting6672019127-5Excavator - 20 ton2.5326.25Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 326.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5Excavator - 36 ton91539 | Corbiere and Sons Contracting6672019127-5Excavator - 36 ton91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 11 | HR | 94.5 | 0 |  |  | 1386 | 180.18 | 1566.18 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5Grader - Cat 12 to 14 or equal111386 | Corbiere and Sons Contracting6672019127-5Grader - Cat 12 to 14 or equal111386Inv#004-R02 | [5 empty] | 1 | 1386 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 10 | HR | 74.25 | 0 |  |  | 990 | 128.7 | 1118.7 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5Loader JD 524 to 624 or equal10990 | Corbiere and Sons Contracting6672019127-5Loader JD 524 to 624 or equal10990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53510111 | Access | 0 | Sander Truck | 112.5 | 10 | HR | 84.38 | 0 |  |  | 1125 | 146.25 | 1271.25 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5Sander Truck101125 | Corbiere and Sons Contracting6672019127-5Sander Truck101125Inv#004-R02 | [5 empty] | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5Light Truck - Pick up20600 | Corbiere and Sons Contracting6672019127-5Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5Light Truck - Pick up10300 | Corbiere and Sons Contracting6672019127-5Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5Light Truck - Pick up10300 | Corbiere and Sons Contracting6672019127-5Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5Light Truck - Pick up501500 | Corbiere and Sons Contracting6672019127-5Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53520104 | Clearing | 0 | Foreman | 95 | 24 | HR |  |  |  | 0 | 2280 | 296.4 | 2576.4 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5Foreman242280 | Corbiere and Sons Contracting6672019127-5Foreman242280Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5Operator - Principle11990 | Corbiere and Sons Contracting6672019127-5Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5Operator - Principle11990 | Corbiere and Sons Contracting6672019127-5Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 55 | HR |  |  |  | 0 | 4950 | 643.5 | 5593.5 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5Operator - Principle554950 | Corbiere and Sons Contracting6672019127-5Operator - Principle554950Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 3.5 | HR |  |  |  | 0 | 315 | 40.95 | 355.95 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5Operator - Principle3.5315 | Corbiere and Sons Contracting6672019127-5Operator - Principle3.5315Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 315 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5Operator - Principle11990 | Corbiere and Sons Contracting6672019127-5Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 110 | HR |  |  |  | 0 | 8250 | 1072.5 | 9322.5 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5Labourer - Specialized1108250 | Corbiere and Sons Contracting6672019127-5Labourer - Specialized1108250Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 8250 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53520102 | Clearing | 0 | Labourer - General | 65 | 3.5 | HR |  |  |  | 0 | 227.5 | 29.575 | 257.075 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5Labourer - General3.5227.5 | Corbiere and Sons Contracting6672019127-5Labourer - General3.5227.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 227.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5L.O.A.2420 | Corbiere and Sons Contracting6672019127-5L.O.A.2420Inv#004-R02 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 12 | DAY |  |  |  | 0 | 2520 | 327.6 | 2847.6 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5L.O.A.122520 | Corbiere and Sons Contracting6672019127-5L.O.A.122520Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2520 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 667 | 2019127-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling spread out from A110 down to A102; Grinding of material at A112 and A108; Brushing and Mulching at A101 down to A094-A095; Install Culvert at A105 water course; Building Road from A106 to A109; DZ working at A114 with Gravel Trucks; EX and DZ working at Pit; EX006 raking going West from A101; DZ002 moved from Beck Rd, to Pearl Pit; Grader working at Wind farm on Access Roads; Sander Truck accross Beck road and Wind Farm; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6672019127-5L.O.A.81680 | Corbiere and Sons Contracting6672019127-5L.O.A.81680Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 668 | 2019127-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling of equipment overnight at all areas where located; |  |  | Night Shift Fuelling-All Segments | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6682019127-6Light Truck - Pick up20600 | Corbiere and Sons Contracting6682019127-6Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 668 | 2019127-6 | 53520102 | Clearing | 0 | Labourer - General | 65 | 24 | HR |  |  |  | 0 | 1560 | 202.8 | 1762.8 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling of equipment overnight at all areas where located; |  |  | Night Shift Fuelling-All Segments | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6682019127-6Labourer - General241560 | Corbiere and Sons Contracting6682019127-6Labourer - General241560Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 668 | 2019127-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling of equipment overnight at all areas where located; |  |  | Night Shift Fuelling-All Segments | 0 |  |  | 36 | 43807 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6682019127-6L.O.A.1210 | Corbiere and Sons Contracting6682019127-6L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 669 | 2019127-7 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 |  | HR | 94.5 | 9 |  |  | 850.5 | 110.565 | 961.065 | 2019-12-08 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Secondary Grader requested by Valard on SB. |  |  | Wind Farm - A080 to A117 | 0 |  |  | 12 | 43843 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6692019127-7Grader - Cat 12 to 14 or equal850.5 | Corbiere and Sons Contracting6692019127-7Grader - Cat 12 to 14 or equal850.5Inv#006R01 | [5 empty] | 1 | 850.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 670 | 2019128-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6702019128-1Light Truck - Pick up501500 | Corbiere and Sons Contracting6702019128-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 670 | 2019128-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6702019128-1Project Manager121320 | Corbiere and Sons Contracting6702019128-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 670 | 2019128-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6702019128-1Superintendent121260 | Corbiere and Sons Contracting6702019128-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 670 | 2019128-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6702019128-1Project Coordinator12960 | Corbiere and Sons Contracting6702019128-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 670 | 2019128-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6702019128-1Safety Advisor121020 | Corbiere and Sons Contracting6702019128-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 670 | 2019128-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6702019128-1Project Controls12840 | Corbiere and Sons Contracting6702019128-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 670 | 2019128-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6702019128-1L.O.A.51050 | Corbiere and Sons Contracting6702019128-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 671 | 2019128-2-R2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-08 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenance |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6712019128-2-R2Light Truck - Pick up10300 | Corbiere and Sons Contracting6712019128-2-R2Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 671 | 2019128-2-R2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2019-12-08 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenance |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6712019128-2-R2Operator - Apprentice10600 | Corbiere and Sons Contracting6712019128-2-R2Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 671 | 2019128-2-R2 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-08 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenance |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6712019128-2-R2L.O.A.1210 | Corbiere and Sons Contracting6712019128-2-R2L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 671 | 2019128-2-R2 | 53520102 | Clearing | 0 | Warehouse Supervisor | 75 | 0 | HR |  |  | 0 | 0 | 0 | 0 | 0 | 2019-12-08 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenance |  |  |  | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6712019128-2-R2Warehouse Supervisor00 | Corbiere and Sons Contracting6712019128-2-R2Warehouse Supervisor00Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 0 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 672 | 2019128-3 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 30 | HR | 180 | 0 |  |  | 7200 | 936 | 8136 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing cut up to A074-A073; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6722019128-3Feller Buncher307200 | Corbiere and Sons Contracting6722019128-3Feller Buncher307200Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 7200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 672 | 2019128-3 | 53520101 | Clearing | 0 | Skidder | 171 | 21 | HR | 128.25 | 0 |  |  | 3591 | 466.83 | 4057.83 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing cut up to A074-A073; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6722019128-3Skidder 213591 | Corbiere and Sons Contracting6722019128-3Skidder 213591Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3591 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 672 | 2019128-3 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing cut up to A074-A073; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6722019128-3Light Truck - Pick up401200 | Corbiere and Sons Contracting6722019128-3Light Truck - Pick up401200Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 672 | 2019128-3 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 63 | HR |  |  |  | 0 | 5670 | 737.1 | 6407.1 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing cut up to A074-A073; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6722019128-3Operator - Principle635670 | Corbiere and Sons Contracting6722019128-3Operator - Principle635670Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5670 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 672 | 2019128-3 | 53520101 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing cut up to A074-A073; |  |  | Eldorado - A055 to A079 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6722019128-3L.O.A.71470 | Corbiere and Sons Contracting6722019128-3L.O.A.71470Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 27 | HR | 151.88 | 0 |  |  | 5467.5 | 710.775 | 6178.275 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Brusher275467.5 | Corbiere and Sons Contracting6732019128-4Brusher275467.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5467.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 6 | HR | 180 | 0 |  |  | 1440 | 187.2 | 1627.2 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Feller Buncher61440 | Corbiere and Sons Contracting6732019128-4Feller Buncher61440Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting6732019128-4Grinder - 4710 Peterson or equal1810022.4Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Log Loader182754 | Corbiere and Sons Contracting6732019128-4Log Loader182754Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Mulcher91845 | Corbiere and Sons Contracting6732019128-4Mulcher91845Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520102 | Clearing | 0 | Skidder | 171 | 6 | HR | 128.25 | 0 |  |  | 1026 | 133.38 | 1159.38 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Skidder 61026 | Corbiere and Sons Contracting6732019128-4Skidder 61026Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1026 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 8 | Day |  | 0 |  |  | 960 | 124.8 | 1084.8 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Chainsaw and consummables8960 | Corbiere and Sons Contracting6732019128-4Chainsaw and consummables8960Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520102 | Clearing | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Dozer D6 or equal91215 | Corbiere and Sons Contracting6732019128-4Dozer D6 or equal91215Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520102 | Clearing | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Excavator - 30 ton91255.5 | Corbiere and Sons Contracting6732019128-4Excavator - 30 ton91255.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Excavator - 36 ton91539 | Corbiere and Sons Contracting6732019128-4Excavator - 36 ton91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Excavator - 36 ton91539 | Corbiere and Sons Contracting6732019128-4Excavator - 36 ton91539Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520102 | Clearing | 0 | Excavator - 50 ton | 189 | 7 | HR | 141.75 | 0 |  |  | 1323 | 171.99 | 1494.99 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Excavator - 50 ton71323 | Corbiere and Sons Contracting6732019128-4Excavator - 50 ton71323Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1323 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting6732019128-4Grader - Cat 12 to 14 or equal91134Inv#004-R02 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 10 | HR | 74.25 | 0 |  |  | 990 | 128.7 | 1118.7 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Loader JD 524 to 624 or equal10990 | Corbiere and Sons Contracting6732019128-4Loader JD 524 to 624 or equal10990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53510111 | Access | 0 | Sander Truck | 112.5 | 11 | HR | 84.38 | 0 |  |  | 1237.5 | 160.875 | 1398.375 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Sander Truck111237.5 | Corbiere and Sons Contracting6732019128-4Sander Truck111237.5Inv#004-R02 | [5 empty] | 1 | 1237.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Light Truck - Pick up10300 | Corbiere and Sons Contracting6732019128-4Light Truck - Pick up10300Inv#004-R02 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 80 | HR | 22.5 | 0 |  |  | 2400 | 312 | 2712 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Light Truck - Pick up802400 | Corbiere and Sons Contracting6732019128-4Light Truck - Pick up802400Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Light Truck - Pick up401200 | Corbiere and Sons Contracting6732019128-4Light Truck - Pick up401200Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520102 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Tractor Trailer - 60 Ton91215 | Corbiere and Sons Contracting6732019128-4Tractor Trailer - 60 Ton91215Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520104 | Clearing | 0 | Foreman | 95 | 24 | HR |  |  |  | 0 | 2280 | 296.4 | 2576.4 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Foreman242280 | Corbiere and Sons Contracting6732019128-4Foreman242280Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Operator - Principle221980 | Corbiere and Sons Contracting6732019128-4Operator - Principle221980Inv#004-R02 | [5 empty] | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 81 | HR |  |  |  | 0 | 7290 | 947.7 | 8237.7 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Operator - Principle817290 | Corbiere and Sons Contracting6732019128-4Operator - Principle817290Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 7290 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520104 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Operator - Principle221980 | Corbiere and Sons Contracting6732019128-4Operator - Principle221980Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Operator - Intermdiate11825 | Corbiere and Sons Contracting6732019128-4Operator - Intermdiate11825Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 66 | HR |  |  |  | 0 | 4950 | 643.5 | 5593.5 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Labourer - Specialized664950 | Corbiere and Sons Contracting6732019128-4Labourer - Specialized664950Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520102 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4Labourer - General11715 | Corbiere and Sons Contracting6732019128-4Labourer - General11715Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4L.O.A.2420 | Corbiere and Sons Contracting6732019128-4L.O.A.2420Inv#004-R02 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 14 | DAY |  |  |  | 0 | 2940 | 382.2 | 3322.2 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4L.O.A.142940 | Corbiere and Sons Contracting6732019128-4L.O.A.142940Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2940 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 673 | 2019128-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 14 | DAY |  |  |  | 0 | 2940 | 382.2 | 3322.2 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Mike Dumas and Ghislain moved here from Eldorado for 7 Hours; Handfelling at A102-A104; Grinding of Material from A112 to A108; Brushing/Raking/Mulching all at A099 and A094-A095; DZ finished last 30 meters of Rd. at A114, Moved to A108-107; Exs Prepping Rd. and Access from A06 to A110; Labourers cleaning tracks and rolling out GEO; EX006 Raking at A094; EX001 and DZ001 working at Pit; Grader and Sander Truck working all day accross Ouimet Canyon; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 36 | 43809 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6732019128-4L.O.A.142940 | Corbiere and Sons Contracting6732019128-4L.O.A.142940Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 2940 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 674 | 2019128-5 | 53520102 | Clearing | 1 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling of field equipment at night |  |  | All areas in field where equipment is located | 0 |  |  | 36 | 43808 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6742019128-5Light Truck - Pick up20600 | Corbiere and Sons Contracting6742019128-5Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 674 | 2019128-5 | 53520102 | Clearing | 1 | Labourer - General | 65 | 23 | HR |  |  |  | 0 | 1495 | 194.35 | 1689.35 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling of field equipment at night |  |  | All areas in field where equipment is located | 0 |  |  | 36 | 43808 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6742019128-5Labourer - General231495 | Corbiere and Sons Contracting6742019128-5Labourer - General231495Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 674 | 2019128-5 | 53520102 | Clearing | 1 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-08 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling of field equipment at night |  |  | All areas in field where equipment is located | 0 |  |  | 36 | 43808 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6742019128-5L.O.A.1210 | Corbiere and Sons Contracting6742019128-5L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 680 | 2019128-6 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 |  | HR | 94.5 | 9 |  |  | 850.5 | 110.565 | 961.065 | 2019-12-08 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Standby - 2 EX on standby 1 at Pearl pit and 1 on Beck road; 1 grader |  |  | Beck Road West - A036-A046 | 0 |  |  | 12 | 43843 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6802019128-6Grader - Cat 12 to 14 or equal850.5 | Corbiere and Sons Contracting6802019128-6Grader - Cat 12 to 14 or equal850.5Inv#006R01 | [5 empty] | 1 | 850.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 681 | 2019129-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6812019129-1Light Truck - Pick up501500 | Corbiere and Sons Contracting6812019129-1Light Truck - Pick up501500Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 681 | 2019129-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6812019129-1Project Manager121320 | Corbiere and Sons Contracting6812019129-1Project Manager121320Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 681 | 2019129-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6812019129-1Superintendent121260 | Corbiere and Sons Contracting6812019129-1Superintendent121260Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 681 | 2019129-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6812019129-1Project Coordinator12960 | Corbiere and Sons Contracting6812019129-1Project Coordinator12960Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 681 | 2019129-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6812019129-1Safety Advisor121020 | Corbiere and Sons Contracting6812019129-1Safety Advisor121020Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 681 | 2019129-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6812019129-1Project Controls12840 | Corbiere and Sons Contracting6812019129-1Project Controls12840Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 681 | 2019129-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  |  | 0 |  |  | 12 | 43810 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6812019129-1L.O.A.51050 | Corbiere and Sons Contracting6812019129-1L.O.A.51050Inv#004-R02 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 682 | 2019129-2-R2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6822019129-2-R2Light Truck - Pick up10300 | Corbiere and Sons Contracting6822019129-2-R2Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 682 | 2019129-2-R2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2019-12-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6822019129-2-R2Operator - Apprentice10600 | Corbiere and Sons Contracting6822019129-2-R2Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 682 | 2019129-2-R2 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6822019129-2-R2L.O.A.1210 | Corbiere and Sons Contracting6822019129-2-R2L.O.A.1210Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 682 | 2019129-2-R2 | 53520102 | Clearing | 0 | Warehouse Supervisor | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2019-12-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 0 |  |  | 35 | 43845 | [5 empty] | Deena Kruper | 01 | Corbiere and Sons Contracting6822019129-2-R2Warehouse Supervisor12900 | Corbiere and Sons Contracting6822019129-2-R2Warehouse Supervisor12900Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 684 | 2019129-4 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 36 | HR | 180 | 0 |  |  | 8640 | 1123.2 | 9763.2 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished clearing at towers A076, A075 and A071; started walking equipment out. |  |  | Eldorado Road - A055-A079 | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6842019129-4Feller Buncher368640 | Corbiere and Sons Contracting6842019129-4Feller Buncher368640Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 8640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 684 | 2019129-4 | 53520102 | Clearing | 0 | Skidder | 171 | 27 | HR | 128.25 | 0 |  |  | 4617 | 600.21 | 5217.21 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished clearing at towers A076, A075 and A071; started walking equipment out. |  |  | Eldorado Road - A055-A079 | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6842019129-4Skidder 274617 | Corbiere and Sons Contracting6842019129-4Skidder 274617Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 684 | 2019129-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished clearing at towers A076, A075 and A071; started walking equipment out. |  |  | Eldorado Road - A055-A079 | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6842019129-4Light Truck - Pick up401200 | Corbiere and Sons Contracting6842019129-4Light Truck - Pick up401200Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 684 | 2019129-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 77 | HR |  |  |  | 0 | 6930 | 900.9 | 7830.9 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished clearing at towers A076, A075 and A071; started walking equipment out. |  |  | Eldorado Road - A055-A079 | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6842019129-4Operator - Principle776930 | Corbiere and Sons Contracting6842019129-4Operator - Principle776930Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 6930 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 684 | 2019129-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Finished clearing at towers A076, A075 and A071; started walking equipment out. |  |  | Eldorado Road - A055-A079 | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6842019129-4L.O.A.61260 | Corbiere and Sons Contracting6842019129-4L.O.A.61260Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 685 | 2019129-5 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 7 | Day |  | 0 |  |  | 840 | 109.2 | 949.2 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A020 and Archaeoligical site |  |  | Shuniah | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6852019129-5Chainsaw and consummables7840 | Corbiere and Sons Contracting6852019129-5Chainsaw and consummables7840Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 685 | 2019129-5 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A020 and Archaeoligical site |  |  | Shuniah | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6852019129-5Light Truck - Pick up30900 | Corbiere and Sons Contracting6852019129-5Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 685 | 2019129-5 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A020 and Archaeoligical site |  |  | Shuniah | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6852019129-5Foreman121140 | Corbiere and Sons Contracting6852019129-5Foreman121140Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 685 | 2019129-5 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 66 | HR |  |  |  | 0 | 4950 | 643.5 | 5593.5 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A020 and Archaeoligical site |  |  | Shuniah | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6852019129-5Labourer - Specialized664950 | Corbiere and Sons Contracting6852019129-5Labourer - Specialized664950Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 685 | 2019129-5 | 53520104 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A020 and Archaeoligical site |  |  | Shuniah | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6852019129-5L.O.A.71470 | Corbiere and Sons Contracting6852019129-5L.O.A.71470Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Brusher91822.5 | Corbiere and Sons Contracting6882019129-6Brusher91822.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting6882019129-6Grinder - 4710 Peterson or equal1810022.4Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Log Loader182754 | Corbiere and Sons Contracting6882019129-6Log Loader182754Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 7 | Day |  | 0 |  |  | 840 | 109.2 | 949.2 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Chainsaw and consummables7840 | Corbiere and Sons Contracting6882019129-6Chainsaw and consummables7840Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53520102 | Clearing | 0 | Excavator - 20 ton | 130.5 | 9 | HR | 97.88 | 0 |  |  | 1174.5 | 152.685 | 1327.185 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Excavator - 20 ton91174.5 | Corbiere and Sons Contracting6882019129-6Excavator - 20 ton91174.5Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1174.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 5 | HR | 128.25 | 0 |  |  | 855 | 111.15 | 966.15 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Excavator - 36 ton5855 | Corbiere and Sons Contracting6882019129-6Excavator - 36 ton5855Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 855 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53520102 | Clearing | 0 | Excavator - 50 ton | 189 | 2 | HR | 141.75 | 0 |  |  | 378 | 49.14 | 427.14 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Excavator - 50 ton2378 | Corbiere and Sons Contracting6882019129-6Excavator - 50 ton2378Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 378 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting6882019129-6Grader - Cat 12 to 14 or equal91134Inv#004-R02 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 10 | HR | 74.25 | 0 |  |  | 990 | 128.7 | 1118.7 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Loader JD 524 to 624 or equal10990 | Corbiere and Sons Contracting6882019129-6Loader JD 524 to 624 or equal10990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53510111 | Access | 0 | Sander Truck | 112.5 | 11 | HR | 84.38 | 0 |  |  | 1237.5 | 160.875 | 1398.375 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Sander Truck111237.5 | Corbiere and Sons Contracting6882019129-6Sander Truck111237.5Inv#004-R02 | [5 empty] | 1 | 1237.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Light Truck - Pick up20600 | Corbiere and Sons Contracting6882019129-6Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Light Truck - Pick up20600 | Corbiere and Sons Contracting6882019129-6Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Light Truck - Pick up10300 | Corbiere and Sons Contracting6882019129-6Light Truck - Pick up10300Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Light Truck - Pick up30900 | Corbiere and Sons Contracting6882019129-6Light Truck - Pick up30900Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53520102 | Clearing | 0 | Tractor Trailer - 60 Ton | 135 | 11 | HR | 101.25 | 0 |  |  | 1485 | 193.05 | 1678.05 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Tractor Trailer - 60 Ton111485 | Corbiere and Sons Contracting6882019129-6Tractor Trailer - 60 Ton111485Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1485 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53510111 | Access | 0 | Foreman | 95 | 2 | HR |  |  |  | 0 | 190 | 24.7 | 214.7 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Foreman2190 | Corbiere and Sons Contracting6882019129-6Foreman2190Inv#004-R02 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53520102 | Clearing | 0 | Foreman | 95 | 10 | HR |  |  |  | 0 | 950 | 123.5 | 1073.5 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Foreman10950 | Corbiere and Sons Contracting6882019129-6Foreman10950Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Foreman121140 | Corbiere and Sons Contracting6882019129-6Foreman121140Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Operator - Principle11990 | Corbiere and Sons Contracting6882019129-6Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Operator - Principle11990 | Corbiere and Sons Contracting6882019129-6Operator - Principle11990Inv#004-R02 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Operator - Principle443960 | Corbiere and Sons Contracting6882019129-6Operator - Principle443960Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Operator - Principle11990 | Corbiere and Sons Contracting6882019129-6Operator - Principle11990Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 16 | HR |  |  |  | 0 | 1440 | 187.2 | 1627.2 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Operator - Principle161440 | Corbiere and Sons Contracting6882019129-6Operator - Principle161440Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Operator - Intermdiate11825 | Corbiere and Sons Contracting6882019129-6Operator - Intermdiate11825Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 66 | HR |  |  |  | 0 | 4950 | 643.5 | 5593.5 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Labourer - Specialized664950 | Corbiere and Sons Contracting6882019129-6Labourer - Specialized664950Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53520102 | Clearing | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6Labourer - General11715 | Corbiere and Sons Contracting6882019129-6Labourer - General11715Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6L.O.A.2420 | Corbiere and Sons Contracting6882019129-6L.O.A.2420Inv#004-R02 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6L.O.A.102100 | Corbiere and Sons Contracting6882019129-6L.O.A.102100Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 688 | 2019129-6 | 53520104 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling from A102-A104; Grinding of material at A113 and A105; Raking and Brusher from A091-A092 to A094-A095; Gravelling from A109-A110; DZ working with gravel from A105-A106; Rolling out Geo at all gravelling towers; Prepping corderroy; Culvert Installation; Sander access roads accross Ouimet; Grading accross all segments where necessary; John Macvey Orientation; Floated SKD and FB from Beck E to Fish Hatchery |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6882019129-6L.O.A.71470 | Corbiere and Sons Contracting6882019129-6L.O.A.71470Inv#004-R02 |  |  | WF1-Handfalling |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 686 | 2019129-7 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Night shift fuelling of all equipment in the field. |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6862019129-7Light Truck - Pick up20600 | Corbiere and Sons Contracting6862019129-7Light Truck - Pick up20600Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 686 | 2019129-7 | 53520102 | Clearing | 0 | Labourer - General | 65 | 24 | HR |  |  |  | 0 | 1560 | 202.8 | 1762.8 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Night shift fuelling of all equipment in the field. |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6862019129-7Labourer - General241560 | Corbiere and Sons Contracting6862019129-7Labourer - General241560Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 686 | 2019129-7 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2019-12-09 | 1 | Inv#004-R02 | 43820 | 82 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Night shift fuelling of all equipment in the field. |  |  |  | 0 |  |  | 36 | 43810 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting6862019129-7L.O.A.1210 | Corbiere and Sons Contracting6862019129-7L.O.A.1210Inv#004-R02 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 687 | 2019129-8 | 53520102 | Clearing | 0 | Grader - Cat 12 to 14 or equal | 126 | 0 | HR | 94.5 | 9 |  |  | 850.5 | 110.565 | 961.065 | 2019-12-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Standby- 2nd grader on site, no work available |  |  | Wind Farm A079-A117 | 0 |  |  | 12 | 43843 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting6872019129-8Grader - Cat 12 to 14 or equal0850.5 | Corbiere and Sons Contracting6872019129-8Grader - Cat 12 to 14 or equal0850.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 850.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 988 | 2019129-9 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2020-01-08 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing Towers Floated from Towe 42 to BO12 , Graded Dorion Cut off road , open up 3KM. Open to Cavern Lake Road 4KM in. Loading sand truck - stock pile Pearl Pit |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting9882019129-9Feller Buncher92160 | Corbiere and Sons Contracting9882019129-9Feller Buncher92160Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 988 | 2019129-9 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-08 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing Towers Floated from Towe 42 to BO12 , Graded Dorion Cut off road , open up 3KM. Open to Cavern Lake Road 4KM in. Loading sand truck - stock pile Pearl Pit |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting9882019129-9Skidder 91539 | Corbiere and Sons Contracting9882019129-9Skidder 91539Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 988 | 2019129-9 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2020-01-08 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing Towers Floated from Towe 42 to BO12 , Graded Dorion Cut off road , open up 3KM. Open to Cavern Lake Road 4KM in. Loading sand truck - stock pile Pearl Pit |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting9882019129-9Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting9882019129-9Grader - Cat 12 to 14 or equal91134Inv#006R01 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 988 | 2019129-9 | 53510111 | Access | 0 | Sander Truck | 112.5 | 9 | HR | 84.38 | 0 |  |  | 1012.5 | 131.625 | 1144.125 | 2020-01-08 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing Towers Floated from Towe 42 to BO12 , Graded Dorion Cut off road , open up 3KM. Open to Cavern Lake Road 4KM in. Loading sand truck - stock pile Pearl Pit |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting9882019129-9Sander Truck91012.5 | Corbiere and Sons Contracting9882019129-9Sander Truck91012.5Inv#006R01 | [5 empty] | 1 | 1012.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 988 | 2019129-9 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-08 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing Towers Floated from Towe 42 to BO12 , Graded Dorion Cut off road , open up 3KM. Open to Cavern Lake Road 4KM in. Loading sand truck - stock pile Pearl Pit |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting9882019129-9Light Truck - Pick up20600 | Corbiere and Sons Contracting9882019129-9Light Truck - Pick up20600Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 988 | 2019129-9 | 53520101 | Clearing | 0 | Foreman | 95 | 1 | HR |  |  |  | 0 | 95 | 12.35 | 107.35 | 2020-01-08 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing Towers Floated from Towe 42 to BO12 , Graded Dorion Cut off road , open up 3KM. Open to Cavern Lake Road 4KM in. Loading sand truck - stock pile Pearl Pit |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting9882019129-9Foreman195 | Corbiere and Sons Contracting9882019129-9Foreman195Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 988 | 2019129-9 | 53520102 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  |  | 0 | 570 | 74.1 | 644.1 | 2020-01-08 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing Towers Floated from Towe 42 to BO12 , Graded Dorion Cut off road , open up 3KM. Open to Cavern Lake Road 4KM in. Loading sand truck - stock pile Pearl Pit |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting9882019129-9Foreman6570 | Corbiere and Sons Contracting9882019129-9Foreman6570Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 988 | 2019129-9 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 1 | HR |  |  |  | 0 | 90 | 11.7 | 101.7 | 2020-01-08 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing Towers Floated from Towe 42 to BO12 , Graded Dorion Cut off road , open up 3KM. Open to Cavern Lake Road 4KM in. Loading sand truck - stock pile Pearl Pit |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting9882019129-9Operator - Principle190 | Corbiere and Sons Contracting9882019129-9Operator - Principle190Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 90 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 988 | 2019129-9 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 1 | HR |  |  |  | 0 | 90 | 11.7 | 101.7 | 2020-01-08 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing Towers Floated from Towe 42 to BO12 , Graded Dorion Cut off road , open up 3KM. Open to Cavern Lake Road 4KM in. Loading sand truck - stock pile Pearl Pit |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting9882019129-9Operator - Principle190 | Corbiere and Sons Contracting9882019129-9Operator - Principle190Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 90 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 988 | 2019129-9 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-08 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing Towers Floated from Towe 42 to BO12 , Graded Dorion Cut off road , open up 3KM. Open to Cavern Lake Road 4KM in. Loading sand truck - stock pile Pearl Pit |  |  | Fish Hatchery Road - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting9882019129-9L.O.A.2420 | Corbiere and Sons Contracting9882019129-9L.O.A.2420Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1049 | 20200110-1 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 6 | DAY | 182.81 | 0 |  |  | 1462.5 | 190.125 | 1652.625 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting104920200110-1Light Truck - Pick up- After Jan 1061462.5 | Corbiere and Sons Contracting104920200110-1Light Truck - Pick up- After Jan 1061462.5Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1462.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1049 | 20200110-1 | 53510106 | Access | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting104920200110-1Project Manager121320 | Corbiere and Sons Contracting104920200110-1Project Manager121320Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1049 | 20200110-1 | 53510106 | Access | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting104920200110-1Superintendent121260 | Corbiere and Sons Contracting104920200110-1Superintendent121260Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1049 | 20200110-1 | 53510106 | Access | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting104920200110-1Project Coordinator12960 | Corbiere and Sons Contracting104920200110-1Project Coordinator12960Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1049 | 20200110-1 | 53510106 | Access | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting104920200110-1Project Coordinator12960 | Corbiere and Sons Contracting104920200110-1Project Coordinator12960Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1049 | 20200110-1 | 53510106 | Access | 0 | Safety Advisor | 85 | 12 | HR |  |  |  | 0 | 1020 | 132.6 | 1152.6 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting104920200110-1Safety Advisor121020 | Corbiere and Sons Contracting104920200110-1Safety Advisor121020Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1049 | 20200110-1 | 53510106 | Access | 0 | Site Administrator | 50 | 10 | HR |  |  |  | 0 | 500 | 65 | 565 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting104920200110-1Site Administrator10500 | Corbiere and Sons Contracting104920200110-1Site Administrator10500Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1049 | 20200110-1 | 53510106 | Access | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting104920200110-1Project Controls12840 | Corbiere and Sons Contracting104920200110-1Project Controls12840Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1049 | 20200110-1 | 53510106 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting104920200110-1L.O.A.71470 | Corbiere and Sons Contracting104920200110-1L.O.A.71470Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1159 | 20200110-10 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 6 | unit/man/day | 0 | 0 |  |  | 360 | 46.8 | 406.8 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Hand felling from A117-A122 |  |  | Wolf Lake | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting115920200110-10Chainsaw and consumables- After Jan 106360 | Corbiere and Sons Contracting115920200110-10Chainsaw and consumables- After Jan 106360Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1159 | 20200110-10 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Hand felling from A117-A122 |  |  | Wolf Lake | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting115920200110-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting115920200110-10Light Truck - Pick up- After Jan 103731.25Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1159 | 20200110-10 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Hand felling from A117-A122 |  |  | Wolf Lake | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting115920200110-10Foreman121140 | Corbiere and Sons Contracting115920200110-10Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1159 | 20200110-10 | 53520104 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Hand felling from A117-A122 |  |  | Wolf Lake | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting115920200110-10L.O.A.61260 | Corbiere and Sons Contracting115920200110-10L.O.A.61260Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1159 | 20200110-10 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 55 | HR |  |  | 70 | 0 | 3850 | 500.5 | 4350.5 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Hand felling from A117-A122 |  |  | Wolf Lake | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting115920200110-10Labourer - Specialized - After Jan 10553850 | Corbiere and Sons Contracting115920200110-10Labourer - Specialized - After Jan 10553850Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 3850 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1060 | 20200110-12 | 53520102 | Clearing | 0 | Brusher | 202.5 | 18 | HR | 151.88 | 0 |  |  | 3645 | 473.85 | 4118.85 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | 3 FBs and 2 SKDs finished clearing from A134 to B002 and then moved to WF2 to at 3PM; Rest of equipement and Operators continued at Fish Hatchery WF1 |  |  | Fish Hatchery-A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106020200110-12Brusher183645 | Corbiere and Sons Contracting106020200110-12Brusher183645Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3645 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1060 | 20200110-12 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 30 | HR | 180 | 0 |  |  | 7200 | 936 | 8136 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | 3 FBs and 2 SKDs finished clearing from A134 to B002 and then moved to WF2 to at 3PM; Rest of equipement and Operators continued at Fish Hatchery WF1 |  |  | Fish Hatchery-A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106020200110-12Feller Buncher307200 | Corbiere and Sons Contracting106020200110-12Feller Buncher307200Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 7200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1060 | 20200110-12 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | 3 FBs and 2 SKDs finished clearing from A134 to B002 and then moved to WF2 to at 3PM; Rest of equipement and Operators continued at Fish Hatchery WF1 |  |  | Fish Hatchery-A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106020200110-12Mulcher91845 | Corbiere and Sons Contracting106020200110-12Mulcher91845Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1060 | 20200110-12 | 53520102 | Clearing | 0 | Skidder | 171 | 23 | HR | 128.25 | 0 |  |  | 3933 | 511.29 | 4444.29 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | 3 FBs and 2 SKDs finished clearing from A134 to B002 and then moved to WF2 to at 3PM; Rest of equipement and Operators continued at Fish Hatchery WF1 |  |  | Fish Hatchery-A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106020200110-12Skidder 233933 | Corbiere and Sons Contracting106020200110-12Skidder 233933Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3933 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1060 | 20200110-12 | 53520102 | Clearing | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 110.22 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | 3 FBs and 2 SKDs finished clearing from A134 to B002 and then moved to WF2 to at 3PM; Rest of equipement and Operators continued at Fish Hatchery WF1 |  |  | Fish Hatchery-A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106020200110-12Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting106020200110-12Excavator - 36 ton- After Jan 10182645.28Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2645.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1060 | 20200110-12 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | 3 FBs and 2 SKDs finished clearing from A134 to B002 and then moved to WF2 to at 3PM; Rest of equipement and Operators continued at Fish Hatchery WF1 |  |  | Fish Hatchery-A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106020200110-12Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting106020200110-12Light Truck - Pick up- After Jan 1071706.25Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1706.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1060 | 20200110-12 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | 3 FBs and 2 SKDs finished clearing from A134 to B002 and then moved to WF2 to at 3PM; Rest of equipement and Operators continued at Fish Hatchery WF1 |  |  | Fish Hatchery-A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106020200110-12Foreman121140 | Corbiere and Sons Contracting106020200110-12Foreman121140Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1060 | 20200110-12 | 53520102 | Clearing | 0 | L.O.A. | 210 | 11 | DAY |  |  |  | 0 | 2310 | 300.3 | 2610.3 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | 3 FBs and 2 SKDs finished clearing from A134 to B002 and then moved to WF2 to at 3PM; Rest of equipement and Operators continued at Fish Hatchery WF1 |  |  | Fish Hatchery-A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106020200110-12L.O.A.112310 | Corbiere and Sons Contracting106020200110-12L.O.A.112310Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1060 | 20200110-12 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 111 | HR |  |  | 75 | 0 | 8325 | 1082.25 | 9407.25 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | 3 FBs and 2 SKDs finished clearing from A134 to B002 and then moved to WF2 to at 3PM; Rest of equipement and Operators continued at Fish Hatchery WF1 |  |  | Fish Hatchery-A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106020200110-12Operator - Principle - After Jan 101118325 | Corbiere and Sons Contracting106020200110-12Operator - Principle - After Jan 101118325Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 8325 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1061 | 20200110-13 | 53510111 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 110.22 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Access Maintenance from A134 to B001 |  |  | Fish Hatchery-A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106120200110-13Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting106120200110-13Excavator - 36 ton- After Jan 10182645.28Inv#007-R01 | [5 empty] | 1 | 2645.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1061 | 20200110-13 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Access Maintenance from A134 to B001 |  |  | Fish Hatchery-A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106120200110-13L.O.A.2420 | Corbiere and Sons Contracting106120200110-13L.O.A.2420Inv#007-R01 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1061 | 20200110-13 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Access Maintenance from A134 to B001 |  |  | Fish Hatchery-A128 to B017 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106120200110-13Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting106120200110-13Operator - Principle - After Jan 10221650Inv#007-R01 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1050 | 20200110-2 | 53510106 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 74.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105020200110-2Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting105020200110-2Loader JD 524 to 624 or equal5495Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1050 | 20200110-2 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105020200110-2Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting105020200110-2Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1050 | 20200110-2 | 53510106 | Access | 0 | Operator - Apprentice | 60 | 10 | HR |  |  | 60 | 0 | 600 | 78 | 678 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105020200110-2Operator - Apprentice10600 | Corbiere and Sons Contracting105020200110-2Operator - Apprentice10600Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1051 | 20200110-3 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 4 | Approved | Beck Road Gravelling | 9004 | Snow Removal and Gravel Pit hauling and maintenance; Labourers cleaning tracks, gravel detail, escorting, laying GEO; |  |  | Beck Road West-A036-A046 | 1 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105120200110-3L.O.A.1210 | Corbiere and Sons Contracting105120200110-3L.O.A.1210Inv#007-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1051 | 20200110-3 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 4 | Approved | Beck Road Gravelling | 9004 | Snow Removal and Gravel Pit hauling and maintenance; Labourers cleaning tracks, gravel detail, escorting, laying GEO; |  |  | Beck Road West-A036-A046 | 1 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105120200110-3Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting105120200110-3Operator - Principle - After Jan 1010750Inv#007-R01 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1051 | 20200110-3 | 53510111 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 4 | Approved | Beck Road Gravelling | 9004 | Snow Removal and Gravel Pit hauling and maintenance; Labourers cleaning tracks, gravel detail, escorting, laying GEO; |  |  | Beck Road West-A036-A046 | 1 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105120200110-3Labourer - General - After Jan 106360 | Corbiere and Sons Contracting105120200110-3Labourer - General - After Jan 106360Inv#007-R01 | [5 empty] | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1052 | 20200110-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing towards A036; Grinding of material from A046 to A041; Handfelling from A042 down to A038; |  |  | Beck Road West-A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105220200110-4Brusher91822.5 | Corbiere and Sons Contracting105220200110-4Brusher91822.5Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1052 | 20200110-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing towards A036; Grinding of material from A046 to A041; Handfelling from A042 down to A038; |  |  | Beck Road West-A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105220200110-4Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting105220200110-4Grinder - 4710 Peterson or equal95011.2Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1052 | 20200110-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 |  |  |  | 1377 | 179.01 | 1556.01 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing towards A036; Grinding of material from A046 to A041; Handfelling from A042 down to A038; |  |  | Beck Road West-A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105220200110-4Log Loader91377 | Corbiere and Sons Contracting105220200110-4Log Loader91377Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1052 | 20200110-4 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 5 | unit/man/day | 0 | 0 |  |  | 300 | 39 | 339 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing towards A036; Grinding of material from A046 to A041; Handfelling from A042 down to A038; |  |  | Beck Road West-A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105220200110-4Chainsaw and consumables- After Jan 105300 | Corbiere and Sons Contracting105220200110-4Chainsaw and consumables- After Jan 105300Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1052 | 20200110-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing towards A036; Grinding of material from A046 to A041; Handfelling from A042 down to A038; |  |  | Beck Road West-A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105220200110-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting105220200110-4Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1052 | 20200110-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing towards A036; Grinding of material from A046 to A041; Handfelling from A042 down to A038; |  |  | Beck Road West-A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105220200110-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting105220200110-4Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1052 | 20200110-4 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing towards A036; Grinding of material from A046 to A041; Handfelling from A042 down to A038; |  |  | Beck Road West-A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105220200110-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting105220200110-4Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1052 | 20200110-4 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing towards A036; Grinding of material from A046 to A041; Handfelling from A042 down to A038; |  |  | Beck Road West-A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105220200110-4Foreman121140 | Corbiere and Sons Contracting105220200110-4Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1052 | 20200110-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing towards A036; Grinding of material from A046 to A041; Handfelling from A042 down to A038; |  |  | Beck Road West-A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105220200110-4L.O.A.2420 | Corbiere and Sons Contracting105220200110-4L.O.A.2420Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1052 | 20200110-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing towards A036; Grinding of material from A046 to A041; Handfelling from A042 down to A038; |  |  | Beck Road West-A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105220200110-4L.O.A.51050 | Corbiere and Sons Contracting105220200110-4L.O.A.51050Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1052 | 20200110-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing towards A036; Grinding of material from A046 to A041; Handfelling from A042 down to A038; |  |  | Beck Road West-A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105220200110-4Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting105220200110-4Operator - Principle - After Jan 10221650Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1052 | 20200110-4 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 44 | HR |  |  | 70 | 0 | 3080 | 400.4 | 3480.4 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing towards A036; Grinding of material from A046 to A041; Handfelling from A042 down to A038; |  |  | Beck Road West-A036 to A046 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105220200110-4Labourer - Specialized - After Jan 10443080 | Corbiere and Sons Contracting105220200110-4Labourer - Specialized - After Jan 10443080Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 3080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1053 | 20200110-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 1.5 | HR | 151.88 | 0 |  |  | 303.75 | 39.4875 | 343.2375 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A071; Clearing from A062-A063; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105320200110-5Brusher1.5303.75 | Corbiere and Sons Contracting105320200110-5Brusher1.5303.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 303.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1053 | 20200110-5 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A071; Clearing from A062-A063; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105320200110-5Feller Buncher92160 | Corbiere and Sons Contracting105320200110-5Feller Buncher92160Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1053 | 20200110-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A071; Clearing from A062-A063; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105320200110-5Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting105320200110-5Grinder - 4710 Peterson or equal95011.2Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1053 | 20200110-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A071; Clearing from A062-A063; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105320200110-5Log Loader91377 | Corbiere and Sons Contracting105320200110-5Log Loader91377Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1053 | 20200110-5 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A071; Clearing from A062-A063; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105320200110-5Skidder 91539 | Corbiere and Sons Contracting105320200110-5Skidder 91539Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1053 | 20200110-5 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A071; Clearing from A062-A063; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105320200110-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting105320200110-5Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1053 | 20200110-5 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A071; Clearing from A062-A063; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105320200110-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting105320200110-5Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1053 | 20200110-5 | 53520101 | Clearing | 0 | Foreman | 95 | 5 | HR |  |  | 95 | 0 | 475 | 61.75 | 536.75 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A071; Clearing from A062-A063; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105320200110-5Foreman5475 | Corbiere and Sons Contracting105320200110-5Foreman5475Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1053 | 20200110-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A071; Clearing from A062-A063; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105320200110-5L.O.A.3630 | Corbiere and Sons Contracting105320200110-5L.O.A.3630Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1053 | 20200110-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A071; Clearing from A062-A063; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105320200110-5L.O.A.2420 | Corbiere and Sons Contracting105320200110-5L.O.A.2420Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1053 | 20200110-5 | 53520101 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A071; Clearing from A062-A063; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105320200110-5Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting105320200110-5Operator - Principle - After Jan 10221650Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1053 | 20200110-5 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A071; Clearing from A062-A063; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105320200110-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting105320200110-5Operator - Principle - After Jan 1011825Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1053 | 20200110-5 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 2.5 | HR |  |  | 75 | 0 | 187.5 | 24.375 | 211.875 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A071; Clearing from A062-A063; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting105320200110-5Operator - Principle - After Jan 102.5187.5 | Corbiere and Sons Contracting105320200110-5Operator - Principle - After Jan 102.5187.5Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 187.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1054 | 20200110-6 | 53510111 | Access | 0 | Dozer - D5 or equal- After Jan 10 | 80.93 | 9 | Dynamic | 60.7 | 0 |  |  | 728.37 | 94.6881 | 823.0581 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance; Rd. Building and Winter Maintenance from A |  |  | Eldorado-A-055 to A-084 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105420200110-6Dozer - D5 or equal- After Jan 109728.37 | Corbiere and Sons Contracting105420200110-6Dozer - D5 or equal- After Jan 109728.37Inv#007-R01 | [5 empty] | 1 | 728.37 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1054 | 20200110-6 | 53510111 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance; Rd. Building and Winter Maintenance from A |  |  | Eldorado-A-055 to A-084 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105420200110-6Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting105420200110-6Excavator - 36 ton- After Jan 1091322.64Inv#007-R01 | [5 empty] | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1054 | 20200110-6 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance; Rd. Building and Winter Maintenance from A |  |  | Eldorado-A-055 to A-084 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105420200110-6Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting105420200110-6Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#007-R01 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1054 | 20200110-6 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance; Rd. Building and Winter Maintenance from A |  |  | Eldorado-A-055 to A-084 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105420200110-6L.O.A.2420 | Corbiere and Sons Contracting105420200110-6L.O.A.2420Inv#007-R01 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1054 | 20200110-6 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance; Rd. Building and Winter Maintenance from A |  |  | Eldorado-A-055 to A-084 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105420200110-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting105420200110-6Operator - Principle - After Jan 1011825Inv#007-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1054 | 20200110-6 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance; Rd. Building and Winter Maintenance from A |  |  | Eldorado-A-055 to A-084 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105420200110-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting105420200110-6Operator - Principle - After Jan 1011825Inv#007-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1055 | 20200110-7 | 53510111 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance from A080 up to A089; Winter Road Maintenance across access roads; Graders out early after snowfall; |  |  |  | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105520200110-7Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting105520200110-7Dozer D6 or equal- After Jan 1091183.32Inv#007-R01 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1055 | 20200110-7 | 53510111 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance from A080 up to A089; Winter Road Maintenance across access roads; Graders out early after snowfall; |  |  |  | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105520200110-7Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting105520200110-7Dozer D6 or equal- After Jan 1091183.32Inv#007-R01 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1055 | 20200110-7 | 53510111 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance from A080 up to A089; Winter Road Maintenance across access roads; Graders out early after snowfall; |  |  |  | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105520200110-7Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting105520200110-7Excavator - 30 ton- After Jan 1091246.05Inv#007-R01 | [5 empty] | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1055 | 20200110-7 | 53510111 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance from A080 up to A089; Winter Road Maintenance across access roads; Graders out early after snowfall; |  |  |  | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105520200110-7Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting105520200110-7Excavator - 30 ton- After Jan 1091246.05Inv#007-R01 | [5 empty] | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1055 | 20200110-7 | 53510111 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance from A080 up to A089; Winter Road Maintenance across access roads; Graders out early after snowfall; |  |  |  | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105520200110-7Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting105520200110-7Excavator - 36 ton- After Jan 1091322.64Inv#007-R01 | [5 empty] | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1055 | 20200110-7 | 53510111 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance from A080 up to A089; Winter Road Maintenance across access roads; Graders out early after snowfall; |  |  |  | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105520200110-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting105520200110-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#007-R01 | [5 empty] | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1055 | 20200110-7 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 32 | Dynamic | 95.24 | 0 |  |  | 4063.36 | 528.2368 | 4591.5968 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance from A080 up to A089; Winter Road Maintenance across access roads; Graders out early after snowfall; |  |  |  | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105520200110-7Grader - Cat 12 to 14 or equal- After Jan 10324063.36 | Corbiere and Sons Contracting105520200110-7Grader - Cat 12 to 14 or equal- After Jan 10324063.36Inv#007-R01 | [5 empty] | 1 | 4063.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1055 | 20200110-7 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 9 | Dynamic | 64.79 | 0 |  |  | 777.42 | 101.0646 | 878.4846 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance from A080 up to A089; Winter Road Maintenance across access roads; Graders out early after snowfall; |  |  |  | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105520200110-7Sander Truck - Forestry- After Jan 109777.42 | Corbiere and Sons Contracting105520200110-7Sander Truck - Forestry- After Jan 109777.42Inv#007-R01 | [5 empty] | 1 | 777.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1055 | 20200110-7 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance from A080 up to A089; Winter Road Maintenance across access roads; Graders out early after snowfall; |  |  |  | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105520200110-7Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting105520200110-7Light Truck - Pick up- After Jan 103731.25Inv#007-R01 | [5 empty] | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1055 | 20200110-7 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance from A080 up to A089; Winter Road Maintenance across access roads; Graders out early after snowfall; |  |  |  | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105520200110-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting105520200110-7Light Truck - Pick up- After Jan 102487.5Inv#007-R01 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1055 | 20200110-7 | 53510111 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 10 | Dynamic | 91.79 | 0 |  |  | 1223.9 | 159.107 | 1383.007 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance from A080 up to A089; Winter Road Maintenance across access roads; Graders out early after snowfall; |  |  |  | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105520200110-7Tractor Trailer - 60 Ton- After Jan 10101223.9 | Corbiere and Sons Contracting105520200110-7Tractor Trailer - 60 Ton- After Jan 10101223.9Inv#007-R01 | [5 empty] | 1 | 1223.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1055 | 20200110-7 | 53510111 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance from A080 up to A089; Winter Road Maintenance across access roads; Graders out early after snowfall; |  |  |  | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105520200110-7Foreman121140 | Corbiere and Sons Contracting105520200110-7Foreman121140Inv#007-R01 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1055 | 20200110-7 | 53510111 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance from A080 up to A089; Winter Road Maintenance across access roads; Graders out early after snowfall; |  |  |  | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105520200110-7Foreman121140 | Corbiere and Sons Contracting105520200110-7Foreman121140Inv#007-R01 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1055 | 20200110-7 | 53510111 | Access | 0 | L.O.A. | 210 | 15 | DAY |  |  |  | 0 | 3150 | 409.5 | 3559.5 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance from A080 up to A089; Winter Road Maintenance across access roads; Graders out early after snowfall; |  |  |  | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105520200110-7L.O.A.153150 | Corbiere and Sons Contracting105520200110-7L.O.A.153150Inv#007-R01 | [5 empty] | 1 | 3150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1055 | 20200110-7 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance from A080 up to A089; Winter Road Maintenance across access roads; Graders out early after snowfall; |  |  |  | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105520200110-7Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting105520200110-7Operator - Principle - After Jan 10332475Inv#007-R01 | [5 empty] | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1055 | 20200110-7 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance from A080 up to A089; Winter Road Maintenance across access roads; Graders out early after snowfall; |  |  |  | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105520200110-7Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting105520200110-7Operator - Principle - After Jan 10221650Inv#007-R01 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1055 | 20200110-7 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance from A080 up to A089; Winter Road Maintenance across access roads; Graders out early after snowfall; |  |  |  | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105520200110-7Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting105520200110-7Operator - Principle - After Jan 1013975Inv#007-R01 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1055 | 20200110-7 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 32.5 | HR |  |  | 75 | 0 | 2437.5 | 316.875 | 2754.375 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance from A080 up to A089; Winter Road Maintenance across access roads; Graders out early after snowfall; |  |  |  | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105520200110-7Operator - Principle - After Jan 1032.52437.5 | Corbiere and Sons Contracting105520200110-7Operator - Principle - After Jan 1032.52437.5Inv#007-R01 | [5 empty] | 1 | 2437.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1055 | 20200110-7 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance from A080 up to A089; Winter Road Maintenance across access roads; Graders out early after snowfall; |  |  |  | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105520200110-7Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting105520200110-7Operator - Principle - After Jan 103225Inv#007-R01 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1055 | 20200110-7 | 53510111 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance from A080 up to A089; Winter Road Maintenance across access roads; Graders out early after snowfall; |  |  |  | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105520200110-7Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting105520200110-7Operator - Intermdiate - After Jan 1011770Inv#007-R01 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1055 | 20200110-7 | 53510111 | Access | 0 | Labourer - General - After Jan 10 | 60 | 22 | HR |  |  | 60 | 0 | 1320 | 171.6 | 1491.6 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance from A080 up to A089; Winter Road Maintenance across access roads; Graders out early after snowfall; |  |  |  | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105520200110-7Labourer - General - After Jan 10221320 | Corbiere and Sons Contracting105520200110-7Labourer - General - After Jan 10221320Inv#007-R01 | [5 empty] | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1055 | 20200110-7 | 53510111 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Maintenance from A080 up to A089; Winter Road Maintenance across access roads; Graders out early after snowfall; |  |  |  | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105520200110-7Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting105520200110-7Labourer - General - After Jan 1011660Inv#007-R01 | [5 empty] | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1057 | 20200110-9 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A084 and then moving to A098 |  |  | Wind Farm-A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105720200110-9Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting105720200110-9Chainsaw and consumables- After Jan 103180Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1057 | 20200110-9 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A084 and then moving to A098 |  |  | Wind Farm-A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105720200110-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting105720200110-9Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1057 | 20200110-9 | 53520104 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A084 and then moving to A098 |  |  | Wind Farm-A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105720200110-9L.O.A.3630 | Corbiere and Sons Contracting105720200110-9L.O.A.3630Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1057 | 20200110-9 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-01-10 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A084 and then moving to A098 |  |  | Wind Farm-A080 to A117 | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting105720200110-9Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting105720200110-9Labourer - Specialized - After Jan 10332310Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1.0472 | DAY | 182.81 | 0 |  |  | 255.2467 | 33.1821 | 288.4288 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Light Truck - Pick up- After Jan 101.0471661255.2467 | Corbiere and Sons Contracting116820200111-1Light Truck - Pick up- After Jan 101.0471661255.2467Inv#007-R01 | [5 empty] | 1 | 255.2467 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1.5859 | DAY | 182.81 | 0 |  |  | 386.5723 | 50.2544 | 436.8267 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Light Truck - Pick up- After Jan 101.5859375386.5723 | Corbiere and Sons Contracting116820200111-1Light Truck - Pick up- After Jan 101.5859375386.5723Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 386.5723 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1.1989 | DAY | 182.81 | 0 |  |  | 292.2439 | 37.9917 | 330.2356 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Light Truck - Pick up- After Jan 101.1989494292.2439 | Corbiere and Sons Contracting116820200111-1Light Truck - Pick up- After Jan 101.1989494292.2439Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 292.2439 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.65853 | DAY | 182.81 | 0 |  |  | 160.5162 | 20.8671 | 181.3833 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Light Truck - Pick up- After Jan 100.658528160.5162 | Corbiere and Sons Contracting116820200111-1Light Truck - Pick up- After Jan 100.658528160.5162Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 160.5162 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53510111 | Access | 0 | Project Manager | 110 | 2.0943 | HR |  |  | 110 | 0 | 230.3765 | 29.9489 | 260.3254 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Project Manager2.0943322230.3765 | Corbiere and Sons Contracting116820200111-1Project Manager2.0943322230.3765Inv#007-R01 | [5 empty] | 1 | 230.3765 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 3.1719 | HR |  |  | 110 | 0 | 348.9062 | 45.3578 | 394.264 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Project Manager3.171875348.9062 | Corbiere and Sons Contracting116820200111-1Project Manager3.171875348.9062Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 348.9062 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520102 | Clearing | 0 | Project Manager | 110 | 2.3979 | HR |  |  | 110 | 0 | 263.7689 | 34.29 | 298.0589 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Project Manager2.3978987263.7689 | Corbiere and Sons Contracting116820200111-1Project Manager2.3978987263.7689Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 263.7689 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520104 | Clearing | 0 | Project Manager | 110 | 1.3171 | HR |  |  | 110 | 0 | 144.8762 | 18.8339 | 163.7101 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Project Manager1.3170561144.8762 | Corbiere and Sons Contracting116820200111-1Project Manager1.3170561144.8762Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 144.8762 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53510111 | Access | 0 | Superintendent | 105 | 2.0943 | HR |  |  | 105 | 0 | 219.9049 | 28.5876 | 248.4925 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Superintendent2.0943322219.9049 | Corbiere and Sons Contracting116820200111-1Superintendent2.0943322219.9049Inv#007-R01 | [5 empty] | 1 | 219.9049 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 3.1719 | HR |  |  | 105 | 0 | 333.0469 | 43.2961 | 376.343 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Superintendent3.171875333.0469 | Corbiere and Sons Contracting116820200111-1Superintendent3.171875333.0469Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 333.0469 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520102 | Clearing | 0 | Superintendent | 105 | 2.3979 | HR |  |  | 105 | 0 | 251.7794 | 32.7313 | 284.5107 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Superintendent2.3978987251.7794 | Corbiere and Sons Contracting116820200111-1Superintendent2.3978987251.7794Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 251.7794 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520104 | Clearing | 0 | Superintendent | 105 | 1.3171 | HR |  |  | 105 | 0 | 138.2909 | 17.9778 | 156.2687 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Superintendent1.3170561138.2909 | Corbiere and Sons Contracting116820200111-1Superintendent1.3170561138.2909Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 138.2909 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53510111 | Access | 0 | Project Coordinator | 80 | 2.0943 | HR |  |  | 80 | 0 | 167.5466 | 21.7811 | 189.3277 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Project Coordinator2.0943322167.5466 | Corbiere and Sons Contracting116820200111-1Project Coordinator2.0943322167.5466Inv#007-R01 | [5 empty] | 1 | 167.5466 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53510111 | Access | 0 | Project Coordinator | 80 | 2.0943 | HR |  |  | 80 | 0 | 167.5466 | 21.7811 | 189.3277 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Project Coordinator2.0943322167.5466 | Corbiere and Sons Contracting116820200111-1Project Coordinator2.0943322167.5466Inv#007-R01 | [5 empty] | 1 | 167.5466 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 3.1719 | HR |  |  | 80 | 0 | 253.75 | 32.9875 | 286.7375 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Project Coordinator3.171875253.75 | Corbiere and Sons Contracting116820200111-1Project Coordinator3.171875253.75Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 253.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 3.1719 | HR |  |  | 80 | 0 | 253.75 | 32.9875 | 286.7375 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Project Coordinator3.171875253.75 | Corbiere and Sons Contracting116820200111-1Project Coordinator3.171875253.75Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 253.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520102 | Clearing | 0 | Project Coordinator | 80 | 2.3979 | HR |  |  | 80 | 0 | 191.8319 | 24.9381 | 216.77 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Project Coordinator2.3978987191.8319 | Corbiere and Sons Contracting116820200111-1Project Coordinator2.3978987191.8319Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 191.8319 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520102 | Clearing | 0 | Project Coordinator | 80 | 2.3979 | HR |  |  | 80 | 0 | 191.8319 | 24.9381 | 216.77 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Project Coordinator2.3978987191.8319 | Corbiere and Sons Contracting116820200111-1Project Coordinator2.3978987191.8319Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 191.8319 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520104 | Clearing | 0 | Project Coordinator | 80 | 1.3171 | HR |  |  | 80 | 0 | 105.3645 | 13.6974 | 119.0619 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Project Coordinator1.3170561105.3645 | Corbiere and Sons Contracting116820200111-1Project Coordinator1.3170561105.3645Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 105.3645 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520104 | Clearing | 0 | Project Coordinator | 80 | 1.3171 | HR |  |  | 80 | 0 | 105.3645 | 13.6974 | 119.0619 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Project Coordinator1.3170561105.3645 | Corbiere and Sons Contracting116820200111-1Project Coordinator1.3170561105.3645Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 105.3645 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53510111 | Access | 0 | Safety Advisor | 85 | 2.0943 | HR |  |  | 85 | 0 | 178.0182 | 23.1424 | 201.1606 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Safety Advisor2.0943322178.0182 | Corbiere and Sons Contracting116820200111-1Safety Advisor2.0943322178.0182Inv#007-R01 | [5 empty] | 1 | 178.0182 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 3.1719 | HR |  |  | 85 | 0 | 269.6094 | 35.0492 | 304.6586 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Safety Advisor3.171875269.6094 | Corbiere and Sons Contracting116820200111-1Safety Advisor3.171875269.6094Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 269.6094 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520102 | Clearing | 0 | Safety Advisor | 85 | 2.3979 | HR |  |  | 85 | 0 | 203.8214 | 26.4968 | 230.3182 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Safety Advisor2.3978987203.8214 | Corbiere and Sons Contracting116820200111-1Safety Advisor2.3978987203.8214Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 203.8214 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520104 | Clearing | 0 | Safety Advisor | 85 | 1.3171 | HR |  |  | 85 | 0 | 111.9498 | 14.5535 | 126.5033 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Safety Advisor1.3170561111.9498 | Corbiere and Sons Contracting116820200111-1Safety Advisor1.3170561111.9498Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 111.9498 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53510111 | Access | 0 | Site Administrator | 50 | 1.9198 | HR |  |  | 50 | 0 | 95.9902 | 12.4787 | 108.4689 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Site Administrator1.919804595.9902 | Corbiere and Sons Contracting116820200111-1Site Administrator1.919804595.9902Inv#007-R01 | [5 empty] | 1 | 95.9902 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520101 | Clearing | 0 | Site Administrator | 50 | 2.9076 | HR |  |  | 50 | 0 | 145.3776 | 18.8991 | 164.2767 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Site Administrator2.9075521145.3776 | Corbiere and Sons Contracting116820200111-1Site Administrator2.9075521145.3776Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 145.3776 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520102 | Clearing | 0 | Site Administrator | 50 | 2.1981 | HR |  |  | 50 | 0 | 109.9037 | 14.2875 | 124.1912 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Site Administrator2.1980738109.9037 | Corbiere and Sons Contracting116820200111-1Site Administrator2.1980738109.9037Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 109.9037 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520104 | Clearing | 0 | Site Administrator | 50 | 1.2073 | HR |  |  | 50 | 0 | 60.3651 | 7.8475 | 68.2126 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Site Administrator1.207301460.3651 | Corbiere and Sons Contracting116820200111-1Site Administrator1.207301460.3651Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 60.3651 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53510111 | Access | 0 | Project Controls | 70 | 2.0943 | HR |  |  | 70 | 0 | 146.6033 | 19.0584 | 165.6617 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Project Controls2.0943322146.6033 | Corbiere and Sons Contracting116820200111-1Project Controls2.0943322146.6033Inv#007-R01 | [5 empty] | 1 | 146.6033 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 3.1719 | HR |  |  | 70 | 0 | 222.0312 | 28.8641 | 250.8953 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Project Controls3.171875222.0312 | Corbiere and Sons Contracting116820200111-1Project Controls3.171875222.0312Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 222.0312 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520102 | Clearing | 0 | Project Controls | 70 | 2.3979 | HR |  |  | 70 | 0 | 167.8529 | 21.8209 | 189.6738 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Project Controls2.3978987167.8529 | Corbiere and Sons Contracting116820200111-1Project Controls2.3978987167.8529Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 167.8529 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520104 | Clearing | 0 | Project Controls | 70 | 1.3171 | HR |  |  | 70 | 0 | 92.1939 | 11.9852 | 104.1791 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1Project Controls1.317056192.1939 | Corbiere and Sons Contracting116820200111-1Project Controls1.317056192.1939Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 92.1939 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53510111 | Access | 0 | L.O.A. | 210 | 1.2217 | DAY |  |  |  | 0 | 256.5557 | 33.3522 | 289.9079 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1L.O.A.1.2216938256.5557 | Corbiere and Sons Contracting116820200111-1L.O.A.1.2216938256.5557Inv#007-R01 | [5 empty] | 1 | 256.5557 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 1.8503 | DAY |  |  |  | 0 | 388.5547 | 50.5121 | 439.0668 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1L.O.A.1.8502604388.5547 | Corbiere and Sons Contracting116820200111-1L.O.A.1.8502604388.5547Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 388.5547 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1.3988 | DAY |  |  |  | 0 | 293.7426 | 38.1865 | 331.9291 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1L.O.A.1.3987742293.7426 | Corbiere and Sons Contracting116820200111-1L.O.A.1.3987742293.7426Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 293.7426 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1168 | 20200111-1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 0.76828 | DAY |  |  |  | 0 | 161.3394 | 20.9741 | 182.3135 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116820200111-1L.O.A.0.7682827161.3394 | Corbiere and Sons Contracting116820200111-1L.O.A.0.7682827161.3394Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 161.3394 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1177 | 20200111-10 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 6 | unit/man/day | 0 | 0 |  |  | 360 | 46.8 | 406.8 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A118 to A122; |  |  | Wolf Lake | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117720200111-10Chainsaw and consumables- After Jan 106360 | Corbiere and Sons Contracting117720200111-10Chainsaw and consumables- After Jan 106360Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1177 | 20200111-10 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A118 to A122; |  |  | Wolf Lake | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117720200111-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting117720200111-10Light Truck - Pick up- After Jan 103731.25Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1177 | 20200111-10 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A118 to A122; |  |  | Wolf Lake | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117720200111-10Foreman121140 | Corbiere and Sons Contracting117720200111-10Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1177 | 20200111-10 | 53520104 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A118 to A122; |  |  | Wolf Lake | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117720200111-10L.O.A.61260 | Corbiere and Sons Contracting117720200111-10L.O.A.61260Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1177 | 20200111-10 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 55 | HR |  |  | 70 | 0 | 3850 | 500.5 | 4350.5 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A118 to A122; |  |  | Wolf Lake | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117720200111-10Labourer - Specialized - After Jan 10553850 | Corbiere and Sons Contracting117720200111-10Labourer - Specialized - After Jan 10553850Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 3850 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1178 | 20200111-11-R1 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing from B013 to B015 and A131; |  |  | Fish Hatchery | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting117820200111-11-R1Brusher91822.5 | Corbiere and Sons Contracting117820200111-11-R1Brusher91822.5Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1178 | 20200111-11-R1 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 27 | HR | 180 | 0 |  |  | 6480 | 842.4 | 7322.4 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing from B013 to B015 and A131; |  |  | Fish Hatchery | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting117820200111-11-R1Feller Buncher276480 | Corbiere and Sons Contracting117820200111-11-R1Feller Buncher276480Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 6480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1178 | 20200111-11-R1 | 53520101 | Clearing | 0 | Skidder | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing from B013 to B015 and A131; |  |  | Fish Hatchery | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting117820200111-11-R1Skidder 183078 | Corbiere and Sons Contracting117820200111-11-R1Skidder 183078Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1178 | 20200111-11-R1 | 53520102 | Clearing | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing from B013 to B015 and A131; |  |  | Fish Hatchery | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting117820200111-11-R1Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting117820200111-11-R1Excavator - 36 ton- After Jan 1091322.64Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1178 | 20200111-11-R1 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing from B013 to B015 and A131; |  |  | Fish Hatchery | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting117820200111-11-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting117820200111-11-R1Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1178 | 20200111-11-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing from B013 to B015 and A131; |  |  | Fish Hatchery | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting117820200111-11-R1Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting117820200111-11-R1Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1178 | 20200111-11-R1 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing from B013 to B015 and A131; |  |  | Fish Hatchery | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting117820200111-11-R1Foreman121140 | Corbiere and Sons Contracting117820200111-11-R1Foreman121140Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1178 | 20200111-11-R1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing from B013 to B015 and A131; |  |  | Fish Hatchery | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting117820200111-11-R1L.O.A.4840 | Corbiere and Sons Contracting117820200111-11-R1L.O.A.4840Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1178 | 20200111-11-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing from B013 to B015 and A131; |  |  | Fish Hatchery | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting117820200111-11-R1L.O.A.3630 | Corbiere and Sons Contracting117820200111-11-R1L.O.A.3630Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1178 | 20200111-11-R1 | 53520101 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 55 | HR |  |  | 75 | 0 | 4125 | 536.25 | 4661.25 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing from B013 to B015 and A131; |  |  | Fish Hatchery | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting117820200111-11-R1Operator - Principle - After Jan 10554125 | Corbiere and Sons Contracting117820200111-11-R1Operator - Principle - After Jan 10554125Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1178 | 20200111-11-R1 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Clearing from B013 to B015 and A131; |  |  | Fish Hatchery | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting117820200111-11-R1Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting117820200111-11-R1Operator - Principle - After Jan 10221650Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1169 | 20200111-2 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 0.87264 | HR | 74.25 | 0 |  |  | 86.3912 | 11.2309 | 97.6221 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116920200111-2Loader JD 524 to 624 or equal0.872638486.3912 | Corbiere and Sons Contracting116920200111-2Loader JD 524 to 624 or equal0.872638486.3912Inv#007-R01 | [5 empty] | 1 | 86.3912 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1169 | 20200111-2 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 1.3216 | HR | 74.25 | 0 |  |  | 130.8398 | 17.0092 | 147.849 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116920200111-2Loader JD 524 to 624 or equal1.3216146130.8398 | Corbiere and Sons Contracting116920200111-2Loader JD 524 to 624 or equal1.3216146130.8398Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 130.8398 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1169 | 20200111-2 | 53520102 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.99912 | HR | 74.25 | 0 |  |  | 98.9133 | 12.8587 | 111.772 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116920200111-2Loader JD 524 to 624 or equal0.999124598.9133 | Corbiere and Sons Contracting116920200111-2Loader JD 524 to 624 or equal0.999124598.9133Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 98.9133 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1169 | 20200111-2 | 53520104 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.54877 | HR | 74.25 | 0 |  |  | 54.3286 | 7.0627 | 61.3913 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116920200111-2Loader JD 524 to 624 or equal0.548773454.3286 | Corbiere and Sons Contracting116920200111-2Loader JD 524 to 624 or equal0.548773454.3286Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 54.3286 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1169 | 20200111-2 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.17453 | DAY | 182.81 | 0 |  |  | 42.5411 | 5.5303 | 48.0714 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116920200111-2Light Truck - Pick up- After Jan 100.174527742.5411 | Corbiere and Sons Contracting116920200111-2Light Truck - Pick up- After Jan 100.174527742.5411Inv#007-R01 | [5 empty] | 1 | 42.5411 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1169 | 20200111-2 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.26432 | DAY | 182.81 | 0 |  |  | 64.4287 | 8.3757 | 72.8044 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116920200111-2Light Truck - Pick up- After Jan 100.264322964.4287 | Corbiere and Sons Contracting116920200111-2Light Truck - Pick up- After Jan 100.264322964.4287Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 64.4287 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1169 | 20200111-2 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.19982 | DAY | 182.81 | 0 |  |  | 48.7073 | 6.3319 | 55.0392 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116920200111-2Light Truck - Pick up- After Jan 100.199824948.7073 | Corbiere and Sons Contracting116920200111-2Light Truck - Pick up- After Jan 100.199824948.7073Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 48.7073 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1169 | 20200111-2 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.10975 | DAY | 182.81 | 0 |  |  | 26.7527 | 3.4779 | 30.2306 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116920200111-2Light Truck - Pick up- After Jan 100.109754726.7527 | Corbiere and Sons Contracting116920200111-2Light Truck - Pick up- After Jan 100.109754726.7527Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 26.7527 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1169 | 20200111-2 | 53510111 | Access | 0 | Operator - Apprentice | 60 | 1.7453 | HR |  |  | 60 | 0 | 104.7166 | 13.6132 | 118.3298 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116920200111-2Operator - Apprentice1.7452768104.7166 | Corbiere and Sons Contracting116920200111-2Operator - Apprentice1.7452768104.7166Inv#007-R01 | [5 empty] | 1 | 104.7166 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1169 | 20200111-2 | 53520101 | Clearing | 0 | Operator - Apprentice | 60 | 2.6432 | HR |  |  | 60 | 0 | 158.5938 | 20.6172 | 179.211 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116920200111-2Operator - Apprentice2.6432292158.5938 | Corbiere and Sons Contracting116920200111-2Operator - Apprentice2.6432292158.5938Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 158.5938 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1169 | 20200111-2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 1.9982 | HR |  |  | 60 | 0 | 119.8949 | 15.5863 | 135.4812 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116920200111-2Operator - Apprentice1.9982489119.8949 | Corbiere and Sons Contracting116920200111-2Operator - Apprentice1.9982489119.8949Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 119.8949 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1169 | 20200111-2 | 53520104 | Clearing | 0 | Operator - Apprentice | 60 | 1.0975 | HR |  |  | 60 | 0 | 65.8528 | 8.5609 | 74.4137 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | General Yard Maintenance | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting116920200111-2Operator - Apprentice1.097546765.8528 | Corbiere and Sons Contracting116920200111-2Operator - Apprentice1.097546765.8528Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 65.8528 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1171 | 20200111-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working it's way to A036; Grinding of material at A038; Handfelling from A042 to A038; |  |  |  | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117120200111-4Brusher91822.5 | Corbiere and Sons Contracting117120200111-4Brusher91822.5Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1171 | 20200111-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working it's way to A036; Grinding of material at A038; Handfelling from A042 to A038; |  |  |  | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117120200111-4Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting117120200111-4Grinder - 4710 Peterson or equal95011.2Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1171 | 20200111-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working it's way to A036; Grinding of material at A038; Handfelling from A042 to A038; |  |  |  | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117120200111-4Log Loader91377 | Corbiere and Sons Contracting117120200111-4Log Loader91377Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1171 | 20200111-4 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 5 | unit/man/day | 0 | 0 |  |  | 300 | 39 | 339 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working it's way to A036; Grinding of material at A038; Handfelling from A042 to A038; |  |  |  | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117120200111-4Chainsaw and consumables- After Jan 105300 | Corbiere and Sons Contracting117120200111-4Chainsaw and consumables- After Jan 105300Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1171 | 20200111-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working it's way to A036; Grinding of material at A038; Handfelling from A042 to A038; |  |  |  | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117120200111-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting117120200111-4Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1171 | 20200111-4 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working it's way to A036; Grinding of material at A038; Handfelling from A042 to A038; |  |  |  | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117120200111-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting117120200111-4Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1171 | 20200111-4 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working it's way to A036; Grinding of material at A038; Handfelling from A042 to A038; |  |  |  | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117120200111-4Foreman121140 | Corbiere and Sons Contracting117120200111-4Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1171 | 20200111-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working it's way to A036; Grinding of material at A038; Handfelling from A042 to A038; |  |  |  | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117120200111-4L.O.A.2420 | Corbiere and Sons Contracting117120200111-4L.O.A.2420Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1171 | 20200111-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working it's way to A036; Grinding of material at A038; Handfelling from A042 to A038; |  |  |  | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117120200111-4L.O.A.51050 | Corbiere and Sons Contracting117120200111-4L.O.A.51050Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1171 | 20200111-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working it's way to A036; Grinding of material at A038; Handfelling from A042 to A038; |  |  |  | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117120200111-4Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting117120200111-4Operator - Principle - After Jan 10221650Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1171 | 20200111-4 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 44 | HR |  |  | 70 | 0 | 3080 | 400.4 | 3480.4 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher working it's way to A036; Grinding of material at A038; Handfelling from A042 to A038; |  |  |  | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117120200111-4Labourer - Specialized - After Jan 10443080 | Corbiere and Sons Contracting117120200111-4Labourer - Specialized - After Jan 10443080Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 3080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1172 | 20200111-5 | 53520101 | Clearing | 0 | Brusher | 202.5 | 2 | HR | 151.88 | 0 |  |  | 405 | 52.65 | 457.65 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A075; Clearing from A076 to A079, 1 FB, 1 SKD, 1 EX;; Clearing from A060-A061; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117220200111-5Brusher2405 | Corbiere and Sons Contracting117220200111-5Brusher2405Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 405 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1172 | 20200111-5 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A075; Clearing from A076 to A079, 1 FB, 1 SKD, 1 EX;; Clearing from A060-A061; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117220200111-5Feller Buncher92160 | Corbiere and Sons Contracting117220200111-5Feller Buncher92160Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1172 | 20200111-5 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A075; Clearing from A076 to A079, 1 FB, 1 SKD, 1 EX;; Clearing from A060-A061; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117220200111-5Feller Buncher92160 | Corbiere and Sons Contracting117220200111-5Feller Buncher92160Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1172 | 20200111-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 7 | HR | 417.6 | 0 |  |  | 3897.6 | 506.688 | 4404.288 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A075; Clearing from A076 to A079, 1 FB, 1 SKD, 1 EX;; Clearing from A060-A061; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117220200111-5Grinder - 4710 Peterson or equal73897.6 | Corbiere and Sons Contracting117220200111-5Grinder - 4710 Peterson or equal73897.6Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3897.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1172 | 20200111-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 7 | HR | 114.75 | 0 |  |  | 1071 | 139.23 | 1210.23 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A075; Clearing from A076 to A079, 1 FB, 1 SKD, 1 EX;; Clearing from A060-A061; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117220200111-5Log Loader71071 | Corbiere and Sons Contracting117220200111-5Log Loader71071Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1071 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1172 | 20200111-5 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A075; Clearing from A076 to A079, 1 FB, 1 SKD, 1 EX;; Clearing from A060-A061; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117220200111-5Skidder 91539 | Corbiere and Sons Contracting117220200111-5Skidder 91539Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1172 | 20200111-5 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A075; Clearing from A076 to A079, 1 FB, 1 SKD, 1 EX;; Clearing from A060-A061; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117220200111-5Skidder 91539 | Corbiere and Sons Contracting117220200111-5Skidder 91539Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1172 | 20200111-5 | 53520101 | Clearing | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A075; Clearing from A076 to A079, 1 FB, 1 SKD, 1 EX;; Clearing from A060-A061; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117220200111-5Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting117220200111-5Excavator - 30 ton- After Jan 1091246.05Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1172 | 20200111-5 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 6 | DAY | 182.81 | 0 |  |  | 1462.5 | 190.125 | 1652.625 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A075; Clearing from A076 to A079, 1 FB, 1 SKD, 1 EX;; Clearing from A060-A061; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117220200111-5Light Truck - Pick up- After Jan 1061462.5 | Corbiere and Sons Contracting117220200111-5Light Truck - Pick up- After Jan 1061462.5Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1462.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1172 | 20200111-5 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A075; Clearing from A076 to A079, 1 FB, 1 SKD, 1 EX;; Clearing from A060-A061; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117220200111-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting117220200111-5Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1172 | 20200111-5 | 53520101 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A075; Clearing from A076 to A079, 1 FB, 1 SKD, 1 EX;; Clearing from A060-A061; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117220200111-5Foreman6570 | Corbiere and Sons Contracting117220200111-5Foreman6570Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1172 | 20200111-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A075; Clearing from A076 to A079, 1 FB, 1 SKD, 1 EX;; Clearing from A060-A061; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117220200111-5L.O.A.71470 | Corbiere and Sons Contracting117220200111-5L.O.A.71470Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1172 | 20200111-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A075; Clearing from A076 to A079, 1 FB, 1 SKD, 1 EX;; Clearing from A060-A061; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117220200111-5L.O.A.1210 | Corbiere and Sons Contracting117220200111-5L.O.A.1210Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1172 | 20200111-5 | 53520101 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 66 | HR |  |  | 75 | 0 | 4950 | 643.5 | 5593.5 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A075; Clearing from A076 to A079, 1 FB, 1 SKD, 1 EX;; Clearing from A060-A061; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117220200111-5Operator - Principle - After Jan 10664950 | Corbiere and Sons Contracting117220200111-5Operator - Principle - After Jan 10664950Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1172 | 20200111-5 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A075; Clearing from A076 to A079, 1 FB, 1 SKD, 1 EX;; Clearing from A060-A061; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117220200111-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting117220200111-5Operator - Principle - After Jan 1011825Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1173 | 20200111-6 | 53510111 | Access | 0 | Dozer - D5 or equal- After Jan 10 | 80.93 | 9 | Dynamic | 60.7 | 0 |  |  | 728.37 | 94.6881 | 823.0581 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Deena to review. Snow Removal 9013? | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow removal from A071; Rd. Building from A064; |  |  | Eldorado | 1 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117320200111-6Dozer - D5 or equal- After Jan 109728.37 | Corbiere and Sons Contracting117320200111-6Dozer - D5 or equal- After Jan 109728.37Inv#007-R01 | [5 empty] | 1 | 728.37 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1173 | 20200111-6 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 1 | Dynamic | 95.24 | 0 |  |  | 126.98 | 16.5074 | 143.4874 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Deena to review. Snow Removal 9013? | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow removal from A071; Rd. Building from A064; |  |  | Eldorado | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117320200111-6Grader - Cat 12 to 14 or equal- After Jan 101126.98 | Corbiere and Sons Contracting117320200111-6Grader - Cat 12 to 14 or equal- After Jan 101126.98Inv#007-R01 | [5 empty] | 1 | 126.98 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1173 | 20200111-6 | 53520102 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | Deena to review. Snow Removal 9013? | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow removal from A071; Rd. Building from A064; |  |  | Eldorado | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117320200111-6Foreman6570 | Corbiere and Sons Contracting117320200111-6Foreman6570Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1173 | 20200111-6 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Deena to review. Snow Removal 9013? | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow removal from A071; Rd. Building from A064; |  |  | Eldorado | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117320200111-6L.O.A.1210 | Corbiere and Sons Contracting117320200111-6L.O.A.1210Inv#007-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1173 | 20200111-6 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 1 | HR |  |  | 75 | 0 | 75 | 9.75 | 84.75 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Deena to review. Snow Removal 9013? | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow removal from A071; Rd. Building from A064; |  |  | Eldorado | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117320200111-6Operator - Principle - After Jan 10175 | Corbiere and Sons Contracting117320200111-6Operator - Principle - After Jan 10175Inv#007-R01 | [5 empty] | 1 | 75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1173 | 20200111-6 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | Deena to review. Snow Removal 9013? | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow removal from A071; Rd. Building from A064; |  |  | Eldorado | 1 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117320200111-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting117320200111-6Operator - Principle - After Jan 1011825Inv#007-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1174 | 20200111-7 | 53510111 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves; Graders working across all access roads; Labourers flagging, cleaning tracks, escorting; Winter road maintenance from A081 to A087; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117420200111-7Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting117420200111-7Dozer D6 or equal- After Jan 106788.88Inv#007-R01 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1174 | 20200111-7 | 53510111 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves; Graders working across all access roads; Labourers flagging, cleaning tracks, escorting; Winter road maintenance from A081 to A087; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117420200111-7Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting117420200111-7Excavator - 30 ton- After Jan 1091246.05Inv#007-R01 | [5 empty] | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1174 | 20200111-7 | 53510111 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves; Graders working across all access roads; Labourers flagging, cleaning tracks, escorting; Winter road maintenance from A081 to A087; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117420200111-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting117420200111-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#007-R01 | [5 empty] | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1174 | 20200111-7 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 27 | Dynamic | 95.24 | 0 |  |  | 3428.46 | 445.6998 | 3874.1598 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves; Graders working across all access roads; Labourers flagging, cleaning tracks, escorting; Winter road maintenance from A081 to A087; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117420200111-7Grader - Cat 12 to 14 or equal- After Jan 10273428.46 | Corbiere and Sons Contracting117420200111-7Grader - Cat 12 to 14 or equal- After Jan 10273428.46Inv#007-R01 | [5 empty] | 1 | 3428.46 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1174 | 20200111-7 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 10 | Dynamic | 64.79 | 0 |  |  | 863.8 | 112.294 | 976.094 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves; Graders working across all access roads; Labourers flagging, cleaning tracks, escorting; Winter road maintenance from A081 to A087; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117420200111-7Sander Truck - Forestry- After Jan 1010863.8 | Corbiere and Sons Contracting117420200111-7Sander Truck - Forestry- After Jan 1010863.8Inv#007-R01 | [5 empty] | 1 | 863.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1174 | 20200111-7 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves; Graders working across all access roads; Labourers flagging, cleaning tracks, escorting; Winter road maintenance from A081 to A087; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117420200111-7Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting117420200111-7Light Truck - Pick up- After Jan 1051218.75Inv#007-R01 | [5 empty] | 1 | 1218.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1174 | 20200111-7 | 53510111 | Access | 0 | Foreman | 95 | 24 | HR |  |  | 95 | 0 | 2280 | 296.4 | 2576.4 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves; Graders working across all access roads; Labourers flagging, cleaning tracks, escorting; Winter road maintenance from A081 to A087; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117420200111-7Foreman242280 | Corbiere and Sons Contracting117420200111-7Foreman242280Inv#007-R01 | [5 empty] | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1174 | 20200111-7 | 53510111 | Access | 0 | L.O.A. | 210 | 11 | DAY |  |  |  | 0 | 2310 | 300.3 | 2610.3 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves; Graders working across all access roads; Labourers flagging, cleaning tracks, escorting; Winter road maintenance from A081 to A087; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117420200111-7L.O.A.112310 | Corbiere and Sons Contracting117420200111-7L.O.A.112310Inv#007-R01 | [5 empty] | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1174 | 20200111-7 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 77 | HR |  |  | 75 | 0 | 5775 | 750.75 | 6525.75 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves; Graders working across all access roads; Labourers flagging, cleaning tracks, escorting; Winter road maintenance from A081 to A087; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117420200111-7Operator - Principle - After Jan 10775775 | Corbiere and Sons Contracting117420200111-7Operator - Principle - After Jan 10775775Inv#007-R01 | [5 empty] | 1 | 5775 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1174 | 20200111-7 | 53510111 | Access | 0 | Labourer - General - After Jan 10 | 60 | 22 | HR |  |  | 60 | 0 | 1320 | 171.6 | 1491.6 | 2020-01-11 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Float Moves; Graders working across all access roads; Labourers flagging, cleaning tracks, escorting; Winter road maintenance from A081 to A087; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting117420200111-7Labourer - General - After Jan 10221320 | Corbiere and Sons Contracting117420200111-7Labourer - General - After Jan 10221320Inv#007-R01 | [5 empty] | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1082 | 20200112-1 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 6 | DAY | 0 | 0 |  |  | 1462.5 | 190.125 | 1652.625 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108220200112-1Light Truck - Pick up- After Jan 1061462.5 | Corbiere and Sons Contracting108220200112-1Light Truck - Pick up- After Jan 1061462.5Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1462.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1082 | 20200112-1 | 53510106 | Access | 0 | Project Manager | 110 | 12 | HR |  |  | 0 | 0 | 1320 | 171.6 | 1491.6 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108220200112-1Project Manager121320 | Corbiere and Sons Contracting108220200112-1Project Manager121320Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1082 | 20200112-1 | 53510106 | Access | 0 | Superintendent | 105 | 12 | HR |  |  | 0 | 0 | 1260 | 163.8 | 1423.8 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108220200112-1Superintendent121260 | Corbiere and Sons Contracting108220200112-1Superintendent121260Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1082 | 20200112-1 | 53510106 | Access | 0 | Project Coordinator | 80 | 12 | HR |  |  | 0 | 0 | 960 | 124.8 | 1084.8 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108220200112-1Project Coordinator12960 | Corbiere and Sons Contracting108220200112-1Project Coordinator12960Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1082 | 20200112-1 | 53510106 | Access | 0 | Project Coordinator | 80 | 12 | HR |  |  | 0 | 0 | 960 | 124.8 | 1084.8 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108220200112-1Project Coordinator12960 | Corbiere and Sons Contracting108220200112-1Project Coordinator12960Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1082 | 20200112-1 | 53510106 | Access | 0 | Safety Advisor | 85 | 12 | HR |  |  | 0 | 0 | 1020 | 132.6 | 1152.6 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108220200112-1Safety Advisor121020 | Corbiere and Sons Contracting108220200112-1Safety Advisor121020Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1082 | 20200112-1 | 53510106 | Access | 0 | Site Administrator | 50 | 0 | HR |  |  | 0 | 0 | 0 | 0 | 0 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108220200112-1Site Administrator00 | Corbiere and Sons Contracting108220200112-1Site Administrator00Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 0 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1082 | 20200112-1 | 53510106 | Access | 0 | Project Controls | 70 | 12 | HR |  |  | 0 | 0 | 840 | 109.2 | 949.2 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108220200112-1Project Controls12840 | Corbiere and Sons Contracting108220200112-1Project Controls12840Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1082 | 20200112-1 | 53510106 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  | 0 | 0 | 1470 | 191.1 | 1661.1 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108220200112-1L.O.A.71470 | Corbiere and Sons Contracting108220200112-1L.O.A.71470Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1091 | 20200112-10 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 5 | unit/man/day | 0 | 0 |  |  | 300 | 39 | 339 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A118 to 122; |  |  | Wolf Lake Road-A118-A127 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109120200112-10Chainsaw and consumables- After Jan 105300 | Corbiere and Sons Contracting109120200112-10Chainsaw and consumables- After Jan 105300Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1091 | 20200112-10 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A118 to 122; |  |  | Wolf Lake Road-A118-A127 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109120200112-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting109120200112-10Light Truck - Pick up- After Jan 103731.25Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1091 | 20200112-10 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A118 to 122; |  |  | Wolf Lake Road-A118-A127 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109120200112-10Foreman121140 | Corbiere and Sons Contracting109120200112-10Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1091 | 20200112-10 | 53520104 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A118 to 122; |  |  | Wolf Lake Road-A118-A127 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109120200112-10L.O.A.51050 | Corbiere and Sons Contracting109120200112-10L.O.A.51050Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1091 | 20200112-10 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 44 | HR |  |  | 70 | 0 | 3080 | 400.4 | 3480.4 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A118 to 122; |  |  | Wolf Lake Road-A118-A127 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109120200112-10Labourer - Specialized - After Jan 10443080 | Corbiere and Sons Contracting109120200112-10Labourer - Specialized - After Jan 10443080Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 3080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1092 | 20200112-11 | 53520102 | Clearing | 0 | Brusher | 202.5 | 7 | HR | 151.88 | 0 |  |  | 1417.5 | 184.275 | 1601.775 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing and Mulching from A129 to A132 |  |  | Fish Hatchery-A128 to B017 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting109220200112-11Brusher71417.5 | Corbiere and Sons Contracting109220200112-11Brusher71417.5Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1417.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1092 | 20200112-11 | 53520102 | Clearing | 0 | Mulcher | 205 | 9 | HR | 153.75 | 0 |  |  | 1845 | 239.85 | 2084.85 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing and Mulching from A129 to A132 |  |  | Fish Hatchery-A128 to B017 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting109220200112-11Mulcher91845 | Corbiere and Sons Contracting109220200112-11Mulcher91845Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1092 | 20200112-11 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing and Mulching from A129 to A132 |  |  | Fish Hatchery-A128 to B017 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting109220200112-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting109220200112-11Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1092 | 20200112-11 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing and Mulching from A129 to A132 |  |  | Fish Hatchery-A128 to B017 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting109220200112-11Foreman121140 | Corbiere and Sons Contracting109220200112-11Foreman121140Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1092 | 20200112-11 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing and Mulching from A129 to A132 |  |  | Fish Hatchery-A128 to B017 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting109220200112-11L.O.A.4840 | Corbiere and Sons Contracting109220200112-11L.O.A.4840Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1092 | 20200112-11 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing and Mulching from A129 to A132 |  |  | Fish Hatchery-A128 to B017 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting109220200112-11Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting109220200112-11Operator - Principle - After Jan 10221650Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1092 | 20200112-11 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing and Mulching from A129 to A132 |  |  | Fish Hatchery-A128 to B017 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting109220200112-11Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting109220200112-11Labourer - General - After Jan 1011660Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1151 | 20200112-16 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Begin Clearing in Santoy Lake Road; Mobilization of crew members and equipment; |  |  | Santoy Lake | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting115120200112-16Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting115120200112-16Dozer D6 or equal- After Jan 107920.36Inv#007-R01 | [5 empty] | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1151 | 20200112-16 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Begin Clearing in Santoy Lake Road; Mobilization of crew members and equipment; |  |  | Santoy Lake | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting115120200112-16Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting115120200112-16Light Truck - Pick up- After Jan 102487.5Inv#007-R01 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1151 | 20200112-16 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Begin Clearing in Santoy Lake Road; Mobilization of crew members and equipment; |  |  | Santoy Lake | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting115120200112-16L.O.A.3630 | Corbiere and Sons Contracting115120200112-16L.O.A.3630Inv#007-R01 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1151 | 20200112-16 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Begin Clearing in Santoy Lake Road; Mobilization of crew members and equipment; |  |  | Santoy Lake | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting115120200112-16Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting115120200112-16Operator - Principle - After Jan 107525Inv#007-R01 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1151 | 20200112-16 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Begin Clearing in Santoy Lake Road; Mobilization of crew members and equipment; |  |  | Santoy Lake | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting115120200112-16Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting115120200112-16Operator - Principle - After Jan 1011825Inv#007-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1083 | 20200112-2 | 53510106 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 0 | 0 |  |  | 495 | 64.35 | 559.35 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108320200112-2Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting108320200112-2Loader JD 524 to 624 or equal5495Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1083 | 20200112-2 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108320200112-2Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting108320200112-2Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1083 | 20200112-2 | 53510106 | Access | 0 | Operator - Apprentice | 60 | 10 | HR |  |  | 0 | 0 | 600 | 78 | 678 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Terrance Bob | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108320200112-2Operator - Apprentice10600 | Corbiere and Sons Contracting108320200112-2Operator - Apprentice10600Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1084 | 20200112-3 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2020-02-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Operators all went to site waiting on equipment to be moved; Floats didn't make it; Labour time paid; No equipment time; Labourer cleaned tracks, moved signage; |  |  | Beck Road W-A036-A046 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108420200112-3L.O.A.2420 | Corbiere and Sons Contracting108420200112-3L.O.A.2420Inv#007-R01 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1084 | 20200112-3 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2020-02-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Operators all went to site waiting on equipment to be moved; Floats didn't make it; Labour time paid; No equipment time; Labourer cleaned tracks, moved signage; |  |  | Beck Road W-A036-A046 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108420200112-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting108420200112-3Operator - Principle - After Jan 1011825Inv#007-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1085 | 20200112-4 | 53520104 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Operators all went to site waiting on equipment to be moved; Floats didn't make it; Labour time paid; No equipment time; Labourer cleaned tracks, moved signage; Handfelling from A036 to A037; Grinding of Material at A036; |  |  | Beck Road W-A036 to A046 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108520200112-4Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting108520200112-4Grinder - 4710 Peterson or equal95011.2Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1085 | 20200112-4 | 53520104 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Operators all went to site waiting on equipment to be moved; Floats didn't make it; Labour time paid; No equipment time; Labourer cleaned tracks, moved signage; Handfelling from A036 to A037; Grinding of Material at A036; |  |  | Beck Road W-A036 to A046 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108520200112-4Log Loader91377 | Corbiere and Sons Contracting108520200112-4Log Loader91377Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1085 | 20200112-4 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 4 | unit/man/day | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Operators all went to site waiting on equipment to be moved; Floats didn't make it; Labour time paid; No equipment time; Labourer cleaned tracks, moved signage; Handfelling from A036 to A037; Grinding of Material at A036; |  |  | Beck Road W-A036 to A046 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108520200112-4Chainsaw and consumables- After Jan 104240 | Corbiere and Sons Contracting108520200112-4Chainsaw and consumables- After Jan 104240Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1085 | 20200112-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Operators all went to site waiting on equipment to be moved; Floats didn't make it; Labour time paid; No equipment time; Labourer cleaned tracks, moved signage; Handfelling from A036 to A037; Grinding of Material at A036; |  |  | Beck Road W-A036 to A046 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108520200112-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting108520200112-4Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1085 | 20200112-4 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Operators all went to site waiting on equipment to be moved; Floats didn't make it; Labour time paid; No equipment time; Labourer cleaned tracks, moved signage; Handfelling from A036 to A037; Grinding of Material at A036; |  |  | Beck Road W-A036 to A046 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108520200112-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting108520200112-4Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1085 | 20200112-4 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Operators all went to site waiting on equipment to be moved; Floats didn't make it; Labour time paid; No equipment time; Labourer cleaned tracks, moved signage; Handfelling from A036 to A037; Grinding of Material at A036; |  |  | Beck Road W-A036 to A046 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108520200112-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting108520200112-4Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1085 | 20200112-4 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Operators all went to site waiting on equipment to be moved; Floats didn't make it; Labour time paid; No equipment time; Labourer cleaned tracks, moved signage; Handfelling from A036 to A037; Grinding of Material at A036; |  |  | Beck Road W-A036 to A046 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108520200112-4Foreman121140 | Corbiere and Sons Contracting108520200112-4Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1085 | 20200112-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Operators all went to site waiting on equipment to be moved; Floats didn't make it; Labour time paid; No equipment time; Labourer cleaned tracks, moved signage; Handfelling from A036 to A037; Grinding of Material at A036; |  |  | Beck Road W-A036 to A046 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108520200112-4L.O.A.61260 | Corbiere and Sons Contracting108520200112-4L.O.A.61260Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1085 | 20200112-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Operators all went to site waiting on equipment to be moved; Floats didn't make it; Labour time paid; No equipment time; Labourer cleaned tracks, moved signage; Handfelling from A036 to A037; Grinding of Material at A036; |  |  | Beck Road W-A036 to A046 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108520200112-4L.O.A.51050 | Corbiere and Sons Contracting108520200112-4L.O.A.51050Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1085 | 20200112-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Operators all went to site waiting on equipment to be moved; Floats didn't make it; Labour time paid; No equipment time; Labourer cleaned tracks, moved signage; Handfelling from A036 to A037; Grinding of Material at A036; |  |  | Beck Road W-A036 to A046 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108520200112-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting108520200112-4Operator - Principle - After Jan 1011825Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1085 | 20200112-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Operators all went to site waiting on equipment to be moved; Floats didn't make it; Labour time paid; No equipment time; Labourer cleaned tracks, moved signage; Handfelling from A036 to A037; Grinding of Material at A036; |  |  | Beck Road W-A036 to A046 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108520200112-4Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting108520200112-4Operator - Principle - After Jan 10332475Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1085 | 20200112-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Operators all went to site waiting on equipment to be moved; Floats didn't make it; Labour time paid; No equipment time; Labourer cleaned tracks, moved signage; Handfelling from A036 to A037; Grinding of Material at A036; |  |  | Beck Road W-A036 to A046 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108520200112-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting108520200112-4Operator - Principle - After Jan 1011825Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1085 | 20200112-4 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 44 | HR |  |  | 70 | 0 | 3080 | 400.4 | 3480.4 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Operators all went to site waiting on equipment to be moved; Floats didn't make it; Labour time paid; No equipment time; Labourer cleaned tracks, moved signage; Handfelling from A036 to A037; Grinding of Material at A036; |  |  | Beck Road W-A036 to A046 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108520200112-4Labourer - Specialized - After Jan 10443080 | Corbiere and Sons Contracting108520200112-4Labourer - Specialized - After Jan 10443080Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 3080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1085 | 20200112-4 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 6.5 | HR |  |  | 60 | 0 | 390 | 50.7 | 440.7 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Operators all went to site waiting on equipment to be moved; Floats didn't make it; Labour time paid; No equipment time; Labourer cleaned tracks, moved signage; Handfelling from A036 to A037; Grinding of Material at A036; |  |  | Beck Road W-A036 to A046 | 0 |  |  | 36 | 43851 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting108520200112-4Labourer - General - After Jan 106.5390 | Corbiere and Sons Contracting108520200112-4Labourer - General - After Jan 106.5390Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 390 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1086 | 20200112-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 0 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A071; Brushing from A076, skidder walking out to be float moved; |  |  | Eldorado-A055 to A079 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting108620200112-5Brusher91822.5 | Corbiere and Sons Contracting108620200112-5Brusher91822.5Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1086 | 20200112-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 5 | HR | 0 | 0 |  |  | 2784 | 361.92 | 3145.92 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A071; Brushing from A076, skidder walking out to be float moved; |  |  | Eldorado-A055 to A079 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting108620200112-5Grinder - 4710 Peterson or equal52784 | Corbiere and Sons Contracting108620200112-5Grinder - 4710 Peterson or equal52784Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2784 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1086 | 20200112-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 5 | HR | 0 | 0 |  |  | 765 | 99.45 | 864.45 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A071; Brushing from A076, skidder walking out to be float moved; |  |  | Eldorado-A055 to A079 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting108620200112-5Log Loader5765 | Corbiere and Sons Contracting108620200112-5Log Loader5765Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 765 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1086 | 20200112-5 | 53520102 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A071; Brushing from A076, skidder walking out to be float moved; |  |  | Eldorado-A055 to A079 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting108620200112-5Skidder 91539 | Corbiere and Sons Contracting108620200112-5Skidder 91539Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1086 | 20200112-5 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 0 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A071; Brushing from A076, skidder walking out to be float moved; |  |  | Eldorado-A055 to A079 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting108620200112-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting108620200112-5Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1086 | 20200112-5 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A071; Brushing from A076, skidder walking out to be float moved; |  |  | Eldorado-A055 to A079 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting108620200112-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting108620200112-5Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1086 | 20200112-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  | 0 | 0 | 630 | 81.9 | 711.9 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A071; Brushing from A076, skidder walking out to be float moved; |  |  | Eldorado-A055 to A079 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting108620200112-5L.O.A.3630 | Corbiere and Sons Contracting108620200112-5L.O.A.3630Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1086 | 20200112-5 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 0 | 0 | 2475 | 321.75 | 2796.75 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A071; Brushing from A076, skidder walking out to be float moved; |  |  | Eldorado-A055 to A079 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting108620200112-5Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting108620200112-5Operator - Principle - After Jan 10332475Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1088 | 20200112-7 | 53510111 | Access | 0 | Dozer - D5 or equal- After Jan 10 | 80.93 | 9 | Dynamic | 60.7 | 0 |  |  | 728.37 | 94.6881 | 823.0581 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grading and Sanding across all access roads; float moves; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting108820200112-7Dozer - D5 or equal- After Jan 109728.37 | Corbiere and Sons Contracting108820200112-7Dozer - D5 or equal- After Jan 109728.37Inv#007-R01 | [5 empty] | 1 | 728.37 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1088 | 20200112-7 | 53510111 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grading and Sanding across all access roads; float moves; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting108820200112-7Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting108820200112-7Excavator - 30 ton- After Jan 1091246.05Inv#007-R01 | [5 empty] | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1088 | 20200112-7 | 53510111 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grading and Sanding across all access roads; float moves; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting108820200112-7Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting108820200112-7Excavator - 36 ton- After Jan 1091322.64Inv#007-R01 | [5 empty] | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1088 | 20200112-7 | 53510111 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grading and Sanding across all access roads; float moves; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting108820200112-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting108820200112-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#007-R01 | [5 empty] | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1088 | 20200112-7 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 27 | Dynamic | 95.24 | 0 |  |  | 3428.46 | 445.6998 | 3874.1598 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grading and Sanding across all access roads; float moves; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting108820200112-7Grader - Cat 12 to 14 or equal- After Jan 10273428.46 | Corbiere and Sons Contracting108820200112-7Grader - Cat 12 to 14 or equal- After Jan 10273428.46Inv#007-R01 | [5 empty] | 1 | 3428.46 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1088 | 20200112-7 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 10 | Dynamic | 64.79 | 0 |  |  | 863.8 | 112.294 | 976.094 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grading and Sanding across all access roads; float moves; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting108820200112-7Sander Truck - Forestry- After Jan 1010863.8 | Corbiere and Sons Contracting108820200112-7Sander Truck - Forestry- After Jan 1010863.8Inv#007-R01 | [5 empty] | 1 | 863.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1088 | 20200112-7 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grading and Sanding across all access roads; float moves; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting108820200112-7Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting108820200112-7Light Truck - Pick up- After Jan 104975Inv#007-R01 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1088 | 20200112-7 | 53510111 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 10 | Dynamic | 91.79 | 0 |  |  | 1223.9 | 159.107 | 1383.007 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grading and Sanding across all access roads; float moves; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting108820200112-7Tractor Trailer - 60 Ton- After Jan 10101223.9 | Corbiere and Sons Contracting108820200112-7Tractor Trailer - 60 Ton- After Jan 10101223.9Inv#007-R01 | [5 empty] | 1 | 1223.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1088 | 20200112-7 | 53510111 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grading and Sanding across all access roads; float moves; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting108820200112-7Foreman121140 | Corbiere and Sons Contracting108820200112-7Foreman121140Inv#007-R01 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1088 | 20200112-7 | 53510111 | Access | 0 | L.O.A. | 210 | 11 | DAY |  |  |  | 0 | 2310 | 300.3 | 2610.3 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grading and Sanding across all access roads; float moves; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting108820200112-7L.O.A.112310 | Corbiere and Sons Contracting108820200112-7L.O.A.112310Inv#007-R01 | [5 empty] | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1088 | 20200112-7 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 88 | HR |  |  | 75 | 0 | 6600 | 858 | 7458 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grading and Sanding across all access roads; float moves; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting108820200112-7Operator - Principle - After Jan 10886600 | Corbiere and Sons Contracting108820200112-7Operator - Principle - After Jan 10886600Inv#007-R01 | [5 empty] | 1 | 6600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1088 | 20200112-7 | 53510111 | Access | 0 | Labourer - General - After Jan 10 | 60 | 22 | HR |  |  | 60 | 0 | 1320 | 171.6 | 1491.6 | 2020-01-12 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grading and Sanding across all access roads; float moves; |  |  | Wind Farm-A080 to A117 | 0 |  |  | 37 | 43851 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting108820200112-7Labourer - General - After Jan 10221320 | Corbiere and Sons Contracting108820200112-7Labourer - General - After Jan 10221320Inv#007-R01 | [5 empty] | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1065 | 20200113-1 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 |  |  |  | 100 WolfRiver | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106520200113-1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting106520200113-1Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1065 | 20200113-1 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 |  |  |  | 100 WolfRiver | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106520200113-1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting106520200113-1Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1065 | 20200113-1 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 |  |  |  | 100 WolfRiver | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106520200113-1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting106520200113-1Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1065 | 20200113-1 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 |  |  |  | 100 WolfRiver | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106520200113-1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting106520200113-1Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1065 | 20200113-1 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 |  |  |  | 100 WolfRiver | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106520200113-1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting106520200113-1Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1065 | 20200113-1 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 |  |  |  | 100 WolfRiver | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106520200113-1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting106520200113-1Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1065 | 20200113-1 | 53510106 | Access | 0 | Project Manager | 110 | 12 | HR |  |  | 110 | 0 | 1320 | 171.6 | 1491.6 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 |  |  |  | 100 WolfRiver | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106520200113-1Project Manager121320 | Corbiere and Sons Contracting106520200113-1Project Manager121320Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1065 | 20200113-1 | 53510106 | Access | 0 | Superintendent | 105 | 12 | HR |  |  | 105 | 0 | 1260 | 163.8 | 1423.8 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 |  |  |  | 100 WolfRiver | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106520200113-1Superintendent121260 | Corbiere and Sons Contracting106520200113-1Superintendent121260Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1065 | 20200113-1 | 53510106 | Access | 0 | Project Coordinator | 80 | 12 | HR |  |  | 80 | 0 | 960 | 124.8 | 1084.8 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 |  |  |  | 100 WolfRiver | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106520200113-1Project Coordinator12960 | Corbiere and Sons Contracting106520200113-1Project Coordinator12960Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1065 | 20200113-1 | 53510106 | Access | 0 | Project Coordinator | 80 | 12 | HR |  |  | 80 | 0 | 960 | 124.8 | 1084.8 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 |  |  |  | 100 WolfRiver | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106520200113-1Project Coordinator12960 | Corbiere and Sons Contracting106520200113-1Project Coordinator12960Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1065 | 20200113-1 | 53510106 | Access | 0 | Safety Advisor | 85 | 12 | HR |  |  | 85 | 0 | 1020 | 132.6 | 1152.6 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 |  |  |  | 100 WolfRiver | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106520200113-1Safety Advisor121020 | Corbiere and Sons Contracting106520200113-1Safety Advisor121020Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1065 | 20200113-1 | 53510106 | Access | 0 | Site Administrator | 50 | 10 | HR |  |  | 50 | 0 | 500 | 65 | 565 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 |  |  |  | 100 WolfRiver | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106520200113-1Site Administrator10500 | Corbiere and Sons Contracting106520200113-1Site Administrator10500Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1065 | 20200113-1 | 53510106 | Access | 0 | Project Controls | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 |  |  |  | 100 WolfRiver | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106520200113-1Project Controls12840 | Corbiere and Sons Contracting106520200113-1Project Controls12840Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1065 | 20200113-1 | 53510106 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 |  |  |  | 100 WolfRiver | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106520200113-1L.O.A.71470 | Corbiere and Sons Contracting106520200113-1L.O.A.71470Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1074 | 20200113-10 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A118 to 122 |  |  | Wolf Lake Road | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107420200113-10Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting107420200113-10Chainsaw and consumables- After Jan 103180Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1074 | 20200113-10 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A118 to 122 |  |  | Wolf Lake Road | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107420200113-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting107420200113-10Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1074 | 20200113-10 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A118 to 122 |  |  | Wolf Lake Road | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107420200113-10Foreman121140 | Corbiere and Sons Contracting107420200113-10Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1074 | 20200113-10 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A118 to 122 |  |  | Wolf Lake Road | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107420200113-10L.O.A.4840 | Corbiere and Sons Contracting107420200113-10L.O.A.4840Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1074 | 20200113-10 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A118 to 122 |  |  | Wolf Lake Road | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107420200113-10Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting107420200113-10Labourer - Specialized - After Jan 10332310Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1075 | 20200113-11 | 53520102 | Clearing | 0 | Brusher | 202.5 | 3 | HR | 151.88 | 0 |  |  | 607.5 | 78.975 | 686.475 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Raking and Brushing from A132 to A139 |  |  | Fish Hatchery | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107520200113-11Brusher3607.5 | Corbiere and Sons Contracting107520200113-11Brusher3607.5Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 607.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1075 | 20200113-11 | 53520102 | Clearing | 0 | Mulcher | 205 | 3 | HR | 153.75 | 0 |  |  | 615 | 79.95 | 694.95 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Raking and Brushing from A132 to A139 |  |  | Fish Hatchery | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107520200113-11Mulcher3615 | Corbiere and Sons Contracting107520200113-11Mulcher3615Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 615 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1075 | 20200113-11 | 53520102 | Clearing | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Raking and Brushing from A132 to A139 |  |  | Fish Hatchery | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107520200113-11Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting107520200113-11Excavator - 36 ton- After Jan 1091322.64Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1075 | 20200113-11 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Raking and Brushing from A132 to A139 |  |  | Fish Hatchery | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107520200113-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting107520200113-11Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1075 | 20200113-11 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Raking and Brushing from A132 to A139 |  |  | Fish Hatchery | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107520200113-11L.O.A.2420 | Corbiere and Sons Contracting107520200113-11L.O.A.2420Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1075 | 20200113-11 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 15 | HR |  |  | 75 | 0 | 1125 | 146.25 | 1271.25 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Raking and Brushing from A132 to A139 |  |  | Fish Hatchery | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107520200113-11Operator - Principle - After Jan 10151125 | Corbiere and Sons Contracting107520200113-11Operator - Principle - After Jan 10151125Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1077 | 20200113-13-R1 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 2 | HR | 180 | 0 |  |  | 480 | 62.4 | 542.4 | 2020-01-13 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 FB and 1 SKD had to walk roughly 6 KM's up Black Sturgeon Rd. to get to cutting area at B024 as their was no ability for a float truck to be able to make the drop off and turn around. This took 7 hours for both Operators and Equipment units. | 2 | B018 - B029 | Black Sturgeon | 0 | 44141 |  | 36 | 43994 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107720200113-13-R1Feller Buncher2480 | Corbiere and Sons Contracting107720200113-13-R1Feller Buncher2480Inv#071 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1077 | 20200113-13-R1 | 53520102 | Clearing | 0 | Skidder | 171 | 1 | HR | 128.25 | 0 |  |  | 171 | 22.23 | 193.23 | 2020-01-13 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 FB and 1 SKD had to walk roughly 6 KM's up Black Sturgeon Rd. to get to cutting area at B024 as their was no ability for a float truck to be able to make the drop off and turn around. This took 7 hours for both Operators and Equipment units. | 2 | B018 - B029 | Black Sturgeon | 0 | 44141 |  | 36 | 43994 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107720200113-13-R1Skidder 1171 | Corbiere and Sons Contracting107720200113-13-R1Skidder 1171Inv#071 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 171 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1077 | 20200113-13-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-13 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 FB and 1 SKD had to walk roughly 6 KM's up Black Sturgeon Rd. to get to cutting area at B024 as their was no ability for a float truck to be able to make the drop off and turn around. This took 7 hours for both Operators and Equipment units. | 2 | B018 - B029 | Black Sturgeon | 0 | 44141 |  | 36 | 43994 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107720200113-13-R1L.O.A.2420 | Corbiere and Sons Contracting107720200113-13-R1L.O.A.2420Inv#071 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1077 | 20200113-13-R1 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-01-13 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 FB and 1 SKD had to walk roughly 6 KM's up Black Sturgeon Rd. to get to cutting area at B024 as their was no ability for a float truck to be able to make the drop off and turn around. This took 7 hours for both Operators and Equipment units. | 2 | B018 - B029 | Black Sturgeon | 0 | 44141 |  | 36 | 43994 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107720200113-13-R1Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting107720200113-13-R1Operator - Principle - After Jan 103225Inv#071 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1152 | 20200113-17-R1 | 53510611 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 7 | HR | 74.25 | 0 |  |  | 693 | 90.09 | 783.09 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | Clearing new access road into Santoy Lake; Flagging; Mobing; Landowner held up work for 2 hours (CC9010) |  |  | Santoy Lake Road | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting115220200113-17-R1Loader JD 524 to 624 or equal7693 | Corbiere and Sons Contracting115220200113-17-R1Loader JD 524 to 624 or equal7693Inv#007-R01 | [5 empty] | 1 | 693 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1152 | 20200113-17-R1 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 14 | Dynamic | 98.61 | 0 |  |  | 1840.72 | 239.2936 | 2080.0136 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | Clearing new access road into Santoy Lake; Flagging; Mobing; Landowner held up work for 2 hours (CC9010) |  |  | Santoy Lake Road | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting115220200113-17-R1Dozer D6 or equal- After Jan 10141840.72 | Corbiere and Sons Contracting115220200113-17-R1Dozer D6 or equal- After Jan 10141840.72Inv#007-R01 | [5 empty] | 1 | 1840.72 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1152 | 20200113-17-R1 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | Clearing new access road into Santoy Lake; Flagging; Mobing; Landowner held up work for 2 hours (CC9010) |  |  | Santoy Lake Road | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting115220200113-17-R1Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting115220200113-17-R1Light Truck - Pick up- After Jan 103731.25Inv#007-R01 | [5 empty] | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1152 | 20200113-17-R1 | 53510611 | Access | 0 | Foreman | 95 | 7 | HR |  |  | 95 | 0 | 665 | 86.45 | 751.45 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | Clearing new access road into Santoy Lake; Flagging; Mobing; Landowner held up work for 2 hours (CC9010) |  |  | Santoy Lake Road | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting115220200113-17-R1Foreman7665 | Corbiere and Sons Contracting115220200113-17-R1Foreman7665Inv#007-R01 | [5 empty] | 1 | 665 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1152 | 20200113-17-R1 | 53510611 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | Clearing new access road into Santoy Lake; Flagging; Mobing; Landowner held up work for 2 hours (CC9010) |  |  | Santoy Lake Road | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting115220200113-17-R1Foreman2190 | Corbiere and Sons Contracting115220200113-17-R1Foreman2190Inv#007-R01 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1152 | 20200113-17-R1 | 53510611 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | Clearing new access road into Santoy Lake; Flagging; Mobing; Landowner held up work for 2 hours (CC9010) |  |  | Santoy Lake Road | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting115220200113-17-R1L.O.A.4840 | Corbiere and Sons Contracting115220200113-17-R1L.O.A.4840Inv#007-R01 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1152 | 20200113-17-R1 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | Clearing new access road into Santoy Lake; Flagging; Mobing; Landowner held up work for 2 hours (CC9010) |  |  | Santoy Lake Road | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting115220200113-17-R1Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting115220200113-17-R1Operator - Principle - After Jan 1012900Inv#007-R01 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1152 | 20200113-17-R1 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | Clearing new access road into Santoy Lake; Flagging; Mobing; Landowner held up work for 2 hours (CC9010) |  |  | Santoy Lake Road | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting115220200113-17-R1Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting115220200113-17-R1Labourer - General - After Jan 1011660Inv#007-R01 | [5 empty] | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1066 | 20200113-2 | 53510106 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 74.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 |  |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106620200113-2Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting106620200113-2Loader JD 524 to 624 or equal5495Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1066 | 20200113-2 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 |  |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106620200113-2Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting106620200113-2Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1066 | 20200113-2 | 53510106 | Access | 0 | Operator - Apprentice | 60 | 10 | HR |  |  | 60 | 0 | 600 | 78 | 678 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 |  |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106620200113-2Operator - Apprentice10600 | Corbiere and Sons Contracting106620200113-2Operator - Apprentice10600Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1067 | 20200113-3 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Walking out and then equipment floated |  |  | Beck Road W | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106720200113-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting106720200113-3Light Truck - Pick up- After Jan 101243.75Inv#007-R01 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1067 | 20200113-3 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Walking out and then equipment floated |  |  | Beck Road W | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106720200113-3L.O.A.2420 | Corbiere and Sons Contracting106720200113-3L.O.A.2420Inv#007-R01 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1067 | 20200113-3 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Walking out and then equipment floated |  |  | Beck Road W | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting106720200113-3Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting106720200113-3Operator - Principle - After Jan 10221650Inv#007-R01 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1068 | 20200113-4-R1 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling at A038; Grinding of Material at A036; |  |  | Beck Road W | 0 |  |  | 37 | 43849 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting106820200113-4-R1Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting106820200113-4-R1Grinder - 4710 Peterson or equal95011.2Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1068 | 20200113-4-R1 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling at A038; Grinding of Material at A036; |  |  | Beck Road W | 0 |  |  | 37 | 43849 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting106820200113-4-R1Log Loader91377 | Corbiere and Sons Contracting106820200113-4-R1Log Loader91377Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1068 | 20200113-4-R1 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 4 | unit/man/day | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling at A038; Grinding of Material at A036; |  |  | Beck Road W | 0 |  |  | 37 | 43849 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting106820200113-4-R1Chainsaw and consumables- After Jan 104240 | Corbiere and Sons Contracting106820200113-4-R1Chainsaw and consumables- After Jan 104240Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1068 | 20200113-4-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling at A038; Grinding of Material at A036; |  |  | Beck Road W | 0 |  |  | 37 | 43849 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting106820200113-4-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting106820200113-4-R1Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1068 | 20200113-4-R1 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling at A038; Grinding of Material at A036; |  |  | Beck Road W | 0 |  |  | 37 | 43849 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting106820200113-4-R1Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting106820200113-4-R1Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1068 | 20200113-4-R1 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling at A038; Grinding of Material at A036; |  |  | Beck Road W | 0 |  |  | 37 | 43849 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting106820200113-4-R1Foreman121140 | Corbiere and Sons Contracting106820200113-4-R1Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1068 | 20200113-4-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling at A038; Grinding of Material at A036; |  |  | Beck Road W | 0 |  |  | 37 | 43849 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting106820200113-4-R1L.O.A.1210 | Corbiere and Sons Contracting106820200113-4-R1L.O.A.1210Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1068 | 20200113-4-R1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling at A038; Grinding of Material at A036; |  |  | Beck Road W | 0 |  |  | 37 | 43849 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting106820200113-4-R1L.O.A.51050 | Corbiere and Sons Contracting106820200113-4-R1L.O.A.51050Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1068 | 20200113-4-R1 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling at A038; Grinding of Material at A036; |  |  | Beck Road W | 0 |  |  | 37 | 43849 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting106820200113-4-R1Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting106820200113-4-R1Operator - Principle - After Jan 1011825Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1068 | 20200113-4-R1 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 44 | HR |  |  | 70 | 0 | 3080 | 400.4 | 3480.4 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling at A038; Grinding of Material at A036; |  |  | Beck Road W | 0 |  |  | 37 | 43849 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting106820200113-4-R1Labourer - Specialized - After Jan 10443080 | Corbiere and Sons Contracting106820200113-4-R1Labourer - Specialized - After Jan 10443080Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 3080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1069 | 20200113-5 | 53520101 | Clearing | 0 | Brusher | 202.5 | 5 | HR | 151.88 | 0 |  |  | 1012.5 | 131.625 | 1144.125 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing from A076; FB and SKD working from A067 |  |  | Eldorado | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting106920200113-5Brusher51012.5 | Corbiere and Sons Contracting106920200113-5Brusher51012.5Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1012.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1069 | 20200113-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing from A076; FB and SKD working from A067 |  |  | Eldorado | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting106920200113-5Brusher91822.5 | Corbiere and Sons Contracting106920200113-5Brusher91822.5Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1069 | 20200113-5 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing from A076; FB and SKD working from A067 |  |  | Eldorado | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting106920200113-5Feller Buncher92160 | Corbiere and Sons Contracting106920200113-5Feller Buncher92160Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1069 | 20200113-5 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing from A076; FB and SKD working from A067 |  |  | Eldorado | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting106920200113-5Skidder 91539 | Corbiere and Sons Contracting106920200113-5Skidder 91539Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1069 | 20200113-5 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing from A076; FB and SKD working from A067 |  |  | Eldorado | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting106920200113-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting106920200113-5Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1069 | 20200113-5 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing from A076; FB and SKD working from A067 |  |  | Eldorado | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting106920200113-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting106920200113-5Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1069 | 20200113-5 | 53520101 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing from A076; FB and SKD working from A067 |  |  | Eldorado | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting106920200113-5Foreman6570 | Corbiere and Sons Contracting106920200113-5Foreman6570Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1069 | 20200113-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing from A076; FB and SKD working from A067 |  |  | Eldorado | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting106920200113-5L.O.A.3630 | Corbiere and Sons Contracting106920200113-5L.O.A.3630Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1069 | 20200113-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing from A076; FB and SKD working from A067 |  |  | Eldorado | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting106920200113-5L.O.A.2420 | Corbiere and Sons Contracting106920200113-5L.O.A.2420Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1069 | 20200113-5 | 53520101 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing from A076; FB and SKD working from A067 |  |  | Eldorado | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting106920200113-5Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting106920200113-5Operator - Principle - After Jan 10221650Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1069 | 20200113-5 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 18 | HR |  |  | 75 | 0 | 1350 | 175.5 | 1525.5 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brushing from A076; FB and SKD working from A067 |  |  | Eldorado | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting106920200113-5Operator - Principle - After Jan 10181350 | Corbiere and Sons Contracting106920200113-5Operator - Principle - After Jan 10181350Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1070 | 20200113-6 | 53510111 | Access | 0 | Dozer - D5 or equal- After Jan 10 | 80.93 | 9 | Dynamic | 60.7 | 0 |  |  | 728.37 | 94.6881 | 823.0581 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Winter Road Building from A077 to A078; Clearing pads from A072, A072, A073, A077; Winter Road Building and Maintenance from A055 and from A063-A064 |  |  | Eldorado | 1 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting107020200113-6Dozer - D5 or equal- After Jan 109728.37 | Corbiere and Sons Contracting107020200113-6Dozer - D5 or equal- After Jan 109728.37Inv#007-R01 | [5 empty] | 1 | 728.37 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1070 | 20200113-6 | 53510111 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Winter Road Building from A077 to A078; Clearing pads from A072, A072, A073, A077; Winter Road Building and Maintenance from A055 and from A063-A064 |  |  | Eldorado | 1 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting107020200113-6Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting107020200113-6Dozer D6 or equal- After Jan 106788.88Inv#007-R01 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1070 | 20200113-6 | 53510111 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Winter Road Building from A077 to A078; Clearing pads from A072, A072, A073, A077; Winter Road Building and Maintenance from A055 and from A063-A064 |  |  | Eldorado | 1 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting107020200113-6Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting107020200113-6Excavator - 30 ton- After Jan 1091246.05Inv#007-R01 | [5 empty] | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1070 | 20200113-6 | 53510111 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Winter Road Building from A077 to A078; Clearing pads from A072, A072, A073, A077; Winter Road Building and Maintenance from A055 and from A063-A064 |  |  | Eldorado | 1 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting107020200113-6L.O.A.4840 | Corbiere and Sons Contracting107020200113-6L.O.A.4840Inv#007-R01 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1070 | 20200113-6 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 45.5 | HR |  |  | 75 | 0 | 3412.5 | 443.625 | 3856.125 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Winter Road Building from A077 to A078; Clearing pads from A072, A072, A073, A077; Winter Road Building and Maintenance from A055 and from A063-A064 |  |  | Eldorado | 1 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting107020200113-6Operator - Principle - After Jan 1045.53412.5 | Corbiere and Sons Contracting107020200113-6Operator - Principle - After Jan 1045.53412.5Inv#007-R01 | [5 empty] | 1 | 3412.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1071 | 20200113-7 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A114 |  |  | Wind Farm | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting107120200113-7Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting107120200113-7Grinder - 4710 Peterson or equal95011.2Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1071 | 20200113-7 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A114 |  |  | Wind Farm | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting107120200113-7Log Loader91377 | Corbiere and Sons Contracting107120200113-7Log Loader91377Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1071 | 20200113-7 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A114 |  |  | Wind Farm | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting107120200113-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting107120200113-7Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1071 | 20200113-7 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A114 |  |  | Wind Farm | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting107120200113-7L.O.A.1210 | Corbiere and Sons Contracting107120200113-7L.O.A.1210Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1071 | 20200113-7 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A114 |  |  | Wind Farm | 0 |  |  | 37 | 43850 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting107120200113-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting107120200113-7Operator - Principle - After Jan 1011825Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1072 | 20200113-8 | 53510111 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders and Sanders working across access Roads; Float moves, FBs and brushers from field to yard, Exs and DZs from Field to Yard; Rd. Building at A085; |  |  | Wind Farm | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107220200113-8Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting107220200113-8Excavator - 30 ton- After Jan 1091246.05Inv#007-R01 | [5 empty] | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1072 | 20200113-8 | 53510111 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 110.22 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders and Sanders working across access Roads; Float moves, FBs and brushers from field to yard, Exs and DZs from Field to Yard; Rd. Building at A085; |  |  | Wind Farm | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107220200113-8Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting107220200113-8Excavator - 36 ton- After Jan 10182645.28Inv#007-R01 | [5 empty] | 1 | 2645.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1072 | 20200113-8 | 53510111 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders and Sanders working across access Roads; Float moves, FBs and brushers from field to yard, Exs and DZs from Field to Yard; Rd. Building at A085; |  |  | Wind Farm | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107220200113-8Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting107220200113-8Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#007-R01 | [5 empty] | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1072 | 20200113-8 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 21 | Dynamic | 95.24 | 0 |  |  | 2666.58 | 346.6554 | 3013.2354 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders and Sanders working across access Roads; Float moves, FBs and brushers from field to yard, Exs and DZs from Field to Yard; Rd. Building at A085; |  |  | Wind Farm | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107220200113-8Grader - Cat 12 to 14 or equal- After Jan 10212666.58 | Corbiere and Sons Contracting107220200113-8Grader - Cat 12 to 14 or equal- After Jan 10212666.58Inv#007-R01 | [5 empty] | 1 | 2666.58 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1072 | 20200113-8 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 11 | Dynamic | 64.79 | 0 |  |  | 950.18 | 123.5234 | 1073.7034 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders and Sanders working across access Roads; Float moves, FBs and brushers from field to yard, Exs and DZs from Field to Yard; Rd. Building at A085; |  |  | Wind Farm | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107220200113-8Sander Truck - Forestry- After Jan 1011950.18 | Corbiere and Sons Contracting107220200113-8Sander Truck - Forestry- After Jan 1011950.18Inv#007-R01 | [5 empty] | 1 | 950.18 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1072 | 20200113-8 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders and Sanders working across access Roads; Float moves, FBs and brushers from field to yard, Exs and DZs from Field to Yard; Rd. Building at A085; |  |  | Wind Farm | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107220200113-8Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting107220200113-8Light Truck - Pick up- After Jan 104975Inv#007-R01 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1072 | 20200113-8 | 53510111 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 9 | Dynamic | 91.79 | 0 |  |  | 1101.51 | 143.1963 | 1244.7063 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders and Sanders working across access Roads; Float moves, FBs and brushers from field to yard, Exs and DZs from Field to Yard; Rd. Building at A085; |  |  | Wind Farm | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107220200113-8Tractor Trailer - 60 Ton- After Jan 1091101.51 | Corbiere and Sons Contracting107220200113-8Tractor Trailer - 60 Ton- After Jan 1091101.51Inv#007-R01 | [5 empty] | 1 | 1101.51 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1072 | 20200113-8 | 53510111 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders and Sanders working across access Roads; Float moves, FBs and brushers from field to yard, Exs and DZs from Field to Yard; Rd. Building at A085; |  |  | Wind Farm | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107220200113-8Foreman121140 | Corbiere and Sons Contracting107220200113-8Foreman121140Inv#007-R01 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1072 | 20200113-8 | 53510111 | Access | 0 | L.O.A. | 210 | 11 | DAY |  |  |  | 0 | 2310 | 300.3 | 2610.3 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders and Sanders working across access Roads; Float moves, FBs and brushers from field to yard, Exs and DZs from Field to Yard; Rd. Building at A085; |  |  | Wind Farm | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107220200113-8L.O.A.112310 | Corbiere and Sons Contracting107220200113-8L.O.A.112310Inv#007-R01 | [5 empty] | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1072 | 20200113-8 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 88 | HR |  |  | 75 | 0 | 6600 | 858 | 7458 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders and Sanders working across access Roads; Float moves, FBs and brushers from field to yard, Exs and DZs from Field to Yard; Rd. Building at A085; |  |  | Wind Farm | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107220200113-8Operator - Principle - After Jan 10886600 | Corbiere and Sons Contracting107220200113-8Operator - Principle - After Jan 10886600Inv#007-R01 | [5 empty] | 1 | 6600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1072 | 20200113-8 | 53510111 | Access | 0 | Labourer - General - After Jan 10 | 60 | 22 | HR |  |  | 60 | 0 | 1320 | 171.6 | 1491.6 | 2020-01-13 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Graders and Sanders working across access Roads; Float moves, FBs and brushers from field to yard, Exs and DZs from Field to Yard; Rd. Building at A085; |  |  | Wind Farm | 0 |  |  | 36 | 43849 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting107220200113-8Labourer - General - After Jan 10221320 | Corbiere and Sons Contracting107220200113-8Labourer - General - After Jan 10221320Inv#007-R01 | [5 empty] | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.053803 | DAY | 182.81 | 0 |  |  | 13.1145 | 1.7049 | 14.8194 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Light Truck - Pick up- After Jan 100.053803213.1145 | Corbiere and Sons Contracting108120200114-1Light Truck - Pick up- After Jan 100.053803213.1145Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 13.1145 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510107 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.088977 | DAY | 182.81 | 0 |  |  | 21.6882 | 2.8195 | 24.5077 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Light Truck - Pick up- After Jan 100.088977121.6882 | Corbiere and Sons Contracting108120200114-1Light Truck - Pick up- After Jan 100.088977121.6882Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 10.8441 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1.5089 | DAY | 182.81 | 0 |  |  | 367.7941 | 47.8132 | 415.6073 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Light Truck - Pick up- After Jan 101.508899367.7941 | Corbiere and Sons Contracting108120200114-1Light Truck - Pick up- After Jan 101.508899367.7941Inv#007-R01 | [5 empty] | 1 | 367.7941 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.5613 | DAY | 182.81 | 0 |  |  | 136.8174 | 17.7863 | 154.6037 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Light Truck - Pick up- After Jan 100.5613021136.8174 | Corbiere and Sons Contracting108120200114-1Light Truck - Pick up- After Jan 100.5613021136.8174Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 136.8174 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1.2359 | DAY | 182.81 | 0 |  |  | 301.2436 | 39.1617 | 340.4053 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Light Truck - Pick up- After Jan 101.2358711301.2436 | Corbiere and Sons Contracting108120200114-1Light Truck - Pick up- After Jan 101.2358711301.2436Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 301.2436 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.55028 | DAY | 182.81 | 0 |  |  | 134.1312 | 17.4371 | 151.5683 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Light Truck - Pick up- After Jan 100.550282134.1312 | Corbiere and Sons Contracting108120200114-1Light Truck - Pick up- After Jan 100.550282134.1312Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 134.1312 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510106 | Access | 0 | Project Manager | 110 | 0.12913 | HR |  |  | 110 | 0 | 14.204 | 1.8465 | 16.0505 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Project Manager0.129127714.204 | Corbiere and Sons Contracting108120200114-1Project Manager0.129127714.204Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 14.204 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510107 | Access | 0 | Project Manager | 110 | 0.21355 | HR |  |  | 110 | 0 | 23.49 | 3.0537 | 26.5437 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Project Manager0.21354523.49 | Corbiere and Sons Contracting108120200114-1Project Manager0.21354523.49Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 11.745 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510111 | Access | 0 | Project Manager | 110 | 3.6214 | HR |  |  | 110 | 0 | 398.3493 | 51.7854 | 450.1347 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Project Manager3.6213575398.3493 | Corbiere and Sons Contracting108120200114-1Project Manager3.6213575398.3493Inv#007-R01 | [5 empty] | 1 | 398.3493 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 1.3471 | HR |  |  | 110 | 0 | 148.1838 | 19.2639 | 167.4477 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Project Manager1.347125148.1838 | Corbiere and Sons Contracting108120200114-1Project Manager1.347125148.1838Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 148.1838 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520102 | Clearing | 0 | Project Manager | 110 | 2.9661 | HR |  |  | 110 | 0 | 326.27 | 42.4151 | 368.6851 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Project Manager2.9660906326.27 | Corbiere and Sons Contracting108120200114-1Project Manager2.9660906326.27Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 326.27 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520104 | Clearing | 0 | Project Manager | 110 | 1.3207 | HR |  |  | 110 | 0 | 145.2745 | 18.8857 | 164.1602 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Project Manager1.3206769145.2745 | Corbiere and Sons Contracting108120200114-1Project Manager1.3206769145.2745Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 145.2745 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510106 | Access | 0 | Superintendent | 105 | 0.12913 | HR |  |  | 105 | 0 | 13.5584 | 1.7626 | 15.321 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Superintendent0.129127713.5584 | Corbiere and Sons Contracting108120200114-1Superintendent0.129127713.5584Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 13.5584 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510107 | Access | 0 | Superintendent | 105 | 0.21355 | HR |  |  | 105 | 0 | 22.4222 | 2.9149 | 25.3371 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Superintendent0.21354522.4222 | Corbiere and Sons Contracting108120200114-1Superintendent0.21354522.4222Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 11.2111 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510111 | Access | 0 | Superintendent | 105 | 3.6214 | HR |  |  | 105 | 0 | 380.2425 | 49.4315 | 429.674 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Superintendent3.6213575380.2425 | Corbiere and Sons Contracting108120200114-1Superintendent3.6213575380.2425Inv#007-R01 | [5 empty] | 1 | 380.2425 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 1.3471 | HR |  |  | 105 | 0 | 141.4481 | 18.3883 | 159.8364 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Superintendent1.347125141.4481 | Corbiere and Sons Contracting108120200114-1Superintendent1.347125141.4481Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 141.4481 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520102 | Clearing | 0 | Superintendent | 105 | 2.9661 | HR |  |  | 105 | 0 | 311.4395 | 40.4871 | 351.9266 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Superintendent2.9660906311.4395 | Corbiere and Sons Contracting108120200114-1Superintendent2.9660906311.4395Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 311.4395 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520104 | Clearing | 0 | Superintendent | 105 | 1.3207 | HR |  |  | 105 | 0 | 138.6711 | 18.0272 | 156.6983 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Superintendent1.3206769138.6711 | Corbiere and Sons Contracting108120200114-1Superintendent1.3206769138.6711Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 138.6711 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510106 | Access | 0 | Project Coordinator | 80 | 0.12913 | HR |  |  | 80 | 0 | 10.3302 | 1.3429 | 11.6731 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Project Coordinator0.129127710.3302 | Corbiere and Sons Contracting108120200114-1Project Coordinator0.129127710.3302Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 10.3302 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510107 | Access | 0 | Project Coordinator | 80 | 0.21355 | HR |  |  | 80 | 0 | 17.0836 | 2.2209 | 19.3045 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Project Coordinator0.21354517.0836 | Corbiere and Sons Contracting108120200114-1Project Coordinator0.21354517.0836Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 8.5418 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510111 | Access | 0 | Project Coordinator | 80 | 3.6214 | HR |  |  | 80 | 0 | 289.7086 | 37.6621 | 327.3707 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Project Coordinator3.6213575289.7086 | Corbiere and Sons Contracting108120200114-1Project Coordinator3.6213575289.7086Inv#007-R01 | [5 empty] | 1 | 289.7086 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 1.3471 | HR |  |  | 80 | 0 | 107.77 | 14.0101 | 121.7801 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Project Coordinator1.347125107.77 | Corbiere and Sons Contracting108120200114-1Project Coordinator1.347125107.77Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 107.77 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520102 | Clearing | 0 | Project Coordinator | 80 | 2.9661 | HR |  |  | 80 | 0 | 237.2872 | 30.8473 | 268.1345 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Project Coordinator2.9660906237.2872 | Corbiere and Sons Contracting108120200114-1Project Coordinator2.9660906237.2872Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 237.2872 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520104 | Clearing | 0 | Project Coordinator | 80 | 1.3207 | HR |  |  | 80 | 0 | 105.6542 | 13.735 | 119.3892 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Project Coordinator1.3206769105.6542 | Corbiere and Sons Contracting108120200114-1Project Coordinator1.3206769105.6542Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 105.6542 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510106 | Access | 0 | Safety Advisor | 85 | 0.12913 | HR |  |  | 85 | 0 | 10.9759 | 1.4269 | 12.4028 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Safety Advisor0.129127710.9759 | Corbiere and Sons Contracting108120200114-1Safety Advisor0.129127710.9759Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 10.9759 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510107 | Access | 0 | Safety Advisor | 85 | 0.21355 | HR |  |  | 85 | 0 | 18.1513 | 2.3597 | 20.511 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Safety Advisor0.21354518.1513 | Corbiere and Sons Contracting108120200114-1Safety Advisor0.21354518.1513Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 9.0756 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510111 | Access | 0 | Safety Advisor | 85 | 3.6214 | HR |  |  | 85 | 0 | 307.8154 | 40.016 | 347.8314 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Safety Advisor3.6213575307.8154 | Corbiere and Sons Contracting108120200114-1Safety Advisor3.6213575307.8154Inv#007-R01 | [5 empty] | 1 | 307.8154 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 1.3471 | HR |  |  | 85 | 0 | 114.5056 | 14.8857 | 129.3913 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Safety Advisor1.347125114.5056 | Corbiere and Sons Contracting108120200114-1Safety Advisor1.347125114.5056Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 114.5056 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520102 | Clearing | 0 | Safety Advisor | 85 | 2.9661 | HR |  |  | 85 | 0 | 252.1177 | 32.7753 | 284.893 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Safety Advisor2.9660906252.1177 | Corbiere and Sons Contracting108120200114-1Safety Advisor2.9660906252.1177Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 252.1177 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520104 | Clearing | 0 | Safety Advisor | 85 | 1.3207 | HR |  |  | 85 | 0 | 112.2575 | 14.5935 | 126.851 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Safety Advisor1.3206769112.2575 | Corbiere and Sons Contracting108120200114-1Safety Advisor1.3206769112.2575Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 112.2575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510106 | Access | 0 | Site Administrator | 50 | 0.10761 | HR |  |  | 50 | 0 | 5.3803 | 0.69944 | 6.0797 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Site Administrator0.10760645.3803 | Corbiere and Sons Contracting108120200114-1Site Administrator0.10760645.3803Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 5.3803 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510107 | Access | 0 | Site Administrator | 50 | 0.17795 | HR |  |  | 50 | 0 | 8.8977 | 1.1567 | 10.0544 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Site Administrator0.17795418.8977 | Corbiere and Sons Contracting108120200114-1Site Administrator0.17795418.8977Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 4.4489 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510111 | Access | 0 | Site Administrator | 50 | 3.0178 | HR |  |  | 50 | 0 | 150.8899 | 19.6157 | 170.5056 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Site Administrator3.017798150.8899 | Corbiere and Sons Contracting108120200114-1Site Administrator3.017798150.8899Inv#007-R01 | [5 empty] | 1 | 150.8899 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520101 | Clearing | 0 | Site Administrator | 50 | 1.1226 | HR |  |  | 50 | 0 | 56.1302 | 7.2969 | 63.4271 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Site Administrator1.122604256.1302 | Corbiere and Sons Contracting108120200114-1Site Administrator1.122604256.1302Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 56.1302 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520102 | Clearing | 0 | Site Administrator | 50 | 2.4717 | HR |  |  | 50 | 0 | 123.5871 | 16.0663 | 139.6534 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Site Administrator2.4717422123.5871 | Corbiere and Sons Contracting108120200114-1Site Administrator2.4717422123.5871Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 123.5871 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520104 | Clearing | 0 | Site Administrator | 50 | 1.1006 | HR |  |  | 50 | 0 | 55.0282 | 7.1537 | 62.1819 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Site Administrator1.100564155.0282 | Corbiere and Sons Contracting108120200114-1Site Administrator1.100564155.0282Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 55.0282 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510106 | Access | 0 | Project Controls | 70 | 0.12913 | HR |  |  | 70 | 0 | 9.0389 | 1.1751 | 10.214 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Project Controls0.12912779.0389 | Corbiere and Sons Contracting108120200114-1Project Controls0.12912779.0389Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 9.0389 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510107 | Access | 0 | Project Controls | 70 | 0.21355 | HR |  |  | 70 | 0 | 14.9482 | 1.9433 | 16.8915 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Project Controls0.21354514.9482 | Corbiere and Sons Contracting108120200114-1Project Controls0.21354514.9482Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 7.4741 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510111 | Access | 0 | Project Controls | 70 | 3.6214 | HR |  |  | 70 | 0 | 253.495 | 32.9543 | 286.4493 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Project Controls3.6213575253.495 | Corbiere and Sons Contracting108120200114-1Project Controls3.6213575253.495Inv#007-R01 | [5 empty] | 1 | 253.495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 1.3471 | HR |  |  | 70 | 0 | 94.2987 | 12.2588 | 106.5575 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Project Controls1.34712594.2987 | Corbiere and Sons Contracting108120200114-1Project Controls1.34712594.2987Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 94.2987 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520102 | Clearing | 0 | Project Controls | 70 | 2.9661 | HR |  |  | 70 | 0 | 207.6263 | 26.9914 | 234.6177 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Project Controls2.9660906207.6263 | Corbiere and Sons Contracting108120200114-1Project Controls2.9660906207.6263Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 207.6263 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520104 | Clearing | 0 | Project Controls | 70 | 1.3207 | HR |  |  | 70 | 0 | 92.4474 | 12.0182 | 104.4656 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1Project Controls1.320676992.4474 | Corbiere and Sons Contracting108120200114-1Project Controls1.320676992.4474Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 92.4474 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510106 | Access | 0 | L.O.A. | 210 | 0.064564 | DAY |  |  |  | 0 | 13.5584 | 1.7626 | 15.321 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1L.O.A.0.064563913.5584 | Corbiere and Sons Contracting108120200114-1L.O.A.0.064563913.5584Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 13.5584 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510107 | Access | 0 | L.O.A. | 210 | 0.10677 | DAY |  |  |  | 0 | 22.4222 | 2.9149 | 25.3371 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1L.O.A.0.106772522.4222 | Corbiere and Sons Contracting108120200114-1L.O.A.0.106772522.4222Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 11.2111 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53510111 | Access | 0 | L.O.A. | 210 | 1.8107 | DAY |  |  |  | 0 | 380.2425 | 49.4315 | 429.674 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1L.O.A.1.8106788380.2425 | Corbiere and Sons Contracting108120200114-1L.O.A.1.8106788380.2425Inv#007-R01 | [5 empty] | 1 | 380.2425 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 0.67356 | DAY |  |  |  | 0 | 141.4481 | 18.3883 | 159.8364 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1L.O.A.0.6735625141.4481 | Corbiere and Sons Contracting108120200114-1L.O.A.0.6735625141.4481Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 141.4481 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1.483 | DAY |  |  |  | 0 | 311.4395 | 40.4871 | 351.9266 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1L.O.A.1.4830453311.4395 | Corbiere and Sons Contracting108120200114-1L.O.A.1.4830453311.4395Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 311.4395 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1081 | 20200114-1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 0.66034 | DAY |  |  |  | 0 | 138.6711 | 18.0272 | 156.6983 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting108120200114-1L.O.A.0.6603384138.6711 | Corbiere and Sons Contracting108120200114-1L.O.A.0.6603384138.6711Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 138.6711 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1105 | 20200114-10 | 53520102 | Clearing | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Rd. Building from A135 to B001 |  |  | Fish Hatchery | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting110520200114-10Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting110520200114-10Excavator - 36 ton- After Jan 1091322.64Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1105 | 20200114-10 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Rd. Building from A135 to B001 |  |  | Fish Hatchery | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting110520200114-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting110520200114-10Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1105 | 20200114-10 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Rd. Building from A135 to B001 |  |  | Fish Hatchery | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting110520200114-10L.O.A.3630 | Corbiere and Sons Contracting110520200114-10L.O.A.3630Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1105 | 20200114-10 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Rd. Building from A135 to B001 |  |  | Fish Hatchery | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting110520200114-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting110520200114-10Operator - Principle - After Jan 1011825Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1105 | 20200114-10 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 22 | HR |  |  | 60 | 0 | 1320 | 171.6 | 1491.6 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Rd. Building from A135 to B001 |  |  | Fish Hatchery | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting110520200114-10Labourer - General - After Jan 10221320 | Corbiere and Sons Contracting110520200114-10Labourer - General - After Jan 10221320Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1109 | 20200114-16 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 14 | Dynamic | 98.61 | 0 |  |  | 1840.72 | 239.2936 | 2080.0136 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing new access raods and mobilzation. |  |  | Santoy Lake | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting110920200114-16Dozer D6 or equal- After Jan 10141840.72 | Corbiere and Sons Contracting110920200114-16Dozer D6 or equal- After Jan 10141840.72Inv#007-R01 | [5 empty] | 1 | 1840.72 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1109 | 20200114-16 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing new access raods and mobilzation. |  |  | Santoy Lake | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting110920200114-16Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting110920200114-16Light Truck - Pick up- After Jan 103731.25Inv#007-R01 | [5 empty] | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1109 | 20200114-16 | 53510611 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing new access raods and mobilzation. |  |  | Santoy Lake | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting110920200114-16L.O.A.4840 | Corbiere and Sons Contracting110920200114-16L.O.A.4840Inv#007-R01 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1109 | 20200114-16 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing new access raods and mobilzation. |  |  | Santoy Lake | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting110920200114-16Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting110920200114-16Operator - Principle - After Jan 10141050Inv#007-R01 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1109 | 20200114-16 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 14 | HR |  |  | 60 | 0 | 840 | 109.2 | 949.2 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing new access raods and mobilzation. |  |  | Santoy Lake | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting110920200114-16Labourer - General - After Jan 1014840 | Corbiere and Sons Contracting110920200114-16Labourer - General - After Jan 1014840Inv#007-R01 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1097 | 20200114-2 | 53510106 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 0.053803 | HR | 74.25 | 0 |  |  | 5.3265 | 0.69244 | 6.0189 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting109720200114-2Loader JD 524 to 624 or equal0.05380325.3265 | Corbiere and Sons Contracting109720200114-2Loader JD 524 to 624 or equal0.05380325.3265Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 5.3265 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1097 | 20200114-2 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 1.5089 | HR | 74.25 | 0 |  |  | 149.381 | 19.4195 | 168.8005 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting109720200114-2Loader JD 524 to 624 or equal1.508899149.381 | Corbiere and Sons Contracting109720200114-2Loader JD 524 to 624 or equal1.508899149.381Inv#007-R01 | [5 empty] | 1 | 149.381 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1097 | 20200114-2 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.5613 | HR | 74.25 | 0 |  |  | 55.5689 | 7.224 | 62.7929 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting109720200114-2Loader JD 524 to 624 or equal0.561302155.5689 | Corbiere and Sons Contracting109720200114-2Loader JD 524 to 624 or equal0.561302155.5689Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 55.5689 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1097 | 20200114-2 | 53520102 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 1.2359 | HR | 74.25 | 0 |  |  | 122.3512 | 15.9057 | 138.2569 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting109720200114-2Loader JD 524 to 624 or equal1.2358711122.3512 | Corbiere and Sons Contracting109720200114-2Loader JD 524 to 624 or equal1.2358711122.3512Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 122.3512 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1097 | 20200114-2 | 53520104 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.55028 | HR | 74.25 | 0 |  |  | 54.4779 | 7.0821 | 61.56 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting109720200114-2Loader JD 524 to 624 or equal0.55028254.4779 | Corbiere and Sons Contracting109720200114-2Loader JD 524 to 624 or equal0.55028254.4779Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 54.4779 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1097 | 20200114-2 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.010761 | DAY | 182.81 | 0 |  |  | 2.6229 | 0.34098 | 2.9639 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting109720200114-2Light Truck - Pick up- After Jan 100.01076062.6229 | Corbiere and Sons Contracting109720200114-2Light Truck - Pick up- After Jan 100.01076062.6229Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 2.6229 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1097 | 20200114-2 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.30178 | DAY | 182.81 | 0 |  |  | 73.5588 | 9.5626 | 83.1214 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting109720200114-2Light Truck - Pick up- After Jan 100.301779873.5588 | Corbiere and Sons Contracting109720200114-2Light Truck - Pick up- After Jan 100.301779873.5588Inv#007-R01 | [5 empty] | 1 | 73.5588 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1097 | 20200114-2 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.11226 | DAY | 182.81 | 0 |  |  | 27.3635 | 3.5573 | 30.9208 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting109720200114-2Light Truck - Pick up- After Jan 100.112260427.3635 | Corbiere and Sons Contracting109720200114-2Light Truck - Pick up- After Jan 100.112260427.3635Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 27.3635 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1097 | 20200114-2 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.24717 | DAY | 182.81 | 0 |  |  | 60.2487 | 7.8323 | 68.081 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting109720200114-2Light Truck - Pick up- After Jan 100.247174260.2487 | Corbiere and Sons Contracting109720200114-2Light Truck - Pick up- After Jan 100.247174260.2487Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 60.2487 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1097 | 20200114-2 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.11006 | DAY | 182.81 | 0 |  |  | 26.8262 | 3.4874 | 30.3136 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting109720200114-2Light Truck - Pick up- After Jan 100.110056426.8262 | Corbiere and Sons Contracting109720200114-2Light Truck - Pick up- After Jan 100.110056426.8262Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 26.8262 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1097 | 20200114-2 | 53510106 | Access | 0 | Operator - Apprentice | 60 | 0.10761 | HR |  |  | 60 | 0 | 6.4564 | 0.83933 | 7.2957 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting109720200114-2Operator - Apprentice0.10760646.4564 | Corbiere and Sons Contracting109720200114-2Operator - Apprentice0.10760646.4564Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 6.4564 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1097 | 20200114-2 | 53510111 | Access | 0 | Operator - Apprentice | 60 | 3.0178 | HR |  |  | 60 | 0 | 181.0679 | 23.5388 | 204.6067 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting109720200114-2Operator - Apprentice3.017798181.0679 | Corbiere and Sons Contracting109720200114-2Operator - Apprentice3.017798181.0679Inv#007-R01 | [5 empty] | 1 | 181.0679 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1097 | 20200114-2 | 53520101 | Clearing | 0 | Operator - Apprentice | 60 | 1.1226 | HR |  |  | 60 | 0 | 67.3563 | 8.7563 | 76.1126 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting109720200114-2Operator - Apprentice1.122604267.3563 | Corbiere and Sons Contracting109720200114-2Operator - Apprentice1.122604267.3563Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 67.3563 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1097 | 20200114-2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 2.4717 | HR |  |  | 60 | 0 | 148.3045 | 19.2796 | 167.5841 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting109720200114-2Operator - Apprentice2.4717422148.3045 | Corbiere and Sons Contracting109720200114-2Operator - Apprentice2.4717422148.3045Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 148.3045 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1097 | 20200114-2 | 53520104 | Clearing | 0 | Operator - Apprentice | 60 | 1.1006 | HR |  |  | 60 | 0 | 66.0338 | 8.5844 | 74.6182 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting109720200114-2Operator - Apprentice1.100564166.0338 | Corbiere and Sons Contracting109720200114-2Operator - Apprentice1.100564166.0338Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 66.0338 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1098 | 20200114-3 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A037-A036; Grinding of Material at A036; |  |  | Beck Road West | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109820200114-3Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting109820200114-3Grinder - 4710 Peterson or equal95011.2Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1098 | 20200114-3 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A037-A036; Grinding of Material at A036; |  |  | Beck Road West | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109820200114-3Log Loader91377 | Corbiere and Sons Contracting109820200114-3Log Loader91377Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1098 | 20200114-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 4 | unit/man/day | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A037-A036; Grinding of Material at A036; |  |  | Beck Road West | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109820200114-3Chainsaw and consumables- After Jan 104240 | Corbiere and Sons Contracting109820200114-3Chainsaw and consumables- After Jan 104240Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1098 | 20200114-3 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A037-A036; Grinding of Material at A036; |  |  | Beck Road West | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109820200114-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting109820200114-3Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1098 | 20200114-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A037-A036; Grinding of Material at A036; |  |  | Beck Road West | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109820200114-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting109820200114-3Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1098 | 20200114-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A037-A036; Grinding of Material at A036; |  |  | Beck Road West | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109820200114-3Foreman121140 | Corbiere and Sons Contracting109820200114-3Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1098 | 20200114-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A037-A036; Grinding of Material at A036; |  |  | Beck Road West | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109820200114-3L.O.A.1210 | Corbiere and Sons Contracting109820200114-3L.O.A.1210Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1098 | 20200114-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A037-A036; Grinding of Material at A036; |  |  | Beck Road West | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109820200114-3L.O.A.51050 | Corbiere and Sons Contracting109820200114-3L.O.A.51050Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1098 | 20200114-3 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A037-A036; Grinding of Material at A036; |  |  | Beck Road West | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109820200114-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting109820200114-3Operator - Principle - After Jan 1011825Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1098 | 20200114-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 44 | HR |  |  | 70 | 0 | 3080 | 400.4 | 3480.4 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A037-A036; Grinding of Material at A036; |  |  | Beck Road West | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109820200114-3Labourer - Specialized - After Jan 10443080 | Corbiere and Sons Contracting109820200114-3Labourer - Specialized - After Jan 10443080Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 3080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1099 | 20200114-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 4 | HR | 151.88 | 0 |  |  | 810 | 105.3 | 915.3 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher being float moved to WF2; 1 FB, 1 SKD working from A067-A062; 1 BR working from A061-A064; |  |  | Eldorado | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109920200114-4Brusher4810 | Corbiere and Sons Contracting109920200114-4Brusher4810Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 810 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1099 | 20200114-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher being float moved to WF2; 1 FB, 1 SKD working from A067-A062; 1 BR working from A061-A064; |  |  | Eldorado | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109920200114-4Brusher91822.5 | Corbiere and Sons Contracting109920200114-4Brusher91822.5Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1099 | 20200114-4 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher being float moved to WF2; 1 FB, 1 SKD working from A067-A062; 1 BR working from A061-A064; |  |  | Eldorado | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109920200114-4Feller Buncher92160 | Corbiere and Sons Contracting109920200114-4Feller Buncher92160Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1099 | 20200114-4 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher being float moved to WF2; 1 FB, 1 SKD working from A067-A062; 1 BR working from A061-A064; |  |  | Eldorado | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109920200114-4Skidder 91539 | Corbiere and Sons Contracting109920200114-4Skidder 91539Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1099 | 20200114-4 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher being float moved to WF2; 1 FB, 1 SKD working from A067-A062; 1 BR working from A061-A064; |  |  | Eldorado | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109920200114-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting109920200114-4Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1099 | 20200114-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher being float moved to WF2; 1 FB, 1 SKD working from A067-A062; 1 BR working from A061-A064; |  |  | Eldorado | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109920200114-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting109920200114-4Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1099 | 20200114-4 | 53520101 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher being float moved to WF2; 1 FB, 1 SKD working from A067-A062; 1 BR working from A061-A064; |  |  | Eldorado | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109920200114-4Foreman6570 | Corbiere and Sons Contracting109920200114-4Foreman6570Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1099 | 20200114-4 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher being float moved to WF2; 1 FB, 1 SKD working from A067-A062; 1 BR working from A061-A064; |  |  | Eldorado | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109920200114-4L.O.A.3630 | Corbiere and Sons Contracting109920200114-4L.O.A.3630Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1099 | 20200114-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher being float moved to WF2; 1 FB, 1 SKD working from A067-A062; 1 BR working from A061-A064; |  |  | Eldorado | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109920200114-4L.O.A.2420 | Corbiere and Sons Contracting109920200114-4L.O.A.2420Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1099 | 20200114-4 | 53520101 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher being float moved to WF2; 1 FB, 1 SKD working from A067-A062; 1 BR working from A061-A064; |  |  | Eldorado | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109920200114-4Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting109920200114-4Operator - Principle - After Jan 10221650Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1099 | 20200114-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Brusher being float moved to WF2; 1 FB, 1 SKD working from A067-A062; 1 BR working from A061-A064; |  |  | Eldorado | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting109920200114-4Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting109920200114-4Operator - Principle - After Jan 10221650Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1100 | 20200114-5 | 53510111 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 18 | Dynamic | 103.84 | 0 |  |  | 2492.1 | 323.973 | 2816.073 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road Building from A073-A074 and from A077-A078; Building Rd. from A064-A065 and winter access maintenance from A061-A065; |  |  | Eldorado | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110020200114-5Excavator - 30 ton- After Jan 10182492.1 | Corbiere and Sons Contracting110020200114-5Excavator - 30 ton- After Jan 10182492.1Inv#007-R01 | [5 empty] | 1 | 2492.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1100 | 20200114-5 | 53510111 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road Building from A073-A074 and from A077-A078; Building Rd. from A064-A065 and winter access maintenance from A061-A065; |  |  | Eldorado | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110020200114-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting110020200114-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#007-R01 | [5 empty] | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1100 | 20200114-5 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road Building from A073-A074 and from A077-A078; Building Rd. from A064-A065 and winter access maintenance from A061-A065; |  |  | Eldorado | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110020200114-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting110020200114-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#007-R01 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1100 | 20200114-5 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 9.5 | Dynamic | 64.79 | 0 |  |  | 820.61 | 106.6793 | 927.2893 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road Building from A073-A074 and from A077-A078; Building Rd. from A064-A065 and winter access maintenance from A061-A065; |  |  | Eldorado | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110020200114-5Sander Truck - Forestry- After Jan 109.5820.61 | Corbiere and Sons Contracting110020200114-5Sander Truck - Forestry- After Jan 109.5820.61Inv#007-R01 | [5 empty] | 1 | 820.61 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1100 | 20200114-5 | 53510111 | Access | 0 | Driver - AZ | 70 | 9.5 | HR |  |  | 105 | 0 | 665 | 86.45 | 751.45 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road Building from A073-A074 and from A077-A078; Building Rd. from A064-A065 and winter access maintenance from A061-A065; |  |  | Eldorado | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110020200114-5Driver - AZ9.5665 | Corbiere and Sons Contracting110020200114-5Driver - AZ9.5665Inv#007-R01 | [5 empty] | 1 | 665 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1100 | 20200114-5 | 53510111 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road Building from A073-A074 and from A077-A078; Building Rd. from A064-A065 and winter access maintenance from A061-A065; |  |  | Eldorado | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110020200114-5L.O.A.4840 | Corbiere and Sons Contracting110020200114-5L.O.A.4840Inv#007-R01 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1100 | 20200114-5 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road Building from A073-A074 and from A077-A078; Building Rd. from A064-A065 and winter access maintenance from A061-A065; |  |  | Eldorado | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110020200114-5Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting110020200114-5Operator - Principle - After Jan 10332475Inv#007-R01 | [5 empty] | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1101 | 20200114-6 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A098; Grinding of Material at A114; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110120200114-6Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting110120200114-6Grinder - 4710 Peterson or equal95011.2Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1101 | 20200114-6 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A098; Grinding of Material at A114; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110120200114-6Log Loader91377 | Corbiere and Sons Contracting110120200114-6Log Loader91377Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1101 | 20200114-6 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A098; Grinding of Material at A114; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110120200114-6Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting110120200114-6Chainsaw and consumables- After Jan 103180Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1101 | 20200114-6 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A098; Grinding of Material at A114; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110120200114-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting110120200114-6Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1101 | 20200114-6 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A098; Grinding of Material at A114; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110120200114-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting110120200114-6Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1101 | 20200114-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A098; Grinding of Material at A114; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110120200114-6L.O.A.1210 | Corbiere and Sons Contracting110120200114-6L.O.A.1210Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1101 | 20200114-6 | 53520104 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A098; Grinding of Material at A114; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110120200114-6L.O.A.3630 | Corbiere and Sons Contracting110120200114-6L.O.A.3630Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1101 | 20200114-6 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A098; Grinding of Material at A114; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110120200114-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting110120200114-6Operator - Principle - After Jan 1011825Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1101 | 20200114-6 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A098; Grinding of Material at A114; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110120200114-6Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting110120200114-6Labourer - Specialized - After Jan 10332310Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1102 | 20200114-7 | 53510111 | Access | 0 | Dozer - D5 or equal- After Jan 10 | 80.93 | 3 | Dynamic | 60.7 | 0 |  |  | 242.79 | 31.5627 | 274.3527 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Building Winter Roads and clearing pads from A083-A085; Labourers cleaning tracks, moving signs, picking up garbage; Graders working across all access roads; Labourers flagging; Float moves. |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110220200114-7Dozer - D5 or equal- After Jan 103242.79 | Corbiere and Sons Contracting110220200114-7Dozer - D5 or equal- After Jan 103242.79Inv#007-R01 | [5 empty] | 1 | 242.79 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1102 | 20200114-7 | 53510111 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 110.22 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Building Winter Roads and clearing pads from A083-A085; Labourers cleaning tracks, moving signs, picking up garbage; Graders working across all access roads; Labourers flagging; Float moves. |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110220200114-7Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting110220200114-7Excavator - 36 ton- After Jan 10182645.28Inv#007-R01 | [5 empty] | 1 | 2645.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1102 | 20200114-7 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 18 | Dynamic | 95.24 | 0 |  |  | 2285.64 | 297.1332 | 2582.7732 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Building Winter Roads and clearing pads from A083-A085; Labourers cleaning tracks, moving signs, picking up garbage; Graders working across all access roads; Labourers flagging; Float moves. |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110220200114-7Grader - Cat 12 to 14 or equal- After Jan 10182285.64 | Corbiere and Sons Contracting110220200114-7Grader - Cat 12 to 14 or equal- After Jan 10182285.64Inv#007-R01 | [5 empty] | 1 | 2285.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1102 | 20200114-7 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Building Winter Roads and clearing pads from A083-A085; Labourers cleaning tracks, moving signs, picking up garbage; Graders working across all access roads; Labourers flagging; Float moves. |  |  | Wind Farm | 1 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110220200114-7Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting110220200114-7Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#007-R01 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1102 | 20200114-7 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 11 | Dynamic | 64.79 | 0 |  |  | 950.18 | 123.5234 | 1073.7034 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Building Winter Roads and clearing pads from A083-A085; Labourers cleaning tracks, moving signs, picking up garbage; Graders working across all access roads; Labourers flagging; Float moves. |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110220200114-7Sander Truck - Forestry- After Jan 1011950.18 | Corbiere and Sons Contracting110220200114-7Sander Truck - Forestry- After Jan 1011950.18Inv#007-R01 | [5 empty] | 1 | 950.18 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1102 | 20200114-7 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Building Winter Roads and clearing pads from A083-A085; Labourers cleaning tracks, moving signs, picking up garbage; Graders working across all access roads; Labourers flagging; Float moves. |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110220200114-7Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting110220200114-7Light Truck - Pick up- After Jan 1051218.75Inv#007-R01 | [5 empty] | 1 | 1218.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1102 | 20200114-7 | 53510111 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 20 | Dynamic | 91.79 | 0 |  |  | 2447.8 | 318.214 | 2766.014 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Building Winter Roads and clearing pads from A083-A085; Labourers cleaning tracks, moving signs, picking up garbage; Graders working across all access roads; Labourers flagging; Float moves. |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110220200114-7Tractor Trailer - 60 Ton- After Jan 10202447.8 | Corbiere and Sons Contracting110220200114-7Tractor Trailer - 60 Ton- After Jan 10202447.8Inv#007-R01 | [5 empty] | 1 | 2447.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1102 | 20200114-7 | 53510111 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Building Winter Roads and clearing pads from A083-A085; Labourers cleaning tracks, moving signs, picking up garbage; Graders working across all access roads; Labourers flagging; Float moves. |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110220200114-7Foreman121140 | Corbiere and Sons Contracting110220200114-7Foreman121140Inv#007-R01 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1102 | 20200114-7 | 53510111 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Building Winter Roads and clearing pads from A083-A085; Labourers cleaning tracks, moving signs, picking up garbage; Graders working across all access roads; Labourers flagging; Float moves. |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110220200114-7Foreman121140 | Corbiere and Sons Contracting110220200114-7Foreman121140Inv#007-R01 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1102 | 20200114-7 | 53510111 | Access | 0 | L.O.A. | 210 | 14 | DAY |  |  |  | 0 | 2940 | 382.2 | 3322.2 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Building Winter Roads and clearing pads from A083-A085; Labourers cleaning tracks, moving signs, picking up garbage; Graders working across all access roads; Labourers flagging; Float moves. |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110220200114-7L.O.A.142940 | Corbiere and Sons Contracting110220200114-7L.O.A.142940Inv#007-R01 | [5 empty] | 1 | 2940 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1102 | 20200114-7 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 77 | HR |  |  | 75 | 0 | 5775 | 750.75 | 6525.75 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Building Winter Roads and clearing pads from A083-A085; Labourers cleaning tracks, moving signs, picking up garbage; Graders working across all access roads; Labourers flagging; Float moves. |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110220200114-7Operator - Principle - After Jan 10775775 | Corbiere and Sons Contracting110220200114-7Operator - Principle - After Jan 10775775Inv#007-R01 | [5 empty] | 1 | 5775 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1102 | 20200114-7 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Building Winter Roads and clearing pads from A083-A085; Labourers cleaning tracks, moving signs, picking up garbage; Graders working across all access roads; Labourers flagging; Float moves. |  |  | Wind Farm | 1 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110220200114-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting110220200114-7Operator - Principle - After Jan 1011825Inv#007-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1102 | 20200114-7 | 53510111 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Building Winter Roads and clearing pads from A083-A085; Labourers cleaning tracks, moving signs, picking up garbage; Graders working across all access roads; Labourers flagging; Float moves. |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110220200114-7Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting110220200114-7Operator - Intermdiate - After Jan 1011770Inv#007-R01 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1102 | 20200114-7 | 53510111 | Access | 0 | Labourer - General - After Jan 10 | 60 | 33 | HR |  |  | 60 | 0 | 1980 | 257.4 | 2237.4 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Building Winter Roads and clearing pads from A083-A085; Labourers cleaning tracks, moving signs, picking up garbage; Graders working across all access roads; Labourers flagging; Float moves. |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110220200114-7Labourer - General - After Jan 10331980 | Corbiere and Sons Contracting110220200114-7Labourer - General - After Jan 10331980Inv#007-R01 | [5 empty] | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1104 | 20200114-9 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A118 to A122 |  |  | 20200114-9 | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110420200114-9Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting110420200114-9Chainsaw and consumables- After Jan 103180Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1104 | 20200114-9 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A118 to A122 |  |  | 20200114-9 | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110420200114-9Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting110420200114-9Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1104 | 20200114-9 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A118 to A122 |  |  | 20200114-9 | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110420200114-9Foreman121140 | Corbiere and Sons Contracting110420200114-9Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1104 | 20200114-9 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A118 to A122 |  |  | 20200114-9 | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110420200114-9L.O.A.4840 | Corbiere and Sons Contracting110420200114-9L.O.A.4840Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1104 | 20200114-9 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-01-14 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A118 to A122 |  |  | 20200114-9 | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting110420200114-9Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting110420200114-9Labourer - Specialized - After Jan 10332310Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1110 | 20200115-1 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2020-01-20 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting111020200115-1Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting111020200115-1Light Truck - Pick up- After Jan 1051218.75Inv#010 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1218.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1110 | 20200115-1 | 53510106 | Access | 0 | Project Manager | 110 | 12 | HR |  |  | 110 | 0 | 1320 | 171.6 | 1491.6 | 2020-01-20 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting111020200115-1Project Manager121320 | Corbiere and Sons Contracting111020200115-1Project Manager121320Inv#010 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1110 | 20200115-1 | 53510106 | Access | 0 | Superintendent | 105 | 12 | HR |  |  | 105 | 0 | 1260 | 163.8 | 1423.8 | 2020-01-20 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting111020200115-1Superintendent121260 | Corbiere and Sons Contracting111020200115-1Superintendent121260Inv#010 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1110 | 20200115-1 | 53510106 | Access | 0 | Project Coordinator | 80 | 12 | HR |  |  | 80 | 0 | 960 | 124.8 | 1084.8 | 2020-01-20 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting111020200115-1Project Coordinator12960 | Corbiere and Sons Contracting111020200115-1Project Coordinator12960Inv#010 |  | WF1-Access | WF1-Access |  | 0 | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1110 | 20200115-1 | 53510106 | Access | 0 | Safety Advisor | 85 | 12 | HR |  |  | 85 | 0 | 1020 | 132.6 | 1152.6 | 2020-01-20 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting111020200115-1Safety Advisor121020 | Corbiere and Sons Contracting111020200115-1Safety Advisor121020Inv#010 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1110 | 20200115-1 | 53510106 | Access | 0 | Site Administrator | 50 | 11 | HR |  |  | 50 | 0 | 550 | 71.5 | 621.5 | 2020-01-20 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting111020200115-1Site Administrator11550 | Corbiere and Sons Contracting111020200115-1Site Administrator11550Inv#010 |  | WF1-Access | WF1-Access |  | 0 | 1 | 550 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1110 | 20200115-1 | 53510106 | Access | 0 | Project Controls | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2020-01-20 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting111020200115-1Project Controls12840 | Corbiere and Sons Contracting111020200115-1Project Controls12840Inv#010 |  | WF1-Access | WF1-Access |  | 0 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1110 | 20200115-1 | 53510106 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-01-20 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting111020200115-1L.O.A.61260 | Corbiere and Sons Contracting111020200115-1L.O.A.61260Inv#010 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1119 | 20200115-10 | 53510106 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 110.22 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2020-01-20 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road Building from A132 to A134; |  |  | Fish Hatchery | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting111920200115-10Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting111920200115-10Excavator - 36 ton- After Jan 10182645.28Inv#010 |  | WF1-Access | WF1-Access |  | 0 | 1 | 2645.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1119 | 20200115-10 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-20 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road Building from A132 to A134; |  |  | Fish Hatchery | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting111920200115-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting111920200115-10Light Truck - Pick up- After Jan 102487.5Inv#010 |  | WF1-Access | WF1-Access |  | 0 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1119 | 20200115-10 | 53510106 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-20 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road Building from A132 to A134; |  |  | Fish Hatchery | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting111920200115-10L.O.A.2420 | Corbiere and Sons Contracting111920200115-10L.O.A.2420Inv#010 |  | WF1-Access | WF1-Access |  | 0 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1119 | 20200115-10 | 53510106 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-20 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road Building from A132 to A134; |  |  | Fish Hatchery | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting111920200115-10Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting111920200115-10Operator - Principle - After Jan 10221650Inv#010 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1161 | 20200115-16 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 14 | Dynamic | 98.61 | 0 |  |  | 1840.72 | 239.2936 | 2080.0136 | 2020-01-16 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Need to update the Cost Management line items to pull in actual costs to 9010 - DK | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | Clearing new access roads and mobilization into Wf6; Delay cuased by Landowners |  |  | Santoy Lake | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting116120200115-16Dozer D6 or equal- After Jan 10141840.72 | Corbiere and Sons Contracting116120200115-16Dozer D6 or equal- After Jan 10141840.72Inv#010 | [5 empty] | 1 | 1840.72 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1161 | 20200115-16 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-16 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Need to update the Cost Management line items to pull in actual costs to 9010 - DK | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | Clearing new access roads and mobilization into Wf6; Delay cuased by Landowners |  |  | Santoy Lake | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting116120200115-16Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting116120200115-16Light Truck - Pick up- After Jan 103731.25Inv#010 | [5 empty] | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1161 | 20200115-16 | 53510611 | Access | 0 | Operator - Principle | 75 | 15 | HR |  |  |  | 0 | 1125 | 146.25 | 1271.25 | 2020-01-16 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Need to update the Cost Management line items to pull in actual costs to 9010 - DK | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | Clearing new access roads and mobilization into Wf6; Delay cuased by Landowners |  |  | Santoy Lake | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting116120200115-16Operator - Principle151125 | Corbiere and Sons Contracting116120200115-16Operator - Principle151125Inv#010 | [5 empty] | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1161 | 20200115-16 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-16 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Need to update the Cost Management line items to pull in actual costs to 9010 - DK | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | Clearing new access roads and mobilization into Wf6; Delay cuased by Landowners |  |  | Santoy Lake | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting116120200115-16L.O.A.2420 | Corbiere and Sons Contracting116120200115-16L.O.A.2420Inv#010 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1111 | 20200115-2 | 53510106 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 74.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2020-01-20 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; Cole Corbeire ran for parts in Thunder Bay and Nipigon all day as lots was required for repairs |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting111120200115-2Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting111120200115-2Loader JD 524 to 624 or equal5495Inv#010 |  | WF1-Access | WF1-Access |  | 0 | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1111 | 20200115-2 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-20 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; Cole Corbeire ran for parts in Thunder Bay and Nipigon all day as lots was required for repairs |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting111120200115-2Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting111120200115-2Light Truck - Pick up- After Jan 101243.75Inv#010 |  | WF1-Access | WF1-Access |  | 0 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1111 | 20200115-2 | 53510106 | Access | 0 | Operator - Apprentice | 60 | 10 | HR |  |  | 60 | 0 | 600 | 78 | 678 | 2020-01-20 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; Cole Corbeire ran for parts in Thunder Bay and Nipigon all day as lots was required for repairs |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting111120200115-2Operator - Apprentice10600 | Corbiere and Sons Contracting111120200115-2Operator - Apprentice10600Inv#010 |  | WF1-Access | WF1-Access |  | 0 | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1111 | 20200115-2 | 53510106 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-20 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; Cole Corbeire ran for parts in Thunder Bay and Nipigon all day as lots was required for repairs |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting111120200115-2L.O.A.1210 | Corbiere and Sons Contracting111120200115-2L.O.A.1210Inv#010 |  | WF1-Access | WF1-Access |  | 0 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1111 | 20200115-2 | 53510106 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2020-01-20 | 1 | Inv#010 | 43906 | 87 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; Cole Corbeire ran for parts in Thunder Bay and Nipigon all day as lots was required for repairs |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting111120200115-2Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting111120200115-2Labourer - General - After Jan 1011660Inv#010 |  | WF1-Access | WF1-Access |  | 0 | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1112 | 20200115-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 5 | unit/man/day | 0 | 0 |  |  | 300 | 39 | 339 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A036 |  |  | Beck Road West | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111220200115-3Chainsaw and consumables- After Jan 105300 | Corbiere and Sons Contracting111220200115-3Chainsaw and consumables- After Jan 105300Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1112 | 20200115-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A036 |  |  | Beck Road West | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111220200115-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting111220200115-3Light Truck - Pick up- After Jan 102487.5Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1112 | 20200115-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A036 |  |  | Beck Road West | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111220200115-3Foreman121140 | Corbiere and Sons Contracting111220200115-3Foreman121140Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1112 | 20200115-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A036 |  |  | Beck Road West | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111220200115-3L.O.A.51050 | Corbiere and Sons Contracting111220200115-3L.O.A.51050Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1112 | 20200115-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 44 | HR |  |  | 70 | 0 | 3080 | 400.4 | 3480.4 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A036 |  |  | Beck Road West | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111220200115-3Labourer - Specialized - After Jan 10443080 | Corbiere and Sons Contracting111220200115-3Labourer - Specialized - After Jan 10443080Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 3080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1113 | 20200115-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Handfelling from A097; FB, SKD BR working from A061 to A067; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111320200115-4Brusher91822.5 | Corbiere and Sons Contracting111320200115-4Brusher91822.5Inv#010 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1113 | 20200115-4 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Handfelling from A097; FB, SKD BR working from A061 to A067; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111320200115-4Feller Buncher92160 | Corbiere and Sons Contracting111320200115-4Feller Buncher92160Inv#010 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1113 | 20200115-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Handfelling from A097; FB, SKD BR working from A061 to A067; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111320200115-4Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting111320200115-4Grinder - 4710 Peterson or equal95011.2Inv#010 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1113 | 20200115-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Handfelling from A097; FB, SKD BR working from A061 to A067; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111320200115-4Log Loader91377 | Corbiere and Sons Contracting111320200115-4Log Loader91377Inv#010 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1113 | 20200115-4 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Handfelling from A097; FB, SKD BR working from A061 to A067; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111320200115-4Skidder 91539 | Corbiere and Sons Contracting111320200115-4Skidder 91539Inv#010 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1113 | 20200115-4 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Handfelling from A097; FB, SKD BR working from A061 to A067; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111320200115-4Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting111320200115-4Chainsaw and consumables- After Jan 103180Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1113 | 20200115-4 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Handfelling from A097; FB, SKD BR working from A061 to A067; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111320200115-4Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting111320200115-4Light Truck - Pick up- After Jan 103731.25Inv#010 |  |  | WF1-Merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1113 | 20200115-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Handfelling from A097; FB, SKD BR working from A061 to A067; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111320200115-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting111320200115-4Light Truck - Pick up- After Jan 101243.75Inv#010 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1113 | 20200115-4 | 53520101 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Handfelling from A097; FB, SKD BR working from A061 to A067; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111320200115-4Foreman6570 | Corbiere and Sons Contracting111320200115-4Foreman6570Inv#010 |  |  | WF1-Merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1113 | 20200115-4 | 53520101 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Handfelling from A097; FB, SKD BR working from A061 to A067; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111320200115-4L.O.A.3630 | Corbiere and Sons Contracting111320200115-4L.O.A.3630Inv#010 |  |  | WF1-Merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1113 | 20200115-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Handfelling from A097; FB, SKD BR working from A061 to A067; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111320200115-4L.O.A.2420 | Corbiere and Sons Contracting111320200115-4L.O.A.2420Inv#010 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1113 | 20200115-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Handfelling from A097; FB, SKD BR working from A061 to A067; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111320200115-4L.O.A.3630 | Corbiere and Sons Contracting111320200115-4L.O.A.3630Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1113 | 20200115-4 | 53520101 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Handfelling from A097; FB, SKD BR working from A061 to A067; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111320200115-4Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting111320200115-4Operator - Principle - After Jan 10221650Inv#010 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1113 | 20200115-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Handfelling from A097; FB, SKD BR working from A061 to A067; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111320200115-4Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting111320200115-4Operator - Principle - After Jan 10221650Inv#010 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1113 | 20200115-4 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Handfelling from A097; FB, SKD BR working from A061 to A067; |  |  | Eldorado Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111320200115-4Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting111320200115-4Labourer - Specialized - After Jan 10332310Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1114 | 20200115-5 | 53510111 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 18 | Dynamic | 103.84 | 0 |  |  | 2492.1 | 323.973 | 2816.073 | 2020-01-15 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building from A077-A079 and from A072-A071; 1 DZ and 3 Exs Rd. Building from A065 to A066; |  |  | Eldorado Road | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting111420200115-5Excavator - 30 ton- After Jan 10182492.1 | Corbiere and Sons Contracting111420200115-5Excavator - 30 ton- After Jan 10182492.1Inv#007-R01 | [5 empty] | 1 | 2492.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1114 | 20200115-5 | 53510111 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-01-15 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building from A077-A079 and from A072-A071; 1 DZ and 3 Exs Rd. Building from A065 to A066; |  |  | Eldorado Road | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting111420200115-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting111420200115-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#007-R01 | [5 empty] | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1114 | 20200115-5 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-01-15 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building from A077-A079 and from A072-A071; 1 DZ and 3 Exs Rd. Building from A065 to A066; |  |  | Eldorado Road | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting111420200115-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting111420200115-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#007-R01 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1114 | 20200115-5 | 53510111 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-15 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building from A077-A079 and from A072-A071; 1 DZ and 3 Exs Rd. Building from A065 to A066; |  |  | Eldorado Road | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting111420200115-5L.O.A.3630 | Corbiere and Sons Contracting111420200115-5L.O.A.3630Inv#007-R01 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1114 | 20200115-5 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2020-01-15 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building from A077-A079 and from A072-A071; 1 DZ and 3 Exs Rd. Building from A065 to A066; |  |  | Eldorado Road | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting111420200115-5Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting111420200115-5Operator - Principle - After Jan 10332475Inv#007-R01 | [5 empty] | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1115 | 20200115-6 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A098; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111520200115-6Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting111520200115-6Grinder - 4710 Peterson or equal95011.2Inv#010 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1115 | 20200115-6 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A098; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111520200115-6Log Loader91377 | Corbiere and Sons Contracting111520200115-6Log Loader91377Inv#010 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1115 | 20200115-6 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A098; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111520200115-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting111520200115-6Light Truck - Pick up- After Jan 101243.75Inv#010 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1115 | 20200115-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A098; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111520200115-6L.O.A.1210 | Corbiere and Sons Contracting111520200115-6L.O.A.1210Inv#010 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1115 | 20200115-6 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A098; |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111520200115-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting111520200115-6Operator - Principle - After Jan 1011825Inv#010 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1116 | 20200115-7 | 53510111 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 110.22 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building and Maintenance from A083-A085; Labourers laying GEO; Fuelling, Cleaning Tracks, Graders working across all access roads, floats moves |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111620200115-7Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting111620200115-7Excavator - 36 ton- After Jan 10182645.28Inv#010 | [5 empty] | 1 | 2645.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1116 | 20200115-7 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 27 | Dynamic | 95.24 | 0 |  |  | 3428.46 | 445.6998 | 3874.1598 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building and Maintenance from A083-A085; Labourers laying GEO; Fuelling, Cleaning Tracks, Graders working across all access roads, floats moves |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111620200115-7Grader - Cat 12 to 14 or equal- After Jan 10273428.46 | Corbiere and Sons Contracting111620200115-7Grader - Cat 12 to 14 or equal- After Jan 10273428.46Inv#010 | [5 empty] | 1 | 3428.46 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1116 | 20200115-7 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 11 | Dynamic | 64.79 | 0 |  |  | 950.18 | 123.5234 | 1073.7034 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building and Maintenance from A083-A085; Labourers laying GEO; Fuelling, Cleaning Tracks, Graders working across all access roads, floats moves |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111620200115-7Sander Truck - Forestry- After Jan 1011950.18 | Corbiere and Sons Contracting111620200115-7Sander Truck - Forestry- After Jan 1011950.18Inv#010 | [5 empty] | 1 | 950.18 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1116 | 20200115-7 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building and Maintenance from A083-A085; Labourers laying GEO; Fuelling, Cleaning Tracks, Graders working across all access roads, floats moves |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111620200115-7Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting111620200115-7Light Truck - Pick up- After Jan 1051218.75Inv#010 | [5 empty] | 1 | 1218.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1116 | 20200115-7 | 53510111 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 20 | Dynamic | 91.79 | 0 |  |  | 2447.8 | 318.214 | 2766.014 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building and Maintenance from A083-A085; Labourers laying GEO; Fuelling, Cleaning Tracks, Graders working across all access roads, floats moves |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111620200115-7Tractor Trailer - 60 Ton- After Jan 10202447.8 | Corbiere and Sons Contracting111620200115-7Tractor Trailer - 60 Ton- After Jan 10202447.8Inv#010 | [5 empty] | 1 | 2447.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1116 | 20200115-7 | 53510111 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building and Maintenance from A083-A085; Labourers laying GEO; Fuelling, Cleaning Tracks, Graders working across all access roads, floats moves |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111620200115-7Foreman121140 | Corbiere and Sons Contracting111620200115-7Foreman121140Inv#010 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1116 | 20200115-7 | 53510111 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building and Maintenance from A083-A085; Labourers laying GEO; Fuelling, Cleaning Tracks, Graders working across all access roads, floats moves |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111620200115-7Foreman121140 | Corbiere and Sons Contracting111620200115-7Foreman121140Inv#010 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1116 | 20200115-7 | 53510111 | Access | 0 | L.O.A. | 210 | 14 | DAY |  |  |  | 0 | 2940 | 382.2 | 3322.2 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building and Maintenance from A083-A085; Labourers laying GEO; Fuelling, Cleaning Tracks, Graders working across all access roads, floats moves |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111620200115-7L.O.A.142940 | Corbiere and Sons Contracting111620200115-7L.O.A.142940Inv#010 | [5 empty] | 1 | 2940 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1116 | 20200115-7 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 77 | HR |  |  | 75 | 0 | 5775 | 750.75 | 6525.75 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building and Maintenance from A083-A085; Labourers laying GEO; Fuelling, Cleaning Tracks, Graders working across all access roads, floats moves |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111620200115-7Operator - Principle - After Jan 10775775 | Corbiere and Sons Contracting111620200115-7Operator - Principle - After Jan 10775775Inv#010 | [5 empty] | 1 | 5775 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1116 | 20200115-7 | 53510111 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building and Maintenance from A083-A085; Labourers laying GEO; Fuelling, Cleaning Tracks, Graders working across all access roads, floats moves |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111620200115-7Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting111620200115-7Operator - Intermdiate - After Jan 1011770Inv#010 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1116 | 20200115-7 | 53510111 | Access | 0 | Labourer - General - After Jan 10 | 60 | 44 | HR |  |  | 60 | 0 | 2640 | 343.2 | 2983.2 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building and Maintenance from A083-A085; Labourers laying GEO; Fuelling, Cleaning Tracks, Graders working across all access roads, floats moves |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111620200115-7Labourer - General - After Jan 10442640 | Corbiere and Sons Contracting111620200115-7Labourer - General - After Jan 10442640Inv#010 | [5 empty] | 1 | 2640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1117 | 20200115-8 | 53510106 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road Building from A122 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111720200115-8Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting111720200115-8Excavator - 36 ton- After Jan 1091322.64Inv#010 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1117 | 20200115-8 | 53510106 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road Building from A122 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111720200115-8Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting111720200115-8Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#010 |  | WF1-Access | WF1-Access |  | 0 | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1117 | 20200115-8 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road Building from A122 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111720200115-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting111720200115-8Light Truck - Pick up- After Jan 101243.75Inv#010 |  | WF1-Access | WF1-Access |  | 0 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1117 | 20200115-8 | 53510106 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road Building from A122 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111720200115-8L.O.A.1210 | Corbiere and Sons Contracting111720200115-8L.O.A.1210Inv#010 |  | WF1-Access | WF1-Access |  | 0 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1117 | 20200115-8 | 53510106 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-15 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road Building from A122 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting111720200115-8Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting111720200115-8Operator - Principle - After Jan 1011825Inv#010 |  | WF1-Access | WF1-Access |  | 0 | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1118 | 20200115-9 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-20 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A123; |  |  | Wolf Lake Road | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting111820200115-9Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting111820200115-9Chainsaw and consumables- After Jan 103180Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1118 | 20200115-9 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-20 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A123; |  |  | Wolf Lake Road | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting111820200115-9Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting111820200115-9Light Truck - Pick up- After Jan 102487.5Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1118 | 20200115-9 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-20 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A123; |  |  | Wolf Lake Road | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting111820200115-9Foreman121140 | Corbiere and Sons Contracting111820200115-9Foreman121140Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1118 | 20200115-9 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-20 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A123; |  |  | Wolf Lake Road | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting111820200115-9L.O.A.4840 | Corbiere and Sons Contracting111820200115-9L.O.A.4840Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1118 | 20200115-9 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-01-20 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A123; |  |  | Wolf Lake Road | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting111820200115-9Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting111820200115-9Labourer - Specialized - After Jan 10332310Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1125 | 20200116-1 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting112520200116-1Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting112520200116-1Light Truck - Pick up- After Jan 1051218.75Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1218.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1125 | 20200116-1 | 53510106 | Access | 0 | Project Manager | 110 | 12 | HR |  |  | 110 | 0 | 1320 | 171.6 | 1491.6 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting112520200116-1Project Manager121320 | Corbiere and Sons Contracting112520200116-1Project Manager121320Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1125 | 20200116-1 | 53510106 | Access | 0 | Superintendent | 105 | 12 | HR |  |  | 105 | 0 | 1260 | 163.8 | 1423.8 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting112520200116-1Superintendent121260 | Corbiere and Sons Contracting112520200116-1Superintendent121260Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1125 | 20200116-1 | 53510106 | Access | 0 | Project Coordinator | 80 | 12 | HR |  |  | 80 | 0 | 960 | 124.8 | 1084.8 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting112520200116-1Project Coordinator12960 | Corbiere and Sons Contracting112520200116-1Project Coordinator12960Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1125 | 20200116-1 | 53510106 | Access | 0 | Safety Advisor | 85 | 12 | HR |  |  | 85 | 0 | 1020 | 132.6 | 1152.6 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting112520200116-1Safety Advisor121020 | Corbiere and Sons Contracting112520200116-1Safety Advisor121020Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1125 | 20200116-1 | 53510106 | Access | 0 | Site Administrator | 50 | 11 | HR |  |  | 50 | 0 | 550 | 71.5 | 621.5 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting112520200116-1Site Administrator11550 | Corbiere and Sons Contracting112520200116-1Site Administrator11550Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 550 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1125 | 20200116-1 | 53510106 | Access | 0 | Project Controls | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting112520200116-1Project Controls12840 | Corbiere and Sons Contracting112520200116-1Project Controls12840Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1125 | 20200116-1 | 53510106 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting112520200116-1L.O.A.61260 | Corbiere and Sons Contracting112520200116-1L.O.A.61260Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1182 | 20200116-15-R1 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 14 | Dynamic | 98.61 | 0 |  |  | 1840.72 | 239.2936 | 2080.0136 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | See LEM for Highlighted 9010 code breakdown | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | DZ's creating access raods, mobilization of equipment: Labourers doing traffic control, delay caused by landowner and coded under 9010 |  |  | Santoy Lake | 0 |  | Land Owner delay | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting118220200116-15-R1Dozer D6 or equal- After Jan 10141840.72 | Corbiere and Sons Contracting118220200116-15-R1Dozer D6 or equal- After Jan 10141840.72Inv#007-R01 | [5 empty] | 1 | 1840.72 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1182 | 20200116-15-R1 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | See LEM for Highlighted 9010 code breakdown | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | DZ's creating access raods, mobilization of equipment: Labourers doing traffic control, delay caused by landowner and coded under 9010 |  |  | Santoy Lake | 0 |  | Land Owner delay | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting118220200116-15-R1Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting118220200116-15-R1Light Truck - Pick up- After Jan 103731.25Inv#007-R01 | [5 empty] | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1182 | 20200116-15-R1 | 53510611 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | See LEM for Highlighted 9010 code breakdown | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | DZ's creating access raods, mobilization of equipment: Labourers doing traffic control, delay caused by landowner and coded under 9010 |  |  | Santoy Lake | 0 |  | Land Owner delay | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting118220200116-15-R1Foreman121140 | Corbiere and Sons Contracting118220200116-15-R1Foreman121140Inv#007-R01 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1182 | 20200116-15-R1 | 53510611 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  |  | 1050 | 136.5 | 1186.5 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | See LEM for Highlighted 9010 code breakdown | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | DZ's creating access raods, mobilization of equipment: Labourers doing traffic control, delay caused by landowner and coded under 9010 |  |  | Santoy Lake | 0 |  | Land Owner delay | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting118220200116-15-R1L.O.A.51050 | Corbiere and Sons Contracting118220200116-15-R1L.O.A.51050Inv#007-R01 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1182 | 20200116-15-R1 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 15 | HR |  |  | 75 | 0 | 1125 | 146.25 | 1271.25 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | See LEM for Highlighted 9010 code breakdown | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | DZ's creating access raods, mobilization of equipment: Labourers doing traffic control, delay caused by landowner and coded under 9010 |  |  | Santoy Lake | 0 |  | Land Owner delay | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting118220200116-15-R1Operator - Principle - After Jan 10151125 | Corbiere and Sons Contracting118220200116-15-R1Operator - Principle - After Jan 10151125Inv#007-R01 | [5 empty] | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1182 | 20200116-15-R1 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 10 | HR |  |  | 60 | 0 | 600 | 78 | 678 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | See LEM for Highlighted 9010 code breakdown | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | DZ's creating access raods, mobilization of equipment: Labourers doing traffic control, delay caused by landowner and coded under 9010 |  |  | Santoy Lake | 0 |  | Land Owner delay | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting118220200116-15-R1Labourer - General - After Jan 1010600 | Corbiere and Sons Contracting118220200116-15-R1Labourer - General - After Jan 1010600Inv#007-R01 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1126 | 20200116-2 | 53510106 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 74.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; Cole Corbeire ran for parts in Thunder Bay and Nipigon all day as lots was required for repairs; |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting112620200116-2Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting112620200116-2Loader JD 524 to 624 or equal5495Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1126 | 20200116-2 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; Cole Corbeire ran for parts in Thunder Bay and Nipigon all day as lots was required for repairs; |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting112620200116-2Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting112620200116-2Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1126 | 20200116-2 | 53510106 | Access | 0 | Operator - Apprentice | 60 | 10 | HR |  |  | 60 | 0 | 600 | 78 | 678 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; Cole Corbeire ran for parts in Thunder Bay and Nipigon all day as lots was required for repairs; |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting112620200116-2Operator - Apprentice10600 | Corbiere and Sons Contracting112620200116-2Operator - Apprentice10600Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1127 | 20200116-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 4 | unit/man/day | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling at A036; |  |  | Beck Road West | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112720200116-3Chainsaw and consumables- After Jan 104240 | Corbiere and Sons Contracting112720200116-3Chainsaw and consumables- After Jan 104240Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1127 | 20200116-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling at A036; |  |  | Beck Road West | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112720200116-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting112720200116-3Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1127 | 20200116-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling at A036; |  |  | Beck Road West | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112720200116-3Foreman121140 | Corbiere and Sons Contracting112720200116-3Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1127 | 20200116-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling at A036; |  |  | Beck Road West | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112720200116-3L.O.A.51050 | Corbiere and Sons Contracting112720200116-3L.O.A.51050Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1127 | 20200116-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 44 | HR |  |  | 70 | 0 | 3080 | 400.4 | 3480.4 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling at A036; |  |  | Beck Road West | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112720200116-3Labourer - Specialized - After Jan 10443080 | Corbiere and Sons Contracting112720200116-3Labourer - Specialized - After Jan 10443080Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 3080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1128 | 20200116-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Hazzard tree clearing with no mention of that type of work being done. |  | Approved |  |  | Grinding of Material from A061; Fb and SKD finishing up and being mobbed to A071-A072; 1 BR working from A064-A065; Float Truck moving clearing equipment; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112820200116-4Brusher91822.5 | Corbiere and Sons Contracting112820200116-4Brusher91822.5Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1128 | 20200116-4 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 3 | HR | 180 | 0 |  |  | 720 | 93.6 | 813.6 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Hazzard tree clearing with no mention of that type of work being done. |  | Approved |  |  | Grinding of Material from A061; Fb and SKD finishing up and being mobbed to A071-A072; 1 BR working from A064-A065; Float Truck moving clearing equipment; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112820200116-4Feller Buncher3720 | Corbiere and Sons Contracting112820200116-4Feller Buncher3720Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1128 | 20200116-4 | 53520107 | Clearing | 0 | Feller Buncher | 240 | 6 | HR | 180 | 0 |  |  | 1440 | 187.2 | 1627.2 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  | Hazzard tree clearing with no mention of that type of work being done. |  | Approved |  |  | Grinding of Material from A061; Fb and SKD finishing up and being mobbed to A071-A072; 1 BR working from A064-A065; Float Truck moving clearing equipment; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112820200116-4Feller Buncher61440 | Corbiere and Sons Contracting112820200116-4Feller Buncher61440Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 1440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1128 | 20200116-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Hazzard tree clearing with no mention of that type of work being done. |  | Approved |  |  | Grinding of Material from A061; Fb and SKD finishing up and being mobbed to A071-A072; 1 BR working from A064-A065; Float Truck moving clearing equipment; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112820200116-4Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting112820200116-4Grinder - 4710 Peterson or equal95011.2Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1128 | 20200116-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Hazzard tree clearing with no mention of that type of work being done. |  | Approved |  |  | Grinding of Material from A061; Fb and SKD finishing up and being mobbed to A071-A072; 1 BR working from A064-A065; Float Truck moving clearing equipment; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112820200116-4Log Loader91377 | Corbiere and Sons Contracting112820200116-4Log Loader91377Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1128 | 20200116-4 | 53520101 | Clearing | 0 | Skidder | 171 | 1 | HR | 128.25 | 0 |  |  | 171 | 22.23 | 193.23 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Hazzard tree clearing with no mention of that type of work being done. |  | Approved |  |  | Grinding of Material from A061; Fb and SKD finishing up and being mobbed to A071-A072; 1 BR working from A064-A065; Float Truck moving clearing equipment; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112820200116-4Skidder 1171 | Corbiere and Sons Contracting112820200116-4Skidder 1171Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 171 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1128 | 20200116-4 | 53520107 | Clearing | 0 | Skidder | 171 | 8 | HR | 128.25 | 0 |  |  | 1368 | 177.84 | 1545.84 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  | Hazzard tree clearing with no mention of that type of work being done. |  | Approved |  |  | Grinding of Material from A061; Fb and SKD finishing up and being mobbed to A071-A072; 1 BR working from A064-A065; Float Truck moving clearing equipment; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112820200116-4Skidder 81368 | Corbiere and Sons Contracting112820200116-4Skidder 81368Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 1368 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1128 | 20200116-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Hazzard tree clearing with no mention of that type of work being done. |  | Approved |  |  | Grinding of Material from A061; Fb and SKD finishing up and being mobbed to A071-A072; 1 BR working from A064-A065; Float Truck moving clearing equipment; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112820200116-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting112820200116-4Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1128 | 20200116-4 | 53520107 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  | Hazzard tree clearing with no mention of that type of work being done. |  | Approved |  |  | Grinding of Material from A061; Fb and SKD finishing up and being mobbed to A071-A072; 1 BR working from A064-A065; Float Truck moving clearing equipment; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112820200116-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting112820200116-4Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1128 | 20200116-4 | 53520107 | Clearing | 0 | Tractor Trailer - 50 Ton- After Jan 10 | 111.75 | 12 | Dynamic | 83.81 | 0 |  |  | 1341 | 174.33 | 1515.33 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  | Hazzard tree clearing with no mention of that type of work being done. |  | Approved |  |  | Grinding of Material from A061; Fb and SKD finishing up and being mobbed to A071-A072; 1 BR working from A064-A065; Float Truck moving clearing equipment; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112820200116-4Tractor Trailer - 50 Ton- After Jan 10121341 | Corbiere and Sons Contracting112820200116-4Tractor Trailer - 50 Ton- After Jan 10121341Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 1341 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1128 | 20200116-4 | 53520102 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Hazzard tree clearing with no mention of that type of work being done. |  | Approved |  |  | Grinding of Material from A061; Fb and SKD finishing up and being mobbed to A071-A072; 1 BR working from A064-A065; Float Truck moving clearing equipment; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112820200116-4Foreman6570 | Corbiere and Sons Contracting112820200116-4Foreman6570Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1128 | 20200116-4 | 53520107 | Clearing | 0 | Driver - AZ | 70 | 12 | HR |  |  | 105 | 0 | 840 | 109.2 | 949.2 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  | Hazzard tree clearing with no mention of that type of work being done. |  | Approved |  |  | Grinding of Material from A061; Fb and SKD finishing up and being mobbed to A071-A072; 1 BR working from A064-A065; Float Truck moving clearing equipment; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112820200116-4Driver - AZ12840 | Corbiere and Sons Contracting112820200116-4Driver - AZ12840Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1128 | 20200116-4 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Hazzard tree clearing with no mention of that type of work being done. |  | Approved |  |  | Grinding of Material from A061; Fb and SKD finishing up and being mobbed to A071-A072; 1 BR working from A064-A065; Float Truck moving clearing equipment; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112820200116-4L.O.A.2420 | Corbiere and Sons Contracting112820200116-4L.O.A.2420Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1128 | 20200116-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Hazzard tree clearing with no mention of that type of work being done. |  | Approved |  |  | Grinding of Material from A061; Fb and SKD finishing up and being mobbed to A071-A072; 1 BR working from A064-A065; Float Truck moving clearing equipment; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112820200116-4L.O.A.3630 | Corbiere and Sons Contracting112820200116-4L.O.A.3630Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1128 | 20200116-4 | 53520107 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  | Hazzard tree clearing with no mention of that type of work being done. |  | Approved |  |  | Grinding of Material from A061; Fb and SKD finishing up and being mobbed to A071-A072; 1 BR working from A064-A065; Float Truck moving clearing equipment; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112820200116-4L.O.A.2420 | Corbiere and Sons Contracting112820200116-4L.O.A.2420Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1128 | 20200116-4 | 53520101 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Hazzard tree clearing with no mention of that type of work being done. |  | Approved |  |  | Grinding of Material from A061; Fb and SKD finishing up and being mobbed to A071-A072; 1 BR working from A064-A065; Float Truck moving clearing equipment; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112820200116-4Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting112820200116-4Operator - Principle - After Jan 104300Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1128 | 20200116-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Hazzard tree clearing with no mention of that type of work being done. |  | Approved |  |  | Grinding of Material from A061; Fb and SKD finishing up and being mobbed to A071-A072; 1 BR working from A064-A065; Float Truck moving clearing equipment; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112820200116-4Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting112820200116-4Operator - Principle - After Jan 10221650Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1128 | 20200116-4 | 53520107 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 18 | HR |  |  | 75 | 0 | 1350 | 175.5 | 1525.5 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  | Hazzard tree clearing with no mention of that type of work being done. |  | Approved |  |  | Grinding of Material from A061; Fb and SKD finishing up and being mobbed to A071-A072; 1 BR working from A064-A065; Float Truck moving clearing equipment; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112820200116-4Operator - Principle - After Jan 10181350 | Corbiere and Sons Contracting112820200116-4Operator - Principle - After Jan 10181350Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1128 | 20200116-4 | 53520107 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  | Hazzard tree clearing with no mention of that type of work being done. |  | Approved |  |  | Grinding of Material from A061; Fb and SKD finishing up and being mobbed to A071-A072; 1 BR working from A064-A065; Float Truck moving clearing equipment; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112820200116-4Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting112820200116-4Labourer - General - After Jan 1011660Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1129 | 20200116-5 | 53510106 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building from A078-A079 and from A071-A070; 3 Exs, 1 Dz, and grader working between A065 and A070 |  |  | Eldorado | 1 |  |  | 37 | 43889 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112920200116-5Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting112920200116-5Excavator - 30 ton- After Jan 1091246.05Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1129 | 20200116-5 | 53510106 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building from A078-A079 and from A071-A070; 3 Exs, 1 Dz, and grader working between A065 and A070 |  |  | Eldorado | 1 |  |  | 37 | 43889 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112920200116-5Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting112920200116-5Excavator - 30 ton- After Jan 1091246.05Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1129 | 20200116-5 | 53510106 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building from A078-A079 and from A071-A070; 3 Exs, 1 Dz, and grader working between A065 and A070 |  |  | Eldorado | 1 |  |  | 37 | 43889 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112920200116-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting112920200116-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1129 | 20200116-5 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building from A078-A079 and from A071-A070; 3 Exs, 1 Dz, and grader working between A065 and A070 |  |  | Eldorado | 0 |  |  | 37 | 43889 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112920200116-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting112920200116-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#007-R01 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1129 | 20200116-5 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 10 | Dynamic | 64.79 | 0 |  |  | 863.8 | 112.294 | 976.094 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building from A078-A079 and from A071-A070; 3 Exs, 1 Dz, and grader working between A065 and A070 |  |  | Eldorado | 0 |  |  | 37 | 43889 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112920200116-5Sander Truck - Forestry- After Jan 1010863.8 | Corbiere and Sons Contracting112920200116-5Sander Truck - Forestry- After Jan 1010863.8Inv#007-R01 | [5 empty] | 1 | 863.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1129 | 20200116-5 | 53510111 | Access | 0 | Driver - AZ | 70 | 10 | HR |  |  | 105 | 0 | 700 | 91 | 791 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building from A078-A079 and from A071-A070; 3 Exs, 1 Dz, and grader working between A065 and A070 |  |  | Eldorado | 0 |  |  | 37 | 43889 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112920200116-5Driver - AZ10700 | Corbiere and Sons Contracting112920200116-5Driver - AZ10700Inv#007-R01 | [5 empty] | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1129 | 20200116-5 | 53510106 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building from A078-A079 and from A071-A070; 3 Exs, 1 Dz, and grader working between A065 and A070 |  |  | Eldorado | 0 |  |  | 37 | 43889 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112920200116-5L.O.A.2420 | Corbiere and Sons Contracting112920200116-5L.O.A.2420Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1129 | 20200116-5 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building from A078-A079 and from A071-A070; 3 Exs, 1 Dz, and grader working between A065 and A070 |  |  | Eldorado | 0 |  |  | 37 | 43889 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112920200116-5L.O.A.2420 | Corbiere and Sons Contracting112920200116-5L.O.A.2420Inv#007-R01 |  | WF1-Access |  |  | 0 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1129 | 20200116-5 | 53510106 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building from A078-A079 and from A071-A070; 3 Exs, 1 Dz, and grader working between A065 and A070 |  |  | Eldorado | 1 |  |  | 37 | 43889 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112920200116-5Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting112920200116-5Operator - Principle - After Jan 10221650Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1129 | 20200116-5 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building from A078-A079 and from A071-A070; 3 Exs, 1 Dz, and grader working between A065 and A070 |  |  | Eldorado | 0 |  |  | 37 | 43889 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting112920200116-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting112920200116-5Operator - Principle - After Jan 1011825Inv#007-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1130 | 20200116-6 | 53520104 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A098; Grinding of Material at A094 |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113020200116-6Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting113020200116-6Grinder - 4710 Peterson or equal95011.2Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1130 | 20200116-6 | 53520104 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A098; Grinding of Material at A094 |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113020200116-6Log Loader91377 | Corbiere and Sons Contracting113020200116-6Log Loader91377Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1130 | 20200116-6 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A098; Grinding of Material at A094 |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113020200116-6Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting113020200116-6Chainsaw and consumables- After Jan 103180Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1130 | 20200116-6 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A098; Grinding of Material at A094 |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113020200116-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting113020200116-6Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1130 | 20200116-6 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A098; Grinding of Material at A094 |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113020200116-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting113020200116-6Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1130 | 20200116-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A098; Grinding of Material at A094 |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113020200116-6L.O.A.1210 | Corbiere and Sons Contracting113020200116-6L.O.A.1210Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1130 | 20200116-6 | 53520104 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A098; Grinding of Material at A094 |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113020200116-6L.O.A.3630 | Corbiere and Sons Contracting113020200116-6L.O.A.3630Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1130 | 20200116-6 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A098; Grinding of Material at A094 |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113020200116-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting113020200116-6Operator - Principle - After Jan 1011825Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1130 | 20200116-6 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A098; Grinding of Material at A094 |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113020200116-6Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting113020200116-6Labourer - Specialized - After Jan 10332310Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1131 | 20200116-7 | 53510111 | Access | 0 | Dozer - D5 or equal- After Jan 10 | 80.93 | 6 | Dynamic | 60.7 | 0 |  |  | 485.58 | 63.1254 | 548.7054 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter maintenance from A085-A089 and from A115-A117; Labourers escorting equipment and cleaning tracks; Graders and Sander Truck working across all access roads |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113120200116-7Dozer - D5 or equal- After Jan 106485.58 | Corbiere and Sons Contracting113120200116-7Dozer - D5 or equal- After Jan 106485.58Inv#007-R01 | [5 empty] | 1 | 485.58 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1131 | 20200116-7 | 53510111 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter maintenance from A085-A089 and from A115-A117; Labourers escorting equipment and cleaning tracks; Graders and Sander Truck working across all access roads |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113120200116-7Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting113120200116-7Dozer D6 or equal- After Jan 1091183.32Inv#007-R01 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1131 | 20200116-7 | 53510111 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 110.22 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter maintenance from A085-A089 and from A115-A117; Labourers escorting equipment and cleaning tracks; Graders and Sander Truck working across all access roads |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113120200116-7Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting113120200116-7Excavator - 36 ton- After Jan 10182645.28Inv#007-R01 | [5 empty] | 1 | 2645.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1131 | 20200116-7 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 25.5 | Dynamic | 95.24 | 0 |  |  | 3237.99 | 420.9387 | 3658.9287 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter maintenance from A085-A089 and from A115-A117; Labourers escorting equipment and cleaning tracks; Graders and Sander Truck working across all access roads |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113120200116-7Grader - Cat 12 to 14 or equal- After Jan 1025.53237.99 | Corbiere and Sons Contracting113120200116-7Grader - Cat 12 to 14 or equal- After Jan 1025.53237.99Inv#007-R01 | [5 empty] | 1 | 3237.99 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1131 | 20200116-7 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 11 | Dynamic | 64.79 | 0 |  |  | 950.18 | 123.5234 | 1073.7034 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter maintenance from A085-A089 and from A115-A117; Labourers escorting equipment and cleaning tracks; Graders and Sander Truck working across all access roads |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113120200116-7Sander Truck - Forestry- After Jan 1011950.18 | Corbiere and Sons Contracting113120200116-7Sander Truck - Forestry- After Jan 1011950.18Inv#007-R01 | [5 empty] | 1 | 950.18 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1131 | 20200116-7 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter maintenance from A085-A089 and from A115-A117; Labourers escorting equipment and cleaning tracks; Graders and Sander Truck working across all access roads |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113120200116-7Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting113120200116-7Light Truck - Pick up- After Jan 104975Inv#007-R01 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1131 | 20200116-7 | 53510111 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 10 | Dynamic | 91.79 | 0 |  |  | 1223.9 | 159.107 | 1383.007 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter maintenance from A085-A089 and from A115-A117; Labourers escorting equipment and cleaning tracks; Graders and Sander Truck working across all access roads |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113120200116-7Tractor Trailer - 60 Ton- After Jan 10101223.9 | Corbiere and Sons Contracting113120200116-7Tractor Trailer - 60 Ton- After Jan 10101223.9Inv#007-R01 | [5 empty] | 1 | 1223.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1131 | 20200116-7 | 53510111 | Access | 0 | Foreman | 95 | 24 | HR |  |  | 95 | 0 | 2280 | 296.4 | 2576.4 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter maintenance from A085-A089 and from A115-A117; Labourers escorting equipment and cleaning tracks; Graders and Sander Truck working across all access roads |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113120200116-7Foreman242280 | Corbiere and Sons Contracting113120200116-7Foreman242280Inv#007-R01 | [5 empty] | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1131 | 20200116-7 | 53510111 | Access | 0 | L.O.A. | 210 | 15 | DAY |  |  |  | 0 | 3150 | 409.5 | 3559.5 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter maintenance from A085-A089 and from A115-A117; Labourers escorting equipment and cleaning tracks; Graders and Sander Truck working across all access roads |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113120200116-7L.O.A.153150 | Corbiere and Sons Contracting113120200116-7L.O.A.153150Inv#007-R01 | [5 empty] | 1 | 3150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1131 | 20200116-7 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 85.5 | HR |  |  | 75 | 0 | 6412.5 | 833.625 | 7246.125 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter maintenance from A085-A089 and from A115-A117; Labourers escorting equipment and cleaning tracks; Graders and Sander Truck working across all access roads |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113120200116-7Operator - Principle - After Jan 1085.56412.5 | Corbiere and Sons Contracting113120200116-7Operator - Principle - After Jan 1085.56412.5Inv#007-R01 | [5 empty] | 1 | 6412.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1131 | 20200116-7 | 53510111 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter maintenance from A085-A089 and from A115-A117; Labourers escorting equipment and cleaning tracks; Graders and Sander Truck working across all access roads |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113120200116-7Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting113120200116-7Operator - Intermdiate - After Jan 1011770Inv#007-R01 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1131 | 20200116-7 | 53510111 | Access | 0 | Labourer - General - After Jan 10 | 60 | 41.5 | HR |  |  | 60 | 0 | 2490 | 323.7 | 2813.7 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter maintenance from A085-A089 and from A115-A117; Labourers escorting equipment and cleaning tracks; Graders and Sander Truck working across all access roads |  |  | Wind Farm | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113120200116-7Labourer - General - After Jan 1041.52490 | Corbiere and Sons Contracting113120200116-7Labourer - General - After Jan 1041.52490Inv#007-R01 | [5 empty] | 1 | 2490 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1132 | 20200116-8 | 53510106 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building from A123 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113220200116-8Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting113220200116-8Excavator - 36 ton- After Jan 105734.8Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1132 | 20200116-8 | 53510106 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building from A123 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113220200116-8Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting113220200116-8Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1132 | 20200116-8 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building from A123 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113220200116-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting113220200116-8Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1132 | 20200116-8 | 53510106 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building from A123 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113220200116-8L.O.A.1210 | Corbiere and Sons Contracting113220200116-8L.O.A.1210Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1132 | 20200116-8 | 53510106 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Rd. Building from A123 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113220200116-8Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting113220200116-8Operator - Principle - After Jan 105375Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1133 | 20200116-9 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A123; |  |  | Wolf Lake Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113320200116-9Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting113320200116-9Chainsaw and consumables- After Jan 103180Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1133 | 20200116-9 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A123; |  |  | Wolf Lake Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113320200116-9Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting113320200116-9Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1133 | 20200116-9 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A123; |  |  | Wolf Lake Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113320200116-9Foreman121140 | Corbiere and Sons Contracting113320200116-9Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1133 | 20200116-9 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A123; |  |  | Wolf Lake Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113320200116-9L.O.A.4840 | Corbiere and Sons Contracting113320200116-9L.O.A.4840Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1133 | 20200116-9 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-01-16 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A123; |  |  | Wolf Lake Road | 0 |  |  | 37 | 43858 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113320200116-9Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting113320200116-9Labourer - Specialized - After Jan 10332310Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1138 | 20200117-1 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113820200117-1Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting113820200117-1Light Truck - Pick up- After Jan 1051218.75Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1218.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1138 | 20200117-1 | 53510106 | Access | 0 | Project Manager | 110 | 12 | HR |  |  | 110 | 0 | 1320 | 171.6 | 1491.6 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113820200117-1Project Manager121320 | Corbiere and Sons Contracting113820200117-1Project Manager121320Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1138 | 20200117-1 | 53510106 | Access | 0 | Superintendent | 105 | 12 | HR |  |  | 105 | 0 | 1260 | 163.8 | 1423.8 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113820200117-1Superintendent121260 | Corbiere and Sons Contracting113820200117-1Superintendent121260Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1138 | 20200117-1 | 53510106 | Access | 0 | Project Coordinator | 80 | 12 | HR |  |  | 80 | 0 | 960 | 124.8 | 1084.8 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113820200117-1Project Coordinator12960 | Corbiere and Sons Contracting113820200117-1Project Coordinator12960Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1138 | 20200117-1 | 53510106 | Access | 0 | Safety Advisor | 85 | 12 | HR |  |  | 85 | 0 | 1020 | 132.6 | 1152.6 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113820200117-1Safety Advisor121020 | Corbiere and Sons Contracting113820200117-1Safety Advisor121020Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1138 | 20200117-1 | 53510106 | Access | 0 | Site Administrator | 50 | 11 | HR |  |  | 50 | 0 | 550 | 71.5 | 621.5 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113820200117-1Site Administrator11550 | Corbiere and Sons Contracting113820200117-1Site Administrator11550Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 550 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1138 | 20200117-1 | 53510106 | Access | 0 | Project Controls | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113820200117-1Project Controls12840 | Corbiere and Sons Contracting113820200117-1Project Controls12840Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1138 | 20200117-1 | 53510106 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Deena Kruper | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | 100 Wolf River Road, Dorion, ON | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting113820200117-1L.O.A.61260 | Corbiere and Sons Contracting113820200117-1L.O.A.61260Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1165 | 20200117-15 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing of access roads and mobilization |  |  | Santoy Lake Road | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting116520200117-15Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting116520200117-15Dozer D6 or equal- After Jan 105657.4Inv#007-R01 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1165 | 20200117-15 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing of access roads and mobilization |  |  | Santoy Lake Road | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting116520200117-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting116520200117-15Light Truck - Pick up- After Jan 101243.75Inv#007-R01 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1165 | 20200117-15 | 53510611 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing of access roads and mobilization |  |  | Santoy Lake Road | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting116520200117-15Foreman121140 | Corbiere and Sons Contracting116520200117-15Foreman121140Inv#007-R01 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1165 | 20200117-15 | 53510611 | Access | 0 | Operator - Principle | 75 | 7 | HR |  |  |  | 0 | 525 | 68.25 | 593.25 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing of access roads and mobilization |  |  | Santoy Lake Road | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting116520200117-15Operator - Principle7525 | Corbiere and Sons Contracting116520200117-15Operator - Principle7525Inv#007-R01 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1165 | 20200117-15 | 53510611 | Access | 0 | Operator - Principle | 75 | 8 | HR |  |  |  | 0 | 600 | 78 | 678 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing of access roads and mobilization |  |  | Santoy Lake Road | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting116520200117-15Operator - Principle8600 | Corbiere and Sons Contracting116520200117-15Operator - Principle8600Inv#007-R01 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1165 | 20200117-15 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing of access roads and mobilization |  |  | Santoy Lake Road | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting116520200117-15L.O.A.3630 | Corbiere and Sons Contracting116520200117-15L.O.A.3630Inv#007-R01 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1165 | 20200117-15 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 7 | HR |  |  | 60 | 0 | 420 | 54.6 | 474.6 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing of access roads and mobilization |  |  | Santoy Lake Road | 0 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting116520200117-15Labourer - General - After Jan 107420 | Corbiere and Sons Contracting116520200117-15Labourer - General - After Jan 107420Inv#007-R01 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1139 | 20200117-2 | 53510106 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 0.69411 | HR | 74.25 | 0 |  |  | 68.7167 | 8.9332 | 77.6499 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; |  |  | 100 Wolf River Road, Dorion, ON | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting113920200117-2Loader JD 524 to 624 or equal0.694108568.7167 | Corbiere and Sons Contracting113920200117-2Loader JD 524 to 624 or equal0.694108568.7167Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 68.7167 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1139 | 20200117-2 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 1.6271 | HR | 74.25 | 0 |  |  | 161.08 | 20.9404 | 182.0204 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; |  |  | 100 Wolf River Road, Dorion, ON | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting113920200117-2Loader JD 524 to 624 or equal1.6270711161.08 | Corbiere and Sons Contracting113920200117-2Loader JD 524 to 624 or equal1.6270711161.08Inv#007-R01 | [5 empty] | 1 | 161.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1139 | 20200117-2 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.3154 | HR | 74.25 | 0 |  |  | 31.2248 | 4.0592 | 35.284 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; |  |  | 100 Wolf River Road, Dorion, ON | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting113920200117-2Loader JD 524 to 624 or equal0.315401931.2248 | Corbiere and Sons Contracting113920200117-2Loader JD 524 to 624 or equal0.315401931.2248Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 31.2248 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1139 | 20200117-2 | 53520102 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 1.0602 | HR | 74.25 | 0 |  |  | 104.963 | 13.6452 | 118.6082 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; |  |  | 100 Wolf River Road, Dorion, ON | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting113920200117-2Loader JD 524 to 624 or equal1.0602324104.963 | Corbiere and Sons Contracting113920200117-2Loader JD 524 to 624 or equal1.0602324104.963Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 104.963 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1139 | 20200117-2 | 53520104 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.47583 | HR | 74.25 | 0 |  |  | 47.1067 | 6.1239 | 53.2306 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; |  |  | 100 Wolf River Road, Dorion, ON | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting113920200117-2Loader JD 524 to 624 or equal0.475825147.1067 | Corbiere and Sons Contracting113920200117-2Loader JD 524 to 624 or equal0.475825147.1067Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 47.1067 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1139 | 20200117-2 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.13882 | DAY | 182.81 | 0 |  |  | 33.8378 | 4.3989 | 38.2367 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; |  |  | 100 Wolf River Road, Dorion, ON | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting113920200117-2Light Truck - Pick up- After Jan 100.138821733.8378 | Corbiere and Sons Contracting113920200117-2Light Truck - Pick up- After Jan 100.138821733.8378Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 33.8378 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1139 | 20200117-2 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.32541 | DAY | 182.81 | 0 |  |  | 79.3197 | 10.3116 | 89.6313 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; |  |  | 100 Wolf River Road, Dorion, ON | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting113920200117-2Light Truck - Pick up- After Jan 100.325414279.3197 | Corbiere and Sons Contracting113920200117-2Light Truck - Pick up- After Jan 100.325414279.3197Inv#007-R01 | [5 empty] | 1 | 79.3197 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1139 | 20200117-2 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.06308 | DAY | 182.81 | 0 |  |  | 15.3758 | 1.9989 | 17.3747 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; |  |  | 100 Wolf River Road, Dorion, ON | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting113920200117-2Light Truck - Pick up- After Jan 100.063080415.3758 | Corbiere and Sons Contracting113920200117-2Light Truck - Pick up- After Jan 100.063080415.3758Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 15.3758 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1139 | 20200117-2 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.21205 | DAY | 182.81 | 0 |  |  | 51.6863 | 6.7192 | 58.4055 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; |  |  | 100 Wolf River Road, Dorion, ON | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting113920200117-2Light Truck - Pick up- After Jan 100.212046551.6863 | Corbiere and Sons Contracting113920200117-2Light Truck - Pick up- After Jan 100.212046551.6863Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 51.6863 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1139 | 20200117-2 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.095165 | DAY | 182.81 | 0 |  |  | 23.1965 | 3.0155 | 26.212 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; |  |  | 100 Wolf River Road, Dorion, ON | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting113920200117-2Light Truck - Pick up- After Jan 100.09516523.1965 | Corbiere and Sons Contracting113920200117-2Light Truck - Pick up- After Jan 100.09516523.1965Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 23.1965 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1139 | 20200117-2 | 53510106 | Access | 0 | Operator - Apprentice | 60 | 1.3882 | HR |  |  | 60 | 0 | 83.293 | 10.8281 | 94.1211 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; |  |  | 100 Wolf River Road, Dorion, ON | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting113920200117-2Operator - Apprentice1.388217183.293 | Corbiere and Sons Contracting113920200117-2Operator - Apprentice1.388217183.293Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 83.293 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1139 | 20200117-2 | 53510111 | Access | 0 | Operator - Apprentice | 60 | 3.2541 | HR |  |  | 60 | 0 | 195.2485 | 25.3823 | 220.6308 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; |  |  | 100 Wolf River Road, Dorion, ON | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting113920200117-2Operator - Apprentice3.2541422195.2485 | Corbiere and Sons Contracting113920200117-2Operator - Apprentice3.2541422195.2485Inv#007-R01 | [5 empty] | 1 | 195.2485 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1139 | 20200117-2 | 53520101 | Clearing | 0 | Operator - Apprentice | 60 | 0.6308 | HR |  |  | 60 | 0 | 37.8482 | 4.9203 | 42.7685 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; |  |  | 100 Wolf River Road, Dorion, ON | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting113920200117-2Operator - Apprentice0.630803837.8482 | Corbiere and Sons Contracting113920200117-2Operator - Apprentice0.630803837.8482Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 37.8482 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1139 | 20200117-2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 2.1205 | HR |  |  | 60 | 0 | 127.2279 | 16.5396 | 143.7675 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; |  |  | 100 Wolf River Road, Dorion, ON | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting113920200117-2Operator - Apprentice2.1204647127.2279 | Corbiere and Sons Contracting113920200117-2Operator - Apprentice2.1204647127.2279Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 127.2279 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1139 | 20200117-2 | 53520104 | Clearing | 0 | Operator - Apprentice | 60 | 0.95165 | HR |  |  | 60 | 0 | 57.099 | 7.4229 | 64.5219 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance; |  |  | 100 Wolf River Road, Dorion, ON | 1 |  |  | 40 | 43859 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting113920200117-2Operator - Apprentice0.951650257.099 | Corbiere and Sons Contracting113920200117-2Operator - Apprentice0.951650257.099Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 57.099 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1167 | 20200117-21 | 53520102 | Clearing | 0 | 3rd Party Charges | 1 | 852.5 | unit |  |  |  |  | 852.5 | 110.825 | 963.325 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Deena Kruper | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hired 3rd Party float to aid with float moves to get situated in new work fronts |  |  | Moves from WF1 to WF2-WF6 | 0 |  |  | 37 | 43857 | 20200112 | See below for ticket information |  |  |  | Harold Furlong | 01 | Corbiere and Sons Contracting116720200117-213rd Party Charges852.5852.5 | Corbiere and Sons Contracting116720200117-213rd Party Charges852.5852.5Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 852.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1140 | 20200117-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 5 | unit/man/day | 0 | 0 |  |  | 300 | 39 | 339 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A036; |  |  | Beck Road West | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting114020200117-3Chainsaw and consumables- After Jan 105300 | Corbiere and Sons Contracting114020200117-3Chainsaw and consumables- After Jan 105300Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1140 | 20200117-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A036; |  |  | Beck Road West | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting114020200117-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting114020200117-3Light Truck - Pick up- After Jan 103731.25Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1140 | 20200117-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A036; |  |  | Beck Road West | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting114020200117-3Foreman121140 | Corbiere and Sons Contracting114020200117-3Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1140 | 20200117-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A036; |  |  | Beck Road West | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting114020200117-3L.O.A.61260 | Corbiere and Sons Contracting114020200117-3L.O.A.61260Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1140 | 20200117-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 20 | HR |  |  | 70 | 0 | 1400 | 182 | 1582 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A036; |  |  | Beck Road West | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting114020200117-3Labourer - Specialized - After Jan 10201400 | Corbiere and Sons Contracting114020200117-3Labourer - Specialized - After Jan 10201400Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1142 | 20200117-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Brushing from A065-A066; 1 FB and SKD at A070-A071 |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114220200117-5Brusher91822.5 | Corbiere and Sons Contracting114220200117-5Brusher91822.5Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1142 | 20200117-5 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Brushing from A065-A066; 1 FB and SKD at A070-A071 |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114220200117-5Feller Buncher92160 | Corbiere and Sons Contracting114220200117-5Feller Buncher92160Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1142 | 20200117-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Brushing from A065-A066; 1 FB and SKD at A070-A071 |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114220200117-5Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting114220200117-5Grinder - 4710 Peterson or equal95011.2Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1142 | 20200117-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Brushing from A065-A066; 1 FB and SKD at A070-A071 |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114220200117-5Log Loader91377 | Corbiere and Sons Contracting114220200117-5Log Loader91377Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1142 | 20200117-5 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Brushing from A065-A066; 1 FB and SKD at A070-A071 |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114220200117-5Skidder 91539 | Corbiere and Sons Contracting114220200117-5Skidder 91539Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1142 | 20200117-5 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Brushing from A065-A066; 1 FB and SKD at A070-A071 |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114220200117-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting114220200117-5Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1142 | 20200117-5 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Brushing from A065-A066; 1 FB and SKD at A070-A071 |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114220200117-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting114220200117-5Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1142 | 20200117-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Brushing from A065-A066; 1 FB and SKD at A070-A071 |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114220200117-5L.O.A.2420 | Corbiere and Sons Contracting114220200117-5L.O.A.2420Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1142 | 20200117-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Brushing from A065-A066; 1 FB and SKD at A070-A071 |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114220200117-5L.O.A.2420 | Corbiere and Sons Contracting114220200117-5L.O.A.2420Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1142 | 20200117-5 | 53520101 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Brushing from A065-A066; 1 FB and SKD at A070-A071 |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114220200117-5Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting114220200117-5Operator - Principle - After Jan 10221650Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1142 | 20200117-5 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A061; Brushing from A065-A066; 1 FB and SKD at A070-A071 |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114220200117-5Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting114220200117-5Operator - Principle - After Jan 10221650Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1143 | 20200117-6 | 53510111 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter road maintenance from A071 and A079; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114320200117-6Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting114320200117-6Dozer D6 or equal- After Jan 1091183.32Inv#007-R01 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1143 | 20200117-6 | 53510107 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter road maintenance from A071 and A079; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114320200117-6Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting114320200117-6Excavator - 30 ton- After Jan 103415.35Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 415.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1143 | 20200117-6 | 53510111 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 18 | Dynamic | 103.84 | 0 |  |  | 2492.1 | 323.973 | 2816.073 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter road maintenance from A071 and A079; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114320200117-6Excavator - 30 ton- After Jan 10182492.1 | Corbiere and Sons Contracting114320200117-6Excavator - 30 ton- After Jan 10182492.1Inv#007-R01 | [5 empty] | 1 | 2492.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1143 | 20200117-6 | 53510107 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter road maintenance from A071 and A079; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114320200117-6Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting114320200117-6Excavator - 36 ton- After Jan 106881.76Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 881.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1143 | 20200117-6 | 53510107 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter road maintenance from A071 and A079; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114320200117-6Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting114320200117-6Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1143 | 20200117-6 | 53510107 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter road maintenance from A071 and A079; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114320200117-6Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting114320200117-6Excavator Thumb - 30 - 50 ton- After Jan 10673.26Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 73.26 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1143 | 20200117-6 | 53510111 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter road maintenance from A071 and A079; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114320200117-6Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting114320200117-6Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#007-R01 | [5 empty] | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1143 | 20200117-6 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter road maintenance from A071 and A079; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114320200117-6Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting114320200117-6Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#007-R01 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1143 | 20200117-6 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 7.5 | Dynamic | 64.79 | 0 |  |  | 647.85 | 84.2205 | 732.0705 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter road maintenance from A071 and A079; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114320200117-6Sander Truck - Forestry- After Jan 107.5647.85 | Corbiere and Sons Contracting114320200117-6Sander Truck - Forestry- After Jan 107.5647.85Inv#007-R01 | [5 empty] | 1 | 647.85 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1143 | 20200117-6 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter road maintenance from A071 and A079; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114320200117-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting114320200117-6Light Truck - Pick up- After Jan 101243.75Inv#007-R01 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1143 | 20200117-6 | 53510107 | Access | 0 | Tractor Trailer - 50 Ton- After Jan 10 | 111.75 | 11.5 | Dynamic | 83.81 | 0 |  |  | 1285.125 | 167.0662 | 1452.1913 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter road maintenance from A071 and A079; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114320200117-6Tractor Trailer - 50 Ton- After Jan 1011.51285.125 | Corbiere and Sons Contracting114320200117-6Tractor Trailer - 50 Ton- After Jan 1011.51285.125Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 1285.125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1143 | 20200117-6 | 53510107 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter road maintenance from A071 and A079; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114320200117-6Foreman4380 | Corbiere and Sons Contracting114320200117-6Foreman4380Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1143 | 20200117-6 | 53510111 | Access | 0 | Foreman | 95 | 1 | HR |  |  | 95 | 0 | 95 | 12.35 | 107.35 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter road maintenance from A071 and A079; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114320200117-6Foreman195 | Corbiere and Sons Contracting114320200117-6Foreman195Inv#007-R01 | [5 empty] | 1 | 95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1143 | 20200117-6 | 53510107 | Access | 0 | Driver - AZ | 70 | 11.5 | HR |  |  | 105 | 0 | 805 | 104.65 | 909.65 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter road maintenance from A071 and A079; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114320200117-6Driver - AZ11.5805 | Corbiere and Sons Contracting114320200117-6Driver - AZ11.5805Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1143 | 20200117-6 | 53510111 | Access | 0 | Driver - AZ | 70 | 7.5 | HR |  |  | 105 | 0 | 525 | 68.25 | 593.25 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter road maintenance from A071 and A079; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114320200117-6Driver - AZ7.5525 | Corbiere and Sons Contracting114320200117-6Driver - AZ7.5525Inv#007-R01 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1143 | 20200117-6 | 53510107 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter road maintenance from A071 and A079; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114320200117-6L.O.A.51050 | Corbiere and Sons Contracting114320200117-6L.O.A.51050Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1143 | 20200117-6 | 53510111 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter road maintenance from A071 and A079; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114320200117-6L.O.A.51050 | Corbiere and Sons Contracting114320200117-6L.O.A.51050Inv#007-R01 |  | WF1 Mob/Demob |  |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1143 | 20200117-6 | 53510107 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter road maintenance from A071 and A079; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114320200117-6Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting114320200117-6Operator - Principle - After Jan 109675Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1143 | 20200117-6 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 44 | HR |  |  | 75 | 0 | 3300 | 429 | 3729 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter road maintenance from A071 and A079; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114320200117-6Operator - Principle - After Jan 10443300 | Corbiere and Sons Contracting114320200117-6Operator - Principle - After Jan 10443300Inv#007-R01 | [5 empty] | 1 | 3300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1143 | 20200117-6 | 53510107 | Access | 0 | Labourer - General - After Jan 10 | 60 | 9 | HR |  |  | 60 | 0 | 540 | 70.2 | 610.2 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter road maintenance from A071 and A079; |  |  | Eldorado | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114320200117-6Labourer - General - After Jan 109540 | Corbiere and Sons Contracting114320200117-6Labourer - General - After Jan 109540Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 540 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1144 | 20200117-7 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A096-A097; |  |  | Wind Farm | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114420200117-7Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting114420200117-7Grinder - 4710 Peterson or equal95011.2Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1144 | 20200117-7 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A096-A097; |  |  | Wind Farm | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114420200117-7Log Loader91377 | Corbiere and Sons Contracting114420200117-7Log Loader91377Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1144 | 20200117-7 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A096-A097; |  |  | Wind Farm | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114420200117-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting114420200117-7Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1144 | 20200117-7 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A096-A097; |  |  | Wind Farm | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114420200117-7L.O.A.1210 | Corbiere and Sons Contracting114420200117-7L.O.A.1210Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1144 | 20200117-7 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A096-A097; |  |  | Wind Farm | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114420200117-7Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting114420200117-7Operator - Principle - After Jan 109675Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1145 | 20200117-8 | 53510111 | Access | 0 | Dozer - D5 or equal- After Jan 10 | 80.93 | 9 | Dynamic | 60.7 | 0 |  |  | 728.37 | 94.6881 | 823.0581 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Maintenance from A115-A117 and from A082-A085; Equipment being walked out to be floated; Graders and Sander truck working across access roads; Labourer escorting graders where necessary, cleaning tracks and fuelling; |  |  | Wind Farm | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114520200117-8Dozer - D5 or equal- After Jan 109728.37 | Corbiere and Sons Contracting114520200117-8Dozer - D5 or equal- After Jan 109728.37Inv#007-R01 | [5 empty] | 1 | 728.37 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1145 | 20200117-8 | 53510111 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Maintenance from A115-A117 and from A082-A085; Equipment being walked out to be floated; Graders and Sander truck working across access roads; Labourer escorting graders where necessary, cleaning tracks and fuelling; |  |  | Wind Farm | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114520200117-8Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting114520200117-8Dozer D6 or equal- After Jan 1091183.32Inv#007-R01 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1145 | 20200117-8 | 53510111 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 110.22 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Maintenance from A115-A117 and from A082-A085; Equipment being walked out to be floated; Graders and Sander truck working across access roads; Labourer escorting graders where necessary, cleaning tracks and fuelling; |  |  | Wind Farm | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114520200117-8Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting114520200117-8Excavator - 36 ton- After Jan 10182645.28Inv#007-R01 | [5 empty] | 1 | 2645.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1145 | 20200117-8 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 27 | Dynamic | 95.24 | 0 |  |  | 3428.46 | 445.6998 | 3874.1598 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Maintenance from A115-A117 and from A082-A085; Equipment being walked out to be floated; Graders and Sander truck working across access roads; Labourer escorting graders where necessary, cleaning tracks and fuelling; |  |  | Wind Farm | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114520200117-8Grader - Cat 12 to 14 or equal- After Jan 10273428.46 | Corbiere and Sons Contracting114520200117-8Grader - Cat 12 to 14 or equal- After Jan 10273428.46Inv#007-R01 | [5 empty] | 1 | 3428.46 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1145 | 20200117-8 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 3 | Dynamic | 64.79 | 0 |  |  | 259.14 | 33.6882 | 292.8282 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Maintenance from A115-A117 and from A082-A085; Equipment being walked out to be floated; Graders and Sander truck working across access roads; Labourer escorting graders where necessary, cleaning tracks and fuelling; |  |  | Wind Farm | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114520200117-8Sander Truck - Forestry- After Jan 103259.14 | Corbiere and Sons Contracting114520200117-8Sander Truck - Forestry- After Jan 103259.14Inv#007-R01 | [5 empty] | 1 | 259.14 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1145 | 20200117-8 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Maintenance from A115-A117 and from A082-A085; Equipment being walked out to be floated; Graders and Sander truck working across access roads; Labourer escorting graders where necessary, cleaning tracks and fuelling; |  |  | Wind Farm | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114520200117-8Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting114520200117-8Light Truck - Pick up- After Jan 103731.25Inv#007-R01 | [5 empty] | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1145 | 20200117-8 | 53510111 | Access | 0 | Foreman | 95 | 24 | HR |  |  | 95 | 0 | 2280 | 296.4 | 2576.4 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Maintenance from A115-A117 and from A082-A085; Equipment being walked out to be floated; Graders and Sander truck working across access roads; Labourer escorting graders where necessary, cleaning tracks and fuelling; |  |  | Wind Farm | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114520200117-8Foreman242280 | Corbiere and Sons Contracting114520200117-8Foreman242280Inv#007-R01 | [5 empty] | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1145 | 20200117-8 | 53510111 | Access | 0 | L.O.A. | 210 | 11 | DAY |  |  |  | 0 | 2310 | 300.3 | 2610.3 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Maintenance from A115-A117 and from A082-A085; Equipment being walked out to be floated; Graders and Sander truck working across access roads; Labourer escorting graders where necessary, cleaning tracks and fuelling; |  |  | Wind Farm | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114520200117-8L.O.A.112310 | Corbiere and Sons Contracting114520200117-8L.O.A.112310Inv#007-R01 | [5 empty] | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1145 | 20200117-8 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 88 | HR |  |  | 75 | 0 | 6600 | 858 | 7458 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Maintenance from A115-A117 and from A082-A085; Equipment being walked out to be floated; Graders and Sander truck working across access roads; Labourer escorting graders where necessary, cleaning tracks and fuelling; |  |  | Wind Farm | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114520200117-8Operator - Principle - After Jan 10886600 | Corbiere and Sons Contracting114520200117-8Operator - Principle - After Jan 10886600Inv#007-R01 | [5 empty] | 1 | 6600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1145 | 20200117-8 | 53510111 | Access | 0 | Labourer - General - After Jan 10 | 60 | 22 | HR |  |  | 60 | 0 | 1320 | 171.6 | 1491.6 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Maintenance from A115-A117 and from A082-A085; Equipment being walked out to be floated; Graders and Sander truck working across access roads; Labourer escorting graders where necessary, cleaning tracks and fuelling; |  |  | Wind Farm | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114520200117-8Labourer - General - After Jan 10221320 | Corbiere and Sons Contracting114520200117-8Labourer - General - After Jan 10221320Inv#007-R01 | [5 empty] | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1146 | 20200117-9 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A123 and up to A127 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114620200117-9Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting114620200117-9Chainsaw and consumables- After Jan 103180Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1146 | 20200117-9 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A123 and up to A127 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114620200117-9Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting114620200117-9Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1146 | 20200117-9 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A123 and up to A127 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114620200117-9Foreman121140 | Corbiere and Sons Contracting114620200117-9Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1146 | 20200117-9 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A123 and up to A127 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114620200117-9L.O.A.4840 | Corbiere and Sons Contracting114620200117-9L.O.A.4840Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1146 | 20200117-9 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 28 | HR |  |  | 70 | 0 | 1960 | 254.8 | 2214.8 | 2020-01-17 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A123 and up to A127 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43857 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting114620200117-9Labourer - Specialized - After Jan 10281960 | Corbiere and Sons Contracting114620200117-9Labourer - Specialized - After Jan 10281960Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1.1636 | DAY | 182.81 | 0 |  |  | 283.6227 | 36.871 | 320.4937 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Light Truck - Pick up- After Jan 101.1635802283.6227 | Corbiere and Sons Contracting120120200118-1Light Truck - Pick up- After Jan 101.1635802283.6227Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 283.6227 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1.2388 | DAY | 182.81 | 0 |  |  | 301.9516 | 39.2537 | 341.2053 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Light Truck - Pick up- After Jan 101.2387758301.9516 | Corbiere and Sons Contracting120120200118-1Light Truck - Pick up- After Jan 101.2387758301.9516Inv#007-R01 | [5 empty] | 1 | 301.9516 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1.5551 | DAY | 182.81 | 0 |  |  | 379.0464 | 49.276 | 428.3224 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Light Truck - Pick up- After Jan 101.555062379.0464 | Corbiere and Sons Contracting120120200118-1Light Truck - Pick up- After Jan 101.555062379.0464Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 379.0464 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.59073 | DAY | 182.81 | 0 |  |  | 143.9894 | 18.7186 | 162.708 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Light Truck - Pick up- After Jan 100.5907258143.9894 | Corbiere and Sons Contracting120120200118-1Light Truck - Pick up- After Jan 100.5907258143.9894Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 143.9894 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53510106 | Access | 0 | Project Manager | 110 | 2.7926 | HR |  |  | 110 | 0 | 307.1852 | 39.9341 | 347.1193 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Project Manager2.7925925307.1852 | Corbiere and Sons Contracting120120200118-1Project Manager2.7925925307.1852Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 307.1852 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53510111 | Access | 0 | Project Manager | 110 | 2.9731 | HR |  |  | 110 | 0 | 327.0368 | 42.5148 | 369.5516 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Project Manager2.973062327.0368 | Corbiere and Sons Contracting120120200118-1Project Manager2.973062327.0368Inv#007-R01 | [5 empty] | 1 | 327.0368 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53520102 | Clearing | 0 | Project Manager | 110 | 3.7321 | HR |  |  | 110 | 0 | 410.5364 | 53.3697 | 463.9061 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Project Manager3.7321488410.5364 | Corbiere and Sons Contracting120120200118-1Project Manager3.7321488410.5364Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 410.5364 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53520104 | Clearing | 0 | Project Manager | 110 | 1.4177 | HR |  |  | 110 | 0 | 155.9516 | 20.2737 | 176.2253 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Project Manager1.417742155.9516 | Corbiere and Sons Contracting120120200118-1Project Manager1.417742155.9516Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 155.9516 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53510106 | Access | 0 | Superintendent | 105 | 2.7926 | HR |  |  | 105 | 0 | 293.2222 | 38.1189 | 331.3411 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Superintendent2.7925925293.2222 | Corbiere and Sons Contracting120120200118-1Superintendent2.7925925293.2222Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 293.2222 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53510111 | Access | 0 | Superintendent | 105 | 2.9731 | HR |  |  | 105 | 0 | 312.1715 | 40.5823 | 352.7538 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Superintendent2.973062312.1715 | Corbiere and Sons Contracting120120200118-1Superintendent2.973062312.1715Inv#007-R01 | [5 empty] | 1 | 312.1715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53520102 | Clearing | 0 | Superintendent | 105 | 3.7321 | HR |  |  | 105 | 0 | 391.8756 | 50.9438 | 442.8194 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Superintendent3.7321488391.8756 | Corbiere and Sons Contracting120120200118-1Superintendent3.7321488391.8756Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 391.8756 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53520104 | Clearing | 0 | Superintendent | 105 | 1.4177 | HR |  |  | 105 | 0 | 148.8629 | 19.3522 | 168.2151 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Superintendent1.417742148.8629 | Corbiere and Sons Contracting120120200118-1Superintendent1.417742148.8629Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 148.8629 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53510106 | Access | 0 | Project Coordinator | 80 | 2.7926 | HR |  |  | 80 | 0 | 223.4074 | 29.043 | 252.4504 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Project Coordinator2.7925925223.4074 | Corbiere and Sons Contracting120120200118-1Project Coordinator2.7925925223.4074Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 223.4074 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53510111 | Access | 0 | Project Coordinator | 80 | 2.9731 | HR |  |  | 80 | 0 | 237.845 | 30.9199 | 268.7649 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Project Coordinator2.973062237.845 | Corbiere and Sons Contracting120120200118-1Project Coordinator2.973062237.845Inv#007-R01 | [5 empty] | 1 | 237.845 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53520102 | Clearing | 0 | Project Coordinator | 80 | 3.7321 | HR |  |  | 80 | 0 | 298.5719 | 38.8143 | 337.3862 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Project Coordinator3.7321488298.5719 | Corbiere and Sons Contracting120120200118-1Project Coordinator3.7321488298.5719Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 298.5719 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53520104 | Clearing | 0 | Project Coordinator | 80 | 1.4177 | HR |  |  | 80 | 0 | 113.4194 | 14.7445 | 128.1639 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Project Coordinator1.417742113.4194 | Corbiere and Sons Contracting120120200118-1Project Coordinator1.417742113.4194Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 113.4194 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53510106 | Access | 0 | Safety Advisor | 85 | 2.7926 | HR |  |  | 85 | 0 | 237.3704 | 30.8582 | 268.2286 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Safety Advisor2.7925925237.3704 | Corbiere and Sons Contracting120120200118-1Safety Advisor2.7925925237.3704Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 237.3704 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53510111 | Access | 0 | Safety Advisor | 85 | 2.9731 | HR |  |  | 85 | 0 | 252.7103 | 32.8523 | 285.5626 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Safety Advisor2.973062252.7103 | Corbiere and Sons Contracting120120200118-1Safety Advisor2.973062252.7103Inv#007-R01 | [5 empty] | 1 | 252.7103 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53520102 | Clearing | 0 | Safety Advisor | 85 | 3.7321 | HR |  |  | 85 | 0 | 317.2326 | 41.2402 | 358.4728 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Safety Advisor3.7321488317.2326 | Corbiere and Sons Contracting120120200118-1Safety Advisor3.7321488317.2326Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 317.2326 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53520104 | Clearing | 0 | Safety Advisor | 85 | 1.4177 | HR |  |  | 85 | 0 | 120.5081 | 15.6661 | 136.1742 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Safety Advisor1.417742120.5081 | Corbiere and Sons Contracting120120200118-1Safety Advisor1.417742120.5081Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 120.5081 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53510106 | Access | 0 | Site Administrator | 50 | 2.3272 | HR |  |  | 50 | 0 | 116.358 | 15.1265 | 131.4845 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Site Administrator2.3271604116.358 | Corbiere and Sons Contracting120120200118-1Site Administrator2.3271604116.358Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 116.358 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53510111 | Access | 0 | Site Administrator | 50 | 2.4776 | HR |  |  | 50 | 0 | 123.8776 | 16.1041 | 139.9817 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Site Administrator2.4775516123.8776 | Corbiere and Sons Contracting120120200118-1Site Administrator2.4775516123.8776Inv#007-R01 | [5 empty] | 1 | 123.8776 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53520102 | Clearing | 0 | Site Administrator | 50 | 3.1101 | HR |  |  | 50 | 0 | 155.5062 | 20.2158 | 175.722 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Site Administrator3.110124155.5062 | Corbiere and Sons Contracting120120200118-1Site Administrator3.110124155.5062Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 155.5062 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53520104 | Clearing | 0 | Site Administrator | 50 | 1.1815 | HR |  |  | 50 | 0 | 59.0726 | 7.6794 | 66.752 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Site Administrator1.181451759.0726 | Corbiere and Sons Contracting120120200118-1Site Administrator1.181451759.0726Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 59.0726 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53510106 | Access | 0 | Project Controls | 70 | 2.7926 | HR |  |  | 70 | 0 | 195.4815 | 25.4126 | 220.8941 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Project Controls2.7925925195.4815 | Corbiere and Sons Contracting120120200118-1Project Controls2.7925925195.4815Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 195.4815 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53510111 | Access | 0 | Project Controls | 70 | 2.9731 | HR |  |  | 70 | 0 | 208.1143 | 27.0549 | 235.1692 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Project Controls2.973062208.1143 | Corbiere and Sons Contracting120120200118-1Project Controls2.973062208.1143Inv#007-R01 | [5 empty] | 1 | 208.1143 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53520102 | Clearing | 0 | Project Controls | 70 | 3.7321 | HR |  |  | 70 | 0 | 261.2504 | 33.9626 | 295.213 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Project Controls3.7321488261.2504 | Corbiere and Sons Contracting120120200118-1Project Controls3.7321488261.2504Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 261.2504 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53520104 | Clearing | 0 | Project Controls | 70 | 1.4177 | HR |  |  | 70 | 0 | 99.2419 | 12.9014 | 112.1433 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1Project Controls1.41774299.2419 | Corbiere and Sons Contracting120120200118-1Project Controls1.41774299.2419Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 99.2419 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53510106 | Access | 0 | L.O.A. | 210 | 1.3963 | DAY |  |  |  | 0 | 293.2222 | 38.1189 | 331.3411 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1L.O.A.1.3962963293.2222 | Corbiere and Sons Contracting120120200118-1L.O.A.1.3962963293.2222Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 293.2222 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53510111 | Access | 0 | L.O.A. | 210 | 1.4865 | DAY |  |  |  | 0 | 312.1715 | 40.5823 | 352.7538 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1L.O.A.1.486531312.1715 | Corbiere and Sons Contracting120120200118-1L.O.A.1.486531312.1715Inv#007-R01 | [5 empty] | 1 | 312.1715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1.8661 | DAY |  |  |  | 0 | 391.8756 | 50.9438 | 442.8194 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1L.O.A.1.8660744391.8756 | Corbiere and Sons Contracting120120200118-1L.O.A.1.8660744391.8756Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 391.8756 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1201 | 20200118-1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 0.70887 | DAY |  |  |  | 0 | 148.8629 | 19.3522 | 168.2151 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120120200118-1L.O.A.0.708871148.8629 | Corbiere and Sons Contracting120120200118-1L.O.A.0.708871148.8629Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 148.8629 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1209 | 20200118-10 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 15 | Dynamic | 95.24 | 0 |  |  | 1904.7 | 247.611 | 2152.311 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Standby due to inclement weather shutdown, Safety Concerns |  |  | Wind Farm | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120920200118-10Grader - Cat 12 to 14 or equal- After Jan 10151904.7 | Corbiere and Sons Contracting120920200118-10Grader - Cat 12 to 14 or equal- After Jan 10151904.7Inv#009 | [5 empty] | 1 | 1904.7 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1209 | 20200118-10 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 5 | Dynamic | 64.79 | 0 |  |  | 431.9 | 56.147 | 488.047 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Standby due to inclement weather shutdown, Safety Concerns |  |  | Wind Farm | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120920200118-10Sander Truck - Forestry- After Jan 105431.9 | Corbiere and Sons Contracting120920200118-10Sander Truck - Forestry- After Jan 105431.9Inv#009 | [5 empty] | 1 | 431.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1209 | 20200118-10 | 53510111 | Access | 0 | Foreman | 95 | 5 | HR |  |  | 95 | 0 | 475 | 61.75 | 536.75 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Standby due to inclement weather shutdown, Safety Concerns |  |  | Wind Farm | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120920200118-10Foreman5475 | Corbiere and Sons Contracting120920200118-10Foreman5475Inv#009 | [5 empty] | 1 | 475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1209 | 20200118-10 | 53510111 | Access | 0 | Labourer - General | 60 | 5 | HR |  |  |  | 0 | 300 | 39 | 339 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Standby due to inclement weather shutdown, Safety Concerns |  |  | Wind Farm | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120920200118-10Labourer - General5300 | Corbiere and Sons Contracting120920200118-10Labourer - General5300Inv#009 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1209 | 20200118-10 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 20 | HR |  |  | 75 | 0 | 1500 | 195 | 1695 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Standby due to inclement weather shutdown, Safety Concerns |  |  | Wind Farm | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120920200118-10Operator - Principle - After Jan 10201500 | Corbiere and Sons Contracting120920200118-10Operator - Principle - After Jan 10201500Inv#009 | [5 empty] | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1210 | 20200118-11-R1 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A123/Shutdown for Weather |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting121020200118-11-R1Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting121020200118-11-R1Chainsaw and consumables- After Jan 103180Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1210 | 20200118-11-R1 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A123/Shutdown for Weather |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting121020200118-11-R1Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting121020200118-11-R1Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1210 | 20200118-11-R1 | 53520104 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A123/Shutdown for Weather |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting121020200118-11-R1Foreman6570 | Corbiere and Sons Contracting121020200118-11-R1Foreman6570Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1210 | 20200118-11-R1 | 53520104 | Clearing | 0 | Labourer - Specialized | 70 | 15 | HR |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A123/Shutdown for Weather |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting121020200118-11-R1Labourer - Specialized151050 | Corbiere and Sons Contracting121020200118-11-R1Labourer - Specialized151050Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1210 | 20200118-11-R1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A123/Shutdown for Weather |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting121020200118-11-R1L.O.A.4840 | Corbiere and Sons Contracting121020200118-11-R1L.O.A.4840Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1211 | 20200118-12 | 53520104 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Handfelling at A123 was shut down due to inclement weather, safety concerns |  |  | Wolf Lake Road | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting121120200118-12Foreman6570 | Corbiere and Sons Contracting121120200118-12Foreman6570Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1211 | 20200118-12 | 53520104 | Clearing | 0 | Labourer - Specialized | 70 | 15 | HR |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Handfelling at A123 was shut down due to inclement weather, safety concerns |  |  | Wolf Lake Road | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting121120200118-12Labourer - Specialized151050 | Corbiere and Sons Contracting121120200118-12Labourer - Specialized151050Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1212 | 20200118-13 | 53510111 | Access | 0 | Dozer - D5 or equal- After Jan 10 | 80.93 | 3 | Dynamic | 60.7 | 0 |  |  | 242.79 | 31.5627 | 274.3527 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Maintenace from A118-A127/Weather Delay |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting121220200118-13Dozer - D5 or equal- After Jan 103242.79 | Corbiere and Sons Contracting121220200118-13Dozer - D5 or equal- After Jan 103242.79Inv#007-R01 | [5 empty] | 1 | 242.79 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1212 | 20200118-13 | 53510111 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Maintenace from A118-A127/Weather Delay |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting121220200118-13Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting121220200118-13Excavator - 36 ton- After Jan 103440.88Inv#007-R01 | [5 empty] | 1 | 440.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1212 | 20200118-13 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Maintenace from A118-A127/Weather Delay |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting121220200118-13Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting121220200118-13Light Truck - Pick up- After Jan 102487.5Inv#007-R01 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1212 | 20200118-13 | 53510111 | Access | 0 | Foreman | 95 | 0 | HR |  |  | 95 | 0 | 0 | 0 | 0 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Maintenace from A118-A127/Weather Delay |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting121220200118-13Foreman00 | Corbiere and Sons Contracting121220200118-13Foreman00Inv#007-R01 | [5 empty] | 1 | 0 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1212 | 20200118-13 | 53510111 | Access | 0 | Labourer - General | 60 | 5 | HR |  |  |  | 0 | 300 | 39 | 339 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Maintenace from A118-A127/Weather Delay |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting121220200118-13Labourer - General5300 | Corbiere and Sons Contracting121220200118-13Labourer - General5300Inv#007-R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1212 | 20200118-13 | 53510111 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Maintenace from A118-A127/Weather Delay |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting121220200118-13L.O.A.51050 | Corbiere and Sons Contracting121220200118-13L.O.A.51050Inv#007-R01 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1212 | 20200118-13 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Maintenace from A118-A127/Weather Delay |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting121220200118-13Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting121220200118-13Operator - Principle - After Jan 10141050Inv#007-R01 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1213 | 20200118-14 | 53510111 | Access | 0 | Dozer - D5 or equal- After Jan 10 | 80.93 | 5 | Dynamic | 60.7 | 0 |  |  | 404.65 | 52.6045 | 457.2545 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Stndby after 11am, shutdown due to inclement weather, safety concerns |  |  | Wolf Lake Road | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting121320200118-14Dozer - D5 or equal- After Jan 105404.65 | Corbiere and Sons Contracting121320200118-14Dozer - D5 or equal- After Jan 105404.65Inv#009 | [5 empty] | 1 | 404.65 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1213 | 20200118-14 | 53510111 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Stndby after 11am, shutdown due to inclement weather, safety concerns |  |  | Wolf Lake Road | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting121320200118-14Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting121320200118-14Excavator - 36 ton- After Jan 105734.8Inv#009 | [5 empty] | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1213 | 20200118-14 | 53510111 | Access | 0 | Labourer - General | 60 | 5 | HR |  |  |  | 0 | 300 | 39 | 339 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Stndby after 11am, shutdown due to inclement weather, safety concerns |  |  | Wolf Lake Road | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting121320200118-14Labourer - General5300 | Corbiere and Sons Contracting121320200118-14Labourer - General5300Inv#009 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1213 | 20200118-14 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 15 | HR |  |  | 75 | 0 | 1125 | 146.25 | 1271.25 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Stndby after 11am, shutdown due to inclement weather, safety concerns |  |  | Wolf Lake Road | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting121320200118-14Operator - Principle - After Jan 10151125 | Corbiere and Sons Contracting121320200118-14Operator - Principle - After Jan 10151125Inv#009 | [5 empty] | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1219 | 20200118-20 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Winter Access and Float Moves/ Delay due to inclement weather | 6 |  | Santoy Lake | 0 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting121920200118-20Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting121920200118-20Dozer D6 or equal- After Jan 1091183.32Inv#007-R01 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1219 | 20200118-20 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Winter Access and Float Moves/ Delay due to inclement weather | 6 |  | Santoy Lake | 0 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting121920200118-20Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting121920200118-20Light Truck - Pick up- After Jan 101243.75Inv#007-R01 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1219 | 20200118-20 | 53510611 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Winter Access and Float Moves/ Delay due to inclement weather | 6 |  | Santoy Lake | 0 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting121920200118-20Foreman121140 | Corbiere and Sons Contracting121920200118-20Foreman121140Inv#007-R01 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1219 | 20200118-20 | 53510611 | Access | 0 | Operator - Intermdiate | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Winter Access and Float Moves/ Delay due to inclement weather | 6 |  | Santoy Lake | 0 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting121920200118-20Operator - Intermdiate11770 | Corbiere and Sons Contracting121920200118-20Operator - Intermdiate11770Inv#007-R01 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1219 | 20200118-20 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Winter Access and Float Moves/ Delay due to inclement weather | 6 |  | Santoy Lake | 0 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting121920200118-20L.O.A.2420 | Corbiere and Sons Contracting121920200118-20L.O.A.2420Inv#007-R01 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1222 | 20200118-3 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 3 | HR | 417.6 | 0 |  |  | 1670.4 | 217.152 | 1887.552 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding Material at A061 until shutdown |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122220200118-3Grinder - 4710 Peterson or equal31670.4 | Corbiere and Sons Contracting122220200118-3Grinder - 4710 Peterson or equal31670.4Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1670.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1222 | 20200118-3 | 53520102 | Clearing | 0 | Log Loader | 153 | 3 | HR | 114.75 | 0 |  |  | 459 | 59.67 | 518.67 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding Material at A061 until shutdown |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122220200118-3Log Loader3459 | Corbiere and Sons Contracting122220200118-3Log Loader3459Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 459 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1222 | 20200118-3 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding Material at A061 until shutdown |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122220200118-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting122220200118-3Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1222 | 20200118-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding Material at A061 until shutdown |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122220200118-3L.O.A.1210 | Corbiere and Sons Contracting122220200118-3L.O.A.1210Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1222 | 20200118-3 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding Material at A061 until shutdown |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122220200118-3Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting122220200118-3Operator - Principle - After Jan 105375Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1203 | 20200118-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 5 | HR | 417.6 | 0 |  |  | 2784 | 361.92 | 3145.92 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Standby due to 11am shutdown caused by inclement Weather |  |  | Eldorado | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120320200118-4Grinder - 4710 Peterson or equal52784 | Corbiere and Sons Contracting120320200118-4Grinder - 4710 Peterson or equal52784Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2784 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1203 | 20200118-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 5 | HR | 114.75 | 0 |  |  | 765 | 99.45 | 864.45 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Standby due to 11am shutdown caused by inclement Weather |  |  | Eldorado | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120320200118-4Log Loader5765 | Corbiere and Sons Contracting120320200118-4Log Loader5765Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 765 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1203 | 20200118-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Standby due to 11am shutdown caused by inclement Weather |  |  | Eldorado | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120320200118-4Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting120320200118-4Operator - Principle - After Jan 105375Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1204 | 20200118-5 | 53510106 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6 | Dynamic | 103.84 | 0 |  |  | 830.7 | 107.991 | 938.691 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  | Shutdown early due to weather |  | Approved |  |  | Winter Rd Building from A076-A079 |  |  | Eldorado | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting120420200118-5Excavator - 30 ton- After Jan 106830.7 | Corbiere and Sons Contracting120420200118-5Excavator - 30 ton- After Jan 106830.7Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 830.7 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1204 | 20200118-5 | 53510106 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  | Shutdown early due to weather |  | Approved |  |  | Winter Rd Building from A076-A079 |  |  | Eldorado | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting120420200118-5Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting120420200118-5Excavator Thumb - 30 - 50 ton- After Jan 10673.26Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 73.26 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1204 | 20200118-5 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  | Shutdown early due to weather |  | Approved |  |  | Winter Rd Building from A076-A079 |  |  | Eldorado | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting120420200118-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting120420200118-5Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1204 | 20200118-5 | 53510106 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  | Shutdown early due to weather |  | Approved |  |  | Winter Rd Building from A076-A079 |  |  | Eldorado | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting120420200118-5L.O.A.2420 | Corbiere and Sons Contracting120420200118-5L.O.A.2420Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1204 | 20200118-5 | 53510106 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  | Shutdown early due to weather |  | Approved |  |  | Winter Rd Building from A076-A079 |  |  | Eldorado | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting120420200118-5Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting120420200118-5Operator - Principle - After Jan 1010750Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1205 | 20200118-6 | 53510106 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Work was shut down due to inclement weather, safety concerns |  |  | Eldorado | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120520200118-6Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting120520200118-6Excavator - 30 ton- After Jan 10101384.5Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1205 | 20200118-6 | 53510106 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Work was shut down due to inclement weather, safety concerns |  |  | Eldorado | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120520200118-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting120520200118-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1205 | 20200118-6 | 53510106 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Work was shut down due to inclement weather, safety concerns |  |  | Eldorado | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120520200118-6Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting120520200118-6Operator - Principle - After Jan 1010750Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1206 | 20200118-7 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 1 | unit/man/day | 0 | 0 |  |  | 60 | 7.8 | 67.8 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  | Shutdown for weather |  | Approved |  |  | Handfelling from A098 |  |  | Wind Farm | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting120620200118-7Chainsaw and consumables- After Jan 10160 | Corbiere and Sons Contracting120620200118-7Chainsaw and consumables- After Jan 10160Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 60 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1206 | 20200118-7 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  | Shutdown for weather |  | Approved |  |  | Handfelling from A098 |  |  | Wind Farm | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting120620200118-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting120620200118-7Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1206 | 20200118-7 | 53520104 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  | Shutdown for weather |  | Approved |  |  | Handfelling from A098 |  |  | Wind Farm | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting120620200118-7Foreman6570 | Corbiere and Sons Contracting120620200118-7Foreman6570Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1206 | 20200118-7 | 53520104 | Clearing | 0 | Labourer - Specialized | 70 | 5 | HR |  |  |  | 0 | 350 | 45.5 | 395.5 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  | Shutdown for weather |  | Approved |  |  | Handfelling from A098 |  |  | Wind Farm | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting120620200118-7Labourer - Specialized5350 | Corbiere and Sons Contracting120620200118-7Labourer - Specialized5350Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1206 | 20200118-7 | 53520104 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  | Shutdown for weather |  | Approved |  |  | Handfelling from A098 |  |  | Wind Farm | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting120620200118-7L.O.A.2420 | Corbiere and Sons Contracting120620200118-7L.O.A.2420Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1207 | 20200118-8 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 5 | HR | 417.6 | 0 |  |  | 2784 | 361.92 | 3145.92 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Handfelling at A098 was shutdown due to inclement weather, safety concerns. Grinding shutdown due to weather. Safety Concerns |  |  | Wind Farm | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120720200118-8Grinder - 4710 Peterson or equal52784 | Corbiere and Sons Contracting120720200118-8Grinder - 4710 Peterson or equal52784Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2784 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1207 | 20200118-8 | 53520102 | Clearing | 0 | Log Loader | 153 | 5 | HR | 114.75 | 0 |  |  | 765 | 99.45 | 864.45 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Handfelling at A098 was shutdown due to inclement weather, safety concerns. Grinding shutdown due to weather. Safety Concerns |  |  | Wind Farm | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120720200118-8Log Loader5765 | Corbiere and Sons Contracting120720200118-8Log Loader5765Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 765 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1207 | 20200118-8 | 53520104 | Clearing | 0 | Foreman | 95 | 5 | HR |  |  | 95 | 0 | 475 | 61.75 | 536.75 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Handfelling at A098 was shutdown due to inclement weather, safety concerns. Grinding shutdown due to weather. Safety Concerns |  |  | Wind Farm | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120720200118-8Foreman5475 | Corbiere and Sons Contracting120720200118-8Foreman5475Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1207 | 20200118-8 | 53520104 | Clearing | 0 | Labourer - Specialized | 70 | 5 | HR |  |  |  | 0 | 350 | 45.5 | 395.5 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Handfelling at A098 was shutdown due to inclement weather, safety concerns. Grinding shutdown due to weather. Safety Concerns |  |  | Wind Farm | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120720200118-8Labourer - Specialized5350 | Corbiere and Sons Contracting120720200118-8Labourer - Specialized5350Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1207 | 20200118-8 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Handfelling at A098 was shutdown due to inclement weather, safety concerns. Grinding shutdown due to weather. Safety Concerns |  |  | Wind Farm | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120720200118-8L.O.A.1210 | Corbiere and Sons Contracting120720200118-8L.O.A.1210Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1207 | 20200118-8 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-01-18 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 9 | Approved | Corbiere - Weather Delay - Ongoing | 9009 | Handfelling at A098 was shutdown due to inclement weather, safety concerns. Grinding shutdown due to weather. Safety Concerns |  |  | Wind Farm | 1 |  |  | 40 | 43889 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting120720200118-8Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting120720200118-8Operator - Principle - After Jan 105375Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1208 | 20200118-9 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders and sander truck out until weather shutdown |  |  | Wind Farm | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting120820200118-9Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting120820200118-9Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#007-R01 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1208 | 20200118-9 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 1 | Dynamic | 64.79 | 0 |  |  | 86.38 | 11.2294 | 97.6094 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders and sander truck out until weather shutdown |  |  | Wind Farm | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting120820200118-9Sander Truck - Forestry- After Jan 10186.38 | Corbiere and Sons Contracting120820200118-9Sander Truck - Forestry- After Jan 10186.38Inv#007-R01 | [5 empty] | 1 | 86.38 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1208 | 20200118-9 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders and sander truck out until weather shutdown |  |  | Wind Farm | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting120820200118-9Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting120820200118-9Light Truck - Pick up- After Jan 102487.5Inv#007-R01 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1208 | 20200118-9 | 53510111 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders and sander truck out until weather shutdown |  |  | Wind Farm | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting120820200118-9Foreman6570 | Corbiere and Sons Contracting120820200118-9Foreman6570Inv#007-R01 | [5 empty] | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1208 | 20200118-9 | 53510111 | Access | 0 | Labourer - General | 60 | 5 | HR |  |  |  | 0 | 300 | 39 | 339 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders and sander truck out until weather shutdown |  |  | Wind Farm | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting120820200118-9Labourer - General5300 | Corbiere and Sons Contracting120820200118-9Labourer - General5300Inv#007-R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1208 | 20200118-9 | 53510111 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders and sander truck out until weather shutdown |  |  | Wind Farm | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting120820200118-9L.O.A.61260 | Corbiere and Sons Contracting120820200118-9L.O.A.61260Inv#007-R01 | [5 empty] | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1208 | 20200118-9 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2020-01-18 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders and sander truck out until weather shutdown |  |  | Wind Farm | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting120820200118-9Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting120820200118-9Operator - Principle - After Jan 10141050Inv#007-R01 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1.9546 | DAY | 182.81 | 0 |  |  | 476.4446 | 61.9378 | 538.3824 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Light Truck - Pick up- After Jan 101.9546447476.4446 | Corbiere and Sons Contracting118720200119-1Light Truck - Pick up- After Jan 101.9546447476.4446Inv#007-R01 | [5 empty] | 1 | 476.4446 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.52821 | DAY | 182.81 | 0 |  |  | 128.7505 | 16.7376 | 145.4881 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Light Truck - Pick up- After Jan 100.5282073128.7505 | Corbiere and Sons Contracting118720200119-1Light Truck - Pick up- After Jan 100.5282073128.7505Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 128.7505 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1.5026 | DAY | 182.81 | 0 |  |  | 366.2686 | 47.6149 | 413.8835 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Light Truck - Pick up- After Jan 101.5026406366.2686 | Corbiere and Sons Contracting118720200119-1Light Truck - Pick up- After Jan 101.5026406366.2686Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 366.2686 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.41854 | DAY | 182.81 | 0 |  |  | 102.0188 | 13.2624 | 115.2812 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Light Truck - Pick up- After Jan 100.4185387102.0188 | Corbiere and Sons Contracting118720200119-1Light Truck - Pick up- After Jan 100.4185387102.0188Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 102.0188 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53510111 | Access | 0 | Project Manager | 110 | 4.6911 | HR |  |  | 110 | 0 | 516.0262 | 67.0834 | 583.1096 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Project Manager4.6911472516.0262 | Corbiere and Sons Contracting118720200119-1Project Manager4.6911472516.0262Inv#007-R01 | [5 empty] | 1 | 516.0262 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 1.2677 | HR |  |  | 110 | 0 | 139.4467 | 18.1281 | 157.5748 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Project Manager1.2676975139.4467 | Corbiere and Sons Contracting118720200119-1Project Manager1.2676975139.4467Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 139.4467 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520102 | Clearing | 0 | Project Manager | 110 | 3.6063 | HR |  |  | 110 | 0 | 396.6971 | 51.5706 | 448.2677 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Project Manager3.6063374396.6971 | Corbiere and Sons Contracting118720200119-1Project Manager3.6063374396.6971Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 396.6971 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520104 | Clearing | 0 | Project Manager | 110 | 1.0045 | HR |  |  | 110 | 0 | 110.4942 | 14.3642 | 124.8584 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Project Manager1.0044929110.4942 | Corbiere and Sons Contracting118720200119-1Project Manager1.0044929110.4942Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 110.4942 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53510111 | Access | 0 | Superintendent | 105 | 4.6911 | HR |  |  | 105 | 0 | 492.5705 | 64.0342 | 556.6047 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Superintendent4.6911472492.5705 | Corbiere and Sons Contracting118720200119-1Superintendent4.6911472492.5705Inv#007-R01 | [5 empty] | 1 | 492.5705 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 1.2677 | HR |  |  | 105 | 0 | 133.1082 | 17.3041 | 150.4123 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Superintendent1.2676975133.1082 | Corbiere and Sons Contracting118720200119-1Superintendent1.2676975133.1082Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 133.1082 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520102 | Clearing | 0 | Superintendent | 105 | 3.6063 | HR |  |  | 105 | 0 | 378.6654 | 49.2265 | 427.8919 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Superintendent3.6063374378.6654 | Corbiere and Sons Contracting118720200119-1Superintendent3.6063374378.6654Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 378.6654 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520104 | Clearing | 0 | Superintendent | 105 | 1.0045 | HR |  |  | 105 | 0 | 105.4718 | 13.7113 | 119.1831 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Superintendent1.0044929105.4718 | Corbiere and Sons Contracting118720200119-1Superintendent1.0044929105.4718Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 105.4718 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53510111 | Access | 0 | Project Coordinator | 80 | 4.6911 | HR |  |  | 80 | 0 | 375.2918 | 48.7879 | 424.0797 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Project Coordinator4.6911472375.2918 | Corbiere and Sons Contracting118720200119-1Project Coordinator4.6911472375.2918Inv#007-R01 | [5 empty] | 1 | 375.2918 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 1.2677 | HR |  |  | 80 | 0 | 101.4158 | 13.1841 | 114.5999 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Project Coordinator1.2676975101.4158 | Corbiere and Sons Contracting118720200119-1Project Coordinator1.2676975101.4158Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 101.4158 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520102 | Clearing | 0 | Project Coordinator | 80 | 3.6063 | HR |  |  | 80 | 0 | 288.507 | 37.5059 | 326.0129 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Project Coordinator3.6063374288.507 | Corbiere and Sons Contracting118720200119-1Project Coordinator3.6063374288.507Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 288.507 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520104 | Clearing | 0 | Project Coordinator | 80 | 1.0045 | HR |  |  | 80 | 0 | 80.3594 | 10.4467 | 90.8061 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Project Coordinator1.004492980.3594 | Corbiere and Sons Contracting118720200119-1Project Coordinator1.004492980.3594Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 80.3594 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53510111 | Access | 0 | Safety Advisor | 85 | 4.6911 | HR |  |  | 85 | 0 | 398.7475 | 51.8372 | 450.5847 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Safety Advisor4.6911472398.7475 | Corbiere and Sons Contracting118720200119-1Safety Advisor4.6911472398.7475Inv#007-R01 | [5 empty] | 1 | 398.7475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 1.2677 | HR |  |  | 85 | 0 | 107.7543 | 14.0081 | 121.7624 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Safety Advisor1.2676975107.7543 | Corbiere and Sons Contracting118720200119-1Safety Advisor1.2676975107.7543Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 107.7543 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520102 | Clearing | 0 | Safety Advisor | 85 | 3.6063 | HR |  |  | 85 | 0 | 306.5387 | 39.85 | 346.3887 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Safety Advisor3.6063374306.5387 | Corbiere and Sons Contracting118720200119-1Safety Advisor3.6063374306.5387Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 306.5387 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520104 | Clearing | 0 | Safety Advisor | 85 | 1.0045 | HR |  |  | 85 | 0 | 85.3819 | 11.0996 | 96.4815 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Safety Advisor1.004492985.3819 | Corbiere and Sons Contracting118720200119-1Safety Advisor1.004492985.3819Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 85.3819 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53510111 | Access | 0 | Site Administrator | 50 | 4.3002 | HR |  |  | 50 | 0 | 215.0109 | 27.9514 | 242.9623 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Site Administrator4.3002183215.0109 | Corbiere and Sons Contracting118720200119-1Site Administrator4.3002183215.0109Inv#007-R01 | [5 empty] | 1 | 215.0109 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520101 | Clearing | 0 | Site Administrator | 50 | 1.1621 | HR |  |  | 50 | 0 | 58.1028 | 7.5534 | 65.6562 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Site Administrator1.16205658.1028 | Corbiere and Sons Contracting118720200119-1Site Administrator1.16205658.1028Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 58.1028 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520102 | Clearing | 0 | Site Administrator | 50 | 3.3058 | HR |  |  | 50 | 0 | 165.2905 | 21.4878 | 186.7783 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Site Administrator3.3058093165.2905 | Corbiere and Sons Contracting118720200119-1Site Administrator3.3058093165.2905Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 165.2905 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520104 | Clearing | 0 | Site Administrator | 50 | 0.92079 | HR |  |  | 50 | 0 | 46.0393 | 5.9851 | 52.0244 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Site Administrator0.920785246.0393 | Corbiere and Sons Contracting118720200119-1Site Administrator0.920785246.0393Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 46.0393 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53510111 | Access | 0 | Project Controls | 70 | 4.6911 | HR |  |  | 70 | 0 | 328.3803 | 42.6894 | 371.0697 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Project Controls4.6911472328.3803 | Corbiere and Sons Contracting118720200119-1Project Controls4.6911472328.3803Inv#007-R01 | [5 empty] | 1 | 328.3803 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 1.2677 | HR |  |  | 70 | 0 | 88.7388 | 11.536 | 100.2748 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Project Controls1.267697588.7388 | Corbiere and Sons Contracting118720200119-1Project Controls1.267697588.7388Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 88.7388 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520102 | Clearing | 0 | Project Controls | 70 | 3.6063 | HR |  |  | 70 | 0 | 252.4436 | 32.8177 | 285.2613 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Project Controls3.6063374252.4436 | Corbiere and Sons Contracting118720200119-1Project Controls3.6063374252.4436Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 252.4436 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520104 | Clearing | 0 | Project Controls | 70 | 1.0045 | HR |  |  | 70 | 0 | 70.3145 | 9.1409 | 79.4554 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1Project Controls1.004492970.3145 | Corbiere and Sons Contracting118720200119-1Project Controls1.004492970.3145Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 70.3145 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53510111 | Access | 0 | L.O.A. | 210 | 2.3456 | DAY |  |  |  | 0 | 492.5705 | 64.0342 | 556.6047 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1L.O.A.2.3455736492.5705 | Corbiere and Sons Contracting118720200119-1L.O.A.2.3455736492.5705Inv#007-R01 | [5 empty] | 1 | 492.5705 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 0.63385 | DAY |  |  |  | 0 | 133.1082 | 17.3041 | 150.4123 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1L.O.A.0.6338487133.1082 | Corbiere and Sons Contracting118720200119-1L.O.A.0.6338487133.1082Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 133.1082 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1.8032 | DAY |  |  |  | 0 | 378.6654 | 49.2265 | 427.8919 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1L.O.A.1.8031687378.6654 | Corbiere and Sons Contracting118720200119-1L.O.A.1.8031687378.6654Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 378.6654 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1187 | 20200119-1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 0.50225 | DAY |  |  |  | 0 | 105.4718 | 13.7113 | 119.1831 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118720200119-1L.O.A.0.5022465105.4718 | Corbiere and Sons Contracting118720200119-1L.O.A.0.5022465105.4718Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 105.4718 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1198 | 20200119-12-R1 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization and Winter Access Maintenance |  |  | Santoy Lake | 0 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting119820200119-12-R1Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting119820200119-12-R1Dozer D6 or equal- After Jan 107920.36Inv#007-R01 | [5 empty] | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1198 | 20200119-12-R1 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization and Winter Access Maintenance |  |  | Santoy Lake | 0 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting119820200119-12-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting119820200119-12-R1Light Truck - Pick up- After Jan 101243.75Inv#007-R01 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1198 | 20200119-12-R1 | 53510611 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization and Winter Access Maintenance |  |  | Santoy Lake | 0 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting119820200119-12-R1Foreman121140 | Corbiere and Sons Contracting119820200119-12-R1Foreman121140Inv#007-R01 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1198 | 20200119-12-R1 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization and Winter Access Maintenance |  |  | Santoy Lake | 0 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting119820200119-12-R1L.O.A.2420 | Corbiere and Sons Contracting119820200119-12-R1L.O.A.2420Inv#007-R01 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1198 | 20200119-12-R1 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization and Winter Access Maintenance |  |  | Santoy Lake | 0 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting119820200119-12-R1Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting119820200119-12-R1Operator - Principle - After Jan 107525Inv#007-R01 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1188 | 20200119-2 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 1.9546 | HR | 74.25 | 0 |  |  | 193.5098 | 25.1563 | 218.6661 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118820200119-2Loader JD 524 to 624 or equal1.9546447193.5098 | Corbiere and Sons Contracting118820200119-2Loader JD 524 to 624 or equal1.9546447193.5098Inv#007-R01 | [5 empty] | 1 | 193.5098 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1188 | 20200119-2 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.52821 | HR | 74.25 | 0 |  |  | 52.2925 | 6.798 | 59.0905 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118820200119-2Loader JD 524 to 624 or equal0.528207352.2925 | Corbiere and Sons Contracting118820200119-2Loader JD 524 to 624 or equal0.528207352.2925Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 52.2925 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1188 | 20200119-2 | 53520102 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 1.5026 | HR | 74.25 | 0 |  |  | 148.7614 | 19.339 | 168.1004 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118820200119-2Loader JD 524 to 624 or equal1.5026406148.7614 | Corbiere and Sons Contracting118820200119-2Loader JD 524 to 624 or equal1.5026406148.7614Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 148.7614 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1188 | 20200119-2 | 53520104 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.41854 | HR | 74.25 | 0 |  |  | 41.4353 | 5.3866 | 46.8219 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118820200119-2Loader JD 524 to 624 or equal0.418538741.4353 | Corbiere and Sons Contracting118820200119-2Loader JD 524 to 624 or equal0.418538741.4353Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 41.4353 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1188 | 20200119-2 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.39093 | DAY | 182.81 | 0 |  |  | 95.2889 | 12.3876 | 107.6765 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118820200119-2Light Truck - Pick up- After Jan 100.390928995.2889 | Corbiere and Sons Contracting118820200119-2Light Truck - Pick up- After Jan 100.390928995.2889Inv#007-R01 | [5 empty] | 1 | 95.2889 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1188 | 20200119-2 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.10564 | DAY | 182.81 | 0 |  |  | 25.7501 | 3.3475 | 29.0976 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118820200119-2Light Truck - Pick up- After Jan 100.105641525.7501 | Corbiere and Sons Contracting118820200119-2Light Truck - Pick up- After Jan 100.105641525.7501Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 25.7501 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1188 | 20200119-2 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.30053 | DAY | 182.81 | 0 |  |  | 73.2537 | 9.523 | 82.7767 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118820200119-2Light Truck - Pick up- After Jan 100.300528173.2537 | Corbiere and Sons Contracting118820200119-2Light Truck - Pick up- After Jan 100.300528173.2537Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 73.2537 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1188 | 20200119-2 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.083708 | DAY | 182.81 | 0 |  |  | 20.4038 | 2.6525 | 23.0563 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118820200119-2Light Truck - Pick up- After Jan 100.083707720.4038 | Corbiere and Sons Contracting118820200119-2Light Truck - Pick up- After Jan 100.083707720.4038Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 20.4038 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1188 | 20200119-2 | 53510111 | Access | 0 | Operator - Apprentice | 60 | 3.9093 | HR |  |  | 60 | 0 | 234.5574 | 30.4925 | 265.0499 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118820200119-2Operator - Apprentice3.9092893234.5574 | Corbiere and Sons Contracting118820200119-2Operator - Apprentice3.9092893234.5574Inv#007-R01 | [5 empty] | 1 | 234.5574 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1188 | 20200119-2 | 53520101 | Clearing | 0 | Operator - Apprentice | 60 | 1.0564 | HR |  |  | 60 | 0 | 63.3849 | 8.24 | 71.6249 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118820200119-2Operator - Apprentice1.056414563.3849 | Corbiere and Sons Contracting118820200119-2Operator - Apprentice1.056414563.3849Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 63.3849 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1188 | 20200119-2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 3.0053 | HR |  |  | 60 | 0 | 180.3169 | 23.4412 | 203.7581 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118820200119-2Operator - Apprentice3.0052811180.3169 | Corbiere and Sons Contracting118820200119-2Operator - Apprentice3.0052811180.3169Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 180.3169 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1188 | 20200119-2 | 53520104 | Clearing | 0 | Operator - Apprentice | 60 | 0.83708 | HR |  |  | 60 | 0 | 50.2247 | 6.5292 | 56.7539 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  |  | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting118820200119-2Operator - Apprentice0.837077550.2247 | Corbiere and Sons Contracting118820200119-2Operator - Apprentice0.837077550.2247Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 50.2247 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1189 | 20200119-3-R1 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A064, FB and SKD working from A068 |  |  | Eldorado Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting118920200119-3-R1Feller Buncher92160 | Corbiere and Sons Contracting118920200119-3-R1Feller Buncher92160Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1189 | 20200119-3-R1 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A064, FB and SKD working from A068 |  |  | Eldorado Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting118920200119-3-R1Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting118920200119-3-R1Grinder - 4710 Peterson or equal95011.2Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1189 | 20200119-3-R1 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A064, FB and SKD working from A068 |  |  | Eldorado Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting118920200119-3-R1Log Loader91377 | Corbiere and Sons Contracting118920200119-3-R1Log Loader91377Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1189 | 20200119-3-R1 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A064, FB and SKD working from A068 |  |  | Eldorado Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting118920200119-3-R1Skidder 91539 | Corbiere and Sons Contracting118920200119-3-R1Skidder 91539Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1189 | 20200119-3-R1 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A064, FB and SKD working from A068 |  |  | Eldorado Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting118920200119-3-R1Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting118920200119-3-R1Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1189 | 20200119-3-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A064, FB and SKD working from A068 |  |  | Eldorado Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting118920200119-3-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting118920200119-3-R1Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1189 | 20200119-3-R1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A064, FB and SKD working from A068 |  |  | Eldorado Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting118920200119-3-R1L.O.A.2420 | Corbiere and Sons Contracting118920200119-3-R1L.O.A.2420Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1189 | 20200119-3-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A064, FB and SKD working from A068 |  |  | Eldorado Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting118920200119-3-R1L.O.A.1210 | Corbiere and Sons Contracting118920200119-3-R1L.O.A.1210Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1189 | 20200119-3-R1 | 53520101 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A064, FB and SKD working from A068 |  |  | Eldorado Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting118920200119-3-R1Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting118920200119-3-R1Operator - Principle - After Jan 10221650Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1189 | 20200119-3-R1 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of Material at A064, FB and SKD working from A068 |  |  | Eldorado Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting118920200119-3-R1Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting118920200119-3-R1Operator - Principle - After Jan 1011825Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1190 | 20200119-4 | 53510111 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road Maintenance from A076-A079 |  |  | Eldorado | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting119020200119-4Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting119020200119-4Excavator - 30 ton- After Jan 1091246.05Inv#007-R01 | [5 empty] | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1190 | 20200119-4 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road Maintenance from A076-A079 |  |  | Eldorado | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting119020200119-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting119020200119-4Light Truck - Pick up- After Jan 101243.75Inv#007-R01 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1190 | 20200119-4 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road Maintenance from A076-A079 |  |  | Eldorado | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting119020200119-4L.O.A.1210 | Corbiere and Sons Contracting119020200119-4L.O.A.1210Inv#007-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1190 | 20200119-4 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road Maintenance from A076-A079 |  |  | Eldorado | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting119020200119-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting119020200119-4Operator - Principle - After Jan 1011825Inv#007-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1191 | 20200119-5 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 35 | Dynamic | 95.24 | 0 |  |  | 4444.3 | 577.759 | 5022.059 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grading and sanding of all access roads. |  |  | Wind Farm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting119120200119-5Grader - Cat 12 to 14 or equal- After Jan 10354444.3 | Corbiere and Sons Contracting119120200119-5Grader - Cat 12 to 14 or equal- After Jan 10354444.3Inv#007-R01 | [5 empty] | 1 | 4444.3 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1191 | 20200119-5 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 2.5 | Dynamic | 64.79 | 0 |  |  | 215.95 | 28.0735 | 244.0235 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grading and sanding of all access roads. |  |  | Wind Farm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting119120200119-5Sander Truck - Forestry- After Jan 102.5215.95 | Corbiere and Sons Contracting119120200119-5Sander Truck - Forestry- After Jan 102.5215.95Inv#007-R01 | [5 empty] | 1 | 215.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1191 | 20200119-5 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grading and sanding of all access roads. |  |  | Wind Farm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting119120200119-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting119120200119-5Light Truck - Pick up- After Jan 102487.5Inv#007-R01 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1191 | 20200119-5 | 53510111 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grading and sanding of all access roads. |  |  | Wind Farm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting119120200119-5Foreman121140 | Corbiere and Sons Contracting119120200119-5Foreman121140Inv#007-R01 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1191 | 20200119-5 | 53510111 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grading and sanding of all access roads. |  |  | Wind Farm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting119120200119-5L.O.A.51050 | Corbiere and Sons Contracting119120200119-5L.O.A.51050Inv#007-R01 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1191 | 20200119-5 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 50 | HR |  |  | 75 | 0 | 3750 | 487.5 | 4237.5 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grading and sanding of all access roads. |  |  | Wind Farm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting119120200119-5Operator - Principle - After Jan 10503750 | Corbiere and Sons Contracting119120200119-5Operator - Principle - After Jan 10503750Inv#007-R01 | [5 empty] | 1 | 3750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1192 | 20200119-6 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 5 | HR | 417.6 | 0 |  |  | 2784 | 361.92 | 3145.92 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of material at A085 | 1 | A-085 to A-117 | Windfarm | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting119220200119-6Grinder - 4710 Peterson or equal52784 | Corbiere and Sons Contracting119220200119-6Grinder - 4710 Peterson or equal52784Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2784 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1192 | 20200119-6 | 53520102 | Clearing | 0 | Log Loader | 153 | 5 | HR | 114.75 | 0 |  |  | 765 | 99.45 | 864.45 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of material at A085 | 1 | A-085 to A-117 | Windfarm | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting119220200119-6Log Loader5765 | Corbiere and Sons Contracting119220200119-6Log Loader5765Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 765 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1192 | 20200119-6 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of material at A085 | 1 | A-085 to A-117 | Windfarm | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting119220200119-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting119220200119-6Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1192 | 20200119-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of material at A085 | 1 | A-085 to A-117 | Windfarm | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting119220200119-6L.O.A.1210 | Corbiere and Sons Contracting119220200119-6L.O.A.1210Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1192 | 20200119-6 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Grinding of material at A085 | 1 | A-085 to A-117 | Windfarm | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting119220200119-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting119220200119-6Operator - Principle - After Jan 1011825Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1193 | 20200119-7 | 53510111 | Access | 0 | Dozer - D5 or equal- After Jan 10 | 80.93 | 9 | Dynamic | 60.7 | 0 |  |  | 728.37 | 94.6881 | 823.0581 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road building and Maintenance from A118 to A127 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting119320200119-7Dozer - D5 or equal- After Jan 109728.37 | Corbiere and Sons Contracting119320200119-7Dozer - D5 or equal- After Jan 109728.37Inv#007-R01 | [5 empty] | 1 | 728.37 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1193 | 20200119-7 | 53510111 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 110.22 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road building and Maintenance from A118 to A127 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting119320200119-7Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting119320200119-7Excavator - 36 ton- After Jan 10182645.28Inv#007-R01 | [5 empty] | 1 | 2645.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1193 | 20200119-7 | 53510111 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road building and Maintenance from A118 to A127 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting119320200119-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting119320200119-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#007-R01 | [5 empty] | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1193 | 20200119-7 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road building and Maintenance from A118 to A127 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting119320200119-7Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting119320200119-7Light Truck - Pick up- After Jan 103731.25Inv#007-R01 | [5 empty] | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1193 | 20200119-7 | 53510111 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road building and Maintenance from A118 to A127 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting119320200119-7Foreman121140 | Corbiere and Sons Contracting119320200119-7Foreman121140Inv#007-R01 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1193 | 20200119-7 | 53510111 | Access | 0 | Labourer - General | 60 | 11 | HR |  |  |  | 0 | 660 | 85.8 | 745.8 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road building and Maintenance from A118 to A127 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting119320200119-7Labourer - General11660 | Corbiere and Sons Contracting119320200119-7Labourer - General11660Inv#007-R01 | [5 empty] | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1193 | 20200119-7 | 53510111 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road building and Maintenance from A118 to A127 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting119320200119-7L.O.A.51050 | Corbiere and Sons Contracting119320200119-7L.O.A.51050Inv#007-R01 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1193 | 20200119-7 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Winter Road building and Maintenance from A118 to A127 |  |  | Wolf Lake Road | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting119320200119-7Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting119320200119-7Operator - Principle - After Jan 10332475Inv#007-R01 | [5 empty] | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1194 | 20200119-8 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A123 |  |  | Wolf Lake | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting119420200119-8Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting119420200119-8Chainsaw and consumables- After Jan 103180Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1194 | 20200119-8 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A123 |  |  | Wolf Lake | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting119420200119-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting119420200119-8Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1194 | 20200119-8 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A123 |  |  | Wolf Lake | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting119420200119-8Foreman121140 | Corbiere and Sons Contracting119420200119-8Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1194 | 20200119-8 | 53520104 | Clearing | 0 | Labourer - Specialized | 70 | 33 | HR |  |  |  | 0 | 2310 | 300.3 | 2610.3 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A123 |  |  | Wolf Lake | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting119420200119-8Labourer - Specialized332310 | Corbiere and Sons Contracting119420200119-8Labourer - Specialized332310Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1194 | 20200119-8 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-19 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  |  |  | Approved |  |  | Handfelling from A123 |  |  | Wolf Lake | 0 |  |  | 37 | 43860 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting119420200119-8L.O.A.4840 | Corbiere and Sons Contracting119420200119-8L.O.A.4840Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1.5084 | DAY | 182.81 | 0 |  |  | 367.6644 | 47.7964 | 415.4608 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Light Truck - Pick up- After Jan 101.5083668367.6644 | Corbiere and Sons Contracting122320200120-1Light Truck - Pick up- After Jan 101.5083668367.6644Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 367.6644 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510107 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.050139 | DAY | 182.81 | 0 |  |  | 12.2214 | 1.5888 | 13.8102 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Light Truck - Pick up- After Jan 100.050139212.2214 | Corbiere and Sons Contracting122320200120-1Light Truck - Pick up- After Jan 100.050139212.2214Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 6.1107 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.6587 | DAY | 182.81 | 0 |  |  | 160.5581 | 20.8726 | 181.4307 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Light Truck - Pick up- After Jan 100.6587160.5581 | Corbiere and Sons Contracting122320200120-1Light Truck - Pick up- After Jan 100.6587160.5581Inv#007-R01 | [5 empty] | 1 | 160.5581 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.25237 | DAY | 182.81 | 0 |  |  | 61.5163 | 7.9971 | 69.5134 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Light Truck - Pick up- After Jan 100.252374761.5163 | Corbiere and Sons Contracting122320200120-1Light Truck - Pick up- After Jan 100.252374761.5163Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 61.5163 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.71107 | DAY | 182.81 | 0 |  |  | 173.3241 | 22.5321 | 195.8562 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Light Truck - Pick up- After Jan 100.7110734173.3241 | Corbiere and Sons Contracting122320200120-1Light Truck - Pick up- After Jan 100.7110734173.3241Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 173.3241 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.64008 | DAY | 182.81 | 0 |  |  | 156.02 | 20.2826 | 176.3026 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Light Truck - Pick up- After Jan 100.6400822156.02 | Corbiere and Sons Contracting122320200120-1Light Truck - Pick up- After Jan 100.6400822156.02Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 156.02 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520107 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.1534 | DAY | 182.81 | 0 |  |  | 37.3905 | 4.8608 | 42.2513 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Light Truck - Pick up- After Jan 100.153396837.3905 | Corbiere and Sons Contracting122320200120-1Light Truck - Pick up- After Jan 100.153396837.3905Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 37.3905 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510106 | Access | 0 | Project Manager | 110 | 3.6201 | HR |  |  | 110 | 0 | 398.2088 | 51.7671 | 449.9759 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Project Manager3.6200804398.2088 | Corbiere and Sons Contracting122320200120-1Project Manager3.6200804398.2088Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 398.2088 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510107 | Access | 0 | Project Manager | 110 | 0.12033 | HR |  |  | 110 | 0 | 13.2368 | 1.7208 | 14.9576 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Project Manager0.120334213.2368 | Corbiere and Sons Contracting122320200120-1Project Manager0.120334213.2368Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 6.6184 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510111 | Access | 0 | Project Manager | 110 | 1.5809 | HR |  |  | 110 | 0 | 173.8968 | 22.6066 | 196.5034 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Project Manager1.5808801173.8968 | Corbiere and Sons Contracting122320200120-1Project Manager1.5808801173.8968Inv#007-R01 | [5 empty] | 1 | 173.8968 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 0.6057 | HR |  |  | 110 | 0 | 66.6269 | 8.6615 | 75.2884 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Project Manager0.605699266.6269 | Corbiere and Sons Contracting122320200120-1Project Manager0.605699266.6269Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 66.6269 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520102 | Clearing | 0 | Project Manager | 110 | 1.7066 | HR |  |  | 110 | 0 | 187.7234 | 24.404 | 212.1274 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Project Manager1.7065761187.7234 | Corbiere and Sons Contracting122320200120-1Project Manager1.7065761187.7234Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 187.7234 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520104 | Clearing | 0 | Project Manager | 110 | 1.5362 | HR |  |  | 110 | 0 | 168.9817 | 21.9676 | 190.9493 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Project Manager1.5361973168.9817 | Corbiere and Sons Contracting122320200120-1Project Manager1.5361973168.9817Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 168.9817 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520107 | Clearing | 0 | Project Manager | 110 | 0.36815 | HR |  |  | 110 | 0 | 40.4968 | 5.2646 | 45.7614 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Project Manager0.368152340.4968 | Corbiere and Sons Contracting122320200120-1Project Manager0.368152340.4968Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 40.4968 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510106 | Access | 0 | Superintendent | 105 | 3.6201 | HR |  |  | 105 | 0 | 380.1084 | 49.4141 | 429.5225 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Superintendent3.6200804380.1084 | Corbiere and Sons Contracting122320200120-1Superintendent3.6200804380.1084Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 380.1084 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510107 | Access | 0 | Superintendent | 105 | 0.12033 | HR |  |  | 105 | 0 | 12.6351 | 1.6426 | 14.2777 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Superintendent0.120334212.6351 | Corbiere and Sons Contracting122320200120-1Superintendent0.120334212.6351Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 6.3175 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510111 | Access | 0 | Superintendent | 105 | 1.5809 | HR |  |  | 105 | 0 | 165.9924 | 21.579 | 187.5714 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Superintendent1.5808801165.9924 | Corbiere and Sons Contracting122320200120-1Superintendent1.5808801165.9924Inv#007-R01 | [5 empty] | 1 | 165.9924 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 0.6057 | HR |  |  | 105 | 0 | 63.5984 | 8.2678 | 71.8662 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Superintendent0.605699263.5984 | Corbiere and Sons Contracting122320200120-1Superintendent0.605699263.5984Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 63.5984 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520102 | Clearing | 0 | Superintendent | 105 | 1.7066 | HR |  |  | 105 | 0 | 179.1905 | 23.2948 | 202.4853 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Superintendent1.7065761179.1905 | Corbiere and Sons Contracting122320200120-1Superintendent1.7065761179.1905Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 179.1905 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520104 | Clearing | 0 | Superintendent | 105 | 1.5362 | HR |  |  | 105 | 0 | 161.3007 | 20.9691 | 182.2698 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Superintendent1.5361973161.3007 | Corbiere and Sons Contracting122320200120-1Superintendent1.5361973161.3007Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 161.3007 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520107 | Clearing | 0 | Superintendent | 105 | 0.36815 | HR |  |  | 105 | 0 | 38.656 | 5.0253 | 43.6813 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Superintendent0.368152338.656 | Corbiere and Sons Contracting122320200120-1Superintendent0.368152338.656Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 38.656 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510106 | Access | 0 | Project Coordinator | 80 | 3.6201 | HR |  |  | 80 | 0 | 289.6064 | 37.6488 | 327.2552 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Project Coordinator3.6200804289.6064 | Corbiere and Sons Contracting122320200120-1Project Coordinator3.6200804289.6064Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 289.6064 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510107 | Access | 0 | Project Coordinator | 80 | 0.12033 | HR |  |  | 80 | 0 | 9.6267 | 1.2515 | 10.8782 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Project Coordinator0.12033429.6267 | Corbiere and Sons Contracting122320200120-1Project Coordinator0.12033429.6267Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 4.8133 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510111 | Access | 0 | Project Coordinator | 80 | 1.5809 | HR |  |  | 80 | 0 | 126.4704 | 16.4412 | 142.9116 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Project Coordinator1.5808801126.4704 | Corbiere and Sons Contracting122320200120-1Project Coordinator1.5808801126.4704Inv#007-R01 | [5 empty] | 1 | 126.4704 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 0.6057 | HR |  |  | 80 | 0 | 48.4559 | 6.2993 | 54.7552 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Project Coordinator0.605699248.4559 | Corbiere and Sons Contracting122320200120-1Project Coordinator0.605699248.4559Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 48.4559 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520102 | Clearing | 0 | Project Coordinator | 80 | 1.7066 | HR |  |  | 80 | 0 | 136.5261 | 17.7484 | 154.2745 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Project Coordinator1.7065761136.5261 | Corbiere and Sons Contracting122320200120-1Project Coordinator1.7065761136.5261Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 136.5261 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520104 | Clearing | 0 | Project Coordinator | 80 | 1.5362 | HR |  |  | 80 | 0 | 122.8958 | 15.9765 | 138.8723 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Project Coordinator1.5361973122.8958 | Corbiere and Sons Contracting122320200120-1Project Coordinator1.5361973122.8958Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 122.8958 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520107 | Clearing | 0 | Project Coordinator | 80 | 0.36815 | HR |  |  | 80 | 0 | 29.4522 | 3.8288 | 33.281 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Project Coordinator0.368152329.4522 | Corbiere and Sons Contracting122320200120-1Project Coordinator0.368152329.4522Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 29.4522 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510106 | Access | 0 | Safety Advisor | 85 | 3.6201 | HR |  |  | 85 | 0 | 307.7068 | 40.0019 | 347.7087 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Safety Advisor3.6200804307.7068 | Corbiere and Sons Contracting122320200120-1Safety Advisor3.6200804307.7068Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 307.7068 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510107 | Access | 0 | Safety Advisor | 85 | 0.12033 | HR |  |  | 85 | 0 | 10.2284 | 1.3297 | 11.5581 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Safety Advisor0.120334210.2284 | Corbiere and Sons Contracting122320200120-1Safety Advisor0.120334210.2284Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 5.1142 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510111 | Access | 0 | Safety Advisor | 85 | 1.5809 | HR |  |  | 85 | 0 | 134.3748 | 17.4687 | 151.8435 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Safety Advisor1.5808801134.3748 | Corbiere and Sons Contracting122320200120-1Safety Advisor1.5808801134.3748Inv#007-R01 | [5 empty] | 1 | 134.3748 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 0.6057 | HR |  |  | 85 | 0 | 51.4844 | 6.693 | 58.1774 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Safety Advisor0.605699251.4844 | Corbiere and Sons Contracting122320200120-1Safety Advisor0.605699251.4844Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 51.4844 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520102 | Clearing | 0 | Safety Advisor | 85 | 1.7066 | HR |  |  | 85 | 0 | 145.059 | 18.8577 | 163.9167 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Safety Advisor1.7065761145.059 | Corbiere and Sons Contracting122320200120-1Safety Advisor1.7065761145.059Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 145.059 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520104 | Clearing | 0 | Safety Advisor | 85 | 1.5362 | HR |  |  | 85 | 0 | 130.5768 | 16.975 | 147.5518 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Safety Advisor1.5361973130.5768 | Corbiere and Sons Contracting122320200120-1Safety Advisor1.5361973130.5768Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 130.5768 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520107 | Clearing | 0 | Safety Advisor | 85 | 0.36815 | HR |  |  | 85 | 0 | 31.2929 | 4.0681 | 35.361 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Safety Advisor0.368152331.2929 | Corbiere and Sons Contracting122320200120-1Safety Advisor0.368152331.2929Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 31.2929 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510106 | Access | 0 | Site Administrator | 50 | 3.0167 | HR |  |  | 50 | 0 | 150.8367 | 19.6088 | 170.4455 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Site Administrator3.0167337150.8367 | Corbiere and Sons Contracting122320200120-1Site Administrator3.0167337150.8367Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 150.8367 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510107 | Access | 0 | Site Administrator | 50 | 0.10028 | HR |  |  | 50 | 0 | 5.0139 | 0.65181 | 5.6657 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Site Administrator0.10027855.0139 | Corbiere and Sons Contracting122320200120-1Site Administrator0.10027855.0139Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 2.5069 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510111 | Access | 0 | Site Administrator | 50 | 1.3174 | HR |  |  | 50 | 0 | 65.87 | 8.5631 | 74.4331 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Site Administrator1.317465.87 | Corbiere and Sons Contracting122320200120-1Site Administrator1.317465.87Inv#007-R01 | [5 empty] | 1 | 65.87 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520101 | Clearing | 0 | Site Administrator | 50 | 0.50475 | HR |  |  | 50 | 0 | 25.2375 | 3.2809 | 28.5184 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Site Administrator0.504749325.2375 | Corbiere and Sons Contracting122320200120-1Site Administrator0.504749325.2375Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 25.2375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520102 | Clearing | 0 | Site Administrator | 50 | 1.4221 | HR |  |  | 50 | 0 | 71.1073 | 9.2439 | 80.3512 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Site Administrator1.422146771.1073 | Corbiere and Sons Contracting122320200120-1Site Administrator1.422146771.1073Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 71.1073 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520104 | Clearing | 0 | Site Administrator | 50 | 1.2802 | HR |  |  | 50 | 0 | 64.0082 | 8.3211 | 72.3293 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Site Administrator1.280164564.0082 | Corbiere and Sons Contracting122320200120-1Site Administrator1.280164564.0082Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 64.0082 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520107 | Clearing | 0 | Site Administrator | 50 | 0.30679 | HR |  |  | 50 | 0 | 15.3397 | 1.9942 | 17.3339 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Site Administrator0.306793615.3397 | Corbiere and Sons Contracting122320200120-1Site Administrator0.306793615.3397Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 15.3397 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510106 | Access | 0 | Project Controls | 70 | 3.6201 | HR |  |  | 70 | 0 | 253.4056 | 32.9427 | 286.3483 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Project Controls3.6200804253.4056 | Corbiere and Sons Contracting122320200120-1Project Controls3.6200804253.4056Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 253.4056 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510107 | Access | 0 | Project Controls | 70 | 0.12033 | HR |  |  | 70 | 0 | 8.4234 | 1.095 | 9.5184 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Project Controls0.12033428.4234 | Corbiere and Sons Contracting122320200120-1Project Controls0.12033428.4234Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 4.2117 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510111 | Access | 0 | Project Controls | 70 | 1.5809 | HR |  |  | 70 | 0 | 110.6616 | 14.386 | 125.0476 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Project Controls1.5808801110.6616 | Corbiere and Sons Contracting122320200120-1Project Controls1.5808801110.6616Inv#007-R01 | [5 empty] | 1 | 110.6616 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 0.6057 | HR |  |  | 70 | 0 | 42.3989 | 5.5119 | 47.9108 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Project Controls0.605699242.3989 | Corbiere and Sons Contracting122320200120-1Project Controls0.605699242.3989Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 42.3989 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520102 | Clearing | 0 | Project Controls | 70 | 1.7066 | HR |  |  | 70 | 0 | 119.4603 | 15.5298 | 134.9901 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Project Controls1.7065761119.4603 | Corbiere and Sons Contracting122320200120-1Project Controls1.7065761119.4603Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 119.4603 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520104 | Clearing | 0 | Project Controls | 70 | 1.5362 | HR |  |  | 70 | 0 | 107.5338 | 13.9794 | 121.5132 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Project Controls1.5361973107.5338 | Corbiere and Sons Contracting122320200120-1Project Controls1.5361973107.5338Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 107.5338 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520107 | Clearing | 0 | Project Controls | 70 | 0.36815 | HR |  |  | 70 | 0 | 25.7707 | 3.3502 | 29.1209 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1Project Controls0.368152325.7707 | Corbiere and Sons Contracting122320200120-1Project Controls0.368152325.7707Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 25.7707 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510106 | Access | 0 | L.O.A. | 210 | 1.81 | DAY |  |  |  | 0 | 380.1084 | 49.4141 | 429.5225 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1L.O.A.1.8100402380.1084 | Corbiere and Sons Contracting122320200120-1L.O.A.1.8100402380.1084Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 380.1084 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510107 | Access | 0 | L.O.A. | 210 | 0.060167 | DAY |  |  |  | 0 | 12.6351 | 1.6426 | 14.2777 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1L.O.A.0.060167112.6351 | Corbiere and Sons Contracting122320200120-1L.O.A.0.060167112.6351Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 6.3175 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53510111 | Access | 0 | L.O.A. | 210 | 0.79044 | DAY |  |  |  | 0 | 165.9924 | 21.579 | 187.5714 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1L.O.A.0.79044165.9924 | Corbiere and Sons Contracting122320200120-1L.O.A.0.79044165.9924Inv#007-R01 | [5 empty] | 1 | 165.9924 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 0.30285 | DAY |  |  |  | 0 | 63.5984 | 8.2678 | 71.8662 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1L.O.A.0.302849663.5984 | Corbiere and Sons Contracting122320200120-1L.O.A.0.302849663.5984Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 63.5984 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 0.85329 | DAY |  |  |  | 0 | 179.1905 | 23.2948 | 202.4853 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1L.O.A.0.853288179.1905 | Corbiere and Sons Contracting122320200120-1L.O.A.0.853288179.1905Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 179.1905 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 0.7681 | DAY |  |  |  | 0 | 161.3007 | 20.9691 | 182.2698 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1L.O.A.0.7680987161.3007 | Corbiere and Sons Contracting122320200120-1L.O.A.0.7680987161.3007Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 161.3007 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1223 | 20200120-1 | 53520107 | Clearing | 0 | L.O.A. | 210 | 0.18408 | DAY |  |  |  | 0 | 38.656 | 5.0253 | 43.6813 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision |  |  | Supervision | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122320200120-1L.O.A.0.184076238.656 | Corbiere and Sons Contracting122320200120-1L.O.A.0.184076238.656Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 38.656 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1238 | 20200120-14 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-20 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Maintenance and Mobilization | 6 |  |  | 0 | 43856 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting123820200120-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting123820200120-14Light Truck - Pick up- After Jan 101243.75Inv#009 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1238 | 20200120-14 | 53510611 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-20 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Maintenance and Mobilization | 6 |  |  | 0 | 43856 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting123820200120-14Foreman121140 | Corbiere and Sons Contracting123820200120-14Foreman121140Inv#009 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1238 | 20200120-14 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-20 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Maintenance and Mobilization | 6 |  |  | 0 | 43856 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting123820200120-14L.O.A.1210 | Corbiere and Sons Contracting123820200120-14L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1224 | 20200120-2 | 53510106 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 1.5084 | HR | 74.25 | 0 |  |  | 149.3283 | 19.4127 | 168.741 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | Yard Maintenance | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122420200120-2Loader JD 524 to 624 or equal1.5083668149.3283 | Corbiere and Sons Contracting122420200120-2Loader JD 524 to 624 or equal1.5083668149.3283Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 149.3283 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1224 | 20200120-2 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 0.6587 | HR | 74.25 | 0 |  |  | 65.2113 | 8.4775 | 73.6888 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | Yard Maintenance | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122420200120-2Loader JD 524 to 624 or equal0.658765.2113 | Corbiere and Sons Contracting122420200120-2Loader JD 524 to 624 or equal0.658765.2113Inv#007-R01 | [5 empty] | 1 | 65.2113 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1224 | 20200120-2 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.25237 | HR | 74.25 | 0 |  |  | 24.9851 | 3.2481 | 28.2332 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | Yard Maintenance | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122420200120-2Loader JD 524 to 624 or equal0.252374724.9851 | Corbiere and Sons Contracting122420200120-2Loader JD 524 to 624 or equal0.252374724.9851Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 24.9851 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1224 | 20200120-2 | 53520102 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.71107 | HR | 74.25 | 0 |  |  | 70.3963 | 9.1515 | 79.5478 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | Yard Maintenance | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122420200120-2Loader JD 524 to 624 or equal0.711073470.3963 | Corbiere and Sons Contracting122420200120-2Loader JD 524 to 624 or equal0.711073470.3963Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 70.3963 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1224 | 20200120-2 | 53520104 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.64008 | HR | 74.25 | 0 |  |  | 63.3681 | 8.2379 | 71.606 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | Yard Maintenance | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122420200120-2Loader JD 524 to 624 or equal0.640082263.3681 | Corbiere and Sons Contracting122420200120-2Loader JD 524 to 624 or equal0.640082263.3681Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 63.3681 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1224 | 20200120-2 | 53520107 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.1534 | HR | 74.25 | 0 |  |  | 15.1863 | 1.9742 | 17.1605 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | Yard Maintenance | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122420200120-2Loader JD 524 to 624 or equal0.153396815.1863 | Corbiere and Sons Contracting122420200120-2Loader JD 524 to 624 or equal0.153396815.1863Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 15.1863 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1224 | 20200120-2 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.30167 | DAY | 182.81 | 0 |  |  | 73.5329 | 9.5593 | 83.0922 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | Yard Maintenance | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122420200120-2Light Truck - Pick up- After Jan 100.301673473.5329 | Corbiere and Sons Contracting122420200120-2Light Truck - Pick up- After Jan 100.301673473.5329Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 73.5329 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1224 | 20200120-2 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.13174 | DAY | 182.81 | 0 |  |  | 32.1116 | 4.1745 | 36.2861 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | Yard Maintenance | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122420200120-2Light Truck - Pick up- After Jan 100.1317432.1116 | Corbiere and Sons Contracting122420200120-2Light Truck - Pick up- After Jan 100.1317432.1116Inv#007-R01 | [5 empty] | 1 | 32.1116 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1224 | 20200120-2 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.050475 | DAY | 182.81 | 0 |  |  | 12.3033 | 1.5994 | 13.9027 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | Yard Maintenance | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122420200120-2Light Truck - Pick up- After Jan 100.050474912.3033 | Corbiere and Sons Contracting122420200120-2Light Truck - Pick up- After Jan 100.050474912.3033Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 12.3033 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1224 | 20200120-2 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.14221 | DAY | 182.81 | 0 |  |  | 34.6648 | 4.5064 | 39.1712 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | Yard Maintenance | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122420200120-2Light Truck - Pick up- After Jan 100.142214734.6648 | Corbiere and Sons Contracting122420200120-2Light Truck - Pick up- After Jan 100.142214734.6648Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 34.6648 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1224 | 20200120-2 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.12802 | DAY | 182.81 | 0 |  |  | 31.204 | 4.0565 | 35.2605 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | Yard Maintenance | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122420200120-2Light Truck - Pick up- After Jan 100.128016431.204 | Corbiere and Sons Contracting122420200120-2Light Truck - Pick up- After Jan 100.128016431.204Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 31.204 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1224 | 20200120-2 | 53520107 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.030679 | DAY | 182.81 | 0 |  |  | 7.4781 | 0.97215 | 8.4503 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | Yard Maintenance | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122420200120-2Light Truck - Pick up- After Jan 100.03067947.4781 | Corbiere and Sons Contracting122420200120-2Light Truck - Pick up- After Jan 100.03067947.4781Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 7.4781 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1224 | 20200120-2 | 53510106 | Access | 0 | Operator - Apprentice | 60 | 3.0167 | HR |  |  | 60 | 0 | 181.004 | 23.5305 | 204.5345 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | Yard Maintenance | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122420200120-2Operator - Apprentice3.0167337181.004 | Corbiere and Sons Contracting122420200120-2Operator - Apprentice3.0167337181.004Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 181.004 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1224 | 20200120-2 | 53510111 | Access | 0 | Operator - Apprentice | 60 | 1.3174 | HR |  |  | 60 | 0 | 79.044 | 10.2757 | 89.3197 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | Yard Maintenance | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122420200120-2Operator - Apprentice1.317479.044 | Corbiere and Sons Contracting122420200120-2Operator - Apprentice1.317479.044Inv#007-R01 | [5 empty] | 1 | 79.044 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1224 | 20200120-2 | 53520101 | Clearing | 0 | Operator - Apprentice | 60 | 0.50475 | HR |  |  | 60 | 0 | 30.285 | 3.9371 | 34.2221 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | Yard Maintenance | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122420200120-2Operator - Apprentice0.504749330.285 | Corbiere and Sons Contracting122420200120-2Operator - Apprentice0.504749330.285Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 30.285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1224 | 20200120-2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 1.4221 | HR |  |  | 60 | 0 | 85.3288 | 11.0927 | 96.4215 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | Yard Maintenance | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122420200120-2Operator - Apprentice1.422146785.3288 | Corbiere and Sons Contracting122420200120-2Operator - Apprentice1.422146785.3288Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 85.3288 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1224 | 20200120-2 | 53520104 | Clearing | 0 | Operator - Apprentice | 60 | 1.2802 | HR |  |  | 60 | 0 | 76.8099 | 9.9853 | 86.7952 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | Yard Maintenance | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122420200120-2Operator - Apprentice1.280164576.8099 | Corbiere and Sons Contracting122420200120-2Operator - Apprentice1.280164576.8099Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 76.8099 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1224 | 20200120-2 | 53520107 | Clearing | 0 | Operator - Apprentice | 60 | 0.30679 | HR |  |  | 60 | 0 | 18.4076 | 2.393 | 20.8006 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance |  |  | Yard Maintenance | 1 |  |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting122420200120-2Operator - Apprentice0.306793618.4076 | Corbiere and Sons Contracting122420200120-2Operator - Apprentice0.306793618.4076Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 18.4076 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1225 | 20200120-3 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A062-A067; Clearing from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122520200120-3Feller Buncher92160 | Corbiere and Sons Contracting122520200120-3Feller Buncher92160Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1225 | 20200120-3 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 6 | HR | 417.6 | 0 |  |  | 3340.8 | 434.304 | 3775.104 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A062-A067; Clearing from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122520200120-3Grinder - 4710 Peterson or equal63340.8 | Corbiere and Sons Contracting122520200120-3Grinder - 4710 Peterson or equal63340.8Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3340.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1225 | 20200120-3 | 53520102 | Clearing | 0 | Log Loader | 153 | 6 | HR | 114.75 | 0 |  |  | 918 | 119.34 | 1037.34 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A062-A067; Clearing from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122520200120-3Log Loader6918 | Corbiere and Sons Contracting122520200120-3Log Loader6918Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 918 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1225 | 20200120-3 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A062-A067; Clearing from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122520200120-3Skidder 91539 | Corbiere and Sons Contracting122520200120-3Skidder 91539Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1225 | 20200120-3 | 53520107 | Clearing | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A062-A067; Clearing from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122520200120-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting122520200120-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1225 | 20200120-3 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A062-A067; Clearing from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122520200120-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting122520200120-3Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1225 | 20200120-3 | 53520107 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A062-A067; Clearing from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122520200120-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting122520200120-3Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1225 | 20200120-3 | 53520107 | Clearing | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 10 | Dynamic | 91.79 | 0 |  |  | 1223.9 | 159.107 | 1383.007 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A062-A067; Clearing from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122520200120-3Tractor Trailer - 60 Ton- After Jan 10101223.9 | Corbiere and Sons Contracting122520200120-3Tractor Trailer - 60 Ton- After Jan 10101223.9Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 1223.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1225 | 20200120-3 | 53520101 | Clearing | 0 | Foreman | 95 | 1 | HR |  |  | 95 | 0 | 95 | 12.35 | 107.35 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A062-A067; Clearing from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122520200120-3Foreman195 | Corbiere and Sons Contracting122520200120-3Foreman195Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1225 | 20200120-3 | 53520102 | Clearing | 0 | Foreman | 95 | 1 | HR |  |  | 95 | 0 | 95 | 12.35 | 107.35 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A062-A067; Clearing from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122520200120-3Foreman195 | Corbiere and Sons Contracting122520200120-3Foreman195Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1225 | 20200120-3 | 53520107 | Clearing | 0 | Driver - AZ | 70 | 5 | HR |  |  | 105 | 0 | 350 | 45.5 | 395.5 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A062-A067; Clearing from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122520200120-3Driver - AZ5350 | Corbiere and Sons Contracting122520200120-3Driver - AZ5350Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1225 | 20200120-3 | 53520107 | Clearing | 0 | Labourer - General | 60 | 6 | HR |  |  |  | 0 | 360 | 46.8 | 406.8 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A062-A067; Clearing from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122520200120-3Labourer - General6360 | Corbiere and Sons Contracting122520200120-3Labourer - General6360Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1225 | 20200120-3 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A062-A067; Clearing from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122520200120-3L.O.A.2420 | Corbiere and Sons Contracting122520200120-3L.O.A.2420Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1225 | 20200120-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A062-A067; Clearing from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122520200120-3L.O.A.1210 | Corbiere and Sons Contracting122520200120-3L.O.A.1210Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1225 | 20200120-3 | 53520101 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A062-A067; Clearing from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122520200120-3Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting122520200120-3Operator - Principle - After Jan 10221650Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1225 | 20200120-3 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A062-A067; Clearing from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122520200120-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting122520200120-3Operator - Principle - After Jan 1011825Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1226 | 20200120-4 | 53510106 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building from A076-A079; Rd. Building from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122620200120-4Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting122620200120-4Excavator - 30 ton- After Jan 1091246.05Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1226 | 20200120-4 | 53510106 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building from A076-A079; Rd. Building from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122620200120-4Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting122620200120-4Excavator - 36 ton- After Jan 1091322.64Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1226 | 20200120-4 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 8.5 | Dynamic | 64.79 | 0 |  |  | 734.23 | 95.4499 | 829.6799 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building from A076-A079; Rd. Building from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122620200120-4Sander Truck - Forestry- After Jan 108.5734.23 | Corbiere and Sons Contracting122620200120-4Sander Truck - Forestry- After Jan 108.5734.23Inv#007-R01 | [5 empty] | 1 | 734.23 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1226 | 20200120-4 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building from A076-A079; Rd. Building from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122620200120-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting122620200120-4Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1226 | 20200120-4 | 53510107 | Access | 0 | Foreman | 95 | 1 | HR |  |  | 95 | 0 | 95 | 12.35 | 107.35 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building from A076-A079; Rd. Building from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122620200120-4Foreman195 | Corbiere and Sons Contracting122620200120-4Foreman195Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1226 | 20200120-4 | 53510111 | Access | 0 | Foreman | 95 | 1 | HR |  |  | 95 | 0 | 95 | 12.35 | 107.35 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building from A076-A079; Rd. Building from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122620200120-4Foreman195 | Corbiere and Sons Contracting122620200120-4Foreman195Inv#007-R01 |  | WF1 Mob/Demob |  |  | 1 | 1 | 95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1226 | 20200120-4 | 53510107 | Access | 0 | Driver - AZ | 70 | 5 | HR |  |  | 105 | 0 | 350 | 45.5 | 395.5 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building from A076-A079; Rd. Building from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122620200120-4Driver - AZ5350 | Corbiere and Sons Contracting122620200120-4Driver - AZ5350Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1226 | 20200120-4 | 53510111 | Access | 0 | Driver - AZ | 70 | 8.5 | HR |  |  | 105 | 0 | 595 | 77.35 | 672.35 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building from A076-A079; Rd. Building from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122620200120-4Driver - AZ8.5595 | Corbiere and Sons Contracting122620200120-4Driver - AZ8.5595Inv#007-R01 | [5 empty] | 1 | 595 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1226 | 20200120-4 | 53510107 | Access | 0 | Labourer - General | 60 | 5 | HR |  |  |  | 0 | 300 | 39 | 339 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building from A076-A079; Rd. Building from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122620200120-4Labourer - General5300 | Corbiere and Sons Contracting122620200120-4Labourer - General5300Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1226 | 20200120-4 | 53510106 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building from A076-A079; Rd. Building from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122620200120-4L.O.A.2420 | Corbiere and Sons Contracting122620200120-4L.O.A.2420Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1226 | 20200120-4 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building from A076-A079; Rd. Building from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122620200120-4L.O.A.2420 | Corbiere and Sons Contracting122620200120-4L.O.A.2420Inv#007-R01 |  | WF1-Access |  |  | 0 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1226 | 20200120-4 | 53510106 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building from A076-A079; Rd. Building from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122620200120-4Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting122620200120-4Operator - Principle - After Jan 10221650Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1226 | 20200120-4 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Building from A076-A079; Rd. Building from A067; |  |  | Eldorado | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122620200120-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting122620200120-4Operator - Principle - After Jan 1011825Inv#007-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1227 | 20200120-5 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 21 | Dynamic | 95.24 | 0 |  |  | 2666.58 | 346.6554 | 3013.2354 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding and Grading of access roads; |  |  | Wind Farm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122720200120-5Grader - Cat 12 to 14 or equal- After Jan 10212666.58 | Corbiere and Sons Contracting122720200120-5Grader - Cat 12 to 14 or equal- After Jan 10212666.58Inv#007-R01 | [5 empty] | 1 | 2666.58 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1227 | 20200120-5 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 5 | Dynamic | 64.79 | 0 |  |  | 431.9 | 56.147 | 488.047 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding and Grading of access roads; |  |  | Wind Farm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122720200120-5Sander Truck - Forestry- After Jan 105431.9 | Corbiere and Sons Contracting122720200120-5Sander Truck - Forestry- After Jan 105431.9Inv#007-R01 | [5 empty] | 1 | 431.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1227 | 20200120-5 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding and Grading of access roads; |  |  | Wind Farm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122720200120-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting122720200120-5Light Truck - Pick up- After Jan 102487.5Inv#007-R01 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1227 | 20200120-5 | 53510111 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 9 | Dynamic | 91.79 | 0 |  |  | 1101.51 | 143.1963 | 1244.7063 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding and Grading of access roads; |  |  | Wind Farm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122720200120-5Tractor Trailer - 60 Ton- After Jan 1091101.51 | Corbiere and Sons Contracting122720200120-5Tractor Trailer - 60 Ton- After Jan 1091101.51Inv#007-R01 | [5 empty] | 1 | 1101.51 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1227 | 20200120-5 | 53510111 | Access | 0 | Operator - Intermdiate | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding and Grading of access roads; |  |  | Wind Farm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122720200120-5Operator - Intermdiate11770 | Corbiere and Sons Contracting122720200120-5Operator - Intermdiate11770Inv#007-R01 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1227 | 20200120-5 | 53510111 | Access | 0 | Labourer - General | 60 | 22 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding and Grading of access roads; |  |  | Wind Farm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122720200120-5Labourer - General221320 | Corbiere and Sons Contracting122720200120-5Labourer - General221320Inv#007-R01 | [5 empty] | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1227 | 20200120-5 | 53510111 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding and Grading of access roads; |  |  | Wind Farm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122720200120-5L.O.A.71470 | Corbiere and Sons Contracting122720200120-5L.O.A.71470Inv#007-R01 | [5 empty] | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1227 | 20200120-5 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 35 | HR |  |  | 75 | 0 | 2625 | 341.25 | 2966.25 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding and Grading of access roads; |  |  | Wind Farm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122720200120-5Operator - Principle - After Jan 10352625 | Corbiere and Sons Contracting122720200120-5Operator - Principle - After Jan 10352625Inv#007-R01 | [5 empty] | 1 | 2625 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1228 | 20200120-6 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A085; Handfelling from A098-A096; |  |  | Windfarm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122820200120-6Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting122820200120-6Grinder - 4710 Peterson or equal95011.2Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1228 | 20200120-6 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A085; Handfelling from A098-A096; |  |  | Windfarm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122820200120-6Log Loader91377 | Corbiere and Sons Contracting122820200120-6Log Loader91377Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1228 | 20200120-6 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A085; Handfelling from A098-A096; |  |  | Windfarm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122820200120-6Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting122820200120-6Chainsaw and consumables- After Jan 103180Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1228 | 20200120-6 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A085; Handfelling from A098-A096; |  |  | Windfarm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122820200120-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting122820200120-6Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1228 | 20200120-6 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A085; Handfelling from A098-A096; |  |  | Windfarm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122820200120-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting122820200120-6Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1228 | 20200120-6 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A085; Handfelling from A098-A096; |  |  | Windfarm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122820200120-6Foreman121140 | Corbiere and Sons Contracting122820200120-6Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1228 | 20200120-6 | 53520104 | Clearing | 0 | Labourer - Specialized | 70 | 33 | HR |  |  |  | 0 | 2310 | 300.3 | 2610.3 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A085; Handfelling from A098-A096; |  |  | Windfarm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122820200120-6Labourer - Specialized332310 | Corbiere and Sons Contracting122820200120-6Labourer - Specialized332310Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1228 | 20200120-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A085; Handfelling from A098-A096; |  |  | Windfarm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122820200120-6L.O.A.1210 | Corbiere and Sons Contracting122820200120-6L.O.A.1210Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1228 | 20200120-6 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A085; Handfelling from A098-A096; |  |  | Windfarm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122820200120-6L.O.A.4840 | Corbiere and Sons Contracting122820200120-6L.O.A.4840Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1228 | 20200120-6 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A085; Handfelling from A098-A096; |  |  | Windfarm | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122820200120-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting122820200120-6Operator - Principle - After Jan 1011825Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1229 | 20200120-7 | 53510111 | Access | 0 | Dozer - D5 or equal- After Jan 10 | 80.93 | 9 | Dynamic | 60.7 | 0 |  |  | 728.37 | 94.6881 | 823.0581 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road building and snow removal for access from A122-A124; |  |  | Wolf Lake | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122920200120-7Dozer - D5 or equal- After Jan 109728.37 | Corbiere and Sons Contracting122920200120-7Dozer - D5 or equal- After Jan 109728.37Inv#007-R01 | [5 empty] | 1 | 728.37 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1229 | 20200120-7 | 53510106 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road building and snow removal for access from A122-A124; |  |  | Wolf Lake | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122920200120-7Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting122920200120-7Excavator - 30 ton- After Jan 1091246.05Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1229 | 20200120-7 | 53510106 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 14 | Dynamic | 110.22 | 0 |  |  | 2057.44 | 267.4672 | 2324.9072 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road building and snow removal for access from A122-A124; |  |  | Wolf Lake | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122920200120-7Excavator - 36 ton- After Jan 10142057.44 | Corbiere and Sons Contracting122920200120-7Excavator - 36 ton- After Jan 10142057.44Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 2057.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1229 | 20200120-7 | 53510106 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road building and snow removal for access from A122-A124; |  |  | Wolf Lake | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122920200120-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting122920200120-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1229 | 20200120-7 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road building and snow removal for access from A122-A124; |  |  | Wolf Lake | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122920200120-7Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting122920200120-7Light Truck - Pick up- After Jan 103731.25Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1229 | 20200120-7 | 53510106 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road building and snow removal for access from A122-A124; |  |  | Wolf Lake | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122920200120-7Foreman121140 | Corbiere and Sons Contracting122920200120-7Foreman121140Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1229 | 20200120-7 | 53510106 | Access | 0 | Labourer - General | 60 | 11 | HR |  |  |  | 0 | 660 | 85.8 | 745.8 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road building and snow removal for access from A122-A124; |  |  | Wolf Lake | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122920200120-7Labourer - General11660 | Corbiere and Sons Contracting122920200120-7Labourer - General11660Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1229 | 20200120-7 | 53510106 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road building and snow removal for access from A122-A124; |  |  | Wolf Lake | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122920200120-7L.O.A.51050 | Corbiere and Sons Contracting122920200120-7L.O.A.51050Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1229 | 20200120-7 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road building and snow removal for access from A122-A124; |  |  | Wolf Lake | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122920200120-7L.O.A.1210 | Corbiere and Sons Contracting122920200120-7L.O.A.1210Inv#007-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1229 | 20200120-7 | 53510106 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 27 | HR |  |  | 75 | 0 | 2025 | 263.25 | 2288.25 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road building and snow removal for access from A122-A124; |  |  | Wolf Lake | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122920200120-7Operator - Principle - After Jan 10272025 | Corbiere and Sons Contracting122920200120-7Operator - Principle - After Jan 10272025Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 2025 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1229 | 20200120-7 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road building and snow removal for access from A122-A124; |  |  | Wolf Lake | 0 |  |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting122920200120-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting122920200120-7Operator - Principle - After Jan 1011825Inv#007-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1232 | 20200120-8 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A123; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43856 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting123220200120-8Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting123220200120-8Chainsaw and consumables- After Jan 103180Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1232 | 20200120-8 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A123; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43856 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting123220200120-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting123220200120-8Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1232 | 20200120-8 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A123; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43856 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting123220200120-8Foreman121140 | Corbiere and Sons Contracting123220200120-8Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1232 | 20200120-8 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A123; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43856 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting123220200120-8L.O.A.4840 | Corbiere and Sons Contracting123220200120-8L.O.A.4840Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1232 | 20200120-8 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-01-20 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A123; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43856 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting123220200120-8Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting123220200120-8Labourer - Specialized - After Jan 10332310Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1.2572 | DAY | 182.81 | 0 |  |  | 306.4307 | 39.836 | 346.2667 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Light Truck - Pick up- After Jan 101.2571516306.4307 | Corbiere and Sons Contracting123920200121-1Light Truck - Pick up- After Jan 101.2571516306.4307Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 306.4307 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.60096 | DAY | 182.81 | 0 |  |  | 146.4838 | 19.0429 | 165.5267 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Light Truck - Pick up- After Jan 100.6009593146.4838 | Corbiere and Sons Contracting123920200121-1Light Truck - Pick up- After Jan 100.6009593146.4838Inv#007-R01 | [5 empty] | 1 | 146.4838 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.34945 | DAY | 182.81 | 0 |  |  | 85.1796 | 11.0733 | 96.2529 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Light Truck - Pick up- After Jan 100.349454685.1796 | Corbiere and Sons Contracting123920200121-1Light Truck - Pick up- After Jan 100.349454685.1796Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 85.1796 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1.4453 | DAY | 182.81 | 0 |  |  | 352.2847 | 45.797 | 398.0817 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Light Truck - Pick up- After Jan 101.4452705352.2847 | Corbiere and Sons Contracting123920200121-1Light Truck - Pick up- After Jan 101.4452705352.2847Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 352.2847 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.54402 | DAY | 182.81 | 0 |  |  | 132.6041 | 17.2385 | 149.8426 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Light Truck - Pick up- After Jan 100.5440167132.6041 | Corbiere and Sons Contracting123920200121-1Light Truck - Pick up- After Jan 100.5440167132.6041Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 132.6041 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520107 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.37262 | DAY | 182.81 | 0 |  |  | 90.8266 | 11.8075 | 102.6341 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Light Truck - Pick up- After Jan 100.372621890.8266 | Corbiere and Sons Contracting123920200121-1Light Truck - Pick up- After Jan 100.372621890.8266Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 90.8266 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53510106 | Access | 0 | Project Manager | 110 | 3.0172 | HR |  |  | 110 | 0 | 331.888 | 43.1454 | 375.0334 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Project Manager3.0171638331.888 | Corbiere and Sons Contracting123920200121-1Project Manager3.0171638331.888Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 331.888 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53510111 | Access | 0 | Project Manager | 110 | 1.4423 | HR |  |  | 110 | 0 | 158.6533 | 20.6249 | 179.2782 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Project Manager1.4423024158.6533 | Corbiere and Sons Contracting123920200121-1Project Manager1.4423024158.6533Inv#007-R01 | [5 empty] | 1 | 158.6533 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 0.83869 | HR |  |  | 110 | 0 | 92.256 | 11.9933 | 104.2493 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Project Manager0.838691192.256 | Corbiere and Sons Contracting123920200121-1Project Manager0.838691192.256Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 92.256 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520102 | Clearing | 0 | Project Manager | 110 | 3.4686 | HR |  |  | 110 | 0 | 381.5514 | 49.6017 | 431.1531 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Project Manager3.4686492381.5514 | Corbiere and Sons Contracting123920200121-1Project Manager3.4686492381.5514Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 381.5514 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520104 | Clearing | 0 | Project Manager | 110 | 1.3056 | HR |  |  | 110 | 0 | 143.6204 | 18.6707 | 162.2911 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Project Manager1.3056401143.6204 | Corbiere and Sons Contracting123920200121-1Project Manager1.3056401143.6204Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 143.6204 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520107 | Clearing | 0 | Project Manager | 110 | 0.89429 | HR |  |  | 110 | 0 | 98.3722 | 12.7884 | 111.1606 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Project Manager0.894292498.3722 | Corbiere and Sons Contracting123920200121-1Project Manager0.894292498.3722Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 98.3722 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53510106 | Access | 0 | Superintendent | 105 | 3.0172 | HR |  |  | 105 | 0 | 316.8022 | 41.1843 | 357.9865 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Superintendent3.0171638316.8022 | Corbiere and Sons Contracting123920200121-1Superintendent3.0171638316.8022Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 316.8022 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53510111 | Access | 0 | Superintendent | 105 | 1.4423 | HR |  |  | 105 | 0 | 151.4418 | 19.6874 | 171.1292 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Superintendent1.4423024151.4418 | Corbiere and Sons Contracting123920200121-1Superintendent1.4423024151.4418Inv#007-R01 | [5 empty] | 1 | 151.4418 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 0.83869 | HR |  |  | 105 | 0 | 88.0626 | 11.4481 | 99.5107 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Superintendent0.838691188.0626 | Corbiere and Sons Contracting123920200121-1Superintendent0.838691188.0626Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 88.0626 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520102 | Clearing | 0 | Superintendent | 105 | 3.4686 | HR |  |  | 105 | 0 | 364.2082 | 47.3471 | 411.5553 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Superintendent3.4686492364.2082 | Corbiere and Sons Contracting123920200121-1Superintendent3.4686492364.2082Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 364.2082 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520104 | Clearing | 0 | Superintendent | 105 | 1.3056 | HR |  |  | 105 | 0 | 137.0922 | 17.822 | 154.9142 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Superintendent1.3056401137.0922 | Corbiere and Sons Contracting123920200121-1Superintendent1.3056401137.0922Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 137.0922 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520107 | Clearing | 0 | Superintendent | 105 | 0.89429 | HR |  |  | 105 | 0 | 93.9007 | 12.2071 | 106.1078 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Superintendent0.894292493.9007 | Corbiere and Sons Contracting123920200121-1Superintendent0.894292493.9007Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 93.9007 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53510106 | Access | 0 | Project Coordinator | 80 | 3.0172 | HR |  |  | 80 | 0 | 241.3731 | 31.3785 | 272.7516 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Project Coordinator3.0171638241.3731 | Corbiere and Sons Contracting123920200121-1Project Coordinator3.0171638241.3731Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 241.3731 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53510111 | Access | 0 | Project Coordinator | 80 | 1.4423 | HR |  |  | 80 | 0 | 115.3842 | 14.9999 | 130.3841 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Project Coordinator1.4423024115.3842 | Corbiere and Sons Contracting123920200121-1Project Coordinator1.4423024115.3842Inv#007-R01 | [5 empty] | 1 | 115.3842 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 0.83869 | HR |  |  | 80 | 0 | 67.0953 | 8.7224 | 75.8177 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Project Coordinator0.838691167.0953 | Corbiere and Sons Contracting123920200121-1Project Coordinator0.838691167.0953Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 67.0953 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520102 | Clearing | 0 | Project Coordinator | 80 | 3.4686 | HR |  |  | 80 | 0 | 277.4919 | 36.0739 | 313.5658 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Project Coordinator3.4686492277.4919 | Corbiere and Sons Contracting123920200121-1Project Coordinator3.4686492277.4919Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 277.4919 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520104 | Clearing | 0 | Project Coordinator | 80 | 1.3056 | HR |  |  | 80 | 0 | 104.4512 | 13.5787 | 118.0299 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Project Coordinator1.3056401104.4512 | Corbiere and Sons Contracting123920200121-1Project Coordinator1.3056401104.4512Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 104.4512 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520107 | Clearing | 0 | Project Coordinator | 80 | 0.89429 | HR |  |  | 80 | 0 | 71.5434 | 9.3006 | 80.844 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Project Coordinator0.894292471.5434 | Corbiere and Sons Contracting123920200121-1Project Coordinator0.894292471.5434Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 71.5434 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53510106 | Access | 0 | Safety Advisor | 85 | 3.0172 | HR |  |  | 85 | 0 | 256.4589 | 33.3397 | 289.7986 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Safety Advisor3.0171638256.4589 | Corbiere and Sons Contracting123920200121-1Safety Advisor3.0171638256.4589Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 256.4589 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53510111 | Access | 0 | Safety Advisor | 85 | 1.4423 | HR |  |  | 85 | 0 | 122.5957 | 15.9374 | 138.5331 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Safety Advisor1.4423024122.5957 | Corbiere and Sons Contracting123920200121-1Safety Advisor1.4423024122.5957Inv#007-R01 | [5 empty] | 1 | 122.5957 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 0.83869 | HR |  |  | 85 | 0 | 71.2887 | 9.2675 | 80.5562 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Safety Advisor0.838691171.2887 | Corbiere and Sons Contracting123920200121-1Safety Advisor0.838691171.2887Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 71.2887 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520102 | Clearing | 0 | Safety Advisor | 85 | 3.4686 | HR |  |  | 85 | 0 | 294.8352 | 38.3286 | 333.1638 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Safety Advisor3.4686492294.8352 | Corbiere and Sons Contracting123920200121-1Safety Advisor3.4686492294.8352Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 294.8352 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520104 | Clearing | 0 | Safety Advisor | 85 | 1.3056 | HR |  |  | 85 | 0 | 110.9794 | 14.4273 | 125.4067 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Safety Advisor1.3056401110.9794 | Corbiere and Sons Contracting123920200121-1Safety Advisor1.3056401110.9794Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 110.9794 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520107 | Clearing | 0 | Safety Advisor | 85 | 0.89429 | HR |  |  | 85 | 0 | 76.0149 | 9.8819 | 85.8968 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Safety Advisor0.894292476.0149 | Corbiere and Sons Contracting123920200121-1Safety Advisor0.894292476.0149Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 76.0149 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53510106 | Access | 0 | Site Administrator | 50 | 2.5143 | HR |  |  | 50 | 0 | 125.7152 | 16.343 | 142.0582 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Site Administrator2.5143031125.7152 | Corbiere and Sons Contracting123920200121-1Site Administrator2.5143031125.7152Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 125.7152 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53510111 | Access | 0 | Site Administrator | 50 | 1.2019 | HR |  |  | 50 | 0 | 60.0959 | 7.8125 | 67.9084 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Site Administrator1.201918660.0959 | Corbiere and Sons Contracting123920200121-1Site Administrator1.201918660.0959Inv#007-R01 | [5 empty] | 1 | 60.0959 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520101 | Clearing | 0 | Site Administrator | 50 | 0.69891 | HR |  |  | 50 | 0 | 34.9455 | 4.5429 | 39.4884 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Site Administrator0.698909234.9455 | Corbiere and Sons Contracting123920200121-1Site Administrator0.698909234.9455Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 34.9455 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520102 | Clearing | 0 | Site Administrator | 50 | 2.8905 | HR |  |  | 50 | 0 | 144.5271 | 18.7885 | 163.3156 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Site Administrator2.890541144.5271 | Corbiere and Sons Contracting123920200121-1Site Administrator2.890541144.5271Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 144.5271 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520104 | Clearing | 0 | Site Administrator | 50 | 1.088 | HR |  |  | 50 | 0 | 54.4017 | 7.0722 | 61.4739 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Site Administrator1.088033454.4017 | Corbiere and Sons Contracting123920200121-1Site Administrator1.088033454.4017Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 54.4017 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520107 | Clearing | 0 | Site Administrator | 50 | 0.74524 | HR |  |  | 50 | 0 | 37.2622 | 4.8441 | 42.1063 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Site Administrator0.745243637.2622 | Corbiere and Sons Contracting123920200121-1Site Administrator0.745243637.2622Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 37.2622 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53510106 | Access | 0 | Project Controls | 70 | 3.0172 | HR |  |  | 70 | 0 | 211.2015 | 27.4562 | 238.6577 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Project Controls3.0171638211.2015 | Corbiere and Sons Contracting123920200121-1Project Controls3.0171638211.2015Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 211.2015 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53510111 | Access | 0 | Project Controls | 70 | 1.4423 | HR |  |  | 70 | 0 | 100.9612 | 13.125 | 114.0862 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Project Controls1.4423024100.9612 | Corbiere and Sons Contracting123920200121-1Project Controls1.4423024100.9612Inv#007-R01 | [5 empty] | 1 | 100.9612 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 0.83869 | HR |  |  | 70 | 0 | 58.7084 | 7.6321 | 66.3405 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Project Controls0.838691158.7084 | Corbiere and Sons Contracting123920200121-1Project Controls0.838691158.7084Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 58.7084 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520102 | Clearing | 0 | Project Controls | 70 | 3.4686 | HR |  |  | 70 | 0 | 242.8054 | 31.5647 | 274.3701 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Project Controls3.4686492242.8054 | Corbiere and Sons Contracting123920200121-1Project Controls3.4686492242.8054Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 242.8054 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520104 | Clearing | 0 | Project Controls | 70 | 1.3056 | HR |  |  | 70 | 0 | 91.3948 | 11.8813 | 103.2761 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Project Controls1.305640191.3948 | Corbiere and Sons Contracting123920200121-1Project Controls1.305640191.3948Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 91.3948 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520107 | Clearing | 0 | Project Controls | 70 | 0.89429 | HR |  |  | 70 | 0 | 62.6005 | 8.1381 | 70.7386 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1Project Controls0.894292462.6005 | Corbiere and Sons Contracting123920200121-1Project Controls0.894292462.6005Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 62.6005 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53510106 | Access | 0 | L.O.A. | 210 | 1.5086 | DAY |  |  |  | 0 | 316.8022 | 41.1843 | 357.9865 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1L.O.A.1.5085819316.8022 | Corbiere and Sons Contracting123920200121-1L.O.A.1.5085819316.8022Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 316.8022 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53510111 | Access | 0 | L.O.A. | 210 | 0.72115 | DAY |  |  |  | 0 | 151.4418 | 19.6874 | 171.1292 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1L.O.A.0.7211512151.4418 | Corbiere and Sons Contracting123920200121-1L.O.A.0.7211512151.4418Inv#007-R01 | [5 empty] | 1 | 151.4418 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 0.41935 | DAY |  |  |  | 0 | 88.0626 | 11.4481 | 99.5107 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1L.O.A.0.419345588.0626 | Corbiere and Sons Contracting123920200121-1L.O.A.0.419345588.0626Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 88.0626 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1.7343 | DAY |  |  |  | 0 | 364.2082 | 47.3471 | 411.5553 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1L.O.A.1.7343246364.2082 | Corbiere and Sons Contracting123920200121-1L.O.A.1.7343246364.2082Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 364.2082 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 0.65282 | DAY |  |  |  | 0 | 137.0922 | 17.822 | 154.9142 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1L.O.A.0.6528201137.0922 | Corbiere and Sons Contracting123920200121-1L.O.A.0.6528201137.0922Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 137.0922 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1239 | 20200121-1 | 53520107 | Clearing | 0 | L.O.A. | 210 | 0.44715 | DAY |  |  |  | 0 | 93.9007 | 12.2071 | 106.1078 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting123920200121-1L.O.A.0.447146293.9007 | Corbiere and Sons Contracting123920200121-1L.O.A.0.447146293.9007Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 93.9007 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1248 | 20200121-10 | 53510211 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Access into Black Sturgeon | 2 |  |  | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting124820200121-10Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting124820200121-10Dozer D6 or equal- After Jan 1091183.32Inv#007-R01 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1248 | 20200121-10 | 53510211 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Access into Black Sturgeon | 2 |  |  | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting124820200121-10L.O.A.1210 | Corbiere and Sons Contracting124820200121-10L.O.A.1210Inv#007-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1248 | 20200121-10 | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Access into Black Sturgeon | 2 |  |  | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting124820200121-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting124820200121-10Operator - Principle - After Jan 1011825Inv#007-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.75429 | DAY | 182.81 | 0 |  |  | 183.8584 | 23.9016 | 207.76 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Light Truck - Pick up- After Jan 100.7542909183.8584 | Corbiere and Sons Contracting125120200121-13-R1Light Truck - Pick up- After Jan 100.7542909183.8584Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 183.8584 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.36058 | DAY | 182.81 | 0 |  |  | 87.8903 | 11.4257 | 99.316 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Light Truck - Pick up- After Jan 100.360575687.8903 | Corbiere and Sons Contracting125120200121-13-R1Light Truck - Pick up- After Jan 100.360575687.8903Inv#009 | [5 empty] | 1 | 87.8903 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.20967 | DAY | 182.81 | 0 |  |  | 51.1077 | 6.644 | 57.7517 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Light Truck - Pick up- After Jan 100.209672851.1077 | Corbiere and Sons Contracting125120200121-13-R1Light Truck - Pick up- After Jan 100.209672851.1077Inv#009 |  |  | WF1-Merchantable Clearing |  |  | 1 | 51.1077 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.86716 | DAY | 182.81 | 0 |  |  | 211.3708 | 27.4782 | 238.849 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Light Truck - Pick up- After Jan 100.8671623211.3708 | Corbiere and Sons Contracting125120200121-13-R1Light Truck - Pick up- After Jan 100.8671623211.3708Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 211.3708 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.32641 | DAY | 182.81 | 0 |  |  | 79.5624 | 10.3431 | 89.9055 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Hand Falling |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Light Truck - Pick up- After Jan 100.3264179.5624 | Corbiere and Sons Contracting125120200121-13-R1Light Truck - Pick up- After Jan 100.3264179.5624Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 79.5624 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53520107 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.22357 | DAY | 182.81 | 0 |  |  | 54.4959 | 7.0845 | 61.5804 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Light Truck - Pick up- After Jan 100.223573154.4959 | Corbiere and Sons Contracting125120200121-13-R1Light Truck - Pick up- After Jan 100.223573154.4959Inv#009 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 54.4959 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53510106 | Access | 0 | Project Coordinator | 80 | 3.0172 | HR |  |  | 80 | 0 | 241.3731 | 31.3785 | 272.7516 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator3.0171638241.3731 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator3.0171638241.3731Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 241.3731 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53510106 | Access | 0 | Project Coordinator | 80 | 3.0172 | HR |  |  | 80 | 0 | 241.3731 | 31.3785 | 272.7516 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator3.0171638241.3731 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator3.0171638241.3731Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 241.3731 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53510111 | Access | 0 | Project Coordinator | 80 | 1.4423 | HR |  |  | 80 | 0 | 115.3842 | 14.9999 | 130.3841 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator1.4423024115.3842 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator1.4423024115.3842Inv#009 | [5 empty] | 1 | 115.3842 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53510111 | Access | 0 | Project Coordinator | 80 | 1.4423 | HR |  |  | 80 | 0 | 115.3842 | 14.9999 | 130.3841 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator1.4423024115.3842 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator1.4423024115.3842Inv#009 | [5 empty] | 1 | 115.3842 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 0.83869 | HR |  |  | 80 | 0 | 67.0953 | 8.7224 | 75.8177 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator0.838691167.0953 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator0.838691167.0953Inv#009 |  |  | WF1-Merchantable Clearing |  |  | 1 | 67.0953 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 0.83869 | HR |  |  | 80 | 0 | 67.0953 | 8.7224 | 75.8177 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator0.838691167.0953 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator0.838691167.0953Inv#009 |  |  | WF1-Merchantable Clearing |  |  | 1 | 67.0953 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53520102 | Clearing | 0 | Project Coordinator | 80 | 3.4686 | HR |  |  | 80 | 0 | 277.4919 | 36.0739 | 313.5658 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator3.4686492277.4919 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator3.4686492277.4919Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 277.4919 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53520102 | Clearing | 0 | Project Coordinator | 80 | 3.4686 | HR |  |  | 80 | 0 | 277.4919 | 36.0739 | 313.5658 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator3.4686492277.4919 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator3.4686492277.4919Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 277.4919 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53520104 | Clearing | 0 | Project Coordinator | 80 | 1.3056 | HR |  |  | 80 | 0 | 104.4512 | 13.5787 | 118.0299 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Hand Falling |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator1.3056401104.4512 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator1.3056401104.4512Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 104.4512 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53520104 | Clearing | 0 | Project Coordinator | 80 | 1.3056 | HR |  |  | 80 | 0 | 104.4512 | 13.5787 | 118.0299 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Hand Falling |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator1.3056401104.4512 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator1.3056401104.4512Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 104.4512 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53520107 | Clearing | 0 | Project Coordinator | 80 | 0.89429 | HR |  |  | 80 | 0 | 71.5434 | 9.3006 | 80.844 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator0.894292471.5434 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator0.894292471.5434Inv#009 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 71.5434 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53520107 | Clearing | 0 | Project Coordinator | 80 | 0.89429 | HR |  |  | 80 | 0 | 71.5434 | 9.3006 | 80.844 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator0.894292471.5434 | Corbiere and Sons Contracting125120200121-13-R1Project Coordinator0.894292471.5434Inv#009 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 71.5434 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53510106 | Access | 0 | Foreman | 95 | 3.0172 | HR |  |  | 95 | 0 | 286.6306 | 37.262 | 323.8926 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Foreman3.0171638286.6306 | Corbiere and Sons Contracting125120200121-13-R1Foreman3.0171638286.6306Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 286.6306 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53510111 | Access | 0 | Foreman | 95 | 1.4423 | HR |  |  | 95 | 0 | 137.0187 | 17.8124 | 154.8311 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Foreman1.4423024137.0187 | Corbiere and Sons Contracting125120200121-13-R1Foreman1.4423024137.0187Inv#009 | [5 empty] | 1 | 137.0187 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53520101 | Clearing | 0 | Foreman | 95 | 0.83869 | HR |  |  | 95 | 0 | 79.6757 | 10.3578 | 90.0335 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Foreman0.838691179.6757 | Corbiere and Sons Contracting125120200121-13-R1Foreman0.838691179.6757Inv#009 |  |  | WF1-Merchantable Clearing |  |  | 1 | 79.6757 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53520102 | Clearing | 0 | Foreman | 95 | 3.4686 | HR |  |  | 95 | 0 | 329.5217 | 42.8378 | 372.3595 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Foreman3.4686492329.5217 | Corbiere and Sons Contracting125120200121-13-R1Foreman3.4686492329.5217Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 329.5217 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53520104 | Clearing | 0 | Foreman | 95 | 1.3056 | HR |  |  | 95 | 0 | 124.0358 | 16.1247 | 140.1605 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Hand Falling |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Foreman1.3056401124.0358 | Corbiere and Sons Contracting125120200121-13-R1Foreman1.3056401124.0358Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 124.0358 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53520107 | Clearing | 0 | Foreman | 95 | 0.89429 | HR |  |  | 95 | 0 | 84.9578 | 11.0445 | 96.0023 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1Foreman0.894292484.9578 | Corbiere and Sons Contracting125120200121-13-R1Foreman0.894292484.9578Inv#009 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 84.9578 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53510106 | Access | 0 | L.O.A. | 210 | 0.75429 | DAY |  |  |  | 0 | 158.4011 | 20.5921 | 178.9932 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1L.O.A.0.7542909158.4011 | Corbiere and Sons Contracting125120200121-13-R1L.O.A.0.7542909158.4011Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 158.4011 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53510111 | Access | 0 | L.O.A. | 210 | 0.36058 | DAY |  |  |  | 0 | 75.7209 | 9.8437 | 85.5646 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1L.O.A.0.360575675.7209 | Corbiere and Sons Contracting125120200121-13-R1L.O.A.0.360575675.7209Inv#009 | [5 empty] | 1 | 75.7209 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 0.20967 | DAY |  |  |  | 0 | 44.0313 | 5.7241 | 49.7554 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1L.O.A.0.209672844.0313 | Corbiere and Sons Contracting125120200121-13-R1L.O.A.0.209672844.0313Inv#009 |  |  | WF1-Merchantable Clearing |  |  | 1 | 44.0313 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 0.86716 | DAY |  |  |  | 0 | 182.1041 | 23.6735 | 205.7776 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1L.O.A.0.8671623182.1041 | Corbiere and Sons Contracting125120200121-13-R1L.O.A.0.8671623182.1041Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 182.1041 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 0.32641 | DAY |  |  |  | 0 | 68.5461 | 8.911 | 77.4571 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Hand Falling |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1L.O.A.0.3264168.5461 | Corbiere and Sons Contracting125120200121-13-R1L.O.A.0.3264168.5461Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 68.5461 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1251 | 20200121-13-R1 | 53520107 | Clearing | 0 | L.O.A. | 210 | 0.22357 | DAY |  |  |  | 0 | 46.9504 | 6.1036 | 53.054 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nabeel Malik | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  | had wrong PO number fixed - 3/11/2020 during cost splitting | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Float moves and project supervision | 6 |  | Terrace Yard | 1 | 43854 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting125120200121-13-R1L.O.A.0.223573146.9504 | Corbiere and Sons Contracting125120200121-13-R1L.O.A.0.223573146.9504Inv#009 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 46.9504 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1254 | 20200121-15 | 53510611 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 74.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access into Santoy Mountain; | 6 |  |  | 0 | 43854 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting125420200121-15Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting125420200121-15Loader JD 524 to 624 or equal5495Inv#009 | [5 empty] | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1254 | 20200121-15 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access into Santoy Mountain; | 6 |  |  | 0 | 43854 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting125420200121-15Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting125420200121-15Dozer D6 or equal- After Jan 103394.44Inv#009 | [5 empty] | 1 | 394.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1254 | 20200121-15 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access into Santoy Mountain; | 6 |  |  | 0 | 43854 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting125420200121-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting125420200121-15Light Truck - Pick up- After Jan 101243.75Inv#009 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1254 | 20200121-15 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access into Santoy Mountain; | 6 |  |  | 0 | 43854 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting125420200121-15L.O.A.1210 | Corbiere and Sons Contracting125420200121-15L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1254 | 20200121-15 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access into Santoy Mountain; | 6 |  |  | 0 | 43854 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting125420200121-15Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting125420200121-15Operator - Principle - After Jan 1011825Inv#009 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1259 | 20200121-18 | 53510611 | Access | 0 | Loader JD 644 to 724 or equal | 126 | 7.5 | HR | 94.5 | 0 |  |  | 945 | 122.85 | 1067.85 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization of a Loader and snow removal for access | 6 |  |  | 0 | 43854 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting125920200121-18Loader JD 644 to 724 or equal7.5945 | Corbiere and Sons Contracting125920200121-18Loader JD 644 to 724 or equal7.5945Inv#009 | [5 empty] | 1 | 945 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1259 | 20200121-18 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization of a Loader and snow removal for access | 6 |  |  | 0 | 43854 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting125920200121-18L.O.A.1210 | Corbiere and Sons Contracting125920200121-18L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1259 | 20200121-18 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7.5 | HR |  |  | 75 | 0 | 562.5 | 73.125 | 635.625 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization of a Loader and snow removal for access | 6 |  |  | 0 | 43854 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting125920200121-18Operator - Principle - After Jan 107.5562.5 | Corbiere and Sons Contracting125920200121-18Operator - Principle - After Jan 107.5562.5Inv#009 | [5 empty] | 1 | 562.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1240 | 20200121-2 | 53510106 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 1.2572 | HR | 74.25 | 0 |  |  | 124.458 | 16.1795 | 140.6375 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting124020200121-2Loader JD 524 to 624 or equal1.2571516124.458 | Corbiere and Sons Contracting124020200121-2Loader JD 524 to 624 or equal1.2571516124.458Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 124.458 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1240 | 20200121-2 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 0.60096 | HR | 74.25 | 0 |  |  | 59.495 | 7.7344 | 67.2293 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting124020200121-2Loader JD 524 to 624 or equal0.600959359.495 | Corbiere and Sons Contracting124020200121-2Loader JD 524 to 624 or equal0.600959359.495Inv#007-R01 | [5 empty] | 1 | 59.495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1240 | 20200121-2 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.34945 | HR | 74.25 | 0 |  |  | 34.596 | 4.4975 | 39.0935 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting124020200121-2Loader JD 524 to 624 or equal0.349454634.596 | Corbiere and Sons Contracting124020200121-2Loader JD 524 to 624 or equal0.349454634.596Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 34.596 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1240 | 20200121-2 | 53520102 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 1.4453 | HR | 74.25 | 0 |  |  | 143.0818 | 18.6006 | 161.6824 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting124020200121-2Loader JD 524 to 624 or equal1.4452705143.0818 | Corbiere and Sons Contracting124020200121-2Loader JD 524 to 624 or equal1.4452705143.0818Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 143.0818 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1240 | 20200121-2 | 53520104 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.54402 | HR | 74.25 | 0 |  |  | 53.8577 | 7.0015 | 60.8592 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting124020200121-2Loader JD 524 to 624 or equal0.544016753.8577 | Corbiere and Sons Contracting124020200121-2Loader JD 524 to 624 or equal0.544016753.8577Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 53.8577 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1240 | 20200121-2 | 53520107 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.37262 | HR | 74.25 | 0 |  |  | 36.8896 | 4.7956 | 41.6852 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting124020200121-2Loader JD 524 to 624 or equal0.372621836.8896 | Corbiere and Sons Contracting124020200121-2Loader JD 524 to 624 or equal0.372621836.8896Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 36.8896 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1240 | 20200121-2 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.25143 | DAY | 182.81 | 0 |  |  | 61.2861 | 7.9672 | 69.2533 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting124020200121-2Light Truck - Pick up- After Jan 100.251430361.2861 | Corbiere and Sons Contracting124020200121-2Light Truck - Pick up- After Jan 100.251430361.2861Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 61.2861 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1240 | 20200121-2 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.12019 | DAY | 182.81 | 0 |  |  | 29.2968 | 3.8086 | 33.1054 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting124020200121-2Light Truck - Pick up- After Jan 100.120191929.2968 | Corbiere and Sons Contracting124020200121-2Light Truck - Pick up- After Jan 100.120191929.2968Inv#007-R01 | [5 empty] | 1 | 29.2968 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1240 | 20200121-2 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.069891 | DAY | 182.81 | 0 |  |  | 17.0359 | 2.2147 | 19.2506 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting124020200121-2Light Truck - Pick up- After Jan 100.069890917.0359 | Corbiere and Sons Contracting124020200121-2Light Truck - Pick up- After Jan 100.069890917.0359Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 17.0359 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1240 | 20200121-2 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.28905 | DAY | 182.81 | 0 |  |  | 70.4569 | 9.1594 | 79.6163 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting124020200121-2Light Truck - Pick up- After Jan 100.289054170.4569 | Corbiere and Sons Contracting124020200121-2Light Truck - Pick up- After Jan 100.289054170.4569Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 70.4569 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1240 | 20200121-2 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.1088 | DAY | 182.81 | 0 |  |  | 26.5208 | 3.4477 | 29.9685 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting124020200121-2Light Truck - Pick up- After Jan 100.108803326.5208 | Corbiere and Sons Contracting124020200121-2Light Truck - Pick up- After Jan 100.108803326.5208Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 26.5208 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1240 | 20200121-2 | 53520107 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.074524 | DAY | 182.81 | 0 |  |  | 18.1653 | 2.3615 | 20.5268 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting124020200121-2Light Truck - Pick up- After Jan 100.074524418.1653 | Corbiere and Sons Contracting124020200121-2Light Truck - Pick up- After Jan 100.074524418.1653Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 18.1653 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1240 | 20200121-2 | 53510106 | Access | 0 | Operator - Apprentice | 60 | 2.5143 | HR |  |  | 60 | 0 | 150.8582 | 19.6116 | 170.4698 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting124020200121-2Operator - Apprentice2.5143031150.8582 | Corbiere and Sons Contracting124020200121-2Operator - Apprentice2.5143031150.8582Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 150.8582 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1240 | 20200121-2 | 53510111 | Access | 0 | Operator - Apprentice | 60 | 1.2019 | HR |  |  | 60 | 0 | 72.1151 | 9.375 | 81.4901 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting124020200121-2Operator - Apprentice1.201918672.1151 | Corbiere and Sons Contracting124020200121-2Operator - Apprentice1.201918672.1151Inv#007-R01 | [5 empty] | 1 | 72.1151 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1240 | 20200121-2 | 53520101 | Clearing | 0 | Operator - Apprentice | 60 | 0.69891 | HR |  |  | 60 | 0 | 41.9346 | 5.4515 | 47.3861 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting124020200121-2Operator - Apprentice0.698909241.9346 | Corbiere and Sons Contracting124020200121-2Operator - Apprentice0.698909241.9346Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 41.9346 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1240 | 20200121-2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 2.8905 | HR |  |  | 60 | 0 | 173.4325 | 22.5462 | 195.9787 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting124020200121-2Operator - Apprentice2.890541173.4325 | Corbiere and Sons Contracting124020200121-2Operator - Apprentice2.890541173.4325Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 173.4325 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1240 | 20200121-2 | 53520104 | Clearing | 0 | Operator - Apprentice | 60 | 1.088 | HR |  |  | 60 | 0 | 65.282 | 8.4867 | 73.7687 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting124020200121-2Operator - Apprentice1.088033465.282 | Corbiere and Sons Contracting124020200121-2Operator - Apprentice1.088033465.282Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 65.282 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1240 | 20200121-2 | 53520107 | Clearing | 0 | Operator - Apprentice | 60 | 0.74524 | HR |  |  | 60 | 0 | 44.7146 | 5.8129 | 50.5275 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  |  | 1 | 43854 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting124020200121-2Operator - Apprentice0.745243644.7146 | Corbiere and Sons Contracting124020200121-2Operator - Apprentice0.745243644.7146Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 44.7146 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1384 | 20200121-21 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.37419 | DAY | 182.81 | 0 |  |  | 91.2093 | 11.8572 | 103.0665 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Schrebier Yard Maintenance and Float Moves | 6 |  | Schrebier Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138420200121-21Light Truck - Pick up- After Jan 100.374192291.2093 | Corbiere and Sons Contracting138420200121-21Light Truck - Pick up- After Jan 100.374192291.2093Inv#009 | [5 empty] | 1 | 91.2093 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1384 | 20200121-21 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3.7419 | Dynamic | 91.79 | 0 |  |  | 457.9738 | 59.5366 | 517.5104 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Schrebier Yard Maintenance and Float Moves | 6 |  | Schrebier Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138420200121-21Tractor Trailer - 60 Ton- After Jan 103.7419216457.9738 | Corbiere and Sons Contracting138420200121-21Tractor Trailer - 60 Ton- After Jan 103.7419216457.9738Inv#009 | [5 empty] | 1 | 457.9738 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1384 | 20200121-21 | 53510611 | Access | 0 | L.O.A. | 210 | 0.74838 | DAY |  |  |  | 0 | 157.1607 | 20.4309 | 177.5916 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Schrebier Yard Maintenance and Float Moves | 6 |  | Schrebier Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138420200121-21L.O.A.0.7483843157.1607 | Corbiere and Sons Contracting138420200121-21L.O.A.0.7483843157.1607Inv#009 | [5 empty] | 1 | 157.1607 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1384 | 20200121-21 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4.1161 | HR |  |  | 70 | 0 | 288.128 | 37.4566 | 325.5846 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Schrebier Yard Maintenance and Float Moves | 6 |  | Schrebier Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138420200121-21Operator - Intermdiate - After Jan 104.1161138288.128 | Corbiere and Sons Contracting138420200121-21Operator - Intermdiate - After Jan 104.1161138288.128Inv#009 | [5 empty] | 1 | 288.128 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1384 | 20200121-21 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 4.1161 | HR |  |  | 60 | 0 | 246.9668 | 32.1057 | 279.0725 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Schrebier Yard Maintenance and Float Moves | 6 |  | Schrebier Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138420200121-21Labourer - General - After Jan 104.1161138246.9668 | Corbiere and Sons Contracting138420200121-21Labourer - General - After Jan 104.1161138246.9668Inv#009 | [5 empty] | 1 | 246.9668 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1241 | 20200121-3 | 53520101 | Clearing | 0 | Brusher | 202.5 | 4 | HR | 151.88 | 0 |  |  | 810 | 105.3 | 915.3 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Clearing and Brushing finishing up on Eldorado and then float moves out; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124120200121-3Brusher4810 | Corbiere and Sons Contracting124120200121-3Brusher4810Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 810 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1241 | 20200121-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 5 | HR | 151.88 | 0 |  |  | 1012.5 | 131.625 | 1144.125 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Clearing and Brushing finishing up on Eldorado and then float moves out; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124120200121-3Brusher51012.5 | Corbiere and Sons Contracting124120200121-3Brusher51012.5Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1012.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1241 | 20200121-3 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 13 | HR | 180 | 0 |  |  | 3120 | 405.6 | 3525.6 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Clearing and Brushing finishing up on Eldorado and then float moves out; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124120200121-3Feller Buncher133120 | Corbiere and Sons Contracting124120200121-3Feller Buncher133120Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1241 | 20200121-3 | 53520107 | Clearing | 0 | Feller Buncher | 240 | 5 | HR | 180 | 0 |  |  | 1200 | 156 | 1356 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Clearing and Brushing finishing up on Eldorado and then float moves out; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124120200121-3Feller Buncher51200 | Corbiere and Sons Contracting124120200121-3Feller Buncher51200Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1241 | 20200121-3 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Clearing and Brushing finishing up on Eldorado and then float moves out; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124120200121-3Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting124120200121-3Grinder - 4710 Peterson or equal95011.2Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1241 | 20200121-3 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Clearing and Brushing finishing up on Eldorado and then float moves out; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124120200121-3Log Loader91377 | Corbiere and Sons Contracting124120200121-3Log Loader91377Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1241 | 20200121-3 | 53520101 | Clearing | 0 | Skidder | 171 | 4 | HR | 128.25 | 0 |  |  | 684 | 88.92 | 772.92 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Clearing and Brushing finishing up on Eldorado and then float moves out; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124120200121-3Skidder 4684 | Corbiere and Sons Contracting124120200121-3Skidder 4684Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 684 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1241 | 20200121-3 | 53520107 | Clearing | 0 | Skidder | 171 | 5 | HR | 128.25 | 0 |  |  | 855 | 111.15 | 966.15 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Clearing and Brushing finishing up on Eldorado and then float moves out; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124120200121-3Skidder 5855 | Corbiere and Sons Contracting124120200121-3Skidder 5855Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 855 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1241 | 20200121-3 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Clearing and Brushing finishing up on Eldorado and then float moves out; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124120200121-3Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting124120200121-3Light Truck - Pick up- After Jan 104975Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1241 | 20200121-3 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Clearing and Brushing finishing up on Eldorado and then float moves out; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124120200121-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting124120200121-3Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1241 | 20200121-3 | 53520107 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Clearing and Brushing finishing up on Eldorado and then float moves out; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124120200121-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting124120200121-3Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1241 | 20200121-3 | 53520107 | Clearing | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11.5 | Dynamic | 91.79 | 0 |  |  | 1407.485 | 182.9731 | 1590.458 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Clearing and Brushing finishing up on Eldorado and then float moves out; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124120200121-3Tractor Trailer - 60 Ton- After Jan 1011.51407.485 | Corbiere and Sons Contracting124120200121-3Tractor Trailer - 60 Ton- After Jan 1011.51407.485Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 1407.485 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1241 | 20200121-3 | 53520101 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Clearing and Brushing finishing up on Eldorado and then float moves out; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124120200121-3Foreman6570 | Corbiere and Sons Contracting124120200121-3Foreman6570Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1241 | 20200121-3 | 53520101 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Clearing and Brushing finishing up on Eldorado and then float moves out; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124120200121-3L.O.A.1210 | Corbiere and Sons Contracting124120200121-3L.O.A.1210Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1241 | 20200121-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Clearing and Brushing finishing up on Eldorado and then float moves out; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124120200121-3L.O.A.4840 | Corbiere and Sons Contracting124120200121-3L.O.A.4840Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1241 | 20200121-3 | 53520107 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Clearing and Brushing finishing up on Eldorado and then float moves out; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124120200121-3L.O.A.2420 | Corbiere and Sons Contracting124120200121-3L.O.A.2420Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1241 | 20200121-3 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 28 | HR |  |  | 75 | 0 | 2100 | 273 | 2373 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Clearing and Brushing finishing up on Eldorado and then float moves out; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124120200121-3Operator - Principle - After Jan 10282100 | Corbiere and Sons Contracting124120200121-3Operator - Principle - After Jan 10282100Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1241 | 20200121-3 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Clearing and Brushing finishing up on Eldorado and then float moves out; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124120200121-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting124120200121-3Operator - Principle - After Jan 1011825Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1241 | 20200121-3 | 53520107 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 16 | HR |  |  | 75 | 0 | 1200 | 156 | 1356 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Clearing and Brushing finishing up on Eldorado and then float moves out; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124120200121-3Operator - Principle - After Jan 10161200 | Corbiere and Sons Contracting124120200121-3Operator - Principle - After Jan 10161200Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1241 | 20200121-3 | 53520107 | Clearing | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Clearing and Brushing finishing up on Eldorado and then float moves out; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124120200121-3Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting124120200121-3Driver - AZ - After Jan 1011.5805Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1241 | 20200121-3 | 53520107 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Clearing and Brushing finishing up on Eldorado and then float moves out; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124120200121-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting124120200121-3Labourer - General - After Jan 1011660Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1242 | 20200121-4 | 53520102 | Clearing | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Rd. From A067-A069; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124220200121-4Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting124220200121-4Dozer D6 or equal- After Jan 1091183.32Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1242 | 20200121-4 | 53520102 | Clearing | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Rd. From A067-A069; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124220200121-4Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting124220200121-4Excavator - 30 ton- After Jan 1091246.05Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1242 | 20200121-4 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 27 | HR | 9.16 | 0 |  |  | 329.67 | 42.8571 | 372.5271 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Rd. From A067-A069; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124220200121-4Excavator Thumb - 30 - 50 ton- After Jan 1027329.67 | Corbiere and Sons Contracting124220200121-4Excavator Thumb - 30 - 50 ton- After Jan 1027329.67Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 329.67 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1242 | 20200121-4 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 11 | Dynamic | 64.79 | 0 |  |  | 950.18 | 123.5234 | 1073.7034 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Rd. From A067-A069; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124220200121-4Sander Truck - Forestry- After Jan 1011950.18 | Corbiere and Sons Contracting124220200121-4Sander Truck - Forestry- After Jan 1011950.18Inv#007-R01 | [5 empty] | 1 | 950.18 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1242 | 20200121-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Rd. From A067-A069; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124220200121-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting124220200121-4Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1242 | 20200121-4 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Rd. From A067-A069; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124220200121-4L.O.A.1210 | Corbiere and Sons Contracting124220200121-4L.O.A.1210Inv#007-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1242 | 20200121-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 44 | HR |  |  | 75 | 0 | 3300 | 429 | 3729 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Rd. From A067-A069; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124220200121-4Operator - Principle - After Jan 10443300 | Corbiere and Sons Contracting124220200121-4Operator - Principle - After Jan 10443300Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1242 | 20200121-4 | 53510111 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Rd. From A067-A069; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124220200121-4Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting124220200121-4Driver - AZ - After Jan 1011770Inv#007-R01 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1243 | 20200121-5 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders doing winter access maintenance across access roads; Labourer Fuelling, hauling tires, moving signage; | 1 | A-085 to A-117 | Windfarm | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124320200121-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting124320200121-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#007-R01 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1243 | 20200121-5 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 5 | Dynamic | 64.79 | 0 |  |  | 431.9 | 56.147 | 488.047 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders doing winter access maintenance across access roads; Labourer Fuelling, hauling tires, moving signage; | 1 | A-085 to A-117 | Windfarm | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124320200121-5Sander Truck - Forestry- After Jan 105431.9 | Corbiere and Sons Contracting124320200121-5Sander Truck - Forestry- After Jan 105431.9Inv#007-R01 | [5 empty] | 1 | 431.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1243 | 20200121-5 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders doing winter access maintenance across access roads; Labourer Fuelling, hauling tires, moving signage; | 1 | A-085 to A-117 | Windfarm | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124320200121-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting124320200121-5Light Truck - Pick up- After Jan 102487.5Inv#007-R01 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1243 | 20200121-5 | 53510111 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 10 | Dynamic | 91.79 | 0 |  |  | 1223.9 | 159.107 | 1383.007 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders doing winter access maintenance across access roads; Labourer Fuelling, hauling tires, moving signage; | 1 | A-085 to A-117 | Windfarm | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124320200121-5Tractor Trailer - 60 Ton- After Jan 10101223.9 | Corbiere and Sons Contracting124320200121-5Tractor Trailer - 60 Ton- After Jan 10101223.9Inv#007-R01 | [5 empty] | 1 | 1223.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1243 | 20200121-5 | 53510111 | Access | 0 | Foreman | 95 | 7 | HR |  |  | 95 | 0 | 665 | 86.45 | 751.45 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders doing winter access maintenance across access roads; Labourer Fuelling, hauling tires, moving signage; | 1 | A-085 to A-117 | Windfarm | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124320200121-5Foreman7665 | Corbiere and Sons Contracting124320200121-5Foreman7665Inv#007-R01 | [5 empty] | 1 | 665 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1243 | 20200121-5 | 53510111 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders doing winter access maintenance across access roads; Labourer Fuelling, hauling tires, moving signage; | 1 | A-085 to A-117 | Windfarm | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124320200121-5L.O.A.51050 | Corbiere and Sons Contracting124320200121-5L.O.A.51050Inv#007-R01 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1243 | 20200121-5 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 17 | HR |  |  | 75 | 0 | 1275 | 165.75 | 1440.75 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders doing winter access maintenance across access roads; Labourer Fuelling, hauling tires, moving signage; | 1 | A-085 to A-117 | Windfarm | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124320200121-5Operator - Principle - After Jan 10171275 | Corbiere and Sons Contracting124320200121-5Operator - Principle - After Jan 10171275Inv#007-R01 | [5 empty] | 1 | 1275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1243 | 20200121-5 | 53510111 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders doing winter access maintenance across access roads; Labourer Fuelling, hauling tires, moving signage; | 1 | A-085 to A-117 | Windfarm | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124320200121-5Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting124320200121-5Operator - Intermdiate - After Jan 1011770Inv#007-R01 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1243 | 20200121-5 | 53510111 | Access | 0 | Labourer - General - After Jan 10 | 60 | 10 | HR |  |  | 60 | 0 | 600 | 78 | 678 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders doing winter access maintenance across access roads; Labourer Fuelling, hauling tires, moving signage; | 1 | A-085 to A-117 | Windfarm | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124320200121-5Labourer - General - After Jan 1010600 | Corbiere and Sons Contracting124320200121-5Labourer - General - After Jan 1010600Inv#007-R01 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1244 | 20200121-6 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 7 | HR | 417.6 | 0 |  |  | 3897.6 | 506.688 | 4404.288 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; Grinding of Material from A085-A089; | 1 | A-085 to A-117 | Windfarm | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124420200121-6Grinder - 4710 Peterson or equal73897.6 | Corbiere and Sons Contracting124420200121-6Grinder - 4710 Peterson or equal73897.6Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3897.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1244 | 20200121-6 | 53520102 | Clearing | 0 | Log Loader | 153 | 7 | HR | 114.75 | 0 |  |  | 1071 | 139.23 | 1210.23 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; Grinding of Material from A085-A089; | 1 | A-085 to A-117 | Windfarm | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124420200121-6Log Loader71071 | Corbiere and Sons Contracting124420200121-6Log Loader71071Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1071 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1244 | 20200121-6 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; Grinding of Material from A085-A089; | 1 | A-085 to A-117 | Windfarm | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124420200121-6Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting124420200121-6Chainsaw and consumables- After Jan 103180Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1244 | 20200121-6 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; Grinding of Material from A085-A089; | 1 | A-085 to A-117 | Windfarm | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124420200121-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting124420200121-6Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1244 | 20200121-6 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; Grinding of Material from A085-A089; | 1 | A-085 to A-117 | Windfarm | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124420200121-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting124420200121-6Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1244 | 20200121-6 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; Grinding of Material from A085-A089; | 1 | A-085 to A-117 | Windfarm | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124420200121-6Foreman121140 | Corbiere and Sons Contracting124420200121-6Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1244 | 20200121-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; Grinding of Material from A085-A089; | 1 | A-085 to A-117 | Windfarm | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124420200121-6L.O.A.1210 | Corbiere and Sons Contracting124420200121-6L.O.A.1210Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1244 | 20200121-6 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; Grinding of Material from A085-A089; | 1 | A-085 to A-117 | Windfarm | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124420200121-6L.O.A.4840 | Corbiere and Sons Contracting124420200121-6L.O.A.4840Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1244 | 20200121-6 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; Grinding of Material from A085-A089; | 1 | A-085 to A-117 | Windfarm | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124420200121-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting124420200121-6Operator - Principle - After Jan 1011825Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1244 | 20200121-6 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; Grinding of Material from A085-A089; | 1 | A-085 to A-117 | Windfarm | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124420200121-6Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting124420200121-6Labourer - Specialized - After Jan 10332310Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1245 | 20200121-7 | 53510111 | Access | 0 | Dozer - D5 or equal- After Jan 10 | 80.93 | 7 | Dynamic | 60.7 | 0 |  |  | 566.51 | 73.6463 | 640.1563 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building and Winter Rd. Access Maintenance from A118-A122, and from A124-A126; Labourers Fuelling equipment and cleaning tracks; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124520200121-7Dozer - D5 or equal- After Jan 107566.51 | Corbiere and Sons Contracting124520200121-7Dozer - D5 or equal- After Jan 107566.51Inv#007-R01 | [5 empty] | 1 | 566.51 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1245 | 20200121-7 | 53510106 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 18 | Dynamic | 103.84 | 0 |  |  | 2492.1 | 323.973 | 2816.073 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building and Winter Rd. Access Maintenance from A118-A122, and from A124-A126; Labourers Fuelling equipment and cleaning tracks; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124520200121-7Excavator - 30 ton- After Jan 10182492.1 | Corbiere and Sons Contracting124520200121-7Excavator - 30 ton- After Jan 10182492.1Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 2492.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1245 | 20200121-7 | 53510106 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 110.22 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building and Winter Rd. Access Maintenance from A118-A122, and from A124-A126; Labourers Fuelling equipment and cleaning tracks; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124520200121-7Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting124520200121-7Excavator - 36 ton- After Jan 10182645.28Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 2645.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1245 | 20200121-7 | 53510106 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building and Winter Rd. Access Maintenance from A118-A122, and from A124-A126; Labourers Fuelling equipment and cleaning tracks; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124520200121-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting124520200121-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1245 | 20200121-7 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building and Winter Rd. Access Maintenance from A118-A122, and from A124-A126; Labourers Fuelling equipment and cleaning tracks; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124520200121-7Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting124520200121-7Light Truck - Pick up- After Jan 104975Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1245 | 20200121-7 | 53510106 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building and Winter Rd. Access Maintenance from A118-A122, and from A124-A126; Labourers Fuelling equipment and cleaning tracks; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124520200121-7Foreman121140 | Corbiere and Sons Contracting124520200121-7Foreman121140Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1245 | 20200121-7 | 53510106 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building and Winter Rd. Access Maintenance from A118-A122, and from A124-A126; Labourers Fuelling equipment and cleaning tracks; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124520200121-7L.O.A.51050 | Corbiere and Sons Contracting124520200121-7L.O.A.51050Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1245 | 20200121-7 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building and Winter Rd. Access Maintenance from A118-A122, and from A124-A126; Labourers Fuelling equipment and cleaning tracks; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124520200121-7L.O.A.1210 | Corbiere and Sons Contracting124520200121-7L.O.A.1210Inv#007-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1245 | 20200121-7 | 53510106 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 44 | HR |  |  | 75 | 0 | 3300 | 429 | 3729 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building and Winter Rd. Access Maintenance from A118-A122, and from A124-A126; Labourers Fuelling equipment and cleaning tracks; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124520200121-7Operator - Principle - After Jan 10443300 | Corbiere and Sons Contracting124520200121-7Operator - Principle - After Jan 10443300Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 3300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1245 | 20200121-7 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building and Winter Rd. Access Maintenance from A118-A122, and from A124-A126; Labourers Fuelling equipment and cleaning tracks; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124520200121-7Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting124520200121-7Operator - Principle - After Jan 108600Inv#007-R01 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1245 | 20200121-7 | 53510106 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building and Winter Rd. Access Maintenance from A118-A122, and from A124-A126; Labourers Fuelling equipment and cleaning tracks; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124520200121-7Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting124520200121-7Labourer - General - After Jan 1011660Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1246 | 20200121-8 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A123; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124620200121-8Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting124620200121-8Chainsaw and consumables- After Jan 103180Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1246 | 20200121-8 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A123; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124620200121-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting124620200121-8Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1246 | 20200121-8 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A123; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124620200121-8Foreman121140 | Corbiere and Sons Contracting124620200121-8Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1246 | 20200121-8 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A123; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124620200121-8L.O.A.4840 | Corbiere and Sons Contracting124620200121-8L.O.A.4840Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1246 | 20200121-8 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-01-21 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A123; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43854 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting124620200121-8Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting124620200121-8Labourer - Specialized - After Jan 10332310Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1.0425 | DAY | 182.81 | 0 |  |  | 254.1067 | 33.0339 | 287.1406 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Light Truck - Pick up- After Jan 101.042489254.1067 | Corbiere and Sons Contracting126020200122-1Light Truck - Pick up- After Jan 101.042489254.1067Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 254.1067 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510107 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.44333 | DAY | 182.81 | 0 |  |  | 108.0606 | 14.0479 | 122.1085 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Light Truck - Pick up- After Jan 100.4433257108.0606 | Corbiere and Sons Contracting126020200122-1Light Truck - Pick up- After Jan 100.4433257108.0606Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 54.0303 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.47921 | DAY | 182.81 | 0 |  |  | 116.8069 | 15.1849 | 131.9918 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Light Truck - Pick up- After Jan 100.4792078116.8069 | Corbiere and Sons Contracting126020200122-1Light Truck - Pick up- After Jan 100.4792078116.8069Inv#007-R01 | [5 empty] | 1 | 116.8069 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.59479 | DAY | 182.81 | 0 |  |  | 144.979 | 18.8473 | 163.8263 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Light Truck - Pick up- After Jan 100.5947856144.979 | Corbiere and Sons Contracting126020200122-1Light Truck - Pick up- After Jan 100.5947856144.979Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 144.979 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.89302 | DAY | 182.81 | 0 |  |  | 217.6734 | 28.2975 | 245.9709 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Light Truck - Pick up- After Jan 100.8930189217.6734 | Corbiere and Sons Contracting126020200122-1Light Truck - Pick up- After Jan 100.8930189217.6734Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 217.6734 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.90302 | DAY | 182.81 | 0 |  |  | 220.1114 | 28.6145 | 248.7259 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Light Truck - Pick up- After Jan 100.9030213220.1114 | Corbiere and Sons Contracting126020200122-1Light Truck - Pick up- After Jan 100.9030213220.1114Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 220.1114 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520107 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.052177 | DAY | 182.81 | 0 |  |  | 12.7181 | 1.6534 | 14.3715 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Light Truck - Pick up- After Jan 100.052176812.7181 | Corbiere and Sons Contracting126020200122-1Light Truck - Pick up- After Jan 100.052176812.7181Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 12.7181 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510106 | Access | 0 | Project Manager | 110 | 2.502 | HR |  |  | 110 | 0 | 275.2171 | 35.7782 | 310.9953 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Project Manager2.5019736275.2171 | Corbiere and Sons Contracting126020200122-1Project Manager2.5019736275.2171Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 275.2171 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510107 | Access | 0 | Project Manager | 110 | 1.064 | HR |  |  | 110 | 0 | 117.038 | 15.2149 | 132.2529 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Project Manager1.0639816117.038 | Corbiere and Sons Contracting126020200122-1Project Manager1.0639816117.038Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 58.519 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510111 | Access | 0 | Project Manager | 110 | 1.1501 | HR |  |  | 110 | 0 | 126.5109 | 16.4464 | 142.9573 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Project Manager1.1500987126.5109 | Corbiere and Sons Contracting126020200122-1Project Manager1.1500987126.5109Inv#007-R01 | [5 empty] | 1 | 126.5109 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 1.4275 | HR |  |  | 110 | 0 | 157.0234 | 20.413 | 177.4364 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Project Manager1.4274854157.0234 | Corbiere and Sons Contracting126020200122-1Project Manager1.4274854157.0234Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 157.0234 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520102 | Clearing | 0 | Project Manager | 110 | 2.1432 | HR |  |  | 110 | 0 | 235.757 | 30.6484 | 266.4054 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Project Manager2.1432453235.757 | Corbiere and Sons Contracting126020200122-1Project Manager2.1432453235.757Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 235.757 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520104 | Clearing | 0 | Project Manager | 110 | 2.1673 | HR |  |  | 110 | 0 | 238.3976 | 30.9917 | 269.3893 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Project Manager2.1672511238.3976 | Corbiere and Sons Contracting126020200122-1Project Manager2.1672511238.3976Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 238.3976 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520107 | Clearing | 0 | Project Manager | 110 | 0.12522 | HR |  |  | 110 | 0 | 13.7747 | 1.7907 | 15.5654 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Project Manager0.125224313.7747 | Corbiere and Sons Contracting126020200122-1Project Manager0.125224313.7747Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 13.7747 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510106 | Access | 0 | Superintendent | 105 | 2.502 | HR |  |  | 105 | 0 | 262.7072 | 34.1519 | 296.8591 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Superintendent2.5019736262.7072 | Corbiere and Sons Contracting126020200122-1Superintendent2.5019736262.7072Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 262.7072 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510107 | Access | 0 | Superintendent | 105 | 1.064 | HR |  |  | 105 | 0 | 111.7181 | 14.5234 | 126.2415 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Superintendent1.0639816111.7181 | Corbiere and Sons Contracting126020200122-1Superintendent1.0639816111.7181Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 55.8591 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510111 | Access | 0 | Superintendent | 105 | 1.1501 | HR |  |  | 105 | 0 | 120.7604 | 15.6989 | 136.4593 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Superintendent1.1500987120.7604 | Corbiere and Sons Contracting126020200122-1Superintendent1.1500987120.7604Inv#007-R01 | [5 empty] | 1 | 120.7604 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 1.4275 | HR |  |  | 105 | 0 | 149.886 | 19.4852 | 169.3712 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Superintendent1.4274854149.886 | Corbiere and Sons Contracting126020200122-1Superintendent1.4274854149.886Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 149.886 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520102 | Clearing | 0 | Superintendent | 105 | 2.1432 | HR |  |  | 105 | 0 | 225.0408 | 29.2553 | 254.2961 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Superintendent2.1432453225.0408 | Corbiere and Sons Contracting126020200122-1Superintendent2.1432453225.0408Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 225.0408 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520104 | Clearing | 0 | Superintendent | 105 | 2.1673 | HR |  |  | 105 | 0 | 227.5614 | 29.583 | 257.1444 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Superintendent2.1672511227.5614 | Corbiere and Sons Contracting126020200122-1Superintendent2.1672511227.5614Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 227.5614 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520107 | Clearing | 0 | Superintendent | 105 | 0.12522 | HR |  |  | 105 | 0 | 13.1486 | 1.7093 | 14.8579 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Superintendent0.125224313.1486 | Corbiere and Sons Contracting126020200122-1Superintendent0.125224313.1486Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 13.1486 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510106 | Access | 0 | Project Coordinator | 80 | 2.502 | HR |  |  | 80 | 0 | 200.1579 | 26.0205 | 226.1784 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Project Coordinator2.5019736200.1579 | Corbiere and Sons Contracting126020200122-1Project Coordinator2.5019736200.1579Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 200.1579 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510107 | Access | 0 | Project Coordinator | 80 | 1.064 | HR |  |  | 80 | 0 | 85.1185 | 11.0654 | 96.1839 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Project Coordinator1.063981685.1185 | Corbiere and Sons Contracting126020200122-1Project Coordinator1.063981685.1185Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 42.5592 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510111 | Access | 0 | Project Coordinator | 80 | 1.1501 | HR |  |  | 80 | 0 | 92.0079 | 11.961 | 103.9689 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Project Coordinator1.150098792.0079 | Corbiere and Sons Contracting126020200122-1Project Coordinator1.150098792.0079Inv#007-R01 | [5 empty] | 1 | 92.0079 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 1.4275 | HR |  |  | 80 | 0 | 114.1988 | 14.8458 | 129.0446 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Project Coordinator1.4274854114.1988 | Corbiere and Sons Contracting126020200122-1Project Coordinator1.4274854114.1988Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 114.1988 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520102 | Clearing | 0 | Project Coordinator | 80 | 2.1432 | HR |  |  | 80 | 0 | 171.4596 | 22.2897 | 193.7493 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Project Coordinator2.1432453171.4596 | Corbiere and Sons Contracting126020200122-1Project Coordinator2.1432453171.4596Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 171.4596 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520104 | Clearing | 0 | Project Coordinator | 80 | 2.1673 | HR |  |  | 80 | 0 | 173.3801 | 22.5394 | 195.9195 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Project Coordinator2.1672511173.3801 | Corbiere and Sons Contracting126020200122-1Project Coordinator2.1672511173.3801Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 173.3801 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520107 | Clearing | 0 | Project Coordinator | 80 | 0.12522 | HR |  |  | 80 | 0 | 10.0179 | 1.3023 | 11.3202 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Project Coordinator0.125224310.0179 | Corbiere and Sons Contracting126020200122-1Project Coordinator0.125224310.0179Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 10.0179 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510106 | Access | 0 | Safety Advisor | 85 | 2.502 | HR |  |  | 85 | 0 | 212.6678 | 27.6468 | 240.3146 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Safety Advisor2.5019736212.6678 | Corbiere and Sons Contracting126020200122-1Safety Advisor2.5019736212.6678Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 212.6678 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510107 | Access | 0 | Safety Advisor | 85 | 1.064 | HR |  |  | 85 | 0 | 90.4384 | 11.757 | 102.1954 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Safety Advisor1.063981690.4384 | Corbiere and Sons Contracting126020200122-1Safety Advisor1.063981690.4384Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 45.2192 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510111 | Access | 0 | Safety Advisor | 85 | 1.1501 | HR |  |  | 85 | 0 | 97.7584 | 12.7086 | 110.467 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Safety Advisor1.150098797.7584 | Corbiere and Sons Contracting126020200122-1Safety Advisor1.150098797.7584Inv#007-R01 | [5 empty] | 1 | 97.7584 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 1.4275 | HR |  |  | 85 | 0 | 121.3363 | 15.7737 | 137.11 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Safety Advisor1.4274854121.3363 | Corbiere and Sons Contracting126020200122-1Safety Advisor1.4274854121.3363Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 121.3363 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520102 | Clearing | 0 | Safety Advisor | 85 | 2.1432 | HR |  |  | 85 | 0 | 182.1759 | 23.6829 | 205.8588 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Safety Advisor2.1432453182.1759 | Corbiere and Sons Contracting126020200122-1Safety Advisor2.1432453182.1759Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 182.1759 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520104 | Clearing | 0 | Safety Advisor | 85 | 2.1673 | HR |  |  | 85 | 0 | 184.2163 | 23.9481 | 208.1644 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Safety Advisor2.1672511184.2163 | Corbiere and Sons Contracting126020200122-1Safety Advisor2.1672511184.2163Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 184.2163 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520107 | Clearing | 0 | Safety Advisor | 85 | 0.12522 | HR |  |  | 85 | 0 | 10.6441 | 1.3837 | 12.0278 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Safety Advisor0.125224310.6441 | Corbiere and Sons Contracting126020200122-1Safety Advisor0.125224310.6441Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 10.6441 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510106 | Access | 0 | Site Administrator | 50 | 2.085 | HR |  |  | 50 | 0 | 104.2489 | 13.5524 | 117.8013 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Site Administrator2.084978104.2489 | Corbiere and Sons Contracting126020200122-1Site Administrator2.084978104.2489Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 104.2489 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510107 | Access | 0 | Site Administrator | 50 | 0.88665 | HR |  |  | 50 | 0 | 44.3326 | 5.7632 | 50.0958 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Site Administrator0.886651344.3326 | Corbiere and Sons Contracting126020200122-1Site Administrator0.886651344.3326Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 22.1663 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510111 | Access | 0 | Site Administrator | 50 | 0.95842 | HR |  |  | 50 | 0 | 47.9208 | 6.2297 | 54.1505 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Site Administrator0.958415647.9208 | Corbiere and Sons Contracting126020200122-1Site Administrator0.958415647.9208Inv#007-R01 | [5 empty] | 1 | 47.9208 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520101 | Clearing | 0 | Site Administrator | 50 | 1.1896 | HR |  |  | 50 | 0 | 59.4786 | 7.7322 | 67.2108 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Site Administrator1.189571159.4786 | Corbiere and Sons Contracting126020200122-1Site Administrator1.189571159.4786Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 59.4786 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520102 | Clearing | 0 | Site Administrator | 50 | 1.786 | HR |  |  | 50 | 0 | 89.3019 | 11.6092 | 100.9111 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Site Administrator1.786037789.3019 | Corbiere and Sons Contracting126020200122-1Site Administrator1.786037789.3019Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 89.3019 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520104 | Clearing | 0 | Site Administrator | 50 | 1.806 | HR |  |  | 50 | 0 | 90.3021 | 11.7393 | 102.0414 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Site Administrator1.806042590.3021 | Corbiere and Sons Contracting126020200122-1Site Administrator1.806042590.3021Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 90.3021 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520107 | Clearing | 0 | Site Administrator | 50 | 0.10435 | HR |  |  | 50 | 0 | 5.2177 | 0.6783 | 5.896 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Site Administrator0.10435365.2177 | Corbiere and Sons Contracting126020200122-1Site Administrator0.10435365.2177Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 5.2177 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510106 | Access | 0 | Project Controls | 70 | 2.502 | HR |  |  | 70 | 0 | 175.1382 | 22.768 | 197.9062 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Project Controls2.5019736175.1382 | Corbiere and Sons Contracting126020200122-1Project Controls2.5019736175.1382Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 175.1382 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510107 | Access | 0 | Project Controls | 70 | 1.064 | HR |  |  | 70 | 0 | 74.4787 | 9.6822 | 84.1609 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Project Controls1.063981674.4787 | Corbiere and Sons Contracting126020200122-1Project Controls1.063981674.4787Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 37.2394 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510111 | Access | 0 | Project Controls | 70 | 1.1501 | HR |  |  | 70 | 0 | 80.5069 | 10.4659 | 90.9728 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Project Controls1.150098780.5069 | Corbiere and Sons Contracting126020200122-1Project Controls1.150098780.5069Inv#007-R01 | [5 empty] | 1 | 80.5069 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 1.4275 | HR |  |  | 70 | 0 | 99.924 | 12.9901 | 112.9141 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Project Controls1.427485499.924 | Corbiere and Sons Contracting126020200122-1Project Controls1.427485499.924Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 99.924 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520102 | Clearing | 0 | Project Controls | 70 | 2.1432 | HR |  |  | 70 | 0 | 150.0272 | 19.5035 | 169.5307 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Project Controls2.1432453150.0272 | Corbiere and Sons Contracting126020200122-1Project Controls2.1432453150.0272Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 150.0272 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520104 | Clearing | 0 | Project Controls | 70 | 2.1673 | HR |  |  | 70 | 0 | 151.7076 | 19.722 | 171.4296 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Project Controls2.1672511151.7076 | Corbiere and Sons Contracting126020200122-1Project Controls2.1672511151.7076Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 151.7076 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520107 | Clearing | 0 | Project Controls | 70 | 0.12522 | HR |  |  | 70 | 0 | 8.7657 | 1.1395 | 9.9052 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1Project Controls0.12522438.7657 | Corbiere and Sons Contracting126020200122-1Project Controls0.12522438.7657Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 8.7657 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510106 | Access | 0 | L.O.A. | 210 | 1.251 | DAY |  |  |  | 0 | 262.7072 | 34.1519 | 296.8591 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1L.O.A.1.2509868262.7072 | Corbiere and Sons Contracting126020200122-1L.O.A.1.2509868262.7072Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 262.7072 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510107 | Access | 0 | L.O.A. | 210 | 0.53199 | DAY |  |  |  | 0 | 111.7181 | 14.5234 | 126.2415 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1L.O.A.0.5319908111.7181 | Corbiere and Sons Contracting126020200122-1L.O.A.0.5319908111.7181Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 55.8591 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53510111 | Access | 0 | L.O.A. | 210 | 0.57505 | DAY |  |  |  | 0 | 120.7604 | 15.6989 | 136.4593 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1L.O.A.0.5750493120.7604 | Corbiere and Sons Contracting126020200122-1L.O.A.0.5750493120.7604Inv#007-R01 | [5 empty] | 1 | 120.7604 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 0.71374 | DAY |  |  |  | 0 | 149.886 | 19.4852 | 169.3712 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1L.O.A.0.7137427149.886 | Corbiere and Sons Contracting126020200122-1L.O.A.0.7137427149.886Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 149.886 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1.0716 | DAY |  |  |  | 0 | 225.0407 | 29.2553 | 254.296 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1L.O.A.1.0716226225.0407 | Corbiere and Sons Contracting126020200122-1L.O.A.1.0716226225.0407Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 225.0407 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 1.0836 | DAY |  |  |  | 0 | 227.5614 | 29.583 | 257.1444 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1L.O.A.1.0836255227.5614 | Corbiere and Sons Contracting126020200122-1L.O.A.1.0836255227.5614Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 227.5614 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1260 | 20200122-1 | 53520107 | Clearing | 0 | L.O.A. | 210 | 0.062612 | DAY |  |  |  | 0 | 13.1486 | 1.7093 | 14.8579 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126020200122-1L.O.A.0.062612213.1486 | Corbiere and Sons Contracting126020200122-1L.O.A.0.062612213.1486Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 13.1486 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1269 | 20200122-10 | 53510211 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal from access roads | 2 |  |  | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting126920200122-10Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting126920200122-10Dozer D6 or equal- After Jan 1091183.32Inv#007-R01 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1269 | 20200122-10 | 53510211 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal from access roads | 2 |  |  | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting126920200122-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting126920200122-10Light Truck - Pick up- After Jan 101243.75Inv#007-R01 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1269 | 20200122-10 | 53510211 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal from access roads | 2 |  |  | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting126920200122-10L.O.A.1210 | Corbiere and Sons Contracting126920200122-10L.O.A.1210Inv#007-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1269 | 20200122-10 | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal from access roads | 2 |  |  | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting126920200122-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting126920200122-10Operator - Principle - After Jan 1011825Inv#007-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53510106 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 1.0425 | HR | 74.25 | 0 |  |  | 103.2064 | 13.4168 | 116.6232 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Loader JD 524 to 624 or equal1.042489103.2064 | Corbiere and Sons Contracting127220200122-13Loader JD 524 to 624 or equal1.042489103.2064Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 103.2064 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 0.47921 | HR | 74.25 | 0 |  |  | 47.4416 | 6.1674 | 53.609 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Loader JD 524 to 624 or equal0.479207847.4416 | Corbiere and Sons Contracting127220200122-13Loader JD 524 to 624 or equal0.479207847.4416Inv#007-R01 | [5 empty] | 1 | 47.4416 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.59479 | HR | 74.25 | 0 |  |  | 58.8838 | 7.6549 | 66.5387 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Loader JD 524 to 624 or equal0.594785658.8838 | Corbiere and Sons Contracting127220200122-13Loader JD 524 to 624 or equal0.594785658.8838Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 58.8838 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520102 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.89302 | HR | 74.25 | 0 |  |  | 88.4089 | 11.4932 | 99.9021 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Loader JD 524 to 624 or equal0.893018988.4089 | Corbiere and Sons Contracting127220200122-13Loader JD 524 to 624 or equal0.893018988.4089Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 88.4089 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520104 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.90302 | HR | 74.25 | 0 |  |  | 89.3991 | 11.6219 | 101.021 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Loader JD 524 to 624 or equal0.903021389.3991 | Corbiere and Sons Contracting127220200122-13Loader JD 524 to 624 or equal0.903021389.3991Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 89.3991 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520107 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.052177 | HR | 74.25 | 0 |  |  | 5.1655 | 0.67151 | 5.837 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Loader JD 524 to 624 or equal0.05217685.1655 | Corbiere and Sons Contracting127220200122-13Loader JD 524 to 624 or equal0.05217685.1655Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 5.1655 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.62549 | DAY | 182.81 | 0 |  |  | 152.464 | 19.8203 | 172.2843 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Light Truck - Pick up- After Jan 100.6254934152.464 | Corbiere and Sons Contracting127220200122-13Light Truck - Pick up- After Jan 100.6254934152.464Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 152.464 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.28752 | DAY | 182.81 | 0 |  |  | 70.0841 | 9.1109 | 79.195 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Light Truck - Pick up- After Jan 100.287524770.0841 | Corbiere and Sons Contracting127220200122-13Light Truck - Pick up- After Jan 100.287524770.0841Inv#007-R01 | [5 empty] | 1 | 70.0841 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.35687 | DAY | 182.81 | 0 |  |  | 86.9874 | 11.3084 | 98.2958 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Light Truck - Pick up- After Jan 100.356871386.9874 | Corbiere and Sons Contracting127220200122-13Light Truck - Pick up- After Jan 100.356871386.9874Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 86.9874 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.53581 | DAY | 182.81 | 0 |  |  | 130.604 | 16.9785 | 147.5825 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Light Truck - Pick up- After Jan 100.5358113130.604 | Corbiere and Sons Contracting127220200122-13Light Truck - Pick up- After Jan 100.5358113130.604Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 130.604 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.54181 | DAY | 182.81 | 0 |  |  | 132.0669 | 17.1687 | 149.2356 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Light Truck - Pick up- After Jan 100.5418128132.0669 | Corbiere and Sons Contracting127220200122-13Light Truck - Pick up- After Jan 100.5418128132.0669Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 132.0669 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520107 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.031306 | DAY | 182.81 | 0 |  |  | 7.6309 | 0.99202 | 8.6229 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Light Truck - Pick up- After Jan 100.03130617.6309 | Corbiere and Sons Contracting127220200122-13Light Truck - Pick up- After Jan 100.03130617.6309Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 7.6309 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53510106 | Access | 0 | Project Coordinator | 80 | 2.502 | HR |  |  | 80 | 0 | 200.1579 | 26.0205 | 226.1784 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Project Coordinator2.5019736200.1579 | Corbiere and Sons Contracting127220200122-13Project Coordinator2.5019736200.1579Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 200.1579 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53510111 | Access | 0 | Project Coordinator | 80 | 1.1501 | HR |  |  | 80 | 0 | 92.0079 | 11.961 | 103.9689 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Project Coordinator1.150098792.0079 | Corbiere and Sons Contracting127220200122-13Project Coordinator1.150098792.0079Inv#007-R01 | [5 empty] | 1 | 92.0079 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 1.4275 | HR |  |  | 80 | 0 | 114.1988 | 14.8458 | 129.0446 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Project Coordinator1.4274854114.1988 | Corbiere and Sons Contracting127220200122-13Project Coordinator1.4274854114.1988Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 114.1988 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520102 | Clearing | 0 | Project Coordinator | 80 | 2.1432 | HR |  |  | 80 | 0 | 171.4596 | 22.2897 | 193.7493 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Project Coordinator2.1432453171.4596 | Corbiere and Sons Contracting127220200122-13Project Coordinator2.1432453171.4596Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 171.4596 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520104 | Clearing | 0 | Project Coordinator | 80 | 2.1673 | HR |  |  | 80 | 0 | 173.3801 | 22.5394 | 195.9195 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Project Coordinator2.1672511173.3801 | Corbiere and Sons Contracting127220200122-13Project Coordinator2.1672511173.3801Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 173.3801 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520107 | Clearing | 0 | Project Coordinator | 80 | 0.12522 | HR |  |  | 80 | 0 | 10.0179 | 1.3023 | 11.3202 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Project Coordinator0.125224310.0179 | Corbiere and Sons Contracting127220200122-13Project Coordinator0.125224310.0179Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 10.0179 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53510106 | Access | 0 | Foreman | 95 | 2.502 | HR |  |  | 95 | 0 | 237.6875 | 30.8994 | 268.5869 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Foreman2.5019736237.6875 | Corbiere and Sons Contracting127220200122-13Foreman2.5019736237.6875Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 237.6875 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53510111 | Access | 0 | Foreman | 95 | 1.1501 | HR |  |  | 95 | 0 | 109.2594 | 14.2037 | 123.4631 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Foreman1.1500987109.2594 | Corbiere and Sons Contracting127220200122-13Foreman1.1500987109.2594Inv#007-R01 | [5 empty] | 1 | 109.2594 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520101 | Clearing | 0 | Foreman | 95 | 1.4275 | HR |  |  | 95 | 0 | 135.6111 | 17.6294 | 153.2405 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Foreman1.4274854135.6111 | Corbiere and Sons Contracting127220200122-13Foreman1.4274854135.6111Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 135.6111 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520102 | Clearing | 0 | Foreman | 95 | 2.1432 | HR |  |  | 95 | 0 | 203.6083 | 26.4691 | 230.0774 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Foreman2.1432453203.6083 | Corbiere and Sons Contracting127220200122-13Foreman2.1432453203.6083Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 203.6083 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520104 | Clearing | 0 | Foreman | 95 | 2.1673 | HR |  |  | 95 | 0 | 205.8889 | 26.7656 | 232.6545 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Foreman2.1672511205.8889 | Corbiere and Sons Contracting127220200122-13Foreman2.1672511205.8889Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 205.8889 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520107 | Clearing | 0 | Foreman | 95 | 0.12522 | HR |  |  | 95 | 0 | 11.8963 | 1.5465 | 13.4428 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Foreman0.125224311.8963 | Corbiere and Sons Contracting127220200122-13Foreman0.125224311.8963Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 11.8963 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53510106 | Access | 0 | L.O.A. | 210 | 0.83399 | DAY |  |  |  | 0 | 175.1382 | 22.768 | 197.9062 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13L.O.A.0.8339912175.1382 | Corbiere and Sons Contracting127220200122-13L.O.A.0.8339912175.1382Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 175.1382 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53510111 | Access | 0 | L.O.A. | 210 | 0.38337 | DAY |  |  |  | 0 | 80.5069 | 10.4659 | 90.9728 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13L.O.A.0.383366280.5069 | Corbiere and Sons Contracting127220200122-13L.O.A.0.383366280.5069Inv#007-R01 | [5 empty] | 1 | 80.5069 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520101 | Clearing | 0 | L.O.A. | 210 | 0.47583 | DAY |  |  |  | 0 | 99.924 | 12.9901 | 112.9141 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13L.O.A.0.475828599.924 | Corbiere and Sons Contracting127220200122-13L.O.A.0.475828599.924Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 99.924 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520102 | Clearing | 0 | L.O.A. | 210 | 0.71442 | DAY |  |  |  | 0 | 150.0272 | 19.5035 | 169.5307 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13L.O.A.0.7144151150.0272 | Corbiere and Sons Contracting127220200122-13L.O.A.0.7144151150.0272Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 150.0272 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520104 | Clearing | 0 | L.O.A. | 210 | 0.72242 | DAY |  |  |  | 0 | 151.7076 | 19.722 | 171.4296 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13L.O.A.0.722417151.7076 | Corbiere and Sons Contracting127220200122-13L.O.A.0.722417151.7076Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 151.7076 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520107 | Clearing | 0 | L.O.A. | 210 | 0.041741 | DAY |  |  |  | 0 | 8.7657 | 1.1395 | 9.9052 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13L.O.A.0.04174148.7657 | Corbiere and Sons Contracting127220200122-13L.O.A.0.04174148.7657Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 8.7657 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53510106 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 1.251 | HR |  |  | 70 | 0 | 87.5691 | 11.384 | 98.9531 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Operator - Intermdiate - After Jan 101.250986887.5691 | Corbiere and Sons Contracting127220200122-13Operator - Intermdiate - After Jan 101.250986887.5691Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 87.5691 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53510111 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 0.57505 | HR |  |  | 70 | 0 | 40.2535 | 5.233 | 45.4865 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Operator - Intermdiate - After Jan 100.575049340.2535 | Corbiere and Sons Contracting127220200122-13Operator - Intermdiate - After Jan 100.575049340.2535Inv#007-R01 | [5 empty] | 1 | 40.2535 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520101 | Clearing | 0 | Operator - Intermdiate - After Jan 10 | 70 | 0.71374 | HR |  |  | 70 | 0 | 49.962 | 6.4951 | 56.4571 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Operator - Intermdiate - After Jan 100.713742749.962 | Corbiere and Sons Contracting127220200122-13Operator - Intermdiate - After Jan 100.713742749.962Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 49.962 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520102 | Clearing | 0 | Operator - Intermdiate - After Jan 10 | 70 | 1.0716 | HR |  |  | 70 | 0 | 75.0136 | 9.7518 | 84.7654 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Operator - Intermdiate - After Jan 101.071622675.0136 | Corbiere and Sons Contracting127220200122-13Operator - Intermdiate - After Jan 101.071622675.0136Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 75.0136 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520104 | Clearing | 0 | Operator - Intermdiate - After Jan 10 | 70 | 1.0836 | HR |  |  | 70 | 0 | 75.8538 | 9.861 | 85.7148 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Operator - Intermdiate - After Jan 101.083625575.8538 | Corbiere and Sons Contracting127220200122-13Operator - Intermdiate - After Jan 101.083625575.8538Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 75.8538 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520107 | Clearing | 0 | Operator - Intermdiate - After Jan 10 | 70 | 0.062612 | HR |  |  | 70 | 0 | 4.3829 | 0.56978 | 4.9527 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Operator - Intermdiate - After Jan 100.06261224.3829 | Corbiere and Sons Contracting127220200122-13Operator - Intermdiate - After Jan 100.06261224.3829Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 4.3829 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53510106 | Access | 0 | Labourer - General - After Jan 10 | 60 | 2.2935 | HR |  |  | 60 | 0 | 137.6085 | 17.8891 | 155.4976 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Labourer - General - After Jan 102.2934758137.6085 | Corbiere and Sons Contracting127220200122-13Labourer - General - After Jan 102.2934758137.6085Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 137.6085 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53510111 | Access | 0 | Labourer - General - After Jan 10 | 60 | 1.0543 | HR |  |  | 60 | 0 | 63.2554 | 8.2232 | 71.4786 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Labourer - General - After Jan 101.054257163.2554 | Corbiere and Sons Contracting127220200122-13Labourer - General - After Jan 101.054257163.2554Inv#007-R01 | [5 empty] | 1 | 63.2554 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520101 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 1.3085 | HR |  |  | 60 | 0 | 78.5117 | 10.2065 | 88.7182 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Labourer - General - After Jan 101.308528378.5117 | Corbiere and Sons Contracting127220200122-13Labourer - General - After Jan 101.308528378.5117Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 78.5117 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 1.9646 | HR |  |  | 60 | 0 | 117.8785 | 15.3242 | 133.2027 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Labourer - General - After Jan 101.9646415117.8785 | Corbiere and Sons Contracting127220200122-13Labourer - General - After Jan 101.9646415117.8785Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 117.8785 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520104 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 1.9866 | HR |  |  | 60 | 0 | 119.1988 | 15.4958 | 134.6946 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Labourer - General - After Jan 101.9866468119.1988 | Corbiere and Sons Contracting127220200122-13Labourer - General - After Jan 101.9866468119.1988Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 119.1988 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1272 | 20200122-13 | 53520107 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 0.11479 | HR |  |  | 60 | 0 | 6.8873 | 0.89535 | 7.7826 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Workfront Supervision and yard maintenance | 6 |  | Terrace Bay Yard | 1 | 43855 |  | 17 | 43864 | [5 empty] | David Mercer | 01 | Corbiere and Sons Contracting127220200122-13Labourer - General - After Jan 100.11478896.8873 | Corbiere and Sons Contracting127220200122-13Labourer - General - After Jan 100.11478896.8873Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 6.8873 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1274 | 20200122-15-R1 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Maintenance and Building of Winter Road at Santoy Mountain; Importing of Sand; | 6 |  | Santoy Mountain | 0 | 43855 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting127420200122-15-R1Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting127420200122-15-R1Dozer D6 or equal- After Jan 1091183.32Inv#007-R01 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1274 | 20200122-15-R1 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Maintenance and Building of Winter Road at Santoy Mountain; Importing of Sand; | 6 |  | Santoy Mountain | 0 | 43855 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting127420200122-15-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting127420200122-15-R1Light Truck - Pick up- After Jan 101243.75Inv#007-R01 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1274 | 20200122-15-R1 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Maintenance and Building of Winter Road at Santoy Mountain; Importing of Sand; | 6 |  | Santoy Mountain | 0 | 43855 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting127420200122-15-R1L.O.A.1210 | Corbiere and Sons Contracting127420200122-15-R1L.O.A.1210Inv#007-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1274 | 20200122-15-R1 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Maintenance and Building of Winter Road at Santoy Mountain; Importing of Sand; | 6 |  | Santoy Mountain | 0 | 43855 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting127420200122-15-R1Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting127420200122-15-R1Operator - Intermdiate - After Jan 1011770Inv#007-R01 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1261 | 20200122-2 | 53510106 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 1.0425 | HR | 74.25 | 0 |  |  | 103.2064 | 13.4168 | 116.6232 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126120200122-2Loader JD 524 to 624 or equal1.042489103.2064 | Corbiere and Sons Contracting126120200122-2Loader JD 524 to 624 or equal1.042489103.2064Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 103.2064 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1261 | 20200122-2 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 0.47921 | HR | 74.25 | 0 |  |  | 47.4416 | 6.1674 | 53.609 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126120200122-2Loader JD 524 to 624 or equal0.479207847.4416 | Corbiere and Sons Contracting126120200122-2Loader JD 524 to 624 or equal0.479207847.4416Inv#007-R01 | [5 empty] | 1 | 47.4416 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1261 | 20200122-2 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.59479 | HR | 74.25 | 0 |  |  | 58.8838 | 7.6549 | 66.5387 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126120200122-2Loader JD 524 to 624 or equal0.594785658.8838 | Corbiere and Sons Contracting126120200122-2Loader JD 524 to 624 or equal0.594785658.8838Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 58.8838 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1261 | 20200122-2 | 53520102 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.89302 | HR | 74.25 | 0 |  |  | 88.4089 | 11.4932 | 99.9021 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126120200122-2Loader JD 524 to 624 or equal0.893018988.4089 | Corbiere and Sons Contracting126120200122-2Loader JD 524 to 624 or equal0.893018988.4089Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 88.4089 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1261 | 20200122-2 | 53520104 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.90302 | HR | 74.25 | 0 |  |  | 89.3991 | 11.6219 | 101.021 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126120200122-2Loader JD 524 to 624 or equal0.903021389.3991 | Corbiere and Sons Contracting126120200122-2Loader JD 524 to 624 or equal0.903021389.3991Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 89.3991 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1261 | 20200122-2 | 53520107 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.052177 | HR | 74.25 | 0 |  |  | 5.1655 | 0.67151 | 5.837 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126120200122-2Loader JD 524 to 624 or equal0.05217685.1655 | Corbiere and Sons Contracting126120200122-2Loader JD 524 to 624 or equal0.05217685.1655Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 5.1655 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1261 | 20200122-2 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.2085 | DAY | 182.81 | 0 |  |  | 50.8213 | 6.6068 | 57.4281 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126120200122-2Light Truck - Pick up- After Jan 100.208497850.8213 | Corbiere and Sons Contracting126120200122-2Light Truck - Pick up- After Jan 100.208497850.8213Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 50.8213 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1261 | 20200122-2 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.095842 | DAY | 182.81 | 0 |  |  | 23.3614 | 3.037 | 26.3984 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126120200122-2Light Truck - Pick up- After Jan 100.095841623.3614 | Corbiere and Sons Contracting126120200122-2Light Truck - Pick up- After Jan 100.095841623.3614Inv#007-R01 | [5 empty] | 1 | 23.3614 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1261 | 20200122-2 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.11896 | DAY | 182.81 | 0 |  |  | 28.9958 | 3.7695 | 32.7653 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126120200122-2Light Truck - Pick up- After Jan 100.118957128.9958 | Corbiere and Sons Contracting126120200122-2Light Truck - Pick up- After Jan 100.118957128.9958Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 28.9958 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1261 | 20200122-2 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.1786 | DAY | 182.81 | 0 |  |  | 43.5347 | 5.6595 | 49.1942 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126120200122-2Light Truck - Pick up- After Jan 100.178603843.5347 | Corbiere and Sons Contracting126120200122-2Light Truck - Pick up- After Jan 100.178603843.5347Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 43.5347 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1261 | 20200122-2 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.1806 | DAY | 182.81 | 0 |  |  | 44.0223 | 5.7229 | 49.7452 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126120200122-2Light Truck - Pick up- After Jan 100.180604344.0223 | Corbiere and Sons Contracting126120200122-2Light Truck - Pick up- After Jan 100.180604344.0223Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 44.0223 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1261 | 20200122-2 | 53520107 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.010435 | DAY | 182.81 | 0 |  |  | 2.5436 | 0.33067 | 2.8743 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126120200122-2Light Truck - Pick up- After Jan 100.01043542.5436 | Corbiere and Sons Contracting126120200122-2Light Truck - Pick up- After Jan 100.01043542.5436Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 2.5436 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1261 | 20200122-2 | 53510106 | Access | 0 | Operator - Apprentice | 60 | 2.085 | HR |  |  | 60 | 0 | 125.0987 | 16.2628 | 141.3615 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126120200122-2Operator - Apprentice2.084978125.0987 | Corbiere and Sons Contracting126120200122-2Operator - Apprentice2.084978125.0987Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 125.0987 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1261 | 20200122-2 | 53510111 | Access | 0 | Operator - Apprentice | 60 | 0.95842 | HR |  |  | 60 | 0 | 57.5049 | 7.4756 | 64.9805 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126120200122-2Operator - Apprentice0.958415657.5049 | Corbiere and Sons Contracting126120200122-2Operator - Apprentice0.958415657.5049Inv#007-R01 | [5 empty] | 1 | 57.5049 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1261 | 20200122-2 | 53520101 | Clearing | 0 | Operator - Apprentice | 60 | 1.1896 | HR |  |  | 60 | 0 | 71.3743 | 9.2787 | 80.653 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126120200122-2Operator - Apprentice1.189571171.3743 | Corbiere and Sons Contracting126120200122-2Operator - Apprentice1.189571171.3743Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 71.3743 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1261 | 20200122-2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 1.786 | HR |  |  | 60 | 0 | 107.1623 | 13.9311 | 121.0934 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126120200122-2Operator - Apprentice1.7860377107.1623 | Corbiere and Sons Contracting126120200122-2Operator - Apprentice1.7860377107.1623Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 107.1623 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1261 | 20200122-2 | 53520104 | Clearing | 0 | Operator - Apprentice | 60 | 1.806 | HR |  |  | 60 | 0 | 108.3625 | 14.0871 | 122.4496 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126120200122-2Operator - Apprentice1.8060425108.3625 | Corbiere and Sons Contracting126120200122-2Operator - Apprentice1.8060425108.3625Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 108.3625 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1261 | 20200122-2 | 53520107 | Clearing | 0 | Operator - Apprentice | 60 | 0.10435 | HR |  |  | 60 | 0 | 6.2612 | 0.81396 | 7.0752 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 1 |  |  | 1 | 43855 |  | 40 | 43860 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126120200122-2Operator - Apprentice0.10435366.2612 | Corbiere and Sons Contracting126120200122-2Operator - Apprentice0.10435366.2612Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 6.2612 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1262 | 20200122-3-R1 | 53520101 | Clearing | 0 | Brusher | 202.5 | 6 | HR | 151.88 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Bunching skidding and float moves to Lofty Davies; Brushing at A067-A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 40 | 43864 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126220200122-3-R1Brusher61215 | Corbiere and Sons Contracting126220200122-3-R1Brusher61215Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1262 | 20200122-3-R1 | 53520102 | Clearing | 0 | Brusher | 202.5 | 2 | HR | 151.88 | 0 |  |  | 405 | 52.65 | 457.65 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Bunching skidding and float moves to Lofty Davies; Brushing at A067-A068; | 1 | A-055 to A-084 | Eldorado | 1 | 43854 |  | 40 | 43864 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126220200122-3-R1Brusher2405 | Corbiere and Sons Contracting126220200122-3-R1Brusher2405Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 405 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1262 | 20200122-3-R1 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 13 | HR | 180 | 0 |  |  | 3120 | 405.6 | 3525.6 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Bunching skidding and float moves to Lofty Davies; Brushing at A067-A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 40 | 43864 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126220200122-3-R1Feller Buncher133120 | Corbiere and Sons Contracting126220200122-3-R1Feller Buncher133120Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1262 | 20200122-3-R1 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 5 | HR | 180 | 0 |  |  | 1200 | 156 | 1356 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Bunching skidding and float moves to Lofty Davies; Brushing at A067-A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 40 | 43864 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126220200122-3-R1Feller Buncher51200 | Corbiere and Sons Contracting126220200122-3-R1Feller Buncher51200Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1262 | 20200122-3-R1 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Bunching skidding and float moves to Lofty Davies; Brushing at A067-A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 40 | 43864 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126220200122-3-R1Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting126220200122-3-R1Grinder - 4710 Peterson or equal95011.2Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1262 | 20200122-3-R1 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Bunching skidding and float moves to Lofty Davies; Brushing at A067-A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 40 | 43864 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126220200122-3-R1Log Loader91377 | Corbiere and Sons Contracting126220200122-3-R1Log Loader91377Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1262 | 20200122-3-R1 | 53520101 | Clearing | 0 | Skidder | 171 | 4 | HR | 128.25 | 0 |  |  | 684 | 88.92 | 772.92 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Bunching skidding and float moves to Lofty Davies; Brushing at A067-A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 40 | 43864 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126220200122-3-R1Skidder 4684 | Corbiere and Sons Contracting126220200122-3-R1Skidder 4684Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 684 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1262 | 20200122-3-R1 | 53520102 | Clearing | 0 | Skidder | 171 | 5 | HR | 128.25 | 0 |  |  | 855 | 111.15 | 966.15 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Bunching skidding and float moves to Lofty Davies; Brushing at A067-A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 40 | 43864 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126220200122-3-R1Skidder 5855 | Corbiere and Sons Contracting126220200122-3-R1Skidder 5855Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 855 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1262 | 20200122-3-R1 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Bunching skidding and float moves to Lofty Davies; Brushing at A067-A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 40 | 43864 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126220200122-3-R1Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting126220200122-3-R1Light Truck - Pick up- After Jan 103731.25Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1262 | 20200122-3-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Bunching skidding and float moves to Lofty Davies; Brushing at A067-A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 40 | 43864 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126220200122-3-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting126220200122-3-R1Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1262 | 20200122-3-R1 | 53520107 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Bunching skidding and float moves to Lofty Davies; Brushing at A067-A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 40 | 43864 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126220200122-3-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting126220200122-3-R1Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1262 | 20200122-3-R1 | 53520101 | Clearing | 0 | Foreman | 95 | 8 | HR |  |  | 95 | 0 | 760 | 98.8 | 858.8 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Bunching skidding and float moves to Lofty Davies; Brushing at A067-A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 40 | 43864 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126220200122-3-R1Foreman8760 | Corbiere and Sons Contracting126220200122-3-R1Foreman8760Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 760 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1262 | 20200122-3-R1 | 53520102 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Bunching skidding and float moves to Lofty Davies; Brushing at A067-A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 40 | 43864 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126220200122-3-R1Foreman4380 | Corbiere and Sons Contracting126220200122-3-R1Foreman4380Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1262 | 20200122-3-R1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Bunching skidding and float moves to Lofty Davies; Brushing at A067-A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 40 | 43864 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126220200122-3-R1L.O.A.61260 | Corbiere and Sons Contracting126220200122-3-R1L.O.A.61260Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1262 | 20200122-3-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Bunching skidding and float moves to Lofty Davies; Brushing at A067-A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 40 | 43864 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126220200122-3-R1L.O.A.1210 | Corbiere and Sons Contracting126220200122-3-R1L.O.A.1210Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1262 | 20200122-3-R1 | 53520107 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Bunching skidding and float moves to Lofty Davies; Brushing at A067-A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 40 | 43864 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126220200122-3-R1L.O.A.1210 | Corbiere and Sons Contracting126220200122-3-R1L.O.A.1210Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1262 | 20200122-3-R1 | 53520101 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 26 | HR |  |  | 75 | 0 | 1950 | 253.5 | 2203.5 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Bunching skidding and float moves to Lofty Davies; Brushing at A067-A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 40 | 43864 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126220200122-3-R1Operator - Principle - After Jan 10261950 | Corbiere and Sons Contracting126220200122-3-R1Operator - Principle - After Jan 10261950Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1262 | 20200122-3-R1 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 28 | HR |  |  | 75 | 0 | 2100 | 273 | 2373 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Bunching skidding and float moves to Lofty Davies; Brushing at A067-A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 40 | 43864 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126220200122-3-R1Operator - Principle - After Jan 10282100 | Corbiere and Sons Contracting126220200122-3-R1Operator - Principle - After Jan 10282100Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1262 | 20200122-3-R1 | 53520101 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 4 | HR |  |  | 60 | 0 | 240 | 31.2 | 271.2 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Bunching skidding and float moves to Lofty Davies; Brushing at A067-A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 40 | 43864 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126220200122-3-R1Labourer - General - After Jan 104240 | Corbiere and Sons Contracting126220200122-3-R1Labourer - General - After Jan 104240Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1262 | 20200122-3-R1 | 53520107 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 7 | HR |  |  | 60 | 0 | 420 | 54.6 | 474.6 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061; Bunching skidding and float moves to Lofty Davies; Brushing at A067-A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43854 |  | 40 | 43864 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting126220200122-3-R1Labourer - General - After Jan 107420 | Corbiere and Sons Contracting126220200122-3-R1Labourer - General - After Jan 107420Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1263 | 20200122-4 | 53510107 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning off execess snow and improving ditching and then mobilizing to Lofty Davies | 1 | A-055 to A-084 | Eldorado | 0 | 43886 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126320200122-4Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting126320200122-4Dozer D6 or equal- After Jan 105657.4Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1263 | 20200122-4 | 53510107 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning off execess snow and improving ditching and then mobilizing to Lofty Davies | 1 | A-055 to A-084 | Eldorado | 0 | 43886 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126320200122-4Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting126320200122-4Excavator - 30 ton- After Jan 105692.25Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 692.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1263 | 20200122-4 | 53510107 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning off execess snow and improving ditching and then mobilizing to Lofty Davies | 1 | A-055 to A-084 | Eldorado | 0 | 43886 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126320200122-4Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting126320200122-4Excavator - 36 ton- After Jan 105734.8Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1263 | 20200122-4 | 53510107 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning off execess snow and improving ditching and then mobilizing to Lofty Davies | 1 | A-055 to A-084 | Eldorado | 0 | 43886 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126320200122-4Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting126320200122-4Excavator - 36 ton- After Jan 105734.8Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1263 | 20200122-4 | 53510107 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning off execess snow and improving ditching and then mobilizing to Lofty Davies | 1 | A-055 to A-084 | Eldorado | 0 | 43886 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126320200122-4Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting126320200122-4Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1263 | 20200122-4 | 53510107 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning off execess snow and improving ditching and then mobilizing to Lofty Davies | 1 | A-055 to A-084 | Eldorado | 0 | 43886 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126320200122-4Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting126320200122-4Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1263 | 20200122-4 | 53510107 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning off execess snow and improving ditching and then mobilizing to Lofty Davies | 1 | A-055 to A-084 | Eldorado | 0 | 43886 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126320200122-4Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting126320200122-4Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1263 | 20200122-4 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 9.5 | Dynamic | 64.79 | 0 |  |  | 820.61 | 106.6793 | 927.2893 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning off execess snow and improving ditching and then mobilizing to Lofty Davies | 1 | A-055 to A-084 | Eldorado | 0 | 43886 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126320200122-4Sander Truck - Forestry- After Jan 109.5820.61 | Corbiere and Sons Contracting126320200122-4Sander Truck - Forestry- After Jan 109.5820.61Inv#007-R01 | [5 empty] | 1 | 820.61 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1263 | 20200122-4 | 53510107 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning off execess snow and improving ditching and then mobilizing to Lofty Davies | 1 | A-055 to A-084 | Eldorado | 0 | 43886 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126320200122-4L.O.A.4840 | Corbiere and Sons Contracting126320200122-4L.O.A.4840Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1263 | 20200122-4 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning off execess snow and improving ditching and then mobilizing to Lofty Davies | 1 | A-055 to A-084 | Eldorado | 0 | 43886 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126320200122-4L.O.A.1210 | Corbiere and Sons Contracting126320200122-4L.O.A.1210Inv#007-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1263 | 20200122-4 | 53510107 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 20 | HR |  |  | 75 | 0 | 1500 | 195 | 1695 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning off execess snow and improving ditching and then mobilizing to Lofty Davies | 1 | A-055 to A-084 | Eldorado | 0 | 43886 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126320200122-4Operator - Principle - After Jan 10201500 | Corbiere and Sons Contracting126320200122-4Operator - Principle - After Jan 10201500Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1263 | 20200122-4 | 53510111 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 9.5 | HR |  |  | 70 | 0 | 665 | 86.45 | 751.45 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning off execess snow and improving ditching and then mobilizing to Lofty Davies | 1 | A-055 to A-084 | Eldorado | 0 | 43886 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126320200122-4Driver - AZ - After Jan 109.5665 | Corbiere and Sons Contracting126320200122-4Driver - AZ - After Jan 109.5665Inv#007-R01 | [5 empty] | 1 | 665 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1264 | 20200122-5 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 16 | Dynamic | 95.24 | 0 |  |  | 2031.68 | 264.1184 | 2295.7984 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of Access Roads and Float Moves; | 1 | A-085 to A-117 | Windfarm | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126420200122-5Grader - Cat 12 to 14 or equal- After Jan 10162031.68 | Corbiere and Sons Contracting126420200122-5Grader - Cat 12 to 14 or equal- After Jan 10162031.68Inv#007-R01 | [5 empty] | 1 | 2031.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1264 | 20200122-5 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of Access Roads and Float Moves; | 1 | A-085 to A-117 | Windfarm | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126420200122-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting126420200122-5Light Truck - Pick up- After Jan 102487.5Inv#007-R01 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1264 | 20200122-5 | 53510111 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of Access Roads and Float Moves; | 1 | A-085 to A-117 | Windfarm | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126420200122-5L.O.A.4840 | Corbiere and Sons Contracting126420200122-5L.O.A.4840Inv#007-R01 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1264 | 20200122-5 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of Access Roads and Float Moves; | 1 | A-085 to A-117 | Windfarm | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126420200122-5Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting126420200122-5Operator - Principle - After Jan 10221650Inv#007-R01 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1264 | 20200122-5 | 53510111 | Access | 0 | Labourer - General - After Jan 10 | 60 | 22 | HR |  |  | 60 | 0 | 1320 | 171.6 | 1491.6 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of Access Roads and Float Moves; | 1 | A-085 to A-117 | Windfarm | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126420200122-5Labourer - General - After Jan 10221320 | Corbiere and Sons Contracting126420200122-5Labourer - General - After Jan 10221320Inv#007-R01 | [5 empty] | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1265 | 20200122-6 | 53520104 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; Grinding of Material from A085-A089; | 0 |  |  | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126520200122-6Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting126520200122-6Grinder - 4710 Peterson or equal95011.2Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1265 | 20200122-6 | 53520104 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; Grinding of Material from A085-A089; | 0 |  |  | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126520200122-6Log Loader91377 | Corbiere and Sons Contracting126520200122-6Log Loader91377Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1265 | 20200122-6 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 2 | unit/man/day | 0 | 0 |  |  | 120 | 15.6 | 135.6 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; Grinding of Material from A085-A089; | 0 |  |  | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126520200122-6Chainsaw and consumables- After Jan 102120 | Corbiere and Sons Contracting126520200122-6Chainsaw and consumables- After Jan 102120Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1265 | 20200122-6 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; Grinding of Material from A085-A089; | 0 |  |  | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126520200122-6Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting126520200122-6Light Truck - Pick up- After Jan 103731.25Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1265 | 20200122-6 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; Grinding of Material from A085-A089; | 0 |  |  | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126520200122-6Foreman121140 | Corbiere and Sons Contracting126520200122-6Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1265 | 20200122-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; Grinding of Material from A085-A089; | 0 |  |  | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126520200122-6L.O.A.1210 | Corbiere and Sons Contracting126520200122-6L.O.A.1210Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1265 | 20200122-6 | 53520104 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; Grinding of Material from A085-A089; | 0 |  |  | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126520200122-6L.O.A.3630 | Corbiere and Sons Contracting126520200122-6L.O.A.3630Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1265 | 20200122-6 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; Grinding of Material from A085-A089; | 0 |  |  | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126520200122-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting126520200122-6Operator - Principle - After Jan 1011825Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1265 | 20200122-6 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 22 | HR |  |  | 70 | 0 | 1540 | 200.2 | 1740.2 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; Grinding of Material from A085-A089; | 0 |  |  | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126520200122-6Labourer - Specialized - After Jan 10221540 | Corbiere and Sons Contracting126520200122-6Labourer - Specialized - After Jan 10221540Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1540 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1266 | 20200122-7 | 53510106 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building between A118 and A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126620200122-7Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting126620200122-7Excavator - 30 ton- After Jan 1091246.05Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1266 | 20200122-7 | 53510106 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 110.22 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building between A118 and A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126620200122-7Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting126620200122-7Excavator - 36 ton- After Jan 10182645.28Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 2645.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1266 | 20200122-7 | 53510106 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building between A118 and A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126620200122-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting126620200122-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1266 | 20200122-7 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building between A118 and A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126620200122-7Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting126620200122-7Light Truck - Pick up- After Jan 103731.25Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1266 | 20200122-7 | 53510106 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building between A118 and A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126620200122-7Foreman121140 | Corbiere and Sons Contracting126620200122-7Foreman121140Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1266 | 20200122-7 | 53510106 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building between A118 and A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126620200122-7L.O.A.61260 | Corbiere and Sons Contracting126620200122-7L.O.A.61260Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1266 | 20200122-7 | 53510106 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building between A118 and A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126620200122-7Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting126620200122-7Operator - Principle - After Jan 10332475Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1266 | 20200122-7 | 53510106 | Access | 0 | Labourer - General - After Jan 10 | 60 | 22 | HR |  |  | 60 | 0 | 1320 | 171.6 | 1491.6 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building between A118 and A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126620200122-7Labourer - General - After Jan 10221320 | Corbiere and Sons Contracting126620200122-7Labourer - General - After Jan 10221320Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1267 | 20200122-8 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A118 and A123; | 0 |  |  | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126720200122-8Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting126720200122-8Chainsaw and consumables- After Jan 103180Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1267 | 20200122-8 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A118 and A123; | 0 |  |  | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126720200122-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting126720200122-8Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1267 | 20200122-8 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A118 and A123; | 0 |  |  | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126720200122-8Foreman121140 | Corbiere and Sons Contracting126720200122-8Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1267 | 20200122-8 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A118 and A123; | 0 |  |  | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126720200122-8L.O.A.4840 | Corbiere and Sons Contracting126720200122-8L.O.A.4840Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1267 | 20200122-8 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 27.5 | HR |  |  | 70 | 0 | 1925 | 250.25 | 2175.25 | 2020-01-22 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A118 and A123; | 0 |  |  | 0 | 43855 |  | 36 | 43863 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting126720200122-8Labourer - Specialized - After Jan 1027.51925 | Corbiere and Sons Contracting126720200122-8Labourer - Specialized - After Jan 1027.51925Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1925 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.42148 | DAY | 182.81 | 0 |  |  | 102.7367 | 13.3558 | 116.0925 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Light Truck - Pick up- After Jan 100.4214841102.7367 | Corbiere and Sons Contracting129620200123-1Light Truck - Pick up- After Jan 100.4214841102.7367Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 102.7367 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.48708 | DAY | 182.81 | 0 |  |  | 118.7246 | 15.4342 | 134.1588 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Light Truck - Pick up- After Jan 100.4870753118.7246 | Corbiere and Sons Contracting129620200123-1Light Truck - Pick up- After Jan 100.4870753118.7246Inv#007-R01 | [5 empty] | 1 | 118.7246 |  | #N/A