KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7645 | KL-20211206-4 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2021-12-06 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F175 to F171 and from F185 to F193/ Grader working on High Falls Road and to F203 | 11 | F170-F211 | High Falls | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7645KL-20211206-4CAT D6 - LPG101790 | KABI LAKE FOREST PRODUCTS LTD7645KL-20211206-4CAT D6 - LPG101790OEWT-PA24-LEM | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7649 | KL-20211207-3 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2021-12-07 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F185 to F181 and from F198 to F208/ Grader working on High Falls Road, F200 and F195 access | 11 | F170-F211 | High Falls | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7649KL-20211207-3CAT D6 - LPG101790 | KABI LAKE FOREST PRODUCTS LTD7649KL-20211207-3CAT D6 - LPG101790OEWT-PA24-LEM | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7654 | KL-20211208-3 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F198 to F208 & support of stringing equipment. Grader working on High Falls Road, F170, F175, F176, F185 to F181 & F207 access. | 11 | F170-F211 | High Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7654KL-20211208-3CAT D6 - LPG101790 | KABI LAKE FOREST PRODUCTS LTD7654KL-20211208-3CAT D6 - LPG101790OEWT-PA24-LEM | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7664 | KL-20211209-7 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal @ F180, F172, F171, F173 & F208 to F211. Grader working on High Falls Road, F185 to F181 & access to F207 | 11 | F170-F211 | High Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7664KL-20211209-7CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7664KL-20211209-7CAT D6 - LPG91611OEWT-PA24-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7668 | KL-20211210-4 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 9.5 | HR | 135 | 0 |  |  | 1700.5 | 221.065 | 1921.565 | 2021-12-10 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal to F198, F202 & F2003 to F211. Grader working on High Falls road, F180, F194 to F197 & access to F207. | 11 | F170-F211 | High Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7668KL-20211210-4CAT D6 - LPG9.51700.5 | KABI LAKE FOREST PRODUCTS LTD7668KL-20211210-4CAT D6 - LPG9.51700.5OEWT-PA24-LEM | [5 empty] | 1 | 1700.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7684 | KL-20211212-4 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2021-12-12 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on High Falls Road to Km 13 and F200/ Dozer working from F206 to F211 | 11 | F170-F211 | High Falls | 0 | 44551 |  | 61 | 44561 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7684KL-20211212-4CAT D6 - LPG61074 | KABI LAKE FOREST PRODUCTS LTD7684KL-20211212-4CAT D6 - LPG61074OEWT-PA24-LEM | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7688 | KL-20211213-3 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2021-12-13 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Finish snow removal from F198 to F201 | 11 | F170-F211 | High Falls | 0 | 44551 |  | 61 | 44560 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7688KL-20211213-3CAT D6 - LPG4716 | KABI LAKE FOREST PRODUCTS LTD7688KL-20211213-3CAT D6 - LPG4716OEWT-PA24-LEM | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7691 | KL-20211214-3 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 7 | HR | 135 | 0 |  |  | 1253 | 162.89 | 1415.89 | 2021-12-14 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Scarifying hills and corners from Km 12 to Hwy 17/Dozer starting snow removal from Hensen road to F128 | 11 | F118-F127 | Henson | 0 | 44551 |  | 61 | 44560 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7691KL-20211214-3CAT D6 - LPG71253 | KABI LAKE FOREST PRODUCTS LTD7691KL-20211214-3CAT D6 - LPG71253OEWT-PA24-LEM | [5 empty] | 1 | 1253 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7697 | KL-20211215-4 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2021-12-15 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer finishing snow removal from Hensen road to F132 | 11 | F118-F127 | Henson | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7697KL-20211215-4CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7697KL-20211215-4CAT D6 - LPG91611OEWT-PA24-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7700 | KL-20211216-3 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2021-12-16 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F037 to F033 | 10 | F066-F118 | Paint Lake 2 | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7700KL-20211216-3CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7700KL-20211216-3CAT D6 - LPG91611OEWT-PA24-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7708 | KL-20211219-4 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2021-12-19 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hensen Road to F127 | 11 | F118-F127 | Henson | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7708KL-20211219-4CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7708KL-20211219-4CAT D6 - LPG91611OEWT-PA24-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7714 | KL-20211229-2 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2021-12-29 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hensen Road to F132 | 11 | F119-F127 | Henson | 0 |  |  | 61 | 44572 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7714KL-20211229-2CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7714KL-20211229-2CAT D6 - LPG91611OEWT-PA25-Lem | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7716 | KL-20211230-2 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2021-12-30 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal from Hensen Road to F132 for freezing | 11 | F119-F127 | Henson | 0 |  |  | 61 | 44572 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7716KL-20211230-2CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7716KL-20211230-2CAT D6 - LPG91611OEWT-PA25-Lem | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7717 | KL-20211231-1 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 6.5 | HR | 135 | 0 |  |  | 1163.5 | 151.255 | 1314.755 | 2021-12-31 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hensen Road to F132 | 11 | F119-F127 | Henson | 0 |  |  | 61 | 44572 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7717KL-20211231-1CAT D6 - LPG6.51163.5 | KABI LAKE FOREST PRODUCTS LTD7717KL-20211231-1CAT D6 - LPG6.51163.5OEWT-PA25-Lem | [5 empty] | 1 | 1163.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7720 | KL-20220102-1 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-01-02 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal, widening road and clearing pull offs from Hensen road to F132 for freezing | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7720KL-20220102-1CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7720KL-20220102-1CAT D6 - LPG91611OEWT-PA25-Lem | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7732 | KL-20220105-2 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-01-05 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hensen Road to F132 and assisting stringing crews/Excavatorcleaning up and setting up a face @Km 17 for sand access | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7732KL-20220105-2CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7732KL-20220105-2CAT D6 - LPG91611OEWT-PA25-Lem | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7738 | KL-20220106-3 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 4.5 | HR | 135 | 0 |  |  | 805.5 | 104.715 | 910.215 | 2022-01-06 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on filling water holes with snow, widening road and corners to F127 for stringing crews | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7738KL-20220106-3CAT D6 - LPG4.5805.5 | KABI LAKE FOREST PRODUCTS LTD7738KL-20220106-3CAT D6 - LPG4.5805.5OEWT-PA25-Lem | [5 empty] | 1 | 805.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7741 | KL-20220107-3 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 8.5 | HR | 135 | 0 |  |  | 1521.5 | 197.795 | 1719.295 | 2022-01-07 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road and corners to F132 for stringing crews | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7741KL-20220107-3CAT D6 - LPG8.51521.5 | KABI LAKE FOREST PRODUCTS LTD7741KL-20220107-3CAT D6 - LPG8.51521.5OEWT-PA25-Lem | [5 empty] | 1 | 1521.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7749 | KL-20220109-1 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2022-01-09 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working on snow removal from Km 17 on Hensen to Hwy 17 and clearing pull offs/Dozer pushing back snow banks from Km 17 to Km 1 on Hensen Road | 11 | F118-F127 | Henson | 0 | 44575 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7749KL-20220109-1CAT D6 - LPG101790 | KABI LAKE FOREST PRODUCTS LTD7749KL-20220109-1CAT D6 - LPG101790OEWT-PA25-Lem | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7752 | KL-20220110-2 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 9.5 | HR | 135 | 0 |  |  | 1700.5 | 221.065 | 1921.565 | 2022-01-10 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer pushing back snow banks and clearing pull offs from Km .5 to Km 17 on Hensen Road | 11 | F118-F127 | Henson | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7752KL-20220110-2CAT D6 - LPG9.51700.5 | KABI LAKE FOREST PRODUCTS LTD7752KL-20220110-2CAT D6 - LPG9.51700.5OEWT-PA25-Lem | [5 empty] | 1 | 1700.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7787 | KL-20220119-3 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-01-19 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road, clearing pull offs & spur roads from Hensen to F131. grader working on snow removal on Hensen to 17Km and Hensen East to F131. | 11 | F118-F127 | Henson | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7787KL-20220119-3CAT D6 - LPG91611 | KABI LAKE FOREST PRODUCTS LTD7787KL-20220119-3CAT D6 - LPG91611OEWT-PA25-Lem | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7792 | KL-20220120-5 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 8.5 | HR | 135 | 0 |  |  | 1521.5 | 197.795 | 1719.295 | 2022-01-20 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer tracking from 11 Km on High Falls road & Working on Snow Removal to F207. | 11 | F170 - F211 | High Falls | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7792KL-20220120-5CAT D6 - LPG8.51521.5 | KABI LAKE FOREST PRODUCTS LTD7792KL-20220120-5CAT D6 - LPG8.51521.5OEWT-PA25-Lem | [5 empty] | 1 | 1521.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7798 | KL-20220122-2 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 7.5 | HR | 135 | 0 |  |  | 1342.5 | 174.525 | 1517.025 | 2022-01-22 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer tracking from km 11 on High Falls Road and working on snow removal from High Falls Road to F207/track back to Km 11 | 11 | F170-F211 | High Falls | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7798KL-20220122-2CAT D6 - LPG7.51342.5 | KABI LAKE FOREST PRODUCTS LTD7798KL-20220122-2CAT D6 - LPG7.51342.5OEWT-PA25-Lem | [5 empty] | 1 | 1342.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7858 | KL-20220209-1 | 53511111 | Access | 0 | CAT D6 - LPG | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2022-02-09 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer finishing snow removal from F021 to F032 and clear pads @ F032 | 10 | F009-F065 | Paint Lake | 0 | 44604 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7858KL-20220209-1CAT D6 - LPG81432 | KABI LAKE FOREST PRODUCTS LTD7858KL-20220209-1CAT D6 - LPG81432OEWT-PA26-LEM | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6140 | KL-20210222-14 | 53511111 | Access | 0 | CAT D5 | 138 | 8.5 | HR | 104 | 0 |  |  | 1173 | 152.49 | 1325.49 | 2021-02-22 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer clearing roads km20 to km15, loader clearing km 0 to 5 Hensen West. | 11 | F119-F134 | Hensen Road | 0 | 44269 |  | 56 | 44270 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6140KL-20210222-14CAT D58.51173 | KABI LAKE FOREST PRODUCTS LTD6140KL-20210222-14CAT D58.51173OEWT PA15-LEM | [5 empty] | 1 | 1173 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1322 | KL-20200317-7 | 53510812 | Access | 0 | CAT 962 | 172 | 7 | HR | 129 | 0 |  |  | 1204 | 156.52 | 1360.52 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | RV-40002 SPREAD GRAVEL; HAUL GRAVEL IN SOFT SOPT ACROSS HONI LINE AND TO GAIN ACCESS OVER ROCK IN EXISTING ENTRANCE RD | 8 | E-077 to E-091 | Blue Cedar W | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7CAT 96271204 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7CAT 96271204OEWT-PA3-LEM | [5 empty] | 1 | 1204 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6900 | KL-20210510-3 | 53510812 | Access | 0 | CAT 962 | 172 | 3.5 | HR | 129 | 0 |  |  | 602 | 78.26 | 680.26 | 2021-05-10 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 962M loader repairing washout @Blue Cedar entrance/Labourer escorting loader on Hwy 17 from Kabi Yard and back | 8 | E077-E091 | Blue Cedar | 0 | 44337 |  | 56 | 44341 | [5 empty] | Mandy Sandhu | 08 | KABI LAKE FOREST PRODUCTS LTD6900KL-20210510-3CAT 9623.5602 | KABI LAKE FOREST PRODUCTS LTD6900KL-20210510-3CAT 9623.5602OEWT-PA17-LEM | [5 empty] | 1 | 602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7899 | KL-20220217-4 | 53510911 | Access | 0 | CAT 962 | 172 | 8.5 | HR | 129 | 0 |  |  | 1462 | 190.06 | 1652.06 | 2022-02-17 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from Km 9 to Km 25 on 600 Road | 9 | E092-F009 | 600 Road | 0 | 44614 |  | 61 | 44614 | [6 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD7899KL-20220217-4CAT 9628.51462 | KABI LAKE FOREST PRODUCTS LTD7899KL-20220217-4CAT 9628.51462OEWT-PA26-LEM | [5 empty] | 1 | 1462 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7924 | KL-20220224-5 | 53510911 | Access | 0 | CAT 962 | 172 | 2 | HR | 129 | 0 |  |  | 344 | 44.72 | 388.72 | 2022-02-24 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader Starting Working Snow Removal From 9 Km To 12 Km On 600 Road | 9 | E092-F009 | 600 Road | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 09 | KABI LAKE FOREST PRODUCTS LTD7924KL-20220224-5CAT 9622344 | KABI LAKE FOREST PRODUCTS LTD7924KL-20220224-5CAT 9622344OEWT-PA26-LEM | [5 empty] | 1 | 344 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7927 | KL-20220225-3 | 53510911 | Access | 0 | CAT 962 | 172 | 11.5 | HR | 129 | 0 |  |  | 1978 | 257.14 | 2235.14 | 2022-02-25 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader and dozer finishing snow removal fro 9km to E-182 on 600 Road | 9 | E092-F009 | 600 Raod | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 09 | KABI LAKE FOREST PRODUCTS LTD7927KL-20220225-3CAT 96211.51978 | KABI LAKE FOREST PRODUCTS LTD7927KL-20220225-3CAT 96211.51978OEWT-PA26-LEM | [5 empty] | 1 | 1978 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7964 | KL-20220303-3 | 53510911 | Access | 0 | CAT 962 | 172 | 2.5 | HR | 129 | 0 |  |  | 430 | 55.9 | 485.9 | 2022-03-03 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Run Cat 962M Loader From Kabi Yard & Start Snow Removal To E193 On 600 Road | 9 | E092-F009 | 600 Road | 0 | 44630 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD7964KL-20220303-3CAT 9622.5430 | KABI LAKE FOREST PRODUCTS LTD7964KL-20220303-3CAT 9622.5430 | [5 empty] | 1 | 430 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7968 | KL-20220304-3 | 53510911 | Access | 0 | CAT 962 | 172 | 11.5 | HR | 129 | 0 |  |  | 1978 | 257.14 | 2235.14 | 2022-03-04 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader Finishing Snow Removal To E193 On 600 Road & Run Loader Back To Kabi Yard | 9 | E092-F009 | 600 Road | 0 | 44630 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD7968KL-20220304-3CAT 96211.51978 | KABI LAKE FOREST PRODUCTS LTD7968KL-20220304-3CAT 96211.51978 | [5 empty] | 1 | 1978 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5684 | KL-20210129-2 | 53511011 | Access | 0 | CAT 962 | 172 | 6 | HR | 129 | 0 |  |  | 1032 | 134.16 | 1166.16 | 2021-01-29 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow, haul gravel and corduroy, sand, skid corduroy. CDSL laying corduroy. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44234 |  | 50 | 44236 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5684KL-20210129-2CAT 96261032 | KABI LAKE FOREST PRODUCTS LTD5684KL-20210129-2CAT 96261032OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1032 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5678 | KL-20210130-15 | 53511011 | Access | 0 | CAT 962 | 172 | 6 | HR | 129 | 0 |  |  | 1032 | 134.16 | 1166.16 | 2021-01-30 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow, haul gravel and corduroy, Sand roads. Drag in and unload bridge WC 11333.00 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44231 |  | 50 | 44232 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5678KL-20210130-15CAT 96261032 | KABI LAKE FOREST PRODUCTS LTD5678KL-20210130-15CAT 96261032OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1032 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7737 | KL-20220106-2 | 53511011 | Access | 0 | CAT 962 | 172 | 7.5 | HR | 129 | 0 |  |  | 1290 | 167.7 | 1457.7 | 2022-01-06 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Working on Snow Removal and Widening road from Km 46 to F111/ Loader working on snow removal from F037 to F033 and sanding km 10.5 Hill | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7737KL-20220106-2CAT 9627.51290 | KABI LAKE FOREST PRODUCTS LTD7737KL-20220106-2CAT 9627.51290OEWT-PA25-Lem | [5 empty] | 1 | 1290 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7740 | KL-20220107-2 | 53511011 | Access | 0 | CAT 962 | 172 | 9 | HR | 129 | 0 |  |  | 1548 | 201.24 | 1749.24 | 2022-01-07 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working from Km 12 to Km 49 clearing pull offs and scraping hills from km 34 to km 41 | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7740KL-20220107-2CAT 96291548 | KABI LAKE FOREST PRODUCTS LTD7740KL-20220107-2CAT 96291548OEWT-PA25-Lem | [5 empty] | 1 | 1548 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7751 | KL-20220110-1 | 53511011 | Access | 0 | CAT 962 | 172 | 9 | HR | 129 | 0 |  |  | 1548 | 201.24 | 1749.24 | 2022-01-10 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working on snow removal from Km 49 to Km 36 and clearing pull offs | 10 | F066-F118 | Paint Lake 2 | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7751KL-20220110-1CAT 96291548 | KABI LAKE FOREST PRODUCTS LTD7751KL-20220110-1CAT 96291548OEWT-PA25-Lem | [5 empty] | 1 | 1548 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7776 | KL-20220116-1 | 53511011 | Access | 0 | CAT 962 | 172 | 3 | HR | 129 | 0 |  |  | 516 | 67.08 | 583.08 | 2022-01-16 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continue working on widening roads from Km 33 to Km 42 /Loader Clearing pull offs / Grader Scarifying from Km 49 to Km 42 | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7776KL-20220116-1CAT 9623516 | KABI LAKE FOREST PRODUCTS LTD7776KL-20220116-1CAT 9623516OEWT-PA25-Lem | [5 empty] | 1 | 516 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7816 | KL-20220130-1 | 53511011 | Access | 0 | CAT 962 | 172 | 7 | HR | 129 | 0 |  |  | 1204 | 156.52 | 1360.52 | 2022-01-30 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 49 to Km 36 for stringing crews equipment move /Dozer working from Km 35 to Km 32 widening road , clearing pull offs and spur | 10 | F066-F118 | Paint Lake 2 | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7816KL-20220130-1CAT 96271204 | KABI LAKE FOREST PRODUCTS LTD7816KL-20220130-1CAT 96271204OEWT-PA26-LEM | [5 empty] | 1 | 1204 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5207 | KL-20210103-5 | 53511111 | Access | 0 | CAT 962 | 172 | 1.5 | HR | 129 | 0 |  |  | 258 | 33.54 | 291.54 | 2021-01-03 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load of sand from White River town pit/ sanding hills and corners on hensen road from hwy to 17km with existing material as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5207KL-20210103-5CAT 9621.5258 | KABI LAKE FOREST PRODUCTS LTD5207KL-20210103-5CAT 9621.5258OEWT-PA13-LEM | [5 empty] | 1 | 258 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5363 | KL-20210114-9 | 53511111 | Access | 0 | CAT 962 | 172 | 2 | HR | 129 | 0 |  |  | 344 | 44.72 | 388.72 | 2021-01-14 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load screened sand from town pit and finished sanding Hensen Road to 17km with existing sand as per Valard/ Excavator cleaning up @ F119 for Sand | 11 | F119-F134 | Hensen Road | 0 | 44218 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5363KL-20210114-9CAT 9622344 | KABI LAKE FOREST PRODUCTS LTD5363KL-20210114-9CAT 9622344OEWT-PA13-LEM | [5 empty] | 1 | 344 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7745 | KL-20220108-2 | 53511111 | Access | 0 | CAT 962 | 172 | 9 | HR | 129 | 0 |  |  | 1548 | 201.24 | 1749.24 | 2022-01-08 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working from Hensen Road to F131, dragging road with blast mat, scraping hills and assisting stringers hauling in material | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7745KL-20220108-2CAT 96291548 | KABI LAKE FOREST PRODUCTS LTD7745KL-20220108-2CAT 96291548OEWT-PA25-Lem | [5 empty] | 1 | 1548 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7749 | KL-20220109-1 | 53511111 | Access | 0 | CAT 962 | 172 | 9 | HR | 129 | 0 |  |  | 1548 | 201.24 | 1749.24 | 2022-01-09 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working on snow removal from Km 17 on Hensen to Hwy 17 and clearing pull offs/Dozer pushing back snow banks from Km 17 to Km 1 on Hensen Road | 11 | F118-F127 | Henson | 0 | 44575 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7749KL-20220109-1CAT 96291548 | KABI LAKE FOREST PRODUCTS LTD7749KL-20220109-1CAT 96291548OEWT-PA25-Lem | [5 empty] | 1 | 1548 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7756 | KL-20220111-2 | 53511111 | Access | 0 | CAT 962 | 172 | 8.5 | HR | 129 | 0 |  |  | 1462 | 190.06 | 1652.06 | 2022-01-11 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader dragging road with blast mat, scraping hills and filling in rough areas | 11 | F118-F127 | Henson | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7756KL-20220111-2CAT 9628.51462 | KABI LAKE FOREST PRODUCTS LTD7756KL-20220111-2CAT 9628.51462OEWT-PA25-Lem | [5 empty] | 1 | 1462 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7760 | KL-20220112-3 | 53511111 | Access | 0 | CAT 962 | 172 | 5 | HR | 129 | 0 |  |  | 860 | 111.8 | 971.8 | 2022-01-12 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader scraping hills, clearing spur roads and sanding Hills to F127 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7760KL-20220112-3CAT 9625860 | KABI LAKE FOREST PRODUCTS LTD7760KL-20220112-3CAT 9625860OEWT-PA25-Lem | [5 empty] | 1 | 860 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7765 | KL-20220113-3 | 53511111 | Access | 0 | CAT 962 | 172 | 7 | HR | 129 | 0 |  |  | 1204 | 156.52 | 1360.52 | 2022-01-13 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding and dragging blast mat to F132 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7765KL-20220113-3CAT 96271204 | KABI LAKE FOREST PRODUCTS LTD7765KL-20220113-3CAT 96271204OEWT-PA25-Lem | [5 empty] | 1 | 1204 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7771 | KL-20220114-4 | 53511111 | Access | 0 | CAT 962 | 172 | 9 | HR | 129 | 0 |  |  | 1548 | 201.24 | 1749.24 | 2022-01-14 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader finishing sanding and dragging blast mat from Hensen Road to F132 for stringing crews and start sanding Hensen Road with existing material from Km 10.5 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7771KL-20220114-4CAT 96291548 | KABI LAKE FOREST PRODUCTS LTD7771KL-20220114-4CAT 96291548OEWT-PA25-Lem | [5 empty] | 1 | 1548 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7775 | KL-20220115-4 | 53511111 | Access | 0 | CAT 962 | 172 | 8.5 | HR | 129 | 0 |  |  | 1462 | 190.06 | 1652.06 | 2022-01-15 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding hills on Hensen Road with existing material from Km 10.5 / Grader scarifying and benching snow banks on Hensen road from Km .5 to Km 17 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7775KL-20220115-4CAT 9628.51462 | KABI LAKE FOREST PRODUCTS LTD7775KL-20220115-4CAT 9628.51462OEWT-PA25-Lem | [5 empty] | 1 | 1462 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7778 | KL-20220116-3 | 53511111 | Access | 0 | CAT 962 | 172 | 6 | HR | 129 | 0 |  |  | 1032 | 134.16 | 1166.16 | 2022-01-16 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader clearing pull offs and sanding in Hensen East / Grader working on snow removal on Hensen road from Km .5 to Km 17 and Hensen East to F132 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7778KL-20220116-3CAT 96261032 | KABI LAKE FOREST PRODUCTS LTD7778KL-20220116-3CAT 96261032OEWT-PA25-Lem | [5 empty] | 1 | 1032 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7781 | KL-20220117-3 | 53511111 | Access | 0 | CAT 962 | 172 | 4.5 | HR | 129 | 0 |  |  | 774 | 100.62 | 874.62 | 2022-01-17 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding in Hensen East / Grader working on snow removal on Hensen road from Km .5 to Km 17 and Hensen East to F132 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7781KL-20220117-3CAT 9624.5774 | KABI LAKE FOREST PRODUCTS LTD7781KL-20220117-3CAT 9624.5774OEWT-PA25-Lem | [5 empty] | 1 | 774 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7784 | KL-20220118-3 | 53511111 | Access | 0 | CAT 962 | 172 | 8 | HR | 129 | 0 |  |  | 1376 | 178.88 | 1554.88 | 2022-01-18 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding in Hensen East & driving out to 0.5Km for float. Grader working on benching & pushing back on Hensen road to 15Km. | 11 | F118-F127 | Henson | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7784KL-20220118-3CAT 96281376 | KABI LAKE FOREST PRODUCTS LTD7784KL-20220118-3CAT 96281376OEWT-PA25-Lem | [5 empty] | 1 | 1376 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7948 | KL-20220228-5 | 53511111 | Access | 0 | CAT 962 | 172 | 6.5 | HR | 129 | 0 |  |  | 1118 | 145.34 | 1263.34 | 2022-02-28 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loaders Working On Snow Removal From F184 To F181 & Starting @ F175 To F171. Access/Winter Access Maintenance (Cost Code: 67776007556.591100.57010107) | 11 | F170 - F211 | High Falls | 1 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7948KL-20220228-5CAT 9626.51118 | KABI LAKE FOREST PRODUCTS LTD7948KL-20220228-5CAT 9626.51118 | [5 empty] | 1 | 1118 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7956 | KL-20220301-3 | 53511111 | Access | 0 | CAT 962 | 172 | 5 | HR | 129 | 0 |  |  | 860 | 111.8 | 971.8 | 2022-03-01 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loaders finishing on snow removal from F175 to F171 Cost Code: 67776007556.591100.57010107 ) | 11 | F170 - F211 | High Falls | 1 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7956KL-20220301-3CAT 9625860 | KABI LAKE FOREST PRODUCTS LTD7956KL-20220301-3CAT 9625860 | [5 empty] | 1 | 860 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7962 | KL-20220302-7 | 53511111 | Access | 0 | CAT 962 | 172 | 6.5 | HR | 129 | 0 |  |  | 1118 | 145.34 | 1263.34 | 2022-03-02 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader working on snow removal from Anjigami to F228 | 11 | F212-F235 | Anjigame | 0 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7962KL-20220302-7CAT 9626.51118 | KABI LAKE FOREST PRODUCTS LTD7962KL-20220302-7CAT 9626.51118 | [5 empty] | 1 | 1118 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7972 | KL-20220307-2 | 53511111 | Access | 0 | CAT 962 | 172 | 8.5 | HR | 129 | 0 |  |  | 1462 | 190.06 | 1652.06 | 2022-03-07 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader Working On Snow Removal From Anjigami Road To F228 & F235 To F233 | 11 | F212-F235 | Anjigame | 0 | 44634 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7972KL-20220307-2CAT 9628.51462 | KABI LAKE FOREST PRODUCTS LTD7972KL-20220307-2CAT 9628.51462 | [5 empty] | 1 | 1462 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7786 | KL-20220119-2 | 53511111 | Access | 0 | CAT 962 | 172 | 9 | HR | 129 | 0 |  |  | 1548 | 201.24 | 1749.24 | 2022-01-19 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working on snow removal from F231 to F235 & clearing pads. | 11 | F212-F235 | Anjigame | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7786KL-20220119-2CAT 96291548 | KABI LAKE FOREST PRODUCTS LTD7786KL-20220119-2CAT 96291548OEWT-PA25-Lem | [5 empty] | 1 | 1548 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7789 | KL-20220120-2 | 53511111 | Access | 0 | CAT 962 | 172 | 7.5 | HR | 129 | 0 |  |  | 1290 | 167.7 | 1457.7 | 2022-01-20 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader finishing snow removal from F231 to F235 & clearing pads. Start snow removal from F231 to F226. | 11 | F212-F235 | Anjigame | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7789KL-20220120-2CAT 9627.51290 | KABI LAKE FOREST PRODUCTS LTD7789KL-20220120-2CAT 9627.51290OEWT-PA25-Lem | [5 empty] | 1 | 1290 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7796 | KL-20220121-4 | 53511111 | Access | 0 | CAT 962 | 172 | 9 | HR | 129 | 0 |  |  | 1548 | 201.24 | 1749.24 | 2022-01-21 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader snow removal from F231 to F226 and F232 to F235 | 11 | F212-F235 | Anjigame | 0 | 44589 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7796KL-20220121-4CAT 96291548 | KABI LAKE FOREST PRODUCTS LTD7796KL-20220121-4CAT 96291548OEWT-PA25-Lem | [5 empty] | 1 | 1548 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7797 | KL-20220122-1 | 53511111 | Access | 0 | CAT 962 | 172 | 9.5 | HR | 129 | 0 |  |  | 1634 | 212.42 | 1846.42 | 2022-01-22 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on Hensen Road to Km 17 and Hensen East to F132(plowed Hensen Road 3 times due to winter storm) /Loader clearing pulloffs and widening corners to Km 12 | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7797KL-20220122-1CAT 9629.51634 | KABI LAKE FOREST PRODUCTS LTD7797KL-20220122-1CAT 9629.51634OEWT-PA25-Lem | [5 empty] | 1 | 1634 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7800 | KL-20220123-2 | 53511111 | Access | 0 | CAT 962 | 172 | 9 | HR | 129 | 0 |  |  | 1548 | 201.24 | 1749.24 | 2022-01-23 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on Hensen Road to F121 and Hensen East to F132/Loader clearing pulloffs and widening corners | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7800KL-20220123-2CAT 96291548 | KABI LAKE FOREST PRODUCTS LTD7800KL-20220123-2CAT 96291548OEWT-PA25-Lem | [5 empty] | 1 | 1548 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7802 | KL-20220124-2 | 53511111 | Access | 0 | CAT 962 | 172 | 4 | HR | 129 | 0 |  |  | 688 | 89.44 | 777.44 | 2022-01-24 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working benching snowbanks and widening road from Hwy 17 to Km 10/ Loader continuing clearing pulloffs and widening corners | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7802KL-20220124-2CAT 9624688 | KABI LAKE FOREST PRODUCTS LTD7802KL-20220124-2CAT 9624688OEWT-PA25-Lem | [5 empty] | 1 | 688 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7804 | KL-20220124-4 | 53511111 | Access | 0 | CAT 962 | 172 | 4.5 | HR | 129 | 0 |  |  | 774 | 100.62 | 874.62 | 2022-01-24 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from Anjigami Road to F231 and clearing pads in support of stringing crew | 11 |  | Anjigame | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7804KL-20220124-4CAT 9624.5774 | KABI LAKE FOREST PRODUCTS LTD7804KL-20220124-4CAT 9624.5774OEWT-PA25-Lem | [5 empty] | 1 | 774 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7808 | KL-20220125-4 | 53511111 | Access | 0 | CAT 962 | 172 | 3.5 | HR | 129 | 0 |  |  | 602 | 78.26 | 680.26 | 2022-01-25 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal and Heli Pads in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7808KL-20220125-4CAT 9623.5602 | KABI LAKE FOREST PRODUCTS LTD7808KL-20220125-4CAT 9623.5602OEWT-PA25-Lem | [5 empty] | 1 | 602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7811 | KL-20220126-3 | 53511111 | Access | 0 | CAT 962 | 172 | 9 | HR | 129 | 0 |  |  | 1548 | 201.24 | 1749.24 | 2022-01-26 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader continuing working snow removal and Heli Pads in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7811KL-20220126-3CAT 96291548 | KABI LAKE FOREST PRODUCTS LTD7811KL-20220126-3CAT 96291548OEWT-PA26-LEM | [5 empty] | 1 | 1548 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7813 | KL-20220128-2 | 53511111 | Access | 0 | CAT 962 | 172 | 9.5 | HR | 129 | 0 |  |  | 1634 | 212.42 | 1846.42 | 2022-01-28 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from F235 to F230 and Pads in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7813KL-20220128-2CAT 9629.51634 | KABI LAKE FOREST PRODUCTS LTD7813KL-20220128-2CAT 9629.51634OEWT-PA26-LEM | [5 empty] | 1 | 1634 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1410 | KL-20200329-4 | 53510711 | Access | 0 | CAT 950 | 153 | 4 | HR | 115 | 0 |  |  | 612 | 79.56 | 691.56 | 2020-03-29 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Drag Road Black River East Main Access to D-051 | 7 | D-032 to D-055 | Black River | 0 | 43927 |  | 45 | 43924 | [5 empty] | Howard Beaudet | 07 | KABI LAKE FOREST PRODUCTS LTD1410KL-20200329-4CAT 9504612 | KABI LAKE FOREST PRODUCTS LTD1410KL-20200329-4CAT 9504612OEWT PA4-LEM-R1 | [5 empty] | 1 | 612 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1445 | KL-20200402-6 | 53510711 | Access | 0 | CAT 950 | 153 | 4 | HR | 115 | 0 |  |  | 612 | 79.56 | 691.56 | 2020-04-02 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Remove and demob pusher for haul trucks on log haul | 7 | D-032 to D-055 | Black River | 0 | 43930 |  | 43 | 43933 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1445KL-20200402-6CAT 9504612 | KABI LAKE FOREST PRODUCTS LTD1445KL-20200402-6CAT 9504612OEWT PA4-LEM-R1 | [5 empty] | 1 | 612 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7268 | KL-20210823-2 | 53510812 | Access | 0 | CAT 950 | 153 | 1 | HR | 115 | 0 |  |  | 153 | 19.89 | 172.89 | 2021-08-23 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair & shape road from 9049.00 WC to E-017. Loader loading rig mats on float for return to Valard Marathon yard | 8 | E017-E024 | North Regan | 0 | 44438 |  | 50 | 44440 | [5 empty] | Jim Budgell | 08 | KABI LAKE FOREST PRODUCTS LTD7268KL-20210823-2CAT 9501153 | KABI LAKE FOREST PRODUCTS LTD7268KL-20210823-2CAT 9501153OEWT-PA20-Lem | [5 empty] | 1 | 153 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5413 | KL-20210117-1 | 53510911 | Access | 0 | CAT 950 | 153 | 1 | HR | 115 | 0 |  |  | 153 | 19.89 | 172.89 | 2021-01-17 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding hills on 600 Road between km 52 and Km 22, float truck was stuck on 47km hill | 9 | E091-E102 | 600 Road | 0 | 44216 |  | 53 | 44229 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5413KL-20210117-1CAT 9501153 | KABI LAKE FOREST PRODUCTS LTD5413KL-20210117-1CAT 9501153OEWT-PA13-LEM | [5 empty] | 1 | 153 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5842 | KL-20210210-4 | 53511011 | Access | 0 | CAT 950 | 153 | 11 | HR | 115 | 0 |  |  | 1683 | 218.79 | 1901.79 | 2021-02-10 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul gravel, pull bridges and legos in, plow and sand roads. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44244 |  | 50 | 44249 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5842KL-20210210-4CAT 950111683 | KABI LAKE FOREST PRODUCTS LTD5842KL-20210210-4CAT 950111683OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1683 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5976 | KL-20210220-3 | 53511011 | Access | 0 | CAT 950 | 153 | 10 | HR | 115 | 0 |  |  | 1530 | 198.9 | 1728.9 | 2021-02-20 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Paint Lake 2 Road, Plow snow on access road. Corduroy F62-F63 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44252 |  | 57 | 44252 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD5976KL-20210220-3CAT 950101530 | KABI LAKE FOREST PRODUCTS LTD5976KL-20210220-3CAT 950101530OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1530 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5990 | KL-20210221-8 | 53511011 | Access | 0 | CAT 950 | 153 | 9 | HR | 115 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2021-02-21 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Paint Lake 2 Rd, plow snow on access rd, haul geo from km 9 to km 23, skid corduroy | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44252 |  | 57 | 44255 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD5990KL-20210221-8CAT 95091377 | KABI LAKE FOREST PRODUCTS LTD5990KL-20210221-8CAT 95091377OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1377 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5997 | KL-20210222-3 | 53511011 | Access | 0 | CAT 950 | 153 | 11 | HR | 115 | 0 |  |  | 1683 | 218.79 | 1901.79 | 2021-02-22 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, skid corduroy, haul rig mats to snow crossing, work on snow crossing, place mats, track buncher to snow crossing, haul gravel. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44254 | . | 57 | 44255 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD5997KL-20210222-3CAT 950111683 | KABI LAKE FOREST PRODUCTS LTD5997KL-20210222-3CAT 950111683OEWT PA15-LEM | [5 empty] | 1 | 1683 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6017 | KL-20210223-10 | 53511011 | Access | 0 | CAT 950 | 153 | 10 | HR | 115 | 0 |  |  | 1530 | 198.9 | 1728.9 | 2021-02-23 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, work on snow crossing, haul and place rig mats, load and haul gravel. Haul and spread gravel, roll out geo, hammer access road to F60 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44253 |  | 57 | 44257 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD6017KL-20210223-10CAT 950101530 | KABI LAKE FOREST PRODUCTS LTD6017KL-20210223-10CAT 950101530OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1530 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6021 | KL-20210224-1 | 53511011 | Access | 0 | CAT 950 | 153 | 10 | HR | 115 | 0 |  |  | 1530 | 198.9 | 1728.9 | 2021-02-24 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, load and haul gravel. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44256 |  | 57 | 44259 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD6021KL-20210224-1CAT 950101530 | KABI LAKE FOREST PRODUCTS LTD6021KL-20210224-1CAT 950101530OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1530 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6044 | KL-20210225-12-R1 | 53511011 | Access | 0 | CAT 950 | 153 | 9 | HR | 115 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2021-02-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, load and haul gravel, move bridge, and sand road. WC 12000.00 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44256 |  | 56 | 44259 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6044KL-20210225-12-R1CAT 95091377 | KABI LAKE FOREST PRODUCTS LTD6044KL-20210225-12-R1CAT 95091377OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1377 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6101 | KL-20210226-11 | 53511011 | Access | 0 | CAT 950 | 153 | 10 | HR | 115 | 0 |  |  | 1530 | 198.9 | 1728.9 | 2021-02-26 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow, load and haul gravel, sand rd, unload and move legos, skid and place corduroy,Buncher was cutting wood and tracking wood to place on road | 10 | F-033 to F-118 | Paint Lake Road 2 | 0 | 44262 |  | 57 | 44277 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD6101KL-20210226-11CAT 950101530 | KABI LAKE FOREST PRODUCTS LTD6101KL-20210226-11CAT 950101530OEWT PA15-LEM | [5 empty] | 1 | 1530 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6109 | KL-20210227-7 | 53511011 | Access | 0 | CAT 950 | 153 | 9 | HR | 115 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2021-02-27 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, load and haul gravel, sand road. Skid corduroy, move mats, place corduroy. | 10 | F-033 to F-118 | Paint Lake Road 2 | 0 | 44262 |  | 57 | 44266 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD6109KL-20210227-7CAT 95091377 | KABI LAKE FOREST PRODUCTS LTD6109KL-20210227-7CAT 95091377OEWT-PA16-Lem | [5 empty] | 1 | 1377 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6129 | KL-20210301-5 | 53511011 | Access | 0 | CAT 950 | 153 | 6 | HR | 115 | 0 |  |  | 918 | 119.34 | 1037.34 | 2021-03-01 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, load and haul gravel, sand road, skid corduroy, placing corduroy, cut bundles in half | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44263 |  | 57 | 44266 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD6129KL-20210301-5CAT 9506918 | KABI LAKE FOREST PRODUCTS LTD6129KL-20210301-5CAT 9506918OEWT PA15-LEM | [5 empty] | 1 | 918 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5829 | KL-20210209-6 | 53511011 | Access | 0 | CAT 950 | 153 | 5 | HR | 115 | 0 |  |  | 765 | 99.45 | 864.45 | 2021-02-09 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul gravel, pull bridges and legos in, plow and sand roads. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44243 |  | 50 | 44249 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5829KL-20210209-6CAT 9505765 | KABI LAKE FOREST PRODUCTS LTD5829KL-20210209-6CAT 9505765OEWT-PA14-Lem-R1 | [5 empty] | 1 | 765 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6290 | KL-20210310-3 | 53511011 | Access | 0 | CAT 950 | 153 | 5 | HR | 115 | 0 |  |  | 765 | 99.45 | 864.45 | 2021-03-10 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying Paint Lake 2 Rd/Loader pushing out snow banks in low areas for drainage. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44278 |  | 56 | 44280 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6290KL-20210310-3CAT 9505765 | KABI LAKE FOREST PRODUCTS LTD6290KL-20210310-3CAT 9505765OEWT PA15-LEM | [5 empty] | 1 | 765 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7620 | KL-20211202-2 | 53511011 | Access | 0 | CAT 950 | 153 | 4 | HR | 115 | 0 |  |  | 612 | 79.56 | 691.56 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Km 49 to Km 40/ loader sanding road from Km 48 to Km 46.5 with existing material | 10 | F066-F118 | Paint Lake 2 | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7620KL-20211202-2CAT 9504612 | KABI LAKE FOREST PRODUCTS LTD7620KL-20211202-2CAT 9504612OEWT-PA24-LEM | [5 empty] | 1 | 612 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7628 | KL-20211203-2 | 53511011 | Access | 0 | CAT 950 | 153 | 9.5 | HR | 115 | 0 |  |  | 1453.5 | 188.955 | 1642.455 | 2021-12-03 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding and scraping road from Km 46.5 to Km 38 with existing material | 10 | F066-F118 | Paint Lake 2 | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7628KL-20211203-2CAT 9509.51453.5 | KABI LAKE FOREST PRODUCTS LTD7628KL-20211203-2CAT 9509.51453.5OEWT-PA24-LEM | [5 empty] | 1 | 1453.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7637 | KL-20211204-5 | 53511011 | Access | 0 | CAT 950 | 153 | 9 | HR | 115 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2021-12-04 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding and scraping road from Km 46 to Km 38 with existing material /dozer working from Km 49 to Km 13/ supervisior picking up dozer operator @ Km 13 at end of shift | 10 | F066-F118 | Paint Lake 2 | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7637KL-20211204-5CAT 95091377 | KABI LAKE FOREST PRODUCTS LTD7637KL-20211204-5CAT 95091377OEWT-PA24-LEM | [5 empty] | 1 | 1377 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7639 | KL-20211205-2 | 53511011 | Access | 0 | CAT 950 | 153 | 9 | HR | 115 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2021-12-05 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader piling existing material from Km 46 to Km 38 for upcoming snow fall/ dozer working on snow removal from km 13 to km 21 | 10 | F066-F118 | Paint Lake 2 | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7639KL-20211205-2CAT 95091377 | KABI LAKE FOREST PRODUCTS LTD7639KL-20211205-2CAT 95091377OEWT-PA24-LEM | [5 empty] | 1 | 1377 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7643 | KL-20211206-2 | 53511011 | Access | 0 | CAT 950 | 153 | 9 | HR | 115 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2021-12-06 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working on snow removal and sanding from Km 49 to Km 35 | 10 | F066-F118 | Paint Lake 2 | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7643KL-20211206-2CAT 95091377 | KABI LAKE FOREST PRODUCTS LTD7643KL-20211206-2CAT 95091377OEWT-PA24-LEM | [5 empty] | 1 | 1377 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7647 | KL-20211207-1 | 53511011 | Access | 0 | CAT 950 | 153 | 9 | HR | 115 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2021-12-07 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding from Km 48 to Km 40 | 10 | F066-F118 | Paint Lake 2 | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7647KL-20211207-1CAT 95091377 | KABI LAKE FOREST PRODUCTS LTD7647KL-20211207-1CAT 95091377OEWT-PA24-LEM | [5 empty] | 1 | 1377 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7652 | KL-20211208-1 | 53511011 | Access | 0 | CAT 950 | 153 | 6.5 | HR | 115 | 0 |  |  | 994.5 | 129.285 | 1123.785 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding from Km 48 to Km 45. Dozer working from 13km to 18km. Sand truck sanding from 0km to 12km in support of Valard Fuel Tank Demob. Excavator loading existing material. Skagen grader on PLR 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-1CAT 9506.5994.5 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-1CAT 9506.5994.5OEWT-PA24-LEM | [5 empty] | 1 | 994.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7657 | KL-20211209-1 | 53511011 | Access | 0 | CAT 950 | 153 | 9 | HR | 115 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working from 48km to 34km sanding & clearing pull offs. Dozer working to F057, F058 & F058 access. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7657KL-20211209-1CAT 95091377 | KABI LAKE FOREST PRODUCTS LTD7657KL-20211209-1CAT 95091377OEWT-PA24-LEM | [5 empty] | 1 | 1377 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7665 | KL-20211210-1 | 53511011 | Access | 0 | CAT 950 | 153 | 10.5 | HR | 115 | 0 |  |  | 1606.5 | 208.845 | 1815.345 | 2021-12-10 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal and sanding from 48Km to 38Km. Grader working on snow removal from Paint Lake Road to 13Km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7665KL-20211210-1CAT 95010.51606.5 | KABI LAKE FOREST PRODUCTS LTD7665KL-20211210-1CAT 95010.51606.5OEWT-PA24-LEM | [5 empty] | 1 | 1606.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7670 | KL-20211211-1 | 53511011 | Access | 0 | CAT 950 | 153 | 6.5 | HR | 115 | 0 |  |  | 994.5 | 129.285 | 1123.785 | 2021-12-11 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from 49Km to 40Km. Grader 1 working on snow removal 0Km to 23Km for Crane demob. Grader 2 scarifying from 49 to 45Km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7670KL-20211211-1CAT 9506.5994.5 | KABI LAKE FOREST PRODUCTS LTD7670KL-20211211-1CAT 9506.5994.5OEWT-PA24-LEM | [5 empty] | 1 | 994.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7904 | KL-20220220-1 | 53511011 | Access | 0 | CAT 950 | 153 | 10.5 | HR | 115 | 0 |  |  | 1606.5 | 208.845 | 1815.345 | 2022-02-20 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 29km. Grader 2 working on snow removal from Paint Lake Road to 29km. Loader pushing back snow banks & pull offs from 45km to 38km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44617 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7904KL-20220220-1CAT 95010.51606.5 | KABI LAKE FOREST PRODUCTS LTD7904KL-20220220-1CAT 95010.51606.5OEWT-PA26-LEM | [5 empty] | 1 | 1606.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7905 | KL-20220219-1 | 53511011 | Access | 0 | CAT 950 | 153 | 9 | HR | 115 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2022-02-19 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 39km. Grader 2 working on snow removal from Paint Lake Road to 39km. Loader sanding & clearing pull offs to 34km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7905KL-20220219-1CAT 95091377 | KABI LAKE FOREST PRODUCTS LTD7905KL-20220219-1CAT 95091377OEWT-PA26-LEM | [5 empty] | 1 | 1377 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7911 | KL-20220221-1 | 53511011 | Access | 0 | CAT 950 | 153 | 6 | HR | 115 | 0 |  |  | 918 | 119.34 | 1037.34 | 2022-02-21 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 40km. Grader 2 working on snow removal from Paint Lake Road to 40km. Loader pushing back snow banks & pull offs from 49km to 40km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44617 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7911KL-20220221-1CAT 9506918 | KABI LAKE FOREST PRODUCTS LTD7911KL-20220221-1CAT 9506918OEWT-PA26-LEM | [5 empty] | 1 | 918 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7913 | KL-20220222-1 | 53511011 | Access | 0 | CAT 950 | 153 | 9 | HR | 115 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2022-02-22 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 38km. Grader 2 benchig snow banks from Paint Lake Road to 49km. Loader assisting with Demob of 50 Ton Crane from 32Km to Hensen Road. | 10 | F-066 to F-118 | Paint Lake Road 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7913KL-20220222-1CAT 95091377 | KABI LAKE FOREST PRODUCTS LTD7913KL-20220222-1CAT 95091377OEWT-PA26-LEM | [5 empty] | 1 | 1377 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7919 | KL-20220223-4 | 53511011 | Access | 0 | CAT 950 | 153 | 7 | HR | 115 | 0 |  |  | 1071 | 139.23 | 1210.23 | 2022-02-23 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from 49km to 29km. Loader working ahead of grader due to deep snow drifts | 10 | F066-F118 | Paint Lake 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7919KL-20220223-4CAT 95071071 | KABI LAKE FOREST PRODUCTS LTD7919KL-20220223-4CAT 95071071OEWT-PA26-LEM | [5 empty] | 1 | 1071 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7920 | KL-20220224-1 | 53511011 | Access | 0 | CAT 950 | 153 | 9 | HR | 115 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2022-02-24 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working on snow removal from 9.2Km to F-033 & to 23Km on Paint Lake Road #2. Supervisor doing pickup shuffle. | 10 | F066-F118 | Paint Lake 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7920KL-20220224-1CAT 95091377 | KABI LAKE FOREST PRODUCTS LTD7920KL-20220224-1CAT 95091377OEWT-PA26-LEM | [5 empty] | 1 | 1377 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7925 | KL-20220225-1 | 53511011 | Access | 0 | CAT 950 | 153 | 3.5 | HR | 115 | 0 |  |  | 535.5 | 69.615 | 605.115 | 2022-02-25 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 18km. Grader 2 working from Paint Lake Road to 18Km. Loader clearing pulloffs on Paint lake Road 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7925KL-20220225-1CAT 9503.5535.5 | KABI LAKE FOREST PRODUCTS LTD7925KL-20220225-1CAT 9503.5535.5OEWT-PA26-LEM | [5 empty] | 1 | 535.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7935 | KL-20220226-1 | 53511011 | Access | 0 | CAT 950 | 153 | 9.5 | HR | 115 | 0 |  |  | 1453.5 | 188.955 | 1642.455 | 2022-02-26 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader working from Paint Lake Road to Km 34 benching and widening / Loader clearing pull offs on Paint Lake Road 2 and widening @ Km 27 | 10 | F066-F118 | Paint Lake 2 | 0 | 44628 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7935KL-20220226-1CAT 9509.51453.5 | KABI LAKE FOREST PRODUCTS LTD7935KL-20220226-1CAT 9509.51453.5 | [5 empty] | 1 | 1453.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7938 | KL-20220227-1 | 53511011 | Access | 0 | CAT 950 | 153 | 6.5 | HR | 115 | 0 |  |  | 994.5 | 129.285 | 1123.785 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader 1 working from 49km to 26km. Grader 2 working from Paint Lake Road to 8km. Loader working on clearing pull offs between 9.2Km & 5Km on Paint Lake Road #2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44628 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7938KL-20220227-1CAT 9506.5994.5 | KABI LAKE FOREST PRODUCTS LTD7938KL-20220227-1CAT 9506.5994.5 | [5 empty] | 1 | 994.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7966 | KL-20220303-5 | 53511011 | Access | 0 | CAT 950 | 153 | 6.5 | HR | 115 | 0 |  |  | 994.5 | 129.285 | 1123.785 | 2022-03-03 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader working on snow removal from Paint Lake Road to F-033 | 10 | F009 - F065 | Paint Lake | 0 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7966KL-20220303-5CAT 9506.5994.5 | KABI LAKE FOREST PRODUCTS LTD7966KL-20220303-5CAT 9506.5994.5 | [5 empty] | 1 | 994.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7969 | KL-20220304-4 | 53511011 | Access | 0 | CAT 950 | 153 | 6.5 | HR | 115 | 0 |  |  | 994.5 | 129.285 | 1123.785 | 2022-03-04 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader Continuing Working On Snow Removal From Paint Lake Road 2 To F033 | 10 | F009 - F065 | Paint Lake | 0 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7969KL-20220304-4CAT 9506.5994.5 | KABI LAKE FOREST PRODUCTS LTD7969KL-20220304-4CAT 9506.5994.5 | [5 empty] | 1 | 994.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7970 | KL-20220305-2 | 53511011 | Access | 0 | CAT 950 | 153 | 9.5 | HR | 115 | 0 |  |  | 1453.5 | 188.955 | 1642.455 | 2022-03-05 |  |  |  |  | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Loader Working On Snow Removal From Paint Lake Road 2 To F033 | 10 | F009 - F065 | Paint Lake | 0 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7970KL-20220305-2CAT 9509.51453.5 | KABI LAKE FOREST PRODUCTS LTD7970KL-20220305-2CAT 9509.51453.5 | [5 empty] | 1 | 1453.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7978 | KL-20220306-3 | 53511011 | Access | 0 | CAT 950 | 153 | 4.5 | HR | 115 | 0 |  |  | 688.5 | 89.505 | 778.005 | 2022-03-06 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader Working On Snow Removal From Paint Lake Road To 12.5 Km On Paint Lake Road 2/Graded 3 Times Due To Winter Storm/Loader Working From F037 To F034 | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44637 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7978KL-20220306-3CAT 9504.5688.5 | KABI LAKE FOREST PRODUCTS LTD7978KL-20220306-3CAT 9504.5688.5 | [5 empty] | 1 | 688.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6140 | KL-20210222-14 | 53511111 | Access | 0 | CAT 950 | 153 | 6 | HR | 115 | 0 |  |  | 918 | 119.34 | 1037.34 | 2021-02-22 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer clearing roads km20 to km15, loader clearing km 0 to 5 Hensen West. | 11 | F119-F134 | Hensen Road | 0 | 44269 |  | 56 | 44270 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6140KL-20210222-14CAT 9506918 | KABI LAKE FOREST PRODUCTS LTD6140KL-20210222-14CAT 9506918OEWT PA15-LEM | [5 empty] | 1 | 918 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7592 | KL-20211124-4 | 53511111 | Access | 0 | CAT 950 | 153 | 9.5 | HR | 115 | 0 |  |  | 1453.5 | 188.955 | 1642.455 | 2021-11-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader continuing to scraping and sand road to F213/F214 for stringing crews | 11 | F212-F235 | Ainjigame | 0 | 44529 |  | 61 | 44530 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7592KL-20211124-4CAT 9509.51453.5 | KABI LAKE FOREST PRODUCTS LTD7592KL-20211124-4CAT 9509.51453.5OEWT-PA23-Lem | [5 empty] | 1 | 1453.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7594 | KL-20211125-3 | 53511111 | Access | 0 | CAT 950 | 153 | 9.5 | HR | 115 | 0 |  |  | 1453.5 | 188.955 | 1642.455 | 2021-11-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader continuing to scraping and sand road to F213, F217 and to F218 for stringing crews/ Supervision of Skagen | 11 | F212-F235 | Anjigame | 0 | 44525 |  | 61 | 44530 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7594KL-20211125-3CAT 9509.51453.5 | KABI LAKE FOREST PRODUCTS LTD7594KL-20211125-3CAT 9509.51453.5OEWT-PA23-Lem | [5 empty] | 1 | 1453.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7607 | KL-20211129-4 | 53511111 | Access | 0 | CAT 950 | 153 | 4 | HR | 115 | 0 |  |  | 612 | 79.56 | 691.56 | 2021-11-29 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader starting scraping and sanding road to F213/F214 for stringing crews | 11 | F212-F235 | Ainjigame Road | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7607KL-20211129-4CAT 9504612 | KABI LAKE FOREST PRODUCTS LTD7607KL-20211129-4CAT 9504612OEWT-PA24-LEM | [5 empty] | 1 | 612 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7610 | KL-20211130-3 | 53511111 | Access | 0 | CAT 950 | 153 | 9.5 | HR | 115 | 0 |  |  | 1453.5 | 188.955 | 1642.455 | 2021-11-30 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader continuing scraping and sanding road to F213/F214 for stringing crews | 11 | F212-F235 | Anjigame Road | 0 | 44537 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7610KL-20211130-3CAT 9509.51453.5 | KABI LAKE FOREST PRODUCTS LTD7610KL-20211130-3CAT 9509.51453.5OEWT-PA24-LEM | [5 empty] | 1 | 1453.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7615 | KL-20211201-5 | 53511111 | Access | 0 | CAT 950 | 153 | 9 | HR | 115 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2021-12-01 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader starting scraping and sanding road to F213/F214 and access to F216 for stringing crews | 11 | F212-F235 | Anjigami | 0 | 44537 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7615KL-20211201-5CAT 95091377 | KABI LAKE FOREST PRODUCTS LTD7615KL-20211201-5CAT 95091377OEWT-PA24-LEM | [5 empty] | 1 | 1377 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7623 | KL-20211202-5 | 53511111 | Access | 0 | CAT 950 | 153 | 5 | HR | 115 | 0 |  |  | 765 | 99.45 | 864.45 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader doing snow removal from Anjigami road to F218 | 11 | F212-F235 | Anjigame | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7623KL-20211202-5CAT 9505765 | KABI LAKE FOREST PRODUCTS LTD7623KL-20211202-5CAT 9505765OEWT-PA24-LEM | [5 empty] | 1 | 765 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7894 | KL-20220216-2 | 53511111 | Access | 0 | CAT 950 | 153 | 1 | HR | 115 | 0 |  |  | 153 | 19.89 | 172.89 | 2022-02-16 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen Road / Loader clearing entrance @ Hwy 17 and Hensen Road | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7894KL-20220216-2CAT 9501153 | KABI LAKE FOREST PRODUCTS LTD7894KL-20220216-2CAT 9501153OEWT-PA26-LEM | [5 empty] | 1 | 153 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7898 | KL-20220217-3 | 53511111 | Access | 0 | CAT 950 | 153 | 10 | HR | 115 | 0 |  |  | 1530 | 198.9 | 1728.9 | 2022-02-17 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen Road and to F131 in Hensen East / Loader clearing pull off on Hensen Road and F126 Access | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7898KL-20220217-3CAT 950101530 | KABI LAKE FOREST PRODUCTS LTD7898KL-20220217-3CAT 950101530OEWT-PA26-LEM | [5 empty] | 1 | 1530 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7901 | KL-20220218-2 | 53511111 | Access | 0 | CAT 950 | 153 | 9.5 | HR | 115 | 0 |  |  | 1453.5 | 188.955 | 1642.455 | 2022-02-18 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader finishing clearing pull off, widening corners and sanding from Km 5 to Km 17/ Supervisor doing pickup shuffle | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7901KL-20220218-2CAT 9509.51453.5 | KABI LAKE FOREST PRODUCTS LTD7901KL-20220218-2CAT 9509.51453.5OEWT-PA26-LEM | [5 empty] | 1 | 1453.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7912 | KL-20220221-2 | 53511111 | Access | 0 | CAT 950 | 153 | 3.5 | HR | 115 | 0 |  |  | 535.5 | 69.615 | 605.115 | 2022-02-21 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal & benching snow banks from Hwy 17 to 17Km on Hensen Road. Loader starting clearing of pull offs on Hensen Road & widening corners | 11 | F118-F127 | Henson | 0 | 44617 |  | 61 | 44617 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7912KL-20220221-2CAT 9503.5535.5 | KABI LAKE FOREST PRODUCTS LTD7912KL-20220221-2CAT 9503.5535.5OEWT-PA26-LEM | [5 empty] | 1 | 535.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7917 | KL-20220223-2 | 53511111 | Access | 0 | CAT 950 | 153 | 4 | HR | 115 | 0 |  |  | 612 | 79.56 | 691.56 | 2022-02-23 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17km on Hensen Road. Loader widening corners & assisting float trucks | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7917KL-20220223-2CAT 9504612 | KABI LAKE FOREST PRODUCTS LTD7917KL-20220223-2CAT 9504612OEWT-PA26-LEM | [5 empty] | 1 | 612 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7941 | KL-20220227-4 | 53511111 | Access | 0 | CAT 950 | 153 | 3 | HR | 115 | 0 |  |  | 459 | 59.67 | 518.67 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader Starting Snow Removal From F168 To F165. Access/Winter Access Maintenance (Cost Code: 67776007556.591100.57010107) | 11 | F165 - F169 | Magpie Hills | 0 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7941KL-20220227-4CAT 9503459 | KABI LAKE FOREST PRODUCTS LTD7941KL-20220227-4CAT 9503459 | [5 empty] | 1 | 459 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7946 | KL-20220228-3 | 53511111 | Access | 0 | CAT 950 | 153 | 5 | HR | 115 | 0 |  |  | 765 | 99.45 | 864.45 | 2022-02-28 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loader Finishing Snow Removal From F165 To F169. Access/Winter Access Maintenance (Cost Code: 67776007556.591100.57010107) | 11 | F165 - F169 | Magpie Hills | 1 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7946KL-20220228-3CAT 9505765 | KABI LAKE FOREST PRODUCTS LTD7946KL-20220228-3CAT 9505765 | [5 empty] | 1 | 765 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7948 | KL-20220228-5 | 53511111 | Access | 0 | CAT 950 | 153 | 5 | HR | 115 | 0 |  |  | 765 | 99.45 | 864.45 | 2022-02-28 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loaders Working On Snow Removal From F184 To F181 & Starting @ F175 To F171. Access/Winter Access Maintenance (Cost Code: 67776007556.591100.57010107) | 11 | F170 - F211 | High Falls | 1 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7948KL-20220228-5CAT 9505765 | KABI LAKE FOREST PRODUCTS LTD7948KL-20220228-5CAT 9505765 | [5 empty] | 1 | 765 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7956 | KL-20220301-3 | 53511111 | Access | 0 | CAT 950 | 153 | 5 | HR | 115 | 0 |  |  | 765 | 99.45 | 864.45 | 2022-03-01 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loaders finishing on snow removal from F175 to F171 Cost Code: 67776007556.591100.57010107 ) | 11 | F170 - F211 | High Falls | 1 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7956KL-20220301-3CAT 9505765 | KABI LAKE FOREST PRODUCTS LTD7956KL-20220301-3CAT 9505765 | [5 empty] | 1 | 765 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7960 | KL-20220302-5 | 53511111 | Access | 0 | CAT 950 | 153 | 7 | HR | 115 | 0 |  |  | 1071 | 139.23 | 1210.23 | 2022-03-02 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loaders finishing on snow removal and turn around @ F170 / Traffic control required for clearing of Entrance ( Cost Code: 67776007556.591100.57010107 ) | 11 | F170 - F211 | High Falls | 1 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7960KL-20220302-5CAT 95071071 | KABI LAKE FOREST PRODUCTS LTD7960KL-20220302-5CAT 95071071 | [5 empty] | 1 | 1071 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7974 | KL-20220307-4 | 53511111 | Access | 0 | CAT 950 | 153 | 9 | HR | 115 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2022-03-07 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loader Working On Snow Removal From High Falls Road To F175, F174, F172 & F171 ( Cost Code: 67776007556.591100.57010107 ) | 11 | F170-F211 | High Falls | 1 | 44634 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7974KL-20220307-4CAT 95091377 | KABI LAKE FOREST PRODUCTS LTD7974KL-20220307-4CAT 95091377 | [5 empty] | 1 | 1377 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7821 | KL-20220131-4 | 53511111 | Access | 0 | CAT 950 | 153 | 9 | HR | 115 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2022-01-31 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from F235 to F230 and Pads in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7821KL-20220131-4CAT 95091377 | KABI LAKE FOREST PRODUCTS LTD7821KL-20220131-4CAT 95091377OEWT-PA26-LEM | [5 empty] | 1 | 1377 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7825 | KL-20220201-4 | 53511111 | Access | 0 | CAT 950 | 153 | 7 | HR | 115 | 0 |  |  | 1071 | 139.23 | 1210.23 | 2022-02-01 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from F235 to F230 and Pads in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7825KL-20220201-4CAT 95071071 | KABI LAKE FOREST PRODUCTS LTD7825KL-20220201-4CAT 95071071OEWT-PA26-LEM | [5 empty] | 1 | 1071 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7831 | KL-20220202-3 | 53511111 | Access | 0 | CAT 950 | 153 | 9 | HR | 115 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2022-02-02 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7831KL-20220202-3CAT 95091377 | KABI LAKE FOREST PRODUCTS LTD7831KL-20220202-3CAT 95091377OEWT-PA26-LEM | [5 empty] | 1 | 1377 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7835 | KL-20220204-4 | 53511111 | Access | 0 | CAT 950 | 153 | 9 | HR | 115 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2022-02-04 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7835KL-20220204-4CAT 95091377 | KABI LAKE FOREST PRODUCTS LTD7835KL-20220204-4CAT 95091377OEWT-PA26-LEM | [5 empty] | 1 | 1377 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7853 | KL-20220208-2 | 53511111 | Access | 0 | CAT 950 | 153 | 8 | HR | 115 | 0 |  |  | 1224 | 159.12 | 1383.12 | 2022-02-08 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to 17Km on Hensen Road & snow removal to F131 on Hensen East. Loader clearing pull offs & widening corners to 7km. Supervisor doing pickup shuffle. | 11 | F118 - F127 | Henson | 0 | 44604 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7853KL-20220208-2CAT 95081224 | KABI LAKE FOREST PRODUCTS LTD7853KL-20220208-2CAT 95081224OEWT-PA26-LEM | [5 empty] | 1 | 1224 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7862 | KL-20220209-5 | 53511111 | Access | 0 | CAT 950 | 153 | 9 | HR | 115 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2022-02-09 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to Km 17 on Hensen road /Loader clearing pull offs and widening corners and sanding to Km 12 /Supervisor doing pickup shuffle | 11 | F118-F127 | Henson | 0 | 44604 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7862KL-20220209-5CAT 95091377 | KABI LAKE FOREST PRODUCTS LTD7862KL-20220209-5CAT 95091377OEWT-PA26-LEM | [5 empty] | 1 | 1377 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7867 | KL-20220210-4 | 53511111 | Access | 0 | CAT 950 | 153 | 9 | HR | 115 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2022-02-10 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to Km 17 on Hensen road and benching snowbanks from Km .5 to Km 5/Loader clearing pull offs and widening corners and sanding from Km 5 to Km 17 | 11 | F118-F127 | Henson | 0 | 44605 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7867KL-20220210-4CAT 95091377 | KABI LAKE FOREST PRODUCTS LTD7867KL-20220210-4CAT 95091377OEWT-PA26-LEM | [5 empty] | 1 | 1377 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7870 | KL-20220211-2 | 53511111 | Access | 0 | CAT 950 | 153 | 5 | HR | 115 | 0 |  |  | 765 | 99.45 | 864.45 | 2022-02-11 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen road /Loader clearing pull offs and sanding from Km 10 to Km 17 | 11 | F118-F127 | Henson | 0 | 44605 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7870KL-20220211-2CAT 9505765 | KABI LAKE FOREST PRODUCTS LTD7870KL-20220211-2CAT 9505765OEWT-PA26-LEM | [5 empty] | 1 | 765 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7876 | KL-20220212-4 | 53511111 | Access | 0 | CAT 950 | 153 | 4.5 | HR | 115 | 0 |  |  | 688.5 | 89.505 | 778.005 | 2022-02-12 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen road and Hensen Road East to F123/Loader clearing pull offs and sanding from Km 10 to Km 4 | 11 | F118-F127 | Henson | 0 | 44605 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7876KL-20220212-4CAT 9504.5688.5 | KABI LAKE FOREST PRODUCTS LTD7876KL-20220212-4CAT 9504.5688.5OEWT-PA26-LEM | [5 empty] | 1 | 688.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7589 | KL-20211123-4 | 53511112 | Access | 0 | CAT 950 | 153 | 3 | HR | 115 | 0 |  |  | 459 | 59.67 | 518.67 | 2021-11-23 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader starting to scrape and sand road to Km 14 for stringing crews | 11 | F212-F235 | Ainjigame | 0 | 44529 |  | 61 | 44530 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7589KL-20211123-4CAT 9503459 | KABI LAKE FOREST PRODUCTS LTD7589KL-20211123-4CAT 9503459OEWT-PA23-Lem | [5 empty] | 1 | 459 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7496 | KL-20211027-1 | 53511012 | Access | 0 | CAT 35 ton Articulated Truck | 229 | 5 | HR | 172 | 0 |  |  | 1145 | 148.85 | 1293.85 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 44, laying Geo and spreading existing material/Excavtor 2 loading existing material@ km 17 on Hensen/rock truck hauling existing material to Km 44 supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-1CAT 35 ton Articulated Truck51145 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-1CAT 35 ton Articulated Truck51145OEWT-PA23-Lem | [5 empty] | 1 | 1145 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7502 | KL-20211028-1 | 53511012 | Access | 0 | CAT 35 ton Articulated Truck | 229 | 9.5 | HR | 172 | 0 |  |  | 2175.5 | 282.815 | 2458.315 | 2021-10-28 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 laying Geo and spreading existing material @ Km 44 and shaping road to Km 45/Excavtor 2 cleaning up excavation @ km 17 on Hensen road and shaping road to F114 rock truck2 hauling from F088 to Km 34-33 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-1CAT 35 ton Articulated Truck9.52175.5 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-1CAT 35 ton Articulated Truck9.52175.5OEWT-PA23-Lem | [5 empty] | 1 | 2175.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6999 | KL-20210531-1 | 53510812 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 3 | HR | 142 | 0 |  |  | 567 | 73.71 | 640.71 | 2021-05-31 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauling existing material for covering of soft sections on E005 access | 8 | E004-E016 | White Lake East | 0 | 44358 |  | 36 | 44359 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6999KL-20210531-1CAT 30 ton Articulated Truck3567 | KABI LAKE FOREST PRODUCTS LTD6999KL-20210531-1CAT 30 ton Articulated Truck3567OEWT-PA18-Lem | [5 empty] | 1 | 567 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511003 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 8 | HR | 142 | 0 |  |  | 1512 | 196.56 | 1708.56 | 2021-09-20 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44466 |  | 50 | 44466 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1CAT 30 ton Articulated Truck81512 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1CAT 30 ton Articulated Truck81512OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.59731 | 903.1344 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7379 | KL-20210923-1 | 53511003 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 9 | HR | 142 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2021-09-23 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees@ 18 km, excavator 2 placing trees/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 61 | 44471 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-1CAT 30 ton Articulated Truck91701 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-1CAT 30 ton Articulated Truck91701OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 850.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7384 | KL-20210924-1 | 53511003 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 9 | HR | 142 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2021-09-24 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees, excavator 2 placing trees @km 16.5 and Km 21 hill/Chapman rock truck hauling Gravel From km 38 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 50 | 44470 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-1CAT 30 ton Articulated Truck91701 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-1CAT 30 ton Articulated Truck91701OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.51268 | 872.0697 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7307 | KL-20210901-2 | 53511004 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 7 | HR | 142 | 0 |  |  | 1323 | 171.99 | 1494.99 | 2021-09-01 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from @ km49 to Skagen excavator @ km 43/ 2 Kabi , 1 Chapman and 3 Cobiere rock trucks/ excavator 2 preping access @km 35 to 34 for gravel Haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 37 | 44457 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-2CAT 30 ton Articulated Truck71323 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-2CAT 30 ton Articulated Truck71323OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 1323 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7311 | KL-20210902-2 | 53511004 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 9 | HR | 142 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2021-09-02 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from 38.5 km Morin excavator @ km 40/41 for road capping | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 37 | 44457 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7311KL-20210902-2CAT 30 ton Articulated Truck91701 | KABI LAKE FOREST PRODUCTS LTD7311KL-20210902-2CAT 30 ton Articulated Truck91701OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 1701 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7312 | KL-20210903-2 | 53511004 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 8 | HR | 142 | 0 |  |  | 1512 | 196.56 | 1708.56 | 2021-09-03 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from 38.5 km Morin excavator @ km 40/41 for road capping | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 50 | 44450 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7312KL-20210903-2CAT 30 ton Articulated Truck81512 | KABI LAKE FOREST PRODUCTS LTD7312KL-20210903-2CAT 30 ton Articulated Truck81512OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 1512 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7330 | KL-20210910-2 | 53511004 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 5 | HR | 142 | 0 |  |  | 945 | 122.85 | 1067.85 | 2021-09-10 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 12 and Km 5 to Km 19 / 1 rock truck hauling from 38 km to Morin Excavator @ 40/42 km/rock truck 2 driving from Hwy to Km 38 and haul gravel | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44454 |  | 50 | 44462 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-2CAT 30 ton Articulated Truck5945 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-2CAT 30 ton Articulated Truck5945OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.81072 | 766.133 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7332 | KL-20210911-2 | 53511004 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 4 | HR | 142 | 0 |  |  | 756 | 98.28 | 854.28 | 2021-09-11 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck hauling from km 38 to km 40 with Skagen and Morin/Kabi rock truck driving from km .5 on Hensen to km 38 for gravel haul | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44460 |  | 50 | 44462 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2CAT 30 ton Articulated Truck4756 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2CAT 30 ton Articulated Truck4756OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.71555 | 540.9556 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7350 | KL-20210916-1 | 53511004 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 9.5 | HR | 142 | 0 |  |  | 1795.5 | 233.415 | 2028.915 | 2021-09-16 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator loading and hauling from 18 to19.5 km /Chapman rock truck and Kabi 30 ton rock truck hauling from 38 to 42/43 km with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44463 |  |  | 44464 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1CAT 30 ton Articulated Truck9.51795.5 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1CAT 30 ton Articulated Truck9.51795.5OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.76183 | 1367.8583 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511004 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 5 | HR | 142 | 0 |  |  | 945 | 122.85 | 1067.85 | 2021-09-17 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44463 |  | 50 | 44466 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1CAT 30 ton Articulated Truck5945 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1CAT 30 ton Articulated Truck5945OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.55803 | 527.3376 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7334 | KL-20210912-2 | 53511004 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 9.5 | HR | 142 | 0 |  |  | 1795.5 | 233.415 | 2028.915 | 2021-09-12 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 19/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44460 |  | 50 | 44462 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-2CAT 30 ton Articulated Truck9.51795.5 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-2CAT 30 ton Articulated Truck9.51795.5OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.68622 | 1232.1073 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7335 | KL-20210913-2 | 53511004 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 9 | HR | 142 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2021-09-13 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44460 |  |  | 44461 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2CAT 30 ton Articulated Truck91701 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2CAT 30 ton Articulated Truck91701OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.79105 | 1345.5739 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511004 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 5 | HR | 142 | 0 |  |  | 945 | 122.85 | 1067.85 | 2021-09-14 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 44460 |  |  | 44461 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2CAT 30 ton Articulated Truck5945 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2CAT 30 ton Articulated Truck5945OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 472.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511004 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 9 | HR | 142 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2021-09-27 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44475 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1CAT 30 ton Articulated Truck91701 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1CAT 30 ton Articulated Truck91701OEWT-PA22-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1701 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7427 | KL-20211005-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 9 | HR | 142 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2021-10-05 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F112. Excavator 2 working @ 43/42km. Rock trucks hauling from 37.5km to Skagen @ 36km. Labourer hauling fuel to 35km as per Valard. Supervision of Skagen/Morin. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-1CAT 30 ton Articulated Truck91701 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-1CAT 30 ton Articulated Truck91701OEWT-PA22-Lem | [5 empty] | 1 | 1701 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7431 | KL-20211006-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 9 | HR | 142 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2021-10-06 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-1CAT 30 ton Articulated Truck91701 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-1CAT 30 ton Articulated Truck91701OEWT-PA22-Lem | [5 empty] | 1 | 1701 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7457 | KL-20211015-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 9.5 | HR | 142 | 0 |  |  | 1795.5 | 233.415 | 2028.915 | 2021-10-15 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Flll toFlOO level ruts & drainage isting material from F088 to 34.SKm as per Valard. Supervise Morin, Skagen, Pleson, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1CAT 30 ton Articulated Truck9.51795.5 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1CAT 30 ton Articulated Truck9.51795.5OEWT-PA22-Lem | [5 empty] | 1 | 1795.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7460 | KL-20211016-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 9.5 | HR | 142 | 0 |  |  | 1795.5 | 233.415 | 2028.915 | 2021-10-16 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F194 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1CAT 30 ton Articulated Truck9.51795.5 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1CAT 30 ton Articulated Truck9.51795.5OEWT-PA22-Lem | [5 empty] | 1 | 1795.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7414 | KL-20211001-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 10 | HR | 142 | 0 |  |  | 1890 | 245.7 | 2135.7 | 2021-10-01 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-1CAT 30 ton Articulated Truck101890 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-1CAT 30 ton Articulated Truck101890OEWT-PA22-Lem | [5 empty] | 1 | 1890 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7419 | KL-20211002-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 9 | HR | 142 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2021-10-02 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-1CAT 30 ton Articulated Truck91701 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-1CAT 30 ton Articulated Truck91701OEWT-PA22-Lem | [5 empty] | 1 | 1701 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7421 | KL-20211003-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 8.5 | HR | 142 | 0 |  |  | 1606.5 | 208.845 | 1815.345 | 2021-10-03 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading & hauling from 46km to 45km. Labourers hauling fuel to 35km & installing silt fencing as per Valard. Supervision o Skagen & Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-1CAT 30 ton Articulated Truck8.51606.5 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-1CAT 30 ton Articulated Truck8.51606.5OEWT-PA22-Lem | [5 empty] | 1 | 1606.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7424 | KL-20211004-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 9 | HR | 142 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2021-10-04 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working from Paint 2 to F115. excavator 2 working from 45km to 43km. Rock truck hauling existing material from 37.5km to Skagen @36km. Supervision of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7424KL-20211004-1CAT 30 ton Articulated Truck91701 | KABI LAKE FOREST PRODUCTS LTD7424KL-20211004-1CAT 30 ton Articulated Truck91701OEWT-PA22-Lem | [5 empty] | 1 | 1701 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7434 | KL-20211007-1-R1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 9 | HR | 142 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2021-10-07 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R1CAT 30 ton Articulated Truck91701 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R1CAT 30 ton Articulated Truck91701OEWT-PA22-Lem | [5 empty] | 1 | 1701 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7439 | KL-20211009-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 5 | HR | 142 | 0 |  |  | 945 | 122.85 | 1067.85 | 2021-10-09 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km. Rock trucks on site for gravel haul. Supervision of Morin & Skagen. | 10 | F033 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-1CAT 30 ton Articulated Truck5945 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-1CAT 30 ton Articulated Truck5945OEWT-PA22-Lem | [5 empty] | 1 | 945 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7441 | KL-20211010-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 4 | HR | 142 | 0 |  |  | 756 | 98.28 | 854.28 | 2021-10-10 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, corduroy & cap 43km hill. Rock trucks on site for gravel haul. Supervise Morin & Skagen. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-1CAT 30 ton Articulated Truck4756 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-1CAT 30 ton Articulated Truck4756OEWT-PA22-Lem | [5 empty] | 1 | 756 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7442 | KL-20211011-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 4 | HR | 142 | 0 |  |  | 756 | 98.28 | 854.28 | 2021-10-11 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, levelling ruts & drainage. Rock trucks on site for gravel haul. Supervisor touring for blasting locations. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-1CAT 30 ton Articulated Truck4756 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-1CAT 30 ton Articulated Truck4756OEWT-PA22-Lem | [5 empty] | 1 | 756 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7444 | KL-20211008-1-R1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 11 | HR | 142 | 0 |  |  | 2079 | 270.27 | 2349.27 | 2021-10-08 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7444KL-20211008-1-R1CAT 30 ton Articulated Truck112079 | KABI LAKE FOREST PRODUCTS LTD7444KL-20211008-1-R1CAT 30 ton Articulated Truck112079OEWT-PA22-Lem | [5 empty] | 1 | 2079 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7445 | KL-20211012-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 4 | HR | 142 | 0 |  |  | 756 | 98.28 | 854.28 | 2021-10-12 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45 to 43km. Excavator 2 working from 43 to 40.5km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervisor site visit with blaster. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-1CAT 30 ton Articulated Truck4756 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-1CAT 30 ton Articulated Truck4756OEWT-PA22-Lem | [5 empty] | 1 | 756 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7448 | KL-20211013-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 4 | HR | 142 | 0 |  |  | 756 | 98.28 | 854.28 | 2021-10-13 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 46 to 43km. Excavator 2 working from 43 to 39km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervision of Morin, Skagen, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-1CAT 30 ton Articulated Truck4756 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-1CAT 30 ton Articulated Truck4756OEWT-PA22-Lem | [5 empty] | 1 | 756 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7453 | KL-20211014-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 10 | HR | 142 | 0 |  |  | 1890 | 245.7 | 2135.7 | 2021-10-14 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from 46 to 39Km, levelling ruts & drainage. Rock trucks haulig existing material from F088 to 34.5Km. Labourer hauling fuel as per Valard. Supervision of Morin, Skagen & Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-1CAT 30 ton Articulated Truck101890 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-1CAT 30 ton Articulated Truck101890OEWT-PA22-Lem | [5 empty] | 1 | 1890 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7465 | KL-20211017-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 9.5 | HR | 142 | 0 |  |  | 1795.5 | 233.415 | 2028.915 | 2021-10-17 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F108, F105,and F103 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | PAINT Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-1CAT 30 ton Articulated Truck9.51795.5 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-1CAT 30 ton Articulated Truck9.51795.5OEWT-PA22-Lem | [5 empty] | 1 | 1795.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7471 | KL-20211018-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 9.5 | HR | 142 | 0 |  |  | 1795.5 | 233.415 | 2028.915 | 2021-10-18 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34 as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1CAT 30 ton Articulated Truck9.51795.5 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1CAT 30 ton Articulated Truck9.51795.5OEWT-PA22-Lem | [5 empty] | 1 | 1795.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7475 | KL-20211019-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 10 | HR | 142 | 0 |  |  | 1890 | 245.7 | 2135.7 | 2021-10-19 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts, laying Geo and spreading existing material @ Km 42 hill/rock trucks hauling existing material from F088 to Km 34 as per Valard. Labourers picking up 4 roll of Geo @12km on Paint Lake Road 2and deliver it to km 42/worked late to finish capping @km 42 for pickup access/Supervision of Morin, Skagen, Pleson and Opas | 10 |  | Paint | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1CAT 30 ton Articulated Truck101890 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1CAT 30 ton Articulated Truck101890OEWT-PA22-Lem | [5 empty] | 1 | 1890 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7478 | KL-20211020-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 9.5 | HR | 142 | 0 |  |  | 1795.5 | 233.415 | 2028.915 | 2021-10-20 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material @ Km 42.5/rock trucks hauling existing material from F088 to Km 34 and Km 42.5 as per Valard. Excavator 3 tracking from Km 49, starting @ F112 to F114 leveling ruts,shaping and drainage/725 rock truck driving to Km .5 for float/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1CAT 30 ton Articulated Truck9.51795.5 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1CAT 30 ton Articulated Truck9.51795.5OEWT-PA22-Lem | [5 empty] | 1 | 1795.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7480 | KL-20211021-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 9 | HR | 142 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2021-10-21 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material on sections/rock trucks hauling existing material from F088 as per Valard. Excavator 3 continuing @ F113 to F115 leveling ruts,shaping and drainage for freezing/ Supervision of Morin, Skagen, Pleson and Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-1CAT 30 ton Articulated Truck91701 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-1CAT 30 ton Articulated Truck91701OEWT-PA22-Lem | [5 empty] | 1 | 1701 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7484 | KL-20211023-2 | 53511112 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 9 | HR | 142 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2021-10-23 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul trees for fill and start capping with existing material @ F123 to F124 access realignment | 11 | F119-F134 | Hensen Road | 0 | 44495 |  | 61 | 44496 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7484KL-20211023-2CAT 30 ton Articulated Truck91701 | KABI LAKE FOREST PRODUCTS LTD7484KL-20211023-2CAT 30 ton Articulated Truck91701OEWT-PA22-Lem | [5 empty] | 1 | 1701 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2426 | KL-20200812-2 | 53510712 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 8 | HR | 134 | 0 |  |  | 1424 | 185.12 | 1609.12 | 2020-08-12 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 2 Rock Trucks hauling from stock pile to D132/ Excavator loading | 7 | D-119 to D-141 | Alder Creek | 0 | 44060 |  | 47 | 44061 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD2426KL-20200812-2CAT 25 ton Articulated Truck81424 | KABI LAKE FOREST PRODUCTS LTD2426KL-20200812-2CAT 25 ton Articulated Truck81424OEWT-PA8-LEM | [5 empty] | 1 | 1424 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6922 | KL-20210515-6 | 53510812 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-05-15 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading, hauling and spreading pit run from stock pile to E007/E006 access/loading and hauling trees for soft sections/dozer leveling ruts and excavator placing corduroy | 8 | E004-E016 | White Lake East | 0 | 44337 |  | 56 | 44342 | [5 empty] | Mandy Sandhu | 08 | KABI LAKE FOREST PRODUCTS LTD6922KL-20210515-6CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD6922KL-20210515-6CAT 25 ton Articulated Truck9.51691OEWT-PA17-LEM | [5 empty] | 1 | 1691 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6945 | KL-20210518-2 | 53510812 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 2.5 | HR | 134 | 0 |  |  | 445 | 57.85 | 502.85 | 2021-05-18 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | loading , hauling and spreading existing material @ E014 for road repairs from E014.5 to E016 to maintain pickup access | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44349 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6945KL-20210518-2CAT 25 ton Articulated Truck2.5445 | KABI LAKE FOREST PRODUCTS LTD6945KL-20210518-2CAT 25 ton Articulated Truck2.5445OEWT-PA17-LEM | [5 empty] | 1 | 445 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6951 | KL-20210519-2 | 53510812 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 3.5 | HR | 134 | 0 |  |  | 623 | 80.99 | 703.99 | 2021-05-19 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading, hauling and spreading exsiting material @ E014 for road repairs from E016 to E013.5 (revised) | 8 | E034 - E036 | White Lake East | 0 | 44345 |  | 14 | 44352 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6951KL-20210519-2CAT 25 ton Articulated Truck3.5623 | KABI LAKE FOREST PRODUCTS LTD6951KL-20210519-2CAT 25 ton Articulated Truck3.5623OEWT-PA17-LEM | [5 empty] | 1 | 623 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6959 | KL-20210520-1 | 53510812 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10.5 | HR | 134 | 0 |  |  | 1869 | 242.97 | 2111.97 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread existing material @ 1.5 km and pit run from stock pile for road repair on E007/E006 main access road/ Laboures laying Geo ( revised) | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6959KL-20210520-1CAT 25 ton Articulated Truck10.51869 | KABI LAKE FOREST PRODUCTS LTD6959KL-20210520-1CAT 25 ton Articulated Truck10.51869OEWT-PA17-LEM | [5 empty] | 1 | 1869 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6967 | KL-20210521-2 | 53510812 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10.5 | HR | 134 | 0 |  |  | 1869 | 242.97 | 2111.97 | 2021-05-21 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material from stockpile for road repairs to the access going into E005. Dozer spreading loads from from rock truck and fixing ruts. | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6967KL-20210521-2CAT 25 ton Articulated Truck10.51869 | KABI LAKE FOREST PRODUCTS LTD6967KL-20210521-2CAT 25 ton Articulated Truck10.51869OEWT-PA17-LEM | [5 empty] | 1 | 1869 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6970 | KL-20210522-1 | 53510812 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10.5 | HR | 134 | 0 |  |  | 1869 | 242.97 | 2111.97 | 2021-05-22 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material from stock pile and bundles of wood from the main road to E006 for road repairs, dozer spreading loads and pushing up bundle of wood | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44348 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6970KL-20210522-1CAT 25 ton Articulated Truck10.51869 | KABI LAKE FOREST PRODUCTS LTD6970KL-20210522-1CAT 25 ton Articulated Truck10.51869OEWT-PA17-LEM | [5 empty] | 1 | 1869 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6977 | KL-20210523-4 | 53510812 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10.5 | HR | 134 | 0 |  |  | 1869 | 242.97 | 2111.97 | 2021-05-23 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material for road repairs near E011, 330 loading material and dozer spreading loads from rock truck and fixing punch outs | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6977KL-20210523-4CAT 25 ton Articulated Truck10.51869 | KABI LAKE FOREST PRODUCTS LTD6977KL-20210523-4CAT 25 ton Articulated Truck10.51869OEWT-PA17-LEM | [5 empty] | 1 | 1869 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6983 | KL-20210525-2 | 53510812 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 3 | HR | 134 | 0 |  |  | 534 | 69.42 | 603.42 | 2021-05-25 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load Haul and spread existing material @ E014 for Road repairs from E015 to E016/Excavator and Dozer working on Road maintenance E013 to E006 | 8 | E004-E016 | White Lake East | 0 | 44343 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6983KL-20210525-2CAT 25 ton Articulated Truck3534 | KABI LAKE FOREST PRODUCTS LTD6983KL-20210525-2CAT 25 ton Articulated Truck3534OEWT-PA17-LEM | [5 empty] | 1 | 534 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3623 | KL-20201009-12 | 53510912 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 16 | HR | 134 | 0 |  |  | 2848 | 370.24 | 3218.24 | 2020-10-09 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fix road and spread loads between E173 and E172, Haul gravel to E168 to E171 and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3623KL-20201009-12CAT 25 ton Articulated Truck162848 | KABI LAKE FOREST PRODUCTS LTD3623KL-20201009-12CAT 25 ton Articulated Truck162848OEWT-PA10-LEM | [5 empty] | 1 | 2848 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3648 | KL-20201010-12 | 53510912 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 33 | HR | 134 | 0 |  |  | 5874 | 763.62 | 6637.62 | 2020-10-10 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trucks from 650 pit, fix rds, spread loads between E-173, E-172 and haul gravel to E-168/E-171and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3648KL-20201010-12CAT 25 ton Articulated Truck335874 | KABI LAKE FOREST PRODUCTS LTD3648KL-20201010-12CAT 25 ton Articulated Truck335874OEWT-PA10-LEM | [5 empty] | 1 | 5874 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3671 | KL-20201011-11 | 53510912 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 44 | HR | 134 | 0 |  |  | 7832 | 1018.16 | 8850.16 | 2020-10-11 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trucks from 650 pit, fix road and haul gravel to E168 to E171 and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44157 |  | 15 | 44131 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3671KL-20201011-11CAT 25 ton Articulated Truck447832 | KABI LAKE FOREST PRODUCTS LTD3671KL-20201011-11CAT 25 ton Articulated Truck447832OEWT-PA10-LEM | [5 empty] | 1 | 7832 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3698 | KL-20201012-16 | 53510912 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 44 | HR | 134 | 0 |  |  | 7832 | 1018.16 | 8850.16 | 2020-10-12 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trucks from 650 pit, fix roads and haul gravel to E168 to E171 and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44126 |  | 15 | 44132 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3698KL-20201012-16CAT 25 ton Articulated Truck447832 | KABI LAKE FOREST PRODUCTS LTD3698KL-20201012-16CAT 25 ton Articulated Truck447832OEWT-PA10-LEM | [5 empty] | 1 | 7832 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511003 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-09-20 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44466 |  | 50 | 44466 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1CAT 25 ton Articulated Truck9.51691OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.59731 | 1010.0531 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7361 | KL-20210919-1 | 53511003 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-09-19 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km and pulling pickups @ end of shift /Chapman rock truck hauling trees from F104 to Morin @ km 41 and 42. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44466 |  | 50 | 44466 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-1CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-1CAT 25 ton Articulated Truck91602OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 801 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7370 | KL-20210921-1 | 53511003 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-09-21 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 17 to 20 km/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44467 |  | 50 | 44467 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1CAT 25 ton Articulated Truck91602OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.51171 | 819.7556 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7379 | KL-20210923-1 | 53511003 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-09-23 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees@ 18 km, excavator 2 placing trees/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 61 | 44471 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-1CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-1CAT 25 ton Articulated Truck91602OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 801 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7200 | KL-20210804-1 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-08-04 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load existing material from 17Km on Hensen Road & Gravel road sections @ 46/45Km on Paint Lake road 2 as per Valard. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7200KL-20210804-1CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7200KL-20210804-1CAT 25 ton Articulated Truck91602OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 801 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7201 | KL-20210808-1 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-08-08 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading existing material from 17Km on Hensen Road & Gravel road sections @ 46/44Km on Paint Lake road 2 as per Valard. 1 Kabi Rock Truck & 2 Valard Rock Trucks Hauling | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7201KL-20210808-1CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7201KL-20210808-1CAT 25 ton Articulated Truck91602OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 801 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7202 | KL-20210805-1 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-08-05 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading existing material from 17Km on Hensen Road & Gravel road sections @ 45/44Km on Paint Lake road 2 as per Valard. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7202KL-20210805-1CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7202KL-20210805-1CAT 25 ton Articulated Truck91602OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 801 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7204 | KL-20210806-1 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-08-06 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading existing material from 17Km on Hensen Road & Gravel road sections @ 46/44Km on Paint Lake road 2 as per Valard. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7204KL-20210806-1CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7204KL-20210806-1CAT 25 ton Articulated Truck91602OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 801 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7207 | KL-20210809-1 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-08-09 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/loading mats on Valard Rock truck. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7207KL-20210809-1CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7207KL-20210809-1CAT 25 ton Articulated Truck91602OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7211 | KL-20210810-1 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-08-10 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/loading mats on Valard Rock truck. | 10 | F033-F118 | Paint Lake Road2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7211KL-20210810-1CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7211KL-20210810-1CAT 25 ton Articulated Truck91602OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7212 | KL-20210811-1 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-08-11 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 45/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/2 Valard Rock truck. Continue grading Paint Lake Road 2 from Km 7.5 to Km 11.5 - SSF-14324 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7212KL-20210811-1CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7212KL-20210811-1CAT 25 ton Articulated Truck91602OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7213 | KL-20210812-1 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 8.5 | HR | 134 | 0 |  |  | 1513 | 196.69 | 1709.69 | 2021-08-12 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel access mat sections @ 45/44 km on Paint Lake Road 2/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on Valard 2nd rock truck. Finish grading Paint Lake Road 2 to Km 13 and touch up on way out to Paint Lake Road - SSF-14325 | 10 | F033-F118 | Paint ake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7213KL-20210812-1CAT 25 ton Articulated Truck8.51513 | KABI LAKE FOREST PRODUCTS LTD7213KL-20210812-1CAT 25 ton Articulated Truck8.51513OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1513 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7214 | KL-20210813-1 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-08-13 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on 2nd Valard Rock truck | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7214KL-20210813-1CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7214KL-20210813-1CAT 25 ton Articulated Truck91602OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7215 | KL-20210814-1 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-08-14 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/43 km/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on 2nd Valard Rock truck/Excavator working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7215KL-20210814-1CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7215KL-20210814-1CAT 25 ton Articulated Truck91602OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7218 | KL-20210815-1 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-08-15 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/43 km/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on 2nd Valard Rock truck/Excavator 2 working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7218KL-20210815-1CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7218KL-20210815-1CAT 25 ton Articulated Truck91602OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7221 | KL-20210816-1 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 8.5 | HR | 134 | 0 |  |  | 1513 | 196.69 | 1709.69 | 2021-08-16 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/43 km/ 1 Kabi Rock Truck, Corbiere and Valard Rock truck/Excavator 2 working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7221KL-20210816-1CAT 25 ton Articulated Truck8.51513 | KABI LAKE FOREST PRODUCTS LTD7221KL-20210816-1CAT 25 ton Articulated Truck8.51513OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1513 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7224 | KL-20210817-1 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-08-17 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/46 km/ 1 Kabi Rock Truck, Corbiere and Valard Rock truck/Excavator 2 working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7224KL-20210817-1CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7224KL-20210817-1CAT 25 ton Articulated Truck91602OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7248 | KL-20210819-4 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-08-19 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44433 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7248KL-20210819-4CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7248KL-20210819-4CAT 25 ton Articulated Truck91602OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7252 | KL-20210820-5 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 8 | HR | 134 | 0 |  |  | 1424 | 185.12 | 1609.12 | 2021-08-20 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44433 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-5CAT 25 ton Articulated Truck81424 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-5CAT 25 ton Articulated Truck81424OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1424 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7257 | KL-20210821-5 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-08-21 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/46/3 rock trucks Kabi, Corbiere and Valard/ 2nd Ex working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44434 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-5CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-5CAT 25 ton Articulated Truck91602OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7267 | KL-20210822-4 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-08-22 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/4. One Kabi rock truck, one Corbiere, and 1 Valard. 2nd excavator working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 50 | 44440 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-4CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-4CAT 25 ton Articulated Truck91602OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7271 | KL-20210823-5 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-08-23 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/44. One Kabi rock truck, Corbiere and Valard/ 2nd Ex working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 37 | 44439 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-5CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-5CAT 25 ton Articulated Truck91602OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7275 | KL-20210824-3 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 5 | HR | 134 | 0 |  |  | 890 | 115.7 | 1005.7 | 2021-08-24 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from km 17 on Hensen Road to Corbiere Dozer@km 44.5/43.5/3 rock trucks Kabi, Corbiere and Valard/ Excavator 2 working ahead @km 42 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-3CAT 25 ton Articulated Truck5890 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-3CAT 25 ton Articulated Truck5890OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 890 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7285 | KL-20210828-3 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-08-28 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from km49 to Skagen excavator @ 46/45 km - 1 Kabi , 1 Chapman and 2 Cobiere rock trucks | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7285KL-20210828-3CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7285KL-20210828-3CAT 25 ton Articulated Truck91602OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 1602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7288 | KL-20210830-2 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-08-30 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks/ excavator 2 shaping and leveling slopes | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44439 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-2CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-2CAT 25 ton Articulated Truck91602OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 1602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7292 | KL-20210831-2 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 8.5 | HR | 134 | 0 |  |  | 1513 | 196.69 | 1709.69 | 2021-08-31 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from 49 Km to 44/43Km. 1 Kabi rock truck, 2 Corbiere Rock Trucks & 1 Chapman Rock Truck. Excavator 2 tracking from 49Km to F-086 for gravel haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44442 |  | 37 | 44445 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-2CAT 25 ton Articulated Truck8.51513 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-2CAT 25 ton Articulated Truck8.51513OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 1513 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7307 | KL-20210901-2 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-09-01 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from @ km49 to Skagen excavator @ km 43/ 2 Kabi , 1 Chapman and 3 Cobiere rock trucks/ excavator 2 preping access @km 35 to 34 for gravel Haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 37 | 44457 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-2CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-2CAT 25 ton Articulated Truck91602OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 1602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7311 | KL-20210902-2 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-09-02 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from 38.5 km Morin excavator @ km 40/41 for road capping | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 37 | 44457 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7311KL-20210902-2CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7311KL-20210902-2CAT 25 ton Articulated Truck91602OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 1602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7312 | KL-20210903-2 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 8 | HR | 134 | 0 |  |  | 1424 | 185.12 | 1609.12 | 2021-09-03 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from 38.5 km Morin excavator @ km 40/41 for road capping | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 50 | 44450 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7312KL-20210903-2CAT 25 ton Articulated Truck81424 | KABI LAKE FOREST PRODUCTS LTD7312KL-20210903-2CAT 25 ton Articulated Truck81424OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 1424 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7330 | KL-20210910-2 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-09-10 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 12 and Km 5 to Km 19 / 1 rock truck hauling from 38 km to Morin Excavator @ 40/42 km/rock truck 2 driving from Hwy to Km 38 and haul gravel | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44454 |  | 50 | 44462 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-2CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-2CAT 25 ton Articulated Truck91602OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.81072 | 1298.7778 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7332 | KL-20210911-2 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 8.5 | HR | 134 | 0 |  |  | 1513 | 196.69 | 1709.69 | 2021-09-11 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck hauling from km 38 to km 40 with Skagen and Morin/Kabi rock truck driving from km .5 on Hensen to km 38 for gravel haul | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44460 |  | 50 | 44462 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2CAT 25 ton Articulated Truck8.51513 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2CAT 25 ton Articulated Truck8.51513OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.71555 | 1082.6267 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7332 | KL-20210911-2 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-09-11 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck hauling from km 38 to km 40 with Skagen and Morin/Kabi rock truck driving from km .5 on Hensen to km 38 for gravel haul | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44460 |  | 50 | 44462 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2CAT 25 ton Articulated Truck9.51691OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.71555 | 1209.9946 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7350 | KL-20210916-1 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-09-16 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator loading and hauling from 18 to19.5 km /Chapman rock truck and Kabi 30 ton rock truck hauling from 38 to 42/43 km with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44463 |  |  | 44464 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1CAT 25 ton Articulated Truck9.51691OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.76183 | 1288.2475 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7350 | KL-20210916-1 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-09-16 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator loading and hauling from 18 to19.5 km /Chapman rock truck and Kabi 30 ton rock truck hauling from 38 to 42/43 km with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44463 |  |  | 44464 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1CAT 25 ton Articulated Truck91602OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.76183 | 1220.445 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-09-17 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44463 |  | 50 | 44466 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1CAT 25 ton Articulated Truck91602OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.55803 | 893.9627 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 5 | HR | 134 | 0 |  |  | 890 | 115.7 | 1005.7 | 2021-09-17 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44463 |  | 50 | 44466 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1CAT 25 ton Articulated Truck5890 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1CAT 25 ton Articulated Truck5890OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.55803 | 496.646 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7334 | KL-20210912-2 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 5.5 | HR | 134 | 0 |  |  | 979 | 127.27 | 1106.27 | 2021-09-12 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 19/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44460 |  | 50 | 44462 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-2CAT 25 ton Articulated Truck5.5979 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-2CAT 25 ton Articulated Truck5.5979OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.68622 | 671.809 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7334 | KL-20210912-2 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-09-12 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 19/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44460 |  | 50 | 44462 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-2CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-2CAT 25 ton Articulated Truck91602OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.68622 | 1099.3238 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7335 | KL-20210913-2 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-09-13 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44460 |  |  | 44461 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2CAT 25 ton Articulated Truck91602OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.79105 | 1267.2601 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7335 | KL-20210913-2 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-09-13 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44460 |  |  | 44461 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2CAT 25 ton Articulated Truck91602OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.79105 | 1267.2601 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 5 | HR | 134 | 0 |  |  | 890 | 115.7 | 1005.7 | 2021-09-14 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 44460 |  |  | 44461 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2CAT 25 ton Articulated Truck5890 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2CAT 25 ton Articulated Truck5890OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 445 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 5 | HR | 134 | 0 |  |  | 890 | 115.7 | 1005.7 | 2021-09-14 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 44460 |  |  | 44461 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2CAT 25 ton Articulated Truck5890 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2CAT 25 ton Articulated Truck5890OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 445 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7279 | KL-20210825-3 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-08-25 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 42 to Morin Excavator/ Excavator 2 fixing up access from Km 44 to Km 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7279KL-20210825-3CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7279KL-20210825-3CAT 25 ton Articulated Truck91602OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7347 | KL-20210915-1 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 5 | HR | 134 | 0 |  |  | 890 | 115.7 | 1005.7 | 2021-09-15 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator working from 18 to 19.5 km leveling ruts and shaping road for pick up access /Chapman rock truck and Kabi 30 ton rock truck on site to haul with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44454 |  |  | 44464 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-1CAT 25 ton Articulated Truck5890 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-1CAT 25 ton Articulated Truck5890OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 0.5 | 0.5 | 445 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7384 | KL-20210924-1 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-09-24 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees, excavator 2 placing trees @km 16.5 and Km 21 hill/Chapman rock truck hauling Gravel From km 38 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 50 | 44470 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-1CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-1CAT 25 ton Articulated Truck91602OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.51268 | 821.3143 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511004 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-09-27 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44475 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1CAT 25 ton Articulated Truck9.51691OEWT-PA22-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 1691 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7427 | KL-20211005-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 7 | HR | 134 | 0 |  |  | 1246 | 161.98 | 1407.98 | 2021-10-05 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F112. Excavator 2 working @ 43/42km. Rock trucks hauling from 37.5km to Skagen @ 36km. Labourer hauling fuel to 35km as per Valard. Supervision of Skagen/Morin. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-1CAT 25 ton Articulated Truck71246 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-1CAT 25 ton Articulated Truck71246OEWT-PA22-Lem | [5 empty] | 1 | 1246 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7431 | KL-20211006-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-10-06 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-1CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-1CAT 25 ton Articulated Truck101780OEWT-PA22-Lem | [5 empty] | 1 | 1780 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7457 | KL-20211015-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 19 | HR | 134 | 0 |  |  | 3382 | 439.66 | 3821.66 | 2021-10-15 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Flll toFlOO level ruts & drainage isting material from F088 to 34.SKm as per Valard. Supervise Morin, Skagen, Pleson, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1CAT 25 ton Articulated Truck193382 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1CAT 25 ton Articulated Truck193382OEWT-PA22-Lem | [5 empty] | 1 | 3382 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7460 | KL-20211016-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-10-16 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F194 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1CAT 25 ton Articulated Truck9.51691OEWT-PA22-Lem | [5 empty] | 1 | 1691 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7460 | KL-20211016-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-10-16 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F194 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1CAT 25 ton Articulated Truck9.51691OEWT-PA22-Lem | [5 empty] | 1 | 1691 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7414 | KL-20211001-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-10-01 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-1CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-1CAT 25 ton Articulated Truck101780OEWT-PA22-Lem | [5 empty] | 1 | 1780 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7419 | KL-20211002-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 5.5 | HR | 134 | 0 |  |  | 979 | 127.27 | 1106.27 | 2021-10-02 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-1CAT 25 ton Articulated Truck5.5979 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-1CAT 25 ton Articulated Truck5.5979OEWT-PA22-Lem | [5 empty] | 1 | 979 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7434 | KL-20211007-1-R1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-10-07 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R1CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R1CAT 25 ton Articulated Truck101780OEWT-PA22-Lem | [5 empty] | 1 | 1780 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7439 | KL-20211009-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 5 | HR | 134 | 0 |  |  | 890 | 115.7 | 1005.7 | 2021-10-09 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km. Rock trucks on site for gravel haul. Supervision of Morin & Skagen. | 10 | F033 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-1CAT 25 ton Articulated Truck5890 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-1CAT 25 ton Articulated Truck5890OEWT-PA22-Lem | [5 empty] | 1 | 890 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7441 | KL-20211010-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 4 | HR | 134 | 0 |  |  | 712 | 92.56 | 804.56 | 2021-10-10 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, corduroy & cap 43km hill. Rock trucks on site for gravel haul. Supervise Morin & Skagen. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-1CAT 25 ton Articulated Truck4712 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-1CAT 25 ton Articulated Truck4712OEWT-PA22-Lem | [5 empty] | 1 | 712 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7442 | KL-20211011-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 4 | HR | 134 | 0 |  |  | 712 | 92.56 | 804.56 | 2021-10-11 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, levelling ruts & drainage. Rock trucks on site for gravel haul. Supervisor touring for blasting locations. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-1CAT 25 ton Articulated Truck4712 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-1CAT 25 ton Articulated Truck4712OEWT-PA22-Lem | [5 empty] | 1 | 712 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7444 | KL-20211008-1-R1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 11 | HR | 134 | 0 |  |  | 1958 | 254.54 | 2212.54 | 2021-10-08 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7444KL-20211008-1-R1CAT 25 ton Articulated Truck111958 | KABI LAKE FOREST PRODUCTS LTD7444KL-20211008-1-R1CAT 25 ton Articulated Truck111958OEWT-PA22-Lem | [5 empty] | 1 | 1958 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7445 | KL-20211012-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 8 | HR | 134 | 0 |  |  | 1424 | 185.12 | 1609.12 | 2021-10-12 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45 to 43km. Excavator 2 working from 43 to 40.5km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervisor site visit with blaster. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-1CAT 25 ton Articulated Truck81424 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-1CAT 25 ton Articulated Truck81424OEWT-PA22-Lem | [5 empty] | 1 | 1424 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7448 | KL-20211013-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 8 | HR | 134 | 0 |  |  | 1424 | 185.12 | 1609.12 | 2021-10-13 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 46 to 43km. Excavator 2 working from 43 to 39km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervision of Morin, Skagen, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-1CAT 25 ton Articulated Truck81424 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-1CAT 25 ton Articulated Truck81424OEWT-PA22-Lem | [5 empty] | 1 | 1424 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7453 | KL-20211014-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-10-14 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from 46 to 39Km, levelling ruts & drainage. Rock trucks haulig existing material from F088 to 34.5Km. Labourer hauling fuel as per Valard. Supervision of Morin, Skagen & Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-1CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-1CAT 25 ton Articulated Truck101780OEWT-PA22-Lem | [5 empty] | 1 | 1780 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7465 | KL-20211017-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 19 | HR | 134 | 0 |  |  | 3382 | 439.66 | 3821.66 | 2021-10-17 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F108, F105,and F103 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | PAINT Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-1CAT 25 ton Articulated Truck193382 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-1CAT 25 ton Articulated Truck193382OEWT-PA22-Lem | [5 empty] | 1 | 3382 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7471 | KL-20211018-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 19 | HR | 134 | 0 |  |  | 3382 | 439.66 | 3821.66 | 2021-10-18 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34 as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1CAT 25 ton Articulated Truck193382 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1CAT 25 ton Articulated Truck193382OEWT-PA22-Lem | [5 empty] | 1 | 3382 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7475 | KL-20211019-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 20 | HR | 134 | 0 |  |  | 3560 | 462.8 | 4022.8 | 2021-10-19 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts, laying Geo and spreading existing material @ Km 42 hill/rock trucks hauling existing material from F088 to Km 34 as per Valard. Labourers picking up 4 roll of Geo @12km on Paint Lake Road 2and deliver it to km 42/worked late to finish capping @km 42 for pickup access/Supervision of Morin, Skagen, Pleson and Opas | 10 |  | Paint | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1CAT 25 ton Articulated Truck203560 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1CAT 25 ton Articulated Truck203560OEWT-PA22-Lem | [5 empty] | 1 | 3560 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7478 | KL-20211020-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 19.5 | HR | 134 | 0 |  |  | 3471 | 451.23 | 3922.23 | 2021-10-20 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material @ Km 42.5/rock trucks hauling existing material from F088 to Km 34 and Km 42.5 as per Valard. Excavator 3 tracking from Km 49, starting @ F112 to F114 leveling ruts,shaping and drainage/725 rock truck driving to Km .5 for float/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1CAT 25 ton Articulated Truck19.53471 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1CAT 25 ton Articulated Truck19.53471OEWT-PA22-Lem | [5 empty] | 1 | 3471 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7496 | KL-20211027-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 5 | HR | 134 | 0 |  |  | 890 | 115.7 | 1005.7 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 44, laying Geo and spreading existing material/Excavtor 2 loading existing material@ km 17 on Hensen/rock truck hauling existing material to Km 44 supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-1CAT 25 ton Articulated Truck5890 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-1CAT 25 ton Articulated Truck5890OEWT-PA23-Lem | [5 empty] | 1 | 890 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7502 | KL-20211028-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 5.5 | HR | 134 | 0 |  |  | 979 | 127.27 | 1106.27 | 2021-10-28 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 laying Geo and spreading existing material @ Km 44 and shaping road to Km 45/Excavtor 2 cleaning up excavation @ km 17 on Hensen road and shaping road to F114 rock truck2 hauling from F088 to Km 34-33 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-1CAT 25 ton Articulated Truck5.5979 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-1CAT 25 ton Articulated Truck5.5979OEWT-PA23-Lem | [5 empty] | 1 | 979 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7506 | KL-20211029-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-10-29 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing clean up of excavation @ Km 17 on Hensen road and start shaping road to Km 45.5. Rock truck hauling existing material from F088 to Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44502 |  | 61 | 44503 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7506KL-20211029-1CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7506KL-20211029-1CAT 25 ton Articulated Truck91602OEWT-PA23-Lem | [5 empty] | 1 | 1602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7510 | KL-20211030-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-10-30 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road to Km 45 to Km 43 and spreading spotted rock trucks loads. Rock truck hauling existing material from F088 to Morin @ Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas. | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44502 |  | 61 | 44503 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7510KL-20211030-1CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7510KL-20211030-1CAT 25 ton Articulated Truck9.51691OEWT-PA23-Lem | [5 empty] | 1 | 1691 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7517 | KL-20211031-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-10-31 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 43 to Km 40.5 and spreading spotted rock trucks loads /Excavator 2 leveling ruts and shaping road from F116 to F112 rock truck hauling existing material from F088 to Morin @ Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F033 - F071 | Paint Lake 2 | 0 | 44505 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7517KL-20211031-1CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7517KL-20211031-1CAT 25 ton Articulated Truck9.51691OEWT-PA23-Lem | [5 empty] | 1 | 1691 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7519 | KL-20211101-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-11-01 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 43 to Km 40.5 and spreading spotted rock trucks loads. Rock truck hauling existing material from F-088 to Morin @ 33.5Km as per Valard. Supervision of Morin, Skagen, JJR & Opas | 10 | F033 - F071 | Paint Lake 2 | 0 | 44501 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7519KL-20211101-1CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7519KL-20211101-1CAT 25 ton Articulated Truck9.51691OEWT-PA23-Lem | [5 empty] | 1 | 1691 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7547 | KL-20211102-2 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-11-02 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking from Km 43 to Km 17 on Hensen Road for float access /Rock truck hauling existing material from F088 to Morin@Km 33 as per Valard. Supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-2CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-2CAT 25 ton Articulated Truck9.51691OEWT-PA23-Lem | [5 empty] | 1 | 1691 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7547 | KL-20211102-2 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-11-02 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking from Km 43 to Km 17 on Hensen Road for float access /Rock truck hauling existing material from F088 to Morin@Km 33 as per Valard. Supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-2CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-2CAT 25 ton Articulated Truck9.51691OEWT-PA23-Lem | [5 empty] | 1 | 1691 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7549 | KL-20211103-2 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-11-03 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 41 shape road. Rock trucks haul existing material from F088 to Morin @ Km 33 as per Valard /Supervision of Morin, Skagen, JJR, Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-2CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-2CAT 25 ton Articulated Truck9.51691OEWT-PA23-Lem | [5 empty] | 1 | 1691 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7549 | KL-20211103-2 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-11-03 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 41 shape road. Rock trucks haul existing material from F088 to Morin @ Km 33 as per Valard /Supervision of Morin, Skagen, JJR, Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-2CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-2CAT 25 ton Articulated Truck9.51691OEWT-PA23-Lem | [5 empty] | 1 | 1691 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7550 | KL-20211104-2 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-11-04 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 42 shaping road and spreading existing material on road surfaces Rock trucks hauling existing material from F088 to @ Km 43/42 as per Valard /Supervision of Morin, Skagen, JJR and OPAS | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-2CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-2CAT 25 ton Articulated Truck9.51691OEWT-PA23-Lem | [5 empty] | 1 | 1691 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7550 | KL-20211104-2 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-11-04 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 42 shaping road and spreading existing material on road surfaces Rock trucks hauling existing material from F088 to @ Km 43/42 as per Valard /Supervision of Morin, Skagen, JJR and OPAS | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-2CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-2CAT 25 ton Articulated Truck9.51691OEWT-PA23-Lem | [5 empty] | 1 | 1691 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7566 | KL-20211111-4 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-11-11 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-4CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-4CAT 25 ton Articulated Truck101780OEWT-PA23-Lem | [5 empty] | 1 | 1780 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7570 | KL-20211112-2 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 5 | HR | 134 | 0 |  |  | 890 | 115.7 | 1005.7 | 2021-11-12 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44520 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7570KL-20211112-2CAT 25 ton Articulated Truck5890 | KABI LAKE FOREST PRODUCTS LTD7570KL-20211112-2CAT 25 ton Articulated Truck5890OEWT-PA23-Lem | [5 empty] | 1 | 890 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7571 | KL-20211113-3 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 4 | HR | 134 | 0 |  |  | 712 | 92.56 | 804.56 | 2021-11-13 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Rock truck on site for hauling of existing material @ 24km. Supervision of Morin, Skagen, JJR & Opas. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7571KL-20211113-3CAT 25 ton Articulated Truck4712 | KABI LAKE FOREST PRODUCTS LTD7571KL-20211113-3CAT 25 ton Articulated Truck4712OEWT-PA23-Lem | [5 empty] | 1 | 712 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7572 | KL-20211114-2 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 4 | HR | 134 | 0 |  |  | 712 | 92.56 | 804.56 | 2021-11-14 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from 44Km to 41Km levelling ruts and shaping road. Rock truck on site for hauling of existing material @ 27Km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7572KL-20211114-2CAT 25 ton Articulated Truck4712 | KABI LAKE FOREST PRODUCTS LTD7572KL-20211114-2CAT 25 ton Articulated Truck4712OEWT-PA23-Lem | [5 empty] | 1 | 712 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7573 | KL-20211115-2 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-11-15 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road. Rock truck hauling existing material from 25Km and spotting dumping @ 22/23Km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7573KL-20211115-2CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7573KL-20211115-2CAT 25 ton Articulated Truck9.51691OEWT-PA23-Lem | [5 empty] | 1 | 1691 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7565 | KL-20211110-4 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-11-10 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 42 access leveling ruts and shaping road rock trucks hauling from Km 27 to JJR @ Km 26/24 repairing road sections /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-4CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-4CAT 25 ton Articulated Truck91602OEWT-PA23-Lem | [5 empty] | 1 | 1602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7565 | KL-20211110-4 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 5 | HR | 134 | 0 |  |  | 890 | 115.7 | 1005.7 | 2021-11-10 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 42 access leveling ruts and shaping road rock trucks hauling from Km 27 to JJR @ Km 26/24 repairing road sections /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-4CAT 25 ton Articulated Truck5890 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-4CAT 25 ton Articulated Truck5890OEWT-PA23-Lem | [5 empty] | 1 | 890 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7575 | KL-20211116-3 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 11 | HR | 134 | 0 |  |  | 1958 | 254.54 | 2212.54 | 2021-11-16 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road for freezing. Rock truck hauling existing material from 27Km to 23/24Km & dricing out to 9Km at end of shift for float accesss. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-3CAT 25 ton Articulated Truck111958 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-3CAT 25 ton Articulated Truck111958OEWT-PA23-Lem | [5 empty] | 1 | 1958 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7551 | KL-20211105-2 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-11-05 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 42 to Km 41 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F088 to @ Km 42/41 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-2CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-2CAT 25 ton Articulated Truck9.51691OEWT-PA23-Lem | [5 empty] | 1 | 1691 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7551 | KL-20211105-2 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-11-05 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 42 to Km 41 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F088 to @ Km 42/41 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-2CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-2CAT 25 ton Articulated Truck9.51691OEWT-PA23-Lem | [5 empty] | 1 | 1691 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7553 | KL-20211107-2 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-11-07 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working fro Km 41 to Km 39 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 41/39 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-2CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-2CAT 25 ton Articulated Truck9.51691OEWT-PA23-Lem | [5 empty] | 1 | 1691 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7553 | KL-20211107-2 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-11-07 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working fro Km 41 to Km 39 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 41/39 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-2CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-2CAT 25 ton Articulated Truck9.51691OEWT-PA23-Lem | [5 empty] | 1 | 1691 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7563 | KL-20211108-3 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-11-08 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 42 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-3CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-3CAT 25 ton Articulated Truck101780OEWT-PA23-Lem | [5 empty] | 1 | 1780 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7563 | KL-20211108-3 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-11-08 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 42 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-3CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-3CAT 25 ton Articulated Truck101780OEWT-PA23-Lem | [5 empty] | 1 | 1780 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7562 | KL-20211106-2-R1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-11-06 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 41 to Km 40 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F093 to @ Km 41/40 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44522 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R1CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R1CAT 25 ton Articulated Truck9.51691OEWT-PA23-Lem | [5 empty] | 1 | 1691 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7562 | KL-20211106-2-R1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-11-06 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 41 to Km 40 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F093 to @ Km 41/40 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44522 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R1CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R1CAT 25 ton Articulated Truck9.51691OEWT-PA23-Lem | [5 empty] | 1 | 1691 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7564 | KL-20211109-3 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-11-09 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 44 leveling ruts and shaping road Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-3CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-3CAT 25 ton Articulated Truck91602OEWT-PA23-Lem | [5 empty] | 1 | 1602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7564 | KL-20211109-3 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-11-09 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 44 leveling ruts and shaping road Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-3CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-3CAT 25 ton Articulated Truck91602OEWT-PA23-Lem | [5 empty] | 1 | 1602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7194 | KL-20210803-1 | 53511112 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 4 | HR | 134 | 0 |  |  | 712 | 92.56 | 804.56 | 2021-08-03 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer & Operator moving rock truck from F-037 to F-119 & tracking Cat 330 excavator from 17Km on Hensen to 46Km on paint lake road 2 for gravel haul | 11 | F118-F127 | Hensen Road | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD7194KL-20210803-1CAT 25 ton Articulated Truck4712 | KABI LAKE FOREST PRODUCTS LTD7194KL-20210803-1CAT 25 ton Articulated Truck4712OEWT-PA20-Lem | [5 empty] | 1 | 712 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7486 | KL-20211024-2 | 53511112 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-10-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from F123 access to F124 access realignment capping and start raising road and 1.5 km for crane access | 11 | F119-F134 | Hensen Road | 0 | 44495 |  | 61 | 44497 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7486KL-20211024-2CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7486KL-20211024-2CAT 25 ton Articulated Truck91602OEWT-PA23-Lem | [5 empty] | 1 | 1602 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7489 | KL-20211025-2 | 53511112 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9.5 | HR | 134 | 0 |  |  | 1691 | 219.83 | 1910.83 | 2021-10-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to 1.5 km for raising of road | 11 | F119-F134 | Hensen Road | 0 | 44496 |  | 61 | 44497 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7489KL-20211025-2CAT 25 ton Articulated Truck9.51691 | KABI LAKE FOREST PRODUCTS LTD7489KL-20211025-2CAT 25 ton Articulated Truck9.51691OEWT-PA23-Lem | [5 empty] | 1 | 1691 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7493 | KL-20211026-2 | 53511112 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 18.5 | HR | 134 | 0 |  |  | 3293 | 428.09 | 3721.09 | 2021-10-26 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul existing material from Km 17 on Hensen Road to F124 for capping | 11 | F118-F127 | Hensen | 0 | 44501 |  | 61 | 44502 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7493KL-20211026-2CAT 25 ton Articulated Truck18.53293 | KABI LAKE FOREST PRODUCTS LTD7493KL-20211026-2CAT 25 ton Articulated Truck18.53293OEWT-PA23-Lem | [5 empty] | 1 | 3293 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7497 | KL-20211027-2 | 53511112 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 7 | HR | 134 | 0 |  |  | 1246 | 161.98 | 1407.98 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul existing material from Km 17 on Hensen Road to F124 for capping/excavator speading existing material and shaping road from Hensen Road to F123 | 11 | F118-F127 | Hensen | 0 | 44501 |  | 61 | 44502 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7497KL-20211027-2CAT 25 ton Articulated Truck71246 | KABI LAKE FOREST PRODUCTS LTD7497KL-20211027-2CAT 25 ton Articulated Truck71246OEWT-PA23-Lem | [5 empty] | 1 | 1246 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7885 | KL-20220214-3 | 53510711 | Access | 0 | CAT 14G | 185 | 4 | HR | 139 | 0 |  |  | 740 | 96.2 | 836.2 | 2022-02-14 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run Grader from Kabi Yard to Alder Creek Road, clear snow @ entrance for float access and run grader back to Kabi Yard | 7 | D119-D141 | Alder Creek | 0 | 44614 |  | 61 | 44614 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7885KL-20220214-3CAT 14G4740 | KABI LAKE FOREST PRODUCTS LTD7885KL-20220214-3CAT 14G4740OEWT-PA26-LEM | [5 empty] | 1 | 740 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7951 | KL-20220207-8 | 53510711 | Access | 0 | CAT 14G | 185 | 1.5 | HR | 139 | 0 |  |  | 277.5 | 36.075 | 313.575 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from 41 road to White Lake West & clear lay down for float turn around. | 7 | D142 - E002 | White Lake West | 0 |  |  | 61 | 44614 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7951KL-20220207-8CAT 14G1.5277.5 | KABI LAKE FOREST PRODUCTS LTD7951KL-20220207-8CAT 14G1.5277.5OEWT-PA26-LEM | [5 empty] | 1 | 277.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7851 | KL-20220207-9 | 53510711 | Access | 0 | CAT 14G | 185 | 2 | HR | 139 | 0 |  |  | 370 | 48.1 | 418.1 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from White Lake West, clear hwy entrance, access & turn around for float access. | 7 | D100-D106 | 614 Road | 0 | 44604 |  | 61 | 44614 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7851KL-20220207-9CAT 14G2370 | KABI LAKE FOREST PRODUCTS LTD7851KL-20220207-9CAT 14G2370OEWT-PA26-LEM | [5 empty] | 1 | 370 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2018 | KL-20200712-9 | 53510712 | Access | 0 | CAT 14G | 185 | 5 | HR | 139 | 0 |  |  | 925 | 120.25 | 1045.25 | 2020-07-12 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 100 Road from Hwy to 5KM pit for gravel haul | 7 | D-119 to D-141 | Alder Creek | 0 | 44027 |  | 48 | 44028 | [5 empty] | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2018KL-20200712-9CAT 14G5925 | KABI LAKE FOREST PRODUCTS LTD2018KL-20200712-9CAT 14G5925OEWT-PA7-LEM | [5 empty] | 1 | 925 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2019 | KL-20200712-10 | 53510712 | Access | 0 | CAT 14G | 185 | 4 | HR | 139 | 0 |  |  | 740 | 96.2 | 836.2 | 2020-07-12 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Grade 600 road from Km 4 to Km 9 | 9 | E-091 to E-102 | 600 Road | 0 | 44027 | [9 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD2019KL-20200712-10CAT 14G4740 | KABI LAKE FOREST PRODUCTS LTD2019KL-20200712-10CAT 14G4740OEWT-PA7-LEM | [5 empty] | 1 | 740 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2101 | KL-20200717-13 | 53510712 | Access | 0 | CAT 14G | 185 | 5 | HR | 139 | 0 |  |  | 925 | 120.25 | 1045.25 | 2020-07-17 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 100 road from Hwy to 5km pit for gravel Haul | 7 | D-100 to D-106 | 614 Road | 0 | 44034 |  | 48 | 44034 | [5 empty] | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2101KL-20200717-13CAT 14G5925 | KABI LAKE FOREST PRODUCTS LTD2101KL-20200717-13CAT 14G5925OEWT-PA7-LEM | [5 empty] | 1 | 925 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7839 | KL-20220205-4 | 53510811 | Access | 0 | CAT 14G | 185 | 2 | HR | 139 | 0 |  |  | 370 | 48.1 | 418.1 | 2022-02-05 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from Kabi yard, clear snow around highway entrance and turn around for float access. | 8 | E042-E058 | Denis Lake W | 0 | 44603 |  | 61 | 44603 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7839KL-20220205-4CAT 14G2370 | KABI LAKE FOREST PRODUCTS LTD7839KL-20220205-4CAT 14G2370OEWT-PA26-LEM | [5 empty] | 1 | 370 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7840 | KL-20220205-5 | 53510811 | Access | 0 | CAT 14G | 185 | 3 | HR | 139 | 0 |  |  | 555 | 72.15 | 627.15 | 2022-02-05 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run Grader From Denis Lake West to 41 Road, Clear Snow @ Hwy Entrance, Open Road & Turn Around For Float Access/Supervisor Doing Pickup Shuffle | 8 | E037 - E041 | Road 41 | 0 | 44603 |  | 61 | 44603 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7840KL-20220205-5CAT 14G3555 | KABI LAKE FOREST PRODUCTS LTD7840KL-20220205-5CAT 14G3555OEWT-PA26-LEM | [5 empty] | 1 | 555 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7848 | KL-20220207-5 | 53510811 | Access | 0 | CAT 14G | 185 | 1.5 | HR | 139 | 0 |  |  | 277.5 | 36.075 | 313.575 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader clearing hwy entrance, open road & turn around for float access. | 8 | E037-E041 | 41 Road | 0 | 44604 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7848KL-20220207-5CAT 14G1.5277.5 | KABI LAKE FOREST PRODUCTS LTD7848KL-20220207-5CAT 14G1.5277.5OEWT-PA26-LEM | [5 empty] | 1 | 277.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7849 | KL-20220207-6 | 53510811 | Access | 0 | CAT 14G | 185 | 1.5 | HR | 139 | 0 |  |  | 277.5 | 36.075 | 313.575 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from 614 road & clear entrance for float access. | 8 | E004 - E010 | White Lake East | 0 | 44604 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7849KL-20220207-6CAT 14G1.5277.5 | KABI LAKE FOREST PRODUCTS LTD7849KL-20220207-6CAT 14G1.5277.5OEWT-PA26-LEM | [5 empty] | 1 | 277.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7850 | KL-20220207-7 | 53510811 | Access | 0 | CAT 14G | 185 | 1.5 | HR | 139 | 0 |  |  | 277.5 | 36.075 | 313.575 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from White Lake East, clear hwy entrance & turn around for float access. Run grader to 41 road & park. | 8 | E011-E025 | North Regan | 0 | 44604 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7850KL-20220207-7CAT 14G1.5277.5 | KABI LAKE FOREST PRODUCTS LTD7850KL-20220207-7CAT 14G1.5277.5OEWT-PA26-LEM | [5 empty] | 1 | 277.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7856 | KL-20220208-5 | 53510811 | Access | 0 | CAT 14G | 185 | 8 | HR | 139 | 0 |  |  | 1480 | 192.4 | 1672.4 | 2022-02-08 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run Grader From 41 Road,Clear Hwy Entrance, Open Road For Float Access & Run Grader Back To Kabi Yard | 8 | E025-E036 | Silver City | 0 | 44604 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7856KL-20220208-5CAT 14G81480 | KABI LAKE FOREST PRODUCTS LTD7856KL-20220208-5CAT 14G81480OEWT-PA26-LEM | [5 empty] | 1 | 1480 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1640 | KL-20200602-10 | 53510812 | Access | 0 | CAT 14G | 185 | 5 | HR | 139 | 0 |  |  | 925 | 120.25 | 1045.25 | 2020-06-02 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 100 road to 5 KM Pit gor Blue Cedar Gravel Haul | 8 | E077-E091 | Blue Cedar Road | 0 | 43987 |  | 15 | 43988 | [5 empty] | Martin Hunt | 08 | KABI LAKE FOREST PRODUCTS LTD1640KL-20200602-10CAT 14G5925 | KABI LAKE FOREST PRODUCTS LTD1640KL-20200602-10CAT 14G5925OEWT-PA6-LEM | [5 empty] | 1 | 925 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4356 | KL-20201114-9 | 53510812 | Access | 0 | CAT 14G | 185 | 3 | HR | 139 | 0 |  |  | 555 | 72.15 | 627.15 | 2020-11-14 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade sections of Access to D142 as per Valard | 8 | E004-E016 | White Lake East | 0 | 44166 |  | 53 | 44171 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4356KL-20201114-9CAT 14G3555 | KABI LAKE FOREST PRODUCTS LTD4356KL-20201114-9CAT 14G3555OEWT-PA11-LEM | [5 empty] | 1 | 555 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4385 | KL-20201114-20 | 53510812 | Access | 0 | CAT 14G | 185 | 2 | HR | 139 | 0 |  |  | 370 | 48.1 | 418.1 | 2020-11-14 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade access to ROW as per Valard | 8 | E037-E041 | 41 Road | 0 | 44167 |  | 53 | 44171 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4385KL-20201114-20CAT 14G2370 | KABI LAKE FOREST PRODUCTS LTD4385KL-20201114-20CAT 14G2370OEWT-PA11-LEM | [5 empty] | 1 | 370 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4514 | KL-20201121-15 | 53510911 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-11-21 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road, 100 Road, and Access Roads in WF 9 | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4514KL-20201121-15CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD4514KL-20201121-15CAT 14G112035OEWT-PA11-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4659 | KL-20201126-12 | 53510911 | Access | 0 | CAT 14G | 185 | 10 | HR | 139 | 0 |  |  | 1850 | 240.5 | 2090.5 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 and 100 road and access roads in WF 9 | 9 | E091-E102 | 600 Road | 0 | 44178 |  | 47 | 44183 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD4659KL-20201126-12CAT 14G101850 | KABI LAKE FOREST PRODUCTS LTD4659KL-20201126-12CAT 14G101850OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1850 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4703 | KL-20201128-11 | 53510911 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-11-28 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600rd, 100rd, and access in WF9 | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44201 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4703KL-20201128-11CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD4703KL-20201128-11CAT 14G112035OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4723 | KL-20201130-6 | 53510911 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-11-30 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600, 100 roads and access roads in WF9 | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44203 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4723KL-20201130-6CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD4723KL-20201130-6CAT 14G112035OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4745 | KL-20201201-17 | 53510911 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-12-01 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600rd, 100rd, and access roads in WF9 | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4745KL-20201201-17CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD4745KL-20201201-17CAT 14G112035OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4813 | KL-20201209-15 | 53510911 | Access | 0 | CAT 14G | 185 | 11.5 | HR | 139 | 0 |  |  | 2127.5 | 276.575 | 2404.075 | 2020-12-09 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 and 700 Road | 9 | E091-E102 | 600 Road | 0 | 44194 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4813KL-20201209-15CAT 14G11.52127.5 | KABI LAKE FOREST PRODUCTS LTD4813KL-20201209-15CAT 14G11.52127.5OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2127.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4829 | KL-20201211-7 | 53510911 | Access | 0 | CAT 14G | 185 | 14 | HR | 139 | 0 |  |  | 2590 | 336.7 | 2926.7 | 2020-12-11 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4829KL-20201211-7CAT 14G142590 | KABI LAKE FOREST PRODUCTS LTD4829KL-20201211-7CAT 14G142590OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2590 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4844 | KL-20201212-9 | 53510911 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-12-12 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 & 700 Roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44208 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4844KL-20201212-9CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD4844KL-20201212-9CAT 14G112035OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4891 | KL-20201204-14 | 53510911 | Access | 0 | CAT 14G | 185 |  | HR | 139 | 11 |  |  | 1529 | 198.77 | 1727.77 | 2020-12-04 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 23 | Approved | KABI LAKE - Standby - For Permits & Misc - ONGOING | 8002 | Standby due to Valard not requiring equipment . | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4891KL-20201204-14CAT 14G1529 | KABI LAKE FOREST PRODUCTS LTD4891KL-20201204-14CAT 14G1529OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1529 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4938 | KL-20201207-13 | 53510911 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 and 700 roads | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44206 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4938KL-20201207-13CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD4938KL-20201207-13CAT 14G112035OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4952 | KL-20201208-10 | 53510911 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-12-08 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44194 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4952KL-20201208-10CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD4952KL-20201208-10CAT 14G112035OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4973 | KL-20201210-12 | 53510911 | Access | 0 | CAT 14G | 185 | 12.5 | HR | 139 | 0 |  |  | 2312.5 | 300.625 | 2613.125 | 2020-12-10 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700, and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4973KL-20201210-12CAT 14G12.52312.5 | KABI LAKE FOREST PRODUCTS LTD4973KL-20201210-12CAT 14G12.52312.5OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2312.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4983 | KL-20201213-8 | 53510911 | Access | 0 | CAT 14G | 185 | 10 | HR | 139 | 0 |  |  | 1850 | 240.5 | 2090.5 | 2020-12-13 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4983KL-20201213-8CAT 14G101850 | KABI LAKE FOREST PRODUCTS LTD4983KL-20201213-8CAT 14G101850OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1850 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5018 | KL-20201215-6 | 53510911 | Access | 0 | CAT 14G | 185 | 12 | HR | 139 | 0 |  |  | 2220 | 288.6 | 2508.6 | 2020-12-15 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44198 |  | 53 | 44210 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5018KL-20201215-6CAT 14G122220 | KABI LAKE FOREST PRODUCTS LTD5018KL-20201215-6CAT 14G122220OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2220 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5031 | KL-20201216-3 | 53510911 | Access | 0 | CAT 14G | 185 | 13 | HR | 139 | 0 |  |  | 2405 | 312.65 | 2717.65 | 2020-12-16 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44210 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5031KL-20201216-3CAT 14G132405 | KABI LAKE FOREST PRODUCTS LTD5031KL-20201216-3CAT 14G132405OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2405 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5042 | KL-20201218-3 | 53510911 | Access | 0 | CAT 14G | 185 | 6 | HR | 139 | 0 |  |  | 1110 | 144.3 | 1254.3 | 2020-12-18 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700 Roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5042KL-20201218-3CAT 14G61110 | KABI LAKE FOREST PRODUCTS LTD5042KL-20201218-3CAT 14G61110OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1110 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5056 | KL-20201219-3 | 53510911 | Access | 0 | CAT 14G | 185 | 8 | HR | 139 | 0 |  |  | 1480 | 192.4 | 1672.4 | 2020-12-19 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 & 700 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5056KL-20201219-3CAT 14G81480 | KABI LAKE FOREST PRODUCTS LTD5056KL-20201219-3CAT 14G81480OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1480 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5099 | KL-20201217-7 | 53510911 | Access | 0 | CAT 14G | 185 | 13 | HR | 139 | 0 |  |  | 2405 | 312.65 | 2717.65 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5099KL-20201217-7CAT 14G132405 | KABI LAKE FOREST PRODUCTS LTD5099KL-20201217-7CAT 14G132405OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2405 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5129 | KL-20201221-4 | 53510911 | Access | 0 | CAT 14G | 185 | 12 | HR | 139 | 0 |  |  | 2220 | 288.6 | 2508.6 | 2020-12-21 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader on 600, 700, and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5129KL-20201221-4CAT 14G122220 | KABI LAKE FOREST PRODUCTS LTD5129KL-20201221-4CAT 14G122220OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2220 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5152 | KL-20201228-3 | 53510911 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-12-28 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44202 |  | 36 | 44213 | [5 empty] | Mike Lecocq | 09 | KABI LAKE FOREST PRODUCTS LTD5152KL-20201228-3CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD5152KL-20201228-3CAT 14G112035OEWT-PA13-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5196 | KL-20210102-3 | 53510911 | Access | 0 | CAT 14G | 185 | 4 | HR | 139 | 0 |  |  | 740 | 96.2 | 836.2 | 2021-01-02 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 100 road to km5 pit | 9 | E091-E102 | 600 Road | 0 | 44204 |  | 36 | 44217 | [5 empty] | Mike Lecocq | 09 | KABI LAKE FOREST PRODUCTS LTD5196KL-20210102-3CAT 14G4740 | KABI LAKE FOREST PRODUCTS LTD5196KL-20210102-3CAT 14G4740OEWT-PA13-LEM | [5 empty] | 1 | 740 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7902 | KL-20220218-3 | 53510911 | Access | 0 | CAT 14G | 185 | 10.5 | HR | 139 | 0 |  |  | 1942.5 | 252.525 | 2195.025 | 2022-02-18 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working snow removal from Km 9 to Km 35 on 600 Road | 9 | E092-F009 | 600 Road | 0 | 44614 |  | 61 | 44614 | [6 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD7902KL-20220218-3CAT 14G10.51942.5 | KABI LAKE FOREST PRODUCTS LTD7902KL-20220218-3CAT 14G10.51942.5OEWT-PA26-LEM | [5 empty] | 1 | 1942.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1963 | KL-20200708-10 | 53510912 | Access | 0 | CAT 14G | 185 | 12 | HR | 139 | 0 |  |  | 2220 | 288.6 | 2508.6 | 2020-07-08 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Backup - pickup 12 hrs, only allowed 10 - charged for only 10 on LEM |  | Approved |  |  | Grade 600 Road from 9km to 17km | 9 | E-091 to E-102 | 600 Road | 0 | 44025 |  | 50 | 44026 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD1963KL-20200708-10CAT 14G122220 | KABI LAKE FOREST PRODUCTS LTD1963KL-20200708-10CAT 14G122220OEWT-PA7-LEM | [5 empty] | 1 | 2220 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1973 | KL-20200702-9 | 53510912 | Access | 0 | CAT 14G | 185 | 5 | HR | 139 | 0 |  |  | 925 | 120.25 | 1045.25 | 2020-07-02 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road from 47km to 51km | 9 | E-091 to E-102 | 600 Road | 0 | 44021 |  | 50 | 44027 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD1973KL-20200702-9CAT 14G5925 | KABI LAKE FOREST PRODUCTS LTD1973KL-20200702-9CAT 14G5925OEWT-PA7-LEM | [5 empty] | 1 | 925 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2005 | KL-20200711-11 | 53510912 | Access | 0 | CAT 14G | 185 | 8.5 | HR | 139 | 0 |  |  | 1572.5 | 204.425 | 1776.925 | 2020-07-11 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 Road from Km17 to Km23 | 9 | E-091 to E-102 | 600 Road` | 0 | 44027 |  | 50 | 44028 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2005KL-20200711-11CAT 14G8.51572.5 | KABI LAKE FOREST PRODUCTS LTD2005KL-20200711-11CAT 14G8.51572.5OEWT-PA7-LEM | [5 empty] | 1 | 1572.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2099 | KL-20200717-11 | 53510912 | Access | 0 | CAT 14G | 185 | 3 | HR | 139 | 0 |  |  | 555 | 72.15 | 627.15 | 2020-07-17 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade E106 Access Road | 9 | E091-E106 | 600 Road | 0 | 44034 |  | 15 | 44034 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2099KL-20200717-11CAT 14G3555 | KABI LAKE FOREST PRODUCTS LTD2099KL-20200717-11CAT 14G3555OEWT-PA7-LEM | [5 empty] | 1 | 555 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2176 | KL-20200703-1 | 53510912 | Access | 0 | CAT 14G | 185 | 3 | HR | 139 | 0 |  |  | 555 | 72.15 | 627.15 | 2020-07-03 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade AU1 Access to E-126/E-124 | 9 | E-091 to E-102 | 600 road | 0 | 44020 |  | 50 | 44020 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2176KL-20200703-1CAT 14G3555 | KABI LAKE FOREST PRODUCTS LTD2176KL-20200703-1CAT 14G3555OEWT-PA7-LEM | [5 empty] | 1 | 555 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2180 | KL-20200703-5 | 53510912 | Access | 0 | CAT 14G | 185 | 5.5 | HR | 139 | 0 |  |  | 1017.5 | 132.275 | 1149.775 | 2020-07-03 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 road from 2 Km to 9 Km | 9 | E-091 to E-102 | 600 Road | 0 | 44020 |  | 50 | 44020 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2180KL-20200703-5CAT 14G5.51017.5 | KABI LAKE FOREST PRODUCTS LTD2180KL-20200703-5CAT 14G5.51017.5OEWT-PA7-LEM | [5 empty] | 1 | 1017.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2237 | KL-20200723-13 | 53510912 | Access | 0 | CAT 14G | 185 | 12 | HR | 139 | 0 |  |  | 2220 | 288.6 | 2508.6 | 2020-07-23 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Road from Hwy to Km 10 | 9 | E-091 to E-102 | 600 Road | 0 | 44040 |  | 15 | 44040 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2237KL-20200723-13CAT 14G122220 | KABI LAKE FOREST PRODUCTS LTD2237KL-20200723-13CAT 14G122220OEWT-PA7-LEM | [5 empty] | 1 | 2220 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2305 | KL-20200729-8 | 53510912 | Access | 0 | CAT 14G | 185 | 10 | HR | 139 | 0 |  |  | 1850 | 240.5 | 2090.5 | 2020-07-29 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 road from Hwy to Km 11 | 9 | E091-E102 | 600 Road | 0 | 44047 |  | 14 | 44048 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD2305KL-20200729-8CAT 14G101850 | KABI LAKE FOREST PRODUCTS LTD2305KL-20200729-8CAT 14G101850OEWT-PA8-LEM | [5 empty] | 1 | 1850 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2322 | KL-20200730-14 | 53510912 | Access | 0 | CAT 14G | 185 | 12 | HR | 139 | 0 |  |  | 2220 | 288.6 | 2508.6 | 2020-07-30 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Hills on 600 road 11km to 53km | 9 | E091-E102 | 600 Road | 0 | 44048 |  | 50 | 44049 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2322KL-20200730-14CAT 14G122220 | KABI LAKE FOREST PRODUCTS LTD2322KL-20200730-14CAT 14G122220OEWT-PA8-LEM | [5 empty] | 1 | 2220 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2336 | KL-20200731-11 | 53510912 | Access | 0 | CAT 14G | 185 | 6 | HR | 139 | 0 |  |  | 1110 | 144.3 | 1254.3 | 2020-07-31 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road 53km to 49km | 9 | E091-E102. | 600 Road | 0 | 44048 |  | 50 | 44049 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2336KL-20200731-11CAT 14G61110 | KABI LAKE FOREST PRODUCTS LTD2336KL-20200731-11CAT 14G61110OEWT-PA8-LEM | [5 empty] | 1 | 1110 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2396 | KL-20200808-3 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-08-08 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44057 |  | 47 | 44057 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2396KL-20200808-3CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD2396KL-20200808-3CAT 14G112035OEWT-PA8-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2405 | KL-20200809-5 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-08-09 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44057 |  | 47 | 44058 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2405KL-20200809-5CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD2405KL-20200809-5CAT 14G112035OEWT-PA8-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2412 | KL-20200810-5 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-08-10 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 Road | 9 | E091-E102 | 600 Road | 0 | 44057 |  | 47 | 44058 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2412KL-20200810-5CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD2412KL-20200810-5CAT 14G112035OEWT-PA8-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2419 | KL-20200811-2 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-08-11 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44060 |  | 47 | 44061 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2419KL-20200811-2CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD2419KL-20200811-2CAT 14G112035OEWT-PA8-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2425 | KL-20200812-1 | 53510912 | Access | 0 | CAT 14G | 185 | 7 | HR | 139 | 0 |  |  | 1295 | 168.35 | 1463.35 | 2020-08-12 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 Road!! | 9 | E091-E102 | 600 Road | 0 | 44060 |  | 47 | 44061 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2425KL-20200812-1CAT 14G71295 | KABI LAKE FOREST PRODUCTS LTD2425KL-20200812-1CAT 14G71295OEWT-PA8-LEM | [5 empty] | 1 | 1295 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2435 | KL-20200813-2 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-08-13 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44062 |  | 47 | 44062 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2435KL-20200813-2CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD2435KL-20200813-2CAT 14G112035OEWT-PA8-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2444 | KL-20200814-4 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-08-14 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44062 |  | 47 | 44062 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2444KL-20200814-4CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD2444KL-20200814-4CAT 14G112035OEWT-PA8-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2449 | KL-20200815-4 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-08-15 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Continue grading 600 Road @ 30 Km to 35 Km | 9 | E091-E102 | 600 Road | 0 | 44062 |  | 15 | 44066 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2449KL-20200815-4CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD2449KL-20200815-4CAT 14G112035OEWT-PA8-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2457 | KL-20200816-4 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-08-16 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E091-E | 600 Road | 0 | 44062 |  | 15 | 44066 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2457KL-20200816-4CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD2457KL-20200816-4CAT 14G112035OEWT-PA8-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2464 | KL-20200817-4 | 53510912 | Access | 0 | CAT 14G | 185 | 8 | HR | 139 | 0 |  |  | 1480 | 192.4 | 1672.4 | 2020-08-17 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E091-E102 | 600 Road | 0 | 44063 |  | 15 | 44064 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2464KL-20200817-4CAT 14G81480 | KABI LAKE FOREST PRODUCTS LTD2464KL-20200817-4CAT 14G81480OEWT-PA8-LEM | [5 empty] | 1 | 1480 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2585 | KL-20200824-6 | 53510912 | Access | 0 | CAT 14G | 185 | 5 | HR | 139 | 0 |  |  | 925 | 120.25 | 1045.25 | 2020-08-24 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road from 9 to 13 Km | 9 | E-091 to E-102 | 600 Road | 0 | 44069 |  | 15 | 44071 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2585KL-20200824-6CAT 14G5925 | KABI LAKE FOREST PRODUCTS LTD2585KL-20200824-6CAT 14G5925OEWT-PA8-LEM | [5 empty] | 1 | 925 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2597 | KL-20200825-6 | 53510912 | Access | 0 | CAT 14G | 185 | 9 | HR | 139 | 0 |  |  | 1665 | 216.45 | 1881.45 | 2020-08-25 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44072 |  | 15 | 44074 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2597KL-20200825-6CAT 14G91665 | KABI LAKE FOREST PRODUCTS LTD2597KL-20200825-6CAT 14G91665OEWT-PA8-LEM | [5 empty] | 1 | 1665 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2612 | KL-20200829-3 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-08-29 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44076 |  | 15 | 44077 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2612KL-20200829-3CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD2612KL-20200829-3CAT 14G112035OEWT-PA9-Lem-R1 | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2618 | KL-20200830-1 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-08-30 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44076 |  | 47 | 44077 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2618KL-20200830-1CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD2618KL-20200830-1CAT 14G112035OEWT-PA9-Lem-R1 | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2635 | KL-20200831-7 | 53510912 | Access | 0 | CAT 14G | 185 | 10 | HR | 139 | 0 |  |  | 1850 | 240.5 | 2090.5 | 2020-08-31 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E091-E102 | 600 Road | 0 | 44084 |  | 50 | 44087 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2635KL-20200831-7CAT 14G101850 | KABI LAKE FOREST PRODUCTS LTD2635KL-20200831-7CAT 14G101850OEWT-PA9-Lem-R1 | [5 empty] | 1 | 1850 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2647 | KL-20200901-10 | 53510912 | Access | 0 | CAT 14G | 185 | 8 | HR | 139 | 0 |  |  | 1480 | 192.4 | 1672.4 | 2020-09-01 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road Km 31 -33 | 9 | E092-E109 | 600 Road | 0 | 44084 |  | 50 | 44087 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2647KL-20200901-10CAT 14G81480 | KABI LAKE FOREST PRODUCTS LTD2647KL-20200901-10CAT 14G81480OEWT-PA9-Lem-R1 | [5 empty] | 1 | 1480 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2677 | KL-20200903-14 | 53510912 | Access | 0 | CAT 14G | 185 | 8 | HR | 139 | 0 |  |  | 1480 | 192.4 | 1672.4 | 2020-09-03 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E091-E102 | 600 Road | 0 | 44084 |  | 50 | 44088 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2677KL-20200903-14CAT 14G81480 | KABI LAKE FOREST PRODUCTS LTD2677KL-20200903-14CAT 14G81480OEWT-PA9-Lem-R1 | [5 empty] | 1 | 1480 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2689 | KL-20200904-10 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-09-04 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44088 |  | 50 | 44089 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2689KL-20200904-10CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD2689KL-20200904-10CAT 14G112035OEWT-PA9-Lem-R1 | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2736 | KL-20200907-13 | 53510912 | Access | 0 | CAT 14G | 185 | 8 | HR | 139 | 0 |  |  | 1480 | 192.4 | 1672.4 | 2020-09-07 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44089 |  | 15 | 44092 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2736KL-20200907-13CAT 14G81480 | KABI LAKE FOREST PRODUCTS LTD2736KL-20200907-13CAT 14G81480OEWT-PA9-Lem-R1 | [5 empty] | 1 | 1480 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2754 | KL-20200908-15 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-09-08 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44089 |  | 15 | 44092 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2754KL-20200908-15CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD2754KL-20200908-15CAT 14G112035OEWT-PA9-Lem-R1 | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2778 | KL-20200909-19 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-09-09 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44092 |  | 15 | 44092 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2778KL-20200909-19CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD2778KL-20200909-19CAT 14G112035OEWT-PA9-Lem-R1 | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2802 | KL-20200910-18 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-09-10 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44091 |  | 15 | 44094 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2802KL-20200910-18CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD2802KL-20200910-18CAT 14G112035OEWT-PA9-Lem-R1 | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2853 | KL-20200911-20 | 53510912 | Access | 0 | CAT 14G | 185 | 5 | HR | 139 | 0 |  |  | 925 | 120.25 | 1045.25 | 2020-09-11 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44094 |  | 15 | 44095 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2853KL-20200911-20CAT 14G5925 | KABI LAKE FOREST PRODUCTS LTD2853KL-20200911-20CAT 14G5925OEWT-PA9-Lem-R1 | [5 empty] | 1 | 925 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2968 | KL-20200916-11 | 53510912 | Access | 0 | CAT 14G | 185 | 10 | HR | 139 | 0 |  |  | 1850 | 240.5 | 2090.5 | 2020-09-16 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44096 |  | 15 | 44098 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2968KL-20200916-11CAT 14G101850 | KABI LAKE FOREST PRODUCTS LTD2968KL-20200916-11CAT 14G101850OEWT-PA9-Lem-R1 | [5 empty] | 1 | 1850 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3131 | KL-20200922-16 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-09-22 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44103 |  | 15 | 44103 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3131KL-20200922-16CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD3131KL-20200922-16CAT 14G112035OEWT-PA9-Lem-R1 | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3171 | KL-20200923-12 | 53510912 | Access | 0 | CAT 14G | 185 | 12 | HR | 139 | 0 |  |  | 2220 | 288.6 | 2508.6 | 2020-09-23 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44103 |  | 15 | 44104 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3171KL-20200923-12CAT 14G122220 | KABI LAKE FOREST PRODUCTS LTD3171KL-20200923-12CAT 14G122220OEWT-PA9-Lem-R1 | [5 empty] | 1 | 2220 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3268 | KL-20200927-12 | 53510912 | Access | 0 | CAT 14G | 185 | 4 | HR | 139 | 0 |  |  | 740 | 96.2 | 836.2 | 2020-09-27 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 43900 |  | 53 | 43900 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD3268KL-20200927-12CAT 14G4740 | KABI LAKE FOREST PRODUCTS LTD3268KL-20200927-12CAT 14G4740OEWT-PA10-LEM | [5 empty] | 1 | 740 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3289 | KL-20200928-12 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-09-28 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E091-E102 | 600 road | 0 | 44109 |  | 15 | 44121 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3289KL-20200928-12CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD3289KL-20200928-12CAT 14G112035OEWT-PA10-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3320 | KL-20200929-11 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-09-29 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44109 |  | 50 | 44115 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3320KL-20200929-11CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD3320KL-20200929-11CAT 14G112035OEWT-PA10-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3487 | KL-20201005-12 | 53510912 | Access | 0 | CAT 14G | 185 | 2 | HR | 139 | 0 |  |  | 370 | 48.1 | 418.1 | 2020-10-05 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44123 |  | 15 | 44125 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3487KL-20201005-12CAT 14G2370 | KABI LAKE FOREST PRODUCTS LTD3487KL-20201005-12CAT 14G2370OEWT-PA10-LEM | [5 empty] | 1 | 370 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3517 | KL-20201006-13 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-10-06 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44124 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3517KL-20201006-13CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD3517KL-20201006-13CAT 14G112035OEWT-PA10-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3624 | KL-20201009-13 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-10-09 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3624KL-20201009-13CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD3624KL-20201009-13CAT 14G112035OEWT-PA10-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3647 | KL-20201010-11 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-10-10 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3647KL-20201010-11CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD3647KL-20201010-11CAT 14G112035OEWT-PA10-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3717 | KL-20201013-11 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-10-13 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44129 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3717KL-20201013-11CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD3717KL-20201013-11CAT 14G112035OEWT-PA10-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3767 | KL-20201015-15 | 53510912 | Access | 0 | CAT 14G | 185 | 5 | HR | 139 | 0 |  |  | 925 | 120.25 | 1045.25 | 2020-10-15 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44130 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3767KL-20201015-15CAT 14G5925 | KABI LAKE FOREST PRODUCTS LTD3767KL-20201015-15CAT 14G5925OEWT-PA10-LEM | [5 empty] | 1 | 925 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3845 | KL-20201019-10 | 53510912 | Access | 0 | CAT 14G | 185 | 5 | HR | 139 | 0 |  |  | 925 | 120.25 | 1045.25 | 2020-10-19 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44130 |  | 50 | 44133 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3845KL-20201019-10CAT 14G5925 | KABI LAKE FOREST PRODUCTS LTD3845KL-20201019-10CAT 14G5925OEWT-PA10-LEM | [5 empty] | 1 | 925 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3877 | KL-20201021-6 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-10-21 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44131 |  | 15 | 44133 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3877KL-20201021-6CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD3877KL-20201021-6CAT 14G112035OEWT-PA10-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3888 | KL-20201023-7 | 53510912 | Access | 0 | CAT 14G | 185 | 7 | HR | 139 | 0 |  |  | 1295 | 168.35 | 1463.35 | 2020-10-23 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44133 |  | 50 | 44134 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3888KL-20201023-7CAT 14G71295 | KABI LAKE FOREST PRODUCTS LTD3888KL-20201023-7CAT 14G71295OEWT-PA10-LEM | [5 empty] | 1 | 1295 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3914 | KL-20201022-7 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-10-22 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44133 |  | 15 | 44134 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3914KL-20201022-7CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD3914KL-20201022-7CAT 14G112035OEWT-PA10-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3990 | KL-20201026-15 | 53510912 | Access | 0 | CAT 14G | 185 | 12 | HR | 139 | 0 |  |  | 2220 | 288.6 | 2508.6 | 2020-10-26 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E091-E102 | 600 Rd | 0 | 44147 |  | 50 | 44161 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3990KL-20201026-15CAT 14G122220 | KABI LAKE FOREST PRODUCTS LTD3990KL-20201026-15CAT 14G122220OEWT-PA11-LEM | [5 empty] | 1 | 2220 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4005 | KL-20201027-10 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-10-27 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E091-E102 | 600 Rd | 0 | 44147 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4005KL-20201027-10CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD4005KL-20201027-10CAT 14G112035OEWT-PA11-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4021 | KL-20201028-8 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-10-28 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E091-E102 | 600 Rd | 0 | 44147 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4021KL-20201028-8CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD4021KL-20201028-8CAT 14G112035OEWT-PA11-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4048 | KL-20201029-14 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-10-29 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E091-E102 | 600 Rd | 0 | 44152 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4048KL-20201029-14CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD4048KL-20201029-14CAT 14G112035OEWT-PA11-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4199 | KL-20201106-11 | 53510912 | Access | 0 | CAT 14G | 185 | 8 | HR | 139 | 0 |  |  | 1480 | 192.4 | 1672.4 | 2020-11-06 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road and 100 road | 9 | E091-E102 | 600 Road | 0 | 44162 |  | 48 | 44162 | [5 empty] | Larse Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4199KL-20201106-11CAT 14G81480 | KABI LAKE FOREST PRODUCTS LTD4199KL-20201106-11CAT 14G81480OEWT-PA11-LEM | [5 empty] | 1 | 1480 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4263 | KL-20201109-12 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-11-09 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E091-E102 | 600 Road | 0 | 44164 |  | 15 | 44171 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4263KL-20201109-12CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD4263KL-20201109-12CAT 14G112035OEWT-PA11-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4288 | KL-20201103-17 | 53510912 | Access | 0 | CAT 14G | 185 | 10 | HR | 139 | 0 |  |  | 1850 | 240.5 | 2090.5 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road, 700 road and 100 road | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 50 | 44167 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4288KL-20201103-17CAT 14G101850 | KABI LAKE FOREST PRODUCTS LTD4288KL-20201103-17CAT 14G101850OEWT-PA11-LEM | [5 empty] | 1 | 1850 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4298 | KL-20201110-8 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-11-10 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Rd 2 graders | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44168 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4298KL-20201110-8CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD4298KL-20201110-8CAT 14G112035OEWT-PA11-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4316 | KL-20201111-12 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-11-11 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road and 100 Road | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44170 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4316KL-20201111-12CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD4316KL-20201111-12CAT 14G112035OEWT-PA11-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4329 | KL-20201112-12 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-11-12 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road and 100 Road | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44168 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4329KL-20201112-12CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD4329KL-20201112-12CAT 14G112035OEWT-PA11-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4340 | KL-20201113-8 | 53510912 | Access | 0 | CAT 14G | 185 | 12 | HR | 139 | 0 |  |  | 2220 | 288.6 | 2508.6 | 2020-11-13 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600rd and 100rd | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44170 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4340KL-20201113-8CAT 14G122220 | KABI LAKE FOREST PRODUCTS LTD4340KL-20201113-8CAT 14G122220OEWT-PA11-LEM | [5 empty] | 1 | 2220 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4397 | KL-20201115-11 | 53510912 | Access | 0 | CAT 14G | 185 | 12 | HR | 139 | 0 |  |  | 2220 | 288.6 | 2508.6 | 2020-11-15 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road and 100 Road. | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 53 | 44171 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4397KL-20201115-11CAT 14G122220 | KABI LAKE FOREST PRODUCTS LTD4397KL-20201115-11CAT 14G122220OEWT-PA11-LEM | [5 empty] | 1 | 2220 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4416 | KL-20201116-15 | 53510912 | Access | 0 | CAT 14G | 185 | 15.5 | HR | 139 | 0 |  |  | 2867.5 | 372.775 | 3240.275 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road, 100 road, Paint Lake 2 Rd | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4416KL-20201116-15CAT 14G15.52867.5 | KABI LAKE FOREST PRODUCTS LTD4416KL-20201116-15CAT 14G15.52867.5OEWT-PA11-LEM | [5 empty] | 1 | 2867.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4431 | KL-20201117-10 | 53510912 | Access | 0 | CAT 14G | 185 | 12 | HR | 139 | 0 |  |  | 2220 | 288.6 | 2508.6 | 2020-11-17 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 rd, 100 rd, and Paint Lake 2 road | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4431KL-20201117-10CAT 14G122220 | KABI LAKE FOREST PRODUCTS LTD4431KL-20201117-10CAT 14G122220OEWT-PA11-LEM | [5 empty] | 1 | 2220 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4575 | KL-20201123-13 | 53510912 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-11-23 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Contine grading 600 road and 100 roadand access roads in WF 9 | 9 | E091-E102 | 600 road | 0 | 44172 |  | 15 | 44176 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4575KL-20201123-13CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD4575KL-20201123-13CAT 14G112035OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4607 | KL-20201124-10 | 53510912 | Access | 0 | CAT 14G | 185 | 10 | HR | 139 | 0 |  |  | 1850 | 240.5 | 2090.5 | 2020-11-24 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road, 100 road and access roads in WF 9 | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4607KL-20201124-10CAT 14G101850 | KABI LAKE FOREST PRODUCTS LTD4607KL-20201124-10CAT 14G101850OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1850 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4634 | KL-20201125-11 | 53510912 | Access | 0 | CAT 14G | 185 | 10 | HR | 139 | 0 |  |  | 1850 | 240.5 | 2090.5 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600rd, 100rd, and access rds in WF9 | 9 | E091-E102 | 600 Road | 0 | 44173 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4634KL-20201125-11CAT 14G101850 | KABI LAKE FOREST PRODUCTS LTD4634KL-20201125-11CAT 14G101850OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1850 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6953 | KL-20210519-4 | 53510912 | Access | 0 | CAT 14G | 185 | 11.5 | HR | 139 |  |  |  | 2127.5 | 276.575 | 2404.075 | 2021-05-19 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 14M grader started road maintenance from Km 1 to Km 18 on 600 road labourers spotted pickup @Km 18 for grader operator (revised) | 9 | E091-E102 | 600 Road | 0 | 44345 |  | 14 | 44352 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD6953KL-20210519-4CAT 14G11.52127.5 | KABI LAKE FOREST PRODUCTS LTD6953KL-20210519-4CAT 14G11.52127.5OEWT-PA17-LEM | [5 empty] | 1 | 2127.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6962 | KL-20210520-4 | 53510912 | Access | 0 | CAT 14G | 185 | 11.5 | HR | 139 | 0 |  |  | 2127.5 | 276.575 | 2404.075 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 14M grader continuing grading of 600 road and repairing small wash out/ labourer spotting pickup @ 22km for grader operator ( revised ) | 9 | E091-E102 | 600 Road | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD6962KL-20210520-4CAT 14G11.52127.5 | KABI LAKE FOREST PRODUCTS LTD6962KL-20210520-4CAT 14G11.52127.5OEWT-PA17-LEM | [5 empty] | 1 | 2127.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6968 | KL-20210521-3 | 53510912 | Access | 0 | CAT 14G | 185 | 8.5 | HR | 139 | 0 |  |  | 1572.5 | 204.425 | 1776.925 | 2021-05-21 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 14M grader continuing grading of 600 Road and repairing small wash outs | 9 | E091-E102 | 600 Road | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD6968KL-20210521-3CAT 14G8.51572.5 | KABI LAKE FOREST PRODUCTS LTD6968KL-20210521-3CAT 14G8.51572.5OEWT-PA17-LEM | [5 empty] | 1 | 1572.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6985 | KL-20210525-3 | 53510912 | Access | 0 | CAT 14G | 185 | 4.5 | HR | 139 | 0 |  |  | 832.5 | 108.225 | 940.725 | 2021-05-25 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 14M grader continuing grading of 600 road and repairing small washouts | 9 | E091-E102 | 600 Road | 0 | 44348 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 09 | KABI LAKE FOREST PRODUCTS LTD6985KL-20210525-3CAT 14G4.5832.5 | KABI LAKE FOREST PRODUCTS LTD6985KL-20210525-3CAT 14G4.5832.5OEWT-PA17-LEM | [5 empty] | 1 | 832.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5143 | KL-20201222-6 | 53511011 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-12-22 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Paint Lake 2 Road | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44200 |  | 56 | 44213 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD5143KL-20201222-6CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD5143KL-20201222-6CAT 14G112035OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5181 | KL-20201231-4 | 53511011 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2020-12-31 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Paint lake road 2 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44204 |  | 56 | 44216 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD5181KL-20201231-4CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD5181KL-20201231-4CAT 14G112035OEWT-PA13-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5188 | KL-20210101-1 | 53511011 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2021-01-01 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Paint Lake road 2 and 600 Road | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44204 |  | 56 | 44216 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD5188KL-20210101-1CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD5188KL-20210101-1CAT 14G112035OEWT-PA13-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5899 | KL-20210214-3 | 53511011 | Access | 0 | CAT 14G | 185 | 8 | HR | 139 | 0 |  |  | 1480 | 192.4 | 1672.4 | 2021-02-14 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Skid corduroy, grade Paint Lake Road 2, unload and load legos, load and haul Gravel. Loading , Hauling and spreading gravel, drag in 50' bridge WC 11190,- | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44245 |  | 50 | 44251 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5899KL-20210214-3CAT 14G81480 | KABI LAKE FOREST PRODUCTS LTD5899KL-20210214-3CAT 14G81480OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1480 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5908 | KL-20210215-3 | 53511011 | Access | 0 | CAT 14G | 185 | 4 | HR | 139 | 0 |  |  | 740 | 96.2 | 836.2 | 2021-02-15 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Skid corduroy, grade Paint Lake Road 2, load and haul legos, load and haul gravel, sand hills, install 800mm culvert WC 11160 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44249 |  | 50 | 44251 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5908KL-20210215-3CAT 14G4740 | KABI LAKE FOREST PRODUCTS LTD5908KL-20210215-3CAT 14G4740OEWT-PA14-Lem-R1 | [5 empty] | 1 | 740 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6336 | KL-20210315-4 | 53511011 | Access | 0 | CAT 14G | 185 | 4 | HR | 139 | 0 |  |  | 740 | 96.2 | 836.2 | 2021-03-15 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Scarifying hills and corners on Paint Lake Road 2 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44279 |  | 56 | 44280 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6336KL-20210315-4CAT 14G4740 | KABI LAKE FOREST PRODUCTS LTD6336KL-20210315-4CAT 14G4740OEWT PA15-LEM | [5 empty] | 1 | 740 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7670 | KL-20211211-1 | 53511011 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2021-12-11 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from 49Km to 40Km. Grader 1 working on snow removal 0Km to 23Km for Crane demob. Grader 2 scarifying from 49 to 45Km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7670KL-20211211-1CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD7670KL-20211211-1CAT 14G112035OEWT-PA24-LEM | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7681 | KL-20211212-1 | 53511011 | Access | 0 | CAT 14G | 185 | 10.5 | HR | 139 | 0 |  |  | 1942.5 | 252.525 | 2195.025 | 2021-12-12 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working from Km 2 to Km 49 for scarifying and clearing pull offs | 10 | F066-F118 | Paint Lake 2 | 0 | 44551 |  | 61 | 44561 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7681KL-20211212-1CAT 14G10.51942.5 | KABI LAKE FOREST PRODUCTS LTD7681KL-20211212-1CAT 14G10.51942.5OEWT-PA24-LEM | [5 empty] | 1 | 1942.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4524 | KL-20201102-17 | 53511012 | Access | 0 | CAT 14G | 185 | 10 | HR | 139 | 0 |  |  | 1850 | 240.5 | 2090.5 | 2020-11-02 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E091-E102 | 600 Road | 0 | 44174 |  | 15 | 44175 | [5 empty] | Martin Hunt | 10 | KABI LAKE FOREST PRODUCTS LTD4524KL-20201102-17CAT 14G101850 | KABI LAKE FOREST PRODUCTS LTD4524KL-20201102-17CAT 14G101850OEWT-PA11-LEM | [5 empty] | 1 | 1850 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6990 | KL-20210526-3 | 53511012 | Access | 0 | CAT 14G | 185 | 7 | HR | 139 | 0 |  |  | 1295 | 168.35 | 1463.35 | 2021-05-26 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator working on road maintenance to F40/ Grader starting on Paint Lake Road 2 to Km 4 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD6990KL-20210526-3CAT 14G71295 | KABI LAKE FOREST PRODUCTS LTD6990KL-20210526-3CAT 14G71295OEWT-PA18-Lem | [5 empty] | 1 | 1295 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6992 | KL-20210527-2 | 53511012 | Access | 0 | CAT 14G | 185 | 11 | HR | 139 | 0 |  |  | 2035 | 264.55 | 2299.55 | 2021-05-27 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator working on road maintenance to F040 / Grader working on Paint Lake Road 2 at km4 to km 10 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD6992KL-20210527-2CAT 14G112035 | KABI LAKE FOREST PRODUCTS LTD6992KL-20210527-2CAT 14G112035OEWT-PA18-Lem | [5 empty] | 1 | 2035 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6994 | KL-20210528-2 | 53511012 | Access | 0 | CAT 14G | 185 | 10.5 | HR | 139 | 0 |  |  | 1942.5 | 252.525 | 2195.025 | 2021-05-28 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator working on road maintenance from Km 15.5 to Km 19/ Grader working on Paint Lake Road 2 at Km 7 to 12 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD6994KL-20210528-2CAT 14G10.51942.5 | KABI LAKE FOREST PRODUCTS LTD6994KL-20210528-2CAT 14G10.51942.5OEWT-PA18-Lem | [5 empty] | 1 | 1942.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7001 | KL-20210531-3 | 53511012 | Access | 0 | CAT 14G | 185 | 10.5 | HR | 139 | 0 |  |  | 1942.5 | 252.525 | 2195.025 | 2021-05-31 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator working on road maintenance and drainage from Km 16.5 to Km 19 /grader working on Paint Lake Road 2 from Km 12 to KM4 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44358 |  | 36 | 44360 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7001KL-20210531-3CAT 14G10.51942.5 | KABI LAKE FOREST PRODUCTS LTD7001KL-20210531-3CAT 14G10.51942.5OEWT-PA18-Lem | [5 empty] | 1 | 1942.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7004 | KL-20210601-3 | 53511012 | Access | 0 | CAT 14G | 185 | 6 | HR | 139 | 0 |  |  | 1110 | 144.3 | 1254.3 | 2021-06-01 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator continue working on road maintenance and drainage from km 17 to km 18/ Grader finishing on Paint Lake Road 2 to Km 0 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44358 |  | 14 | 44359 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7004KL-20210601-3CAT 14G61110 | KABI LAKE FOREST PRODUCTS LTD7004KL-20210601-3CAT 14G61110OEWT-PA18-Lem | [5 empty] | 1 | 1110 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7691 | KL-20211214-3 | 53511111 | Access | 0 | CAT 14G | 185 | 4 | HR | 139 | 0 |  |  | 740 | 96.2 | 836.2 | 2021-12-14 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Scarifying hills and corners from Km 12 to Hwy 17/Dozer starting snow removal from Hensen road to F128 | 11 | F118-F127 | Henson | 0 | 44551 |  | 61 | 44560 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7691KL-20211214-3CAT 14G4740 | KABI LAKE FOREST PRODUCTS LTD7691KL-20211214-3CAT 14G4740OEWT-PA24-LEM | [5 empty] | 1 | 740 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1124 | KL-20200222-4 | 53510711 | Access | 0 | CAT 140M | 179 | 2 | HR | 135 | 0 |  |  | 358 | 46.54 | 404.54 | 2020-02-22 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | low snow on Black River East road | 7 | D-032 to D-055 | Black River | 0 | 43887 |  | 43 | 43889 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1124KL-20200222-4CAT 140M2358 | KABI LAKE FOREST PRODUCTS LTD1124KL-20200222-4CAT 140M2358OEWT-PA2-LEM-R1 | [5 empty] | 1 | 358 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1125 | KL-20200222-5 | 53510711 | Access | 0 | CAT 140M | 179 | 2 | HR | 135 | 0 |  |  | 358 | 46.54 | 404.54 | 2020-02-22 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow for access on Wabakoba Creek | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 43887 |  | 43 | 43889 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1125KL-20200222-5CAT 140M2358 | KABI LAKE FOREST PRODUCTS LTD1125KL-20200222-5CAT 140M2358OEWT-PA2-LEM-R1 | [5 empty] | 1 | 358 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1129 | KL-20200223-3 | 53510711 | Access | 0 | CAT 140M | 179 | 2 | HR | 135 | 0 |  |  | 358 | 46.54 | 404.54 | 2020-02-23 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow and maintain road | 7 | D-032 to D-055 | Black River | 0 | 43887 |  | 43 | 43889 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1129KL-20200223-3CAT 140M2358 | KABI LAKE FOREST PRODUCTS LTD1129KL-20200223-3CAT 140M2358OEWT-PA2-LEM-R1 | [5 empty] | 1 | 358 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1291 | KL-20200313-1 | 53510711 | Access | 0 | CAT 140M | 179 | 3 | HR | 135 | 0 |  |  | 537 | 69.81 | 606.81 | 2020-03-13 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Grade road from HWY to D-038 and D-032 | 7 | D-032 to D-055 | Black River | 0 | 43908 |  | 42 | 43914 | [5 empty] | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1291KL-20200313-1CAT 140M3537 | KABI LAKE FOREST PRODUCTS LTD1291KL-20200313-1CAT 140M3537OEWT-PA3-LEM | [5 empty] | 1 | 537 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1296 | KL-20200313-3 | 53510711 | Access | 0 | CAT 140M | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2020-03-13 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade road from HWY and D038 to D054 | 7 | D-032 to D-055 | Black River | 0 | 43907 |  | 42 | 43914 | [5 empty] | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1296KL-20200313-3CAT 140M61074 | KABI LAKE FOREST PRODUCTS LTD1296KL-20200313-3CAT 140M61074OEWT-PA3-LEM | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1303 | KL-20200314-2 | 53510711 | Access | 0 | CAT 140M | 179 | 3 | HR | 135 | 0 |  |  | 537 | 69.81 | 606.81 | 2020-03-14 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow to open road after snow. | 7 | D-018 to D-031 | Pic River West | 0 | 43908 |  | 42 | 43915 | [5 empty] | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1303KL-20200314-2CAT 140M3537 | KABI LAKE FOREST PRODUCTS LTD1303KL-20200314-2CAT 140M3537OEWT-PA3-LEM | [5 empty] | 1 | 537 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1305 | KL-20200314-4 | 53510711 | Access | 0 | CAT 140M | 179 | 3 | HR | 135 | 0 |  |  | 537 | 69.81 | 606.81 | 2020-03-14 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open road after snow | 7 | D-018 to D-031 | Pic River East | 0 | 43908 |  | 42 | 43915 | [5 empty] | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1305KL-20200314-4CAT 140M3537 | KABI LAKE FOREST PRODUCTS LTD1305KL-20200314-4CAT 140M3537OEWT-PA3-LEM | [5 empty] | 1 | 537 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1306 | KL-20200314-5 | 53510711 | Access | 0 | CAT 140M | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2020-03-14 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open road after snow | 7 | D-032 to D-055 | Black River | 0 | 43908 |  | 42 | 43915 | [5 empty] | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1306KL-20200314-5CAT 140M4716 | KABI LAKE FOREST PRODUCTS LTD1306KL-20200314-5CAT 140M4716OEWT-PA3-LEM | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1352 | KL-20200322-1 | 53510711 | Access | 0 | CAT 140M | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2020-03-22 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | PLOW SNOW IN ACCESS ROADS | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 43915 |  | 46 | 43919 | [5 empty] | Dave Ofukany | 07 | KABI LAKE FOREST PRODUCTS LTD1352KL-20200322-1CAT 140M61074 | KABI LAKE FOREST PRODUCTS LTD1352KL-20200322-1CAT 140M61074OEWT-PA3-LEM | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1404 | KL-20200328-2 | 53510712 | Access | 0 | CAT 140M | 179 | 2 | HR | 135 | 0 |  |  | 358 | 46.54 | 404.54 | 2020-03-28 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Push snow banks back on access road , scrape road and grade | 7 | D-119 to D-141 | Alder Creek | 0 | 43925 |  | 45 | 43924 | [5 empty] | Howard Beaudet | 07 | KABI LAKE FOREST PRODUCTS LTD1404KL-20200328-2CAT 140M2358 | KABI LAKE FOREST PRODUCTS LTD1404KL-20200328-2CAT 140M2358OEWT PA4-LEM-R1 | [5 empty] | 1 | 358 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1886 | KL-20200626-7 | 53510712 | Access | 0 | CAT 140M | 179 | 3 | HR | 135 | 0 |  |  | 537 | 69.81 | 606.81 | 2020-06-26 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade section on 100 road to 5km pit for gravel haul to Alder Creek | 7 | D-119 to D-141 | Alder Creek | 0 | 44038 |  | 47 | 44014 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD1886KL-20200626-7CAT 140M3537 | KABI LAKE FOREST PRODUCTS LTD1886KL-20200626-7CAT 140M3537OEWT-PA7-LEM | [5 empty] | 1 | 537 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1055 | KL-20200211-13 | 53510811 | Access | 0 | CAT 140M | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2020-02-13 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Winter road maintenance. Plow open access to North Crocker Lake Rd | 8 | E-068 to E-076 | North Crockers Lake | 0 | 43878 |  | 42 | 43882 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1055KL-20200211-13CAT 140M4716 | KABI LAKE FOREST PRODUCTS LTD1055KL-20200211-13CAT 140M4716OEWT-PA2-LEM-R1 | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1309 | KL-20200316-3 | 53510811 | Access | 0 | CAT 140M | 179 | 3 | HR | 135 | 0 |  |  | 537 | 69.81 | 606.81 | 2020-03-16 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow road at Blue Cedar | 8 | E-077 to E-091 | Blue Cedar W | 0 | 43908 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1309KL-20200316-3CAT 140M3537 | KABI LAKE FOREST PRODUCTS LTD1309KL-20200316-3CAT 140M3537OEWT-PA3-LEM | [5 empty] | 1 | 537 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1318 | KL-20200317-3 | 53510811 | Access | 0 | CAT 140M | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow and maintain road | 8 | E086 - E092E-068 to E-076 | North Crockers Lake | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1318KL-20200317-3CAT 140M4716 | KABI LAKE FOREST PRODUCTS LTD1318KL-20200317-3CAT 140M4716OEWT-PA3-LEM | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1319 | KL-20200317-4 | 53510811 | Access | 0 | CAT 140M | 179 | 2 | HR | 135 | 0 |  |  | 358 | 46.54 | 404.54 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | CONTINUE TO OPEN ROAD TO ACCESS ROW | 8 | E-062 to E-067 | Buck Lake | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1319KL-20200317-4CAT 140M2358 | KABI LAKE FOREST PRODUCTS LTD1319KL-20200317-4CAT 140M2358OEWT-PA3-LEM | [5 empty] | 1 | 358 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5000 | KL-20201214-3 | 53510811 | Access | 0 | CAT 140M | 179 | 2 | HR | 135 | 0 |  |  | 358 | 46.54 | 404.54 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding and Grading Access to E073 for concrete haul as per Valard | 8 | E004-E016 | White Lake East | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD5000KL-20201214-3CAT 140M2358 | KABI LAKE FOREST PRODUCTS LTD5000KL-20201214-3CAT 140M2358OEWT-PA12-LEM-R1 | [5 empty] | 1 | 358 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5001 | KL-20201214-4 | 53510811 | Access | 0 | CAT 140M | 179 | 1 | HR | 135 | 0 |  |  | 179 | 23.27 | 202.27 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Access to E064 | 8 | E062-E067 | Buck Lake | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD5001KL-20201214-4CAT 140M1179 | KABI LAKE FOREST PRODUCTS LTD5001KL-20201214-4CAT 140M1179OEWT-PA12-LEM-R1 | [5 empty] | 1 | 179 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1322 | KL-20200317-7 | 53510812 | Access | 0 | CAT 140M | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | RV-40002 SPREAD GRAVEL; HAUL GRAVEL IN SOFT SOPT ACROSS HONI LINE AND TO GAIN ACCESS OVER ROCK IN EXISTING ENTRANCE RD | 8 | E-077 to E-091 | Blue Cedar W | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7CAT 140M4716 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7CAT 140M4716OEWT-PA3-LEM | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1093 | KL-20200213-2-R1 | 53510911 | Access | 0 | CAT 140M | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2020-02-13 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Standby should be 5 hours. | 23 | Approved | KABI LAKE - Standby - For Permits & Misc - ONGOING | 8002 | Winter Maintenance- continue to plow open 600 road | 9 | E-091-E121 | 600 Road | 0 | 43889 |  | 43 | 43896 | [5 empty] | Dean MacArthur | 09 | KABI LAKE FOREST PRODUCTS LTD1093KL-20200213-2-R1CAT 140M4716 | KABI LAKE FOREST PRODUCTS LTD1093KL-20200213-2-R1CAT 140M4716OEWT-PA3-LEM | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1093 | KL-20200213-2-R1 | 53510911 | Access | 0 | CAT 140M | 179 |  | HR | 135 | 7 |  |  | 945 | 122.85 | 1067.85 | 2020-02-13 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Standby should be 5 hours. | 23 | Approved | KABI LAKE - Standby - For Permits & Misc - ONGOING | 8002 | Winter Maintenance- continue to plow open 600 road | 9 | E-091-E121 | 600 Road | 0 | 43889 |  | 43 | 43896 | [5 empty] | Dean MacArthur | 09 | KABI LAKE FOREST PRODUCTS LTD1093KL-20200213-2-R1CAT 140M945 | KABI LAKE FOREST PRODUCTS LTD1093KL-20200213-2-R1CAT 140M945OEWT-PA3-LEM | [5 empty] | 1 | 945 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1178 | KL-20200227-3 | 53510911 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-02-27 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 600 Rd winter road maintenance - continue to open 600 rd @ 22km | 9 | E091-E121 | 600 Road | 0 | 43894 |  | 43 | 43896 | [5 empty] | Dean MacArthur | 09 | KABI LAKE FOREST PRODUCTS LTD1178KL-20200227-3CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD1178KL-20200227-3CAT 140M111969OEWT-PA3-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1189 | KL-20200229-3 | 53510911 | Access | 0 | CAT 140M | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2020-02-29 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 600 Rd - open 600 road to 32KM | 9 | E091-E102 | 600 Road | 0 | 43896 |  | 45 | 43914 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1189KL-20200229-3CAT 140M81432 | KABI LAKE FOREST PRODUCTS LTD1189KL-20200229-3CAT 140M81432OEWT-PA3-LEM | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1197 | KL-20200301-5 | 53510911 | Access | 0 | CAT 140M | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2020-03-01 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow down 600 road pushing back banks at 22km | 9 | E091-E102 | 600 Road | 0 | 43896 |  | 45 | 43914 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1197KL-20200301-5CAT 140M101790 | KABI LAKE FOREST PRODUCTS LTD1197KL-20200301-5CAT 140M101790OEWT-PA3-LEM | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1209 | KL-20200302-7 | 53510911 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-03-02 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open 600 Road for access km 4 with grader and open sub roads at 2km | 9 | E-091 to E-102 | 600 Road | 0 | 43896 |  | 42 | 43910 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1209KL-20200302-7CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD1209KL-20200302-7CAT 140M111969OEWT-PA3-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1225 | KL-20200305-1 | 53510911 | Access | 0 | CAT 140M | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2020-03-05 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open road and make turn arounds on 600 Road | 9 | E-091 to E-102 | 600 road | 0 | 43901 |  | 42 | 43910 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1225KL-20200305-1CAT 140M101790 | KABI LAKE FOREST PRODUCTS LTD1225KL-20200305-1CAT 140M101790OEWT-PA3-LEM | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1234 | KL-20200306-5 | 53510911 | Access | 0 | CAT 140M | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2020-03-06 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open 600 road to 32 KM | 9 | E-091 to E-102 | 600 Road | 0 | 43901 |  | 42 | 43910 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1234KL-20200306-5CAT 140M91611 | KABI LAKE FOREST PRODUCTS LTD1234KL-20200306-5CAT 140M91611OEWT-PA3-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1310 | KL-20200316-4 | 53510911 | Access | 0 | CAT 140M | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2020-03-16 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open road by KM 30 and plow after snowfall | 9 | E-091 to E-102 | 600 Road | 0 | 43908 |  | 42 | 43915 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1310KL-20200316-4CAT 140M91611 | KABI LAKE FOREST PRODUCTS LTD1310KL-20200316-4CAT 140M91611OEWT-PA3-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1324 | KL-20200318-2 | 53510911 | Access | 0 | CAT 140M | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2020-03-18 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | PLOW OPEN ROAD AT 40KM AND WING BACK BANKS | 9 | E-091 to E-102 | 600 Road | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1324KL-20200318-2CAT 140M81432 | KABI LAKE FOREST PRODUCTS LTD1324KL-20200318-2CAT 140M81432OEWT-PA3-LEM | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1400 | KL-20200327-5 | 53510911 | Access | 0 | CAT 140M | 179 | 12 | HR | 135 | 0 |  |  | 2148 | 279.24 | 2427.24 | 2020-03-27 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open 600 for WF-9 access and grade road | 9 | E-091 to E-102 | 600 Road | 0 | 43925 |  | 45 | 43924 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1400KL-20200327-5CAT 140M122148 | KABI LAKE FOREST PRODUCTS LTD1400KL-20200327-5CAT 140M122148OEWT PA4-LEM-R1 | [5 empty] | 1 | 2148 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1418 | KL-20200330-6 | 53510911 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-03-30 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Open up 600 Road (plow snow) | 9 |  | 600 Road | 0 | 43928 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD1418KL-20200330-6CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD1418KL-20200330-6CAT 140M111969OEWT PA4-LEM-R1 | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5002 | KL-20201214-5 | 53510911 | Access | 0 | CAT 140M | 179 | 8.5 | HR | 135 | 0 |  |  | 1521.5 | 197.795 | 1719.295 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5002KL-20201214-5CAT 140M8.51521.5 | KABI LAKE FOREST PRODUCTS LTD5002KL-20201214-5CAT 140M8.51521.5OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1521.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1538 | KL-20200520-9 | 53510912 | Access | 0 | CAT 140M | 179 | 12.5 | HR | 135 | 0 |  |  | 2237.5 | 290.875 | 2528.375 | 2020-05-20 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road to KM 30 | 9 | E091-E102 | 600 Road | 0 | 43976 |  | 15 | 43977 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1538KL-20200520-9CAT 140M12.52237.5 | KABI LAKE FOREST PRODUCTS LTD1538KL-20200520-9CAT 140M12.52237.5OEWT-PA5-LEM | [5 empty] | 1 | 2237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1552 | KL-20200521-4 | 53510912 | Access | 0 | CAT 140M | 179 | 11.5 | HR | 135 | 0 |  |  | 2058.5 | 267.605 | 2326.105 | 2020-05-21 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road to 40 km | 9 | E091-E102 | 600 Road | 0 | 43977 |  | 15 | 43977 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1552KL-20200521-4CAT 140M11.52058.5 | KABI LAKE FOREST PRODUCTS LTD1552KL-20200521-4CAT 140M11.52058.5OEWT-PA5-LEM | [5 empty] | 1 | 2058.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1559 | KL-20200519-3 | 53510912 | Access | 0 | CAT 140M | 179 | 13 | HR | 135 | 0 |  |  | 2327 | 302.51 | 2629.51 | 2020-05-19 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start grading 600 Road at Km 9 | 9 | E091-E102 | 600 Road | 0 | 43976 |  | 15 | 43977 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1559KL-20200519-3CAT 140M132327 | KABI LAKE FOREST PRODUCTS LTD1559KL-20200519-3CAT 140M132327OEWT-PA5-LEM | [5 empty] | 1 | 2327 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1795 | KL-20200619-5 | 53510912 | Access | 0 | CAT 140M | 179 | 7 | HR | 135 | 0 |  |  | 1253 | 162.89 | 1415.89 | 2020-06-19 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade sections on 100 Road to 5KM pit for Gravel Haul (2 hours) & 600 Road to 15KM (5 Hours) | 9 | E-091 to E-102 | 600 Road | 0 | 44006 |  | 15 | 44005 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1795KL-20200619-5CAT 140M71253 | KABI LAKE FOREST PRODUCTS LTD1795KL-20200619-5CAT 140M71253OEWT-PA6-LEM | [5 empty] | 1 | 1253 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1850 | KL-20200623-13 | 53510912 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-06-23 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road from 20 km to 26km | 9 |  | 600 Road | 0 | 44007 |  | 14 | 44009 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD1850KL-20200623-13CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD1850KL-20200623-13CAT 140M111969OEWT-PA6-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1864 | KL-20200624-14 | 53510912 | Access | 0 | CAT 140M | 179 | 11.5 | HR | 135 | 0 |  |  | 2058.5 | 267.605 | 2326.105 | 2020-06-24 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Approver- William Ouiet, not in data base as of June 27th |  | Approved |  |  | Continue grading 600 road from 25km to 32 km | 9 |  | 600 Road | 0 | 44008 |  | 14 | 44011 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD1864KL-20200624-14CAT 140M11.52058.5 | KABI LAKE FOREST PRODUCTS LTD1864KL-20200624-14CAT 140M11.52058.5OEWT-PA6-LEM | [5 empty] | 1 | 2058.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1919 | KL-20200630-8 | 53510912 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-06-30 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road from 31 Km to 40 Km | 9 |  | 600 Road | 0 | 44012 |  | 50 | 44015 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD1919KL-20200630-8CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD1919KL-20200630-8CAT 140M111969OEWT-PA7-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2128 | KL-20200701-12 | 53510912 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-07-01 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road from 40km to 47km | 9 | E-091 to E-102 | 600 Road | 0 | 44019 |  | 50 | 44020 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2128KL-20200701-12CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD2128KL-20200701-12CAT 140M111969OEWT-PA7-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2802 | KL-20200910-18 | 53510912 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-09-10 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44091 |  | 15 | 44094 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2802KL-20200910-18CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD2802KL-20200910-18CAT 140M111969OEWT-PA9-Lem-R1 | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3320 | KL-20200929-11 | 53510912 | Access | 0 | CAT 140M | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2020-09-29 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44109 |  | 50 | 44115 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3320KL-20200929-11CAT 140M5895 | KABI LAKE FOREST PRODUCTS LTD3320KL-20200929-11CAT 140M5895OEWT-PA10-LEM | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3487 | KL-20201005-12 | 53510912 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-10-05 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44123 |  | 15 | 44125 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3487KL-20201005-12CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD3487KL-20201005-12CAT 140M111969OEWT-PA10-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3598 | KL-20201008-18 | 53510912 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-10-08 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3598KL-20201008-18CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD3598KL-20201008-18CAT 140M111969OEWT-PA10-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3624 | KL-20201009-13 | 53510912 | Access | 0 | CAT 140M | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2020-10-09 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3624KL-20201009-13CAT 140M61074 | KABI LAKE FOREST PRODUCTS LTD3624KL-20201009-13CAT 140M61074OEWT-PA10-LEM | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3743 | KL-20201014-14 | 53510912 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-10-14 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44129 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3743KL-20201014-14CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD3743KL-20201014-14CAT 140M111969OEWT-PA10-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3792 | KL-20201016-10 | 53510912 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-10-16 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44130 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3792KL-20201016-10CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD3792KL-20201016-10CAT 140M111969OEWT-PA10-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3845 | KL-20201019-10 | 53510912 | Access | 0 | CAT 140M | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2020-10-19 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44130 |  | 50 | 44133 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3845KL-20201019-10CAT 140M81432 | KABI LAKE FOREST PRODUCTS LTD3845KL-20201019-10CAT 140M81432OEWT-PA10-LEM | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3990 | KL-20201026-15 | 53510912 | Access | 0 | CAT 140M | 179 | 12 | HR | 135 | 0 |  |  | 2148 | 279.24 | 2427.24 | 2020-10-26 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E091-E102 | 600 Rd | 0 | 44147 |  | 50 | 44161 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3990KL-20201026-15CAT 140M122148 | KABI LAKE FOREST PRODUCTS LTD3990KL-20201026-15CAT 140M122148OEWT-PA11-LEM | [5 empty] | 1 | 2148 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4005 | KL-20201027-10 | 53510912 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-10-27 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E091-E102 | 600 Rd | 0 | 44147 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4005KL-20201027-10CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD4005KL-20201027-10CAT 140M111969OEWT-PA11-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4021 | KL-20201028-8 | 53510912 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-10-28 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E091-E102 | 600 Rd | 0 | 44147 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4021KL-20201028-8CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD4021KL-20201028-8CAT 140M111969OEWT-PA11-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4065 | KL-20201030-7 | 53510912 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-10-30 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Paint Lake Road 2 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44152 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4065KL-20201030-7CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD4065KL-20201030-7CAT 140M111969OEWT-PA11-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4164 | KL-20201104-19 | 53510912 | Access | 0 | CAT 140M | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2020-11-04 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Rd | 9 | E091-E102 | 600 Road | 0 | 44160 |  | 50 | 44163 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4164KL-20201104-19CAT 140M101790 | KABI LAKE FOREST PRODUCTS LTD4164KL-20201104-19CAT 140M101790OEWT-PA11-LEM | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4183 | KL-20201105-17 | 53510912 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-11-05 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road , 700 road and 100 road | 9 | E091-E102 | 600 Road | 0 | 44160 |  | 50 | 44163 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4183KL-20201105-17CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD4183KL-20201105-17CAT 140M111969OEWT-PA11-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4237 | KL-20201108-16 | 53510912 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-11-08 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44162 |  | 50 | 44163 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4237KL-20201108-16CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD4237KL-20201108-16CAT 140M111969OEWT-PA11-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4263 | KL-20201109-12 | 53510912 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-11-09 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E091-E102 | 600 Road | 0 | 44164 |  | 15 | 44171 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4263KL-20201109-12CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD4263KL-20201109-12CAT 140M111969OEWT-PA11-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4288 | KL-20201103-17 | 53510912 | Access | 0 | CAT 140M | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road, 700 road and 100 road | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 50 | 44167 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4288KL-20201103-17CAT 140M81432 | KABI LAKE FOREST PRODUCTS LTD4288KL-20201103-17CAT 140M81432OEWT-PA11-LEM | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4298 | KL-20201110-8 | 53510912 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-11-10 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Rd 2 graders | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44168 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4298KL-20201110-8CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD4298KL-20201110-8CAT 140M111969OEWT-PA11-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4316 | KL-20201111-12 | 53510912 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-11-11 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road and 100 Road | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44170 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4316KL-20201111-12CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD4316KL-20201111-12CAT 140M111969OEWT-PA11-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4329 | KL-20201112-12 | 53510912 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-11-12 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road and 100 Road | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44168 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4329KL-20201112-12CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD4329KL-20201112-12CAT 140M111969OEWT-PA11-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4340 | KL-20201113-8 | 53510912 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-11-13 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600rd and 100rd | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44170 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4340KL-20201113-8CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD4340KL-20201113-8CAT 140M111969OEWT-PA11-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4360 | KL-20201114-13 | 53510912 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-11-14 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4360KL-20201114-13CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD4360KL-20201114-13CAT 140M111969OEWT-PA11-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4397 | KL-20201115-11 | 53510912 | Access | 0 | CAT 140M | 179 | 12 | HR | 135 | 0 |  |  | 2148 | 279.24 | 2427.24 | 2020-11-15 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road and 100 Road. | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 53 | 44171 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4397KL-20201115-11CAT 140M122148 | KABI LAKE FOREST PRODUCTS LTD4397KL-20201115-11CAT 140M122148OEWT-PA11-LEM | [5 empty] | 1 | 2148 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4416 | KL-20201116-15 | 53510912 | Access | 0 | CAT 140M | 179 | 17.5 | HR | 135 | 0 |  |  | 3132.5 | 407.225 | 3539.725 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road, 100 road, Paint Lake 2 Rd | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4416KL-20201116-15CAT 140M17.53132.5 | KABI LAKE FOREST PRODUCTS LTD4416KL-20201116-15CAT 140M17.53132.5OEWT-PA11-LEM | [5 empty] | 1 | 3132.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4431 | KL-20201117-10 | 53510912 | Access | 0 | CAT 140M | 179 | 12 | HR | 135 | 0 |  |  | 2148 | 279.24 | 2427.24 | 2020-11-17 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 rd, 100 rd, and Paint Lake 2 road | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4431KL-20201117-10CAT 140M122148 | KABI LAKE FOREST PRODUCTS LTD4431KL-20201117-10CAT 140M122148OEWT-PA11-LEM | [5 empty] | 1 | 2148 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4708 | KL-20201129-7 | 53511011 | Access | 0 | CAT 140M | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2020-11-29 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading Paint Lake 2 Road | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44181 |  | 47 | 44208 | [5 empty] | Bruce Bennett | 10 | KABI LAKE FOREST PRODUCTS LTD4708KL-20201129-7CAT 140M101790 | KABI LAKE FOREST PRODUCTS LTD4708KL-20201129-7CAT 140M101790OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5606 | KL-20210125-3 | 53511011 | Access | 0 | CAT 140M | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2021-01-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow, Grade Paint Lake 2 Rd, haul gravel & corduroy. Drag 70' bridge in from km 9 lay down | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44225 |  | 50 | 44232 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5606KL-20210125-3CAT 140M101790 | KABI LAKE FOREST PRODUCTS LTD5606KL-20210125-3CAT 140M101790OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5617 | KL-20210126-1 | 53511011 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2021-01-26 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Drag 70' bridge in from km 9 laydown, plow snow, grade PL2 Rd and F20-F10. Haul gravel and corduroy, sand roads, unload bridge, skidder drag mats to WC 11150 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44228 |  | 50 | 44232 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5617KL-20210126-1CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD5617KL-20210126-1CAT 140M111969OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5778 | KL-20210205-4 | 53511011 | Access | 0 | CAT 140M | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2021-02-05 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Paint Lake 2 Rd, plow snow, haul gravel. Ditch and load rock trucks. Haul & spread material, trim road, and track out plow. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44243 |  | 50 | 44248 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5778KL-20210205-4CAT 140M61074 | KABI LAKE FOREST PRODUCTS LTD5778KL-20210205-4CAT 140M61074OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5976 | KL-20210220-3 | 53511011 | Access | 0 | CAT 140M | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2021-02-20 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Paint Lake 2 Road, Plow snow on access road. Corduroy F62-F63 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44252 |  | 57 | 44252 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD5976KL-20210220-3CAT 140M101790 | KABI LAKE FOREST PRODUCTS LTD5976KL-20210220-3CAT 140M101790OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5990 | KL-20210221-8 | 53511011 | Access | 0 | CAT 140M | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2021-02-21 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Paint Lake 2 Rd, plow snow on access rd, haul geo from km 9 to km 23, skid corduroy | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44252 |  | 57 | 44255 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD5990KL-20210221-8CAT 140M91611 | KABI LAKE FOREST PRODUCTS LTD5990KL-20210221-8CAT 140M91611OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6290 | KL-20210310-3 | 53511011 | Access | 0 | CAT 140M | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2021-03-10 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying Paint Lake 2 Rd/Loader pushing out snow banks in low areas for drainage. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44278 |  | 56 | 44280 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6290KL-20210310-3CAT 140M81432 | KABI LAKE FOREST PRODUCTS LTD6290KL-20210310-3CAT 140M81432OEWT PA15-LEM | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6301 | KL-20210311-2 | 53511011 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2021-03-11 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal & scarifying Paint Lake 2 Rd. JJR pushing snowbanks back. CDSL excavator walking out to float access. | 10 | F033-F118 | Paint Lake Raod 2 | 0 | 44278 |  | 56 | 44280 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6301KL-20210311-2CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD6301KL-20210311-2CAT 140M111969OEWT PA15-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6309 | KL-20210312-6 | 53511011 | Access | 0 | CAT 140M | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2021-03-12 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal & scarifying Paint Lake 2 Rd | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44278 |  | 56 | 44280 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6309KL-20210312-6CAT 140M81432 | KABI LAKE FOREST PRODUCTS LTD6309KL-20210312-6CAT 140M81432OEWT PA15-LEM | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7670 | KL-20211211-1 | 53511011 | Access | 0 | CAT 140M | 179 | 2.5 | HR | 135 | 0 |  |  | 447.5 | 58.175 | 505.675 | 2021-12-11 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from 49Km to 40Km. Grader 1 working on snow removal 0Km to 23Km for Crane demob. Grader 2 scarifying from 49 to 45Km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7670KL-20211211-1CAT 140M2.5447.5 | KABI LAKE FOREST PRODUCTS LTD7670KL-20211211-1CAT 140M2.5447.5OEWT-PA24-LEM | [5 empty] | 1 | 447.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7883 | KL-20220214-1 | 53511011 | Access | 0 | CAT 140M | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-02-14 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal, scarifying and benching snowbanks from Paint Lake Road to Km 19 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7883KL-20220214-1CAT 140M91611 | KABI LAKE FOREST PRODUCTS LTD7883KL-20220214-1CAT 140M91611OEWT-PA26-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7893 | KL-20220216-1 | 53511011 | Access | 0 | CAT 140M | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-02-16 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from Km 49 to Km 19 / grader 2 working on snow removal and pushing back snowbanks from Paint Lake Road to Km 19 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7893KL-20220216-1CAT 140M91611 | KABI LAKE FOREST PRODUCTS LTD7893KL-20220216-1CAT 140M91611OEWT-PA26-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7896 | KL-20220217-1 | 53511011 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2022-02-17 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal and scarifying from Km 49 to Km 41 / grader 2 working on snow removal and benching snowbanks from Paint Lake Road to Km 41 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7896KL-20220217-1CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD7896KL-20220217-1CAT 140M111969OEWT-PA26-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7897 | KL-20220217-2 | 53511011 | Access | 0 | CAT 140M | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2022-02-17 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from Paint Lake Road 2, work on snow removal from F021 to F032 after hours and run grader back to Paint Lake Road 2 / Supervisor stayed after hours due to Operator working alone | 10 | F009-F065 | Paint Lake | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7897KL-20220217-2CAT 140M5895 | KABI LAKE FOREST PRODUCTS LTD7897KL-20220217-2CAT 140M5895OEWT-PA26-LEM | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7900 | KL-20220218-1 | 53511011 | Access | 0 | CAT 140M | 179 | 8.5 | HR | 135 | 0 |  |  | 1521.5 | 197.795 | 1719.295 | 2022-02-18 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying and benching snowbanks from Paint Lake Road to Km 13 and snow removal from F037 to F033 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7900KL-20220218-1CAT 140M8.51521.5 | KABI LAKE FOREST PRODUCTS LTD7900KL-20220218-1CAT 140M8.51521.5OEWT-PA26-LEM | [5 empty] | 1 | 1521.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7904 | KL-20220220-1 | 53511011 | Access | 0 | CAT 140M | 179 | 12 | HR | 135 | 0 |  |  | 2148 | 279.24 | 2427.24 | 2022-02-20 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 29km. Grader 2 working on snow removal from Paint Lake Road to 29km. Loader pushing back snow banks & pull offs from 45km to 38km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44617 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7904KL-20220220-1CAT 140M122148 | KABI LAKE FOREST PRODUCTS LTD7904KL-20220220-1CAT 140M122148OEWT-PA26-LEM | [5 empty] | 1 | 2148 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7905 | KL-20220219-1 | 53511011 | Access | 0 | CAT 140M | 179 | 13 | HR | 135 | 0 |  |  | 2327 | 302.51 | 2629.51 | 2022-02-19 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 39km. Grader 2 working on snow removal from Paint Lake Road to 39km. Loader sanding & clearing pull offs to 34km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7905KL-20220219-1CAT 140M132327 | KABI LAKE FOREST PRODUCTS LTD7905KL-20220219-1CAT 140M132327OEWT-PA26-LEM | [5 empty] | 1 | 2327 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7911 | KL-20220221-1 | 53511011 | Access | 0 | CAT 140M | 179 | 13 | HR | 135 | 0 |  |  | 2327 | 302.51 | 2629.51 | 2022-02-21 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 40km. Grader 2 working on snow removal from Paint Lake Road to 40km. Loader pushing back snow banks & pull offs from 49km to 40km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44617 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7911KL-20220221-1CAT 140M132327 | KABI LAKE FOREST PRODUCTS LTD7911KL-20220221-1CAT 140M132327OEWT-PA26-LEM | [5 empty] | 1 | 2327 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7913 | KL-20220222-1 | 53511011 | Access | 0 | CAT 140M | 179 | 9.5 | HR | 135 | 0 |  |  | 1700.5 | 221.065 | 1921.565 | 2022-02-22 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 38km. Grader 2 benchig snow banks from Paint Lake Road to 49km. Loader assisting with Demob of 50 Ton Crane from 32Km to Hensen Road. | 10 | F-066 to F-118 | Paint Lake Road 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7913KL-20220222-1CAT 140M9.51700.5 | KABI LAKE FOREST PRODUCTS LTD7913KL-20220222-1CAT 140M9.51700.5OEWT-PA26-LEM | [5 empty] | 1 | 1700.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7919 | KL-20220223-4 | 53511011 | Access | 0 | CAT 140M | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-02-23 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from 49km to 29km. Loader working ahead of grader due to deep snow drifts | 10 | F066-F118 | Paint Lake 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7919KL-20220223-4CAT 140M91611 | KABI LAKE FOREST PRODUCTS LTD7919KL-20220223-4CAT 140M91611OEWT-PA26-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7925 | KL-20220225-1 | 53511011 | Access | 0 | CAT 140M | 179 | 7 | HR | 135 | 0 |  |  | 1253 | 162.89 | 1415.89 | 2022-02-25 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 18km. Grader 2 working from Paint Lake Road to 18Km. Loader clearing pulloffs on Paint lake Road 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7925KL-20220225-1CAT 140M71253 | KABI LAKE FOREST PRODUCTS LTD7925KL-20220225-1CAT 140M71253OEWT-PA26-LEM | [5 empty] | 1 | 1253 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7935 | KL-20220226-1 | 53511011 | Access | 0 | CAT 140M | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2022-02-26 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader working from Paint Lake Road to Km 34 benching and widening / Loader clearing pull offs on Paint Lake Road 2 and widening @ Km 27 | 10 | F066-F118 | Paint Lake 2 | 0 | 44628 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7935KL-20220226-1CAT 140M111969 | KABI LAKE FOREST PRODUCTS LTD7935KL-20220226-1CAT 140M111969 | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7938 | KL-20220227-1 | 53511011 | Access | 0 | CAT 140M | 179 | 3.5 | HR | 135 | 0 |  |  | 626.5 | 81.445 | 707.945 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader 1 working from 49km to 26km. Grader 2 working from Paint Lake Road to 8km. Loader working on clearing pull offs between 9.2Km & 5Km on Paint Lake Road #2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44628 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7938KL-20220227-1CAT 140M3.5626.5 | KABI LAKE FOREST PRODUCTS LTD7938KL-20220227-1CAT 140M3.5626.5 | [5 empty] | 1 | 626.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7954 | KL-20220301-2 | 53511011 | Access | 0 | CAT 140M | 179 | 8.5 | HR | 135 | 0 |  |  | 1521.5 | 197.795 | 1719.295 | 2022-03-01 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader working on Snow Removal and benching snow banks from Km 1 to Km 13 on Paint Lake Road 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7954KL-20220301-2CAT 140M8.51521.5 | KABI LAKE FOREST PRODUCTS LTD7954KL-20220301-2CAT 140M8.51521.5 | [5 empty] | 1 | 1521.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4077 | KL-20201031-9 | 53511012 | Access | 0 | CAT 140M | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2020-10-31 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Paint Lake Road 2 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44152 |  | 47 | 44156 | [5 empty] | Bruce Bennett | 10 | KABI LAKE FOREST PRODUCTS LTD4077KL-20201031-9CAT 140M81432 | KABI LAKE FOREST PRODUCTS LTD4077KL-20201031-9CAT 140M81432OEWT-PA11-LEM | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7606 | KL-20211129-3 | 53511111 | Access | 0 | CAT 140M | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2021-11-29 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17.5 on Hensen Road | 11 | F118-F127 | Hensen Road | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7606KL-20211129-3CAT 140M101790 | KABI LAKE FOREST PRODUCTS LTD7606KL-20211129-3CAT 140M101790OEWT-PA24-LEM | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7616 | KL-20211201-6 | 53511111 | Access | 0 | CAT 140M | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2021-12-01 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17.5 km on Hensen Road | 11 | F118-F127 | Henson | 0 | 44537 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7616KL-20211201-6CAT 140M101790 | KABI LAKE FOREST PRODUCTS LTD7616KL-20211201-6CAT 140M101790OEWT-PA24-LEM | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7622 | KL-20211202-4 | 53511111 | Access | 0 | CAT 140M | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17.5 on Hensen road/ Dozer working on snow removal and shaping road from F122 to F132 | 11 | F118 - F127 | Henson | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7622KL-20211202-4CAT 140M101790 | KABI LAKE FOREST PRODUCTS LTD7622KL-20211202-4CAT 140M101790OEWT-PA24-LEM | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7630 | KL-20211203-4 | 53511111 | Access | 0 | CAT 140M | 179 | 7 | HR | 135 | 0 |  |  | 1253 | 162.89 | 1415.89 | 2021-12-03 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on sections from Hwy 17 to Km 17.5 on Hensen road filling rough sections with snow | 11 | F118 - F127 | Henson | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7630KL-20211203-4CAT 140M71253 | KABI LAKE FOREST PRODUCTS LTD7630KL-20211203-4CAT 140M71253OEWT-PA24-LEM | [5 empty] | 1 | 1253 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7635 | KL-20211204-3 | 53511111 | Access | 0 | CAT 140M | 179 | 9.5 | HR | 135 | 0 |  |  | 1700.5 | 221.065 | 1921.565 | 2021-12-04 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Graderworking on snow removal from Hwy 17 to Km 17 | 11 | F118 - F127 | Henson | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7635KL-20211204-3CAT 140M9.51700.5 | KABI LAKE FOREST PRODUCTS LTD7635KL-20211204-3CAT 140M9.51700.5OEWT-PA24-LEM | [5 empty] | 1 | 1700.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7642 | KL-20211206-1 | 53511111 | Access | 0 | CAT 140M | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2021-12-06 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 | 11 | F118-F127 | Henson | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7642KL-20211206-1CAT 140M91611 | KABI LAKE FOREST PRODUCTS LTD7642KL-20211206-1CAT 140M91611OEWT-PA24-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7648 | KL-20211207-2 | 53511111 | Access | 0 | CAT 140M | 179 | 8.5 | HR | 135 | 0 |  |  | 1521.5 | 197.795 | 1719.295 | 2021-12-07 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on benching snow banks from Hwy 17 to Km 17 and clearing pull offs | 11 | F118-F127 | Henson | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7648KL-20211207-2CAT 140M8.51521.5 | KABI LAKE FOREST PRODUCTS LTD7648KL-20211207-2CAT 140M8.51521.5OEWT-PA24-LEM | [5 empty] | 1 | 1521.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7653 | KL-20211208-2 | 53511111 | Access | 0 | CAT 140M | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Hensen Road from Hwy 17 to 17Km & widening corners. | 11 | F118-F127 | Henson | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7653KL-20211208-2CAT 140M91611 | KABI LAKE FOREST PRODUCTS LTD7653KL-20211208-2CAT 140M91611OEWT-PA24-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7661 | KL-20211209-4 | 53511111 | Access | 0 | CAT 140M | 179 | 8.5 | HR | 135 | 0 |  |  | 1521.5 | 197.795 | 1719.295 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying Hensen Road from hwy 17 to 17km. Sand truck sanding hills & corners with existing sand from 17km. Excavator used for loading sand. | 11 | F118-F127 | Henson | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7661KL-20211209-4CAT 140M8.51521.5 | KABI LAKE FOREST PRODUCTS LTD7661KL-20211209-4CAT 140M8.51521.5OEWT-PA24-LEM | [5 empty] | 1 | 1521.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7667 | KL-20211210-3 | 53511111 | Access | 0 | CAT 140M | 179 | 8.5 | HR | 135 | 0 |  |  | 1521.5 | 197.795 | 1719.295 | 2021-12-10 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow remvoal and scarifying Hensen Road from hwy 17 to 17Km. | 11 | F118-F127 | Henson | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7667KL-20211210-3CAT 140M8.51521.5 | KABI LAKE FOREST PRODUCTS LTD7667KL-20211210-3CAT 140M8.51521.5OEWT-PA24-LEM | [5 empty] | 1 | 1521.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7672 | KL-20211211-3 | 53511111 | Access | 0 | CAT 140M | 179 | 7 | HR | 135 |  |  |  | 1253 | 162.89 | 1415.89 | 2021-12-11 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow remvoal from Hwy 17 to 17Km. | 11 | F118-F127 | Henson | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7672KL-20211211-3CAT 140M71253 | KABI LAKE FOREST PRODUCTS LTD7672KL-20211211-3CAT 140M71253OEWT-PA24-LEM | [5 empty] | 1 | 1253 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7683 | KL-20211212-3 | 53511111 | Access | 0 | CAT 140M | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2021-12-12 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Scarifying from Hwy 17 to Km 17 and clearing pull offs | 11 | F118-F127 | Henson | 0 | 44551 |  | 61 | 44561 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7683KL-20211212-3CAT 140M91611 | KABI LAKE FOREST PRODUCTS LTD7683KL-20211212-3CAT 140M91611OEWT-PA24-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7914 | KL-20220222-2 | 53511111 | Access | 0 | CAT 140M | 179 | 3 | HR | 135 | 0 |  |  | 537 | 69.81 | 606.81 | 2022-02-22 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen Road /Grader 2 benching snow banks from Km 17 to Hwy 17 | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7914KL-20220222-2CAT 140M3537 | KABI LAKE FOREST PRODUCTS LTD7914KL-20220222-2CAT 140M3537OEWT-PA26-LEM | [5 empty] | 1 | 537 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7917 | KL-20220223-2 | 53511111 | Access | 0 | CAT 140M | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2022-02-23 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17km on Hensen Road. Loader widening corners & assisting float trucks | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7917KL-20220223-2CAT 140M61074 | KABI LAKE FOREST PRODUCTS LTD7917KL-20220223-2CAT 140M61074OEWT-PA26-LEM | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7921 | KL-20220224-2 | 53511111 | Access | 0 | CAT 140M | 179 | 10.5 | HR | 135 | 0 |  |  | 1879.5 | 244.335 | 2123.835 | 2022-02-24 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal, benching snowbanks and widening road from Hwy 17 to 17km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7921KL-20220224-2CAT 140M10.51879.5 | KABI LAKE FOREST PRODUCTS LTD7921KL-20220224-2CAT 140M10.51879.5OEWT-PA26-LEM | [5 empty] | 1 | 1879.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1121 | KL-20200222-1 | 53510711 | Access | 0 | CAT 140H | 179 | 1 | HR | 135 | 0 |  |  | 179 | 23.27 | 202.27 | 2020-02-22 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow for road access | 7 | D-119 to D-141 | Alder Creek | 0 | 43887 |  | 43 | 43889 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1121KL-20200222-1CAT 140H1179 | KABI LAKE FOREST PRODUCTS LTD1121KL-20200222-1CAT 140H1179OEWT-PA2-LEM-R1 | [5 empty] | 1 | 179 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1122 | KL-20200222-2 | 53510711 | Access | 0 | CAT 140H | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2020-02-22 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow- White Lake Road | 7 | D-142 to E-002 | White Lake | 0 | 43887 |  | 43 | 43889 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1122KL-20200222-2CAT 140H4716 | KABI LAKE FOREST PRODUCTS LTD1122KL-20200222-2CAT 140H4716OEWT-PA2-LEM-R1 | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2941 | KL-20200915-12 | 53510812 | Access | 0 | CAT 140H | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2020-09-15 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 100 road to 5Km pit for gravel haul | 8 | E068 - E076 | Denis Lake W | 0 | 44096 |  | 15 | 44097 | [5 empty] | Martin Hunt | 08 | KABI LAKE FOREST PRODUCTS LTD2941KL-20200915-12CAT 140H4716 | KABI LAKE FOREST PRODUCTS LTD2941KL-20200915-12CAT 140H4716OEWT-PA9-Lem-R1 | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1778 | KL-20200618-4 | 53510912 | Access | 0 | CAT 140H | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2020-06-18 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 road to 9 KM | 9 | E-091 to E-102 | 600 Road | 0 | 44005 |  | 15 | 44004 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1778KL-20200618-4CAT 140H61074 | KABI LAKE FOREST PRODUCTS LTD1778KL-20200618-4CAT 140H61074OEWT-PA6-LEM | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1829 | KL-20200622-4 | 53510912 | Access | 0 | CAT 140H | 179 | 12 | HR | 135 | 0 |  |  | 2148 | 279.24 | 2427.24 | 2020-06-22 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road from 12m to 20km | 9 |  | 600 Road | 0 | 44007 |  | 15 | 44008 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1829KL-20200622-4CAT 140H122148 | KABI LAKE FOREST PRODUCTS LTD1829KL-20200622-4CAT 140H122148OEWT-PA6-LEM | [5 empty] | 1 | 2148 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2605 | KL-20200827-2 | 53510912 | Access | 0 | CAT 140H | 179 | 12 | HR | 135 | 0 |  |  | 2148 | 279.24 | 2427.24 | 2020-08-27 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 road from Hwy to 9km | 9 | E091-E102 | 600 Road | 0 | 44074 |  | 15 | 44075 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2605KL-20200827-2CAT 140H122148 | KABI LAKE FOREST PRODUCTS LTD2605KL-20200827-2CAT 140H122148OEWT-PA9-Lem-R1 | [5 empty] | 1 | 2148 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2606 | KL-20200828-1 | 53510912 | Access | 0 | CAT 140H | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2020-08-28 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 road from Hwy to 14km | 9 | E091-E102 | 600 Road | 0 | 44076 |  | 15 | 44077 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2606KL-20200828-1CAT 140H81432 | KABI LAKE FOREST PRODUCTS LTD2606KL-20200828-1CAT 140H81432OEWT-PA9-Lem-R1 | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2754 | KL-20200908-15 | 53510912 | Access | 0 | CAT 140H | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-09-08 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44089 |  | 15 | 44092 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2754KL-20200908-15CAT 140H111969 | KABI LAKE FOREST PRODUCTS LTD2754KL-20200908-15CAT 140H111969OEWT-PA9-Lem-R1 | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2778 | KL-20200909-19 | 53510912 | Access | 0 | CAT 140H | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-09-09 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44092 |  | 15 | 44092 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2778KL-20200909-19CAT 140H111969 | KABI LAKE FOREST PRODUCTS LTD2778KL-20200909-19CAT 140H111969OEWT-PA9-Lem-R1 | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2853 | KL-20200911-20 | 53510912 | Access | 0 | CAT 140H | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2020-09-11 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44094 |  | 15 | 44095 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2853KL-20200911-20CAT 140H101790 | KABI LAKE FOREST PRODUCTS LTD2853KL-20200911-20CAT 140H101790OEWT-PA9-Lem-R1 | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2937 | KL-20200915-8 | 53510912 | Access | 0 | CAT 140H | 179 | 2 | HR | 135 | 0 |  |  | 358 | 46.54 | 404.54 | 2020-09-15 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44096 |  | 15 | 44097 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2937KL-20200915-8CAT 140H2358 | KABI LAKE FOREST PRODUCTS LTD2937KL-20200915-8CAT 140H2358OEWT-PA9-Lem-R1 | [5 empty] | 1 | 358 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2968 | KL-20200916-11 | 53510912 | Access | 0 | CAT 140H | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2020-09-16 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44096 |  | 15 | 44098 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2968KL-20200916-11CAT 140H81432 | KABI LAKE FOREST PRODUCTS LTD2968KL-20200916-11CAT 140H81432OEWT-PA9-Lem-R1 | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2996 | KL-20200917-13 | 53510912 | Access | 0 | CAT 140H | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2020-09-17 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44097 |  | 15 | 44098 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2996KL-20200917-13CAT 140H101790 | KABI LAKE FOREST PRODUCTS LTD2996KL-20200917-13CAT 140H101790OEWT-PA9-Lem-R1 | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3036 | KL-20200918-16 | 53510912 | Access | 0 | CAT 140H | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-09-18 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | KL-20200918-16 | 600 Road | 0 | 44098 |  | 15 | 44099 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3036KL-20200918-16CAT 140H111969 | KABI LAKE FOREST PRODUCTS LTD3036KL-20200918-16CAT 140H111969OEWT-PA9-Lem-R1 | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3059 | KL-20200920-12 | 53510912 | Access | 0 | CAT 140H | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2020-09-20 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44099 |  | 15 | 44101 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3059KL-20200920-12CAT 140H81432 | KABI LAKE FOREST PRODUCTS LTD3059KL-20200920-12CAT 140H81432OEWT-PA9-Lem-R1 | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3517 | KL-20201006-13 | 53510912 | Access | 0 | CAT 140H | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-10-06 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44124 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3517KL-20201006-13CAT 140H111969 | KABI LAKE FOREST PRODUCTS LTD3517KL-20201006-13CAT 140H111969OEWT-PA10-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3717 | KL-20201013-11 | 53510912 | Access | 0 | CAT 140H | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2020-10-13 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44129 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3717KL-20201013-11CAT 140H111969 | KABI LAKE FOREST PRODUCTS LTD3717KL-20201013-11CAT 140H111969OEWT-PA10-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4634 | KL-20201125-11 | 53510912 | Access | 0 | CAT 140H | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600rd, 100rd, and access rds in WF9 | 9 | E091-E102 | 600 Road | 0 | 44173 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4634KL-20201125-11CAT 140H81432 | KABI LAKE FOREST PRODUCTS LTD4634KL-20201125-11CAT 140H81432OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7665 | KL-20211210-1 | 53511011 | Access | 0 | CAT 12G | 179 | 8.5 | HR | 135 | 0 |  |  | 1521.5 | 197.795 | 1719.295 | 2021-12-10 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal and sanding from 48Km to 38Km. Grader working on snow removal from Paint Lake Road to 13Km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7665KL-20211210-1CAT 12G8.51521.5 | KABI LAKE FOREST PRODUCTS LTD7665KL-20211210-1CAT 12G8.51521.5OEWT-PA24-LEM | [5 empty] | 1 | 1521.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7776 | KL-20220116-1 | 53511011 | Access | 0 | CAT 12G | 179 | 2 | HR | 135 | 0 |  |  | 358 | 46.54 | 404.54 | 2022-01-16 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continue working on widening roads from Km 33 to Km 42 /Loader Clearing pull offs / Grader Scarifying from Km 49 to Km 42 | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7776KL-20220116-1CAT 12G2358 | KABI LAKE FOREST PRODUCTS LTD7776KL-20220116-1CAT 12G2358OEWT-PA25-Lem | [5 empty] | 1 | 358 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7779 | KL-20220117-1 | 53511011 | Access | 0 | CAT 12G | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2022-01-17 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Finish working on widening roads and clearing pull offs from Km 42 to Km 49 /Grader Scarifying from Km 49 to Km 39 and F117 to F112/ supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7779KL-20220117-1CAT 12G4716 | KABI LAKE FOREST PRODUCTS LTD7779KL-20220117-1CAT 12G4716OEWT-PA25-Lem | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7785 | KL-20220119-1 | 53511011 | Access | 0 | CAT 12G | 179 | 2.5 | HR | 135 | 0 |  |  | 447.5 | 58.175 | 505.675 | 2022-01-19 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from 49Km to 42Km on Paint Lake Road 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7785KL-20220119-1CAT 12G2.5447.5 | KABI LAKE FOREST PRODUCTS LTD7785KL-20220119-1CAT 12G2.5447.5OEWT-PA25-Lem | [5 empty] | 1 | 447.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7888 | KL-20220215-1 | 53511011 | Access | 0 | CAT 12G | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2022-02-15 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal, scarifying from Km 49 to Km 38 on Paint Lake Road 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7888KL-20220215-1CAT 12G5895 | KABI LAKE FOREST PRODUCTS LTD7888KL-20220215-1CAT 12G5895OEWT-PA26-LEM | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7893 | KL-20220216-1 | 53511011 | Access | 0 | CAT 12G | 179 | 7.5 | HR | 135 | 0 |  |  | 1342.5 | 174.525 | 1517.025 | 2022-02-16 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from Km 49 to Km 19 / grader 2 working on snow removal and pushing back snowbanks from Paint Lake Road to Km 19 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7893KL-20220216-1CAT 12G7.51342.5 | KABI LAKE FOREST PRODUCTS LTD7893KL-20220216-1CAT 12G7.51342.5OEWT-PA26-LEM | [5 empty] | 1 | 1342.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7896 | KL-20220217-1 | 53511011 | Access | 0 | CAT 12G | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2022-02-17 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal and scarifying from Km 49 to Km 41 / grader 2 working on snow removal and benching snowbanks from Paint Lake Road to Km 41 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7896KL-20220217-1CAT 12G4716 | KABI LAKE FOREST PRODUCTS LTD7896KL-20220217-1CAT 12G4716OEWT-PA26-LEM | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7904 | KL-20220220-1 | 53511011 | Access | 0 | CAT 12G | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-02-20 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 29km. Grader 2 working on snow removal from Paint Lake Road to 29km. Loader pushing back snow banks & pull offs from 45km to 38km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44617 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7904KL-20220220-1CAT 12G91611 | KABI LAKE FOREST PRODUCTS LTD7904KL-20220220-1CAT 12G91611OEWT-PA26-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7905 | KL-20220219-1 | 53511011 | Access | 0 | CAT 12G | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2022-02-19 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 39km. Grader 2 working on snow removal from Paint Lake Road to 39km. Loader sanding & clearing pull offs to 34km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7905KL-20220219-1CAT 12G4716 | KABI LAKE FOREST PRODUCTS LTD7905KL-20220219-1CAT 12G4716OEWT-PA26-LEM | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7911 | KL-20220221-1 | 53511011 | Access | 0 | CAT 12G | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2022-02-21 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 40km. Grader 2 working on snow removal from Paint Lake Road to 40km. Loader pushing back snow banks & pull offs from 49km to 40km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44617 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7911KL-20220221-1CAT 12G61074 | KABI LAKE FOREST PRODUCTS LTD7911KL-20220221-1CAT 12G61074OEWT-PA26-LEM | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7913 | KL-20220222-1 | 53511011 | Access | 0 | CAT 12G | 179 | 5.5 | HR | 135 | 0 |  |  | 984.5 | 127.985 | 1112.485 | 2022-02-22 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 38km. Grader 2 benchig snow banks from Paint Lake Road to 49km. Loader assisting with Demob of 50 Ton Crane from 32Km to Hensen Road. | 10 | F-066 to F-118 | Paint Lake Road 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7913KL-20220222-1CAT 12G5.5984.5 | KABI LAKE FOREST PRODUCTS LTD7913KL-20220222-1CAT 12G5.5984.5OEWT-PA26-LEM | [5 empty] | 1 | 984.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7925 | KL-20220225-1 | 53511011 | Access | 0 | CAT 12G | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-02-25 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 18km. Grader 2 working from Paint Lake Road to 18Km. Loader clearing pulloffs on Paint lake Road 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7925KL-20220225-1CAT 12G91611 | KABI LAKE FOREST PRODUCTS LTD7925KL-20220225-1CAT 12G91611OEWT-PA26-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7938 | KL-20220227-1 | 53511011 | Access | 0 | CAT 12G | 179 | 7 | HR | 135 | 0 |  |  | 1253 | 162.89 | 1415.89 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader 1 working from 49km to 26km. Grader 2 working from Paint Lake Road to 8km. Loader working on clearing pull offs between 9.2Km & 5Km on Paint Lake Road #2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44628 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7938KL-20220227-1CAT 12G71253 | KABI LAKE FOREST PRODUCTS LTD7938KL-20220227-1CAT 12G71253 | [5 empty] | 1 | 1253 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7944 | KL-20220228-1 | 53511011 | Access | 0 | CAT 12G | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2022-02-28 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader Working On Snow Removal From 29 Km To 2 Km On Paint Lake Road 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44628 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7944KL-20220228-1CAT 12G81432 | KABI LAKE FOREST PRODUCTS LTD7944KL-20220228-1CAT 12G81432 | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7957 | KL-20220302-2 | 53511011 | Access | 0 | CAT 12G | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-03-02 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader working on Snow Removal from Km 49 to Km 13 on Paint Lake Road 2 @ park Grader at Km 2/Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7957KL-20220302-2CAT 12G91611 | KABI LAKE FOREST PRODUCTS LTD7957KL-20220302-2CAT 12G91611 | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7978 | KL-20220306-3 | 53511011 | Access | 0 | CAT 12G | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2022-03-06 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader Working On Snow Removal From Paint Lake Road To 12.5 Km On Paint Lake Road 2/Graded 3 Times Due To Winter Storm/Loader Working From F037 To F034 | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44637 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7978KL-20220306-3CAT 12G101790 | KABI LAKE FOREST PRODUCTS LTD7978KL-20220306-3CAT 12G101790 | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7788 | KL-20220120-1 | 53511011 | Access | 0 | CAT 12G | 179 | 2.5 | HR | 135 | 0 |  |  | 447.5 | 58.175 | 505.675 | 2022-01-20 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F112 to F117 | 10 | F066-F118 | Paint Lake 2 | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7788KL-20220120-1CAT 12G2.5447.5 | KABI LAKE FOREST PRODUCTS LTD7788KL-20220120-1CAT 12G2.5447.5OEWT-PA25-Lem | [5 empty] | 1 | 447.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7799 | KL-20220123-1 | 53511011 | Access | 0 | CAT 12G | 179 | 2.5 | HR | 135 | 0 |  |  | 447.5 | 58.175 | 505.675 | 2022-01-23 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on access and F112 to F117 | 10 | F066-F118 | Paint Lake 2 | 0 | 44588 |  | 61 | 44593 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7799KL-20220123-1CAT 12G2.5447.5 | KABI LAKE FOREST PRODUCTS LTD7799KL-20220123-1CAT 12G2.5447.5OEWT-PA25-Lem | [5 empty] | 1 | 447.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7816 | KL-20220130-1 | 53511011 | Access | 0 | CAT 12G | 179 | 6.5 | HR | 135 | 0 |  |  | 1163.5 | 151.255 | 1314.755 | 2022-01-30 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 49 to Km 36 for stringing crews equipment move /Dozer working from Km 35 to Km 32 widening road , clearing pull offs and spur | 10 | F066-F118 | Paint Lake 2 | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7816KL-20220130-1CAT 12G6.51163.5 | KABI LAKE FOREST PRODUCTS LTD7816KL-20220130-1CAT 12G6.51163.5OEWT-PA26-LEM | [5 empty] | 1 | 1163.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7828 | KL-20220203-1 | 53511011 | Access | 0 | CAT 12G | 179 | 6.5 | HR | 135 | 0 |  |  | 1163.5 | 151.255 | 1314.755 | 2022-02-03 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader benching snow banks & scarifying road from 49 to 40km. Dozer widening road, clearing pull offs & spur roads from 21km to 12.5km. Supervisor doing pickup shuffle. | 10 | F066-F118 | Paint Lake 2 | 0 | 44601 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7828KL-20220203-1CAT 12G6.51163.5 | KABI LAKE FOREST PRODUCTS LTD7828KL-20220203-1CAT 12G6.51163.5OEWT-PA26-LEM | [5 empty] | 1 | 1163.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7843 | KL-20220206-3 | 53511011 | Access | 0 | CAT 12G | 179 | 7 | HR | 135 | 0 |  |  | 1253 | 162.89 | 1415.89 | 2022-02-06 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from 49km to 25km on Paint Lake Road #2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44603 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7843KL-20220206-3CAT 12G71253 | KABI LAKE FOREST PRODUCTS LTD7843KL-20220206-3CAT 12G71253OEWT-PA26-LEM | [5 empty] | 1 | 1253 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7846 | KL-20220207-3 | 53511011 | Access | 0 | CAT 12G | 179 | 4.5 | HR | 135 | 0 |  |  | 805.5 | 104.715 | 910.215 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from 49km to 36km on Paint Lake Road #2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44604 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7846KL-20220207-3CAT 12G4.5805.5 | KABI LAKE FOREST PRODUCTS LTD7846KL-20220207-3CAT 12G4.5805.5OEWT-PA26-LEM | [5 empty] | 1 | 805.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7854 | KL-20220208-3 Field Ticket No. P.O. Box 508, 10 Industrial Park Rd White River ON POM 3G0 Frank Ferland Telephone: 807-822-2532 08-Feb-2022 Email: office@kabilake.com SUMMARY INFORMATION Page 1 of 1 | 53511011 | Access | 0 | CAT 12G | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2022-02-08 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from 49km to 30km on Paint Lake Road #2 & snow removal from F116 to F112. | 10 | F066-F118 | Paint Lake | 0 | 44604 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7854KL-20220208-3 Field Ticket No. P.O. Box 508, 10 Industrial Park Rd White River ON POM 3G0 Frank Ferland Telephone: 807-822-2532 08-Feb-2022 Email: office@kabilake.com SUMMARY INFORMATION Page 1 of 1CAT 12G61074 | KABI LAKE FOREST PRODUCTS LTD7854KL-20220208-3 Field Ticket No. P.O. Box 508, 10 Industrial Park Rd White River ON POM 3G0 Frank Ferland Telephone: 807-822-2532 08-Feb-2022 Email: office@kabilake.com SUMMARY INFORMATION Page 1 of 1CAT 12G61074OEWT-PA26-LEM | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7859 | KL-20220209-2 | 53511011 | Access | 0 | CAT 12G | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2022-02-09 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader benching snowbanks and scarifying sections from Km 49 to Km 32 on Paint Lake Road 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44604 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7859KL-20220209-2CAT 12G81432 | KABI LAKE FOREST PRODUCTS LTD7859KL-20220209-2CAT 12G81432OEWT-PA26-LEM | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7864 | KL-20220210-1 | 53511011 | Access | 0 | CAT 12G | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2022-02-10 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Km 49 to Km 32 on Paint Lake Road 2 /Dozer pushing snowbanks and widening road from Km 9.2 to Km 11/Supervisors doing pickup shuffle | 10 | F066-F118 | Paint Lake | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7864KL-20220210-1CAT 12G5895 | KABI LAKE FOREST PRODUCTS LTD7864KL-20220210-1CAT 12G5895OEWT-PA26-LEM | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7869 | KL-20220211-1 | 53511011 | Access | 0 | CAT 12G | 179 | 6.5 | HR | 135 | 0 |  |  | 1163.5 | 151.255 | 1314.755 | 2022-02-11 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 49 to Km 35 /Dozer pushing snowbanks and widening road from Km 11 to Km 15/Supervisors doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7869KL-20220211-1CAT 12G6.51163.5 | KABI LAKE FOREST PRODUCTS LTD7869KL-20220211-1CAT 12G6.51163.5OEWT-PA26-LEM | [5 empty] | 1 | 1163.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7873 | KL-20220212-1 | 53511011 | Access | 0 | CAT 12G | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2022-02-12 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 49 to Km 29 /Dozer tracking from Km 15 to Km 9.2 for float access/Supervisors doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7873KL-20220212-1CAT 12G61074 | KABI LAKE FOREST PRODUCTS LTD7873KL-20220212-1CAT 12G61074OEWT-PA26-LEM | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7645 | KL-20211206-4 | 53511111 | Access | 0 | CAT 12G | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2021-12-06 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F175 to F171 and from F185 to F193/ Grader working on High Falls Road and to F203 | 11 | F170-F211 | High Falls | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7645KL-20211206-4CAT 12G4716 | KABI LAKE FOREST PRODUCTS LTD7645KL-20211206-4CAT 12G4716OEWT-PA24-LEM | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7649 | KL-20211207-3 | 53511111 | Access | 0 | CAT 12G | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2021-12-07 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F185 to F181 and from F198 to F208/ Grader working on High Falls Road, F200 and F195 access | 11 | F170-F211 | High Falls | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7649KL-20211207-3CAT 12G5895 | KABI LAKE FOREST PRODUCTS LTD7649KL-20211207-3CAT 12G5895OEWT-PA24-LEM | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7651 | KL-20211207-5 | 53511111 | Access | 0 | CAT 12G | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2021-12-07 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal @ Trembley Road and F161 to F164 | 11 | F161-F164 | Trembley Falls | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7651KL-20211207-5CAT 12G5895 | KABI LAKE FOREST PRODUCTS LTD7651KL-20211207-5CAT 12G5895OEWT-PA24-LEM | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7654 | KL-20211208-3 | 53511111 | Access | 0 | CAT 12G | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F198 to F208 & support of stringing equipment. Grader working on High Falls Road, F170, F175, F176, F185 to F181 & F207 access. | 11 | F170-F211 | High Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7654KL-20211208-3CAT 12G91611 | KABI LAKE FOREST PRODUCTS LTD7654KL-20211208-3CAT 12G91611OEWT-PA24-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7656 | KL-20211208-5 | 53511111 | Access | 0 | CAT 12G | 179 | 2.5 | HR | 135 | 0 |  |  | 447.5 | 58.175 | 505.675 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal @ F169 to F165 | 11 | F165-F169 | Magpie Hills | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7656KL-20211208-5CAT 12G2.5447.5 | KABI LAKE FOREST PRODUCTS LTD7656KL-20211208-5CAT 12G2.5447.5OEWT-PA24-LEM | [5 empty] | 1 | 447.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7664 | KL-20211209-7 | 53511111 | Access | 0 | CAT 12G | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal @ F180, F172, F171, F173 & F208 to F211. Grader working on High Falls Road, F185 to F181 & access to F207 | 11 | F170-F211 | High Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7664KL-20211209-7CAT 12G91611 | KABI LAKE FOREST PRODUCTS LTD7664KL-20211209-7CAT 12G91611OEWT-PA24-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7668 | KL-20211210-4 | 53511111 | Access | 0 | CAT 12G | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2021-12-10 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal to F198, F202 & F2003 to F211. Grader working on High Falls road, F180, F194 to F197 & access to F207. | 11 | F170-F211 | High Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7668KL-20211210-4CAT 12G4716 | KABI LAKE FOREST PRODUCTS LTD7668KL-20211210-4CAT 12G4716OEWT-PA24-LEM | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7669 | KL-20211210-5 | 53511111 | Access | 0 | CAT 12G | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2021-12-10 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal @ Trembley Road & F161 to F164 | 11 | F161 - F164 | Trembley Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7669KL-20211210-5CAT 12G5895 | KABI LAKE FOREST PRODUCTS LTD7669KL-20211210-5CAT 12G5895OEWT-PA24-LEM | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7673 | KL-20211211-4 | 53511111 | Access | 0 | CAT 12G | 179 | 9.5 | HR | 135 | 0 |  |  | 1700.5 | 221.065 | 1921.565 | 2021-12-11 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working from F171 to F193 & on High Falls Road to 13Km. | 11 | F170-F211 | High Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7673KL-20211211-4CAT 12G9.51700.5 | KABI LAKE FOREST PRODUCTS LTD7673KL-20211211-4CAT 12G9.51700.5OEWT-PA24-LEM | [5 empty] | 1 | 1700.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7684 | KL-20211212-4 | 53511111 | Access | 0 | CAT 12G | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2021-12-12 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on High Falls Road to Km 13 and F200/ Dozer working from F206 to F211 | 11 | F170-F211 | High Falls | 0 | 44551 |  | 61 | 44561 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7684KL-20211212-4CAT 12G4716 | KABI LAKE FOREST PRODUCTS LTD7684KL-20211212-4CAT 12G4716OEWT-PA24-LEM | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7685 | KL-20211212-5 | 53511111 | Access | 0 | CAT 12G | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2021-12-12 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Snow removal and trembley road and F161 to F164 | 11 | F161 - F164 | Trembley Falls | 0 | 44551 |  | 61 | 44560 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7685KL-20211212-5CAT 12G4716 | KABI LAKE FOREST PRODUCTS LTD7685KL-20211212-5CAT 12G4716OEWT-PA24-LEM | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7690 | KL-20211214-2 | 53511111 | Access | 0 | CAT 12G | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2021-12-14 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working from @ F173 to F171 and on High Falls Road to Km 13 | 11 | F170-F211 | High Falls | 0 | 44551 |  | 61 | 44560 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7690KL-20211214-2CAT 12G91611 | KABI LAKE FOREST PRODUCTS LTD7690KL-20211214-2CAT 12G91611OEWT-PA24-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7696 | KL-20211215-3 | 53511111 | Access | 0 | CAT 12G | 179 | 3 | HR | 135 | 0 |  |  | 537 | 69.81 | 606.81 | 2021-12-15 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working High Falls Road and from @ F173 to F171 | 11 | F170 - F211 | High Falls | 0 |  |  | 46 | 44218 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7696KL-20211215-3CAT 12G3537 | KABI LAKE FOREST PRODUCTS LTD7696KL-20211215-3CAT 12G3537OEWT-PA24-LEM | [5 empty] | 1 | 537 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7698 | KL-20211215-5 | 53511111 | Access | 0 | CAT 12G | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2021-12-15 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Scarifying Trembley Road | 11 | F161 - F164 | Trembley Falls | 0 |  |  | 46 | 44583 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7698KL-20211215-5CAT 12G61074 | KABI LAKE FOREST PRODUCTS LTD7698KL-20211215-5CAT 12G61074OEWT-PA24-LEM | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7701 | KL-20211216-4 | 53511111 | Access | 0 | CAT 12G | 179 | 7 | HR | 135 | 0 |  |  | 1253 | 162.89 | 1415.89 | 2021-12-16 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Stringer Support |  | Approved |  |  | Grader @ High Falls Road in Support of Stringing crew | 11 | F170-F211 | High Falls | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7701KL-20211216-4CAT 12G71253 | KABI LAKE FOREST PRODUCTS LTD7701KL-20211216-4CAT 12G71253OEWT-PA24-LEM | [5 empty] | 1 | 1253 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7721 | KL-20220102-2 | 53511111 | Access | 0 | CAT 12G | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2022-01-02 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on Trembley Road from Harbour Road to Hwy 17 | 11 | F161-F164 | Trembley Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7721KL-20220102-2CAT 12G5895 | KABI LAKE FOREST PRODUCTS LTD7721KL-20220102-2CAT 12G5895OEWT-PA25-Lem | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7722 | KL-20220102-3 | 53511111 | Access | 0 | CAT 12G | 179 | 5.5 | HR | 135 | 0 |  |  | 984.5 | 127.985 | 1112.485 | 2022-01-02 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 3.5 on High Falls Road and F171 to F177 | 11 | F118-F127 | Henson | 0 | 44568 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7722KL-20220102-3CAT 12G5.5984.5 | KABI LAKE FOREST PRODUCTS LTD7722KL-20220102-3CAT 12G5.5984.5OEWT-PA25-Lem | [5 empty] | 1 | 984.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7725 | KL-20220103-3 | 53511111 | Access | 0 | CAT 12G | 179 | 3 | HR | 135 | 0 |  |  | 537 | 69.81 | 606.81 | 2022-01-03 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F164 to F161 | 11 | F161-F164 | Trembley Falls | 0 | 44568 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7725KL-20220103-3CAT 12G3537 | KABI LAKE FOREST PRODUCTS LTD7725KL-20220103-3CAT 12G3537OEWT-PA25-Lem | [5 empty] | 1 | 537 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7726 | KL-20220103-4 | 53511111 | Access | 0 | CAT 12G | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2022-01-03 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F171 to F188 | 11 | F170-F211 | High Falls | 0 | 44568 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7726KL-20220103-4CAT 12G61074 | KABI LAKE FOREST PRODUCTS LTD7726KL-20220103-4CAT 12G61074OEWT-PA25-Lem | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7727 | KL-20220103-5 | 53511111 | Access | 0 | CAT 12G | 179 | 2.5 | HR | 135 | 0 |  |  | 447.5 | 58.175 | 505.675 | 2022-01-03 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F169 to F165 | 11 | F165-F169 | Magpie Hills | 0 | 44568 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7727KL-20220103-5CAT 12G2.5447.5 | KABI LAKE FOREST PRODUCTS LTD7727KL-20220103-5CAT 12G2.5447.5OEWT-PA25-Lem | [5 empty] | 1 | 447.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7730 | KL-20220104-3 | 53511111 | Access | 0 | CAT 12G | 179 | 8.5 | HR | 135 | 0 |  |  | 1521.5 | 197.795 | 1719.295 | 2022-01-04 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F171, F180, F165 and High Falls Road to Km 13 | 11 | F170-F211 | High Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7730KL-20220104-3CAT 12G8.51521.5 | KABI LAKE FOREST PRODUCTS LTD7730KL-20220104-3CAT 12G8.51521.5OEWT-PA25-Lem | [5 empty] | 1 | 1521.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7733 | KL-20220105-3 | 53511111 | Access | 0 | CAT 12G | 179 | 4.5 | HR | 135 | 0 |  |  | 805.5 | 104.715 | 910.215 | 2022-01-05 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  |  | 11 | F161 - F164 | Trembley Falls | 0 | 44572 |  | 46 | 44562 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7733KL-20220105-3CAT 12G4.5805.5 | KABI LAKE FOREST PRODUCTS LTD7733KL-20220105-3CAT 12G4.5805.5OEWT-PA25-Lem | [5 empty] | 1 | 805.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7734 | KL-20220105-4 | 53511111 | Access | 0 | CAT 12G | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2022-01-05 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F171 to F188 | 11 | F170-F211 | High Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7734KL-20220105-4CAT 12G4716 | KABI LAKE FOREST PRODUCTS LTD7734KL-20220105-4CAT 12G4716OEWT-PA25-Lem | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7735 | KL-20220105-5 | 53511111 | Access | 0 | CAT 12G | 179 | 2 | HR | 135 | 0 |  |  | 358 | 46.54 | 404.54 | 2022-01-05 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F169 to F165 | 11 | F165 - F169 | Magpie Hills | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7735KL-20220105-5CAT 12G2358 | KABI LAKE FOREST PRODUCTS LTD7735KL-20220105-5CAT 12G2358OEWT-PA25-Lem | [5 empty] | 1 | 358 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7742 | KL-20220107-4 | 53511111 | Access | 0 | CAT 12G | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2022-01-07 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Trembley Road from Km 6 to Km 1 abd F161 to F164 | 11 | F161 - F164 | Trembley Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7742KL-20220107-4CAT 12G61074 | KABI LAKE FOREST PRODUCTS LTD7742KL-20220107-4CAT 12G61074OEWT-PA25-Lem | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7743 | KL-20220107-5 | 53511111 | Access | 0 | CAT 12G | 179 | 2.5 | HR | 135 | 0 |  |  | 447.5 | 58.175 | 505.675 | 2022-01-07 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working from F171 to F177 | 11 | F170-F211 | High Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7743KL-20220107-5CAT 12G2.5447.5 | KABI LAKE FOREST PRODUCTS LTD7743KL-20220107-5CAT 12G2.5447.5OEWT-PA25-Lem | [5 empty] | 1 | 447.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7746 | KL-20220108-3 | 53511111 | Access | 0 | CAT 12G | 179 | 7 | HR | 135 | 0 |  |  | 1253 | 162.89 | 1415.89 | 2022-01-08 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Trembley Road from Km 6 to Km 1 and F161 to F164 | 11 | F161-F164 | Trembley Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7746KL-20220108-3CAT 12G71253 | KABI LAKE FOREST PRODUCTS LTD7746KL-20220108-3CAT 12G71253OEWT-PA25-Lem | [5 empty] | 1 | 1253 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7747 | KL-20220108-4 | 53511111 | Access | 0 | CAT 12G | 179 | 2 | HR | 135 | 0 |  |  | 358 | 46.54 | 404.54 | 2022-01-08 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working from F171 to F177 | 11 | F170-F211 | High Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7747KL-20220108-4CAT 12G2358 | KABI LAKE FOREST PRODUCTS LTD7747KL-20220108-4CAT 12G2358OEWT-PA25-Lem | [5 empty] | 1 | 358 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7748 | KL-20220108-5 | 53511111 | Access | 0 | CAT 12G | 179 | 2 | HR | 135 | 0 |  |  | 358 | 46.54 | 404.54 | 2022-01-08 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F169 to F165 | 11 | F165 - F169 | Magpie Hills | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7748KL-20220108-5CAT 12G2358 | KABI LAKE FOREST PRODUCTS LTD7748KL-20220108-5CAT 12G2358OEWT-PA25-Lem | [5 empty] | 1 | 358 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7750 | KL-20220109-2 | 53511111 | Access | 0 | CAT 12G | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2022-01-09 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Snow removal from F171 to F188 and clearing pads and pull offs | 11 | F170-F211 | High Falls | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7750KL-20220109-2CAT 12G101790 | KABI LAKE FOREST PRODUCTS LTD7750KL-20220109-2CAT 12G101790OEWT-PA25-Lem | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7753 | KL-20220110-3 | 53511111 | Access | 0 | CAT 12G | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2022-01-10 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Trembley Road from Km 7 to Km 1 and F161 to F164 | 11 | F161 - F164 | Trembley Falls | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7753KL-20220110-3CAT 12G61074 | KABI LAKE FOREST PRODUCTS LTD7753KL-20220110-3CAT 12G61074OEWT-PA25-Lem | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7754 | KL-20220110-4 | 53511111 | Access | 0 | CAT 12G | 179 | 3 | HR | 135 | 0 |  |  | 537 | 69.81 | 606.81 | 2022-01-10 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F169 to F165 and pads | 11 | F165 - F169 | Magpie Hills | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7754KL-20220110-4CAT 12G3537 | KABI LAKE FOREST PRODUCTS LTD7754KL-20220110-4CAT 12G3537OEWT-PA25-Lem | [5 empty] | 1 | 537 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7757 | KL-20220111-3 | 53511111 | Access | 0 | CAT 12G | 179 | 7 | HR | 135 | 0 |  |  | 1253 | 162.89 | 1415.89 | 2022-01-11 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F171 to F188 | 11 | F171 - F211 | High Falls | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7757KL-20220111-3CAT 12G71253 | KABI LAKE FOREST PRODUCTS LTD7757KL-20220111-3CAT 12G71253OEWT-PA25-Lem | [5 empty] | 1 | 1253 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7761 | KL-20220112-4 | 53511111 | Access | 0 | CAT 12G | 179 | 2 | HR | 135 | 0 |  |  | 358 | 46.54 | 404.54 | 2022-01-12 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Scarifying road from F171 to F177 | 11 | F170-F211 | High Falls | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7761KL-20220112-4CAT 12G2358 | KABI LAKE FOREST PRODUCTS LTD7761KL-20220112-4CAT 12G2358OEWT-PA25-Lem | [5 empty] | 1 | 358 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7762 | KL-20220112-5 | 53511111 | Access | 0 | CAT 12G | 179 | 7 | HR | 135 | 0 |  |  | 1253 | 162.89 | 1415.89 | 2022-01-12 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader driving from High Falls, scarifing hills and corners Trembley Road from Km 7 to Km 1 and F161 to F164 | 11 | F161 - F164 | Trembley Falls | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7762KL-20220112-5CAT 12G71253 | KABI LAKE FOREST PRODUCTS LTD7762KL-20220112-5CAT 12G71253OEWT-PA25-Lem | [5 empty] | 1 | 1253 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7766 | KL-20220113-4 | 53511111 | Access | 0 | CAT 12G | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2022-01-13 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader for support of stringing crews @ F171 | 11 | F170-F211 | High Falls | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7766KL-20220113-4CAT 12G5895 | KABI LAKE FOREST PRODUCTS LTD7766KL-20220113-4CAT 12G5895OEWT-PA25-Lem | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7767 | KL-20220113-5 | 53511111 | Access | 0 | CAT 12G | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2022-01-13 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader driving from High Falls, scarifing hills and corners Trembley Road from Km 7 to Km 1 | 11 | F161 - F164 | Trembley Falls | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7767KL-20220113-5CAT 12G4716 | KABI LAKE FOREST PRODUCTS LTD7767KL-20220113-5CAT 12G4716OEWT-PA25-Lem | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7775 | KL-20220115-4 | 53511111 | Access | 0 | CAT 12G | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-01-15 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding hills on Hensen Road with existing material from Km 10.5 / Grader scarifying and benching snow banks on Hensen road from Km .5 to Km 17 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7775KL-20220115-4CAT 12G91611 | KABI LAKE FOREST PRODUCTS LTD7775KL-20220115-4CAT 12G91611OEWT-PA25-Lem | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7778 | KL-20220116-3 | 53511111 | Access | 0 | CAT 12G | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2022-01-16 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader clearing pull offs and sanding in Hensen East / Grader working on snow removal on Hensen road from Km .5 to Km 17 and Hensen East to F132 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7778KL-20220116-3CAT 12G81432 | KABI LAKE FOREST PRODUCTS LTD7778KL-20220116-3CAT 12G81432OEWT-PA25-Lem | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7781 | KL-20220117-3 | 53511111 | Access | 0 | CAT 12G | 179 | 7 | HR | 135 | 0 |  |  | 1253 | 162.89 | 1415.89 | 2022-01-17 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding in Hensen East / Grader working on snow removal on Hensen road from Km .5 to Km 17 and Hensen East to F132 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7781KL-20220117-3CAT 12G71253 | KABI LAKE FOREST PRODUCTS LTD7781KL-20220117-3CAT 12G71253OEWT-PA25-Lem | [5 empty] | 1 | 1253 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7784 | KL-20220118-3 | 53511111 | Access | 0 | CAT 12G | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2022-01-18 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding in Hensen East & driving out to 0.5Km for float. Grader working on benching & pushing back on Hensen road to 15Km. | 11 | F118-F127 | Henson | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7784KL-20220118-3CAT 12G101790 | KABI LAKE FOREST PRODUCTS LTD7784KL-20220118-3CAT 12G101790OEWT-PA25-Lem | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7880 | KL-20220213-4 | 53511111 | Access | 0 | CAT 12G | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2022-02-13 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 1 to Km 6 on Trembley road and from Trembley Road to F161 | 11 | F161 - F164 | Trembley Falls | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7880KL-20220213-4CAT 12G81432 | KABI LAKE FOREST PRODUCTS LTD7880KL-20220213-4CAT 12G81432OEWT-PA26-LEM | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7889 | KL-20220215-2 | 53511111 | Access | 0 | CAT 12G | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2022-02-15 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal and scarifying from Hwy 17 to Km 17 on Hensen Road | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7889KL-20220215-2CAT 12G5895 | KABI LAKE FOREST PRODUCTS LTD7889KL-20220215-2CAT 12G5895OEWT-PA26-LEM | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7894 | KL-20220216-2 | 53511111 | Access | 0 | CAT 12G | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2022-02-16 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen Road / Loader clearing entrance @ Hwy 17 and Hensen Road | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7894KL-20220216-2CAT 12G4716 | KABI LAKE FOREST PRODUCTS LTD7894KL-20220216-2CAT 12G4716OEWT-PA26-LEM | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7898 | KL-20220217-3 | 53511111 | Access | 0 | CAT 12G | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-02-17 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen Road and to F131 in Hensen East / Loader clearing pull off on Hensen Road and F126 Access | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7898KL-20220217-3CAT 12G91611 | KABI LAKE FOREST PRODUCTS LTD7898KL-20220217-3CAT 12G91611OEWT-PA26-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7906 | KL-20220219-2 | 53511111 | Access | 0 | CAT 12G | 179 | 8 | HR | 135 | 0 |  |  | 1432 | 186.16 | 1618.16 | 2022-02-19 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17km on Hensen Road & start benching snow banks | 11 | F118-F127 | Henson | 0 | 44617 |  | 61 | 44617 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7906KL-20220219-2CAT 12G81432 | KABI LAKE FOREST PRODUCTS LTD7906KL-20220219-2CAT 12G81432OEWT-PA26-LEM | [5 empty] | 1 | 1432 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7910 | KL-20220220-2 | 53511111 | Access | 0 | CAT 12G | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2022-02-20 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17Km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44617 |  | 61 | 44617 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7910KL-20220220-2CAT 12G5895 | KABI LAKE FOREST PRODUCTS LTD7910KL-20220220-2CAT 12G5895OEWT-PA26-LEM | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7912 | KL-20220221-2 | 53511111 | Access | 0 | CAT 12G | 179 | 6.5 | HR | 135 | 0 |  |  | 1163.5 | 151.255 | 1314.755 | 2022-02-21 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal & benching snow banks from Hwy 17 to 17Km on Hensen Road. Loader starting clearing of pull offs on Hensen Road & widening corners | 11 | F118-F127 | Henson | 0 | 44617 |  | 61 | 44617 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7912KL-20220221-2CAT 12G6.51163.5 | KABI LAKE FOREST PRODUCTS LTD7912KL-20220221-2CAT 12G6.51163.5OEWT-PA26-LEM | [5 empty] | 1 | 1163.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7914 | KL-20220222-2 | 53511111 | Access | 0 | CAT 12G | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2022-02-22 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen Road /Grader 2 benching snow banks from Km 17 to Hwy 17 | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7914KL-20220222-2CAT 12G5895 | KABI LAKE FOREST PRODUCTS LTD7914KL-20220222-2CAT 12G5895OEWT-PA26-LEM | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7917 | KL-20220223-2 | 53511111 | Access | 0 | CAT 12G | 179 | 5 | HR | 135 | 0 |  |  | 895 | 116.35 | 1011.35 | 2022-02-23 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17km on Hensen Road. Loader widening corners & assisting float trucks | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7917KL-20220223-2CAT 12G5895 | KABI LAKE FOREST PRODUCTS LTD7917KL-20220223-2CAT 12G5895OEWT-PA26-LEM | [5 empty] | 1 | 895 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7926 | KL-20220225-2 | 53511111 | Access | 0 | CAT 12G | 179 | 3 | HR | 135 | 0 |  |  | 537 | 69.81 | 606.81 | 2022-02-25 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying sections from Hwy 17 to 17km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7926KL-20220225-2CAT 12G3537 | KABI LAKE FOREST PRODUCTS LTD7926KL-20220225-2CAT 12G3537OEWT-PA26-LEM | [5 empty] | 1 | 537 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7939 | KL-20220227-2 | 53511111 | Access | 0 | CAT 12G | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader working on snow removal from Hwy 17 to 17Km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7939KL-20220227-2CAT 12G4716 | KABI LAKE FOREST PRODUCTS LTD7939KL-20220227-2CAT 12G4716 | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7945 | KL-20220228-2 | 53511111 | Access | 0 | CAT 12G | 179 | 3 | HR | 135 | 0 |  |  | 537 | 69.81 | 606.81 | 2022-02-28 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader Scarifying Sections From Hwy 17 To 17 Km On Hensen Road | 11 | F118-F127 | Henson | 0 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7945KL-20220228-2CAT 12G3537 | KABI LAKE FOREST PRODUCTS LTD7945KL-20220228-2CAT 12G3537 | [5 empty] | 1 | 537 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7958 | KL-20220302-3 | 53511111 | Access | 0 | CAT 12G | 179 | 2 | HR | 135 | 0 |  |  | 358 | 46.54 | 404.54 | 2022-03-02 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader working on snow removal from Hwy to Km 17 on Hensen Road | 11 | F118-F127 | Henson | 0 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7958KL-20220302-3CAT 12G2358 | KABI LAKE FOREST PRODUCTS LTD7958KL-20220302-3CAT 12G2358 | [5 empty] | 1 | 358 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7787 | KL-20220119-3 | 53511111 | Access | 0 | CAT 12G | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-01-19 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road, clearing pull offs & spur roads from Hensen to F131. grader working on snow removal on Hensen to 17Km and Hensen East to F131. | 11 | F118-F127 | Henson | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7787KL-20220119-3CAT 12G91611 | KABI LAKE FOREST PRODUCTS LTD7787KL-20220119-3CAT 12G91611OEWT-PA25-Lem | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7791 | KL-20220120-4 | 53511111 | Access | 0 | CAT 12G | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-01-20 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on Hensen road to F121, hensen East to F131 & start benching snow banks from 17Km to 13Km. | 11 | F118-F127 | Henson | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7791KL-20220120-4CAT 12G91611 | KABI LAKE FOREST PRODUCTS LTD7791KL-20220120-4CAT 12G91611OEWT-PA25-Lem | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7794 | KL-20220121-2 | 53511111 | Access | 0 | CAT 12G | 179 | 9.5 | HR | 135 | 0 |  |  | 1700.5 | 221.065 | 1921.565 | 2022-01-21 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader finishing benching and pushing snow banks from Km .5 to Km 13 | 11 | F118 - F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7794KL-20220121-2CAT 12G9.51700.5 | KABI LAKE FOREST PRODUCTS LTD7794KL-20220121-2CAT 12G9.51700.5OEWT-PA25-Lem | [5 empty] | 1 | 1700.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7797 | KL-20220122-1 | 53511111 | Access | 0 | CAT 12G | 179 | 13 | HR | 135 | 0 |  |  | 2327 | 302.51 | 2629.51 | 2022-01-22 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on Hensen Road to Km 17 and Hensen East to F132(plowed Hensen Road 3 times due to winter storm) /Loader clearing pulloffs and widening corners to Km 12 | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7797KL-20220122-1CAT 12G132327 | KABI LAKE FOREST PRODUCTS LTD7797KL-20220122-1CAT 12G132327OEWT-PA25-Lem | [5 empty] | 1 | 2327 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7800 | KL-20220123-2 | 53511111 | Access | 0 | CAT 12G | 179 | 8.5 | HR | 135 | 0 |  |  | 1521.5 | 197.795 | 1719.295 | 2022-01-23 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on Hensen Road to F121 and Hensen East to F132/Loader clearing pulloffs and widening corners | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7800KL-20220123-2CAT 12G8.51521.5 | KABI LAKE FOREST PRODUCTS LTD7800KL-20220123-2CAT 12G8.51521.5OEWT-PA25-Lem | [5 empty] | 1 | 1521.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7802 | KL-20220124-2 | 53511111 | Access | 0 | CAT 12G | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2022-01-24 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working benching snowbanks and widening road from Hwy 17 to Km 10/ Loader continuing clearing pulloffs and widening corners | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7802KL-20220124-2CAT 12G101790 | KABI LAKE FOREST PRODUCTS LTD7802KL-20220124-2CAT 12G101790OEWT-PA25-Lem | [5 empty] | 1 | 1790 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7807 | KL-20220125-3 | 53511111 | Access | 0 | CAT 12G | 179 | 9.5 | HR | 135 | 0 |  |  | 1700.5 | 221.065 | 1921.565 | 2022-01-25 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Finishing benching snowbanks, scarifying and widening road from Hwy 17 to Km 10 | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7807KL-20220125-3CAT 12G9.51700.5 | KABI LAKE FOREST PRODUCTS LTD7807KL-20220125-3CAT 12G9.51700.5OEWT-PA25-Lem | [5 empty] | 1 | 1700.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7810 | KL-20220126-2 | 53511111 | Access | 0 | CAT 12G | 179 | 5.5 | HR | 135 | 0 |  |  | 984.5 | 127.985 | 1112.485 | 2022-01-26 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying road from Hwy 17 to Km 10 | 11 | F118-F127 | Henson | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7810KL-20220126-2CAT 12G5.5984.5 | KABI LAKE FOREST PRODUCTS LTD7810KL-20220126-2CAT 12G5.5984.5OEWT-PA26-LEM | [5 empty] | 1 | 984.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7812 | KL-20220128-1 | 53511111 | Access | 0 | CAT 12G | 179 | 12 | HR | 135 | 0 |  |  | 2148 | 279.24 | 2427.24 | 2022-01-28 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 and Hensen east to F131 | 11 | F118-F127 | Hensen | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7812KL-20220128-1CAT 12G122148 | KABI LAKE FOREST PRODUCTS LTD7812KL-20220128-1CAT 12G122148OEWT-PA26-LEM | [5 empty] | 1 | 2148 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7815 | KL-20220129-2 | 53511111 | Access | 0 | CAT 12G | 179 | 12.5 | HR | 135 | 0 |  |  | 2237.5 | 290.875 | 2528.375 | 2022-01-29 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal and scarifying from Hwy 17 to Km 17 on Hensen road and Hensen east to F131 | 11 | F118-F127 | Henson | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7815KL-20220129-2CAT 12G12.52237.5 | KABI LAKE FOREST PRODUCTS LTD7815KL-20220129-2CAT 12G12.52237.5OEWT-PA26-LEM | [5 empty] | 1 | 2237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7817 | KL-20220130-2 | 53511111 | Access | 0 | CAT 12G | 179 | 6.5 | HR | 135 | 0 |  |  | 1163.5 | 151.255 | 1314.755 | 2022-01-30 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal and scarifying from Hwy 17 to Km 17 on Hensen road | 11 | F118-F127 | Henson | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7817KL-20220130-2CAT 12G6.51163.5 | KABI LAKE FOREST PRODUCTS LTD7817KL-20220130-2CAT 12G6.51163.5OEWT-PA26-LEM | [5 empty] | 1 | 1163.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7820 | KL-20220131-3 | 53511111 | Access | 0 | CAT 12G | 179 | 7 | HR | 135 | 0 |  |  | 1253 | 162.89 | 1415.89 | 2022-01-31 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader started benching snowbanks and scarifying from Hwy 17 to Km 6 on Hensen road | 11 | F118-F127 | Henson | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7820KL-20220131-3CAT 12G71253 | KABI LAKE FOREST PRODUCTS LTD7820KL-20220131-3CAT 12G71253OEWT-PA26-LEM | [5 empty] | 1 | 1253 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7824 | KL-20220201-3 | 53511111 | Access | 0 | CAT 12G | 179 | 8.5 | HR | 135 | 0 |  |  | 1521.5 | 197.795 | 1719.295 | 2022-02-01 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader benching snow banks, widening road, scarifying from 6km to 10km & clearing snow drifts @ 14Km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7824KL-20220201-3CAT 12G8.51521.5 | KABI LAKE FOREST PRODUCTS LTD7824KL-20220201-3CAT 12G8.51521.5OEWT-PA26-LEM | [5 empty] | 1 | 1521.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7827 | KL-20220202-2 | 53511111 | Access | 0 | CAT 12G | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2022-02-02 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader finishing benching snow banks, widening road, scarifying from 10km to 17km & clearing snow drifts @ 17Km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7827KL-20220202-2CAT 12G111969 | KABI LAKE FOREST PRODUCTS LTD7827KL-20220202-2CAT 12G111969OEWT-PA26-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7829 | KL-20220203-2 | 53511111 | Access | 0 | CAT 12G | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2022-02-03 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to 17km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7829KL-20220203-2CAT 12G4716 | KABI LAKE FOREST PRODUCTS LTD7829KL-20220203-2CAT 12G4716OEWT-PA26-LEM | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7834 | KL-20220204-3 | 53511111 | Access | 0 | CAT 12G | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2022-02-04 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader widening road and scarifying from Hwy 17 to 17km on Hensen Road and Hensen East to F-131. | 11 | F118-F127 | Henson | 0 | 44603 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7834KL-20220204-3CAT 12G111969 | KABI LAKE FOREST PRODUCTS LTD7834KL-20220204-3CAT 12G111969OEWT-PA26-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7838 | KL-20220205-3 | 53511111 | Access | 0 | CAT 12G | 179 | 11 | HR | 135 | 0 |  |  | 1969 | 255.97 | 2224.97 | 2022-02-05 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader benching snowbanks and scarifying from Hwy 17 to 17km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44603 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7838KL-20220205-3CAT 12G111969 | KABI LAKE FOREST PRODUCTS LTD7838KL-20220205-3CAT 12G111969OEWT-PA26-LEM | [5 empty] | 1 | 1969 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7842 | KL-20220206-2 | 53511111 | Access | 0 | CAT 12G | 179 | 9 | HR | 135 | 0 |  |  | 1611 | 209.43 | 1820.43 | 2022-02-06 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17Km on Hensen Road (cleared road 2 times due to heavy snow. | 11 | F118-F127 | Henson | 0 | 44603 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7842KL-20220206-2CAT 12G91611 | KABI LAKE FOREST PRODUCTS LTD7842KL-20220206-2CAT 12G91611OEWT-PA26-LEM | [5 empty] | 1 | 1611 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7845 | KL-20220207-2 | 53511111 | Access | 0 | CAT 12G | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44604 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7845KL-20220207-2CAT 12G4716 | KABI LAKE FOREST PRODUCTS LTD7845KL-20220207-2CAT 12G4716OEWT-PA26-LEM | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7853 | KL-20220208-2 | 53511111 | Access | 0 | CAT 12G | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2022-02-08 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to 17Km on Hensen Road & snow removal to F131 on Hensen East. Loader clearing pull offs & widening corners to 7km. Supervisor doing pickup shuffle. | 11 | F118 - F127 | Henson | 0 | 44604 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7853KL-20220208-2CAT 12G61074 | KABI LAKE FOREST PRODUCTS LTD7853KL-20220208-2CAT 12G61074OEWT-PA26-LEM | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7862 | KL-20220209-5 | 53511111 | Access | 0 | CAT 12G | 179 | 4 | HR | 135 | 0 |  |  | 716 | 93.08 | 809.08 | 2022-02-09 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to Km 17 on Hensen road /Loader clearing pull offs and widening corners and sanding to Km 12 /Supervisor doing pickup shuffle | 11 | F118-F127 | Henson | 0 | 44604 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7862KL-20220209-5CAT 12G4716 | KABI LAKE FOREST PRODUCTS LTD7862KL-20220209-5CAT 12G4716OEWT-PA26-LEM | [5 empty] | 1 | 716 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7867 | KL-20220210-4 | 53511111 | Access | 0 | CAT 12G | 179 | 5.5 | HR | 135 | 0 |  |  | 984.5 | 127.985 | 1112.485 | 2022-02-10 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to Km 17 on Hensen road and benching snowbanks from Km .5 to Km 5/Loader clearing pull offs and widening corners and sanding from Km 5 to Km 17 | 11 | F118-F127 | Henson | 0 | 44605 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7867KL-20220210-4CAT 12G5.5984.5 | KABI LAKE FOREST PRODUCTS LTD7867KL-20220210-4CAT 12G5.5984.5OEWT-PA26-LEM | [5 empty] | 1 | 984.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7870 | KL-20220211-2 | 53511111 | Access | 0 | CAT 12G | 179 | 6.5 | HR | 135 | 0 |  |  | 1163.5 | 151.255 | 1314.755 | 2022-02-11 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen road /Loader clearing pull offs and sanding from Km 10 to Km 17 | 11 | F118-F127 | Henson | 0 | 44605 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7870KL-20220211-2CAT 12G6.51163.5 | KABI LAKE FOREST PRODUCTS LTD7870KL-20220211-2CAT 12G6.51163.5OEWT-PA26-LEM | [5 empty] | 1 | 1163.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7876 | KL-20220212-4 | 53511111 | Access | 0 | CAT 12G | 179 | 6 | HR | 135 | 0 |  |  | 1074 | 139.62 | 1213.62 | 2022-02-12 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen road and Hensen Road East to F123/Loader clearing pull offs and sanding from Km 10 to Km 4 | 11 | F118-F127 | Henson | 0 | 44605 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7876KL-20220212-4CAT 12G61074 | KABI LAKE FOREST PRODUCTS LTD7876KL-20220212-4CAT 12G61074OEWT-PA26-LEM | [5 empty] | 1 | 1074 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 881 | KL-20200108-1-R1 | 53510711 | Access | 0 | 850 Buncher | 303 | 2.5 | HR | 228 | 0 |  |  | 757.5 | 98.475 | 855.975 | 2020-01-10 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Buncher brushing road line on White Lake Rd., Float truck mobilizing mats from Thunder Bay. Supervisor on-site checking roads & ROW clearing. Buncher and skidder cleared estimated 0.8 Ha | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD881KL-20200108-1-R1850 Buncher2.5757.5 | KABI LAKE FOREST PRODUCTS LTD881KL-20200108-1-R1850 Buncher2.5757.5OEWT-PA1-LEM | [5 empty] | 1 | 757.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 941 | KL-20200128-2 | 53510712 | Access | 0 | 30 ton Log Loader | 195 | 2 | HR | 147 | 0 |  |  | 390 | 50.7 | 440.7 | 2020-01-28 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clear snow from access road. | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 43861 |  | 17 | 43863 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD941KL-20200128-230 ton Log Loader2390 | KABI LAKE FOREST PRODUCTS LTD941KL-20200128-230 ton Log Loader2390OEWT-PA2-LEM-R1 | [5 empty] | 1 | 390 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3485 | KL-20201005-10 | 53510912 | Access | 0 | 30 ton Log Loader | 195 | 4 | HR | 147 | 0 |  |  | 780 | 101.4 | 881.4 | 2020-10-05 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Unplug Culverts at km 40 and 48 on 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44123 |  | 15 | 44125 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3485KL-20201005-1030 ton Log Loader4780 | KABI LAKE FOREST PRODUCTS LTD3485KL-20201005-1030 ton Log Loader4780OEWT-PA10-LEM | [5 empty] | 1 | 780 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3691 | KL-20201012-9 | 53510912 | Access | 0 | 30 ton Log Loader | 195 | 4 | HR | 147 | 0 |  |  | 780 | 101.4 | 881.4 | 2020-10-12 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float and use log loader to unclog culverts @ 49km on 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44126 |  | 15 | 44132 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3691KL-20201012-930 ton Log Loader4780 | KABI LAKE FOREST PRODUCTS LTD3691KL-20201012-930 ton Log Loader4780OEWT-PA10-LEM | [5 empty] | 1 | 780 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6903 | KL-20210511-3 | 53510912 | Access | 0 | 30 ton Log Loader | 195 | 3 | HR | 147 | 0 |  |  | 585 | 76.05 | 661.05 | 2021-05-11 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float 250 link belt log loader from mill yard to 13km on 600 road/unplug culvert and float log loader back to mill yard | 9 | E091-E102 | 600 Road | 0 | 44337 |  | 56 | 44341 | [5 empty] | Mandy Sandhu | 09 | KABI LAKE FOREST PRODUCTS LTD6903KL-20210511-330 ton Log Loader3585 | KABI LAKE FOREST PRODUCTS LTD6903KL-20210511-330 ton Log Loader3585OEWT-PA17-LEM | [5 empty] | 1 | 585 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 966 | KL-20200131-5 | 53510711 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-01-31 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clean and sweep off sand, gravel and snow off bridge | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 43867 |  | 41 | 43869 | [5 empty] | Tom Anderson | 07 | KABI LAKE FOREST PRODUCTS LTD966KL-20200131-5Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD966KL-20200131-5Pickup 1/2 Ton250OEWT-PA2-LEM-R1 | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 975 | KL-20200131-10 | 53510711 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-01-31 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clean sand, gravel and snow from bridge on White Lake Road | 7 | D-142 to E-002 | White Lake | 0 | 43867 |  | 41 | 43869 | [5 empty] | Tom Anderson | 07 | KABI LAKE FOREST PRODUCTS LTD975KL-20200131-10Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD975KL-20200131-10Pickup 1/2 Ton250OEWT-PA2-LEM-R1 | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1058 | KL-20200212-3 | 53510711 | Access | 0 | Pickup 1/2 Ton | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2020-02-12 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Winter access - snow removal from D-142 to D-148 | 7 | D-142 to E-002 | White Lake | 0 | 43878 |  | 42 | 43882 | [5 empty] | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1058KL-20200212-3Pickup 1/2 Ton7175 | KABI LAKE FOREST PRODUCTS LTD1058KL-20200212-3Pickup 1/2 Ton7175OEWT-PA2-LEM-R1 | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1291 | KL-20200313-1 | 53510711 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2020-03-13 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Grade road from HWY to D-038 and D-032 | 7 | D-032 to D-055 | Black River | 0 | 43908 |  | 42 | 43914 | [5 empty] | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1291KL-20200313-1Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD1291KL-20200313-1Pickup 1/2 Ton4100OEWT-PA3-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1296 | KL-20200313-3 | 53510711 | Access | 0 | Pickup 1/2 Ton | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2020-03-13 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade road from HWY and D038 to D054 | 7 | D-032 to D-055 | Black River | 0 | 43907 |  | 42 | 43914 | [5 empty] | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1296KL-20200313-3Pickup 1/2 Ton7175 | KABI LAKE FOREST PRODUCTS LTD1296KL-20200313-3Pickup 1/2 Ton7175OEWT-PA3-LEM | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1303 | KL-20200314-2 | 53510711 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2020-03-14 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow to open road after snow. | 7 | D-018 to D-031 | Pic River West | 0 | 43908 |  | 42 | 43915 | [5 empty] | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1303KL-20200314-2Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD1303KL-20200314-2Pickup 1/2 Ton375OEWT-PA3-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1305 | KL-20200314-4 | 53510711 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2020-03-14 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open road after snow | 7 | D-018 to D-031 | Pic River East | 0 | 43908 |  | 42 | 43915 | [5 empty] | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1305KL-20200314-4Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD1305KL-20200314-4Pickup 1/2 Ton375OEWT-PA3-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1306 | KL-20200314-5 | 53510711 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2020-03-14 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open road after snow | 7 | D-032 to D-055 | Black River | 0 | 43908 |  | 42 | 43915 | [5 empty] | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1306KL-20200314-5Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD1306KL-20200314-5Pickup 1/2 Ton4100OEWT-PA3-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1352 | KL-20200322-1 | 53510711 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2020-03-22 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | PLOW SNOW IN ACCESS ROADS | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 43915 |  | 46 | 43919 | [5 empty] | Dave Ofukany | 07 | KABI LAKE FOREST PRODUCTS LTD1352KL-20200322-1Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD1352KL-20200322-1Pickup 1/2 Ton6150OEWT-PA3-LEM | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1353 | KL-20200322-2 | 53510711 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2020-03-22 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | PICK UP BLASTING MAT FOR ROAD MAINTENANCE | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 43915 |  | 46 | 43919 | [5 empty] | Dave Ofukany | 07 | KABI LAKE FOREST PRODUCTS LTD1353KL-20200322-2Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD1353KL-20200322-2Pickup 1/2 Ton4100OEWT-PA3-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1369 | KL-20200323-5 | 53510711 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-03-23 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clearing Road and prep for log haul | 7 | D-032 to D-055 | Black River | 0 | 43917 |  | 46 | 43921 | [5 empty] | Dave Ofukany | 07 | KABI LAKE FOREST PRODUCTS LTD1369KL-20200323-5Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD1369KL-20200323-5Pickup 1/2 Ton13325OEWT PA4-LEM-R1 | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1378 | KL-20200324-8 | 53510711 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-03-24 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Prep and fix roads for log haul | 7 | D-032 to D-055 | Black River East | 0 | 43917 |  | 46 | 43921 | [5 empty] | Dave Ofukany | 07 | KABI LAKE FOREST PRODUCTS LTD1378KL-20200324-8Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD1378KL-20200324-8Pickup 1/2 Ton12300OEWT PA4-LEM-R1 | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1410 | KL-20200329-4 | 53510711 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2020-03-29 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Drag Road Black River East Main Access to D-051 | 7 | D-032 to D-055 | Black River | 0 | 43927 |  | 45 | 43924 | [5 empty] | Howard Beaudet | 07 | KABI LAKE FOREST PRODUCTS LTD1410KL-20200329-4Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD1410KL-20200329-4Pickup 1/2 Ton5125OEWT PA4-LEM-R1 | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1444 | KL-20200402-5 | 53510711 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-04-02 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair and maintain road from D054 to HWY 17 | 7 | D-032 to D-055 | Black River | 0 | 43930 |  | 43 | 43933 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1444KL-20200402-5Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD1444KL-20200402-5Pickup 1/2 Ton10250OEWT PA4-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5040 | KL-20201218-1 | 53510711 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-12-18 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6K Dozer continuing road maintenance from D032 to D061 | 7 | D-032 to D-055 | Black River | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD5040KL-20201218-1Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD5040KL-20201218-1Pickup 1/2 Ton12300OEWT-PA12-LEM-R1 | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7885 | KL-20220214-3 | 53510711 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2022-02-14 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run Grader from Kabi Yard to Alder Creek Road, clear snow @ entrance for float access and run grader back to Kabi Yard | 7 | D119-D141 | Alder Creek | 0 | 44614 |  | 61 | 44614 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7885KL-20220214-3Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD7885KL-20220214-3Pickup 1/2 Ton5125OEWT-PA26-LEM | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7891 | KL-20220215-4 | 53510711 | Access | 0 | Pickup 1/2 Ton | 25 | 4.5 | HR | 19 | 0 |  |  | 112.5 | 14.625 | 127.125 | 2022-02-15 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on snow removal from Lay Down to D148 for wood grinding access and start snow removal to E002 for stringers | 7 | D142-E002 | White Lake West | 0 | 44614 |  | 61 | 44614 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7891KL-20220215-4Pickup 1/2 Ton4.5112.5 | KABI LAKE FOREST PRODUCTS LTD7891KL-20220215-4Pickup 1/2 Ton4.5112.5OEWT-PA26-LEM | [5 empty] | 1 | 112.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7895 | KL-20220216-3 | 53510711 | Access | 0 | Pickup 1/2 Ton | 25 | 8.5 | HR | 19 | 0 |  |  | 212.5 | 27.625 | 240.125 | 2022-02-16 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing snow removal from Lay Down to D148 and to E002 for stringers | 7 | D142 - E002 | White Lake West | 0 | 44614 |  | 61 | 44614 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7895KL-20220216-3Pickup 1/2 Ton8.5212.5 | KABI LAKE FOREST PRODUCTS LTD7895KL-20220216-3Pickup 1/2 Ton8.5212.5OEWT-PA26-LEM | [5 empty] | 1 | 212.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7895 | KL-20220216-3 | 53510711 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2022-02-16 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing snow removal from Lay Down to D148 and to E002 for stringers | 7 | D142 - E002 | White Lake West | 0 | 44614 |  | 61 | 44614 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7895KL-20220216-3Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD7895KL-20220216-3Pickup 1/2 Ton250OEWT-PA26-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7922 | KL-20220224-3 | 53510711 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2022-02-24 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from E-001 to D148. | 7 | D142 - E002 | White Lake West | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7922KL-20220224-3Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD7922KL-20220224-3Pickup 1/2 Ton4100OEWT-PA26-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7951 | KL-20220207-8 | 53510711 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from 41 road to White Lake West & clear lay down for float turn around. | 7 | D142 - E002 | White Lake West | 0 |  |  | 61 | 44614 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7951KL-20220207-8Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD7951KL-20220207-8Pickup 1/2 Ton250OEWT-PA26-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7851 | KL-20220207-9 | 53510711 | Access | 0 | Pickup 1/2 Ton | 25 | 2.5 | HR | 19 | 0 |  |  | 62.5 | 8.125 | 70.625 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from White Lake West, clear hwy entrance, access & turn around for float access. | 7 | D100-D106 | 614 Road | 0 | 44604 |  | 61 | 44614 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7851KL-20220207-9Pickup 1/2 Ton2.562.5 | KABI LAKE FOREST PRODUCTS LTD7851KL-20220207-9Pickup 1/2 Ton2.562.5OEWT-PA26-LEM | [5 empty] | 1 | 62.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 941 | KL-20200128-2 | 53510712 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2020-01-28 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clear snow from access road. | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 43861 |  | 17 | 43863 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD941KL-20200128-2Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD941KL-20200128-2Pickup 1/2 Ton375OEWT-PA2-LEM-R1 | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1404 | KL-20200328-2 | 53510712 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-03-28 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Push snow banks back on access road , scrape road and grade | 7 | D-119 to D-141 | Alder Creek | 0 | 43925 |  | 45 | 43924 | [5 empty] | Howard Beaudet | 07 | KABI LAKE FOREST PRODUCTS LTD1404KL-20200328-2Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD1404KL-20200328-2Pickup 1/2 Ton10250OEWT PA4-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2300 | KL-20200729-3 | 53510712 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2020-07-29 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road Maintenance from D118 to D116 | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 44047 |  | 50 | 44048 | [5 empty] | Jim Budgell | 07 | KABI LAKE FOREST PRODUCTS LTD2300KL-20200729-3Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD2300KL-20200729-3Pickup 1/2 Ton8200OEWT-PA8-LEM | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2426 | KL-20200812-2 | 53510712 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2020-08-12 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 2 Rock Trucks hauling from stock pile to D132/ Excavator loading | 7 | D-119 to D-141 | Alder Creek | 0 | 44060 |  | 47 | 44061 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD2426KL-20200812-2Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD2426KL-20200812-2Pickup 1/2 Ton6150OEWT-PA8-LEM | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2430 | KL-20200812-6 | 53510712 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2020-08-12 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road Maintenance from D114 to D119 | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 44060 |  | 47 | 44061 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD2430KL-20200812-6Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD2430KL-20200812-6Pickup 1/2 Ton8200OEWT-PA8-LEM | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3820 | KL-20201018-4 | 53510712 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2020-10-18 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Level ruts in Access to D096 to D097 for Drainage | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44130 |  | 47 | 44131 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD3820KL-20201018-4Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD3820KL-20201018-4Pickup 1/2 Ton4100OEWT-PA10-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4480 | KL-20201120-6 | 53510712 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2020-11-20 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working access to ROW & to D74 levelling ruts & track packing road for Pickup Access | 7 | D-074 to D-079 | Brett’s Road | 0 | 44167 |  | 47 | 44173 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4480KL-20201120-6Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD4480KL-20201120-6Pickup 1/2 Ton375OEWT-PA11-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7428 | KL-20211005-2 | 53510712 | Access | 0 | Pickup 1/2 Ton | 25 | 23 | HR | 19 | 0 |  |  | 575 | 74.75 | 649.75 | 2021-10-05 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road & hauling concrete anchors on a rig mat for LEG. Excavator levelling ruts, shaping road, assisting pickups & rock truck. | 7 | D018-D031 | Pic River | 0 | 44477 |  | 37 | 44478 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7428KL-20211005-2Pickup 1/2 Ton23575 | KABI LAKE FOREST PRODUCTS LTD7428KL-20211005-2Pickup 1/2 Ton23575OEWT-PA22-Lem | [5 empty] | 1 | 575 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7399 | KL-20210927-3 | 53510712 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-27 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue hauling pit run from Cress Pit & spreading on ROW access. Dozer levelling ruts after hours. | 7 | D018-D031 | Pic River | 0 | 44475 |  | 62 | 44478 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7399KL-20210927-3Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD7399KL-20210927-3Pickup 1/2 Ton10250OEWT-PA22-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7399 | KL-20210927-3 | 53510712 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2021-09-27 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue hauling pit run from Cress Pit & spreading on ROW access. Dozer levelling ruts after hours. | 7 | D018-D031 | Pic River | 0 | 44475 |  | 62 | 44478 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7399KL-20210927-3Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD7399KL-20210927-3Pickup 1/2 Ton250OEWT-PA22-Lem | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7405 | KL-20210928-3 | 53510712 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2021-09-28 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue hauling pit run from Cress Pit & spreading on ROW access/excavator fixing soft areas & track packing for gravel trucks. Labourer sweeping dirt off Hwy 17 | 7 | D018-D031 | pic River West | 0 | 44475 |  | 62 | 44478 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7405KL-20210928-3Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7405KL-20210928-3Pickup 1/2 Ton12300OEWT-PA22-Lem | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7425 | KL-20211004-2 | 53510712 | Access | 0 | Pickup 1/2 Ton | 25 | 23 | HR | 19 | 0 |  |  | 575 | 74.75 | 649.75 | 2021-10-04 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer & excavator levelling ruts, shaping road, pulling pickups & grout truck to D025 due to wet conditions. Excavator working after hours until all crews got out. | 7 | D018-D031 | Pic River | 0 | 44477 |  | 37 | 44478 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7425KL-20211004-2Pickup 1/2 Ton23575 | KABI LAKE FOREST PRODUCTS LTD7425KL-20211004-2Pickup 1/2 Ton23575OEWT-PA22-Lem | [5 empty] | 1 | 575 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7435 | KL-20211007-2 | 53510712 | Access | 0 | Pickup 1/2 Ton | 25 | 19 | HR | 19 | 0 |  |  | 475 | 61.75 | 536.75 | 2021-10-07 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer & excavator levelling ruts & shaping road from D-019 to D-025. | 7 | D018-D031 | Pic River | 0 | 44484 |  | 37 | 44495 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7435KL-20211007-2Pickup 1/2 Ton19475 | KABI LAKE FOREST PRODUCTS LTD7435KL-20211007-2Pickup 1/2 Ton19475OEWT-PA22-Lem | [5 empty] | 1 | 475 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7470 | KL-20211017-6 | 53510712 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2021-10-17 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Double Star Drilling support hauling steel in and light plant out/back blade and shape road | 7 | D018-D031 | Pic River West | 0 | 44494 |  | 37 | 44495 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7470KL-20211017-6Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD7470KL-20211017-6Pickup 1/2 Ton5125OEWT-PA22-Lem | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1244 | KL-20200308-1 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2020-03-08 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | E-042 to E-053 Open access road to ROW | 8 | E068 - E076 | Denis Lake W | 0 | 43903 |  | 42 | 43910 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1244KL-20200308-1Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD1244KL-20200308-1Pickup 1/2 Ton9225OEWT-PA3-LEM | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1299 | KL-20200313-6 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2020-03-13 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open road from HWY to E-049 | 8 | E-042 to E-053 | Denis Lake W | 0 | 43907 |  | 42 | 43914 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1299KL-20200313-6Pickup 1/2 Ton7175 | KABI LAKE FOREST PRODUCTS LTD1299KL-20200313-6Pickup 1/2 Ton7175OEWT-PA3-LEM | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1325 | KL-20200318-3 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2020-03-18 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue to widen access road | 8 | E-062 to E-067 | Buck Lake | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1325KL-20200318-3Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD1325KL-20200318-3Pickup 1/2 Ton4100OEWT-PA3-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1333 | KL-20200319-7 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-03-19 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | PLOW OPEN (WIDEN) ACCESS RD | 8 | E-062 to E-067 | Buck Lake | 0 | 43913 |  | 42 | 43917 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1333KL-20200319-7Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD1333KL-20200319-7Pickup 1/2 Ton10250OEWT-PA3-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1339 | KL-20200320-2 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2020-03-20 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fix road access to ROW | 8 | E-062 to E-067 | Buck Lake | 0 | 43914 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1339KL-20200320-2Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD1339KL-20200320-2Pickup 1/2 Ton6150OEWT-PA3-LEM | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1496 | KL-20200401-7-R1 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2020-04-01 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair rutts on main access road | 8 | E042-E059 | Denis Lake Road West | 0 | 43933 |  | 45 | 43934 | [5 empty] | Howard Beaudet | 08 | KABI LAKE FOREST PRODUCTS LTD1496KL-20200401-7-R1Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD1496KL-20200401-7-R1Pickup 1/2 Ton5125OEWT PA4-LEM-R1 | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4654 | KL-20201126-8 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load sand from 6km pit on 600 road and sand Access from Hwy to E073 for concrete haul as per discussion with Valard | 8 | E068-E076 | North Crockers Lake | 0 | 44178 |  | 47 | 44183 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4654KL-20201126-8Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD4654KL-20201126-8Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4787 | KL-20201203-7 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2020-12-03 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Padda Roadlines hauling pit run from 5 km pit on 100 road to stockpile/labourers sanding access to stockpile with pickup and shovels. | 8 | E004-E016 | White Lake East | 0 | 44193 |  | 53 | 44207 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4787KL-20201203-7Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD4787KL-20201203-7Pickup 1/2 Ton5125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5000 | KL-20201214-3 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding and Grading Access to E073 for concrete haul as per Valard | 8 | E004-E016 | White Lake East | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD5000KL-20201214-3Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD5000KL-20201214-3Pickup 1/2 Ton375OEWT-PA12-LEM-R1 | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5001 | KL-20201214-4 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Access to E064 | 8 | E062-E067 | Buck Lake | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD5001KL-20201214-4Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5001KL-20201214-4Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5858 | KL-20210211-2 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 5.5 | HR | 19 | 0 |  |  | 137.5 | 17.875 | 155.375 | 2021-02-11 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer doing snow removal from 9020.00 WC to Hwy 17 | 8 | E004-E016 | White Lake East | 0 | 44244 |  | 36 | 44250 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD5858KL-20210211-2Pickup 1/2 Ton5.5137.5 | KABI LAKE FOREST PRODUCTS LTD5858KL-20210211-2Pickup 1/2 Ton5.5137.5OEWT-PA14-Lem-R1 | [5 empty] | 1 | 137.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7882 | KL-20220213-6 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-02-13 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal and widening from Hwy 17 to E004 and clearing pad @ E005 | 8 | E004 - E010 | White Lake East | 0 | 44614 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7882KL-20220213-6Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7882KL-20220213-6Pickup 1/2 Ton12300OEWT-PA26-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7886 | KL-20220214-4 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-02-14 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and widening from Hwy 17 to E013 and clearing pad @ E013 | 8 | E004-E010 | White Lake East | 0 | 44614 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7886KL-20220214-4Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7886KL-20220214-4Pickup 1/2 Ton12300OEWT-PA26-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7890 | KL-20220215-3 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2022-02-15 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer finishing snow removal and widening from Hwy 17 to E013 | 8 | E004 - E010 | White Lake East | 0 | 44614 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7890KL-20220215-3Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7890KL-20220215-3Pickup 1/2 Ton9225OEWT-PA26-LEM | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7907 | KL-20220219-3 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2022-02-19 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal & clearing pull offs from Hwy 17 to E051. | 8 | E042 - E058 | Denis Lake W | 0 | 44617 |  | 61 | 44617 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7907KL-20220219-3Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7907KL-20220219-3Pickup 1/2 Ton11275OEWT-PA26-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7916 | KL-20220223-1 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 7.5 | HR | 19 | 0 |  |  | 187.5 | 24.375 | 211.875 | 2022-02-23 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hwy 17 to E013 & to E005. | 8 | E004 - E010 | White Lake East | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 08 | KABI LAKE FOREST PRODUCTS LTD7916KL-20220223-1Pickup 1/2 Ton7.5187.5 | KABI LAKE FOREST PRODUCTS LTD7916KL-20220223-1Pickup 1/2 Ton7.5187.5OEWT-PA26-LEM | [5 empty] | 1 | 187.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7916 | KL-20220223-1 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2022-02-23 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hwy 17 to E013 & to E005. | 8 | E004 - E010 | White Lake East | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 08 | KABI LAKE FOREST PRODUCTS LTD7916KL-20220223-1Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD7916KL-20220223-1Pickup 1/2 Ton250OEWT-PA26-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7943 | KL-20220227-6 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 6.5 | HR | 19 | 0 |  |  | 162.5 | 21.125 | 183.625 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Dozer working on snow removal & clearing pull offs from Hwy 17 to E-051 | 8 | E042 - E058 | Denis Lake W | 0 | 44628 | [9 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7943KL-20220227-6Pickup 1/2 Ton6.5162.5 | KABI LAKE FOREST PRODUCTS LTD7943KL-20220227-6Pickup 1/2 Ton6.5162.5 | [5 empty] | 1 | 162.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7839 | KL-20220205-4 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2022-02-05 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from Kabi yard, clear snow around highway entrance and turn around for float access. | 8 | E042-E058 | Denis Lake W | 0 | 44603 |  | 61 | 44603 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7839KL-20220205-4Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD7839KL-20220205-4Pickup 1/2 Ton375OEWT-PA26-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7840 | KL-20220205-5 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2022-02-05 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run Grader From Denis Lake West to 41 Road, Clear Snow @ Hwy Entrance, Open Road & Turn Around For Float Access/Supervisor Doing Pickup Shuffle | 8 | E037 - E041 | Road 41 | 0 | 44603 |  | 61 | 44603 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7840KL-20220205-5Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD7840KL-20220205-5Pickup 1/2 Ton4100OEWT-PA26-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7848 | KL-20220207-5 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader clearing hwy entrance, open road & turn around for float access. | 8 | E037-E041 | 41 Road | 0 | 44604 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7848KL-20220207-5Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD7848KL-20220207-5Pickup 1/2 Ton250OEWT-PA26-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7849 | KL-20220207-6 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from 614 road & clear entrance for float access. | 8 | E004 - E010 | White Lake East | 0 | 44604 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7849KL-20220207-6Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD7849KL-20220207-6Pickup 1/2 Ton250OEWT-PA26-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7850 | KL-20220207-7 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from White Lake East, clear hwy entrance & turn around for float access. Run grader to 41 road & park. | 8 | E011-E025 | North Regan | 0 | 44604 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7850KL-20220207-7Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD7850KL-20220207-7Pickup 1/2 Ton250OEWT-PA26-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7856 | KL-20220208-5 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2022-02-08 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run Grader From 41 Road,Clear Hwy Entrance, Open Road For Float Access & Run Grader Back To Kabi Yard | 8 | E025-E036 | Silver City | 0 | 44604 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7856KL-20220208-5Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7856KL-20220208-5Pickup 1/2 Ton9225OEWT-PA26-LEM | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7863 | KL-20220209-6 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-02-09 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hwy 17 to E002 | 10 |  | White Lake east | 0 | 44604 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7863KL-20220209-6Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7863KL-20220209-6Pickup 1/2 Ton12300OEWT-PA26-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7868 | KL-20220210-5 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-02-10 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal from Hwy 17 to E002 and to E008 | 8 | E004 - E010 | White Lake East | 0 | 44605 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7868KL-20220210-5Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7868KL-20220210-5Pickup 1/2 Ton12300OEWT-PA26-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7871 | KL-20220211-3 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2022-02-11 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal from Hwy 17 to E004 | 8 | E004 - E010 | White Lake East | 0 | 44605 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7871KL-20220211-3Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD7871KL-20220211-3Pickup 1/2 Ton4100OEWT-PA26-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7872 | KL-20220211-4 | 53510811 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2022-02-11 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on snow removal from E034 to E035/E036 for wood grinding access | 8 | E025-E036 | SIlver City | 0 | 44605 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7872KL-20220211-4Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD7872KL-20220211-4Pickup 1/2 Ton5125OEWT-PA26-LEM | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1322 | KL-20200317-7 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | RV-40002 SPREAD GRAVEL; HAUL GRAVEL IN SOFT SOPT ACROSS HONI LINE AND TO GAIN ACCESS OVER ROCK IN EXISTING ENTRANCE RD | 8 | E-077 to E-091 | Blue Cedar W | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7Pickup 1/2 Ton10250OEWT-PA3-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3982 | KL-20201026-7 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-10-26 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 excavator doing maintenance on access for concrete trucks as per Valard | 8 | E077-E091 | Blue Cedar | 0 | 44147 |  | 47 | 44151 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3982KL-20201026-7Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD3982KL-20201026-7Pickup 1/2 Ton13325OEWT-PA11-LEM | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3999 | KL-20201027-4 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-10-27 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 excavator doing road maintenance on access for Concrete trucks as per Valard | 8 | E-077 to E-091 | Blue Cedar W | 0 | 44147 |  | 47 | 44151 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3999KL-20201027-4Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD3999KL-20201027-4Pickup 1/2 Ton13325OEWT-PA11-LEM | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4018 | KL-20201028-4 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2020-10-28 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Go down to the Paint Lake Road 1-B and drop off 4 rolls of geotextile | 10 | F021-F032 | Paint Lake Road 1-B | 0 | 44147 |  | 50 | 44162 | [5 empty] | Jim Budgell | 08 | KABI LAKE FOREST PRODUCTS LTD4018KL-20201028-4Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD4018KL-20201028-4Pickup 1/2 Ton6150OEWT-PA11-LEM | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4096 | KL-20201101-5 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 6.5 | HR | 19 | 0 |  |  | 162.5 | 21.125 | 183.625 | 2020-11-01 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator doing Road Maintenance on Access per Valard | 8 | E077-E091 | Blue Cedar W | 0 | 44152 |  | 47 | 44163 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4096KL-20201101-5Pickup 1/2 Ton6.5162.5 | KABI LAKE FOREST PRODUCTS LTD4096KL-20201101-5Pickup 1/2 Ton6.5162.5OEWT-PA11-LEM | [5 empty] | 1 | 162.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4385 | KL-20201114-20 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-11-14 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade access to ROW as per Valard | 8 | E037-E041 | 41 Road | 0 | 44167 |  | 53 | 44171 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4385KL-20201114-20Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD4385KL-20201114-20Pickup 1/2 Ton250OEWT-PA11-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4409 | KL-20201116-8 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T dozer working on road, levelling ruts from E069 to E073 as per Valard. (Cost Code as per Frank 53510812) | 8 | E068-E076 | North Crockers Lake | 0 | 44167 |  | 47 | 44171 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4409KL-20201116-8Pickup 1/2 Ton7175 | KABI LAKE FOREST PRODUCTS LTD4409KL-20201116-8Pickup 1/2 Ton7175OEWT-PA11-LEM | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4410 | KL-20201116-9 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Charged to move Cat D6T dozer to E069/due to Adam from foundations (Cost Code 53510812 as per Frank) | 8 | E068-E076 | North Crockers Lake | 0 | 44167 |  | 47 | 44171 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4410KL-20201116-9Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD4410KL-20201116-9Pickup 1/2 Ton125OEWT-PA11-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4425 | KL-20201117-5 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-11-17 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T dozer working on road, levelling ruts from E069 to E073 as per Valard/Support for Foundations (CC as per Frank 53510812) | 8 | E068-E076 | North Crockers Lake | 0 | 44167 |  | 47 | 44172 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4425KL-20201117-5Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD4425KL-20201117-5Pickup 1/2 Ton12300OEWT-PA11-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4447 | KL-20201118-8 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-11-18 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float had dozer loaded and Valard needed the dozer to stay/support for foundations as per email. | 8 | E068-E076 | North Crockers Lake | 0 | 44167 |  | 14 | 44177 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD4447KL-20201118-8Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD4447KL-20201118-8Pickup 1/2 Ton10250OEWT-PA11-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4460 | KL-20201119-6 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-11-19 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T dozer working on road leveling ruts from E069 to E073 as per valard/ Support for foundations | 8 | E068-E076 | North Crockers Lake | 0 | 44167 |  | 47 | 44172 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4460KL-20201119-6Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD4460KL-20201119-6Pickup 1/2 Ton12300OEWT-PA11-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4485 | KL-20201120-11 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-11-20 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | (CC 53510812 as per Frank) needs cost code changed. |  | Approved |  |  | Cat D6T dozer working on road, levelling ruts from E069 to E073 as per Valard/support for Foundations (CC 53510812 as per Frank) | 8 | E068-E076 | North Regan | 0 | 44167 |  | 47 | 44173 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4485KL-20201120-11Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD4485KL-20201120-11Pickup 1/2 Ton12300OEWT-PA11-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4507 | KL-20201121-8 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2020-11-21 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working access from E077 to E086, levelling ruts & track packing road | 8 | E077-E091 | Blue Cedar Road | 0 | 44167 |  | 47 | 44174 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4507KL-20201121-8Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD4507KL-20201121-8Pickup 1/2 Ton6150OEWT-PA11-LEM | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4550 | KL-20201122-8 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2020-11-22 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working access from E086 to E091, leveling ruts and track packing road for freezing | 8 | E077-E091 | Blue Cedar W | 0 | 44172 |  | 47 | 44184 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4550KL-20201122-8Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD4550KL-20201122-8Pickup 1/2 Ton4100OEWT-PA11-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4551 | KL-20201122-9 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2020-11-22 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T dozer working on AU1 Access shaping and leveling ruts/cleaning up the turn around | 8 | E062-E067 | Buck Lake Road | 0 | 44172 |  | 47 | 44183 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4551KL-20201122-9Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD4551KL-20201122-9Pickup 1/2 Ton6150OEWT-PA11-LEM | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4568 | KL-20201123-6 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-11-23 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working access from E086 to E091, leveling ruts and track packing road for freezing | 8 | E077-E091 | Blue Cedar W | 0 | 44172 |  | 47 | 44175 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4568KL-20201123-6Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD4568KL-20201123-6Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4604 | KL-20201124-7 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2020-11-24 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working Access from E086 to E091, leveling ruts and track packing road for freezing | 8 | E077-E091 | Blue Cedar W | 0 | 44172 |  | 47 | 44179 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4604KL-20201124-7Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD4604KL-20201124-7Pickup 1/2 Ton375OEWT-PA11-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4627 | KL-20201125-4 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working access from E086 to E077, leveling ruts & track packing road for freezing | 8 | E077-E091 | Blue Cedar W | 0 | 44173 |  | 47 | 44183 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4627KL-20201125-4Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD4627KL-20201125-4Pickup 1/2 Ton4100OEWT-PA12-LEM-R1 | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6947 | KL-20210518-4 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2021-05-18 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Original route was reclaimed, total supervision 7 hours. |  | Approved |  |  | Excavator leveling ruts and shapes access to E007 for drainage | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44349 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6947KL-20210518-4Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD6947KL-20210518-4Pickup 1/2 Ton250OEWT-PA17-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6951 | KL-20210519-2 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2021-05-19 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading, hauling and spreading exsiting material @ E014 for road repairs from E016 to E013.5 (revised) | 8 | E034 - E036 | White Lake East | 0 | 44345 |  | 14 | 44352 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6951KL-20210519-2Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD6951KL-20210519-2Pickup 1/2 Ton5125OEWT-PA17-LEM | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6959 | KL-20210520-1 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 17 | HR | 19 | 0 |  |  | 425 | 55.25 | 480.25 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread existing material @ 1.5 km and pit run from stock pile for road repair on E007/E006 main access road/ Laboures laying Geo ( revised) | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6959KL-20210520-1Pickup 1/2 Ton17425 | KABI LAKE FOREST PRODUCTS LTD6959KL-20210520-1Pickup 1/2 Ton17425OEWT-PA17-LEM | [5 empty] | 1 | 425 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6960 | KL-20210520-2 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat excavator Leveling ruts and shaping road from E016 to E010 | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6960KL-20210520-2Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD6960KL-20210520-2Pickup 1/2 Ton11275OEWT-PA17-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6965 | KL-20210520-7 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourers shovelling, sweeping bridges & signage repairs @ 9020.00-WC, 801.00-WC, 9010.00-WC & 9040.00-WC. | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6965KL-20210520-7Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD6965KL-20210520-7Pickup 1/2 Ton125OEWT-PA17-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6967 | KL-20210521-2 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-05-21 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material from stockpile for road repairs to the access going into E005. Dozer spreading loads from from rock truck and fixing ruts. | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6967KL-20210521-2Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD6967KL-20210521-2Pickup 1/2 Ton13325OEWT-PA17-LEM | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6970 | KL-20210522-1 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 14 | HR | 19 | 0 |  |  | 350 | 45.5 | 395.5 | 2021-05-22 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material from stock pile and bundles of wood from the main road to E006 for road repairs, dozer spreading loads and pushing up bundle of wood | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44348 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6970KL-20210522-1Pickup 1/2 Ton14350 | KABI LAKE FOREST PRODUCTS LTD6970KL-20210522-1Pickup 1/2 Ton14350OEWT-PA17-LEM | [5 empty] | 1 | 350 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6980 | KL-20210524-1 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 4.5 | HR | 19 | 0 |  |  | 112.5 | 14.625 | 127.125 | 2021-05-24 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 excavator working on drainage out of E016/Dozer leveling ruts and back blading out from E016 to E006 | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6980KL-20210524-1Pickup 1/2 Ton4.5112.5 | KABI LAKE FOREST PRODUCTS LTD6980KL-20210524-1Pickup 1/2 Ton4.5112.5OEWT-PA17-LEM | [5 empty] | 1 | 112.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6983 | KL-20210525-2 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2021-05-25 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load Haul and spread existing material @ E014 for Road repairs from E015 to E016/Excavator and Dozer working on Road maintenance E013 to E006 | 8 | E004-E016 | White Lake East | 0 | 44343 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6983KL-20210525-2Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD6983KL-20210525-2Pickup 1/2 Ton12300OEWT-PA17-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6988 | KL-20210526-1 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-05-26 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer working on road maintenance leveling ruts and drainage E011 to E016 | 8 | E004-E016 | White Lake East | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6988KL-20210526-1Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD6988KL-20210526-1Pickup 1/2 Ton13325OEWT-PA18-Lem | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6991 | KL-20210527-1 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 14 | HR | 19 | 0 |  |  | 350 | 45.5 | 395.5 | 2021-05-27 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer working on road maintenance leveling ruts and drainage E006 to E016/ Supervisor site visit with Valard ROW and directing Operators | 8 | E004-E016 | White Lake East | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6991KL-20210527-1Pickup 1/2 Ton14350 | KABI LAKE FOREST PRODUCTS LTD6991KL-20210527-1Pickup 1/2 Ton14350OEWT-PA18-Lem | [5 empty] | 1 | 350 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6993 | KL-20210528-1 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 14 | HR | 19 | 0 |  |  | 350 | 45.5 | 395.5 | 2021-05-28 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer working on road maintenance leveling ruts and drainage E006 to E016/ Start shaping hill @E017 Access | 8 | E004-E016 | White Lake East | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6993KL-20210528-1Pickup 1/2 Ton14350 | KABI LAKE FOREST PRODUCTS LTD6993KL-20210528-1Pickup 1/2 Ton14350OEWT-PA18-Lem | [5 empty] | 1 | 350 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7068 | KL-20210529-2 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2021-05-29 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer shaping hill and filling ruts on E017 access from E016 | 8 | E004-E016 | White Lake East | 0 | 44372 |  | 36 | 44373 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD7068KL-20210529-2Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD7068KL-20210529-2Pickup 1/2 Ton4100OEWT-PA18-Lem | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7268 | KL-20210823-2 | 53510812 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-08-23 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair & shape road from 9049.00 WC to E-017. Loader loading rig mats on float for return to Valard Marathon yard | 8 | E017-E024 | North Regan | 0 | 44438 |  | 50 | 44440 | [5 empty] | Jim Budgell | 08 | KABI LAKE FOREST PRODUCTS LTD7268KL-20210823-2Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD7268KL-20210823-2Pickup 1/2 Ton13325OEWT-PA20-Lem | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1222 | KL-20200304-4 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-03-04 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open access roads for WF9 | 7 | E-091 to E-102 | 600 Road | 0 | 43900 |  | 42 | 43910 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1222KL-20200304-4Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD1222KL-20200304-4Pickup 1/2 Ton10250OEWT-PA3-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1225 | KL-20200305-1 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 14 | HR | 19 | 0 |  |  | 350 | 45.5 | 395.5 | 2020-03-05 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open road and make turn arounds on 600 Road | 9 | E-091 to E-102 | 600 road | 0 | 43901 |  | 42 | 43910 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1225KL-20200305-1Pickup 1/2 Ton14350 | KABI LAKE FOREST PRODUCTS LTD1225KL-20200305-1Pickup 1/2 Ton14350OEWT-PA3-LEM | [5 empty] | 1 | 350 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1234 | KL-20200306-5 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2020-03-06 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open 600 road to 32 KM | 9 | E-091 to E-102 | 600 Road | 0 | 43901 |  | 42 | 43910 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1234KL-20200306-5Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD1234KL-20200306-5Pickup 1/2 Ton11275OEWT-PA3-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1254 | KL-20200309-5 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-03-09 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Missing LOA |  | Approved |  |  | Continue to open existing roads on 600 Road. Towers E-104 to E-106 | 9 | E-104 to E-106 | 600 Road | 0 | 43903 |  | 42 | 43911 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1254KL-20200309-5Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD1254KL-20200309-5Pickup 1/2 Ton10250OEWT-PA3-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1310 | KL-20200316-4 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-03-16 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open road by KM 30 and plow after snowfall | 9 | E-091 to E-102 | 600 Road | 0 | 43908 |  | 42 | 43915 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1310KL-20200316-4Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD1310KL-20200316-4Pickup 1/2 Ton12300OEWT-PA3-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1315 | KL-20200317-1 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open road on 600 around km 36 | 9 | E-091 to E-102 | 600 Road. | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1315KL-20200317-1Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD1315KL-20200317-1Pickup 1/2 Ton12300OEWT-PA3-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1324 | KL-20200318-2 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2020-03-18 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | PLOW OPEN ROAD AT 40KM AND WING BACK BANKS | 9 | E-091 to E-102 | 600 Road | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1324KL-20200318-2Pickup 1/2 Ton22550 | KABI LAKE FOREST PRODUCTS LTD1324KL-20200318-2Pickup 1/2 Ton22550OEWT-PA3-LEM | [5 empty] | 1 | 550 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1382 | KL-20200325-4 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-03-25 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open 600 road to gain access | 9 | E-091 to E-102 | 600 Road | 0 | 43922 |  | 45 | 43923 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1382KL-20200325-4Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD1382KL-20200325-4Pickup 1/2 Ton13325OEWT PA4-LEM-R1 | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1387 | KL-20200326-5 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-03-26 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open more access on 600 road aprox 50km | 9 | E-091 to E-102 | 600 Road | 0 | 43922 |  | 45 | 43923 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1387KL-20200326-5Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD1387KL-20200326-5Pickup 1/2 Ton10250OEWT PA4-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1400 | KL-20200327-5 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2020-03-27 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open 600 for WF-9 access and grade road | 9 | E-091 to E-102 | 600 Road | 0 | 43925 |  | 45 | 43924 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1400KL-20200327-5Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD1400KL-20200327-5Pickup 1/2 Ton9.5237.5OEWT PA4-LEM-R1 | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1411 | KL-20200329-5 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-03-29 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open up 600 raod (plow snow) | 9 | E-091 to E-102 | 600 Road | 0 | 43927 |  | 45 | 43924 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1411KL-20200329-5Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD1411KL-20200329-5Pickup 1/2 Ton12300OEWT PA4-LEM-R1 | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1418 | KL-20200330-6 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 23 | HR | 19 | 0 |  |  | 575 | 74.75 | 649.75 | 2020-03-30 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Open up 600 Road (plow snow) | 9 |  | 600 Road | 0 | 43928 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD1418KL-20200330-6Pickup 1/2 Ton23575 | KABI LAKE FOREST PRODUCTS LTD1418KL-20200330-6Pickup 1/2 Ton23575OEWT PA4-LEM-R1 | [5 empty] | 1 | 575 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1427 | KL-20200331-7 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2020-03-31 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow off road | 9 | E091-E102 | 600 Road | 0 | 43928 |  | 45 | 43929 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1427KL-20200331-7Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD1427KL-20200331-7Pickup 1/2 Ton5125OEWT PA4-LEM-R1 | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3988 | KL-20201026-13 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-10-26 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading sander truck and sorting material , sanding 600 road | 9 | E091-E102 | 600 Rd | 0 | 44147 |  | 50 | 44161 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3988KL-20201026-13Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD3988KL-20201026-13Pickup 1/2 Ton10250OEWT-PA11-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4113 | KL-20201102-9 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2020-11-02 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading sander truck and sorting materials at km 20 an km 6 pits on the 600 road and 100 road | 9 | E091-E102 | 600 Rd | 0 | 44153 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4113KL-20201102-9Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD4113KL-20201102-9Pickup 1/2 Ton375OEWT-PA11-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4135 | KL-20201103-5 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading Sand Truck and sorting material at 20km pit and 6km pit on 600 road, sanding 600, 700 and 100 roads | 9 | E-091 to E-102 | 600 Rd | 0 | 44153 |  | 50 | 44159 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4135KL-20201103-5Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD4135KL-20201103-5Pickup 1/2 Ton250OEWT-PA11-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4417 | KL-20201116-16 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road and 100 road to km5 pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4417KL-20201116-16Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD4417KL-20201116-16Pickup 1/2 Ton250OEWT-PA11-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4430 | KL-20201117-9 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-11-17 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 Rd and 100 Rd to km5 pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4430KL-20201117-9Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD4430KL-20201117-9Pickup 1/2 Ton250OEWT-PA11-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4439 | KL-20201118-11 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-11-18 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road and 100 road to 5km pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4439KL-20201118-11Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD4439KL-20201118-11Pickup 1/2 Ton250OEWT-PA11-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4462 | KL-20201119-8 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-11-19 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road and 100 road to 5km pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4462KL-20201119-8Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD4462KL-20201119-8Pickup 1/2 Ton250OEWT-PA11-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4514 | KL-20201121-15 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-11-21 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road, 100 Road, and Access Roads in WF 9 | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4514KL-20201121-15Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD4514KL-20201121-15Pickup 1/2 Ton10250OEWT-PA11-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4578 | KL-20201123-16 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-11-23 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanders 600 road, 700 road and 100 Road | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 15 | 44176 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4578KL-20201123-16Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD4578KL-20201123-16Pickup 1/2 Ton250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4610 | KL-20201124-13 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-11-24 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanders for 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4610KL-20201124-13Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD4610KL-20201124-13Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4659 | KL-20201126-12 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 and 100 road and access roads in WF 9 | 9 | E091-E102 | 600 Road | 0 | 44178 |  | 47 | 44183 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD4659KL-20201126-12Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD4659KL-20201126-12Pickup 1/2 Ton10250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4660 | KL-20201126-13 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of grader 600, 700 and 100 roads. | 9 | E091-E102 | 600 Road | 0 | 44178 |  | 50 | 44208 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4660KL-20201126-13Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD4660KL-20201126-13Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4700 | KL-20201128-8 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-11-28 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanding 600, 700 , 100 and Paint Lake Road 2 | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44201 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4700KL-20201128-8Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD4700KL-20201128-8Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4703 | KL-20201128-11 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-11-28 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600rd, 100rd, and access in WF9 | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44201 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4703KL-20201128-11Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD4703KL-20201128-11Pickup 1/2 Ton10250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4704 | KL-20201128-12 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-11-28 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of grader on 600rd, 700rd, 100rd | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44201 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4704KL-20201128-12Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD4704KL-20201128-12Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4710 | KL-20201129-11 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-11-29 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of sanders for 600, 700, 100, and Paint Lake 2Rd | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44203 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4710KL-20201129-11Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD4710KL-20201129-11Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4723 | KL-20201130-6 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-11-30 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600, 100 roads and access roads in WF9 | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44203 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4723KL-20201130-6Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD4723KL-20201130-6Pickup 1/2 Ton10250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4725 | KL-20201130-8 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-11-30 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision for Sanders for 600, 700, 100, and Paint Lake 2 Roads | 9 | E0914-E102 | 600 Road | 0 | 44181 |  | 50 | 44203 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4725KL-20201130-8Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD4725KL-20201130-8Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4740 | KL-20201201-9 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-01 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervison of grader 600, 700, 100 roads | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4740KL-20201201-9Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD4740KL-20201201-9Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4745 | KL-20201201-17 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-12-01 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600rd, 100rd, and access roads in WF9 | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4745KL-20201201-17Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD4745KL-20201201-17Pickup 1/2 Ton10250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4811 | KL-20201209-13 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-09 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanders 600, 700, and 100 roads. | 9 | E091-E102 | 600 Road | 0 | 44194 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4811KL-20201209-13Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD4811KL-20201209-13Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4812 | KL-20201209-14 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-09 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of graders on 600, 700, roads. | 9 | E061-E102 | 600 Road | 0 | 44194 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4812KL-20201209-14Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD4812KL-20201209-14Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4813 | KL-20201209-15 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-12-09 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 and 700 Road | 9 | E091-E102 | 600 Road | 0 | 44194 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4813KL-20201209-15Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD4813KL-20201209-15Pickup 1/2 Ton10250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4829 | KL-20201211-7 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-12-11 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4829KL-20201211-7Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD4829KL-20201211-7Pickup 1/2 Ton10250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4830 | KL-20201211-8 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-11 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4830KL-20201211-8Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD4830KL-20201211-8Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4989 | KL-20201211-17 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-11 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of float truck for bridge mats pick up and delivery | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4989KL-20201211-17Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD4989KL-20201211-17Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5002 | KL-20201214-5 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 8.5 | HR | 19 | 0 |  |  | 212.5 | 27.625 | 240.125 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5002KL-20201214-5Pickup 1/2 Ton8.5212.5 | KABI LAKE FOREST PRODUCTS LTD5002KL-20201214-5Pickup 1/2 Ton8.5212.5OEWT-PA12-LEM-R1 | [5 empty] | 1 | 212.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5003 | KL-20201214-6 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5003KL-20201214-6Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5003KL-20201214-6Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5005 | KL-20201214-8 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5005KL-20201214-8Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5005KL-20201214-8Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5018 | KL-20201215-6 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-12-15 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44198 |  | 53 | 44210 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5018KL-20201215-6Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD5018KL-20201215-6Pickup 1/2 Ton10250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5019 | KL-20201215-7 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-15 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Grading 600, 700 and 100 roads | 9 | E019-E102 | 600 Road | 0 | 44198 |  | 53 | 44210 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5019KL-20201215-7Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5019KL-20201215-7Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5020 | KL-20201215-8 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-12 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervison of Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44198 |  | 53 | 44210 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5020KL-20201215-8Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5020KL-20201215-8Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5031 | KL-20201216-3 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-12-16 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44210 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5031KL-20201216-3Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD5031KL-20201216-3Pickup 1/2 Ton10250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5032 | KL-20201216-4 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-16 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Grading 600, 700 roads | 9 | E091-E102 | 600 Raod | 0 | 44200 |  | 53 | 44210 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5032KL-20201216-4Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5032KL-20201216-4Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5042 | KL-20201218-3 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2020-12-18 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700 Roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5042KL-20201218-3Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD5042KL-20201218-3Pickup 1/2 Ton6150OEWT-PA12-LEM-R1 | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5043 | KL-20201218-4 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-18 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of grader | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5043KL-20201218-4Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5043KL-20201218-4Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5045 | KL-20201218-6 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-18 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of sanders on 600 rd. | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5045KL-20201218-6Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5045KL-20201218-6Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5056 | KL-20201219-3 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2020-12-19 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 & 700 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5056KL-20201219-3Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD5056KL-20201219-3Pickup 1/2 Ton8200OEWT-PA12-LEM-R1 | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5057 | KL-20201219-4 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-19 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervison for Grading 600 & 700 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5057KL-20201219-4Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5057KL-20201219-4Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5196 | KL-20210102-3 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2021-01-02 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 100 road to km5 pit | 9 | E091-E102 | 600 Road | 0 | 44204 |  | 36 | 44217 | [5 empty] | Mike Lecocq | 09 | KABI LAKE FOREST PRODUCTS LTD5196KL-20210102-3Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD5196KL-20210102-3Pickup 1/2 Ton4100OEWT-PA13-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5413 | KL-20210117-1 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2021-01-17 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding hills on 600 Road between km 52 and Km 22, float truck was stuck on 47km hill | 9 | E091-E102 | 600 Road | 0 | 44216 |  | 53 | 44229 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5413KL-20210117-1Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD5413KL-20210117-1Pickup 1/2 Ton4100OEWT-PA13-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7899 | KL-20220217-4 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 10.5 | HR | 19 | 0 |  |  | 262.5 | 34.125 | 296.625 | 2022-02-17 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from Km 9 to Km 25 on 600 Road | 9 | E092-F009 | 600 Road | 0 | 44614 |  | 61 | 44614 | [6 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD7899KL-20220217-4Pickup 1/2 Ton10.5262.5 | KABI LAKE FOREST PRODUCTS LTD7899KL-20220217-4Pickup 1/2 Ton10.5262.5OEWT-PA26-LEM | [5 empty] | 1 | 262.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7902 | KL-20220218-3 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-02-18 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working snow removal from Km 9 to Km 35 on 600 Road | 9 | E092-F009 | 600 Road | 0 | 44614 |  | 61 | 44614 | [6 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD7902KL-20220218-3Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7902KL-20220218-3Pickup 1/2 Ton12300OEWT-PA26-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7924 | KL-20220224-5 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2022-02-24 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader Starting Working Snow Removal From 9 Km To 12 Km On 600 Road | 9 | E092-F009 | 600 Road | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 09 | KABI LAKE FOREST PRODUCTS LTD7924KL-20220224-5Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD7924KL-20220224-5Pickup 1/2 Ton250OEWT-PA26-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7927 | KL-20220225-3 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2022-02-25 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader and dozer finishing snow removal fro 9km to E-182 on 600 Road | 9 | E092-F009 | 600 Raod | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 09 | KABI LAKE FOREST PRODUCTS LTD7927KL-20220225-3Pickup 1/2 Ton22550 | KABI LAKE FOREST PRODUCTS LTD7927KL-20220225-3Pickup 1/2 Ton22550OEWT-PA26-LEM | [5 empty] | 1 | 550 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7964 | KL-20220303-3 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2022-03-03 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Run Cat 962M Loader From Kabi Yard & Start Snow Removal To E193 On 600 Road | 9 | E092-F009 | 600 Road | 0 | 44630 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD7964KL-20220303-3Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD7964KL-20220303-3Pickup 1/2 Ton375 | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7968 | KL-20220304-3 | 53510911 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2022-03-04 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader Finishing Snow Removal To E193 On 600 Road & Run Loader Back To Kabi Yard | 9 | E092-F009 | 600 Road | 0 | 44630 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD7968KL-20220304-3Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD7968KL-20220304-3Pickup 1/2 Ton13325 | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2305 | KL-20200729-8 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-07-29 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 road from Hwy to Km 11 | 9 | E091-E102 | 600 Road | 0 | 44047 |  | 14 | 44048 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD2305KL-20200729-8Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD2305KL-20200729-8Pickup 1/2 Ton12300OEWT-PA8-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2322 | KL-20200730-14 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-07-30 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Hills on 600 road 11km to 53km | 9 | E091-E102 | 600 Road | 0 | 44048 |  | 50 | 44049 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2322KL-20200730-14Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD2322KL-20200730-14Pickup 1/2 Ton13325OEWT-PA8-LEM | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2336 | KL-20200731-11 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2020-07-31 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road 53km to 49km | 9 | E091-E102. | 600 Road | 0 | 44048 |  | 50 | 44049 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2336KL-20200731-11Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD2336KL-20200731-11Pickup 1/2 Ton8200OEWT-PA8-LEM | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2396 | KL-20200808-3 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-08-08 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44057 |  | 47 | 44057 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2396KL-20200808-3Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD2396KL-20200808-3Pickup 1/2 Ton13325OEWT-PA8-LEM | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2405 | KL-20200809-5 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-08-09 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44057 |  | 47 | 44058 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2405KL-20200809-5Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD2405KL-20200809-5Pickup 1/2 Ton13325OEWT-PA8-LEM | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2407 | KL-20200809-7 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-08-09 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Opas Contracting for structure pad E103 | 9 | E091-E102 | 600 Road | 0 | 44057 |  | 47 | 44058 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2407KL-20200809-7Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD2407KL-20200809-7Pickup 1/2 Ton125OEWT-PA8-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2412 | KL-20200810-5 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-08-10 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 Road | 9 | E091-E102 | 600 Road | 0 | 44057 |  | 47 | 44058 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2412KL-20200810-5Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD2412KL-20200810-5Pickup 1/2 Ton13325OEWT-PA8-LEM | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2419 | KL-20200811-2 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-08-11 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44060 |  | 47 | 44061 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2419KL-20200811-2Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD2419KL-20200811-2Pickup 1/2 Ton13325OEWT-PA8-LEM | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2425 | KL-20200812-1 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-08-12 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 Road!! | 9 | E091-E102 | 600 Road | 0 | 44060 |  | 47 | 44061 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2425KL-20200812-1Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD2425KL-20200812-1Pickup 1/2 Ton10250OEWT-PA8-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2435 | KL-20200813-2 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-08-13 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44062 |  | 47 | 44062 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2435KL-20200813-2Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD2435KL-20200813-2Pickup 1/2 Ton13325OEWT-PA8-LEM | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2444 | KL-20200814-4 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-08-14 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44062 |  | 47 | 44062 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2444KL-20200814-4Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD2444KL-20200814-4Pickup 1/2 Ton13325OEWT-PA8-LEM | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2449 | KL-20200815-4 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-08-15 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Continue grading 600 Road @ 30 Km to 35 Km | 9 | E091-E102 | 600 Road | 0 | 44062 |  | 15 | 44066 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2449KL-20200815-4Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD2449KL-20200815-4Pickup 1/2 Ton13325OEWT-PA8-LEM | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2457 | KL-20200816-4 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-08-16 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E091-E | 600 Road | 0 | 44062 |  | 15 | 44066 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2457KL-20200816-4Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD2457KL-20200816-4Pickup 1/2 Ton13325OEWT-PA8-LEM | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2635 | KL-20200831-7 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-08-31 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E091-E102 | 600 Road | 0 | 44084 |  | 50 | 44087 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2635KL-20200831-7Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD2635KL-20200831-7Pickup 1/2 Ton13325OEWT-PA9-Lem-R1 | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2647 | KL-20200901-10 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2020-09-01 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road Km 31 -33 | 9 | E092-E109 | 600 Road | 0 | 44084 |  | 50 | 44087 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2647KL-20200901-10Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD2647KL-20200901-10Pickup 1/2 Ton11275OEWT-PA9-Lem-R1 | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2677 | KL-20200903-14 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2020-09-03 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E091-E102 | 600 Road | 0 | 44084 |  | 50 | 44088 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2677KL-20200903-14Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD2677KL-20200903-14Pickup 1/2 Ton11275OEWT-PA9-Lem-R1 | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2689 | KL-20200904-10 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-09-04 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44088 |  | 50 | 44089 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2689KL-20200904-10Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD2689KL-20200904-10Pickup 1/2 Ton13325OEWT-PA9-Lem-R1 | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3289 | KL-20200928-12 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-09-28 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E091-E102 | 600 road | 0 | 44109 |  | 15 | 44121 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3289KL-20200928-12Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD3289KL-20200928-12Pickup 1/2 Ton13325OEWT-PA10-LEM | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3320 | KL-20200929-11 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-09-29 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44109 |  | 50 | 44115 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3320KL-20200929-11Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD3320KL-20200929-11Pickup 1/2 Ton13325OEWT-PA10-LEM | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3485 | KL-20201005-10 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-10-05 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Unplug Culverts at km 40 and 48 on 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44123 |  | 15 | 44125 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3485KL-20201005-10Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD3485KL-20201005-10Pickup 1/2 Ton250OEWT-PA10-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3792 | KL-20201016-10 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-10-16 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44130 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3792KL-20201016-10Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD3792KL-20201016-10Pickup 1/2 Ton10250OEWT-PA10-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3986 | KL-20201026-11-R1 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-10-26 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of WF 9 | 9 | E091-E102 | 600 Rd | 0 | 44147 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3986KL-20201026-11-R1Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD3986KL-20201026-11-R1Pickup 1/2 Ton10250OEWT-PA11-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3990 | KL-20201026-15 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 20 | HR | 19 | 0 |  |  | 500 | 65 | 565 | 2020-10-26 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E091-E102 | 600 Rd | 0 | 44147 |  | 50 | 44161 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3990KL-20201026-15Pickup 1/2 Ton20500 | KABI LAKE FOREST PRODUCTS LTD3990KL-20201026-15Pickup 1/2 Ton20500OEWT-PA11-LEM | [5 empty] | 1 | 500 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4005 | KL-20201027-10 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 20 | HR | 19 | 0 |  |  | 500 | 65 | 565 | 2020-10-27 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E091-E102 | 600 Rd | 0 | 44147 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4005KL-20201027-10Pickup 1/2 Ton20500 | KABI LAKE FOREST PRODUCTS LTD4005KL-20201027-10Pickup 1/2 Ton20500OEWT-PA11-LEM | [5 empty] | 1 | 500 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4021 | KL-20201028-8 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 20 | HR | 19 | 0 |  |  | 500 | 65 | 565 | 2020-10-28 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E091-E102 | 600 Rd | 0 | 44147 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4021KL-20201028-8Pickup 1/2 Ton20500 | KABI LAKE FOREST PRODUCTS LTD4021KL-20201028-8Pickup 1/2 Ton20500OEWT-PA11-LEM | [5 empty] | 1 | 500 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4064 | KL-20201030-6 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-10-30 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fix Roads between E95 to E102 | 9 | E091-E102 | 600 Rd | 0 | 44152 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4064KL-20201030-6Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD4064KL-20201030-6Pickup 1/2 Ton10250OEWT-PA11-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4065 | KL-20201030-7 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-10-30 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Paint Lake Road 2 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44152 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4065KL-20201030-7Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD4065KL-20201030-7Pickup 1/2 Ton10250OEWT-PA11-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4072 | KL-20201030-14 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-10-30 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of WF 9 (revised Hours) | 9 | E091-E102 | 600 Rd | 0 | 44152 |  | 56 | 44163 | [5 empty] | Mandy Sandhu | 09 | KABI LAKE FOREST PRODUCTS LTD4072KL-20201030-14Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD4072KL-20201030-14Pickup 1/2 Ton10250OEWT-PA11-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4397 | KL-20201115-11 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2020-11-15 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road and 100 Road. | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 53 | 44171 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4397KL-20201115-11Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD4397KL-20201115-11Pickup 1/2 Ton11275OEWT-PA11-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4415 | KL-20201116-14 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fix roads E168 to E171 and E212 to E210 | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4415KL-20201116-14Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD4415KL-20201116-14Pickup 1/2 Ton8200OEWT-PA11-LEM | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4416 | KL-20201116-15 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road, 100 road, Paint Lake 2 Rd | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4416KL-20201116-15Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD4416KL-20201116-15Pickup 1/2 Ton11275OEWT-PA11-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4431 | KL-20201117-10 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2020-11-17 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 rd, 100 rd, and Paint Lake 2 road | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4431KL-20201117-10Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD4431KL-20201117-10Pickup 1/2 Ton11275OEWT-PA11-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4463 | KL-20201119-9 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-11-19 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shaping up and back blading access roads E217 to E194 | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4463KL-20201119-9Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD4463KL-20201119-9Pickup 1/2 Ton12300OEWT-PA11-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4522 | KL-20201031-16 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-10-31 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of WF 9 and WF 10 (Revised Hours) | 9 | E091-E102 | 600 Road | 0 | 44174 |  | 56 | 44174 | [5 empty] | Mandy Sandhu | 09 | KABI LAKE FOREST PRODUCTS LTD4522KL-20201031-16Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD4522KL-20201031-16Pickup 1/2 Ton10250OEWT-PA11-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4573 | KL-20201123-11 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 14 | HR | 19 | 0 |  |  | 350 | 45.5 | 395.5 | 2020-11-23 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shaping up and back blading access roads and pulling a drag F3 and F9 | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 15 | 44175 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4573KL-20201123-11Pickup 1/2 Ton14350 | KABI LAKE FOREST PRODUCTS LTD4573KL-20201123-11Pickup 1/2 Ton14350OEWT-PA12-LEM-R1 | [5 empty] | 1 | 350 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4575 | KL-20201123-13 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-11-23 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Contine grading 600 road and 100 roadand access roads in WF 9 | 9 | E091-E102 | 600 road | 0 | 44172 |  | 15 | 44176 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4575KL-20201123-13Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD4575KL-20201123-13Pickup 1/2 Ton10250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4577 | KL-20201123-15 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-11-23 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Grader 600 road, 700 road and 100 Road | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 15 | 44176 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4577KL-20201123-15Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD4577KL-20201123-15Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4605 | KL-20201124-8 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2020-11-24 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shaping up and back blading access road and pulling a drag F3, F9 | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4605KL-20201124-8Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD4605KL-20201124-8Pickup 1/2 Ton11275OEWT-PA12-LEM-R1 | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4607 | KL-20201124-10 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-11-24 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road, 100 road and access roads in WF 9 | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4607KL-20201124-10Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD4607KL-20201124-10Pickup 1/2 Ton10250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4608 | KL-20201124-11 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-11-24 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Grading 600 road, 100 road and 700 road | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4608KL-20201124-11Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD4608KL-20201124-11Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4634 | KL-20201125-11 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600rd, 100rd, and access rds in WF9 | 9 | E091-E102 | 600 Road | 0 | 44173 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4634KL-20201125-11Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD4634KL-20201125-11Pickup 1/2 Ton10250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4637 | KL-20201125-14 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shaping up and back blading access roads and pulling a drag F3-F9 | 9 | E091-E102 | 600 Road | 0 | 44173 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4637KL-20201125-14Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD4637KL-20201125-14Pickup 1/2 Ton12300OEWT-PA12-LEM-R1 | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6949 | KL-20210518-6 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-05-18 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T dozer leveling ruts and shaping road E200 to E216/ Supervisor while checking on Operator and process did pickup shuffle (Revised) | 9 | E091-E102 | 600 Road | 0 | 44345 |  | 14 | 44349 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD6949KL-20210518-6Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD6949KL-20210518-6Pickup 1/2 Ton13325OEWT-PA17-LEM | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6953 | KL-20210519-4 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-05-19 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 14M grader started road maintenance from Km 1 to Km 18 on 600 road labourers spotted pickup @Km 18 for grader operator (revised) | 9 | E091-E102 | 600 Road | 0 | 44345 |  | 14 | 44352 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD6953KL-20210519-4Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD6953KL-20210519-4Pickup 1/2 Ton11275OEWT-PA17-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6962 | KL-20210520-4 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 14M grader continuing grading of 600 road and repairing small wash out/ labourer spotting pickup @ 22km for grader operator ( revised ) | 9 | E091-E102 | 600 Road | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD6962KL-20210520-4Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD6962KL-20210520-4Pickup 1/2 Ton11275OEWT-PA17-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6968 | KL-20210521-3 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 8.5 | HR | 19 | 0 |  |  | 212.5 | 27.625 | 240.125 | 2021-05-21 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 14M grader continuing grading of 600 Road and repairing small wash outs | 9 | E091-E102 | 600 Road | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD6968KL-20210521-3Pickup 1/2 Ton8.5212.5 | KABI LAKE FOREST PRODUCTS LTD6968KL-20210521-3Pickup 1/2 Ton8.5212.5OEWT-PA17-LEM | [5 empty] | 1 | 212.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6985 | KL-20210525-3 | 53510912 | Access | 0 | Pickup 1/2 Ton | 25 | 4.5 | HR | 19 | 0 |  |  | 112.5 | 14.625 | 127.125 | 2021-05-25 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 14M grader continuing grading of 600 road and repairing small washouts | 9 | E091-E102 | 600 Road | 0 | 44348 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 09 | KABI LAKE FOREST PRODUCTS LTD6985KL-20210525-3Pickup 1/2 Ton4.5112.5 | KABI LAKE FOREST PRODUCTS LTD6985KL-20210525-3Pickup 1/2 Ton4.5112.5OEWT-PA17-LEM | [5 empty] | 1 | 112.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511003 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-09-20 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44466 |  | 50 | 44466 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1Pickup 1/2 Ton9.5237.5OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.59731 | 141.8614 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511003 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-09-20 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44466 |  | 50 | 44466 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1Pickup 1/2 Ton9225OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.59731 | 134.395 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511003 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-09-20 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44466 |  | 50 | 44466 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1Pickup 1/2 Ton9225OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.59731 | 134.395 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511003 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2021-09-20 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44466 |  | 50 | 44466 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1Pickup 1/2 Ton8200OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.59731 | 119.4622 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7361 | KL-20210919-1 | 53511003 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-09-19 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km and pulling pickups @ end of shift /Chapman rock truck hauling trees from F104 to Morin @ km 41 and 42. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44466 |  | 50 | 44466 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-1Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-1Pickup 1/2 Ton9225OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 112.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7361 | KL-20210919-1 | 53511003 | Access | 0 | Pickup 1/2 Ton | 25 | 23 | HR | 19 | 0 |  |  | 575 | 74.75 | 649.75 | 2021-09-19 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km and pulling pickups @ end of shift /Chapman rock truck hauling trees from F104 to Morin @ km 41 and 42. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44466 |  | 50 | 44466 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-1Pickup 1/2 Ton23575 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-1Pickup 1/2 Ton23575OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 287.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7370 | KL-20210921-1 | 53511003 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-09-21 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 17 to 20 km/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44467 |  | 50 | 44467 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1Pickup 1/2 Ton9225OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.51171 | 115.1342 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7379 | KL-20210923-1 | 53511003 | Access | 0 | Pickup 1/2 Ton | 25 | 18 | HR | 19 | 0 |  |  | 450 | 58.5 | 508.5 | 2021-09-23 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees@ 18 km, excavator 2 placing trees/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 61 | 44471 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-1Pickup 1/2 Ton18450 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-1Pickup 1/2 Ton18450OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7379 | KL-20210923-1 | 53511003 | Access | 0 | Pickup 1/2 Ton | 25 | 17 | HR | 19 | 0 |  |  | 425 | 55.25 | 480.25 | 2021-09-23 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees@ 18 km, excavator 2 placing trees/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 61 | 44471 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-1Pickup 1/2 Ton17425 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-1Pickup 1/2 Ton17425OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 212.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7248 | KL-20210819-4 | 53511004 | Access | 0 | Pickup 1/2 Ton | 25 | 19 | HR | 19 | 0 |  |  | 475 | 61.75 | 536.75 | 2021-08-19 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44433 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7248KL-20210819-4Pickup 1/2 Ton19475 | KABI LAKE FOREST PRODUCTS LTD7248KL-20210819-4Pickup 1/2 Ton19475OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 475 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7252 | KL-20210820-5 | 53511004 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-08-20 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44433 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-5Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-5Pickup 1/2 Ton9225OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7252 | KL-20210820-5 | 53511004 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-08-20 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44433 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-5Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-5Pickup 1/2 Ton9225OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7257 | KL-20210821-5 | 53511004 | Access | 0 | Pickup 1/2 Ton | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-08-21 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/46/3 rock trucks Kabi, Corbiere and Valard/ 2nd Ex working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44434 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-5Pickup 1/2 Ton22550 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-5Pickup 1/2 Ton22550OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 550 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7267 | KL-20210822-4 | 53511004 | Access | 0 | Pickup 1/2 Ton | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-08-22 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/4. One Kabi rock truck, one Corbiere, and 1 Valard. 2nd excavator working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 50 | 44440 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-4Pickup 1/2 Ton22550 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-4Pickup 1/2 Ton22550OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 550 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7271 | KL-20210823-5 | 53511004 | Access | 0 | Pickup 1/2 Ton | 25 | 21 | HR | 19 | 0 |  |  | 525 | 68.25 | 593.25 | 2021-08-23 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/44. One Kabi rock truck, Corbiere and Valard/ 2nd Ex working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 37 | 44439 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-5Pickup 1/2 Ton21525 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-5Pickup 1/2 Ton21525OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 525 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7275 | KL-20210824-3 | 53511004 | Access | 0 | Pickup 1/2 Ton | 25 | 18 | HR | 19 | 0 |  |  | 450 | 58.5 | 508.5 | 2021-08-24 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from km 17 on Hensen Road to Corbiere Dozer@km 44.5/43.5/3 rock trucks Kabi, Corbiere and Valard/ Excavator 2 working ahead @km 42 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-3Pickup 1/2 Ton18450 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-3Pickup 1/2 Ton18450OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 450 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7285 | KL-20210828-3 | 53511004 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-08-28 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from km49 to Skagen excavator @ 46/45 km - 1 Kabi , 1 Chapman and 2 Cobiere rock trucks | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7285KL-20210828-3Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD7285KL-20210828-3Pickup 1/2 Ton13325OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7288 | KL-20210830-2 | 53511004 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-08-30 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks/ excavator 2 shaping and leveling slopes | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44439 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-2Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-2Pickup 1/2 Ton9225OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7292 | KL-20210831-2 | 53511004 | Access | 0 | Pickup 1/2 Ton | 25 | 21 | HR | 19 | 0 |  |  | 525 | 68.25 | 593.25 | 2021-08-31 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from 49 Km to 44/43Km. 1 Kabi rock truck, 2 Corbiere Rock Trucks & 1 Chapman Rock Truck. Excavator 2 tracking from 49Km to F-086 for gravel haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44442 |  | 37 | 44445 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-2Pickup 1/2 Ton21525 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-2Pickup 1/2 Ton21525OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 525 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7307 | KL-20210901-2 | 53511004 | Access | 0 | Pickup 1/2 Ton | 25 | 21 | HR | 19 | 0 |  |  | 525 | 68.25 | 593.25 | 2021-09-01 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from @ km49 to Skagen excavator @ km 43/ 2 Kabi , 1 Chapman and 3 Cobiere rock trucks/ excavator 2 preping access @km 35 to 34 for gravel Haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 37 | 44457 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-2Pickup 1/2 Ton21525 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-2Pickup 1/2 Ton21525OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 525 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7311 | KL-20210902-2 | 53511004 | Access | 0 | Pickup 1/2 Ton | 25 | 23 | HR | 19 | 0 |  |  | 575 | 74.75 | 649.75 | 2021-09-02 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from 38.5 km Morin excavator @ km 40/41 for road capping | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 37 | 44457 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7311KL-20210902-2Pickup 1/2 Ton23575 | KABI LAKE FOREST PRODUCTS LTD7311KL-20210902-2Pickup 1/2 Ton23575OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 575 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7312 | KL-20210903-2 | 53511004 | Access | 0 | Pickup 1/2 Ton | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-09-03 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from 38.5 km Morin excavator @ km 40/41 for road capping | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 50 | 44450 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7312KL-20210903-2Pickup 1/2 Ton22550 | KABI LAKE FOREST PRODUCTS LTD7312KL-20210903-2Pickup 1/2 Ton22550OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 550 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7330 | KL-20210910-2 | 53511004 | Access | 0 | Pickup 1/2 Ton | 25 | 18.5 | HR | 19 | 0 |  |  | 462.5 | 60.125 | 522.625 | 2021-09-10 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 12 and Km 5 to Km 19 / 1 rock truck hauling from 38 km to Morin Excavator @ 40/42 km/rock truck 2 driving from Hwy to Km 38 and haul gravel | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44454 |  | 50 | 44462 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-2Pickup 1/2 Ton18.5462.5 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-2Pickup 1/2 Ton18.5462.5OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.81072 | 374.9593 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7334 | KL-20210912-2 | 53511004 | Access | 0 | Pickup 1/2 Ton | 25 | 43 | HR | 19 | 0 |  |  | 1075 | 139.75 | 1214.75 | 2021-09-12 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 19/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44460 |  | 50 | 44462 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-2Pickup 1/2 Ton431075 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-2Pickup 1/2 Ton431075OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.68622 | 737.6861 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7335 | KL-20210913-2 | 53511004 | Access | 0 | Pickup 1/2 Ton | 25 | 36 | HR | 19 | 0 |  |  | 900 | 117 | 1017 | 2021-09-13 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44460 |  |  | 44461 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2Pickup 1/2 Ton36900 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2Pickup 1/2 Ton36900OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.79105 | 711.9439 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7335 | KL-20210913-2 | 53511004 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-13 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44460 |  |  | 44461 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2Pickup 1/2 Ton10250OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.79105 | 197.7622 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511004 | Access | 0 | Pickup 1/2 Ton | 25 | 15 | HR | 19 | 0 |  |  | 375 | 48.75 | 423.75 | 2021-09-14 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 44460 |  |  | 44461 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2Pickup 1/2 Ton15375 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2Pickup 1/2 Ton15375OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 187.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7279 | KL-20210825-3 | 53511004 | Access | 0 | Pickup 1/2 Ton | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-08-25 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 42 to Morin Excavator/ Excavator 2 fixing up access from Km 44 to Km 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7279KL-20210825-3Pickup 1/2 Ton22550 | KABI LAKE FOREST PRODUCTS LTD7279KL-20210825-3Pickup 1/2 Ton22550OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 550 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7347 | KL-20210915-1 | 53511004 | Access | 0 | Pickup 1/2 Ton | 25 | 27 | HR | 19 | 0 |  |  | 675 | 87.75 | 762.75 | 2021-09-15 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator working from 18 to 19.5 km leveling ruts and shaping road for pick up access /Chapman rock truck and Kabi 30 ton rock truck on site to haul with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44454 |  |  | 44464 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-1Pickup 1/2 Ton27675 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-1Pickup 1/2 Ton27675OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 0.5 | 0.5 | 337.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511004 | Access | 0 | Pickup 1/2 Ton | 25 | 18.5 | HR | 19 | 0 |  |  | 462.5 | 60.125 | 522.625 | 2021-09-27 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44475 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1Pickup 1/2 Ton18.5462.5 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1Pickup 1/2 Ton18.5462.5OEWT-PA22-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 462.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4663 | KL-20201126-16 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shaping and back blading access road and pulling a drag F09, F24 | 10 | F009-F020 | Paint Lake Road 1-A | 0 | 44178 |  | 50 | 44208 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD4663KL-20201126-16Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD4663KL-20201126-16Pickup 1/2 Ton12300OEWT-PA12-LEM-R1 | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4708 | KL-20201129-7 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-11-29 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading Paint Lake 2 Road | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44181 |  | 47 | 44208 | [5 empty] | Bruce Bennett | 10 | KABI LAKE FOREST PRODUCTS LTD4708KL-20201129-7Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD4708KL-20201129-7Pickup 1/2 Ton10250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4791 | KL-20201203-11 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-03 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of float truck for picking up 40' bridge mats in Marathon, and deliver to Paint Lake RD 1-B | 10 | F021-F032 | Paint Lake Road 1-B | 0 | 44193 |  | 50 | 44206 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD4791KL-20201203-11Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD4791KL-20201203-11Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5181 | KL-20201231-4 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-12-31 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Paint lake road 2 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44204 |  | 56 | 44216 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD5181KL-20201231-4Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD5181KL-20201231-4Pickup 1/2 Ton10250OEWT-PA13-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5188 | KL-20210101-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-01-01 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Paint Lake road 2 and 600 Road | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44204 |  | 56 | 44216 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD5188KL-20210101-1Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD5188KL-20210101-1Pickup 1/2 Ton10250OEWT-PA13-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5841 | KL-20210210-3 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2021-02-10 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer plow snow & open road between F21 to F32 | 10 | F021-F032 | Paint Lake Road 1-B | 0 | 44244 |  | 50 | 44249 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5841KL-20210210-3Pickup 1/2 Ton7175 | KABI LAKE FOREST PRODUCTS LTD5841KL-20210210-3Pickup 1/2 Ton7175OEWT-PA14-Lem-R1 | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5976 | KL-20210220-3 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 14 | HR | 19 | 0 |  |  | 350 | 45.5 | 395.5 | 2021-02-20 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Paint Lake 2 Road, Plow snow on access road. Corduroy F62-F63 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44252 |  | 57 | 44252 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD5976KL-20210220-3Pickup 1/2 Ton14350 | KABI LAKE FOREST PRODUCTS LTD5976KL-20210220-3Pickup 1/2 Ton14350OEWT-PA14-Lem-R1 | [5 empty] | 1 | 350 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6017 | KL-20210223-10 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2021-02-23 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, work on snow crossing, haul and place rig mats, load and haul gravel. Haul and spread gravel, roll out geo, hammer access road to F60 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44253 |  | 57 | 44257 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD6017KL-20210223-10Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD6017KL-20210223-10Pickup 1/2 Ton8200OEWT-PA14-Lem-R1 | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6021 | KL-20210224-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2021-02-24 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, load and haul gravel. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44256 |  | 57 | 44259 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD6021KL-20210224-1Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD6021KL-20210224-1Pickup 1/2 Ton8200OEWT-PA14-Lem-R1 | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6044 | KL-20210225-12-R1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-02-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, load and haul gravel, move bridge, and sand road. WC 12000.00 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44256 |  | 56 | 44259 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6044KL-20210225-12-R1Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD6044KL-20210225-12-R1Pickup 1/2 Ton9225OEWT-PA14-Lem-R1 | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6044 | KL-20210225-12-R1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2021-02-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, load and haul gravel, move bridge, and sand road. WC 12000.00 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44256 |  | 56 | 44259 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6044KL-20210225-12-R1Pickup 1/2 Ton7175 | KABI LAKE FOREST PRODUCTS LTD6044KL-20210225-12-R1Pickup 1/2 Ton7175OEWT-PA14-Lem-R1 | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5606 | KL-20210125-3 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-01-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow, Grade Paint Lake 2 Rd, haul gravel & corduroy. Drag 70' bridge in from km 9 lay down | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44225 |  | 50 | 44232 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5606KL-20210125-3Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD5606KL-20210125-3Pickup 1/2 Ton10250OEWT-PA14-Lem-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5678 | KL-20210130-15 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2021-01-30 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow, haul gravel and corduroy, Sand roads. Drag in and unload bridge WC 11333.00 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44231 |  | 50 | 44232 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5678KL-20210130-15Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD5678KL-20210130-15Pickup 1/2 Ton6150OEWT-PA14-Lem-R1 | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5778 | KL-20210205-4 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-02-05 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Paint Lake 2 Rd, plow snow, haul gravel. Ditch and load rock trucks. Haul & spread material, trim road, and track out plow. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44243 |  | 50 | 44248 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5778KL-20210205-4Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD5778KL-20210205-4Pickup 1/2 Ton10250OEWT-PA14-Lem-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5842 | KL-20210210-4 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 14 | HR | 19 | 0 |  |  | 350 | 45.5 | 395.5 | 2021-02-10 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul gravel, pull bridges and legos in, plow and sand roads. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44244 |  | 50 | 44249 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5842KL-20210210-4Pickup 1/2 Ton14350 | KABI LAKE FOREST PRODUCTS LTD5842KL-20210210-4Pickup 1/2 Ton14350OEWT-PA14-Lem-R1 | [5 empty] | 1 | 350 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5877 | KL-20210212-8 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-02-12 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul Gravel, pull bridges and legos in, plow snow, sand roads, skid corduroy | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44244 |  | 50 | 44250 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5877KL-20210212-8Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD5877KL-20210212-8Pickup 1/2 Ton10250OEWT-PA14-Lem-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5990 | KL-20210221-8 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 14 | HR | 19 | 0 |  |  | 350 | 45.5 | 395.5 | 2021-02-21 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Paint Lake 2 Rd, plow snow on access rd, haul geo from km 9 to km 23, skid corduroy | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44252 |  | 57 | 44255 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD5990KL-20210221-8Pickup 1/2 Ton14350 | KABI LAKE FOREST PRODUCTS LTD5990KL-20210221-8Pickup 1/2 Ton14350OEWT-PA14-Lem-R1 | [5 empty] | 1 | 350 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5997 | KL-20210222-3 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-02-22 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, skid corduroy, haul rig mats to snow crossing, work on snow crossing, place mats, track buncher to snow crossing, haul gravel. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44254 | . | 57 | 44255 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD5997KL-20210222-3Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD5997KL-20210222-3Pickup 1/2 Ton10250OEWT PA15-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6290 | KL-20210310-3 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-03-10 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying Paint Lake 2 Rd/Loader pushing out snow banks in low areas for drainage. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44278 |  | 56 | 44280 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6290KL-20210310-3Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD6290KL-20210310-3Pickup 1/2 Ton13325OEWT PA15-LEM | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6301 | KL-20210311-2 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-03-11 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal & scarifying Paint Lake 2 Rd. JJR pushing snowbanks back. CDSL excavator walking out to float access. | 10 | F033-F118 | Paint Lake Raod 2 | 0 | 44278 |  | 56 | 44280 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6301KL-20210311-2Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD6301KL-20210311-2Pickup 1/2 Ton10250OEWT PA15-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6309 | KL-20210312-6 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2021-03-12 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal & scarifying Paint Lake 2 Rd | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44278 |  | 56 | 44280 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6309KL-20210312-6Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD6309KL-20210312-6Pickup 1/2 Ton8200OEWT PA15-LEM | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6336 | KL-20210315-4 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2021-03-15 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Scarifying hills and corners on Paint Lake Road 2 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44279 |  | 56 | 44280 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6336KL-20210315-4Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD6336KL-20210315-4Pickup 1/2 Ton4100OEWT PA15-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7593 | KL-20211125-2 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2021-11-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road @ F118, scraping and sanding hill @ Km 48. Excavator filling ruts and shaping road from km 24 to 21 for freezing - JJR-70306 | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7593KL-20211125-2Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD7593KL-20211125-2Pickup 1/2 Ton5125OEWT-PA23-Lem | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7593 | KL-20211125-2 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2021-11-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road @ F118, scraping and sanding hill @ Km 48. Excavator filling ruts and shaping road from km 24 to 21 for freezing - JJR-70306 | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7593KL-20211125-2Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD7593KL-20211125-2Pickup 1/2 Ton125OEWT-PA23-Lem | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7620 | KL-20211202-2 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Km 49 to Km 40/ loader sanding road from Km 48 to Km 46.5 with existing material | 10 | F066-F118 | Paint Lake 2 | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7620KL-20211202-2Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD7620KL-20211202-2Pickup 1/2 Ton10250OEWT-PA24-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7628 | KL-20211203-2 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-12-03 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding and scraping road from Km 46.5 to Km 38 with existing material | 10 | F066-F118 | Paint Lake 2 | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7628KL-20211203-2Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7628KL-20211203-2Pickup 1/2 Ton9.5237.5OEWT-PA24-LEM | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7628 | KL-20211203-2 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2021-12-03 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding and scraping road from Km 46.5 to Km 38 with existing material | 10 | F066-F118 | Paint Lake 2 | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7628KL-20211203-2Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD7628KL-20211203-2Pickup 1/2 Ton375OEWT-PA24-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7637 | KL-20211204-5 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-12-04 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding and scraping road from Km 46 to Km 38 with existing material /dozer working from Km 49 to Km 13/ supervisior picking up dozer operator @ Km 13 at end of shift | 10 | F066-F118 | Paint Lake 2 | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7637KL-20211204-5Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7637KL-20211204-5Pickup 1/2 Ton9225OEWT-PA24-LEM | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7637 | KL-20211204-5 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2021-12-04 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding and scraping road from Km 46 to Km 38 with existing material /dozer working from Km 49 to Km 13/ supervisior picking up dozer operator @ Km 13 at end of shift | 10 | F066-F118 | Paint Lake 2 | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7637KL-20211204-5Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD7637KL-20211204-5Pickup 1/2 Ton6150OEWT-PA24-LEM | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7639 | KL-20211205-2 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 18 | HR | 19 | 0 |  |  | 450 | 58.5 | 508.5 | 2021-12-05 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader piling existing material from Km 46 to Km 38 for upcoming snow fall/ dozer working on snow removal from km 13 to km 21 | 10 | F066-F118 | Paint Lake 2 | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7639KL-20211205-2Pickup 1/2 Ton18450 | KABI LAKE FOREST PRODUCTS LTD7639KL-20211205-2Pickup 1/2 Ton18450OEWT-PA24-LEM | [5 empty] | 1 | 450 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7639 | KL-20211205-2 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2021-12-05 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader piling existing material from Km 46 to Km 38 for upcoming snow fall/ dozer working on snow removal from km 13 to km 21 | 10 | F066-F118 | Paint Lake 2 | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7639KL-20211205-2Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD7639KL-20211205-2Pickup 1/2 Ton4100OEWT-PA24-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7643 | KL-20211206-2 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-12-06 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working on snow removal and sanding from Km 49 to Km 35 | 10 | F066-F118 | Paint Lake 2 | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7643KL-20211206-2Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD7643KL-20211206-2Pickup 1/2 Ton13325OEWT-PA24-LEM | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7646 | KL-20211206-5 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 4.5 | HR | 19 | 0 |  |  | 112.5 | 14.625 | 127.125 | 2021-12-06 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking out from Km 13 to Km 2 for loading of sand truck with existing material in support of Valard fuel tank demob | 10 | F066-F118 | Paint Lake 2 | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7646KL-20211206-5Pickup 1/2 Ton4.5112.5 | KABI LAKE FOREST PRODUCTS LTD7646KL-20211206-5Pickup 1/2 Ton4.5112.5OEWT-PA24-LEM | [5 empty] | 1 | 112.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7647 | KL-20211207-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2021-12-07 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding from Km 48 to Km 40 | 10 | F066-F118 | Paint Lake 2 | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7647KL-20211207-1Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7647KL-20211207-1Pickup 1/2 Ton12300OEWT-PA24-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7652 | KL-20211208-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 6.5 | HR | 19 | 0 |  |  | 162.5 | 21.125 | 183.625 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding from Km 48 to Km 45. Dozer working from 13km to 18km. Sand truck sanding from 0km to 12km in support of Valard Fuel Tank Demob. Excavator loading existing material. Skagen grader on PLR 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-1Pickup 1/2 Ton6.5162.5 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-1Pickup 1/2 Ton6.5162.5OEWT-PA24-LEM | [5 empty] | 1 | 162.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7652 | KL-20211208-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 14 | HR | 19 | 0 |  |  | 350 | 45.5 | 395.5 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding from Km 48 to Km 45. Dozer working from 13km to 18km. Sand truck sanding from 0km to 12km in support of Valard Fuel Tank Demob. Excavator loading existing material. Skagen grader on PLR 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-1Pickup 1/2 Ton14350 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-1Pickup 1/2 Ton14350OEWT-PA24-LEM | [5 empty] | 1 | 350 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7657 | KL-20211209-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 21 | HR | 19 | 0 |  |  | 525 | 68.25 | 593.25 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working from 48km to 34km sanding & clearing pull offs. Dozer working to F057, F058 & F058 access. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7657KL-20211209-1Pickup 1/2 Ton21525 | KABI LAKE FOREST PRODUCTS LTD7657KL-20211209-1Pickup 1/2 Ton21525OEWT-PA24-LEM | [5 empty] | 1 | 525 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7665 | KL-20211210-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 21.5 | HR | 19 | 0 |  |  | 537.5 | 69.875 | 607.375 | 2021-12-10 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal and sanding from 48Km to 38Km. Grader working on snow removal from Paint Lake Road to 13Km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7665KL-20211210-1Pickup 1/2 Ton21.5537.5 | KABI LAKE FOREST PRODUCTS LTD7665KL-20211210-1Pickup 1/2 Ton21.5537.5OEWT-PA24-LEM | [5 empty] | 1 | 537.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7670 | KL-20211211-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 19 | HR | 19 | 0 |  |  | 475 | 61.75 | 536.75 | 2021-12-11 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from 49Km to 40Km. Grader 1 working on snow removal 0Km to 23Km for Crane demob. Grader 2 scarifying from 49 to 45Km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7670KL-20211211-1Pickup 1/2 Ton19475 | KABI LAKE FOREST PRODUCTS LTD7670KL-20211211-1Pickup 1/2 Ton19475OEWT-PA24-LEM | [5 empty] | 1 | 475 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7681 | KL-20211212-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2021-12-12 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working from Km 2 to Km 49 for scarifying and clearing pull offs | 10 | F066-F118 | Paint Lake 2 | 0 | 44551 |  | 61 | 44561 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7681KL-20211212-1Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7681KL-20211212-1Pickup 1/2 Ton12300OEWT-PA24-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7686 | KL-20211213-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2021-12-13 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer starting snow removal from F117 to F112 | 10 | F066-F118 | Paint Lake 2 | 0 | 44551 |  | 61 | 44560 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7686KL-20211213-1Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD7686KL-20211213-1Pickup 1/2 Ton6150OEWT-PA24-LEM | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7689 | KL-20211214-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2021-12-14 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Finishing snow removal from F117 to F112 | 10 | F066-F118 | Paint Lake 2 | 0 | 44551 |  | 61 | 44560 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7689KL-20211214-1Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD7689KL-20211214-1Pickup 1/2 Ton375OEWT-PA24-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7705 | KL-20211218-3 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-12-18 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on shaping road and leveling ruts from F112 to F117 for freezing | 10 | F066-F118 | Paint Lake 2 | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7705KL-20211218-3Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7705KL-20211218-3Pickup 1/2 Ton11275OEWT-PA24-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7718 | KL-20220101-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2022-01-01 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Km 49 on Paint Lake Road 2 to F111 | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7718KL-20220101-1Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7718KL-20220101-1Pickup 1/2 Ton11275OEWT-PA25-Lem | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7723 | KL-20220103-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2022-01-03 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F117 to F112 | 10 | F066-F118 | Paint Lake 2 | 0 | 44568 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7723KL-20220103-1Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7723KL-20220103-1Pickup 1/2 Ton9.5237.5OEWT-PA25-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7728 | KL-20220104-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-01-04 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and widening road from Km 47 to Km 43.5, F109 to F111, F105 and F104 Access | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7728KL-20220104-1Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7728KL-20220104-1Pickup 1/2 Ton12300OEWT-PA25-Lem | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7737 | KL-20220106-2 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 4.5 | HR | 19 | 0 |  |  | 112.5 | 14.625 | 127.125 | 2022-01-06 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Working on Snow Removal and Widening road from Km 46 to F111/ Loader working on snow removal from F037 to F033 and sanding km 10.5 Hill | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7737KL-20220106-2Pickup 1/2 Ton4.5112.5 | KABI LAKE FOREST PRODUCTS LTD7737KL-20220106-2Pickup 1/2 Ton4.5112.5OEWT-PA25-Lem | [5 empty] | 1 | 112.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7737 | KL-20220106-2 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 7.5 | HR | 19 | 0 |  |  | 187.5 | 24.375 | 211.875 | 2022-01-06 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Working on Snow Removal and Widening road from Km 46 to F111/ Loader working on snow removal from F037 to F033 and sanding km 10.5 Hill | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7737KL-20220106-2Pickup 1/2 Ton7.5187.5 | KABI LAKE FOREST PRODUCTS LTD7737KL-20220106-2Pickup 1/2 Ton7.5187.5OEWT-PA25-Lem | [5 empty] | 1 | 187.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7737 | KL-20220106-2 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2022-01-06 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Working on Snow Removal and Widening road from Km 46 to F111/ Loader working on snow removal from F037 to F033 and sanding km 10.5 Hill | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7737KL-20220106-2Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD7737KL-20220106-2Pickup 1/2 Ton250OEWT-PA25-Lem | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7740 | KL-20220107-2 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-01-07 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working from Km 12 to Km 49 clearing pull offs and scraping hills from km 34 to km 41 | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7740KL-20220107-2Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7740KL-20220107-2Pickup 1/2 Ton12300OEWT-PA25-Lem | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7744 | KL-20220108-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2022-01-08 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working from Km 48 to Km 41 pushing back snow banks, clearing pull offs and F105/F104 access | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7744KL-20220108-1Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD7744KL-20220108-1Pickup 1/2 Ton10250OEWT-PA25-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7751 | KL-20220110-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-01-10 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working on snow removal from Km 49 to Km 36 and clearing pull offs | 10 | F066-F118 | Paint Lake 2 | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7751KL-20220110-1Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7751KL-20220110-1Pickup 1/2 Ton12300OEWT-PA25-Lem | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7755 | KL-20220111-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2022-01-11 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and widening roads from Km 48 to Km 38 | 10 | F066-F118 | Paint Lake 2 | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7755KL-20220111-1Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7755KL-20220111-1Pickup 1/2 Ton11275OEWT-PA25-Lem | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7758 | KL-20220112-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-01-12 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and widening roads from Km 42 to Km 34/ Supervisor doing pick up shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7758KL-20220112-1Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7758KL-20220112-1Pickup 1/2 Ton12300OEWT-PA25-Lem | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7763 | KL-20220113-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2022-01-13 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and widening roads from Km 38 to Km 32 | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7763KL-20220113-1Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7763KL-20220113-1Pickup 1/2 Ton11275OEWT-PA25-Lem | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7768 | KL-20220114-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2022-01-14 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal and widening roads from Km 32 to Km 36 /Clearing spur roads on way out | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7768KL-20220114-1Pickup 1/2 Ton7175 | KABI LAKE FOREST PRODUCTS LTD7768KL-20220114-1Pickup 1/2 Ton7175OEWT-PA25-Lem | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7772 | KL-20220115-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2022-01-15 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal and widening roads from Km 32 to Km 36 /Clearing spur roads on way out. Excavator setting up @ 12Km for loader access to sand. | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7772KL-20220115-1Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD7772KL-20220115-1Pickup 1/2 Ton6150OEWT-PA25-Lem | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7776 | KL-20220116-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 15.5 | HR | 19 | 0 |  |  | 387.5 | 50.375 | 437.875 | 2022-01-16 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continue working on widening roads from Km 33 to Km 42 /Loader Clearing pull offs / Grader Scarifying from Km 49 to Km 42 | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7776KL-20220116-1Pickup 1/2 Ton15.5387.5 | KABI LAKE FOREST PRODUCTS LTD7776KL-20220116-1Pickup 1/2 Ton15.5387.5OEWT-PA25-Lem | [5 empty] | 1 | 387.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7779 | KL-20220117-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 14 | HR | 19 | 0 |  |  | 350 | 45.5 | 395.5 | 2022-01-17 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Finish working on widening roads and clearing pull offs from Km 42 to Km 49 /Grader Scarifying from Km 49 to Km 39 and F117 to F112/ supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7779KL-20220117-1Pickup 1/2 Ton14350 | KABI LAKE FOREST PRODUCTS LTD7779KL-20220117-1Pickup 1/2 Ton14350OEWT-PA25-Lem | [5 empty] | 1 | 350 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7785 | KL-20220119-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 3.5 | HR | 19 | 0 |  |  | 87.5 | 11.375 | 98.875 | 2022-01-19 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from 49Km to 42Km on Paint Lake Road 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7785KL-20220119-1Pickup 1/2 Ton3.587.5 | KABI LAKE FOREST PRODUCTS LTD7785KL-20220119-1Pickup 1/2 Ton3.587.5OEWT-PA25-Lem | [5 empty] | 1 | 87.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7878 | KL-20220213-2 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-02-13 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F021 to F032 and clearing pad @ F032 | 10 | F009-F065 | Paint Lake | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7878KL-20220213-2Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7878KL-20220213-2Pickup 1/2 Ton12300OEWT-PA26-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7883 | KL-20220214-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2022-02-14 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal, scarifying and benching snowbanks from Paint Lake Road to Km 19 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7883KL-20220214-1Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7883KL-20220214-1Pickup 1/2 Ton11275OEWT-PA26-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7884 | KL-20220214-2 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2022-02-14 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer finishing snow removal and widening from F021 to F032 and clearing pad @ F032 | 10 | F009-F065 | Paint Lake | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7884KL-20220214-2Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7884KL-20220214-2Pickup 1/2 Ton11275OEWT-PA26-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7888 | KL-20220215-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2022-02-15 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal, scarifying from Km 49 to Km 38 on Paint Lake Road 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7888KL-20220215-1Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD7888KL-20220215-1Pickup 1/2 Ton6150OEWT-PA26-LEM | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7893 | KL-20220216-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 7.5 | HR | 19 | 0 |  |  | 187.5 | 24.375 | 211.875 | 2022-02-16 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from Km 49 to Km 19 / grader 2 working on snow removal and pushing back snowbanks from Paint Lake Road to Km 19 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7893KL-20220216-1Pickup 1/2 Ton7.5187.5 | KABI LAKE FOREST PRODUCTS LTD7893KL-20220216-1Pickup 1/2 Ton7.5187.5OEWT-PA26-LEM | [5 empty] | 1 | 187.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7893 | KL-20220216-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-02-16 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from Km 49 to Km 19 / grader 2 working on snow removal and pushing back snowbanks from Paint Lake Road to Km 19 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7893KL-20220216-1Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7893KL-20220216-1Pickup 1/2 Ton12300OEWT-PA26-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7896 | KL-20220217-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 17 | HR | 19 | 0 |  |  | 425 | 55.25 | 480.25 | 2022-02-17 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal and scarifying from Km 49 to Km 41 / grader 2 working on snow removal and benching snowbanks from Paint Lake Road to Km 41 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7896KL-20220217-1Pickup 1/2 Ton17425 | KABI LAKE FOREST PRODUCTS LTD7896KL-20220217-1Pickup 1/2 Ton17425OEWT-PA26-LEM | [5 empty] | 1 | 425 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7900 | KL-20220218-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 10.5 | HR | 19 | 0 |  |  | 262.5 | 34.125 | 296.625 | 2022-02-18 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying and benching snowbanks from Paint Lake Road to Km 13 and snow removal from F037 to F033 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7900KL-20220218-1Pickup 1/2 Ton10.5262.5 | KABI LAKE FOREST PRODUCTS LTD7900KL-20220218-1Pickup 1/2 Ton10.5262.5OEWT-PA26-LEM | [5 empty] | 1 | 262.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7904 | KL-20220220-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 34 | HR | 19 | 0 |  |  | 850 | 110.5 | 960.5 | 2022-02-20 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 29km. Grader 2 working on snow removal from Paint Lake Road to 29km. Loader pushing back snow banks & pull offs from 45km to 38km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44617 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7904KL-20220220-1Pickup 1/2 Ton34850 | KABI LAKE FOREST PRODUCTS LTD7904KL-20220220-1Pickup 1/2 Ton34850OEWT-PA26-LEM | [5 empty] | 1 | 850 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7905 | KL-20220219-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 27 | HR | 19 | 0 |  |  | 675 | 87.75 | 762.75 | 2022-02-19 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 39km. Grader 2 working on snow removal from Paint Lake Road to 39km. Loader sanding & clearing pull offs to 34km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7905KL-20220219-1Pickup 1/2 Ton27675 | KABI LAKE FOREST PRODUCTS LTD7905KL-20220219-1Pickup 1/2 Ton27675OEWT-PA26-LEM | [5 empty] | 1 | 675 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7911 | KL-20220221-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 26 | HR | 19 | 0 |  |  | 650 | 84.5 | 734.5 | 2022-02-21 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 40km. Grader 2 working on snow removal from Paint Lake Road to 40km. Loader pushing back snow banks & pull offs from 49km to 40km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44617 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7911KL-20220221-1Pickup 1/2 Ton26650 | KABI LAKE FOREST PRODUCTS LTD7911KL-20220221-1Pickup 1/2 Ton26650OEWT-PA26-LEM | [5 empty] | 1 | 650 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7913 | KL-20220222-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 27 | HR | 19 | 0 |  |  | 675 | 87.75 | 762.75 | 2022-02-22 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 38km. Grader 2 benchig snow banks from Paint Lake Road to 49km. Loader assisting with Demob of 50 Ton Crane from 32Km to Hensen Road. | 10 | F-066 to F-118 | Paint Lake Road 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7913KL-20220222-1Pickup 1/2 Ton27675 | KABI LAKE FOREST PRODUCTS LTD7913KL-20220222-1Pickup 1/2 Ton27675OEWT-PA26-LEM | [5 empty] | 1 | 675 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7919 | KL-20220223-4 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 18 | HR | 19 | 0 |  |  | 450 | 58.5 | 508.5 | 2022-02-23 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from 49km to 29km. Loader working ahead of grader due to deep snow drifts | 10 | F066-F118 | Paint Lake 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7919KL-20220223-4Pickup 1/2 Ton18450 | KABI LAKE FOREST PRODUCTS LTD7919KL-20220223-4Pickup 1/2 Ton18450OEWT-PA26-LEM | [5 empty] | 1 | 450 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7920 | KL-20220224-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-02-24 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working on snow removal from 9.2Km to F-033 & to 23Km on Paint Lake Road #2. Supervisor doing pickup shuffle. | 10 | F066-F118 | Paint Lake 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7920KL-20220224-1Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7920KL-20220224-1Pickup 1/2 Ton12300OEWT-PA26-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7925 | KL-20220225-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 22.5 | HR | 19 | 0 |  |  | 562.5 | 73.125 | 635.625 | 2022-02-25 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 18km. Grader 2 working from Paint Lake Road to 18Km. Loader clearing pulloffs on Paint lake Road 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7925KL-20220225-1Pickup 1/2 Ton22.5562.5 | KABI LAKE FOREST PRODUCTS LTD7925KL-20220225-1Pickup 1/2 Ton22.5562.5OEWT-PA26-LEM | [5 empty] | 1 | 562.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7935 | KL-20220226-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 22.5 | HR | 19 | 0 |  |  | 562.5 | 73.125 | 635.625 | 2022-02-26 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader working from Paint Lake Road to Km 34 benching and widening / Loader clearing pull offs on Paint Lake Road 2 and widening @ Km 27 | 10 | F066-F118 | Paint Lake 2 | 0 | 44628 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7935KL-20220226-1Pickup 1/2 Ton22.5562.5 | KABI LAKE FOREST PRODUCTS LTD7935KL-20220226-1Pickup 1/2 Ton22.5562.5 | [5 empty] | 1 | 562.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7938 | KL-20220227-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 18 | HR | 19 | 0 |  |  | 450 | 58.5 | 508.5 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader 1 working from 49km to 26km. Grader 2 working from Paint Lake Road to 8km. Loader working on clearing pull offs between 9.2Km & 5Km on Paint Lake Road #2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44628 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7938KL-20220227-1Pickup 1/2 Ton18450 | KABI LAKE FOREST PRODUCTS LTD7938KL-20220227-1Pickup 1/2 Ton18450 | [5 empty] | 1 | 450 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7944 | KL-20220228-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2022-02-28 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader Working On Snow Removal From 29 Km To 2 Km On Paint Lake Road 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44628 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7944KL-20220228-1Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD7944KL-20220228-1Pickup 1/2 Ton10250 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7954 | KL-20220301-2 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 10.5 | HR | 19 | 0 |  |  | 262.5 | 34.125 | 296.625 | 2022-03-01 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader working on Snow Removal and benching snow banks from Km 1 to Km 13 on Paint Lake Road 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7954KL-20220301-2Pickup 1/2 Ton10.5262.5 | KABI LAKE FOREST PRODUCTS LTD7954KL-20220301-2Pickup 1/2 Ton10.5262.5 | [5 empty] | 1 | 262.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7957 | KL-20220302-2 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-03-02 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader working on Snow Removal from Km 49 to Km 13 on Paint Lake Road 2 @ park Grader at Km 2/Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7957KL-20220302-2Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7957KL-20220302-2Pickup 1/2 Ton12300 | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7966 | KL-20220303-5 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 7.5 | HR | 19 | 0 |  |  | 187.5 | 24.375 | 211.875 | 2022-03-03 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader working on snow removal from Paint Lake Road to F-033 | 10 | F009 - F065 | Paint Lake | 0 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7966KL-20220303-5Pickup 1/2 Ton7.5187.5 | KABI LAKE FOREST PRODUCTS LTD7966KL-20220303-5Pickup 1/2 Ton7.5187.5 | [5 empty] | 1 | 187.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7969 | KL-20220304-4 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 7.5 | HR | 19 | 0 |  |  | 187.5 | 24.375 | 211.875 | 2022-03-04 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader Continuing Working On Snow Removal From Paint Lake Road 2 To F033 | 10 | F009 - F065 | Paint Lake | 0 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7969KL-20220304-4Pickup 1/2 Ton7.5187.5 | KABI LAKE FOREST PRODUCTS LTD7969KL-20220304-4Pickup 1/2 Ton7.5187.5 | [5 empty] | 1 | 187.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7970 | KL-20220305-2 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 10.5 | HR | 19 | 0 |  |  | 262.5 | 34.125 | 296.625 | 2022-03-05 |  |  |  |  | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Loader Working On Snow Removal From Paint Lake Road 2 To F033 | 10 | F009 - F065 | Paint Lake | 0 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7970KL-20220305-2Pickup 1/2 Ton10.5262.5 | KABI LAKE FOREST PRODUCTS LTD7970KL-20220305-2Pickup 1/2 Ton10.5262.5 | [5 empty] | 1 | 262.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7978 | KL-20220306-3 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 17.5 | HR | 19 | 0 |  |  | 437.5 | 56.875 | 494.375 | 2022-03-06 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader Working On Snow Removal From Paint Lake Road To 12.5 Km On Paint Lake Road 2/Graded 3 Times Due To Winter Storm/Loader Working From F037 To F034 | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44637 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7978KL-20220306-3Pickup 1/2 Ton17.5437.5 | KABI LAKE FOREST PRODUCTS LTD7978KL-20220306-3Pickup 1/2 Ton17.5437.5 | [5 empty] | 1 | 437.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7788 | KL-20220120-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 3.5 | HR | 19 | 0 |  |  | 87.5 | 11.375 | 98.875 | 2022-01-20 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F112 to F117 | 10 | F066-F118 | Paint Lake 2 | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7788KL-20220120-1Pickup 1/2 Ton3.587.5 | KABI LAKE FOREST PRODUCTS LTD7788KL-20220120-1Pickup 1/2 Ton3.587.5OEWT-PA25-Lem | [5 empty] | 1 | 87.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7793 | KL-20220121-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 6.5 | HR | 19 | 0 |  |  | 162.5 | 21.125 | 183.625 | 2022-01-21 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer starting from Km 49 Km 45 clearing pull offs and widening where required/Delay Due to Stringers having road closed @ F118/ supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44588 |  | 61 | 44593 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7793KL-20220121-1Pickup 1/2 Ton6.5162.5 | KABI LAKE FOREST PRODUCTS LTD7793KL-20220121-1Pickup 1/2 Ton6.5162.5OEWT-PA25-Lem | [5 empty] | 1 | 162.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7799 | KL-20220123-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 3.5 | HR | 19 | 0 |  |  | 87.5 | 11.375 | 98.875 | 2022-01-23 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on access and F112 to F117 | 10 | F066-F118 | Paint Lake 2 | 0 | 44588 |  | 61 | 44593 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7799KL-20220123-1Pickup 1/2 Ton3.587.5 | KABI LAKE FOREST PRODUCTS LTD7799KL-20220123-1Pickup 1/2 Ton3.587.5OEWT-PA25-Lem | [5 empty] | 1 | 87.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7801 | KL-20220124-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2022-01-24 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening F112 to F117, clearing snow @ F109 to F111, F105 access, widening and cleaning pulloffs from Km 48 to 41.5/Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44588 |  | 61 | 44593 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7801KL-20220124-1Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7801KL-20220124-1Pickup 1/2 Ton9225OEWT-PA25-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7801 | KL-20220124-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2022-01-24 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening F112 to F117, clearing snow @ F109 to F111, F105 access, widening and cleaning pulloffs from Km 48 to 41.5/Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44588 |  | 61 | 44593 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7801KL-20220124-1Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD7801KL-20220124-1Pickup 1/2 Ton375OEWT-PA25-Lem | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7805 | KL-20220125-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2022-01-25 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road and cleaning pulloffs from Km 41 to 38.5/Snow removal on spur roads from F104 to F095 /Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44588 |  | 61 | 44593 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7805KL-20220125-1Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD7805KL-20220125-1Pickup 1/2 Ton8200OEWT-PA25-Lem | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7805 | KL-20220125-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2022-01-25 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road and cleaning pulloffs from Km 41 to 38.5/Snow removal on spur roads from F104 to F095 /Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44588 |  | 61 | 44593 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7805KL-20220125-1Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD7805KL-20220125-1Pickup 1/2 Ton375OEWT-PA25-Lem | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7809 | KL-20220126-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 11.5 | HR | 19 | 0 |  |  | 287.5 | 37.375 | 324.875 | 2022-01-26 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road and cleaning pulloffs from Km 38 to 35/Snow removal on spur roads /Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7809KL-20220126-1Pickup 1/2 Ton11.5287.5 | KABI LAKE FOREST PRODUCTS LTD7809KL-20220126-1Pickup 1/2 Ton11.5287.5OEWT-PA26-LEM | [5 empty] | 1 | 287.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7814 | KL-20220129-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2022-01-29 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road , clearing pull offs and spur roads from Km 38 to Km 35/Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7814KL-20220129-1Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7814KL-20220129-1Pickup 1/2 Ton9225OEWT-PA26-LEM | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7816 | KL-20220130-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 16.5 | HR | 19 | 0 |  |  | 412.5 | 53.625 | 466.125 | 2022-01-30 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 49 to Km 36 for stringing crews equipment move /Dozer working from Km 35 to Km 32 widening road , clearing pull offs and spur | 10 | F066-F118 | Paint Lake 2 | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7816KL-20220130-1Pickup 1/2 Ton16.5412.5 | KABI LAKE FOREST PRODUCTS LTD7816KL-20220130-1Pickup 1/2 Ton16.5412.5OEWT-PA26-LEM | [5 empty] | 1 | 412.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7818 | KL-20220131-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-01-31 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working from Km 35 to Km 32 widening road , clearing pull offs and spur roads from Km 35 to Km 29 / Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7818KL-20220131-1Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7818KL-20220131-1Pickup 1/2 Ton12300OEWT-PA26-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7822 | KL-20220201-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-02-01 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road, clearing pull offs, spur roads from 29km to 25km & access road to F057. Supervisor doing pickup shuffle. | 10 | F066-F118 | Paint Lake 2 | 0 | 44601 |  | 37 | 44597 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7822KL-20220201-1Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7822KL-20220201-1Pickup 1/2 Ton12300OEWT-PA26-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7826 | KL-20220202-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-02-02 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road, clearing pull offs, spur roads from 25km to 21km. Supervisor doing pickup shuffle. | 10 | F066-F118 | Paint Lake 2 | 0 | 44601 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7826KL-20220202-1Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7826KL-20220202-1Pickup 1/2 Ton12300OEWT-PA26-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7828 | KL-20220203-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 19.5 | HR | 19 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2022-02-03 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader benching snow banks & scarifying road from 49 to 40km. Dozer widening road, clearing pull offs & spur roads from 21km to 12.5km. Supervisor doing pickup shuffle. | 10 | F066-F118 | Paint Lake 2 | 0 | 44601 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7828KL-20220203-1Pickup 1/2 Ton19.5487.5 | KABI LAKE FOREST PRODUCTS LTD7828KL-20220203-1Pickup 1/2 Ton19.5487.5OEWT-PA26-LEM | [5 empty] | 1 | 487.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7832 | KL-20220204-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-02-04 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F077 to F073 and clearing laydown at 12km. Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44603 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7832KL-20220204-1Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7832KL-20220204-1Pickup 1/2 Ton12300OEWT-PA26-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7836 | KL-20220205-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-02-05 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F020 to F009 and clearing pull offs. | 10 | F009-F065 | Paint Lake | 0 | 44603 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7836KL-20220205-1Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7836KL-20220205-1Pickup 1/2 Ton12300OEWT-PA26-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7841 | KL-20220206-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 8.5 | HR | 19 | 0 |  |  | 212.5 | 27.625 | 240.125 | 2022-02-06 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F020 to F009 for removal of repeater tower trailer. | 10 | F009-F065 | Paint Lake | 0 | 44603 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7841KL-20220206-1Pickup 1/2 Ton8.5212.5 | KABI LAKE FOREST PRODUCTS LTD7841KL-20220206-1Pickup 1/2 Ton8.5212.5OEWT-PA26-LEM | [5 empty] | 1 | 212.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7843 | KL-20220206-3 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2022-02-06 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from 49km to 25km on Paint Lake Road #2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44603 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7843KL-20220206-3Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7843KL-20220206-3Pickup 1/2 Ton9225OEWT-PA26-LEM | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7844 | KL-20220207-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F021 to F028 | 10 | F009 - F0665 | Paint Lake | 0 | 44604 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7844KL-20220207-1Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7844KL-20220207-1Pickup 1/2 Ton9225OEWT-PA26-LEM | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7844 | KL-20220207-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F021 to F028 | 10 | F009 - F0665 | Paint Lake | 0 | 44604 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7844KL-20220207-1Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD7844KL-20220207-1Pickup 1/2 Ton375OEWT-PA26-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7846 | KL-20220207-3 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 5.5 | HR | 19 | 0 |  |  | 137.5 | 17.875 | 155.375 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from 49km to 36km on Paint Lake Road #2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44604 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7846KL-20220207-3Pickup 1/2 Ton5.5137.5 | KABI LAKE FOREST PRODUCTS LTD7846KL-20220207-3Pickup 1/2 Ton5.5137.5OEWT-PA26-LEM | [5 empty] | 1 | 137.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7852 | KL-20220208-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-02-08 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F021 to F030 | 10 | F009-F065 | Paint Lake | 0 | 44604 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7852KL-20220208-1Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7852KL-20220208-1Pickup 1/2 Ton12300OEWT-PA26-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7854 | KL-20220208-3 Field Ticket No. P.O. Box 508, 10 Industrial Park Rd White River ON POM 3G0 Frank Ferland Telephone: 807-822-2532 08-Feb-2022 Email: office@kabilake.com SUMMARY INFORMATION Page 1 of 1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2022-02-08 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from 49km to 30km on Paint Lake Road #2 & snow removal from F116 to F112. | 10 | F066-F118 | Paint Lake | 0 | 44604 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7854KL-20220208-3 Field Ticket No. P.O. Box 508, 10 Industrial Park Rd White River ON POM 3G0 Frank Ferland Telephone: 807-822-2532 08-Feb-2022 Email: office@kabilake.com SUMMARY INFORMATION Page 1 of 1Pickup 1/2 Ton7175 | KABI LAKE FOREST PRODUCTS LTD7854KL-20220208-3 Field Ticket No. P.O. Box 508, 10 Industrial Park Rd White River ON POM 3G0 Frank Ferland Telephone: 807-822-2532 08-Feb-2022 Email: office@kabilake.com SUMMARY INFORMATION Page 1 of 1Pickup 1/2 Ton7175OEWT-PA26-LEM | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7859 | KL-20220209-2 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2022-02-09 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader benching snowbanks and scarifying sections from Km 49 to Km 32 on Paint Lake Road 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44604 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7859KL-20220209-2Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7859KL-20220209-2Pickup 1/2 Ton9225OEWT-PA26-LEM | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7864 | KL-20220210-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 16 | HR | 19 | 0 |  |  | 400 | 52 | 452 | 2022-02-10 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Km 49 to Km 32 on Paint Lake Road 2 /Dozer pushing snowbanks and widening road from Km 9.2 to Km 11/Supervisors doing pickup shuffle | 10 | F066-F118 | Paint Lake | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7864KL-20220210-1Pickup 1/2 Ton16400 | KABI LAKE FOREST PRODUCTS LTD7864KL-20220210-1Pickup 1/2 Ton16400OEWT-PA26-LEM | [5 empty] | 1 | 400 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7869 | KL-20220211-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 16.5 | HR | 19 | 0 |  |  | 412.5 | 53.625 | 466.125 | 2022-02-11 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 49 to Km 35 /Dozer pushing snowbanks and widening road from Km 11 to Km 15/Supervisors doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7869KL-20220211-1Pickup 1/2 Ton16.5412.5 | KABI LAKE FOREST PRODUCTS LTD7869KL-20220211-1Pickup 1/2 Ton16.5412.5OEWT-PA26-LEM | [5 empty] | 1 | 412.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7873 | KL-20220212-1 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2022-02-12 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 49 to Km 29 /Dozer tracking from Km 15 to Km 9.2 for float access/Supervisors doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7873KL-20220212-1Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7873KL-20220212-1Pickup 1/2 Ton11275OEWT-PA26-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7875 | KL-20220212-3 | 53511011 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2022-02-12 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F021 to F027 | 10 | F009-F065 | Paint Lake | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7875KL-20220212-3Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7875KL-20220212-3Pickup 1/2 Ton9225OEWT-PA26-LEM | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4077 | KL-20201031-9 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2020-10-31 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Paint Lake Road 2 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44152 |  | 47 | 44156 | [5 empty] | Bruce Bennett | 10 | KABI LAKE FOREST PRODUCTS LTD4077KL-20201031-9Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD4077KL-20201031-9Pickup 1/2 Ton8200OEWT-PA11-LEM | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4524 | KL-20201102-17 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2020-11-02 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E091-E102 | 600 Road | 0 | 44174 |  | 15 | 44175 | [5 empty] | Martin Hunt | 10 | KABI LAKE FOREST PRODUCTS LTD4524KL-20201102-17Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD4524KL-20201102-17Pickup 1/2 Ton10250OEWT-PA11-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6963 | KL-20210520-5 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T Dozer starting leveling ruts and shaping road from Km 2 to Km 9.5 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD6963KL-20210520-5Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD6963KL-20210520-5Pickup 1/2 Ton9.5237.5OEWT-PA17-LEM | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6987 | KL-20210525-5 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-05-25 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator Starting road maintenance to F038 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44348 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD6987KL-20210525-5Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD6987KL-20210525-5Pickup 1/2 Ton11275OEWT-PA17-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6990 | KL-20210526-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 10.5 | HR | 19 | 0 |  |  | 262.5 | 34.125 | 296.625 | 2021-05-26 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator working on road maintenance to F40/ Grader starting on Paint Lake Road 2 to Km 4 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD6990KL-20210526-3Pickup 1/2 Ton10.5262.5 | KABI LAKE FOREST PRODUCTS LTD6990KL-20210526-3Pickup 1/2 Ton10.5262.5OEWT-PA18-Lem | [5 empty] | 1 | 262.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6992 | KL-20210527-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 17.5 | HR | 19 | 0 |  |  | 437.5 | 56.875 | 494.375 | 2021-05-27 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator working on road maintenance to F040 / Grader working on Paint Lake Road 2 at km4 to km 10 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD6992KL-20210527-2Pickup 1/2 Ton17.5437.5 | KABI LAKE FOREST PRODUCTS LTD6992KL-20210527-2Pickup 1/2 Ton17.5437.5OEWT-PA18-Lem | [5 empty] | 1 | 437.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6994 | KL-20210528-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 21.5 | HR | 19 | 0 |  |  | 537.5 | 69.875 | 607.375 | 2021-05-28 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator working on road maintenance from Km 15.5 to Km 19/ Grader working on Paint Lake Road 2 at Km 7 to 12 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD6994KL-20210528-2Pickup 1/2 Ton21.5537.5 | KABI LAKE FOREST PRODUCTS LTD6994KL-20210528-2Pickup 1/2 Ton21.5537.5OEWT-PA18-Lem | [5 empty] | 1 | 537.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7066 | KL-20210530-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 13.5 | HR | 19 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2021-05-30 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator working road maintenance and drainage to F044/045 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44372 |  | 36 | 44373 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7066KL-20210530-2Pickup 1/2 Ton13.5337.5 | KABI LAKE FOREST PRODUCTS LTD7066KL-20210530-2Pickup 1/2 Ton13.5337.5OEWT-PA18-Lem | [5 empty] | 1 | 337.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7427 | KL-20211005-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 39.5 | HR | 19 | 0 |  |  | 987.5 | 128.375 | 1115.875 | 2021-10-05 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F112. Excavator 2 working @ 43/42km. Rock trucks hauling from 37.5km to Skagen @ 36km. Labourer hauling fuel to 35km as per Valard. Supervision of Skagen/Morin. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-1Pickup 1/2 Ton39.5987.5 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-1Pickup 1/2 Ton39.5987.5OEWT-PA22-Lem | [5 empty] | 1 | 987.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7431 | KL-20211006-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 30 | HR | 19 | 0 |  |  | 750 | 97.5 | 847.5 | 2021-10-06 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-1Pickup 1/2 Ton30750 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-1Pickup 1/2 Ton30750OEWT-PA22-Lem | [5 empty] | 1 | 750 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7457 | KL-20211015-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 19 | HR | 19 | 0 |  |  | 475 | 61.75 | 536.75 | 2021-10-15 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Flll toFlOO level ruts & drainage isting material from F088 to 34.SKm as per Valard. Supervise Morin, Skagen, Pleson, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1Pickup 1/2 Ton19475 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1Pickup 1/2 Ton19475OEWT-PA22-Lem | [5 empty] | 1 | 475 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7457 | KL-20211015-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 18 | HR | 19 | 0 |  |  | 450 | 58.5 | 508.5 | 2021-10-15 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Flll toFlOO level ruts & drainage isting material from F088 to 34.SKm as per Valard. Supervise Morin, Skagen, Pleson, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1Pickup 1/2 Ton18450 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1Pickup 1/2 Ton18450OEWT-PA22-Lem | [5 empty] | 1 | 450 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7457 | KL-20211015-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2021-10-15 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Flll toFlOO level ruts & drainage isting material from F088 to 34.SKm as per Valard. Supervise Morin, Skagen, Pleson, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1Pickup 1/2 Ton8200OEWT-PA22-Lem | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7460 | KL-20211016-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 18 | HR | 19 | 0 |  |  | 450 | 58.5 | 508.5 | 2021-10-16 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F194 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1Pickup 1/2 Ton18450 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1Pickup 1/2 Ton18450OEWT-PA22-Lem | [5 empty] | 1 | 450 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7460 | KL-20211016-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 18 | HR | 19 | 0 |  |  | 450 | 58.5 | 508.5 | 2021-10-16 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F194 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1Pickup 1/2 Ton18450 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1Pickup 1/2 Ton18450OEWT-PA22-Lem | [5 empty] | 1 | 450 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7460 | KL-20211016-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-10-16 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F194 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1Pickup 1/2 Ton9225OEWT-PA22-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7414 | KL-20211001-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 37 | HR | 19 | 0 |  |  | 925 | 120.25 | 1045.25 | 2021-10-01 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-1Pickup 1/2 Ton37925 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-1Pickup 1/2 Ton37925OEWT-PA22-Lem | [5 empty] | 1 | 925 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7419 | KL-20211002-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 38.5 | HR | 19 | 0 |  |  | 962.5 | 125.125 | 1087.625 | 2021-10-02 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-1Pickup 1/2 Ton38.5962.5 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-1Pickup 1/2 Ton38.5962.5OEWT-PA22-Lem | [5 empty] | 1 | 962.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7421 | KL-20211003-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 35 | HR | 19 | 0 |  |  | 875 | 113.75 | 988.75 | 2021-10-03 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading & hauling from 46km to 45km. Labourers hauling fuel to 35km & installing silt fencing as per Valard. Supervision o Skagen & Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-1Pickup 1/2 Ton35875 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-1Pickup 1/2 Ton35875OEWT-PA22-Lem | [5 empty] | 1 | 875 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7424 | KL-20211004-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 26.5 | HR | 19 | 0 |  |  | 662.5 | 86.125 | 748.625 | 2021-10-04 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working from Paint 2 to F115. excavator 2 working from 45km to 43km. Rock truck hauling existing material from 37.5km to Skagen @36km. Supervision of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7424KL-20211004-1Pickup 1/2 Ton26.5662.5 | KABI LAKE FOREST PRODUCTS LTD7424KL-20211004-1Pickup 1/2 Ton26.5662.5OEWT-PA22-Lem | [5 empty] | 1 | 662.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7439 | KL-20211009-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 17 | HR | 19 | 0 |  |  | 425 | 55.25 | 480.25 | 2021-10-09 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km. Rock trucks on site for gravel haul. Supervision of Morin & Skagen. | 10 | F033 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-1Pickup 1/2 Ton17425 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-1Pickup 1/2 Ton17425OEWT-PA22-Lem | [5 empty] | 1 | 425 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7441 | KL-20211010-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 16.5 | HR | 19 | 0 |  |  | 412.5 | 53.625 | 466.125 | 2021-10-10 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, corduroy & cap 43km hill. Rock trucks on site for gravel haul. Supervise Morin & Skagen. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-1Pickup 1/2 Ton16.5412.5 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-1Pickup 1/2 Ton16.5412.5OEWT-PA22-Lem | [5 empty] | 1 | 412.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7442 | KL-20211011-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 17.5 | HR | 19 | 0 |  |  | 437.5 | 56.875 | 494.375 | 2021-10-11 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, levelling ruts & drainage. Rock trucks on site for gravel haul. Supervisor touring for blasting locations. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-1Pickup 1/2 Ton17.5437.5 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-1Pickup 1/2 Ton17.5437.5OEWT-PA22-Lem | [5 empty] | 1 | 437.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7444 | KL-20211008-1-R1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 47 | HR | 19 | 0 |  |  | 1175 | 152.75 | 1327.75 | 2021-10-08 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7444KL-20211008-1-R1Pickup 1/2 Ton471175 | KABI LAKE FOREST PRODUCTS LTD7444KL-20211008-1-R1Pickup 1/2 Ton471175OEWT-PA22-Lem | [5 empty] | 1 | 1175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7448 | KL-20211013-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 17 | HR | 19 | 0 |  |  | 425 | 55.25 | 480.25 | 2021-10-13 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 46 to 43km. Excavator 2 working from 43 to 39km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervision of Morin, Skagen, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-1Pickup 1/2 Ton17425 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-1Pickup 1/2 Ton17425OEWT-PA22-Lem | [5 empty] | 1 | 425 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7453 | KL-20211014-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 45 | HR | 19 | 0 |  |  | 1125 | 146.25 | 1271.25 | 2021-10-14 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from 46 to 39Km, levelling ruts & drainage. Rock trucks haulig existing material from F088 to 34.5Km. Labourer hauling fuel as per Valard. Supervision of Morin, Skagen & Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-1Pickup 1/2 Ton451125 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-1Pickup 1/2 Ton451125OEWT-PA22-Lem | [5 empty] | 1 | 1125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7465 | KL-20211017-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 44 | HR | 19 | 0 |  |  | 1100 | 143 | 1243 | 2021-10-17 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F108, F105,and F103 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | PAINT Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-1Pickup 1/2 Ton441100 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-1Pickup 1/2 Ton441100OEWT-PA22-Lem | [5 empty] | 1 | 1100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7471 | KL-20211018-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 28 | HR | 19 | 0 |  |  | 700 | 91 | 791 | 2021-10-18 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34 as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1Pickup 1/2 Ton28700 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1Pickup 1/2 Ton28700OEWT-PA22-Lem | [5 empty] | 1 | 700 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7471 | KL-20211018-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 19 | HR | 19 | 0 |  |  | 475 | 61.75 | 536.75 | 2021-10-18 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34 as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1Pickup 1/2 Ton19475 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1Pickup 1/2 Ton19475OEWT-PA22-Lem | [5 empty] | 1 | 475 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7475 | KL-20211019-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 57.5 | HR | 19 | 0 |  |  | 1437.5 | 186.875 | 1624.375 | 2021-10-19 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts, laying Geo and spreading existing material @ Km 42 hill/rock trucks hauling existing material from F088 to Km 34 as per Valard. Labourers picking up 4 roll of Geo @12km on Paint Lake Road 2and deliver it to km 42/worked late to finish capping @km 42 for pickup access/Supervision of Morin, Skagen, Pleson and Opas | 10 |  | Paint | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1Pickup 1/2 Ton57.51437.5 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1Pickup 1/2 Ton57.51437.5OEWT-PA22-Lem | [5 empty] | 1 | 1437.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7478 | KL-20211020-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 56.5 | HR | 19 | 0 |  |  | 1412.5 | 183.625 | 1596.125 | 2021-10-20 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material @ Km 42.5/rock trucks hauling existing material from F088 to Km 34 and Km 42.5 as per Valard. Excavator 3 tracking from Km 49, starting @ F112 to F114 leveling ruts,shaping and drainage/725 rock truck driving to Km .5 for float/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1Pickup 1/2 Ton56.51412.5 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1Pickup 1/2 Ton56.51412.5OEWT-PA22-Lem | [5 empty] | 1 | 1412.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7480 | KL-20211021-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-10-21 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material on sections/rock trucks hauling existing material from F088 as per Valard. Excavator 3 continuing @ F113 to F115 leveling ruts,shaping and drainage for freezing/ Supervision of Morin, Skagen, Pleson and Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-1Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-1Pickup 1/2 Ton9225OEWT-PA22-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7480 | KL-20211021-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-10-21 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material on sections/rock trucks hauling existing material from F088 as per Valard. Excavator 3 continuing @ F113 to F115 leveling ruts,shaping and drainage for freezing/ Supervision of Morin, Skagen, Pleson and Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-1Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-1Pickup 1/2 Ton9225OEWT-PA22-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7480 | KL-20211021-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 19 | HR | 19 | 0 |  |  | 475 | 61.75 | 536.75 | 2021-10-21 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material on sections/rock trucks hauling existing material from F088 as per Valard. Excavator 3 continuing @ F113 to F115 leveling ruts,shaping and drainage for freezing/ Supervision of Morin, Skagen, Pleson and Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-1Pickup 1/2 Ton19475 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-1Pickup 1/2 Ton19475OEWT-PA22-Lem | [5 empty] | 1 | 475 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7483 | KL-20211023-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 26 | HR | 19 | 0 |  |  | 650 | 84.5 | 734.5 | 2021-10-23 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 shaping road from Km 43 to Km 40 anf F098/ Excavator 2 shaping road from 45 to 49 km and starting in F123 access/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44495 |  | 61 | 44496 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7483KL-20211023-1Pickup 1/2 Ton26650 | KABI LAKE FOREST PRODUCTS LTD7483KL-20211023-1Pickup 1/2 Ton26650OEWT-PA22-Lem | [5 empty] | 1 | 650 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7485 | KL-20211024-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 16 | HR | 19 | 0 |  |  | 400 | 52 | 452 | 2021-10-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from Km 46 and F105 access/supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44496 |  | 61 | 44497 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7485KL-20211024-1Pickup 1/2 Ton16400 | KABI LAKE FOREST PRODUCTS LTD7485KL-20211024-1Pickup 1/2 Ton16400OEWT-PA23-Lem | [5 empty] | 1 | 400 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7488 | KL-20211025-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 16 | HR | 19 | 0 |  |  | 400 | 52 | 452 | 2021-10-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from Km 44 to Km 40 and F105 access/supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44496 |  | 61 | 44497 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7488KL-20211025-1Pickup 1/2 Ton16400 | KABI LAKE FOREST PRODUCTS LTD7488KL-20211025-1Pickup 1/2 Ton16400OEWT-PA23-Lem | [5 empty] | 1 | 400 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7492 | KL-20211026-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 16 | HR | 19 | 0 |  |  | 400 | 52 | 452 | 2021-10-26 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from F110 to Km 41 /supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7492KL-20211026-1Pickup 1/2 Ton16400 | KABI LAKE FOREST PRODUCTS LTD7492KL-20211026-1Pickup 1/2 Ton16400OEWT-PA23-Lem | [5 empty] | 1 | 400 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7496 | KL-20211027-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 33.5 | HR | 19 | 0 |  |  | 837.5 | 108.875 | 946.375 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 44, laying Geo and spreading existing material/Excavtor 2 loading existing material@ km 17 on Hensen/rock truck hauling existing material to Km 44 supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-1Pickup 1/2 Ton33.5837.5 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-1Pickup 1/2 Ton33.5837.5OEWT-PA23-Lem | [5 empty] | 1 | 837.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7500 | KL-20211027-5 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Pick up 3 rolls of Geo in Pic River West and 6 partial rolls @ Marathon Yard and deliver to Km 44 on Paint Lake Road 2/Supervisor loading Geo with Labourer@Pic River West | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7500KL-20211027-5Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7500KL-20211027-5Pickup 1/2 Ton11275OEWT-PA23-Lem | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7502 | KL-20211028-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 39 | HR | 19 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-10-28 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 laying Geo and spreading existing material @ Km 44 and shaping road to Km 45/Excavtor 2 cleaning up excavation @ km 17 on Hensen road and shaping road to F114 rock truck2 hauling from F088 to Km 34-33 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-1Pickup 1/2 Ton39975 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-1Pickup 1/2 Ton39975OEWT-PA23-Lem | [5 empty] | 1 | 975 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7506 | KL-20211029-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 25 | HR | 19 | 0 |  |  | 625 | 81.25 | 706.25 | 2021-10-29 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing clean up of excavation @ Km 17 on Hensen road and start shaping road to Km 45.5. Rock truck hauling existing material from F088 to Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44502 |  | 61 | 44503 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7506KL-20211029-1Pickup 1/2 Ton25625 | KABI LAKE FOREST PRODUCTS LTD7506KL-20211029-1Pickup 1/2 Ton25625OEWT-PA23-Lem | [5 empty] | 1 | 625 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7510 | KL-20211030-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 27.5 | HR | 19 | 0 |  |  | 687.5 | 89.375 | 776.875 | 2021-10-30 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road to Km 45 to Km 43 and spreading spotted rock trucks loads. Rock truck hauling existing material from F088 to Morin @ Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas. | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44502 |  | 61 | 44503 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7510KL-20211030-1Pickup 1/2 Ton27.5687.5 | KABI LAKE FOREST PRODUCTS LTD7510KL-20211030-1Pickup 1/2 Ton27.5687.5OEWT-PA23-Lem | [5 empty] | 1 | 687.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7517 | KL-20211031-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 34 | HR | 19 | 0 |  |  | 850 | 110.5 | 960.5 | 2021-10-31 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 43 to Km 40.5 and spreading spotted rock trucks loads /Excavator 2 leveling ruts and shaping road from F116 to F112 rock truck hauling existing material from F088 to Morin @ Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F033 - F071 | Paint Lake 2 | 0 | 44505 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7517KL-20211031-1Pickup 1/2 Ton34850 | KABI LAKE FOREST PRODUCTS LTD7517KL-20211031-1Pickup 1/2 Ton34850OEWT-PA23-Lem | [5 empty] | 1 | 850 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7519 | KL-20211101-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 26.5 | HR | 19 | 0 |  |  | 662.5 | 86.125 | 748.625 | 2021-11-01 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 43 to Km 40.5 and spreading spotted rock trucks loads. Rock truck hauling existing material from F-088 to Morin @ 33.5Km as per Valard. Supervision of Morin, Skagen, JJR & Opas | 10 | F033 - F071 | Paint Lake 2 | 0 | 44501 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7519KL-20211101-1Pickup 1/2 Ton26.5662.5 | KABI LAKE FOREST PRODUCTS LTD7519KL-20211101-1Pickup 1/2 Ton26.5662.5OEWT-PA23-Lem | [5 empty] | 1 | 662.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7547 | KL-20211102-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2021-11-02 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking from Km 43 to Km 17 on Hensen Road for float access /Rock truck hauling existing material from F088 to Morin@Km 33 as per Valard. Supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-2Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-2Pickup 1/2 Ton250OEWT-PA23-Lem | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7547 | KL-20211102-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-11-02 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking from Km 43 to Km 17 on Hensen Road for float access /Rock truck hauling existing material from F088 to Morin@Km 33 as per Valard. Supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-2Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-2Pickup 1/2 Ton9.5237.5OEWT-PA23-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7547 | KL-20211102-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-11-02 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking from Km 43 to Km 17 on Hensen Road for float access /Rock truck hauling existing material from F088 to Morin@Km 33 as per Valard. Supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-2Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-2Pickup 1/2 Ton9.5237.5OEWT-PA23-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7547 | KL-20211102-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-11-02 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking from Km 43 to Km 17 on Hensen Road for float access /Rock truck hauling existing material from F088 to Morin@Km 33 as per Valard. Supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-2Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-2Pickup 1/2 Ton9225OEWT-PA23-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7549 | KL-20211103-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-11-03 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 41 shape road. Rock trucks haul existing material from F088 to Morin @ Km 33 as per Valard /Supervision of Morin, Skagen, JJR, Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-2Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-2Pickup 1/2 Ton9.5237.5OEWT-PA23-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7549 | KL-20211103-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-11-03 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 41 shape road. Rock trucks haul existing material from F088 to Morin @ Km 33 as per Valard /Supervision of Morin, Skagen, JJR, Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-2Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-2Pickup 1/2 Ton9.5237.5OEWT-PA23-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7549 | KL-20211103-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-11-03 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 41 shape road. Rock trucks haul existing material from F088 to Morin @ Km 33 as per Valard /Supervision of Morin, Skagen, JJR, Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-2Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-2Pickup 1/2 Ton9.5237.5OEWT-PA23-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7549 | KL-20211103-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2021-11-03 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 41 shape road. Rock trucks haul existing material from F088 to Morin @ Km 33 as per Valard /Supervision of Morin, Skagen, JJR, Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-2Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-2Pickup 1/2 Ton8200OEWT-PA23-Lem | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7550 | KL-20211104-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-11-04 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 42 shaping road and spreading existing material on road surfaces Rock trucks hauling existing material from F088 to @ Km 43/42 as per Valard /Supervision of Morin, Skagen, JJR and OPAS | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-2Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-2Pickup 1/2 Ton9225OEWT-PA23-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7566 | KL-20211111-4 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-11-11 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-4Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-4Pickup 1/2 Ton9225OEWT-PA23-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7566 | KL-20211111-4 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-11-11 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-4Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-4Pickup 1/2 Ton10250OEWT-PA23-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7566 | KL-20211111-4 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2021-11-11 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-4Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-4Pickup 1/2 Ton375OEWT-PA23-Lem | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7570 | KL-20211112-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 5.5 | HR | 19 | 0 |  |  | 137.5 | 17.875 | 155.375 | 2021-11-12 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44520 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7570KL-20211112-2Pickup 1/2 Ton5.5137.5 | KABI LAKE FOREST PRODUCTS LTD7570KL-20211112-2Pickup 1/2 Ton5.5137.5OEWT-PA23-Lem | [5 empty] | 1 | 137.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7570 | KL-20211112-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2021-11-12 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44520 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7570KL-20211112-2Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD7570KL-20211112-2Pickup 1/2 Ton8200OEWT-PA23-Lem | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7571 | KL-20211113-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2021-11-13 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Rock truck on site for hauling of existing material @ 24km. Supervision of Morin, Skagen, JJR & Opas. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7571KL-20211113-3Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD7571KL-20211113-3Pickup 1/2 Ton5125OEWT-PA23-Lem | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7572 | KL-20211114-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 16 | HR | 19 | 0 |  |  | 400 | 52 | 452 | 2021-11-14 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from 44Km to 41Km levelling ruts and shaping road. Rock truck on site for hauling of existing material @ 27Km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7572KL-20211114-2Pickup 1/2 Ton16400 | KABI LAKE FOREST PRODUCTS LTD7572KL-20211114-2Pickup 1/2 Ton16400OEWT-PA23-Lem | [5 empty] | 1 | 400 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7573 | KL-20211115-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-11-15 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road. Rock truck hauling existing material from 25Km and spotting dumping @ 22/23Km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7573KL-20211115-2Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7573KL-20211115-2Pickup 1/2 Ton9.5237.5OEWT-PA23-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7573 | KL-20211115-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-11-15 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road. Rock truck hauling existing material from 25Km and spotting dumping @ 22/23Km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7573KL-20211115-2Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7573KL-20211115-2Pickup 1/2 Ton9225OEWT-PA23-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7565 | KL-20211110-4 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-11-10 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 42 access leveling ruts and shaping road rock trucks hauling from Km 27 to JJR @ Km 26/24 repairing road sections /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-4Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-4Pickup 1/2 Ton9225OEWT-PA23-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7565 | KL-20211110-4 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-11-10 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 42 access leveling ruts and shaping road rock trucks hauling from Km 27 to JJR @ Km 26/24 repairing road sections /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-4Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-4Pickup 1/2 Ton9225OEWT-PA23-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7565 | KL-20211110-4 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2021-11-10 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 42 access leveling ruts and shaping road rock trucks hauling from Km 27 to JJR @ Km 26/24 repairing road sections /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-4Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-4Pickup 1/2 Ton5125OEWT-PA23-Lem | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7565 | KL-20211110-4 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2021-11-10 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 42 access leveling ruts and shaping road rock trucks hauling from Km 27 to JJR @ Km 26/24 repairing road sections /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-4Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-4Pickup 1/2 Ton375OEWT-PA23-Lem | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7573 | KL-20211115-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2021-11-15 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road. Rock truck hauling existing material from 25Km and spotting dumping @ 22/23Km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7573KL-20211115-2Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD7573KL-20211115-2Pickup 1/2 Ton8200OEWT-PA23-Lem | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7575 | KL-20211116-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-11-16 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road for freezing. Rock truck hauling existing material from 27Km to 23/24Km & dricing out to 9Km at end of shift for float accesss. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-3Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-3Pickup 1/2 Ton9225OEWT-PA23-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7575 | KL-20211116-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-11-16 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road for freezing. Rock truck hauling existing material from 27Km to 23/24Km & dricing out to 9Km at end of shift for float accesss. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-3Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-3Pickup 1/2 Ton10250OEWT-PA23-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7575 | KL-20211116-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2021-11-16 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road for freezing. Rock truck hauling existing material from 27Km to 23/24Km & dricing out to 9Km at end of shift for float accesss. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-3Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-3Pickup 1/2 Ton8200OEWT-PA23-Lem | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7576 | KL-20211117-4 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 17 | HR | 19 | 0 |  |  | 425 | 55.25 | 480.25 | 2021-11-17 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road & snow removal @ 44km to 43km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7576KL-20211117-4Pickup 1/2 Ton17425 | KABI LAKE FOREST PRODUCTS LTD7576KL-20211117-4Pickup 1/2 Ton17425OEWT-PA23-Lem | [5 empty] | 1 | 425 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7577 | KL-20211118-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-11-18 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 43 to Km 46 due to icy conditions /Supervision of Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44525 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7577KL-20211118-3Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7577KL-20211118-3Pickup 1/2 Ton9225OEWT-PA23-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7577 | KL-20211118-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2021-11-18 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 43 to Km 46 due to icy conditions /Supervision of Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44525 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7577KL-20211118-3Pickup 1/2 Ton7175 | KABI LAKE FOREST PRODUCTS LTD7577KL-20211118-3Pickup 1/2 Ton7175OEWT-PA23-Lem | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7550 | KL-20211104-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-11-04 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 42 shaping road and spreading existing material on road surfaces Rock trucks hauling existing material from F088 to @ Km 43/42 as per Valard /Supervision of Morin, Skagen, JJR and OPAS | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-2Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-2Pickup 1/2 Ton9.5237.5OEWT-PA23-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7550 | KL-20211104-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-11-04 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 42 shaping road and spreading existing material on road surfaces Rock trucks hauling existing material from F088 to @ Km 43/42 as per Valard /Supervision of Morin, Skagen, JJR and OPAS | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-2Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-2Pickup 1/2 Ton9.5237.5OEWT-PA23-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7550 | KL-20211104-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2021-11-04 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 42 shaping road and spreading existing material on road surfaces Rock trucks hauling existing material from F088 to @ Km 43/42 as per Valard /Supervision of Morin, Skagen, JJR and OPAS | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-2Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-2Pickup 1/2 Ton8200OEWT-PA23-Lem | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7551 | KL-20211105-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-11-05 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 42 to Km 41 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F088 to @ Km 42/41 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-2Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-2Pickup 1/2 Ton9.5237.5OEWT-PA23-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7551 | KL-20211105-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-11-05 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 42 to Km 41 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F088 to @ Km 42/41 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-2Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-2Pickup 1/2 Ton9.5237.5OEWT-PA23-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7551 | KL-20211105-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-11-05 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 42 to Km 41 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F088 to @ Km 42/41 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-2Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-2Pickup 1/2 Ton9.5237.5OEWT-PA23-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7551 | KL-20211105-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2021-11-05 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 42 to Km 41 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F088 to @ Km 42/41 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-2Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-2Pickup 1/2 Ton8200OEWT-PA23-Lem | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7553 | KL-20211107-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-11-07 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working fro Km 41 to Km 39 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 41/39 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-2Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-2Pickup 1/2 Ton9225OEWT-PA23-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7553 | KL-20211107-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-11-07 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working fro Km 41 to Km 39 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 41/39 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-2Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-2Pickup 1/2 Ton9.5237.5OEWT-PA23-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7553 | KL-20211107-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-11-07 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working fro Km 41 to Km 39 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 41/39 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-2Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-2Pickup 1/2 Ton9.5237.5OEWT-PA23-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7553 | KL-20211107-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2021-11-07 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working fro Km 41 to Km 39 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 41/39 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-2Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-2Pickup 1/2 Ton8200OEWT-PA23-Lem | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7563 | KL-20211108-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-11-08 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 42 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-3Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-3Pickup 1/2 Ton9.5237.5OEWT-PA23-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7563 | KL-20211108-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-11-08 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 42 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-3Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-3Pickup 1/2 Ton10250OEWT-PA23-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7563 | KL-20211108-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-11-08 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 42 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-3Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-3Pickup 1/2 Ton10250OEWT-PA23-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7563 | KL-20211108-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2021-11-08 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 42 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-3Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-3Pickup 1/2 Ton8200OEWT-PA23-Lem | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7564 | KL-20211109-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-11-09 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 44 leveling ruts and shaping road Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-3Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-3Pickup 1/2 Ton9225OEWT-PA23-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7564 | KL-20211109-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-11-09 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 44 leveling ruts and shaping road Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-3Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-3Pickup 1/2 Ton9225OEWT-PA23-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7564 | KL-20211109-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-11-09 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 44 leveling ruts and shaping road Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-3Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-3Pickup 1/2 Ton9225OEWT-PA23-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7564 | KL-20211109-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-11-09 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 44 leveling ruts and shaping road Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-3Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-3Pickup 1/2 Ton10250OEWT-PA23-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7583 | KL-20211119-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-11-19 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 43 to Km 40 due to icy conditions/Supervision of Morin, Skagen, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7583KL-20211119-3Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7583KL-20211119-3Pickup 1/2 Ton9225OEWT-PA23-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7583 | KL-20211119-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2021-11-19 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 43 to Km 40 due to icy conditions/Supervision of Morin, Skagen, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7583KL-20211119-3Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD7583KL-20211119-3Pickup 1/2 Ton8200OEWT-PA23-Lem | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7584 | KL-20211120-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-11-20 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 42 to Km 46 due to slippery conditions/Supervision of Morin, Skagen, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7584KL-20211120-3Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7584KL-20211120-3Pickup 1/2 Ton9225OEWT-PA23-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7584 | KL-20211120-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2021-11-20 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 42 to Km 46 due to slippery conditions/Supervision of Morin, Skagen, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7584KL-20211120-3Pickup 1/2 Ton7175 | KABI LAKE FOREST PRODUCTS LTD7584KL-20211120-3Pickup 1/2 Ton7175OEWT-PA23-Lem | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7585 | KL-20211121-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-11-21 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and sanding road @ Km 42 to Km 46 due to slippery conditions/Supervision of Morin, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7585KL-20211121-2Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7585KL-20211121-2Pickup 1/2 Ton9225OEWT-PA23-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7585 | KL-20211121-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2021-11-21 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and sanding road @ Km 42 to Km 46 due to slippery conditions/Supervision of Morin, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7585KL-20211121-2Pickup 1/2 Ton7175 | KABI LAKE FOREST PRODUCTS LTD7585KL-20211121-2Pickup 1/2 Ton7175OEWT-PA23-Lem | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7587 | KL-20211123-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-11-23 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 scraping and shaping @ Km 42 to Km 46 /Excavator 2 scraping and sanding Km 13.5 to 17 for stringing crews/Supervision of Skagen and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7587KL-20211123-2Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7587KL-20211123-2Pickup 1/2 Ton9225OEWT-PA23-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7587 | KL-20211123-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-11-23 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 scraping and shaping @ Km 42 to Km 46 /Excavator 2 scraping and sanding Km 13.5 to 17 for stringing crews/Supervision of Skagen and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7587KL-20211123-2Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7587KL-20211123-2Pickup 1/2 Ton9225OEWT-PA23-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7587 | KL-20211123-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2021-11-23 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 scraping and shaping @ Km 42 to Km 46 /Excavator 2 scraping and sanding Km 13.5 to 17 for stringing crews/Supervision of Skagen and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7587KL-20211123-2Pickup 1/2 Ton7175 | KABI LAKE FOREST PRODUCTS LTD7587KL-20211123-2Pickup 1/2 Ton7175OEWT-PA23-Lem | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7590 | KL-20211124-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-11-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 scraping and shaping @ Km 45 to Km 48 /Excavator 2 scraping and sanding Km 16 to 18 for stringing crews demob | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7590KL-20211124-2Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7590KL-20211124-2Pickup 1/2 Ton9225OEWT-PA23-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7590 | KL-20211124-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-11-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 scraping and shaping @ Km 45 to Km 48 /Excavator 2 scraping and sanding Km 16 to 18 for stringing crews demob | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7590KL-20211124-2Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7590KL-20211124-2Pickup 1/2 Ton9225OEWT-PA23-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7590 | KL-20211124-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2021-11-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 scraping and shaping @ Km 45 to Km 48 /Excavator 2 scraping and sanding Km 16 to 18 for stringing crews demob | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7590KL-20211124-2Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD7590KL-20211124-2Pickup 1/2 Ton6150OEWT-PA23-Lem | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7932 | KL-20220305-1-RCL | 53541001 | Reclamation | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2022-03-05 |  | OEWT-PA27-RCL | 2022-03-31 |  | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 330 excavator clearing snow from ditches, and spreading ripped material. 336 excavator ripping frozen roadway F033-F034 | 10 | F066-F118 | Paint Lake 2 | 0 | 44625 |  | 37 | 44625 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7932KL-20220305-1-RCLPickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD7932KL-20220305-1-RCLPickup 1/2 Ton10250 | WF10-Access | WF10-Access | WF10-Access | 1 | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7932 | KL-20220305-1-RCL | 53541001 | Reclamation | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2022-03-05 |  | OEWT-PA27-RCL | 2022-03-31 |  | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 330 excavator clearing snow from ditches, and spreading ripped material. 336 excavator ripping frozen roadway F033-F034 | 10 | F066-F118 | Paint Lake 2 | 0 | 44625 |  | 37 | 44625 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7932KL-20220305-1-RCLPickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD7932KL-20220305-1-RCLPickup 1/2 Ton4100 | WF10-Access | WF10-Access | WF10-Access | 1 | 1 | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5248 | KL-20210106-12 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2021-01-06 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track Excavator from F117 to F127 due to no float Access/ Operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44209 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5248KL-20210106-12Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD5248KL-20210106-12Pickup 1/2 Ton250OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5309 | KL-20210111-9 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2021-01-11 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Operator travel for F127 to F134 MFN Road Building. | 11 | F119-F134 | Hensen Road | 0 | 44211 |  | 15 | 44219 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5309KL-20210111-9Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD5309KL-20210111-9Pickup 1/2 Ton250OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5322 | KL-20210112-9 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2021-01-12 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi operator travel to F145 MFN Road building/based out of White River (Revised) | 11 | F135-F149 | Dore Lake Road | 0 | 44214 |  | 56 | 44219 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5322KL-20210112-9Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5322KL-20210112-9Pickup 1/2 Ton125OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5330 | KL-20210112-17 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 2.5 | HR | 19 | 0 |  |  | 62.5 | 8.125 | 70.625 | 2021-01-12 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track from 17km to F127.5 due to no float access. | 11 | f119-F134 | Hensen Road | 0 | 44214 |  | 15 | 44219 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5330KL-20210112-17Pickup 1/2 Ton2.562.5 | KABI LAKE FOREST PRODUCTS LTD5330KL-20210112-17Pickup 1/2 Ton2.562.5OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 62.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5333 | KL-20210112-20 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2021-01-12 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Operator travel for F127 to F134 MFN Road Building. | 11 | F119-F134 | Hensen Road | 0 | 44214 |  | 15 | 44219 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5333KL-20210112-20Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD5333KL-20210112-20Pickup 1/2 Ton4100OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5340 | KL-20210113-6 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2021-01-13 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Operator travel to F134, F145 MFN Clearing. Track in Dumonski buncher. | 11 | F119-F134 | Hensen Road | 0 | 44214 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5340KL-20210113-6Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5340KL-20210113-6Pickup 1/2 Ton125OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5344 | KL-20210113-10 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2021-01-13 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Operator travel from F127 to F134 MFN Road Building | 11 | F119-F134 | Hensen Raod | 0 | 44214 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5344KL-20210113-10Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD5344KL-20210113-10Pickup 1/2 Ton6150OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5345 | KL-20210113-11 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2021-01-13 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi excavator operator extra travel to F145 MFN Road Building/Based out of White River | 11 | F135-F149 | Dore Lake Road | 0 | 44214 |  | 56 | 44219 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5345KL-20210113-11Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5345KL-20210113-11Pickup 1/2 Ton125OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5365 | KL-20210114-11 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2021-01-14 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Operator travel for F127 to F134 MFN Road building. Dumonski cutting for corduroy @ F-133. | 11 | F119-F134 | Hensen Road | 0 | 44218 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5365KL-20210114-11Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD5365KL-20210114-11Pickup 1/2 Ton6150OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5367 | KL-20210114-13 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2021-01-14 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator Operators extra travel to F145 MFN road building/ Based out of White River | 11 | F-135 to F-149 | Dore Lake Road | 0 | 44218 |  | 56 | 44220 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5367KL-20210114-13Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5367KL-20210114-13Pickup 1/2 Ton125OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5381 | KL-20210115-12 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2021-01-15 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator operators extra travel to F145 MFN road building/ Based out of White River | 11 | F135-F149 | Dore Lake Road | 0 | 44218 |  | 56 | 44220 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5381KL-20210115-12Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5381KL-20210115-12Pickup 1/2 Ton125OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5383 | KL-20210115-14 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2021-01-15 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Operator Travel for F127 to F134 MFN road Building. Dumonski to travel and track in for clearing. | 11 | F119-F134 | Hensen Road | 0 | 44218 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5383KL-20210115-14Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD5383KL-20210115-14Pickup 1/2 Ton6150OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5401 | KL-20210116-8 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2021-01-16 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Operator travel for F127 to F134 MFN road Building | 11 | F119-F134 | Hensen Road | 0 | 44216 |  | 15 | 44233 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5401KL-20210116-8Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD5401KL-20210116-8Pickup 1/2 Ton4100OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5422 | KL-20210117-10 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2021-01-17 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Operator travel for F127 to F134 MFN road building | 11 | F119-F134 | Hensen Road | 0 | 44216 |  | 15 | 44238 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5422KL-20210117-10Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD5422KL-20210117-10Pickup 1/2 Ton6150OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5424 | KL-20210117-12 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2021-01-17 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Buncher Operator extra travel to F145 MFN clearing/based out of White River | 11 | F135-F149 | Dore Lake Road | 0 | 44216 |  | 56 | 44229 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5424KL-20210117-12Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5424KL-20210117-12Pickup 1/2 Ton125OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5425 | KL-20210117-13 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2021-01-17 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator Operator extra travel to F145 MFN clearing/based out of White River | 11 | F135-F149 | Dore Lake Road | 0 | 44216 |  | 56 | 44229 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5425KL-20210117-13Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5425KL-20210117-13Pickup 1/2 Ton125OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5438 | KL-20210118-12 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2021-01-18 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Operator travel for F127 to F134 MFN Road Building | 11 | F119-F134 | Hensen Road | 0 | 44216 |  | 15 | 44238 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5438KL-20210118-12Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD5438KL-20210118-12Pickup 1/2 Ton4100OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5442 | KL-20210118-16 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2021-01-18 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator filling gorge with trees for fill @ F144/F143 Access (Revised | 11 | F135-F149 | Dore Lake Road | 0 | 44216 |  | 56 | 44229 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5442KL-20210118-16Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD5442KL-20210118-16Pickup 1/2 Ton8200OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5446 | KL-20210118-20 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2021-01-18 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator Operators extra travel to F145 MFN Clearing/Based out of White River. | 11 | F135-F149 | Dore Lake Road | 0 | 44216 |  | 56 | 44229 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5446KL-20210118-20Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5446KL-20210118-20Pickup 1/2 Ton125OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5464 | KL-20210119-15 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2021-01-19 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator Operators extra travel to F145 MFN Road Building/Based out of White River | 11 | F135-F149 | Dore Lake Road | 0 | 44222 |  | 56 | 44229 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5464KL-20210119-15Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5464KL-20210119-15Pickup 1/2 Ton125OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5475 | KL-20210119-26 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2021-01-19 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator starting to make ramp with trees for F133 Hub | 11 | F119-F134 | Hensen Road | 0 | 44222 |  | 15 | 44238 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5475KL-20210119-26Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD5475KL-20210119-26Pickup 1/2 Ton4100OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5476 | KL-20210119-27 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2021-01-19 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Operator travel for F127 to F134 MFN Road Building. | 11 | F119-F134 | Hensen Road | 0 | 44222 |  | 15 | 44238 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5476KL-20210119-27Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD5476KL-20210119-27Pickup 1/2 Ton250OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5488 | KL-20210120-10 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavators extra travel to F145 MFN Road Building/Based out of White River | 11 | F135-F149 | Dore Lake Road | 0 | 44224 |  | 56 | 44229 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5488KL-20210120-10Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5488KL-20210120-10Pickup 1/2 Ton125OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5496 | KL-20210120-18 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Exc finishing making ramp with trees and capping for F133 Hub Access & track to F114/Operator Extra travel/Based out of White River. | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5496KL-20210120-18Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD5496KL-20210120-18Pickup 1/2 Ton11275OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5497 | KL-20210120-19 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336F excavator building new road around F128 structure as per Valard/Operator extra travel/based out of White River | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5497KL-20210120-19Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD5497KL-20210120-19Pickup 1/2 Ton11275OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5533 | KL-20210122-11 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2021-01-22 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Exc Operators extra travel to F145 MFN Road Building/Based out of White River | 11 | F135-F149 | Dore Lake Road | 0 | 44224 |  | 56 | 44230 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5533KL-20210122-11Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD5533KL-20210122-11Pickup 1/2 Ton250OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5539 | KL-20210122-17 | 53511102 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-01-22 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator using existing material to minimize steep grade at F117/F116 Access, as per Valard (Revised) | 11 | F119--F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5539KL-20210122-17Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD5539KL-20210122-17Pickup 1/2 Ton9.5237.5OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4143 | KL-20201103-13 | 53511103 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Go down to Hensen Road and pick up 8 rolls of Geo and take back to White River Yard | 11 | F119-F134 | Hensen Road | 0 | 44153 |  | 56 | 44163 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD4143KL-20201103-13Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD4143KL-20201103-13Pickup 1/2 Ton4100OEWT-PA11-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5368 | KL-20210114-14 | 53511103 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2021-01-14 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Carry Corduroy for wetlands on F147 Access. Buncher rate from Const. Amend #4. | 11 | F135-F149 | Dore Lake Road | 0 | 44218 |  | 56 | 44220 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5368KL-20210114-14Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD5368KL-20210114-14Pickup 1/2 Ton4100OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5380 | KL-20210115-11 | 53511103 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2021-01-15 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Buncher track in and out from F147 access to F145 Junction. Morin track and place corduroy. Buncher rate from Const. Amend #4 | 11 | F135-F149 | Dore Lake Road | 0 | 44218 |  | 56 | 44220 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5380KL-20210115-11Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD5380KL-20210115-11Pickup 1/2 Ton250OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5474 | KL-20210119-25 | 53511103 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2021-01-19 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 335F Boom Brusher tracking from F124 to F133 & start to grind & freeze corduroy for pick up access. | 11 | F119-F134 | Hensen Road | 0 | 44222 |  | 15 | 44237 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5474KL-20210119-25Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD5474KL-20210119-25Pickup 1/2 Ton5125OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5499 | KL-20210120-21 | 53511103 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 335F boom brusher finishing to grind & freeze corduroy for Pick up access & tracking back to F124 | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5499KL-20210120-21Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD5499KL-20210120-21Pickup 1/2 Ton5125OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3300 | KL-20200928-23 | 53511104 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2020-09-28 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauling pit run from Provost Pit #5 to AE1 on Henson Road /Dozer spreading and widening areas | 11 | F-119 to F-134 | Hensen Road | 0 | 44109 |  | 50 | 44110 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD3300KL-20200928-23Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD3300KL-20200928-23Pickup 1/2 Ton13325OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3301 | KL-20200928-24 | 53511104 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2020-09-28 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of JJR Contracting Gravel Haul | 11 | F-119 to F-134 | Hensen Road | 0 | 44109 |  | 50 | 44110 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD3301KL-20200928-24Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD3301KL-20200928-24Pickup 1/2 Ton375OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4084 | KL-20201031-12 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2020-10-31 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sand Hills and corners on Hensen Road for float truck hauling in a buncher/Sanding hauled from provost pit in Wawa | 11 | F203-F211 | Hensen Rd | 0 | 44152 |  | 48 | 44154 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4084KL-20201031-12Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD4084KL-20201031-12Pickup 1/2 Ton375OEWT-PA11-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4992 | KL-20201211-12 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2020-12-11 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load partial load @6km pit on 600 road for sanding of hill laydown 1/ load sand from F119 and sand road for float access as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 48 | 44203 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4992KL-20201211-12Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD4992KL-20201211-12Pickup 1/2 Ton250OEWT-PA12-LEM-R1 | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5037 | KL-20201216-9 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-16 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Skagen and Son Forestry snow removal | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5037KL-20201216-9Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5037KL-20201216-9Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5059 | KL-20201219-6 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2020-12-19 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Skagen & Son Forestry snow removal on Hensen to Km 17. | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5059KL-20201219-6Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5059KL-20201219-6Pickup 1/2 Ton125OEWT-PA12-LEM-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5207 | KL-20210103-5 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2021-01-03 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load of sand from White River town pit/ sanding hills and corners on hensen road from hwy to 17km with existing material as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5207KL-20210103-5Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5207KL-20210103-5Pickup 1/2 Ton125OEWT-PA13-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5283 | KL-20210109-6 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2021-01-09 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Take 1 load of screened sand from town pit, and finish sanding Hensen Rd to km 17. Floats with existing sand as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44211 |  | 15 | 44219 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5283KL-20210109-6Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD5283KL-20210109-6Pickup 1/2 Ton5125OEWT-PA13-LEM | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5363 | KL-20210114-9 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2021-01-14 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load screened sand from town pit and finished sanding Hensen Road to 17km with existing sand as per Valard/ Excavator cleaning up @ F119 for Sand | 11 | F119-F134 | Hensen Road | 0 | 44218 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5363KL-20210114-9Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD5363KL-20210114-9Pickup 1/2 Ton5125OEWT-PA13-LEM | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5439 | KL-20210118-13 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2021-01-18 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6K Dozer Clearing snow from Anjigami Rd to Anjigami River for Bridge delivery as per Valard. | 11 | F228 | F-228 Road | 0 | 44216 |  | 56 | 44229 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5439KL-20210118-13Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD5439KL-20210118-13Pickup 1/2 Ton12300OEWT-PA13-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5510 | KL-20210121-9 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-01-21 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer doing snow removal from km 17 on Hensen Rd to F133/Operator extra travel/Based out of White River. | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5510KL-20210121-9Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD5510KL-20210121-9Pickup 1/2 Ton10250OEWT-PA13-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5555 | KL-20210123-14 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2021-01-23 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336F tracking out from F127 to 17km on Hensen due to no float access. Plowed out all pullouts and F117 Access | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5555KL-20210123-14Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD5555KL-20210123-14Pickup 1/2 Ton250OEWT-PA13-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5614 | KL-20210125-11 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-01-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | D6K dozer starting snow removal from km 17 on Hensen Rd to F133. | 11 | F119-F134 | Hensen Road | 0 | 44225 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5614KL-20210125-11Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD5614KL-20210125-11Pickup 1/2 Ton11275OEWT-PA14-Lem-R1 | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5632 | KL-20210126-16 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-01-26 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | D6K Dozer finishing snow removal from km 17 on Hensen to F133. | 11 | F119-F134 | Hensen Road | 0 | 44222 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5632KL-20210126-16Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD5632KL-20210126-16Pickup 1/2 Ton11275OEWT-PA14-Lem-R1 | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5838 | KL-20210209-15 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2021-02-09 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Drive from White River/load 5 loads of screened sand from Provost Pit 5/Sand hills & corners to km 17 then drive back to White River. | 11 | F119-F134 | Hensen Road | 0 | 44243 |  | 15 | 44250 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5838KL-20210209-15Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD5838KL-20210209-15Pickup 1/2 Ton250OEWT-PA14-Lem-R1 | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5846 | KL-20210210-8 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2021-02-10 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Go to Hensen Rd and steam a culvert @ km 3.5. Cover corduroy in shoefly past F73. Clear snow from road from 0 to 15Km on Hensen West and from Hwy17 to 17Km. | 11 | F119-F134 | Hensen Road | 0 | 44244 |  | 15 | 44250 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5846KL-20210210-8Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD5846KL-20210210-8Pickup 1/2 Ton12300OEWT-PA14-Lem-R1 | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5874 | KL-20210212-5 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2021-02-12 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load 4 loads screen sand from Provost pit #5/ sand hills and corners to 17km on Hensen Road. Grader work form Hwy 17 to 17Km, loader open road to F110 to F112. | 11 | F119-F134 | Hensen Road | 0 | 44244 |  | 15 | 44254 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5874KL-20210212-5Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD5874KL-20210212-5Pickup 1/2 Ton250OEWT-PA14-Lem-R1 | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5916 | KL-20210215-11 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2021-02-15 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat D5K Dozer to F169 for snow removal. Dozer remove snow from F169 to F165. | 11 | F165-F169 | Magpie Hills Road | 0 | 44249 |  | 14 | 44250 | [5 empty] | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD5916KL-20210215-11Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD5916KL-20210215-11Pickup 1/2 Ton125OEWT-PA14-Lem-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5945 | KL-20210217-9 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 16 | HR | 19 | 0 |  |  | 400 | 52 | 452 | 2021-02-17 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Steam Pipe at km 3.5 on Hensen Rd | 11 | F119-F134 | Hensen Road | 0 | 44251 |  | 15 | 44254 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5945KL-20210217-9Pickup 1/2 Ton16400 | KABI LAKE FOREST PRODUCTS LTD5945KL-20210217-9Pickup 1/2 Ton16400OEWT-PA14-Lem-R1 | [5 empty] | 1 | 400 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6039 | KL-20210225-7 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2021-02-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator moving trees & levelling snow banks for snowmobile trail @ F232 | 11 | F232 | F-232 Road | 0 | 44256 |  | 56 | 44259 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6039KL-20210225-7Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD6039KL-20210225-7Pickup 1/2 Ton375OEWT-PA14-Lem-R1 | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6048 | KL-20210225-16 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2021-02-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load of screeded sand from Town Pit/Haul 2 loads of screened sand from MacIntyre Pit/Sand hills & corners to km 17 on Hensen, drive back to White River | 11 | F119-F134 | Hensen Road | 0 | 44256 |  | 56 | 44262 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6048KL-20210225-16Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD6048KL-20210225-16Pickup 1/2 Ton125OEWT-PA14-Lem-R1 | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5931 | KL-20210216-12 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-02-16 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Lake and Cress float with Legos, access mats and bearing timbers for 12970.00 WC/ Excavator unloaded and storing/labourer cleaning snow off the Dam | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44249 |  | 15 | 44254 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5931KL-20210216-12Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD5931KL-20210216-12Pickup 1/2 Ton10250OEWT-PA14-Lem-R1 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6346 | KL-20210316-5 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2021-03-16 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish tracking 2 excavators out from F215 to 9km on Ajigami road/pushing snow back for drainage (revised | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44281 |  | 56 | 44282 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6346KL-20210316-5Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD6346KL-20210316-5Pickup 1/2 Ton4100OEWT PA15-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6347 | KL-20210316-6 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-03-16 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | D6T Dozer pushing snow banks back and clearing debris off the road fro F121/F215 access on Anjigami road | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44281 |  | 56 | 44282 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6347KL-20210316-6Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD6347KL-20210316-6Pickup 1/2 Ton10250OEWT PA15-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6352 | KL-20210317-5 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 4.5 | HR | 19 | 0 |  |  | 112.5 | 14.625 | 127.125 | 2021-03-17 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track to F123/F124 from Km 17 on Hensen Road and repair hills for pick up use | 11 | F119-F134 | Hensen Road | 0 | 44281 |  | 56 | 44282 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6352KL-20210317-5Pickup 1/2 Ton4.5112.5 | KABI LAKE FOREST PRODUCTS LTD6352KL-20210317-5Pickup 1/2 Ton4.5112.5OEWT PA15-LEM | [5 empty] | 1 | 112.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6357 | KL-20210318-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 4.5 | HR | 19 | 0 |  |  | 112.5 | 14.625 | 127.125 | 2021-03-18 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair hills from F123 to F127 for pick up access | 11 | F119-F134 | Hensen Road | 0 | 44281 |  | 56 | 44282 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6357KL-20210318-3Pickup 1/2 Ton4.5112.5 | KABI LAKE FOREST PRODUCTS LTD6357KL-20210318-3Pickup 1/2 Ton4.5112.5OEWT PA15-LEM | [5 empty] | 1 | 112.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7592 | KL-20211124-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-11-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader continuing to scraping and sand road to F213/F214 for stringing crews | 11 | F212-F235 | Ainjigame | 0 | 44529 |  | 61 | 44530 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7592KL-20211124-4Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7592KL-20211124-4Pickup 1/2 Ton9.5237.5OEWT-PA23-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7592 | KL-20211124-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2021-11-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader continuing to scraping and sand road to F213/F214 for stringing crews | 11 | F212-F235 | Ainjigame | 0 | 44529 |  | 61 | 44530 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7592KL-20211124-4Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD7592KL-20211124-4Pickup 1/2 Ton250OEWT-PA23-Lem | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7594 | KL-20211125-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-11-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader continuing to scraping and sand road to F213, F217 and to F218 for stringing crews/ Supervision of Skagen | 11 | F212-F235 | Anjigame | 0 | 44525 |  | 61 | 44530 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7594KL-20211125-3Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7594KL-20211125-3Pickup 1/2 Ton9.5237.5OEWT-PA23-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7594 | KL-20211125-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2021-11-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader continuing to scraping and sand road to F213, F217 and to F218 for stringing crews/ Supervision of Skagen | 11 | F212-F235 | Anjigame | 0 | 44525 |  | 61 | 44530 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7594KL-20211125-3Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD7594KL-20211125-3Pickup 1/2 Ton5125OEWT-PA23-Lem | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7602 | KL-20211128-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-11-28 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and shaping road from F204 to F211 and to F200 / supervision of Skagen | 11 | F170-F211 | High Falls Road | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7602KL-20211128-2Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7602KL-20211128-2Pickup 1/2 Ton9.5237.5OEWT-PA24-LEM | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7602 | KL-20211128-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2021-11-28 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and shaping road from F204 to F211 and to F200 / supervision of Skagen | 11 | F170-F211 | High Falls Road | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7602KL-20211128-2Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD7602KL-20211128-2Pickup 1/2 Ton4100OEWT-PA24-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7605 | KL-20211129-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 14 | HR | 19 | 0 |  |  | 350 | 45.5 | 395.5 | 2021-11-29 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F203 to F185 / supervision of Skagen | 11 | F170-F211 | High Falls Road | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7605KL-20211129-2Pickup 1/2 Ton14350 | KABI LAKE FOREST PRODUCTS LTD7605KL-20211129-2Pickup 1/2 Ton14350OEWT-PA24-LEM | [5 empty] | 1 | 350 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7606 | KL-20211129-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-11-29 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17.5 on Hensen Road | 11 | F118-F127 | Hensen Road | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7606KL-20211129-3Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7606KL-20211129-3Pickup 1/2 Ton11275OEWT-PA24-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7607 | KL-20211129-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2021-11-29 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader starting scraping and sanding road to F213/F214 for stringing crews | 11 | F212-F235 | Ainjigame Road | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7607KL-20211129-4Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD7607KL-20211129-4Pickup 1/2 Ton5125OEWT-PA24-LEM | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7610 | KL-20211130-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-11-30 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader continuing scraping and sanding road to F213/F214 for stringing crews | 11 | F212-F235 | Anjigame Road | 0 | 44537 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7610KL-20211130-3Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7610KL-20211130-3Pickup 1/2 Ton9.5237.5OEWT-PA24-LEM | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7610 | KL-20211130-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2021-11-30 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader continuing scraping and sanding road to F213/F214 for stringing crews | 11 | F212-F235 | Anjigame Road | 0 | 44537 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7610KL-20211130-3Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD7610KL-20211130-3Pickup 1/2 Ton375OEWT-PA24-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7611 | KL-20211130-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 14 | HR | 19 | 0 |  |  | 350 | 45.5 | 395.5 | 2021-11-30 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F184 to F181 and F177 to F171 / supervision of Skagen | 11 | F170-F211 | High Falls | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7611KL-20211130-4Pickup 1/2 Ton14350 | KABI LAKE FOREST PRODUCTS LTD7611KL-20211130-4Pickup 1/2 Ton14350OEWT-PA24-LEM | [5 empty] | 1 | 350 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7612 | KL-20211201-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-12-01 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal @ F179 to F180 and F193 to F181 / supervision of Skagen | 11 | F170-F212 | High Falls | 0 | 44537 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7612KL-20211201-2Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD7612KL-20211201-2Pickup 1/2 Ton10250OEWT-PA24-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7612 | KL-20211201-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2021-12-01 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal @ F179 to F180 and F193 to F181 / supervision of Skagen | 11 | F170-F212 | High Falls | 0 | 44537 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7612KL-20211201-2Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD7612KL-20211201-2Pickup 1/2 Ton4100OEWT-PA24-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7615 | KL-20211201-5 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-12-01 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader starting scraping and sanding road to F213/F214 and access to F216 for stringing crews | 11 | F212-F235 | Anjigami | 0 | 44537 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7615KL-20211201-5Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7615KL-20211201-5Pickup 1/2 Ton11275OEWT-PA24-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7616 | KL-20211201-6 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-12-01 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17.5 km on Hensen Road | 11 | F118-F127 | Henson | 0 | 44537 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7616KL-20211201-6Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7616KL-20211201-6Pickup 1/2 Ton11275OEWT-PA24-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7622 | KL-20211202-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 17 | HR | 19 | 0 |  |  | 425 | 55.25 | 480.25 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17.5 on Hensen road/ Dozer working on snow removal and shaping road from F122 to F132 | 11 | F118 - F127 | Henson | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7622KL-20211202-4Pickup 1/2 Ton17425 | KABI LAKE FOREST PRODUCTS LTD7622KL-20211202-4Pickup 1/2 Ton17425OEWT-PA24-LEM | [5 empty] | 1 | 425 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7623 | KL-20211202-5 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader doing snow removal from Anjigami road to F218 | 11 | F212-F235 | Anjigame | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7623KL-20211202-5Pickup 1/2 Ton7175 | KABI LAKE FOREST PRODUCTS LTD7623KL-20211202-5Pickup 1/2 Ton7175OEWT-PA24-LEM | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7626 | KL-20211202-8 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and shaping road @ F203 to F211 | 11 | F170-F211 | High Falls | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7626KL-20211202-8Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD7626KL-20211202-8Pickup 1/2 Ton13325OEWT-PA24-LEM | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7629 | KL-20211203-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2021-12-03 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and shaping road @ F198 to F202 and track to Km 11 on High Falls Raod/ Supervision of Skagen | 11 | F170 - F211 | High Falls | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7629KL-20211203-3Pickup 1/2 Ton7175 | KABI LAKE FOREST PRODUCTS LTD7629KL-20211203-3Pickup 1/2 Ton7175OEWT-PA24-LEM | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7629 | KL-20211203-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2021-12-03 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and shaping road @ F198 to F202 and track to Km 11 on High Falls Raod/ Supervision of Skagen | 11 | F170 - F211 | High Falls | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7629KL-20211203-3Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD7629KL-20211203-3Pickup 1/2 Ton375OEWT-PA24-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7630 | KL-20211203-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2021-12-03 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on sections from Hwy 17 to Km 17.5 on Hensen road filling rough sections with snow | 11 | F118 - F127 | Henson | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7630KL-20211203-4Pickup 1/2 Ton7175 | KABI LAKE FOREST PRODUCTS LTD7630KL-20211203-4Pickup 1/2 Ton7175OEWT-PA24-LEM | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7630 | KL-20211203-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2021-12-03 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on sections from Hwy 17 to Km 17.5 on Hensen road filling rough sections with snow | 11 | F118 - F127 | Henson | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7630KL-20211203-4Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD7630KL-20211203-4Pickup 1/2 Ton125OEWT-PA24-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7634 | KL-20211204-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-12-04 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer tracking from Km 11 to 1.5, scraping road from F177 to F171 and assist stringing crews/ Supervision of Skagen | 11 | F170-F211 | High Falls | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7634KL-20211204-2Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7634KL-20211204-2Pickup 1/2 Ton9225OEWT-PA24-LEM | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7634 | KL-20211204-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2021-12-04 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer tracking from Km 11 to 1.5, scraping road from F177 to F171 and assist stringing crews/ Supervision of Skagen | 11 | F170-F211 | High Falls | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7634KL-20211204-2Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD7634KL-20211204-2Pickup 1/2 Ton375OEWT-PA24-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7635 | KL-20211204-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-12-04 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Graderworking on snow removal from Hwy 17 to Km 17 | 11 | F118 - F127 | Henson | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7635KL-20211204-3Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7635KL-20211204-3Pickup 1/2 Ton9.5237.5OEWT-PA24-LEM | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7635 | KL-20211204-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2021-12-04 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Graderworking on snow removal from Hwy 17 to Km 17 | 11 | F118 - F127 | Henson | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7635KL-20211204-3Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD7635KL-20211204-3Pickup 1/2 Ton125OEWT-PA24-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7642 | KL-20211206-1 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-12-06 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 | 11 | F118-F127 | Henson | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7642KL-20211206-1Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD7642KL-20211206-1Pickup 1/2 Ton10250OEWT-PA24-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7648 | KL-20211207-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 8.5 | HR | 19 | 0 |  |  | 212.5 | 27.625 | 240.125 | 2021-12-07 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on benching snow banks from Hwy 17 to Km 17 and clearing pull offs | 11 | F118-F127 | Henson | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7648KL-20211207-2Pickup 1/2 Ton8.5212.5 | KABI LAKE FOREST PRODUCTS LTD7648KL-20211207-2Pickup 1/2 Ton8.5212.5OEWT-PA24-LEM | [5 empty] | 1 | 212.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7648 | KL-20211207-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2021-12-07 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on benching snow banks from Hwy 17 to Km 17 and clearing pull offs | 11 | F118-F127 | Henson | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7648KL-20211207-2Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD7648KL-20211207-2Pickup 1/2 Ton125OEWT-PA24-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7649 | KL-20211207-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 18 | HR | 19 | 0 |  |  | 450 | 58.5 | 508.5 | 2021-12-07 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F185 to F181 and from F198 to F208/ Grader working on High Falls Road, F200 and F195 access | 11 | F170-F211 | High Falls | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7649KL-20211207-3Pickup 1/2 Ton18450 | KABI LAKE FOREST PRODUCTS LTD7649KL-20211207-3Pickup 1/2 Ton18450OEWT-PA24-LEM | [5 empty] | 1 | 450 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7651 | KL-20211207-5 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2021-12-07 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal @ Trembley Road and F161 to F164 | 11 | F161-F164 | Trembley Falls | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7651KL-20211207-5Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD7651KL-20211207-5Pickup 1/2 Ton6150OEWT-PA24-LEM | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7653 | KL-20211208-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Hensen Road from Hwy 17 to 17Km & widening corners. | 11 | F118-F127 | Henson | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7653KL-20211208-2Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7653KL-20211208-2Pickup 1/2 Ton9225OEWT-PA24-LEM | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7654 | KL-20211208-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F198 to F208 & support of stringing equipment. Grader working on High Falls Road, F170, F175, F176, F185 to F181 & F207 access. | 11 | F170-F211 | High Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7654KL-20211208-3Pickup 1/2 Ton22550 | KABI LAKE FOREST PRODUCTS LTD7654KL-20211208-3Pickup 1/2 Ton22550OEWT-PA24-LEM | [5 empty] | 1 | 550 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7656 | KL-20211208-5 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 2.5 | HR | 19 | 0 |  |  | 62.5 | 8.125 | 70.625 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal @ F169 to F165 | 11 | F165-F169 | Magpie Hills | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7656KL-20211208-5Pickup 1/2 Ton2.562.5 | KABI LAKE FOREST PRODUCTS LTD7656KL-20211208-5Pickup 1/2 Ton2.562.5OEWT-PA24-LEM | [5 empty] | 1 | 62.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7661 | KL-20211209-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 8.5 | HR | 19 | 0 |  |  | 212.5 | 27.625 | 240.125 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying Hensen Road from hwy 17 to 17km. Sand truck sanding hills & corners with existing sand from 17km. Excavator used for loading sand. | 11 | F118-F127 | Henson | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7661KL-20211209-4Pickup 1/2 Ton8.5212.5 | KABI LAKE FOREST PRODUCTS LTD7661KL-20211209-4Pickup 1/2 Ton8.5212.5OEWT-PA24-LEM | [5 empty] | 1 | 212.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7661 | KL-20211209-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying Hensen Road from hwy 17 to 17km. Sand truck sanding hills & corners with existing sand from 17km. Excavator used for loading sand. | 11 | F118-F127 | Henson | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7661KL-20211209-4Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD7661KL-20211209-4Pickup 1/2 Ton375OEWT-PA24-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7664 | KL-20211209-7 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 21 | HR | 19 | 0 |  |  | 525 | 68.25 | 593.25 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal @ F180, F172, F171, F173 & F208 to F211. Grader working on High Falls Road, F185 to F181 & access to F207 | 11 | F170-F211 | High Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7664KL-20211209-7Pickup 1/2 Ton21525 | KABI LAKE FOREST PRODUCTS LTD7664KL-20211209-7Pickup 1/2 Ton21525OEWT-PA24-LEM | [5 empty] | 1 | 525 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7667 | KL-20211210-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 8.5 | HR | 19 | 0 |  |  | 212.5 | 27.625 | 240.125 | 2021-12-10 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow remvoal and scarifying Hensen Road from hwy 17 to 17Km. | 11 | F118-F127 | Henson | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7667KL-20211210-3Pickup 1/2 Ton8.5212.5 | KABI LAKE FOREST PRODUCTS LTD7667KL-20211210-3Pickup 1/2 Ton8.5212.5OEWT-PA24-LEM | [5 empty] | 1 | 212.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7668 | KL-20211210-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 16.5 | HR | 19 | 0 |  |  | 412.5 | 53.625 | 466.125 | 2021-12-10 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal to F198, F202 & F2003 to F211. Grader working on High Falls road, F180, F194 to F197 & access to F207. | 11 | F170-F211 | High Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7668KL-20211210-4Pickup 1/2 Ton16.5412.5 | KABI LAKE FOREST PRODUCTS LTD7668KL-20211210-4Pickup 1/2 Ton16.5412.5OEWT-PA24-LEM | [5 empty] | 1 | 412.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7669 | KL-20211210-5 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2021-12-10 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal @ Trembley Road & F161 to F164 | 11 | F161 - F164 | Trembley Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7669KL-20211210-5Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD7669KL-20211210-5Pickup 1/2 Ton6150OEWT-PA24-LEM | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7672 | KL-20211211-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2021-12-11 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow remvoal from Hwy 17 to 17Km. | 11 | F118-F127 | Henson | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7672KL-20211211-3Pickup 1/2 Ton7175 | KABI LAKE FOREST PRODUCTS LTD7672KL-20211211-3Pickup 1/2 Ton7175OEWT-PA24-LEM | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7673 | KL-20211211-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-12-11 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working from F171 to F193 & on High Falls Road to 13Km. | 11 | F170-F211 | High Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7673KL-20211211-4Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7673KL-20211211-4Pickup 1/2 Ton9.5237.5OEWT-PA24-LEM | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7683 | KL-20211212-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-12-12 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Scarifying from Hwy 17 to Km 17 and clearing pull offs | 11 | F118-F127 | Henson | 0 | 44551 |  | 61 | 44561 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7683KL-20211212-3Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7683KL-20211212-3Pickup 1/2 Ton9.5237.5OEWT-PA24-LEM | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7684 | KL-20211212-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2021-12-12 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on High Falls Road to Km 13 and F200/ Dozer working from F206 to F211 | 11 | F170-F211 | High Falls | 0 | 44551 |  | 61 | 44561 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7684KL-20211212-4Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD7684KL-20211212-4Pickup 1/2 Ton4100OEWT-PA24-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7684 | KL-20211212-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2021-12-12 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on High Falls Road to Km 13 and F200/ Dozer working from F206 to F211 | 11 | F170-F211 | High Falls | 0 | 44551 |  | 61 | 44561 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7684KL-20211212-4Pickup 1/2 Ton7175 | KABI LAKE FOREST PRODUCTS LTD7684KL-20211212-4Pickup 1/2 Ton7175OEWT-PA24-LEM | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7685 | KL-20211212-5 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 4.5 | HR | 19 | 0 |  |  | 112.5 | 14.625 | 127.125 | 2021-12-12 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Snow removal and trembley road and F161 to F164 | 11 | F161 - F164 | Trembley Falls | 0 | 44551 |  | 61 | 44560 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7685KL-20211212-5Pickup 1/2 Ton4.5112.5 | KABI LAKE FOREST PRODUCTS LTD7685KL-20211212-5Pickup 1/2 Ton4.5112.5OEWT-PA24-LEM | [5 empty] | 1 | 112.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7688 | KL-20211213-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 4.5 | HR | 19 | 0 |  |  | 112.5 | 14.625 | 127.125 | 2021-12-13 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Finish snow removal from F198 to F201 | 11 | F170-F211 | High Falls | 0 | 44551 |  | 61 | 44560 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7688KL-20211213-3Pickup 1/2 Ton4.5112.5 | KABI LAKE FOREST PRODUCTS LTD7688KL-20211213-3Pickup 1/2 Ton4.5112.5OEWT-PA24-LEM | [5 empty] | 1 | 112.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7690 | KL-20211214-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-12-14 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working from @ F173 to F171 and on High Falls Road to Km 13 | 11 | F170-F211 | High Falls | 0 | 44551 |  | 61 | 44560 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7690KL-20211214-2Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD7690KL-20211214-2Pickup 1/2 Ton10250OEWT-PA24-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7691 | KL-20211214-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-12-14 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Scarifying hills and corners from Km 12 to Hwy 17/Dozer starting snow removal from Hensen road to F128 | 11 | F118-F127 | Henson | 0 | 44551 |  | 61 | 44560 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7691KL-20211214-3Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD7691KL-20211214-3Pickup 1/2 Ton13325OEWT-PA24-LEM | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7696 | KL-20211215-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2021-12-15 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working High Falls Road and from @ F173 to F171 | 11 | F170 - F211 | High Falls | 0 |  |  | 46 | 44218 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7696KL-20211215-3Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD7696KL-20211215-3Pickup 1/2 Ton375OEWT-PA24-LEM | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7697 | KL-20211215-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-12-15 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer finishing snow removal from Hensen road to F132 | 11 | F118-F127 | Henson | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7697KL-20211215-4Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7697KL-20211215-4Pickup 1/2 Ton9225OEWT-PA24-LEM | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7697 | KL-20211215-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2021-12-15 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer finishing snow removal from Hensen road to F132 | 11 | F118-F127 | Henson | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7697KL-20211215-4Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD7697KL-20211215-4Pickup 1/2 Ton250OEWT-PA24-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7698 | KL-20211215-5 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2021-12-15 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Scarifying Trembley Road | 11 | F161 - F164 | Trembley Falls | 0 |  |  | 46 | 44583 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7698KL-20211215-5Pickup 1/2 Ton7175 | KABI LAKE FOREST PRODUCTS LTD7698KL-20211215-5Pickup 1/2 Ton7175OEWT-PA24-LEM | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7700 | KL-20211216-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-12-16 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F037 to F033 | 10 | F066-F118 | Paint Lake 2 | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7700KL-20211216-3Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7700KL-20211216-3Pickup 1/2 Ton11275OEWT-PA24-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7701 | KL-20211216-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2021-12-16 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Stringer Support |  | Approved |  |  | Grader @ High Falls Road in Support of Stringing crew | 11 | F170-F211 | High Falls | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7701KL-20211216-4Pickup 1/2 Ton7175 | KABI LAKE FOREST PRODUCTS LTD7701KL-20211216-4Pickup 1/2 Ton7175OEWT-PA24-LEM | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7708 | KL-20211219-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-12-19 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hensen Road to F127 | 11 | F118-F127 | Henson | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7708KL-20211219-4Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7708KL-20211219-4Pickup 1/2 Ton11275OEWT-PA24-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7714 | KL-20211229-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-12-29 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hensen Road to F132 | 11 | F119-F127 | Henson | 0 |  |  | 61 | 44572 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7714KL-20211229-2Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7714KL-20211229-2Pickup 1/2 Ton9225OEWT-PA25-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7716 | KL-20211230-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-12-30 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal from Hensen Road to F132 for freezing | 11 | F119-F127 | Henson | 0 |  |  | 61 | 44572 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7716KL-20211230-2Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7716KL-20211230-2Pickup 1/2 Ton9225OEWT-PA25-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7717 | KL-20211231-1 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 7.5 | HR | 19 | 0 |  |  | 187.5 | 24.375 | 211.875 | 2021-12-31 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hensen Road to F132 | 11 | F119-F127 | Henson | 0 |  |  | 61 | 44572 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7717KL-20211231-1Pickup 1/2 Ton7.5187.5 | KABI LAKE FOREST PRODUCTS LTD7717KL-20211231-1Pickup 1/2 Ton7.5187.5OEWT-PA25-Lem | [5 empty] | 1 | 187.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7720 | KL-20220102-1 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2022-01-02 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal, widening road and clearing pull offs from Hensen road to F132 for freezing | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7720KL-20220102-1Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7720KL-20220102-1Pickup 1/2 Ton11275OEWT-PA25-Lem | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7721 | KL-20220102-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2022-01-02 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on Trembley Road from Harbour Road to Hwy 17 | 11 | F161-F164 | Trembley Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7721KL-20220102-2Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD7721KL-20220102-2Pickup 1/2 Ton6150OEWT-PA25-Lem | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7722 | KL-20220102-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 6.5 | HR | 19 | 0 |  |  | 162.5 | 21.125 | 183.625 | 2022-01-02 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 3.5 on High Falls Road and F171 to F177 | 11 | F118-F127 | Henson | 0 | 44568 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7722KL-20220102-3Pickup 1/2 Ton6.5162.5 | KABI LAKE FOREST PRODUCTS LTD7722KL-20220102-3Pickup 1/2 Ton6.5162.5OEWT-PA25-Lem | [5 empty] | 1 | 162.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7725 | KL-20220103-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 3.5 | HR | 19 | 0 |  |  | 87.5 | 11.375 | 98.875 | 2022-01-03 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F164 to F161 | 11 | F161-F164 | Trembley Falls | 0 | 44568 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7725KL-20220103-3Pickup 1/2 Ton3.587.5 | KABI LAKE FOREST PRODUCTS LTD7725KL-20220103-3Pickup 1/2 Ton3.587.5OEWT-PA25-Lem | [5 empty] | 1 | 87.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7726 | KL-20220103-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2022-01-03 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F171 to F188 | 11 | F170-F211 | High Falls | 0 | 44568 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7726KL-20220103-4Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD7726KL-20220103-4Pickup 1/2 Ton8200OEWT-PA25-Lem | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7727 | KL-20220103-5 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2022-01-03 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F169 to F165 | 11 | F165-F169 | Magpie Hills | 0 | 44568 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7727KL-20220103-5Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD7727KL-20220103-5Pickup 1/2 Ton375OEWT-PA25-Lem | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7729 | KL-20220104-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2022-01-04 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working out from F131 to F125 fixing rough areas and shaping road | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7729KL-20220104-2Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD7729KL-20220104-2Pickup 1/2 Ton375OEWT-PA25-Lem | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7730 | KL-20220104-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 10.5 | HR | 19 | 0 |  |  | 262.5 | 34.125 | 296.625 | 2022-01-04 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F171, F180, F165 and High Falls Road to Km 13 | 11 | F170-F211 | High Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7730KL-20220104-3Pickup 1/2 Ton10.5262.5 | KABI LAKE FOREST PRODUCTS LTD7730KL-20220104-3Pickup 1/2 Ton10.5262.5OEWT-PA25-Lem | [5 empty] | 1 | 262.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7732 | KL-20220105-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2022-01-05 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hensen Road to F132 and assisting stringing crews/Excavatorcleaning up and setting up a face @Km 17 for sand access | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7732KL-20220105-2Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD7732KL-20220105-2Pickup 1/2 Ton13325OEWT-PA25-Lem | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7733 | KL-20220105-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 4.5 | HR | 19 | 0 |  |  | 112.5 | 14.625 | 127.125 | 2022-01-05 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  |  | 11 | F161 - F164 | Trembley Falls | 0 | 44572 |  | 46 | 44562 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7733KL-20220105-3Pickup 1/2 Ton4.5112.5 | KABI LAKE FOREST PRODUCTS LTD7733KL-20220105-3Pickup 1/2 Ton4.5112.5OEWT-PA25-Lem | [5 empty] | 1 | 112.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7733 | KL-20220105-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2022-01-05 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  |  | 11 | F161 - F164 | Trembley Falls | 0 | 44572 |  | 46 | 44562 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7733KL-20220105-3Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD7733KL-20220105-3Pickup 1/2 Ton125OEWT-PA25-Lem | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7734 | KL-20220105-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2022-01-05 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F171 to F188 | 11 | F170-F211 | High Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7734KL-20220105-4Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD7734KL-20220105-4Pickup 1/2 Ton5125OEWT-PA25-Lem | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7735 | KL-20220105-5 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 2.5 | HR | 19 | 0 |  |  | 62.5 | 8.125 | 70.625 | 2022-01-05 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F169 to F165 | 11 | F165 - F169 | Magpie Hills | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7735KL-20220105-5Pickup 1/2 Ton2.562.5 | KABI LAKE FOREST PRODUCTS LTD7735KL-20220105-5Pickup 1/2 Ton2.562.5OEWT-PA25-Lem | [5 empty] | 1 | 62.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7738 | KL-20220106-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 4.5 | HR | 19 | 0 |  |  | 112.5 | 14.625 | 127.125 | 2022-01-06 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on filling water holes with snow, widening road and corners to F127 for stringing crews | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7738KL-20220106-3Pickup 1/2 Ton4.5112.5 | KABI LAKE FOREST PRODUCTS LTD7738KL-20220106-3Pickup 1/2 Ton4.5112.5OEWT-PA25-Lem | [5 empty] | 1 | 112.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7738 | KL-20220106-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2022-01-06 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on filling water holes with snow, widening road and corners to F127 for stringing crews | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7738KL-20220106-3Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD7738KL-20220106-3Pickup 1/2 Ton125OEWT-PA25-Lem | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7741 | KL-20220107-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 8.5 | HR | 19 | 0 |  |  | 212.5 | 27.625 | 240.125 | 2022-01-07 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road and corners to F132 for stringing crews | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7741KL-20220107-3Pickup 1/2 Ton8.5212.5 | KABI LAKE FOREST PRODUCTS LTD7741KL-20220107-3Pickup 1/2 Ton8.5212.5OEWT-PA25-Lem | [5 empty] | 1 | 212.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7741 | KL-20220107-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2022-01-07 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road and corners to F132 for stringing crews | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7741KL-20220107-3Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD7741KL-20220107-3Pickup 1/2 Ton250OEWT-PA25-Lem | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7742 | KL-20220107-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2022-01-07 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Trembley Road from Km 6 to Km 1 abd F161 to F164 | 11 | F161 - F164 | Trembley Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7742KL-20220107-4Pickup 1/2 Ton7175 | KABI LAKE FOREST PRODUCTS LTD7742KL-20220107-4Pickup 1/2 Ton7175OEWT-PA25-Lem | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7743 | KL-20220107-5 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2022-01-07 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working from F171 to F177 | 11 | F170-F211 | High Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7743KL-20220107-5Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD7743KL-20220107-5Pickup 1/2 Ton375OEWT-PA25-Lem | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7745 | KL-20220108-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2022-01-08 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working from Hensen Road to F131, dragging road with blast mat, scraping hills and assisting stringers hauling in material | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7745KL-20220108-2Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD7745KL-20220108-2Pickup 1/2 Ton10250OEWT-PA25-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7746 | KL-20220108-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2022-01-08 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Trembley Road from Km 6 to Km 1 and F161 to F164 | 11 | F161-F164 | Trembley Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7746KL-20220108-3Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD7746KL-20220108-3Pickup 1/2 Ton8200OEWT-PA25-Lem | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7747 | KL-20220108-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 2.5 | HR | 19 | 0 |  |  | 62.5 | 8.125 | 70.625 | 2022-01-08 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working from F171 to F177 | 11 | F170-F211 | High Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7747KL-20220108-4Pickup 1/2 Ton2.562.5 | KABI LAKE FOREST PRODUCTS LTD7747KL-20220108-4Pickup 1/2 Ton2.562.5OEWT-PA25-Lem | [5 empty] | 1 | 62.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7748 | KL-20220108-5 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 2.5 | HR | 19 | 0 |  |  | 62.5 | 8.125 | 70.625 | 2022-01-08 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F169 to F165 | 11 | F165 - F169 | Magpie Hills | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7748KL-20220108-5Pickup 1/2 Ton2.562.5 | KABI LAKE FOREST PRODUCTS LTD7748KL-20220108-5Pickup 1/2 Ton2.562.5OEWT-PA25-Lem | [5 empty] | 1 | 62.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7749 | KL-20220109-1 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2022-01-09 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working on snow removal from Km 17 on Hensen to Hwy 17 and clearing pull offs/Dozer pushing back snow banks from Km 17 to Km 1 on Hensen Road | 11 | F118-F127 | Henson | 0 | 44575 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7749KL-20220109-1Pickup 1/2 Ton22550 | KABI LAKE FOREST PRODUCTS LTD7749KL-20220109-1Pickup 1/2 Ton22550OEWT-PA25-Lem | [5 empty] | 1 | 550 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7750 | KL-20220109-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-01-09 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Snow removal from F171 to F188 and clearing pads and pull offs | 11 | F170-F211 | High Falls | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7750KL-20220109-2Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7750KL-20220109-2Pickup 1/2 Ton12300OEWT-PA25-Lem | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7752 | KL-20220110-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 10.5 | HR | 19 | 0 |  |  | 262.5 | 34.125 | 296.625 | 2022-01-10 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer pushing back snow banks and clearing pull offs from Km .5 to Km 17 on Hensen Road | 11 | F118-F127 | Henson | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7752KL-20220110-2Pickup 1/2 Ton10.5262.5 | KABI LAKE FOREST PRODUCTS LTD7752KL-20220110-2Pickup 1/2 Ton10.5262.5OEWT-PA25-Lem | [5 empty] | 1 | 262.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7753 | KL-20220110-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2022-01-10 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Trembley Road from Km 7 to Km 1 and F161 to F164 | 11 | F161 - F164 | Trembley Falls | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7753KL-20220110-3Pickup 1/2 Ton7175 | KABI LAKE FOREST PRODUCTS LTD7753KL-20220110-3Pickup 1/2 Ton7175OEWT-PA25-Lem | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7754 | KL-20220110-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 3.5 | HR | 19 | 0 |  |  | 87.5 | 11.375 | 98.875 | 2022-01-10 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F169 to F165 and pads | 11 | F165 - F169 | Magpie Hills | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7754KL-20220110-4Pickup 1/2 Ton3.587.5 | KABI LAKE FOREST PRODUCTS LTD7754KL-20220110-4Pickup 1/2 Ton3.587.5OEWT-PA25-Lem | [5 empty] | 1 | 87.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7756 | KL-20220111-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 10.5 | HR | 19 | 0 |  |  | 262.5 | 34.125 | 296.625 | 2022-01-11 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader dragging road with blast mat, scraping hills and filling in rough areas | 11 | F118-F127 | Henson | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7756KL-20220111-2Pickup 1/2 Ton10.5262.5 | KABI LAKE FOREST PRODUCTS LTD7756KL-20220111-2Pickup 1/2 Ton10.5262.5OEWT-PA25-Lem | [5 empty] | 1 | 262.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7757 | KL-20220111-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2022-01-11 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F171 to F188 | 11 | F171 - F211 | High Falls | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7757KL-20220111-3Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD7757KL-20220111-3Pickup 1/2 Ton8200OEWT-PA25-Lem | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7760 | KL-20220112-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2022-01-12 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader scraping hills, clearing spur roads and sanding Hills to F127 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7760KL-20220112-3Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD7760KL-20220112-3Pickup 1/2 Ton6150OEWT-PA25-Lem | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7761 | KL-20220112-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2022-01-12 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Scarifying road from F171 to F177 | 11 | F170-F211 | High Falls | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7761KL-20220112-4Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD7761KL-20220112-4Pickup 1/2 Ton250OEWT-PA25-Lem | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7762 | KL-20220112-5 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2022-01-12 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader driving from High Falls, scarifing hills and corners Trembley Road from Km 7 to Km 1 and F161 to F164 | 11 | F161 - F164 | Trembley Falls | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7762KL-20220112-5Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD7762KL-20220112-5Pickup 1/2 Ton8200OEWT-PA25-Lem | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7765 | KL-20220113-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2022-01-13 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding and dragging blast mat to F132 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7765KL-20220113-3Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7765KL-20220113-3Pickup 1/2 Ton9225OEWT-PA25-Lem | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7766 | KL-20220113-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2022-01-13 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader for support of stringing crews @ F171 | 11 | F170-F211 | High Falls | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7766KL-20220113-4Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD7766KL-20220113-4Pickup 1/2 Ton6150OEWT-PA25-Lem | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7767 | KL-20220113-5 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2022-01-13 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader driving from High Falls, scarifing hills and corners Trembley Road from Km 7 to Km 1 | 11 | F161 - F164 | Trembley Falls | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7767KL-20220113-5Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD7767KL-20220113-5Pickup 1/2 Ton5125OEWT-PA25-Lem | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7771 | KL-20220114-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2022-01-14 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader finishing sanding and dragging blast mat from Hensen Road to F132 for stringing crews and start sanding Hensen Road with existing material from Km 10.5 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7771KL-20220114-4Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7771KL-20220114-4Pickup 1/2 Ton11275OEWT-PA25-Lem | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7775 | KL-20220115-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 20.5 | HR | 19 | 0 |  |  | 512.5 | 66.625 | 579.125 | 2022-01-15 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding hills on Hensen Road with existing material from Km 10.5 / Grader scarifying and benching snow banks on Hensen road from Km .5 to Km 17 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7775KL-20220115-4Pickup 1/2 Ton20.5512.5 | KABI LAKE FOREST PRODUCTS LTD7775KL-20220115-4Pickup 1/2 Ton20.5512.5OEWT-PA25-Lem | [5 empty] | 1 | 512.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7778 | KL-20220116-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 16 | HR | 19 | 0 |  |  | 400 | 52 | 452 | 2022-01-16 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader clearing pull offs and sanding in Hensen East / Grader working on snow removal on Hensen road from Km .5 to Km 17 and Hensen East to F132 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7778KL-20220116-3Pickup 1/2 Ton16400 | KABI LAKE FOREST PRODUCTS LTD7778KL-20220116-3Pickup 1/2 Ton16400OEWT-PA25-Lem | [5 empty] | 1 | 400 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7781 | KL-20220117-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 12.5 | HR | 19 | 0 |  |  | 312.5 | 40.625 | 353.125 | 2022-01-17 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding in Hensen East / Grader working on snow removal on Hensen road from Km .5 to Km 17 and Hensen East to F132 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7781KL-20220117-3Pickup 1/2 Ton12.5312.5 | KABI LAKE FOREST PRODUCTS LTD7781KL-20220117-3Pickup 1/2 Ton12.5312.5OEWT-PA25-Lem | [5 empty] | 1 | 312.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7784 | KL-20220118-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 21 | HR | 19 | 0 |  |  | 525 | 68.25 | 593.25 | 2022-01-18 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding in Hensen East & driving out to 0.5Km for float. Grader working on benching & pushing back on Hensen road to 15Km. | 11 | F118-F127 | Henson | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7784KL-20220118-3Pickup 1/2 Ton21525 | KABI LAKE FOREST PRODUCTS LTD7784KL-20220118-3Pickup 1/2 Ton21525OEWT-PA25-Lem | [5 empty] | 1 | 525 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7880 | KL-20220213-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2022-02-13 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 1 to Km 6 on Trembley road and from Trembley Road to F161 | 11 | F161 - F164 | Trembley Falls | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7880KL-20220213-4Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD7880KL-20220213-4Pickup 1/2 Ton10250OEWT-PA26-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7889 | KL-20220215-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2022-02-15 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal and scarifying from Hwy 17 to Km 17 on Hensen Road | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7889KL-20220215-2Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD7889KL-20220215-2Pickup 1/2 Ton6150OEWT-PA26-LEM | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7894 | KL-20220216-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2022-02-16 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen Road / Loader clearing entrance @ Hwy 17 and Hensen Road | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7894KL-20220216-2Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD7894KL-20220216-2Pickup 1/2 Ton5125OEWT-PA26-LEM | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7894 | KL-20220216-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2022-02-16 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen Road / Loader clearing entrance @ Hwy 17 and Hensen Road | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7894KL-20220216-2Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD7894KL-20220216-2Pickup 1/2 Ton125OEWT-PA26-LEM | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7898 | KL-20220217-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2022-02-17 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen Road and to F131 in Hensen East / Loader clearing pull off on Hensen Road and F126 Access | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7898KL-20220217-3Pickup 1/2 Ton22550 | KABI LAKE FOREST PRODUCTS LTD7898KL-20220217-3Pickup 1/2 Ton22550OEWT-PA26-LEM | [5 empty] | 1 | 550 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7901 | KL-20220218-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 12.5 | HR | 19 | 0 |  |  | 312.5 | 40.625 | 353.125 | 2022-02-18 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader finishing clearing pull off, widening corners and sanding from Km 5 to Km 17/ Supervisor doing pickup shuffle | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7901KL-20220218-2Pickup 1/2 Ton12.5312.5 | KABI LAKE FOREST PRODUCTS LTD7901KL-20220218-2Pickup 1/2 Ton12.5312.5OEWT-PA26-LEM | [5 empty] | 1 | 312.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7906 | KL-20220219-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2022-02-19 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17km on Hensen Road & start benching snow banks | 11 | F118-F127 | Henson | 0 | 44617 |  | 61 | 44617 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7906KL-20220219-2Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD7906KL-20220219-2Pickup 1/2 Ton10250OEWT-PA26-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7910 | KL-20220220-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2022-02-20 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17Km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44617 |  | 61 | 44617 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7910KL-20220220-2Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD7910KL-20220220-2Pickup 1/2 Ton6150OEWT-PA26-LEM | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7912 | KL-20220221-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2022-02-21 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal & benching snow banks from Hwy 17 to 17Km on Hensen Road. Loader starting clearing of pull offs on Hensen Road & widening corners | 11 | F118-F127 | Henson | 0 | 44617 |  | 61 | 44617 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7912KL-20220221-2Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7912KL-20220221-2Pickup 1/2 Ton11275OEWT-PA26-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7914 | KL-20220222-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2022-02-22 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen Road /Grader 2 benching snow banks from Km 17 to Hwy 17 | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7914KL-20220222-2Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD7914KL-20220222-2Pickup 1/2 Ton9225OEWT-PA26-LEM | [5 empty] | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7917 | KL-20220223-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 15 | HR | 19 | 0 |  |  | 375 | 48.75 | 423.75 | 2022-02-23 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17km on Hensen Road. Loader widening corners & assisting float trucks | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7917KL-20220223-2Pickup 1/2 Ton15375 | KABI LAKE FOREST PRODUCTS LTD7917KL-20220223-2Pickup 1/2 Ton15375OEWT-PA26-LEM | [5 empty] | 1 | 375 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7921 | KL-20220224-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2022-02-24 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal, benching snowbanks and widening road from Hwy 17 to 17km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7921KL-20220224-2Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD7921KL-20220224-2Pickup 1/2 Ton10250OEWT-PA26-LEM | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7921 | KL-20220224-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2022-02-24 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal, benching snowbanks and widening road from Hwy 17 to 17km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7921KL-20220224-2Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD7921KL-20220224-2Pickup 1/2 Ton250OEWT-PA26-LEM | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7926 | KL-20220225-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2022-02-25 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying sections from Hwy 17 to 17km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7926KL-20220225-2Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD7926KL-20220225-2Pickup 1/2 Ton4100OEWT-PA26-LEM | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7939 | KL-20220227-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 4.5 | HR | 19 | 0 |  |  | 112.5 | 14.625 | 127.125 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader working on snow removal from Hwy 17 to 17Km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7939KL-20220227-2Pickup 1/2 Ton4.5112.5 | KABI LAKE FOREST PRODUCTS LTD7939KL-20220227-2Pickup 1/2 Ton4.5112.5 | [5 empty] | 1 | 112.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7941 | KL-20220227-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 4 | HR | 19 | 0 |  |  | 100 | 13 | 113 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader Starting Snow Removal From F168 To F165. Access/Winter Access Maintenance (Cost Code: 67776007556.591100.57010107) | 11 | F165 - F169 | Magpie Hills | 0 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7941KL-20220227-4Pickup 1/2 Ton4100 | KABI LAKE FOREST PRODUCTS LTD7941KL-20220227-4Pickup 1/2 Ton4100 | [5 empty] | 1 | 100 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7945 | KL-20220228-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 3.5 | HR | 19 | 0 |  |  | 87.5 | 11.375 | 98.875 | 2022-02-28 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader Scarifying Sections From Hwy 17 To 17 Km On Hensen Road | 11 | F118-F127 | Henson | 0 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7945KL-20220228-2Pickup 1/2 Ton3.587.5 | KABI LAKE FOREST PRODUCTS LTD7945KL-20220228-2Pickup 1/2 Ton3.587.5 | [5 empty] | 1 | 87.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7946 | KL-20220228-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2022-02-28 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loader Finishing Snow Removal From F165 To F169. Access/Winter Access Maintenance (Cost Code: 67776007556.591100.57010107) | 11 | F165 - F169 | Magpie Hills | 1 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7946KL-20220228-3Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD7946KL-20220228-3Pickup 1/2 Ton6150 | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7948 | KL-20220228-5 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2022-02-28 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loaders Working On Snow Removal From F184 To F181 & Starting @ F175 To F171. Access/Winter Access Maintenance (Cost Code: 67776007556.591100.57010107) | 11 | F170 - F211 | High Falls | 1 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7948KL-20220228-5Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD7948KL-20220228-5Pickup 1/2 Ton5125 | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7948 | KL-20220228-5 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 8.5 | HR | 19 | 0 |  |  | 212.5 | 27.625 | 240.125 | 2022-02-28 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loaders Working On Snow Removal From F184 To F181 & Starting @ F175 To F171. Access/Winter Access Maintenance (Cost Code: 67776007556.591100.57010107) | 11 | F170 - F211 | High Falls | 1 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7948KL-20220228-5Pickup 1/2 Ton8.5212.5 | KABI LAKE FOREST PRODUCTS LTD7948KL-20220228-5Pickup 1/2 Ton8.5212.5 | [5 empty] | 1 | 212.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7956 | KL-20220301-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-03-01 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loaders finishing on snow removal from F175 to F171 Cost Code: 67776007556.591100.57010107 ) | 11 | F170 - F211 | High Falls | 1 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7956KL-20220301-3Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7956KL-20220301-3Pickup 1/2 Ton12300 | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7958 | KL-20220302-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2022-03-02 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader working on snow removal from Hwy to Km 17 on Hensen Road | 11 | F118-F127 | Henson | 0 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7958KL-20220302-3Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD7958KL-20220302-3Pickup 1/2 Ton250 | [5 empty] | 1 | 50 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7959 | KL-20220302-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 3.5 | HR | 19 | 0 |  |  | 87.5 | 11.375 | 98.875 | 2022-03-02 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Float Cat 950M loader from High Falls Road to F170/ Traffic control required ( Cost Code: 67776007556.591100.57010107 ) | 11 | F170-F211 | High Falls | 1 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7959KL-20220302-4Pickup 1/2 Ton3.587.5 | KABI LAKE FOREST PRODUCTS LTD7959KL-20220302-4Pickup 1/2 Ton3.587.5 | [5 empty] | 1 | 87.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7960 | KL-20220302-5 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2022-03-02 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loaders finishing on snow removal and turn around @ F170 / Traffic control required for clearing of Entrance ( Cost Code: 67776007556.591100.57010107 ) | 11 | F170 - F211 | High Falls | 1 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7960KL-20220302-5Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD7960KL-20220302-5Pickup 1/2 Ton10250 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7962 | KL-20220302-7 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 7.5 | HR | 19 | 0 |  |  | 187.5 | 24.375 | 211.875 | 2022-03-02 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader working on snow removal from Anjigami to F228 | 11 | F212-F235 | Anjigame | 0 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7962KL-20220302-7Pickup 1/2 Ton7.5187.5 | KABI LAKE FOREST PRODUCTS LTD7962KL-20220302-7Pickup 1/2 Ton7.5187.5 | [5 empty] | 1 | 187.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7972 | KL-20220307-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 10.5 | HR | 19 | 0 |  |  | 262.5 | 34.125 | 296.625 | 2022-03-07 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader Working On Snow Removal From Anjigami Road To F228 & F235 To F233 | 11 | F212-F235 | Anjigame | 0 | 44634 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7972KL-20220307-2Pickup 1/2 Ton10.5262.5 | KABI LAKE FOREST PRODUCTS LTD7972KL-20220307-2Pickup 1/2 Ton10.5262.5 | [5 empty] | 1 | 262.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7974 | KL-20220307-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2022-03-07 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loader Working On Snow Removal From High Falls Road To F175, F174, F172 & F171 ( Cost Code: 67776007556.591100.57010107 ) | 11 | F170-F211 | High Falls | 1 | 44634 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7974KL-20220307-4Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7974KL-20220307-4Pickup 1/2 Ton11275 | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7786 | KL-20220119-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-01-19 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working on snow removal from F231 to F235 & clearing pads. | 11 | F212-F235 | Anjigame | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7786KL-20220119-2Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7786KL-20220119-2Pickup 1/2 Ton12300OEWT-PA25-Lem | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7787 | KL-20220119-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 21 | HR | 19 | 0 |  |  | 525 | 68.25 | 593.25 | 2022-01-19 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road, clearing pull offs & spur roads from Hensen to F131. grader working on snow removal on Hensen to 17Km and Hensen East to F131. | 11 | F118-F127 | Henson | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7787KL-20220119-3Pickup 1/2 Ton21525 | KABI LAKE FOREST PRODUCTS LTD7787KL-20220119-3Pickup 1/2 Ton21525OEWT-PA25-Lem | [5 empty] | 1 | 525 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7789 | KL-20220120-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2022-01-20 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader finishing snow removal from F231 to F235 & clearing pads. Start snow removal from F231 to F226. | 11 | F212-F235 | Anjigame | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7789KL-20220120-2Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7789KL-20220120-2Pickup 1/2 Ton9.5237.5OEWT-PA25-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7791 | KL-20220120-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2022-01-20 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on Hensen road to F121, hensen East to F131 & start benching snow banks from 17Km to 13Km. | 11 | F118-F127 | Henson | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7791KL-20220120-4Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7791KL-20220120-4Pickup 1/2 Ton11275OEWT-PA25-Lem | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7792 | KL-20220120-5 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 10.5 | HR | 19 | 0 |  |  | 262.5 | 34.125 | 296.625 | 2022-01-20 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer tracking from 11 Km on High Falls road & Working on Snow Removal to F207. | 11 | F170 - F211 | High Falls | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7792KL-20220120-5Pickup 1/2 Ton10.5262.5 | KABI LAKE FOREST PRODUCTS LTD7792KL-20220120-5Pickup 1/2 Ton10.5262.5OEWT-PA25-Lem | [5 empty] | 1 | 262.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7794 | KL-20220121-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 11.5 | HR | 19 | 0 |  |  | 287.5 | 37.375 | 324.875 | 2022-01-21 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader finishing benching and pushing snow banks from Km .5 to Km 13 | 11 | F118 - F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7794KL-20220121-2Pickup 1/2 Ton11.5287.5 | KABI LAKE FOREST PRODUCTS LTD7794KL-20220121-2Pickup 1/2 Ton11.5287.5OEWT-PA25-Lem | [5 empty] | 1 | 287.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7796 | KL-20220121-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2022-01-21 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader snow removal from F231 to F226 and F232 to F235 | 11 | F212-F235 | Anjigame | 0 | 44589 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7796KL-20220121-4Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7796KL-20220121-4Pickup 1/2 Ton11275OEWT-PA25-Lem | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7797 | KL-20220122-1 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2022-01-22 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on Hensen Road to Km 17 and Hensen East to F132(plowed Hensen Road 3 times due to winter storm) /Loader clearing pulloffs and widening corners to Km 12 | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7797KL-20220122-1Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD7797KL-20220122-1Pickup 1/2 Ton10250OEWT-PA25-Lem | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7797 | KL-20220122-1 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 12.5 | HR | 19 | 0 |  |  | 312.5 | 40.625 | 353.125 | 2022-01-22 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on Hensen Road to Km 17 and Hensen East to F132(plowed Hensen Road 3 times due to winter storm) /Loader clearing pulloffs and widening corners to Km 12 | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7797KL-20220122-1Pickup 1/2 Ton12.5312.5 | KABI LAKE FOREST PRODUCTS LTD7797KL-20220122-1Pickup 1/2 Ton12.5312.5OEWT-PA25-Lem | [5 empty] | 1 | 312.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7798 | KL-20220122-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2022-01-22 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer tracking from km 11 on High Falls Road and working on snow removal from High Falls Road to F207/track back to Km 11 | 11 | F170-F211 | High Falls | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7798KL-20220122-2Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7798KL-20220122-2Pickup 1/2 Ton9.5237.5OEWT-PA25-Lem | [5 empty] | 1 | 237.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7800 | KL-20220123-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 8.5 | HR | 19 | 0 |  |  | 212.5 | 27.625 | 240.125 | 2022-01-23 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on Hensen Road to F121 and Hensen East to F132/Loader clearing pulloffs and widening corners | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7800KL-20220123-2Pickup 1/2 Ton8.5212.5 | KABI LAKE FOREST PRODUCTS LTD7800KL-20220123-2Pickup 1/2 Ton8.5212.5OEWT-PA25-Lem | [5 empty] | 1 | 212.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7800 | KL-20220123-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2022-01-23 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on Hensen Road to F121 and Hensen East to F132/Loader clearing pulloffs and widening corners | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7800KL-20220123-2Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD7800KL-20220123-2Pickup 1/2 Ton13325OEWT-PA25-Lem | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7802 | KL-20220124-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 17 | HR | 19 | 0 |  |  | 425 | 55.25 | 480.25 | 2022-01-24 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working benching snowbanks and widening road from Hwy 17 to Km 10/ Loader continuing clearing pulloffs and widening corners | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7802KL-20220124-2Pickup 1/2 Ton17425 | KABI LAKE FOREST PRODUCTS LTD7802KL-20220124-2Pickup 1/2 Ton17425OEWT-PA25-Lem | [5 empty] | 1 | 425 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7804 | KL-20220124-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 5.5 | HR | 19 | 0 |  |  | 137.5 | 17.875 | 155.375 | 2022-01-24 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from Anjigami Road to F231 and clearing pads in support of stringing crew | 11 |  | Anjigame | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7804KL-20220124-4Pickup 1/2 Ton5.5137.5 | KABI LAKE FOREST PRODUCTS LTD7804KL-20220124-4Pickup 1/2 Ton5.5137.5OEWT-PA25-Lem | [5 empty] | 1 | 137.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7807 | KL-20220125-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 11.5 | HR | 19 | 0 |  |  | 287.5 | 37.375 | 324.875 | 2022-01-25 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Finishing benching snowbanks, scarifying and widening road from Hwy 17 to Km 10 | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7807KL-20220125-3Pickup 1/2 Ton11.5287.5 | KABI LAKE FOREST PRODUCTS LTD7807KL-20220125-3Pickup 1/2 Ton11.5287.5OEWT-PA25-Lem | [5 empty] | 1 | 287.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7808 | KL-20220125-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 4.5 | HR | 19 | 0 |  |  | 112.5 | 14.625 | 127.125 | 2022-01-25 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal and Heli Pads in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7808KL-20220125-4Pickup 1/2 Ton4.5112.5 | KABI LAKE FOREST PRODUCTS LTD7808KL-20220125-4Pickup 1/2 Ton4.5112.5OEWT-PA25-Lem | [5 empty] | 1 | 112.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7810 | KL-20220126-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 6.5 | HR | 19 | 0 |  |  | 162.5 | 21.125 | 183.625 | 2022-01-26 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying road from Hwy 17 to Km 10 | 11 | F118-F127 | Henson | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7810KL-20220126-2Pickup 1/2 Ton6.5162.5 | KABI LAKE FOREST PRODUCTS LTD7810KL-20220126-2Pickup 1/2 Ton6.5162.5OEWT-PA26-LEM | [5 empty] | 1 | 162.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7811 | KL-20220126-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2022-01-26 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader continuing working snow removal and Heli Pads in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7811KL-20220126-3Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7811KL-20220126-3Pickup 1/2 Ton11275OEWT-PA26-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7812 | KL-20220128-1 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-01-28 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 and Hensen east to F131 | 11 | F118-F127 | Hensen | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7812KL-20220128-1Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7812KL-20220128-1Pickup 1/2 Ton12300OEWT-PA26-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7813 | KL-20220128-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 11.5 | HR | 19 | 0 |  |  | 287.5 | 37.375 | 324.875 | 2022-01-28 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from F235 to F230 and Pads in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7813KL-20220128-2Pickup 1/2 Ton11.5287.5 | KABI LAKE FOREST PRODUCTS LTD7813KL-20220128-2Pickup 1/2 Ton11.5287.5OEWT-PA26-LEM | [5 empty] | 1 | 287.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7815 | KL-20220129-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2022-01-29 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal and scarifying from Hwy 17 to Km 17 on Hensen road and Hensen east to F131 | 11 | F118-F127 | Henson | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7815KL-20220129-2Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD7815KL-20220129-2Pickup 1/2 Ton13325OEWT-PA26-LEM | [5 empty] | 1 | 325 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7817 | KL-20220130-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 7.5 | HR | 19 | 0 |  |  | 187.5 | 24.375 | 211.875 | 2022-01-30 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal and scarifying from Hwy 17 to Km 17 on Hensen road | 11 | F118-F127 | Henson | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7817KL-20220130-2Pickup 1/2 Ton7.5187.5 | KABI LAKE FOREST PRODUCTS LTD7817KL-20220130-2Pickup 1/2 Ton7.5187.5OEWT-PA26-LEM | [5 empty] | 1 | 187.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7820 | KL-20220131-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2022-01-31 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader started benching snowbanks and scarifying from Hwy 17 to Km 6 on Hensen road | 11 | F118-F127 | Henson | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7820KL-20220131-3Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD7820KL-20220131-3Pickup 1/2 Ton8200OEWT-PA26-LEM | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7821 | KL-20220131-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2022-01-31 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from F235 to F230 and Pads in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7821KL-20220131-4Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7821KL-20220131-4Pickup 1/2 Ton11275OEWT-PA26-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7824 | KL-20220201-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 10.5 | HR | 19 | 0 |  |  | 262.5 | 34.125 | 296.625 | 2022-02-01 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader benching snow banks, widening road, scarifying from 6km to 10km & clearing snow drifts @ 14Km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7824KL-20220201-3Pickup 1/2 Ton10.5262.5 | KABI LAKE FOREST PRODUCTS LTD7824KL-20220201-3Pickup 1/2 Ton10.5262.5OEWT-PA26-LEM | [5 empty] | 1 | 262.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7825 | KL-20220201-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2022-02-01 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from F235 to F230 and Pads in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7825KL-20220201-4Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD7825KL-20220201-4Pickup 1/2 Ton8200OEWT-PA26-LEM | [5 empty] | 1 | 200 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7827 | KL-20220202-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-02-02 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader finishing benching snow banks, widening road, scarifying from 10km to 17km & clearing snow drifts @ 17Km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7827KL-20220202-2Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7827KL-20220202-2Pickup 1/2 Ton12300OEWT-PA26-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7829 | KL-20220203-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2022-02-03 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to 17km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7829KL-20220203-2Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD7829KL-20220203-2Pickup 1/2 Ton5125OEWT-PA26-LEM | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7831 | KL-20220202-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2022-02-02 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7831KL-20220202-3Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7831KL-20220202-3Pickup 1/2 Ton11275OEWT-PA26-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7834 | KL-20220204-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-02-04 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader widening road and scarifying from Hwy 17 to 17km on Hensen Road and Hensen East to F-131. | 11 | F118-F127 | Henson | 0 | 44603 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7834KL-20220204-3Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7834KL-20220204-3Pickup 1/2 Ton12300OEWT-PA26-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7835 | KL-20220204-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2022-02-04 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7835KL-20220204-4Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7835KL-20220204-4Pickup 1/2 Ton11275OEWT-PA26-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7838 | KL-20220205-3 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2022-02-05 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader benching snowbanks and scarifying from Hwy 17 to 17km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44603 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7838KL-20220205-3Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7838KL-20220205-3Pickup 1/2 Ton12300OEWT-PA26-LEM | [5 empty] | 1 | 300 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7842 | KL-20220206-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2022-02-06 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17Km on Hensen Road (cleared road 2 times due to heavy snow. | 11 | F118-F127 | Henson | 0 | 44603 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7842KL-20220206-2Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7842KL-20220206-2Pickup 1/2 Ton11275OEWT-PA26-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7845 | KL-20220207-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44604 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7845KL-20220207-2Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD7845KL-20220207-2Pickup 1/2 Ton5125OEWT-PA26-LEM | [5 empty] | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7853 | KL-20220208-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 17 | HR | 19 | 0 |  |  | 425 | 55.25 | 480.25 | 2022-02-08 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to 17Km on Hensen Road & snow removal to F131 on Hensen East. Loader clearing pull offs & widening corners to 7km. Supervisor doing pickup shuffle. | 11 | F118 - F127 | Henson | 0 | 44604 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7853KL-20220208-2Pickup 1/2 Ton17425 | KABI LAKE FOREST PRODUCTS LTD7853KL-20220208-2Pickup 1/2 Ton17425OEWT-PA26-LEM | [5 empty] | 1 | 425 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7858 | KL-20220209-1 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2022-02-09 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer finishing snow removal from F021 to F032 and clear pads @ F032 | 10 | F009-F065 | Paint Lake | 0 | 44604 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7858KL-20220209-1Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7858KL-20220209-1Pickup 1/2 Ton11275OEWT-PA26-LEM | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7862 | KL-20220209-5 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 16 | HR | 19 | 0 |  |  | 400 | 52 | 452 | 2022-02-09 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to Km 17 on Hensen road /Loader clearing pull offs and widening corners and sanding to Km 12 /Supervisor doing pickup shuffle | 11 | F118-F127 | Henson | 0 | 44604 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7862KL-20220209-5Pickup 1/2 Ton16400 | KABI LAKE FOREST PRODUCTS LTD7862KL-20220209-5Pickup 1/2 Ton16400OEWT-PA26-LEM | [5 empty] | 1 | 400 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7867 | KL-20220210-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 17.5 | HR | 19 | 0 |  |  | 437.5 | 56.875 | 494.375 | 2022-02-10 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to Km 17 on Hensen road and benching snowbanks from Km .5 to Km 5/Loader clearing pull offs and widening corners and sanding from Km 5 to Km 17 | 11 | F118-F127 | Henson | 0 | 44605 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7867KL-20220210-4Pickup 1/2 Ton17.5437.5 | KABI LAKE FOREST PRODUCTS LTD7867KL-20220210-4Pickup 1/2 Ton17.5437.5OEWT-PA26-LEM | [5 empty] | 1 | 437.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7870 | KL-20220211-2 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 14.5 | HR | 19 | 0 |  |  | 362.5 | 47.125 | 409.625 | 2022-02-11 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen road /Loader clearing pull offs and sanding from Km 10 to Km 17 | 11 | F118-F127 | Henson | 0 | 44605 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7870KL-20220211-2Pickup 1/2 Ton14.5362.5 | KABI LAKE FOREST PRODUCTS LTD7870KL-20220211-2Pickup 1/2 Ton14.5362.5OEWT-PA26-LEM | [5 empty] | 1 | 362.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7876 | KL-20220212-4 | 53511111 | Access | 0 | Pickup 1/2 Ton | 25 | 12.5 | HR | 19 | 0 |  |  | 312.5 | 40.625 | 353.125 | 2022-02-12 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen road and Hensen Road East to F123/Loader clearing pull offs and sanding from Km 10 to Km 4 | 11 | F118-F127 | Henson | 0 | 44605 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7876KL-20220212-4Pickup 1/2 Ton12.5312.5 | KABI LAKE FOREST PRODUCTS LTD7876KL-20220212-4Pickup 1/2 Ton12.5312.5OEWT-PA26-LEM | [5 empty] | 1 | 312.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7034 | KL-20210616-1 | 53511112 | Access | 0 | Pickup 1/2 Ton | 25 | 6 | HR | 19 | 0 |  |  | 150 | 19.5 | 169.5 | 2021-06-16 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator working on shaping & drainage to F-127 / Stockpiling existing material fro covering of corduroy sections. | 11 | F119-F134 | Hensen Road | 0 | 44368 |  | 50 | 44369 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7034KL-20210616-1Pickup 1/2 Ton6150 | KABI LAKE FOREST PRODUCTS LTD7034KL-20210616-1Pickup 1/2 Ton6150OEWT-PA18-Lem | [5 empty] | 1 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7044 | KL-20210620-1 | 53511112 | Access | 0 | Pickup 1/2 Ton | 25 | 4.5 | HR | 19 | 0 |  |  | 112.5 | 14.625 | 127.125 | 2021-06-20 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator repairing washout on hill at WC 12570.00 and access to F171 for pickup access. | 11 | F171-F176 | High Falls Road 1 | 0 | 44369 |  | 50 | 44369 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7044KL-20210620-1Pickup 1/2 Ton4.5112.5 | KABI LAKE FOREST PRODUCTS LTD7044KL-20210620-1Pickup 1/2 Ton4.5112.5OEWT-PA18-Lem | [5 empty] | 1 | 112.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7058 | KL-20210621-1 | 53511112 | Access | 0 | Pickup 1/2 Ton | 25 | 7 | HR | 19 | 0 |  |  | 175 | 22.75 | 197.75 | 2021-06-21 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Levelling ruts and shaping access from F-171 to F-177 | 11 | F171-F176 | High Falls Road - 1 | 0 | 44370 |  | 50 | 44371 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7058KL-20210621-1Pickup 1/2 Ton7175 | KABI LAKE FOREST PRODUCTS LTD7058KL-20210621-1Pickup 1/2 Ton7175OEWT-PA18-Lem | [5 empty] | 1 | 175 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7601 | KL-20211029-2 | 53511112 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-10-29 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continue working on drainage, tracking material and shaping road @ F126 / F125 | 11 | F118 - F134 | Henson | 0 | 44501 |  | 61 | 44503 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7601KL-20211029-2Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7601KL-20211029-2Pickup 1/2 Ton11275OEWT-PA23-Lem | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7484 | KL-20211023-2 | 53511112 | Access | 0 | Pickup 1/2 Ton | 25 | 21.5 | HR | 19 | 0 |  |  | 537.5 | 69.875 | 607.375 | 2021-10-23 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul trees for fill and start capping with existing material @ F123 to F124 access realignment | 11 | F119-F134 | Hensen Road | 0 | 44495 |  | 61 | 44496 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7484KL-20211023-2Pickup 1/2 Ton21.5537.5 | KABI LAKE FOREST PRODUCTS LTD7484KL-20211023-2Pickup 1/2 Ton21.5537.5OEWT-PA22-Lem | [5 empty] | 1 | 537.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7486 | KL-20211024-2 | 53511112 | Access | 0 | Pickup 1/2 Ton | 25 | 31 | HR | 19 | 0 |  |  | 775 | 100.75 | 875.75 | 2021-10-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from F123 access to F124 access realignment capping and start raising road and 1.5 km for crane access | 11 | F119-F134 | Hensen Road | 0 | 44495 |  | 61 | 44497 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7486KL-20211024-2Pickup 1/2 Ton31775 | KABI LAKE FOREST PRODUCTS LTD7486KL-20211024-2Pickup 1/2 Ton31775OEWT-PA23-Lem | [5 empty] | 1 | 775 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7489 | KL-20211025-2 | 53511112 | Access | 0 | Pickup 1/2 Ton | 25 | 32.5 | HR | 19 | 0 |  |  | 812.5 | 105.625 | 918.125 | 2021-10-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to 1.5 km for raising of road | 11 | F119-F134 | Hensen Road | 0 | 44496 |  | 61 | 44497 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7489KL-20211025-2Pickup 1/2 Ton32.5812.5 | KABI LAKE FOREST PRODUCTS LTD7489KL-20211025-2Pickup 1/2 Ton32.5812.5OEWT-PA23-Lem | [5 empty] | 1 | 812.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7497 | KL-20211027-2 | 53511112 | Access | 0 | Pickup 1/2 Ton | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul existing material from Km 17 on Hensen Road to F124 for capping/excavator speading existing material and shaping road from Hensen Road to F123 | 11 | F118-F127 | Hensen | 0 | 44501 |  | 61 | 44502 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7497KL-20211027-2Pickup 1/2 Ton22550 | KABI LAKE FOREST PRODUCTS LTD7497KL-20211027-2Pickup 1/2 Ton22550OEWT-PA23-Lem | [5 empty] | 1 | 550 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7503 | KL-20211028-2 | 53511112 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-10-28 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking from F123 to F127 working on drainage and shaping road to F126 | 11 | F118-F127 | Hensen Road | 0 | 44501 |  | 61 | 44502 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7503KL-20211028-2Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7503KL-20211028-2Pickup 1/2 Ton11275OEWT-PA23-Lem | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7511 | KL-20211030-2 | 53511112 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-10-30 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing working on drainage, shaping road and sloping excavation @ Km .5 on Hensen Road East | 11 | F119-F127 | Hensen Road | 0 | 44502 |  | 61 | 44503 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7511KL-20211030-2Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7511KL-20211030-2Pickup 1/2 Ton11275OEWT-PA23-Lem | [5 empty] | 1 | 275 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7589 | KL-20211123-4 | 53511112 | Access | 0 | Pickup 1/2 Ton | 25 | 3 | HR | 19 | 0 |  |  | 75 | 9.75 | 84.75 | 2021-11-23 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader starting to scrape and sand road to Km 14 for stringing crews | 11 | F212-F235 | Ainjigame | 0 | 44529 |  | 61 | 44530 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7589KL-20211123-4Pickup 1/2 Ton375 | KABI LAKE FOREST PRODUCTS LTD7589KL-20211123-4Pickup 1/2 Ton375OEWT-PA23-Lem | [5 empty] | 1 | 75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7589 | KL-20211123-4 | 53511112 | Access | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2021-11-23 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader starting to scrape and sand road to Km 14 for stringing crews | 11 | F212-F235 | Ainjigame | 0 | 44529 |  | 61 | 44530 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7589KL-20211123-4Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD7589KL-20211123-4Pickup 1/2 Ton125OEWT-PA23-Lem | [5 empty] | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6661 | KL-20210406-5-R1 | 53541101 | Reclamation | 0 | Pickup 1/2 Ton | 25 | 17 | HR | 19 | 0 |  |  | 425 | 55.25 | 480.25 | 2021-04-06 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F138 to F141. Two hours of equipment/live out and pick up time removed from each excavator/operator from approved field ticket as per Valard direction. Those charges now listed on LEM KL-20210406-5-S1. | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | 44328 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6661KL-20210406-5-R1Pickup 1/2 Ton17425 | KABI LAKE FOREST PRODUCTS LTD6661KL-20210406-5-R1Pickup 1/2 Ton17425OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 425 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6662 | KL-20210406-6 | 53541101 | Reclamation | 0 | Pickup 1/2 Ton | 25 | 10.5 | HR | 19 | 0 |  |  | 262.5 | 34.125 | 296.625 | 2021-04-06 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F150 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44292 |  | 56 | 44305 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6662KL-20210406-6Pickup 1/2 Ton10.5262.5 | KABI LAKE FOREST PRODUCTS LTD6662KL-20210406-6Pickup 1/2 Ton10.5262.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 262.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6674 | KL-20210407-6 | 53541101 | Reclamation | 0 | Pickup 1/2 Ton | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-04-07 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 1 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  | 29 | Approved | STR & PAD SITE RECLAIM | 8008 | Start Reclamation @ F151/Sloping crane pad amd assembley pad (Revised) | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44305 |  | 56 | 44309 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6674KL-20210407-6Pickup 1/2 Ton9225 | KABI LAKE FOREST PRODUCTS LTD6674KL-20210407-6Pickup 1/2 Ton9225OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6677 | KL-20210408-2 | 53541101 | Reclamation | 0 | Pickup 1/2 Ton | 25 | 10.5 | HR | 19 | 0 |  |  | 262.5 | 34.125 | 296.625 | 2021-04-08 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 1 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  | 29 | Approved | STR & PAD SITE RECLAIM | 8008 | Continue Reclamation @ F151/ sloping crane pads and assembly pad | 11 | F150-F151 | Michipicoten Harbour Road -1 | 1 | 44305 |  | 56 | 44307 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6677KL-20210408-2Pickup 1/2 Ton10.5262.5 | KABI LAKE FOREST PRODUCTS LTD6677KL-20210408-2Pickup 1/2 Ton10.5262.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 262.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6687 | KL-20210409-7 | 53541101 | Reclamation | 0 | Pickup 1/2 Ton | 25 | 5 | HR | 19 | 0 |  |  | 125 | 16.25 | 141.25 | 2021-04-09 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 1 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  | 29 | Approved | STR & PAD SITE RECLAIM | 8008 | Continue Reclamation @F151/ Sloping crane pad and assembley pad | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44306 |  | 56 | 44309 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6687KL-20210409-7Pickup 1/2 Ton5125 | KABI LAKE FOREST PRODUCTS LTD6687KL-20210409-7Pickup 1/2 Ton5125OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6687 | KL-20210409-7 | 53541101 | Reclamation | 0 | Pickup 1/2 Ton | 25 | 0.5 | HR | 19 | 0 |  |  | 12.5 | 1.625 | 14.125 | 2021-04-09 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 1 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  | 29 | Approved | STR & PAD SITE RECLAIM | 8008 | Continue Reclamation @F151/ Sloping crane pad and assembley pad | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44306 |  | 56 | 44309 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6687KL-20210409-7Pickup 1/2 Ton0.512.5 | KABI LAKE FOREST PRODUCTS LTD6687KL-20210409-7Pickup 1/2 Ton0.512.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 12.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6704 | KL-20210412-6 | 53541101 | Reclamation | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-04-12 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @F151 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44308 |  | 56 | 44309 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6704KL-20210412-6Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD6704KL-20210412-6Pickup 1/2 Ton10250OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6757 | KL-20210414-6 | 53541101 | Reclamation | 0 | Pickup 1/2 Ton | 25 | 10 | HR | 19 | 0 |  |  | 250 | 32.5 | 282.5 | 2021-04-14 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue reclamation @ F151 and F150. | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44309 |  | 56 | 44312 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6757KL-20210414-6Pickup 1/2 Ton10250 | KABI LAKE FOREST PRODUCTS LTD6757KL-20210414-6Pickup 1/2 Ton10250OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6610 | KL-20210402-2-R1 | 53541101 | Reclamation | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2021-04-02 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track out to Km 1 on Hensen East for refueling and back to F132/ Continue reclamation @ F132/ ATV used due to no pickup access. Excavator time reduced from signed ticket for tracking as per Valard direction. Remaining excavator time will be submitted on KL-20210402-2-S1 | 11 | F119-F134 | Hensen Road | 0 | 44298 |  | 56 | 44329 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6610KL-20210402-2-R1Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD6610KL-20210402-2-R1Pickup 1/2 Ton125OEWT-PA17-LEM |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6610 | KL-20210402-2-R1 | 53541101 | Reclamation | 0 | Pickup 1/2 Ton | 25 | 7.5 | HR | 19 | 0 |  |  | 187.5 | 24.375 | 211.875 | 2021-04-02 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track out to Km 1 on Hensen East for refueling and back to F132/ Continue reclamation @ F132/ ATV used due to no pickup access. Excavator time reduced from signed ticket for tracking as per Valard direction. Remaining excavator time will be submitted on KL-20210402-2-S1 | 11 | F119-F134 | Hensen Road | 0 | 44298 |  | 56 | 44329 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6610KL-20210402-2-R1Pickup 1/2 Ton7.5187.5 | KABI LAKE FOREST PRODUCTS LTD6610KL-20210402-2-R1Pickup 1/2 Ton7.5187.5OEWT-PA17-LEM |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 187.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6624 | KL-20210405-4-R1 | 53541101 | Reclamation | 0 | Pickup 1/2 Ton | 25 | 4.5 | HR | 19 | 0 |  |  | 112.5 | 14.625 | 127.125 | 2021-04-05 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F137 to F138/ Cat 336 excavator tracking in from km 3 on Dore Road and starting @ F140. Chapman Reclamation of Dore lake Road East - CE-195. Excavator/pickup hours reduced for tracking time from signed ticket per Valard direction. Tracking time will be submitted on LEM KL-20210405-4-S1 | 11 | F-135 to F-149 | Dore lake Road | 0 | 44298 |  | 56 | 44329 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6624KL-20210405-4-R1Pickup 1/2 Ton4.5112.5 | KABI LAKE FOREST PRODUCTS LTD6624KL-20210405-4-R1Pickup 1/2 Ton4.5112.5OEWT-PA17-LEM |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 112.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6624 | KL-20210405-4-R1 | 53541101 | Reclamation | 0 | Pickup 1/2 Ton | 25 | 1 | HR | 19 | 0 |  |  | 25 | 3.25 | 28.25 | 2021-04-05 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F137 to F138/ Cat 336 excavator tracking in from km 3 on Dore Road and starting @ F140. Chapman Reclamation of Dore lake Road East - CE-195. Excavator/pickup hours reduced for tracking time from signed ticket per Valard direction. Tracking time will be submitted on LEM KL-20210405-4-S1 | 11 | F-135 to F-149 | Dore lake Road | 0 | 44298 |  | 56 | 44329 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6624KL-20210405-4-R1Pickup 1/2 Ton125 | KABI LAKE FOREST PRODUCTS LTD6624KL-20210405-4-R1Pickup 1/2 Ton125OEWT-PA17-LEM |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6840 | KL-20210331-5 | 53541101 | Reclamation | 0 | Pickup 1/2 Ton | 25 | 8.5 | HR | 19 | 0 |  |  | 212.5 | 27.625 | 240.125 | 2021-03-31 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track to F133 from Km 17 on Hensen and start reclaimation @ F133/F132. ATV used for crew due to no pickup access | 11 | F119-F134 | Hensen Road | 0 | 44326 |  | 57 | 44327 | [5 empty] | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6840KL-20210331-5Pickup 1/2 Ton8.5212.5 | KABI LAKE FOREST PRODUCTS LTD6840KL-20210331-5Pickup 1/2 Ton8.5212.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 212.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5010 | KL-20201214-13 | 53551103 | Earthworks | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator hydaulic breaker and support excavator working onF123 access breaking outcrops on steep grades and straighten corners / operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44196 |  | 55 | 44209 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5010KL-20201214-13Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD5010KL-20201214-13Pickup 1/2 Ton12300OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5038 | KL-20201216-10 | 53551103 | Earthworks | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2020-12-16 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic Breaker and Support Excavator working on F127 access breaking outcrops on steep grades and straighten corners/ operator travel as per valard | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5038KL-20201216-10Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD5038KL-20201216-10Pickup 1/2 Ton12300OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5062 | KL-20201219-9 | 53551103 | Earthworks | 0 | Pickup 1/2 Ton | 25 | 10.5 | HR | 19 | 0 |  |  | 262.5 | 34.125 | 296.625 | 2020-12-19 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc with hydraulic breaker & support exc working on F127 Access breaking outcrops on steep grades. Straighten corners. Operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5062KL-20201219-9Pickup 1/2 Ton10.5262.5 | KABI LAKE FOREST PRODUCTS LTD5062KL-20201219-9Pickup 1/2 Ton10.5262.5OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 131.25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5217 | KL-20210104-6 | 53551103 | Earthworks | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2021-01-04 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker and support excavator working on F117 access breaking outcrops on steep grades and laying trees/ Operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5217KL-20210104-6Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD5217KL-20210104-6Pickup 1/2 Ton12300OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5230 | KL-20210105-9 | 53551103 | Earthworks | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2021-01-05 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker and support excavator working on F117 access breaking outcrops an steep grades/ Operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5230KL-20210105-9Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD5230KL-20210105-9Pickup 1/2 Ton12300OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5243 | KL-20210106-7 | 53551103 | Earthworks | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2021-01-06 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker working on F117 access breaking outcrops on steep grades/ operator travel as per valard | 11 | F119-F134 | Hensen Road | 0 | 44209 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5243KL-20210106-7Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD5243KL-20210106-7Pickup 1/2 Ton12300OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5267 | KL-20210107-16 | 53551103 | Earthworks | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2021-01-07 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker working on F117 Access breaking outcrops on steep grades/operator travel as per Valard. Skagen excavator supporting breaker. | 11 | F119-F134 | Hensen Road | 0 | 44209 |  | 15 | 44219 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5267KL-20210107-16Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD5267KL-20210107-16Pickup 1/2 Ton12300OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 150 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5280 | KL-20210109-3 | 53551103 | Earthworks | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2021-01-09 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc with hydraulic breaker breaking rock on Access @ 12070.01 WC | 11 | F119-F134 | Hensen Road | 0 | 44211 |  | 15 | 44219 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5280KL-20210109-3Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD5280KL-20210109-3Pickup 1/2 Ton250OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5628 | KL-20210126-12 | 53551103 | Earthworks | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-01-26 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | EXC with breaker & support excavator working on F111 Access breaking outcrops & laying trees. Operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44228 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5628KL-20210126-12Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD5628KL-20210126-12Pickup 1/2 Ton11275OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 137.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5648 | KL-20210127-16 | 53551103 | Earthworks | 0 | Pickup 1/2 Ton | 25 | 7.5 | HR | 19 | 0 |  |  | 187.5 | 24.375 | 211.875 | 2021-01-27 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc with hydraulic breaker & support excavator working on F111 Access breaking outcrops & laying trees/operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44228 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5648KL-20210127-16Pickup 1/2 Ton7.5187.5 | KABI LAKE FOREST PRODUCTS LTD5648KL-20210127-16Pickup 1/2 Ton7.5187.5OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 93.75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5656 | KL-20210128-8 | 53551103 | Earthworks | 0 | Pickup 1/2 Ton | 25 | 10.5 | HR | 19 | 0 |  |  | 262.5 | 34.125 | 296.625 | 2021-01-28 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc w breaker & support exc working on F111 Access breaking outcrops & laying trees/ operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5656KL-20210128-8Pickup 1/2 Ton10.5262.5 | KABI LAKE FOREST PRODUCTS LTD5656KL-20210128-8Pickup 1/2 Ton10.5262.5OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 131.25 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 879 | KL-20200106-1-R1 | 53510711 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6359 | 25.9527 | 225.5886 | 2020-01-10 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Beginning of work in WF7 towers D-142 to E-002. Opening up White Lake Rd., installing signage, and beginning clearing | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD879KL-20200106-1-R1L.O.A.0.81818199.6359 | KABI LAKE FOREST PRODUCTS LTD879KL-20200106-1-R1L.O.A.0.81818199.6359OEWT-PA1-LEM | [5 empty] | 1 | 199.6359 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 880 | KL-20200107-1-R2 | 53510711 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.818 | 28.8363 | 250.6543 | 2020-01-23 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | D7 Opened existing White Lake Road to the end. Kabi supervisor led internal meeting after the 1st day of work updating on the site conditions, planned processes and documentation needs. Buncher and skidder cleared estimated 0.8 Ha | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD880KL-20200107-1-R2L.O.A.0.90909221.818 | KABI LAKE FOREST PRODUCTS LTD880KL-20200107-1-R2L.O.A.0.90909221.818OEWT-PA1-LEM | [5 empty] | 1 | 221.818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 881 | KL-20200108-1-R1 | 53510711 | Access | 0 | L.O.A. | 244 | 0.22727 | Day |  | 0 |  |  | 55.4539 | 7.209 | 62.6629 | 2020-01-10 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Buncher brushing road line on White Lake Rd., Float truck mobilizing mats from Thunder Bay. Supervisor on-site checking roads & ROW clearing. Buncher and skidder cleared estimated 0.8 Ha | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD881KL-20200108-1-R1L.O.A.0.2272755.4539 | KABI LAKE FOREST PRODUCTS LTD881KL-20200108-1-R1L.O.A.0.2272755.4539OEWT-PA1-LEM | [5 empty] | 1 | 55.4539 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 890 | KL-20200115-2-R1 | 53510711 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-01-23 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clear snow from road and parking area | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD890KL-20200115-2-R1L.O.A.0.18181844.3636 | KABI LAKE FOREST PRODUCTS LTD890KL-20200115-2-R1L.O.A.0.18181844.3636OEWT-PA1-LEM | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 895 | KL-20200116-3-R1 | 53510711 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7272 | 11.5345 | 100.2617 | 2020-01-23 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Winter road upgrade to site access | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43889 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD895KL-20200116-3-R1L.O.A.0.36363688.7272 | KABI LAKE FOREST PRODUCTS LTD895KL-20200116-3-R1L.O.A.0.36363688.7272OEWT-PA1-LEM | [5 empty] | 1 | 88.7272 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 895 | KL-20200116-3-R1 | 53510711 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0908 | 17.3018 | 150.3926 | 2020-01-23 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Winter road upgrade to site access | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43889 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD895KL-20200116-3-R1L.O.A.0.545454133.0908 | KABI LAKE FOREST PRODUCTS LTD895KL-20200116-3-R1L.O.A.0.545454133.0908OEWT-PA1-LEM | [5 empty] | 1 | 133.0908 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 902 | KL-20200121-2 | 53510711 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-01-24 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Brushed 15M road ROW to D146. Dozer shaped & pushed snow back D-147 & D146 | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD902KL-20200121-2L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD902KL-20200121-2L.O.A.1244OEWT-PA1-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 902 | KL-20200121-2 | 53510711 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5454 | 8.6509 | 75.1963 | 2020-01-24 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Brushed 15M road ROW to D146. Dozer shaped & pushed snow back D-147 & D146 | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD902KL-20200121-2L.O.A.0.27272766.5454 | KABI LAKE FOREST PRODUCTS LTD902KL-20200121-2L.O.A.0.27272766.5454OEWT-PA1-LEM | [5 empty] | 1 | 66.5454 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 934 | KL-20200126-3 | 53510711 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-01-26 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open Road from Hwy 17 to 3km on White Lake Road | 7 | D-142 to E-002 | White Lake | 0 | 43856 |  | 17 | 43861 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD934KL-20200126-3L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD934KL-20200126-3L.O.A.0.4545455110.9091OEWT-PA2-LEM-R1 | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1058 | KL-20200212-3 | 53510711 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-02-12 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Winter access - snow removal from D-142 to D-148 | 7 | D-142 to E-002 | White Lake | 0 | 43878 |  | 42 | 43882 | [5 empty] | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1058KL-20200212-3L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD1058KL-20200212-3L.O.A.0.4545455110.9091OEWT-PA2-LEM-R1 | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1121 | KL-20200222-1 | 53510711 | Access | 0 | L.O.A. | 244 | 0.090909 | Day |  | 0 |  |  | 22.1818 | 2.8836 | 25.0654 | 2020-02-22 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow for road access | 7 | D-119 to D-141 | Alder Creek | 0 | 43887 |  | 43 | 43889 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1121KL-20200222-1L.O.A.0.090909122.1818 | KABI LAKE FOREST PRODUCTS LTD1121KL-20200222-1L.O.A.0.090909122.1818OEWT-PA2-LEM-R1 | [5 empty] | 1 | 22.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1122 | KL-20200222-2 | 53510711 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-02-22 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow- White Lake Road | 7 | D-142 to E-002 | White Lake | 0 | 43887 |  | 43 | 43889 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1122KL-20200222-2L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD1122KL-20200222-2L.O.A.0.363636488.7273OEWT-PA2-LEM-R1 | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1124 | KL-20200222-4 | 53510711 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-02-22 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | low snow on Black River East road | 7 | D-032 to D-055 | Black River | 0 | 43887 |  | 43 | 43889 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1124KL-20200222-4L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD1124KL-20200222-4L.O.A.0.181818244.3636OEWT-PA2-LEM-R1 | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1125 | KL-20200222-5 | 53510711 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-02-22 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow for access on Wabakoba Creek | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 43887 |  | 43 | 43889 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1125KL-20200222-5L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD1125KL-20200222-5L.O.A.0.181818244.3636OEWT-PA2-LEM-R1 | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1129 | KL-20200223-3 | 53510711 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-02-23 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow and maintain road | 7 | D-032 to D-055 | Black River | 0 | 43887 |  | 43 | 43889 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1129KL-20200223-3L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD1129KL-20200223-3L.O.A.0.181818244.3636OEWT-PA2-LEM-R1 | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1195 | KL-20200301-3 | 53510711 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-03-01 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | At tower D-004 to rework road because of guide wire | 7 | D-001 to Highway 17 | Peninsula Road | 0 | 43896 |  | 45 | 43914 | [5 empty] | Howard Beaudet | 07 | KABI LAKE FOREST PRODUCTS LTD1195KL-20200301-3L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD1195KL-20200301-3L.O.A.0.363636488.7273OEWT-PA3-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1291 | KL-20200313-1 | 53510711 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-03-13 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Grade road from HWY to D-038 and D-032 | 7 | D-032 to D-055 | Black River | 0 | 43908 |  | 42 | 43914 | [5 empty] | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1291KL-20200313-1L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD1291KL-20200313-1L.O.A.0.272727366.5455OEWT-PA3-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1296 | KL-20200313-3 | 53510711 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-03-13 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade road from HWY and D038 to D054 | 7 | D-032 to D-055 | Black River | 0 | 43907 |  | 42 | 43914 | [5 empty] | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1296KL-20200313-3L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD1296KL-20200313-3L.O.A.0.5454545133.0909OEWT-PA3-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1303 | KL-20200314-2 | 53510711 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-03-14 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow to open road after snow. | 7 | D-018 to D-031 | Pic River West | 0 | 43908 |  | 42 | 43915 | [5 empty] | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1303KL-20200314-2L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD1303KL-20200314-2L.O.A.0.272727366.5455OEWT-PA3-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1305 | KL-20200314-4 | 53510711 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-03-14 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open road after snow | 7 | D-018 to D-031 | Pic River East | 0 | 43908 |  | 42 | 43915 | [5 empty] | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1305KL-20200314-4L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD1305KL-20200314-4L.O.A.0.272727366.5455OEWT-PA3-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1306 | KL-20200314-5 | 53510711 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-03-14 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open road after snow | 7 | D-032 to D-055 | Black River | 0 | 43908 |  | 42 | 43915 | [5 empty] | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1306KL-20200314-5L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD1306KL-20200314-5L.O.A.0.363636488.7273OEWT-PA3-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1352 | KL-20200322-1 | 53510711 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-03-22 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | PLOW SNOW IN ACCESS ROADS | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 43915 |  | 46 | 43919 | [5 empty] | Dave Ofukany | 07 | KABI LAKE FOREST PRODUCTS LTD1352KL-20200322-1L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD1352KL-20200322-1L.O.A.0.5454545133.0909OEWT-PA3-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1352 | KL-20200322-1 | 53510711 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-03-22 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | PLOW SNOW IN ACCESS ROADS | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 43915 |  | 46 | 43919 | [5 empty] | Dave Ofukany | 07 | KABI LAKE FOREST PRODUCTS LTD1352KL-20200322-1L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD1352KL-20200322-1L.O.A.0.272727366.5455OEWT-PA3-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1369 | KL-20200323-5 | 53510711 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-03-23 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clearing Road and prep for log haul | 7 | D-032 to D-055 | Black River | 0 | 43917 |  | 46 | 43921 | [5 empty] | Dave Ofukany | 07 | KABI LAKE FOREST PRODUCTS LTD1369KL-20200323-5L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD1369KL-20200323-5L.O.A.1244OEWT PA4-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1378 | KL-20200324-8 | 53510711 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-03-24 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Prep and fix roads for log haul | 7 | D-032 to D-055 | Black River East | 0 | 43917 |  | 46 | 43921 | [5 empty] | Dave Ofukany | 07 | KABI LAKE FOREST PRODUCTS LTD1378KL-20200324-8L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD1378KL-20200324-8L.O.A.1244OEWT PA4-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1410 | KL-20200329-4 | 53510711 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-03-29 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Drag Road Black River East Main Access to D-051 | 7 | D-032 to D-055 | Black River | 0 | 43927 |  | 45 | 43924 | [5 empty] | Howard Beaudet | 07 | KABI LAKE FOREST PRODUCTS LTD1410KL-20200329-4L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD1410KL-20200329-4L.O.A.0.363636488.7273OEWT PA4-LEM-R1 | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1444 | KL-20200402-5 | 53510711 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-04-02 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair and maintain road from D054 to HWY 17 | 7 | D-032 to D-055 | Black River | 0 | 43930 |  | 43 | 43933 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1444KL-20200402-5L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD1444KL-20200402-5L.O.A.0.7272727177.4545OEWT PA4-LEM-R1 | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1445 | KL-20200402-6 | 53510711 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-04-02 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Remove and demob pusher for haul trucks on log haul | 7 | D-032 to D-055 | Black River | 0 | 43930 |  | 43 | 43933 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1445KL-20200402-6L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD1445KL-20200402-6L.O.A.0.363636488.7273OEWT PA4-LEM-R1 | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1445 | KL-20200402-6 | 53510711 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-04-02 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Remove and demob pusher for haul trucks on log haul | 7 | D-032 to D-055 | Black River | 0 | 43930 |  | 43 | 43933 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1445KL-20200402-6L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD1445KL-20200402-6L.O.A.0.363636488.7273OEWT PA4-LEM-R1 | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4932 | KL-20201207-6 | 53510711 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Snow removal from D018 to D025 and filling ruts for freezing | 7 | D-018 to D-031 | Pie River | 0 | 44193 |  | 47 | 44202 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4932KL-20201207-6L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD4932KL-20201207-6L.O.A.0.9090909221.8182OEWT-PA12-LEM-R1 | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5040 | KL-20201218-1 | 53510711 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-12-18 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6K Dozer continuing road maintenance from D032 to D061 | 7 | D-032 to D-055 | Black River | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD5040KL-20201218-1L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD5040KL-20201218-1L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5094 | KL-20201217-2 | 53510711 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6K Dozer starting road maintenance to D032 | 7 | D-032 to D-055 | Black River | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD5094KL-20201217-2L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD5094KL-20201217-2L.O.A.0.181818244.3636OEWT-PA12-LEM-R1 | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7885 | KL-20220214-3 | 53510711 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2022-02-14 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run Grader from Kabi Yard to Alder Creek Road, clear snow @ entrance for float access and run grader back to Kabi Yard | 7 | D119-D141 | Alder Creek | 0 | 44614 |  | 61 | 44614 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7885KL-20220214-3L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7885KL-20220214-3L.O.A.0.363636488.7273OEWT-PA26-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7891 | KL-20220215-4 | 53510711 | Access | 0 | L.O.A. | 244 | 0.31818 | Day |  | 0 |  |  | 77.6364 | 10.0927 | 87.7291 | 2022-02-15 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on snow removal from Lay Down to D148 for wood grinding access and start snow removal to E002 for stringers | 7 | D142-E002 | White Lake West | 0 | 44614 |  | 61 | 44614 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7891KL-20220215-4L.O.A.0.318181877.6364 | KABI LAKE FOREST PRODUCTS LTD7891KL-20220215-4L.O.A.0.318181877.6364OEWT-PA26-LEM | [5 empty] | 1 | 77.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7895 | KL-20220216-3 | 53510711 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2022-02-16 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing snow removal from Lay Down to D148 and to E002 for stringers | 7 | D142 - E002 | White Lake West | 0 | 44614 |  | 61 | 44614 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7895KL-20220216-3L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7895KL-20220216-3L.O.A.0.7727273188.5455OEWT-PA26-LEM | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7918 | KL-20220223-3 | 53510711 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2022-02-23 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat D6T Dozer from Denis Lake East to White Lake West | 7 | D142 - E002 | White Lake West | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7918KL-20220223-3L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7918KL-20220223-3L.O.A.0.272727366.5455OEWT-PA26-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7922 | KL-20220224-3 | 53510711 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2022-02-24 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from E-001 to D148. | 7 | D142 - E002 | White Lake West | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7922KL-20220224-3L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7922KL-20220224-3L.O.A.0.363636488.7273OEWT-PA26-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7951 | KL-20220207-8 | 53510711 | Access | 0 | L.O.A. | 244 | 0.13636 | Day |  | 0 |  |  | 33.2727 | 4.3255 | 37.5982 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from 41 road to White Lake West & clear lay down for float turn around. | 7 | D142 - E002 | White Lake West | 0 |  |  | 61 | 44614 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7951KL-20220207-8L.O.A.0.136363633.2727 | KABI LAKE FOREST PRODUCTS LTD7951KL-20220207-8L.O.A.0.136363633.2727OEWT-PA26-LEM | [5 empty] | 1 | 33.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7851 | KL-20220207-9 | 53510711 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from White Lake West, clear hwy entrance, access & turn around for float access. | 7 | D100-D106 | 614 Road | 0 | 44604 |  | 61 | 44614 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7851KL-20220207-9L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD7851KL-20220207-9L.O.A.0.181818244.3636OEWT-PA26-LEM | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 885 | KL-20200112-1-R2 | 53510712 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-01-23 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Terrance Bob | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Brush out White Lake Rd. for All season access | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD885KL-20200112-1-R2L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD885KL-20200112-1-R2L.O.A.1244OEWT-PA1-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 886 | KL-20200113-1-R1 | 53510712 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-01-23 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clear and brush existing road for equpiment access | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD886KL-20200113-1-R1L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD886KL-20200113-1-R1L.O.A.2488OEWT-PA1-LEM | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 897 | KL-20200120-1 | 53510712 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5454 | 8.6509 | 75.1963 | 2020-01-24 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Mob Brusher to site, initiate all seanson access maintenance | 7 | D-109 to D-118 | Wabakoba Creek | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD897KL-20200120-1L.O.A.0.27272766.5454 | KABI LAKE FOREST PRODUCTS LTD897KL-20200120-1L.O.A.0.27272766.5454OEWT-PA1-LEM | [5 empty] | 1 | 66.5454 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 941 | KL-20200128-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-01-28 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clear snow from access road. | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 43861 |  | 17 | 43863 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD941KL-20200128-2L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD941KL-20200128-2L.O.A.0.181818244.3636OEWT-PA2-LEM-R1 | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1404 | KL-20200328-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-03-28 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Push snow banks back on access road , scrape road and grade | 7 | D-119 to D-141 | Alder Creek | 0 | 43925 |  | 45 | 43924 | [5 empty] | Howard Beaudet | 07 | KABI LAKE FOREST PRODUCTS LTD1404KL-20200328-2L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD1404KL-20200328-2L.O.A.0.181818244.3636OEWT PA4-LEM-R1 | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1404 | KL-20200328-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-03-28 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Push snow banks back on access road , scrape road and grade | 7 | D-119 to D-141 | Alder Creek | 0 | 43925 |  | 45 | 43924 | [5 empty] | Howard Beaudet | 07 | KABI LAKE FOREST PRODUCTS LTD1404KL-20200328-2L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD1404KL-20200328-2L.O.A.0.181818244.3636OEWT PA4-LEM-R1 | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1404 | KL-20200328-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-03-28 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Push snow banks back on access road , scrape road and grade | 7 | D-119 to D-141 | Alder Creek | 0 | 43925 |  | 45 | 43924 | [5 empty] | Howard Beaudet | 07 | KABI LAKE FOREST PRODUCTS LTD1404KL-20200328-2L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD1404KL-20200328-2L.O.A.0.4545455110.9091OEWT PA4-LEM-R1 | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1404 | KL-20200328-2 | 53510712 | Access | 0 | L.O.A. | 244 | -4.098e-05 | Day |  | 0 |  |  | -0.01 | -0.0013 | -0.0113 | 2020-03-28 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Push snow banks back on access road , scrape road and grade | 7 | D-119 to D-141 | Alder Creek | 0 | 43925 |  | 45 | 43924 | [5 empty] | Howard Beaudet | 07 | KABI LAKE FOREST PRODUCTS LTD1404KL-20200328-2L.O.A.-0.00004098-0.01 | KABI LAKE FOREST PRODUCTS LTD1404KL-20200328-2L.O.A.-0.00004098-0.01OEWT PA4-LEM-R1 | [5 empty] | 1 | -0.01 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1551 | KL-20200521-3 | 53510712 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-05-21 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Ditching and Shaping Road | 7 | D032-D055 | Black River East | 0 | 43977 |  | 15 | 43977 | [5 empty] | Martin Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD1551KL-20200521-3L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD1551KL-20200521-3L.O.A.0.4545455110.9091OEWT-PA5-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1886 | KL-20200626-7 | 53510712 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-06-26 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade section on 100 road to 5km pit for gravel haul to Alder Creek | 7 | D-119 to D-141 | Alder Creek | 0 | 44038 |  | 47 | 44014 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD1886KL-20200626-7L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD1886KL-20200626-7L.O.A.0.272727366.5455OEWT-PA7-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2018 | KL-20200712-9 | 53510712 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-07-12 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 100 Road from Hwy to 5KM pit for gravel haul | 7 | D-119 to D-141 | Alder Creek | 0 | 44027 |  | 48 | 44028 | [5 empty] | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2018KL-20200712-9L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD2018KL-20200712-9L.O.A.0.4545455110.9091OEWT-PA7-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2019 | KL-20200712-10 | 53510712 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-07-12 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Grade 600 road from Km 4 to Km 9 | 9 | E-091 to E-102 | 600 Road | 0 | 44027 | [9 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD2019KL-20200712-10L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD2019KL-20200712-10L.O.A.0.363636488.7273OEWT-PA7-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2092 | KL-20200717-4 | 53510712 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-07-17 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road to D055 to D053 | 7 | D-056 to D-073 | Umbatta Falls | 0 | 44034 |  | 48 | 44034 | [5 empty] | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2092KL-20200717-4L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD2092KL-20200717-4L.O.A.0.363636488.7273OEWT-PA7-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2101 | KL-20200717-13 | 53510712 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-07-17 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 100 road from Hwy to 5km pit for gravel Haul | 7 | D-100 to D-106 | 614 Road | 0 | 44034 |  | 48 | 44034 | [5 empty] | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2101KL-20200717-13L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD2101KL-20200717-13L.O.A.0.4545455110.9091OEWT-PA7-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2108 | KL-20200718-6 | 53510712 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2020-07-18 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road from D053 to D043 | 7 | D-032 to D-055 | Black River | 0 | 44034 |  | 48 | 44034 | [5 empty] | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2108KL-20200718-6L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD2108KL-20200718-6L.O.A.0.6363636155.2727OEWT-PA7-LEM | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2275 | KL-20200726-6 | 53510712 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-07-26 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road maintenance from D109 to D112 | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 44041 |  | 48 | 44041 | [5 empty] | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2275KL-20200726-6L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD2275KL-20200726-6L.O.A.0.4545455110.9091OEWT-PA8-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2300 | KL-20200729-3 | 53510712 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-07-29 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road Maintenance from D118 to D116 | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 44047 |  | 50 | 44048 | [5 empty] | Jim Budgell | 07 | KABI LAKE FOREST PRODUCTS LTD2300KL-20200729-3L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD2300KL-20200729-3L.O.A.0.5454545133.0909OEWT-PA8-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2426 | KL-20200812-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-08-12 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 2 Rock Trucks hauling from stock pile to D132/ Excavator loading | 7 | D-119 to D-141 | Alder Creek | 0 | 44060 |  | 47 | 44061 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD2426KL-20200812-2L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD2426KL-20200812-2L.O.A.0.363636488.7273OEWT-PA8-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2426 | KL-20200812-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-08-12 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 2 Rock Trucks hauling from stock pile to D132/ Excavator loading | 7 | D-119 to D-141 | Alder Creek | 0 | 44060 |  | 47 | 44061 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD2426KL-20200812-2L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD2426KL-20200812-2L.O.A.0.363636488.7273OEWT-PA8-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2426 | KL-20200812-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-08-12 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 2 Rock Trucks hauling from stock pile to D132/ Excavator loading | 7 | D-119 to D-141 | Alder Creek | 0 | 44060 |  | 47 | 44061 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD2426KL-20200812-2L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD2426KL-20200812-2L.O.A.0.363636488.7273OEWT-PA8-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2430 | KL-20200812-6 | 53510712 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-08-12 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road Maintenance from D114 to D119 | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 44060 |  | 47 | 44061 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD2430KL-20200812-6L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD2430KL-20200812-6L.O.A.0.5454545133.0909OEWT-PA8-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3820 | KL-20201018-4 | 53510712 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-10-18 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Level ruts in Access to D096 to D097 for Drainage | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44130 |  | 47 | 44131 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD3820KL-20201018-4L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD3820KL-20201018-4L.O.A.0.272727366.5455OEWT-PA10-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4293 | KL-20201110-3 | 53510712 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and spread gravel and chips D071-D073 BMC-30143 | 7 | D065-D066 | Camp 36 Road | 0 | 44166 |  | 53 | 44168 | [5 empty] | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD4293KL-20201110-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD4293KL-20201110-3L.O.A.0.9090909221.8182OEWT-PA11-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4293 | KL-20201110-3 | 53510712 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and spread gravel and chips D071-D073 BMC-30143 | 7 | D065-D066 | Camp 36 Road | 0 | 44166 |  | 53 | 44168 | [5 empty] | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD4293KL-20201110-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD4293KL-20201110-3L.O.A.0.9090909221.8182OEWT-PA11-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4352 | KL-20201114-5 | 53510712 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9113 | 14.4185 | 125.3298 | 2020-11-14 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc working access from D125 to D129/1 hr excavator & grinder travel due to poor condition of access mats D121 to D132 | 7 | D-119 to D-141 | Alder Creek | 0 | 44166 |  | 53 | 44171 | [5 empty] | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD4352KL-20201114-5L.O.A.0.45455455110.9113 | KABI LAKE FOREST PRODUCTS LTD4352KL-20201114-5L.O.A.0.45455455110.9113OEWT-PA11-LEM | [5 empty] | 1 | 110.9113 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4456 | KL-20201119-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2020-11-19 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working access to ROW and from D074 to D078, leveling ruts and track packing road | 7 | D-074 to D-079 | Brett’s Road | 0 | 44167 |  | 47 | 44172 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4456KL-20201119-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD4456KL-20201119-2L.O.A.0.8181818199.6364OEWT-PA11-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4480 | KL-20201120-6 | 53510712 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-11-20 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working access to ROW & to D74 levelling ruts & track packing road for Pickup Access | 7 | D-074 to D-079 | Brett’s Road | 0 | 44167 |  | 47 | 44173 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4480KL-20201120-6L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD4480KL-20201120-6L.O.A.0.272727366.5455OEWT-PA11-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7428 | KL-20211005-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-05 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road & hauling concrete anchors on a rig mat for LEG. Excavator levelling ruts, shaping road, assisting pickups & rock truck. | 7 | D018-D031 | Pic River | 0 | 44477 |  | 37 | 44478 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7428KL-20211005-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7428KL-20211005-2L.O.A.0.9090909221.8182OEWT-PA22-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7428 | KL-20211005-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-10-05 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road & hauling concrete anchors on a rig mat for LEG. Excavator levelling ruts, shaping road, assisting pickups & rock truck. | 7 | D018-D031 | Pic River | 0 | 44477 |  | 37 | 44478 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7428KL-20211005-2L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7428KL-20211005-2L.O.A.0.9545455232.9091OEWT-PA22-Lem | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7399 | KL-20210927-3 | 53510712 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2021-09-27 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue hauling pit run from Cress Pit & spreading on ROW access. Dozer levelling ruts after hours. | 7 | D018-D031 | Pic River | 0 | 44475 |  | 62 | 44478 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7399KL-20210927-3L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD7399KL-20210927-3L.O.A.1244OEWT-PA22-Lem | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7405 | KL-20210928-3 | 53510712 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-09-28 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue hauling pit run from Cress Pit & spreading on ROW access/excavator fixing soft areas & track packing for gravel trucks. Labourer sweeping dirt off Hwy 17 | 7 | D018-D031 | pic River West | 0 | 44475 |  | 62 | 44478 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7405KL-20210928-3L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7405KL-20210928-3L.O.A.0.9545455232.9091OEWT-PA22-Lem | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7425 | KL-20211004-2 | 53510712 | Access | 0 | L.O.A. | 244 | 1.9545 | Day |  | 0 |  |  | 476.9091 | 61.9982 | 538.9073 | 2021-10-04 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer & excavator levelling ruts, shaping road, pulling pickups & grout truck to D025 due to wet conditions. Excavator working after hours until all crews got out. | 7 | D018-D031 | Pic River | 0 | 44477 |  | 37 | 44478 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7425KL-20211004-2L.O.A.1.9545455476.9091 | KABI LAKE FOREST PRODUCTS LTD7425KL-20211004-2L.O.A.1.9545455476.9091OEWT-PA22-Lem | [5 empty] | 1 | 476.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7432 | KL-20211006-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-10-06 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road and pushing rock trucks hauling gravel to D025 /excavator leveling ruts and shaping road. | 7 | D018-D031 | Pic river | 0 | 44484 |  | 63 | 44484 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7432KL-20211006-2L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7432KL-20211006-2L.O.A.0.9545455232.9091OEWT-PA22-Lem | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7432 | KL-20211006-2 | 53510712 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2021-10-06 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road and pushing rock trucks hauling gravel to D025 /excavator leveling ruts and shaping road. | 7 | D018-D031 | Pic river | 0 | 44484 |  | 63 | 44484 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7432KL-20211006-2L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD7432KL-20211006-2L.O.A.1244OEWT-PA22-Lem | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7435 | KL-20211007-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-10-07 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer & excavator levelling ruts & shaping road from D-019 to D-025. | 7 | D018-D031 | Pic River | 0 | 44484 |  | 37 | 44495 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7435KL-20211007-2L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7435KL-20211007-2L.O.A.0.7727273188.5455OEWT-PA22-Lem | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7435 | KL-20211007-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-10-07 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer & excavator levelling ruts & shaping road from D-019 to D-025. | 7 | D018-D031 | Pic River | 0 | 44484 |  | 37 | 44495 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7435KL-20211007-2L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7435KL-20211007-2L.O.A.0.7727273188.5455OEWT-PA22-Lem | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7437 | KL-20211008-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2021-10-08 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer & excavator finishing levelling ruts & shaping road from D-019 to D-025 for pickup access. | 7 | D018-D031 | Pic River | 0 | 44484 |  | 37 | 44495 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7437KL-20211008-2L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7437KL-20211008-2L.O.A.0.272727366.5455OEWT-PA22-Lem | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7437 | KL-20211008-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2021-10-08 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer & excavator finishing levelling ruts & shaping road from D-019 to D-025 for pickup access. | 7 | D018-D031 | Pic River | 0 | 44484 |  | 37 | 44495 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7437KL-20211008-2L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7437KL-20211008-2L.O.A.0.272727366.5455OEWT-PA22-Lem | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7487 | KL-20211024-3 | 53510712 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  |  |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer leveling ruts and shaping road from Hwy 17 to D018 and to D025 after completion of foundation work | 7 | D018-D031 | Pic River | 0 | 44493 |  | 61 | 44497 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7487KL-20211024-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7487KL-20211024-3L.O.A.0.9090909221.8182OEWT-PA23-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 898 | KL-20200120-2 | 53510811 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.818 | 28.8363 | 250.6543 | 2020-01-24 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open road to E002 | 8 |  |  | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 08 | KABI LAKE FOREST PRODUCTS LTD898KL-20200120-2L.O.A.0.90909221.818 | KABI LAKE FOREST PRODUCTS LTD898KL-20200120-2L.O.A.0.90909221.818OEWT-PA1-LEM | [5 empty] | 1 | 221.818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1055 | KL-20200211-13 | 53510811 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  |  |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-02-13 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Winter road maintenance. Plow open access to North Crocker Lake Rd | 8 | E-068 to E-076 | North Crockers Lake | 0 | 43878 |  | 42 | 43882 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1055KL-20200211-13L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD1055KL-20200211-13L.O.A.0.363636488.7273OEWT-PA2-LEM-R1 | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1244 | KL-20200308-1 | 53510811 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2020-03-08 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | E-042 to E-053 Open access road to ROW | 8 | E068 - E076 | Denis Lake W | 0 | 43903 |  | 42 | 43910 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1244KL-20200308-1L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD1244KL-20200308-1L.O.A.0.6363636155.2727OEWT-PA3-LEM | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1299 | KL-20200313-6 | 53510811 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-03-13 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open road from HWY to E-049 | 8 | E-042 to E-053 | Denis Lake W | 0 | 43907 |  | 42 | 43914 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1299KL-20200313-6L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD1299KL-20200313-6L.O.A.0.5454545133.0909OEWT-PA3-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1309 | KL-20200316-3 | 53510811 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-03-16 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow road at Blue Cedar | 8 | E-077 to E-091 | Blue Cedar W | 0 | 43908 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1309KL-20200316-3L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD1309KL-20200316-3L.O.A.0.272727366.5455OEWT-PA3-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1318 | KL-20200317-3 | 53510811 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow and maintain road | 8 | E086 - E092E-068 to E-076 | North Crockers Lake | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1318KL-20200317-3L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD1318KL-20200317-3L.O.A.0.363636488.7273OEWT-PA3-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1319 | KL-20200317-4 | 53510811 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | CONTINUE TO OPEN ROAD TO ACCESS ROW | 8 | E-062 to E-067 | Buck Lake | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1319KL-20200317-4L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD1319KL-20200317-4L.O.A.0.181818244.3636OEWT-PA3-LEM | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1319 | KL-20200317-4 | 53510811 | Access | 0 | L.O.A. | 244 | 0.090909 | Day |  | 0 |  |  | 22.1818 | 2.8836 | 25.0654 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | CONTINUE TO OPEN ROAD TO ACCESS ROW | 8 | E-062 to E-067 | Buck Lake | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1319KL-20200317-4L.O.A.0.090909122.1818 | KABI LAKE FOREST PRODUCTS LTD1319KL-20200317-4L.O.A.0.090909122.1818OEWT-PA3-LEM | [5 empty] | 1 | 22.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1325 | KL-20200318-3 | 53510811 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-03-18 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue to widen access road | 8 | E-062 to E-067 | Buck Lake | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1325KL-20200318-3L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD1325KL-20200318-3L.O.A.0.363636488.7273OEWT-PA3-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1333 | KL-20200319-7 | 53510811 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-03-19 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | PLOW OPEN (WIDEN) ACCESS RD | 8 | E-062 to E-067 | Buck Lake | 0 | 43913 |  | 42 | 43917 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1333KL-20200319-7L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD1333KL-20200319-7L.O.A.0.7272727177.4545OEWT-PA3-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1339 | KL-20200320-2 | 53510811 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-03-20 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fix road access to ROW | 8 | E-062 to E-067 | Buck Lake | 0 | 43914 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1339KL-20200320-2L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD1339KL-20200320-2L.O.A.0.5454545133.0909OEWT-PA3-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1496 | KL-20200401-7-R1 | 53510811 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-04-01 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair rutts on main access road | 8 | E042-E059 | Denis Lake Road West | 0 | 43933 |  | 45 | 43934 | [5 empty] | Howard Beaudet | 08 | KABI LAKE FOREST PRODUCTS LTD1496KL-20200401-7-R1L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD1496KL-20200401-7-R1L.O.A.0.363636488.7273OEWT PA4-LEM-R1 | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4654 | KL-20201126-8 | 53510811 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load sand from 6km pit on 600 road and sand Access from Hwy to E073 for concrete haul as per discussion with Valard | 8 | E068-E076 | North Crockers Lake | 0 | 44178 |  | 47 | 44183 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4654KL-20201126-8L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD4654KL-20201126-8L.O.A.0.363636488.7273OEWT-PA12-LEM-R1 | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4654 | KL-20201126-8 | 53510811 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load sand from 6km pit on 600 road and sand Access from Hwy to E073 for concrete haul as per discussion with Valard | 8 | E068-E076 | North Crockers Lake | 0 | 44178 |  | 47 | 44183 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4654KL-20201126-8L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD4654KL-20201126-8L.O.A.0.181818244.3636OEWT-PA12-LEM-R1 | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4902 | KL-20201205-5 | 53510811 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-12-05 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding Silver City AU1 Access to E025 as per Valard | 8 | E025-E036 | Silver City | 0 | 44193 |  | 53 | 44207 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4902KL-20201205-5L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD4902KL-20201205-5L.O.A.0.363636488.7273OEWT-PA12-LEM-R1 | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4902 | KL-20201205-5 | 53510811 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-12-05 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding Silver City AU1 Access to E025 as per Valard | 8 | E025-E036 | Silver City | 0 | 44193 |  | 53 | 44207 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4902KL-20201205-5L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD4902KL-20201205-5L.O.A.0.181818244.3636OEWT-PA12-LEM-R1 | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4919 | KL-20201206-6 | 53510811 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-12-06 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer blading AE1 Access from Hwy to ROW | 8 | E017-E024 | North Regan | 0 | 44193 |  | 53 | 44207 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4919KL-20201206-6L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD4919KL-20201206-6L.O.A.0.181818244.3636OEWT-PA12-LEM-R1 | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5000 | KL-20201214-3 | 53510811 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding and Grading Access to E073 for concrete haul as per Valard | 8 | E004-E016 | White Lake East | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD5000KL-20201214-3L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD5000KL-20201214-3L.O.A.0.181818244.3636OEWT-PA12-LEM-R1 | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5000 | KL-20201214-3 | 53510811 | Access | 0 | L.O.A. | 244 | 0.13636 | Day |  | 0 |  |  | 33.2727 | 4.3255 | 37.5982 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding and Grading Access to E073 for concrete haul as per Valard | 8 | E004-E016 | White Lake East | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD5000KL-20201214-3L.O.A.0.136363633.2727 | KABI LAKE FOREST PRODUCTS LTD5000KL-20201214-3L.O.A.0.136363633.2727OEWT-PA12-LEM-R1 | [5 empty] | 1 | 33.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5000 | KL-20201214-3 | 53510811 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding and Grading Access to E073 for concrete haul as per Valard | 8 | E004-E016 | White Lake East | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD5000KL-20201214-3L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD5000KL-20201214-3L.O.A.0.272727366.5455OEWT-PA12-LEM-R1 | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5151 | KL-20201228-2 | 53510811 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-12-28 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6K Dozer working on snow removal from Hwy 17 to E014/E015 Access | 8 | E004-E016 | White Lake East | 0 | 43836 |  | 36 | 44213 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD5151KL-20201228-2L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD5151KL-20201228-2L.O.A.0.7272727177.4545OEWT-PA13-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5858 | KL-20210211-2 | 53510811 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-02-11 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer doing snow removal from 9020.00 WC to Hwy 17 | 8 | E004-E016 | White Lake East | 0 | 44244 |  | 36 | 44250 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD5858KL-20210211-2L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD5858KL-20210211-2L.O.A.0.4545455110.9091OEWT-PA14-Lem-R1 | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7882 | KL-20220213-6 | 53510811 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2022-02-13 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal and widening from Hwy 17 to E004 and clearing pad @ E005 | 8 | E004 - E010 | White Lake East | 0 | 44614 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7882KL-20220213-6L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7882KL-20220213-6L.O.A.0.9545455232.9091OEWT-PA26-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7886 | KL-20220214-4 | 53510811 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2022-02-14 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and widening from Hwy 17 to E013 and clearing pad @ E013 | 8 | E004-E010 | White Lake East | 0 | 44614 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7886KL-20220214-4L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7886KL-20220214-4L.O.A.0.9545455232.9091OEWT-PA26-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7890 | KL-20220215-3 | 53510811 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2022-02-15 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer finishing snow removal and widening from Hwy 17 to E013 | 8 | E004 - E010 | White Lake East | 0 | 44614 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7890KL-20220215-3L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7890KL-20220215-3L.O.A.0.6363636155.2727OEWT-PA26-LEM | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7903 | KL-20220219-4 | 53510811 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2022-02-19 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat D6T Dozer from White Lake East to Denis Lake Road West | 8 | E042 - E058 | Denis Lake W | 0 | 44617 |  | 61 | 44617 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7903KL-20220219-4L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7903KL-20220219-4L.O.A.0.272727366.5455OEWT-PA26-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7907 | KL-20220219-3 | 53510811 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-19 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal & clearing pull offs from Hwy 17 to E051. | 8 | E042 - E058 | Denis Lake W | 0 | 44617 |  | 61 | 44617 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7907KL-20220219-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7907KL-20220219-3L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7915 | KL-20220222-3 | 53510811 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2022-02-22 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat D6T Dozer from Denis Lake West to Hwy entrance @ White Lake East | 8 | E004-E010 | White Lake East | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 08 | KABI LAKE FOREST PRODUCTS LTD7915KL-20220222-3L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7915KL-20220222-3L.O.A.0.272727366.5455OEWT-PA26-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7916 | KL-20220223-1 | 53510811 | Access | 0 | L.O.A. | 244 | 0.68182 | Day |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2022-02-23 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hwy 17 to E013 & to E005. | 8 | E004 - E010 | White Lake East | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 08 | KABI LAKE FOREST PRODUCTS LTD7916KL-20220223-1L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD7916KL-20220223-1L.O.A.0.6818182166.3636OEWT-PA26-LEM | [5 empty] | 1 | 166.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7942 | KL-20220227-5 | 53510811 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Float Kabi Cat D6T Dozer From Kabi Yard To Denis Lake Road West | 8 | E042 - E058 | Denis Lake W | 0 | 44628 | [9 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7942KL-20220227-5L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7942KL-20220227-5L.O.A.0.272727366.5455 | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7943 | KL-20220227-6 | 53510811 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Dozer working on snow removal & clearing pull offs from Hwy 17 to E-051 | 8 | E042 - E058 | Denis Lake W | 0 | 44628 | [9 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7943KL-20220227-6L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7943KL-20220227-6L.O.A.0.5454545133.0909 | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7947 | KL-20220228-4 | 53510811 | Access | 0 | L.O.A. | 244 | 0.22727 | Day |  | 0 |  |  | 55.4545 | 7.2091 | 62.6636 | 2022-02-28 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Float Kabi Cat D6T Dozer From Denis Lake Road West to Kabi Yard. | 8 | E042 - E058 | Denis Lake W | 0 | 44628 | [9 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7947KL-20220228-4L.O.A.0.227272755.4545 | KABI LAKE FOREST PRODUCTS LTD7947KL-20220228-4L.O.A.0.227272755.4545 | [5 empty] | 1 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7839 | KL-20220205-4 | 53510811 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2022-02-05 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from Kabi yard, clear snow around highway entrance and turn around for float access. | 8 | E042-E058 | Denis Lake W | 0 | 44603 |  | 61 | 44603 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7839KL-20220205-4L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD7839KL-20220205-4L.O.A.0.181818244.3636OEWT-PA26-LEM | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7840 | KL-20220205-5 | 53510811 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2022-02-05 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run Grader From Denis Lake West to 41 Road, Clear Snow @ Hwy Entrance, Open Road & Turn Around For Float Access/Supervisor Doing Pickup Shuffle | 8 | E037 - E041 | Road 41 | 0 | 44603 |  | 61 | 44603 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7840KL-20220205-5L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7840KL-20220205-5L.O.A.0.272727366.5455OEWT-PA26-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7848 | KL-20220207-5 | 53510811 | Access | 0 | L.O.A. | 244 | 0.13636 | Day |  | 0 |  |  | 33.2727 | 4.3255 | 37.5982 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader clearing hwy entrance, open road & turn around for float access. | 8 | E037-E041 | 41 Road | 0 | 44604 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7848KL-20220207-5L.O.A.0.136363633.2727 | KABI LAKE FOREST PRODUCTS LTD7848KL-20220207-5L.O.A.0.136363633.2727OEWT-PA26-LEM | [5 empty] | 1 | 33.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7849 | KL-20220207-6 | 53510811 | Access | 0 | L.O.A. | 244 | 0.13636 | Day |  | 0 |  |  | 33.2727 | 4.3255 | 37.5982 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from 614 road & clear entrance for float access. | 8 | E004 - E010 | White Lake East | 0 | 44604 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7849KL-20220207-6L.O.A.0.136363633.2727 | KABI LAKE FOREST PRODUCTS LTD7849KL-20220207-6L.O.A.0.136363633.2727OEWT-PA26-LEM | [5 empty] | 1 | 33.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7850 | KL-20220207-7 | 53510811 | Access | 0 | L.O.A. | 244 | 0.13636 | Day |  | 0 |  |  | 33.2727 | 4.3255 | 37.5982 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from White Lake East, clear hwy entrance & turn around for float access. Run grader to 41 road & park. | 8 | E011-E025 | North Regan | 0 | 44604 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7850KL-20220207-7L.O.A.0.136363633.2727 | KABI LAKE FOREST PRODUCTS LTD7850KL-20220207-7L.O.A.0.136363633.2727OEWT-PA26-LEM | [5 empty] | 1 | 33.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7856 | KL-20220208-5 | 53510811 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2022-02-08 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run Grader From 41 Road,Clear Hwy Entrance, Open Road For Float Access & Run Grader Back To Kabi Yard | 8 | E025-E036 | Silver City | 0 | 44604 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7856KL-20220208-5L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7856KL-20220208-5L.O.A.0.7272727177.4545OEWT-PA26-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7863 | KL-20220209-6 | 53510811 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2022-02-09 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hwy 17 to E002 | 10 |  | White Lake east | 0 | 44604 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7863KL-20220209-6L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7863KL-20220209-6L.O.A.0.9545455232.9091OEWT-PA26-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7868 | KL-20220210-5 | 53510811 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2022-02-10 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal from Hwy 17 to E002 and to E008 | 8 | E004 - E010 | White Lake East | 0 | 44605 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7868KL-20220210-5L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7868KL-20220210-5L.O.A.0.9545455232.9091OEWT-PA26-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7871 | KL-20220211-3 | 53510811 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2022-02-11 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal from Hwy 17 to E004 | 8 | E004 - E010 | White Lake East | 0 | 44605 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7871KL-20220211-3L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7871KL-20220211-3L.O.A.0.272727366.5455OEWT-PA26-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7872 | KL-20220211-4 | 53510811 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2022-02-11 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on snow removal from E034 to E035/E036 for wood grinding access | 8 | E025-E036 | SIlver City | 0 | 44605 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7872KL-20220211-4L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7872KL-20220211-4L.O.A.0.363636488.7273OEWT-PA26-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1322 | KL-20200317-7 | 53510812 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | RV-40002 SPREAD GRAVEL; HAUL GRAVEL IN SOFT SOPT ACROSS HONI LINE AND TO GAIN ACCESS OVER ROCK IN EXISTING ENTRANCE RD | 8 | E-077 to E-091 | Blue Cedar W | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7L.O.A.0.7272727177.4545OEWT-PA3-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1322 | KL-20200317-7 | 53510812 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | RV-40002 SPREAD GRAVEL; HAUL GRAVEL IN SOFT SOPT ACROSS HONI LINE AND TO GAIN ACCESS OVER ROCK IN EXISTING ENTRANCE RD | 8 | E-077 to E-091 | Blue Cedar W | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7L.O.A.0.7272727177.4545OEWT-PA3-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1322 | KL-20200317-7 | 53510812 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | RV-40002 SPREAD GRAVEL; HAUL GRAVEL IN SOFT SOPT ACROSS HONI LINE AND TO GAIN ACCESS OVER ROCK IN EXISTING ENTRANCE RD | 8 | E-077 to E-091 | Blue Cedar W | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7L.O.A.0.181818244.3636OEWT-PA3-LEM | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1322 | KL-20200317-7 | 53510812 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | RV-40002 SPREAD GRAVEL; HAUL GRAVEL IN SOFT SOPT ACROSS HONI LINE AND TO GAIN ACCESS OVER ROCK IN EXISTING ENTRANCE RD | 8 | E-077 to E-091 | Blue Cedar W | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7L.O.A.0.363636488.7273OEWT-PA3-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1322 | KL-20200317-7 | 53510812 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | RV-40002 SPREAD GRAVEL; HAUL GRAVEL IN SOFT SOPT ACROSS HONI LINE AND TO GAIN ACCESS OVER ROCK IN EXISTING ENTRANCE RD | 8 | E-077 to E-091 | Blue Cedar W | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7L.O.A.0.6363636155.2727OEWT-PA3-LEM | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1542 | KL-20200520-13 | 53510812 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-05-20 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start Ditching main access road | 8 | E068-E076 | North Crockers Lake | 0 | 43976 |  | 15 | 43977 | [5 empty] | Martin Hunt | 08 | KABI LAKE FOREST PRODUCTS LTD1542KL-20200520-13L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD1542KL-20200520-13L.O.A.1244OEWT-PA5-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1640 | KL-20200602-10 | 53510812 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-06-02 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 100 road to 5 KM Pit gor Blue Cedar Gravel Haul | 8 | E077-E091 | Blue Cedar Road | 0 | 43987 |  | 15 | 43988 | [5 empty] | Martin Hunt | 08 | KABI LAKE FOREST PRODUCTS LTD1640KL-20200602-10L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD1640KL-20200602-10L.O.A.0.4545455110.9091OEWT-PA6-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2941 | KL-20200915-12 | 53510812 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-09-15 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 100 road to 5Km pit for gravel haul | 8 | E068 - E076 | Denis Lake W | 0 | 44096 |  | 15 | 44097 | [5 empty] | Martin Hunt | 08 | KABI LAKE FOREST PRODUCTS LTD2941KL-20200915-12L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD2941KL-20200915-12L.O.A.0.363636488.7273OEWT-PA9-Lem-R1 | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3900 | KL-20201025-4 | 53510812 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-10-25 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator starting maintenance on access for concrete truck as per Valard | 8 | E-077 to E-091 | Blue Cedar Road | 0 | 44133 |  | 47 | 44133 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3900KL-20201025-4L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD3900KL-20201025-4L.O.A.0.5454545133.0909OEWT-PA10-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3982 | KL-20201026-7 | 53510812 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-10-26 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 excavator doing maintenance on access for concrete trucks as per Valard | 8 | E077-E091 | Blue Cedar | 0 | 44147 |  | 47 | 44151 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3982KL-20201026-7L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD3982KL-20201026-7L.O.A.1244OEWT-PA11-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3999 | KL-20201027-4 | 53510812 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-10-27 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 excavator doing road maintenance on access for Concrete trucks as per Valard | 8 | E-077 to E-091 | Blue Cedar W | 0 | 44147 |  | 47 | 44151 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3999KL-20201027-4L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD3999KL-20201027-4L.O.A.1244OEWT-PA11-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4096 | KL-20201101-5 | 53510812 | Access | 0 | L.O.A. | 244 | 0.5 | Day |  | 0 |  |  | 122 | 15.86 | 137.86 | 2020-11-01 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator doing Road Maintenance on Access per Valard | 8 | E077-E091 | Blue Cedar W | 0 | 44152 |  | 47 | 44163 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4096KL-20201101-5L.O.A.0.5122 | KABI LAKE FOREST PRODUCTS LTD4096KL-20201101-5L.O.A.0.5122OEWT-PA11-LEM | [5 empty] | 1 | 122 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4356 | KL-20201114-9 | 53510812 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-11-14 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade sections of Access to D142 as per Valard | 8 | E004-E016 | White Lake East | 0 | 44166 |  | 53 | 44171 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4356KL-20201114-9L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD4356KL-20201114-9L.O.A.0.272727366.5455OEWT-PA11-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4385 | KL-20201114-20 | 53510812 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-11-14 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade access to ROW as per Valard | 8 | E037-E041 | 41 Road | 0 | 44167 |  | 53 | 44171 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4385KL-20201114-20L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD4385KL-20201114-20L.O.A.0.181818244.3636OEWT-PA11-LEM | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4409 | KL-20201116-8 | 53510812 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T dozer working on road, levelling ruts from E069 to E073 as per Valard. (Cost Code as per Frank 53510812) | 8 | E068-E076 | North Crockers Lake | 0 | 44167 |  | 47 | 44171 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4409KL-20201116-8L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4409KL-20201116-8L.O.A.1244OEWT-PA11-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4410 | KL-20201116-9 | 53510812 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Charged to move Cat D6T dozer to E069/due to Adam from foundations (Cost Code 53510812 as per Frank) | 8 | E068-E076 | North Crockers Lake | 0 | 44167 |  | 47 | 44171 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4410KL-20201116-9L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD4410KL-20201116-9L.O.A.0.181818244.3636OEWT-PA11-LEM | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4425 | KL-20201117-5 | 53510812 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-11-17 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T dozer working on road, levelling ruts from E069 to E073 as per Valard/Support for Foundations (CC as per Frank 53510812) | 8 | E068-E076 | North Crockers Lake | 0 | 44167 |  | 47 | 44172 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4425KL-20201117-5L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4425KL-20201117-5L.O.A.1244OEWT-PA11-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4447 | KL-20201118-8 | 53510812 | Access | 0 | L.O.A. | 244 | 1.1818 | Day |  | 0 |  |  | 288.3636 | 37.4873 | 325.8509 | 2020-11-18 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float had dozer loaded and Valard needed the dozer to stay/support for foundations as per email. | 8 | E068-E076 | North Crockers Lake | 0 | 44167 |  | 14 | 44177 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD4447KL-20201118-8L.O.A.1.1818182288.3636 | KABI LAKE FOREST PRODUCTS LTD4447KL-20201118-8L.O.A.1.1818182288.3636OEWT-PA11-LEM | [5 empty] | 1 | 288.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4460 | KL-20201119-6 | 53510812 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-11-19 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T dozer working on road leveling ruts from E069 to E073 as per valard/ Support for foundations | 8 | E068-E076 | North Crockers Lake | 0 | 44167 |  | 47 | 44172 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4460KL-20201119-6L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4460KL-20201119-6L.O.A.1244OEWT-PA11-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4485 | KL-20201120-11 | 53510812 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-11-20 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | (CC 53510812 as per Frank) needs cost code changed. |  | Approved |  |  | Cat D6T dozer working on road, levelling ruts from E069 to E073 as per Valard/support for Foundations (CC 53510812 as per Frank) | 8 | E068-E076 | North Regan | 0 | 44167 |  | 47 | 44173 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4485KL-20201120-11L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4485KL-20201120-11L.O.A.1244OEWT-PA11-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4507 | KL-20201121-8 | 53510812 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-11-21 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working access from E077 to E086, levelling ruts & track packing road | 8 | E077-E091 | Blue Cedar Road | 0 | 44167 |  | 47 | 44174 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4507KL-20201121-8L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD4507KL-20201121-8L.O.A.0.4545455110.9091OEWT-PA11-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4550 | KL-20201122-8 | 53510812 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-11-22 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working access from E086 to E091, leveling ruts and track packing road for freezing | 8 | E077-E091 | Blue Cedar W | 0 | 44172 |  | 47 | 44184 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4550KL-20201122-8L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD4550KL-20201122-8L.O.A.0.272727366.5455OEWT-PA11-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4551 | KL-20201122-9 | 53510812 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-11-22 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T dozer working on AU1 Access shaping and leveling ruts/cleaning up the turn around | 8 | E062-E067 | Buck Lake Road | 0 | 44172 |  | 47 | 44183 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4551KL-20201122-9L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD4551KL-20201122-9L.O.A.0.4545455110.9091OEWT-PA11-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4568 | KL-20201123-6 | 53510812 | Access | 0 | L.O.A. | 244 | 0.090909 | Day |  | 0 |  |  | 22.1818 | 2.8836 | 25.0654 | 2020-11-23 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working access from E086 to E091, leveling ruts and track packing road for freezing | 8 | E077-E091 | Blue Cedar W | 0 | 44172 |  | 47 | 44175 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4568KL-20201123-6L.O.A.0.090909122.1818 | KABI LAKE FOREST PRODUCTS LTD4568KL-20201123-6L.O.A.0.090909122.1818OEWT-PA12-LEM-R1 | [5 empty] | 1 | 22.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4604 | KL-20201124-7 | 53510812 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-11-24 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working Access from E086 to E091, leveling ruts and track packing road for freezing | 8 | E077-E091 | Blue Cedar W | 0 | 44172 |  | 47 | 44179 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4604KL-20201124-7L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD4604KL-20201124-7L.O.A.0.272727366.5455OEWT-PA11-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4627 | KL-20201125-4 | 53510812 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working access from E086 to E077, leveling ruts & track packing road for freezing | 8 | E077-E091 | Blue Cedar W | 0 | 44173 |  | 47 | 44183 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4627KL-20201125-4L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD4627KL-20201125-4L.O.A.0.363636488.7273OEWT-PA12-LEM-R1 | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6900 | KL-20210510-3 | 53510812 | Access | 0 | L.O.A. | 244 | 0.31818 | Day |  | 0 |  |  | 77.6364 | 10.0927 | 87.7291 | 2021-05-10 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 962M loader repairing washout @Blue Cedar entrance/Labourer escorting loader on Hwy 17 from Kabi Yard and back | 8 | E077-E091 | Blue Cedar | 0 | 44337 |  | 56 | 44341 | [5 empty] | Mandy Sandhu | 08 | KABI LAKE FOREST PRODUCTS LTD6900KL-20210510-3L.O.A.0.318181877.6364 | KABI LAKE FOREST PRODUCTS LTD6900KL-20210510-3L.O.A.0.318181877.6364OEWT-PA17-LEM | [5 empty] | 1 | 77.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6922 | KL-20210515-6 | 53510812 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2021-05-15 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading, hauling and spreading pit run from stock pile to E007/E006 access/loading and hauling trees for soft sections/dozer leveling ruts and excavator placing corduroy | 8 | E004-E016 | White Lake East | 0 | 44337 |  | 56 | 44342 | [5 empty] | Mandy Sandhu | 08 | KABI LAKE FOREST PRODUCTS LTD6922KL-20210515-6L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD6922KL-20210515-6L.O.A.2488OEWT-PA17-LEM | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6922 | KL-20210515-6 | 53510812 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-05-15 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading, hauling and spreading pit run from stock pile to E007/E006 access/loading and hauling trees for soft sections/dozer leveling ruts and excavator placing corduroy | 8 | E004-E016 | White Lake East | 0 | 44337 |  | 56 | 44342 | [5 empty] | Mandy Sandhu | 08 | KABI LAKE FOREST PRODUCTS LTD6922KL-20210515-6L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD6922KL-20210515-6L.O.A.0.8636364210.7273OEWT-PA17-LEM | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6925 | KL-20210516-2 | 53510812 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-05-16 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator ditching along access @ E006 to E007 for capping material | 8 | E004-E016 | White Lake East | 0 | 44337 |  | 56 | 44343 | [5 empty] | Mandy Sandhu | 08 | KABI LAKE FOREST PRODUCTS LTD6925KL-20210516-2L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD6925KL-20210516-2L.O.A.0.7272727177.4545OEWT-PA17-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6945 | KL-20210518-2 | 53510812 | Access | 0 | L.O.A. | 244 | 0.22727 | Day |  | 0 |  |  | 55.4545 | 7.2091 | 62.6636 | 2021-05-18 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | loading , hauling and spreading existing material @ E014 for road repairs from E014.5 to E016 to maintain pickup access | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44349 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6945KL-20210518-2L.O.A.0.227272755.4545 | KABI LAKE FOREST PRODUCTS LTD6945KL-20210518-2L.O.A.0.227272755.4545OEWT-PA17-LEM | [5 empty] | 1 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6945 | KL-20210518-2 | 53510812 | Access | 0 | L.O.A. | 244 | 0.22727 | Day |  | 0 |  |  | 55.4545 | 7.2091 | 62.6636 | 2021-05-18 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | loading , hauling and spreading existing material @ E014 for road repairs from E014.5 to E016 to maintain pickup access | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44349 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6945KL-20210518-2L.O.A.0.227272755.4545 | KABI LAKE FOREST PRODUCTS LTD6945KL-20210518-2L.O.A.0.227272755.4545OEWT-PA17-LEM | [5 empty] | 1 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6945 | KL-20210518-2 | 53510812 | Access | 0 | L.O.A. | 244 | 0.22727 | Day |  | 0 |  |  | 55.4545 | 7.2091 | 62.6636 | 2021-05-18 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | loading , hauling and spreading existing material @ E014 for road repairs from E014.5 to E016 to maintain pickup access | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44349 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6945KL-20210518-2L.O.A.0.227272755.4545 | KABI LAKE FOREST PRODUCTS LTD6945KL-20210518-2L.O.A.0.227272755.4545OEWT-PA17-LEM | [5 empty] | 1 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6947 | KL-20210518-4 | 53510812 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2021-05-18 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Original route was reclaimed, total supervision 7 hours. |  | Approved |  |  | Excavator leveling ruts and shapes access to E007 for drainage | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44349 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6947KL-20210518-4L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD6947KL-20210518-4L.O.A.0.181818244.3636OEWT-PA17-LEM | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6951 | KL-20210519-2 | 53510812 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-05-19 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading, hauling and spreading exsiting material @ E014 for road repairs from E016 to E013.5 (revised) | 8 | E034 - E036 | White Lake East | 0 | 44345 |  | 14 | 44352 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6951KL-20210519-2L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD6951KL-20210519-2L.O.A.0.363636488.7273OEWT-PA17-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6951 | KL-20210519-2 | 53510812 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-05-19 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading, hauling and spreading exsiting material @ E014 for road repairs from E016 to E013.5 (revised) | 8 | E034 - E036 | White Lake East | 0 | 44345 |  | 14 | 44352 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6951KL-20210519-2L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD6951KL-20210519-2L.O.A.0.363636488.7273OEWT-PA17-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6951 | KL-20210519-2 | 53510812 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-05-19 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading, hauling and spreading exsiting material @ E014 for road repairs from E016 to E013.5 (revised) | 8 | E034 - E036 | White Lake East | 0 | 44345 |  | 14 | 44352 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6951KL-20210519-2L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD6951KL-20210519-2L.O.A.0.363636488.7273OEWT-PA17-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6959 | KL-20210520-1 | 53510812 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread existing material @ 1.5 km and pit run from stock pile for road repair on E007/E006 main access road/ Laboures laying Geo ( revised) | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6959KL-20210520-1L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD6959KL-20210520-1L.O.A.0.9545455232.9091OEWT-PA17-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6959 | KL-20210520-1 | 53510812 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread existing material @ 1.5 km and pit run from stock pile for road repair on E007/E006 main access road/ Laboures laying Geo ( revised) | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6959KL-20210520-1L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD6959KL-20210520-1L.O.A.0.9545455232.9091OEWT-PA17-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6959 | KL-20210520-1 | 53510812 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread existing material @ 1.5 km and pit run from stock pile for road repair on E007/E006 main access road/ Laboures laying Geo ( revised) | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6959KL-20210520-1L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD6959KL-20210520-1L.O.A.0.9545455232.9091OEWT-PA17-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6960 | KL-20210520-2 | 53510812 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat excavator Leveling ruts and shaping road from E016 to E010 | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6960KL-20210520-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD6960KL-20210520-2L.O.A.0.8181818199.6364OEWT-PA17-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6967 | KL-20210521-2 | 53510812 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-05-21 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material from stockpile for road repairs to the access going into E005. Dozer spreading loads from from rock truck and fixing ruts. | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6967KL-20210521-2L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD6967KL-20210521-2L.O.A.0.9545455232.9091OEWT-PA17-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6967 | KL-20210521-2 | 53510812 | Access | 0 | L.O.A. | 244 | 0.59091 | Day |  | 0 |  |  | 144.1818 | 18.7436 | 162.9254 | 2021-05-21 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material from stockpile for road repairs to the access going into E005. Dozer spreading loads from from rock truck and fixing ruts. | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6967KL-20210521-2L.O.A.0.5909091144.1818 | KABI LAKE FOREST PRODUCTS LTD6967KL-20210521-2L.O.A.0.5909091144.1818OEWT-PA17-LEM | [5 empty] | 1 | 144.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6967 | KL-20210521-2 | 53510812 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-05-21 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material from stockpile for road repairs to the access going into E005. Dozer spreading loads from from rock truck and fixing ruts. | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6967KL-20210521-2L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD6967KL-20210521-2L.O.A.0.9545455232.9091OEWT-PA17-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6970 | KL-20210522-1 | 53510812 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  |  |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-05-22 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material from stock pile and bundles of wood from the main road to E006 for road repairs, dozer spreading loads and pushing up bundle of wood | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44348 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6970KL-20210522-1L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD6970KL-20210522-1L.O.A.0.9545455232.9091OEWT-PA17-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6970 | KL-20210522-1 | 53510812 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-05-22 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material from stock pile and bundles of wood from the main road to E006 for road repairs, dozer spreading loads and pushing up bundle of wood | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44348 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6970KL-20210522-1L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD6970KL-20210522-1L.O.A.0.9545455232.9091OEWT-PA17-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6970 | KL-20210522-1 | 53510812 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-05-22 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material from stock pile and bundles of wood from the main road to E006 for road repairs, dozer spreading loads and pushing up bundle of wood | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44348 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6970KL-20210522-1L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD6970KL-20210522-1L.O.A.0.9545455232.9091OEWT-PA17-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6976 | KL-20210523-3 | 53510812 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2021-05-23 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator fixing road going to E016 | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6976KL-20210523-3L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD6976KL-20210523-3L.O.A.0.5454545133.0909OEWT-PA17-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6977 | KL-20210523-4 | 53510812 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  |  |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-05-23 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material for road repairs near E011, 330 loading material and dozer spreading loads from rock truck and fixing punch outs | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6977KL-20210523-4L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD6977KL-20210523-4L.O.A.0.9545455232.9091OEWT-PA17-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6977 | KL-20210523-4 | 53510812 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-05-23 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material for road repairs near E011, 330 loading material and dozer spreading loads from rock truck and fixing punch outs | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6977KL-20210523-4L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD6977KL-20210523-4L.O.A.0.9545455232.9091OEWT-PA17-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6977 | KL-20210523-4 | 53510812 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2021-05-23 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material for road repairs near E011, 330 loading material and dozer spreading loads from rock truck and fixing punch outs | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6977KL-20210523-4L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD6977KL-20210523-4L.O.A.0.409090999.8182OEWT-PA17-LEM | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6980 | KL-20210524-1 | 53510812 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2021-05-24 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 excavator working on drainage out of E016/Dozer leveling ruts and back blading out from E016 to E006 | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6980KL-20210524-1L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD6980KL-20210524-1L.O.A.0.181818244.3636OEWT-PA17-LEM | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6980 | KL-20210524-1 | 53510812 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-05-24 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 excavator working on drainage out of E016/Dozer leveling ruts and back blading out from E016 to E006 | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6980KL-20210524-1L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD6980KL-20210524-1L.O.A.0.9545455232.9091OEWT-PA17-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6983 | KL-20210525-2 | 53510812 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-05-25 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load Haul and spread existing material @ E014 for Road repairs from E015 to E016/Excavator and Dozer working on Road maintenance E013 to E006 | 8 | E004-E016 | White Lake East | 0 | 44343 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6983KL-20210525-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD6983KL-20210525-2L.O.A.0.8181818199.6364OEWT-PA17-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6983 | KL-20210525-2 | 53510812 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-05-25 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load Haul and spread existing material @ E014 for Road repairs from E015 to E016/Excavator and Dozer working on Road maintenance E013 to E006 | 8 | E004-E016 | White Lake East | 0 | 44343 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6983KL-20210525-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD6983KL-20210525-2L.O.A.0.8181818199.6364OEWT-PA17-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6983 | KL-20210525-2 | 53510812 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2021-05-25 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load Haul and spread existing material @ E014 for Road repairs from E015 to E016/Excavator and Dozer working on Road maintenance E013 to E006 | 8 | E004-E016 | White Lake East | 0 | 44343 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6983KL-20210525-2L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD6983KL-20210525-2L.O.A.0.272727366.5455OEWT-PA17-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6988 | KL-20210526-1 | 53510812 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-05-26 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer working on road maintenance leveling ruts and drainage E011 to E016 | 8 | E004-E016 | White Lake East | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6988KL-20210526-1L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD6988KL-20210526-1L.O.A.0.9545455232.9091OEWT-PA18-Lem | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6988 | KL-20210526-1 | 53510812 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-05-26 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer working on road maintenance leveling ruts and drainage E011 to E016 | 8 | E004-E016 | White Lake East | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6988KL-20210526-1L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD6988KL-20210526-1L.O.A.0.9545455232.9091OEWT-PA18-Lem | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6991 | KL-20210527-1 | 53510812 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-05-27 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer working on road maintenance leveling ruts and drainage E006 to E016/ Supervisor site visit with Valard ROW and directing Operators | 8 | E004-E016 | White Lake East | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6991KL-20210527-1L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD6991KL-20210527-1L.O.A.0.9545455232.9091OEWT-PA18-Lem | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6991 | KL-20210527-1 | 53510812 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-05-27 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer working on road maintenance leveling ruts and drainage E006 to E016/ Supervisor site visit with Valard ROW and directing Operators | 8 | E004-E016 | White Lake East | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6991KL-20210527-1L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD6991KL-20210527-1L.O.A.0.9545455232.9091OEWT-PA18-Lem | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6993 | KL-20210528-1 | 53510812 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-05-28 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer working on road maintenance leveling ruts and drainage E006 to E016/ Start shaping hill @E017 Access | 8 | E004-E016 | White Lake East | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6993KL-20210528-1L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD6993KL-20210528-1L.O.A.0.9545455232.9091OEWT-PA18-Lem | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6993 | KL-20210528-1 | 53510812 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-05-28 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer working on road maintenance leveling ruts and drainage E006 to E016/ Start shaping hill @E017 Access | 8 | E004-E016 | White Lake East | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6993KL-20210528-1L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD6993KL-20210528-1L.O.A.0.9545455232.9091OEWT-PA18-Lem | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6999 | KL-20210531-1 | 53510812 | Access | 0 | L.O.A. | 244 | 0.090909 | Day |  | 0 |  |  | 22.1818 | 2.8836 | 25.0654 | 2021-05-31 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauling existing material for covering of soft sections on E005 access | 8 | E004-E016 | White Lake East | 0 | 44358 |  | 36 | 44359 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6999KL-20210531-1L.O.A.0.090909122.1818 | KABI LAKE FOREST PRODUCTS LTD6999KL-20210531-1L.O.A.0.090909122.1818OEWT-PA18-Lem | [5 empty] | 1 | 22.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6999 | KL-20210531-1 | 53510812 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2021-05-31 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauling existing material for covering of soft sections on E005 access | 8 | E004-E016 | White Lake East | 0 | 44358 |  | 36 | 44359 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6999KL-20210531-1L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD6999KL-20210531-1L.O.A.0.272727366.5455OEWT-PA18-Lem | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6999 | KL-20210531-1 | 53510812 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2021-05-31 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauling existing material for covering of soft sections on E005 access | 8 | E004-E016 | White Lake East | 0 | 44358 |  | 36 | 44359 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6999KL-20210531-1L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD6999KL-20210531-1L.O.A.0.272727366.5455OEWT-PA18-Lem | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7002 | KL-20210601-1 | 53510812 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-06-01 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road and leveling ruts from 8907.01 WC to Hwy 17/Cleaning up old access road from E007 to E006 as new route was built | 8 | E004-E016 | White Lake East | 0 | 44358 |  | 14 | 44359 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD7002KL-20210601-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7002KL-20210601-1L.O.A.0.9090909221.8182OEWT-PA18-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7002 | KL-20210601-1 | 53510812 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-06-01 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road and leveling ruts from 8907.01 WC to Hwy 17/Cleaning up old access road from E007 to E006 as new route was built | 8 | E004-E016 | White Lake East | 0 | 44358 |  | 14 | 44359 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD7002KL-20210601-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7002KL-20210601-1L.O.A.0.9090909221.8182OEWT-PA18-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7068 | KL-20210529-2 | 53510812 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2021-05-29 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer shaping hill and filling ruts on E017 access from E016 | 8 | E004-E016 | White Lake East | 0 | 44372 |  | 36 | 44373 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD7068KL-20210529-2L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7068KL-20210529-2L.O.A.0.272727366.5455OEWT-PA18-Lem | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7068 | KL-20210529-2 | 53510812 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2021-05-29 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer shaping hill and filling ruts on E017 access from E016 | 8 | E004-E016 | White Lake East | 0 | 44372 |  | 36 | 44373 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD7068KL-20210529-2L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7068KL-20210529-2L.O.A.0.272727366.5455OEWT-PA18-Lem | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7268 | KL-20210823-2 | 53510812 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2021-08-23 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair & shape road from 9049.00 WC to E-017. Loader loading rig mats on float for return to Valard Marathon yard | 8 | E017-E024 | North Regan | 0 | 44438 |  | 50 | 44440 | [5 empty] | Jim Budgell | 08 | KABI LAKE FOREST PRODUCTS LTD7268KL-20210823-2L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7268KL-20210823-2L.O.A.0.6363636155.2727OEWT-PA20-Lem | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7268 | KL-20210823-2 | 53510812 | Access | 0 | L.O.A. | 244 | 0.090909 | Day |  | 0 |  |  | 22.1818 | 2.8836 | 25.0654 | 2021-08-23 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair & shape road from 9049.00 WC to E-017. Loader loading rig mats on float for return to Valard Marathon yard | 8 | E017-E024 | North Regan | 0 | 44438 |  | 50 | 44440 | [5 empty] | Jim Budgell | 08 | KABI LAKE FOREST PRODUCTS LTD7268KL-20210823-2L.O.A.0.090909122.1818 | KABI LAKE FOREST PRODUCTS LTD7268KL-20210823-2L.O.A.0.090909122.1818OEWT-PA20-Lem | [5 empty] | 1 | 22.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1057 | KL-20200212-2 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-02-12 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Winter Maintenance - Plow open road to get access to WF9 | 9 | E-091 to E-121 | 600 Rd | 0 | 43878 |  | 42 | 43882 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1057KL-20200212-2L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD1057KL-20200212-2L.O.A.1244OEWT-PA2-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1093 | KL-20200213-2-R1 | 53510911 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-02-13 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Standby should be 5 hours. | 23 | Approved | KABI LAKE - Standby - For Permits & Misc - ONGOING | 8002 | Winter Maintenance- continue to plow open 600 road | 9 | E-091-E121 | 600 Road | 0 | 43889 |  | 43 | 43896 | [5 empty] | Dean MacArthur | 09 | KABI LAKE FOREST PRODUCTS LTD1093KL-20200213-2-R1L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD1093KL-20200213-2-R1L.O.A.0.363636488.7273OEWT-PA3-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1093 | KL-20200213-2-R1 | 53510911 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-02-13 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Standby should be 5 hours. | 23 | Approved | KABI LAKE - Standby - For Permits & Misc - ONGOING | 8002 | Winter Maintenance- continue to plow open 600 road | 9 | E-091-E121 | 600 Road | 0 | 43889 |  | 43 | 43896 | [5 empty] | Dean MacArthur | 09 | KABI LAKE FOREST PRODUCTS LTD1093KL-20200213-2-R1L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD1093KL-20200213-2-R1L.O.A.0.7272727177.4545OEWT-PA3-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1153 | KL-20200225-3 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-02-25 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open 600 Road KM 10-15 | 9 | E-091-E102 | 600 rd | 0 | 43889 |  | 43 | 43890 | [5 empty] | Dean MacArthur | 09 | KABI LAKE FOREST PRODUCTS LTD1153KL-20200225-3L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD1153KL-20200225-3L.O.A.1244OEWT-PA2-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1173 | KL-20200226-10 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-03-26 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 600 RD - Continue to plow road to gain access to 20KM | 9 | E091-E121 | 600 Road | 0 | 43894 |  | 43 | 43896 | [5 empty] | Dean MacArthur | 09 | KABI LAKE FOREST PRODUCTS LTD1173KL-20200226-10L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD1173KL-20200226-10L.O.A.1244OEWT-PA3-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1178 | KL-20200227-3 | 53510911 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-02-27 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 600 Rd winter road maintenance - continue to open 600 rd @ 22km | 9 | E091-E121 | 600 Road | 0 | 43894 |  | 43 | 43896 | [5 empty] | Dean MacArthur | 09 | KABI LAKE FOREST PRODUCTS LTD1178KL-20200227-3L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD1178KL-20200227-3L.O.A.2488OEWT-PA3-LEM | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1184 | KL-20200228-3 | 53510911 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-02-28 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 600 Rd - plow 600 rd for access @30km. | 9 | E091-E102 | 600 road | 0 | 43896 |  | 45 | 43914 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1184KL-20200228-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD1184KL-20200228-3L.O.A.0.9090909221.8182OEWT-PA3-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1189 | KL-20200229-3 | 53510911 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-02-29 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 600 Rd - open 600 road to 32KM | 9 | E091-E102 | 600 Road | 0 | 43896 |  | 45 | 43914 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1189KL-20200229-3L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD1189KL-20200229-3L.O.A.0.7272727177.4545OEWT-PA3-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1197 | KL-20200301-5 | 53510911 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-03-01 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow down 600 road pushing back banks at 22km | 9 | E091-E102 | 600 Road | 0 | 43896 |  | 45 | 43914 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1197KL-20200301-5L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD1197KL-20200301-5L.O.A.0.9090909221.8182OEWT-PA3-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1209 | KL-20200302-7 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-03-02 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open 600 Road for access km 4 with grader and open sub roads at 2km | 9 | E-091 to E-102 | 600 Road | 0 | 43896 |  | 42 | 43910 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1209KL-20200302-7L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD1209KL-20200302-7L.O.A.1244OEWT-PA3-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1209 | KL-20200302-7 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-03-02 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open 600 Road for access km 4 with grader and open sub roads at 2km | 9 | E-091 to E-102 | 600 Road | 0 | 43896 |  | 42 | 43910 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1209KL-20200302-7L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD1209KL-20200302-7L.O.A.1244OEWT-PA3-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1222 | KL-20200304-4 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-03-04 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open access roads for WF9 | 7 | E-091 to E-102 | 600 Road | 0 | 43900 |  | 42 | 43910 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1222KL-20200304-4L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD1222KL-20200304-4L.O.A.1244OEWT-PA3-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1225 | KL-20200305-1 | 53510911 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-03-05 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open road and make turn arounds on 600 Road | 9 | E-091 to E-102 | 600 road | 0 | 43901 |  | 42 | 43910 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1225KL-20200305-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD1225KL-20200305-1L.O.A.0.9090909221.8182OEWT-PA3-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1225 | KL-20200305-1 | 53510911 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-03-05 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open road and make turn arounds on 600 Road | 9 | E-091 to E-102 | 600 road | 0 | 43901 |  | 42 | 43910 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1225KL-20200305-1L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD1225KL-20200305-1L.O.A.0.272727366.5455OEWT-PA3-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1225 | KL-20200305-1 | 53510911 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-03-05 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open road and make turn arounds on 600 Road | 9 | E-091 to E-102 | 600 road | 0 | 43901 |  | 42 | 43910 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1225KL-20200305-1L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD1225KL-20200305-1L.O.A.0.363636488.7273OEWT-PA3-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1225 | KL-20200305-1 | 53510911 | Access | 0 | L.O.A. | 244 | 4.098e-05 | Day |  | 0 |  |  | 0.01 | 0.0013 | 0.0113 | 2020-03-05 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open road and make turn arounds on 600 Road | 9 | E-091 to E-102 | 600 road | 0 | 43901 |  | 42 | 43910 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1225KL-20200305-1L.O.A.0.000040980.01 | KABI LAKE FOREST PRODUCTS LTD1225KL-20200305-1L.O.A.0.000040980.01OEWT-PA3-LEM | [5 empty] | 1 | 0.01 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1234 | KL-20200306-5 | 53510911 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2020-03-06 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open 600 road to 32 KM | 9 | E-091 to E-102 | 600 Road | 0 | 43901 |  | 42 | 43910 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1234KL-20200306-5L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD1234KL-20200306-5L.O.A.0.8181818199.6364OEWT-PA3-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1310 | KL-20200316-4 | 53510911 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2020-03-16 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open road by KM 30 and plow after snowfall | 9 | E-091 to E-102 | 600 Road | 0 | 43908 |  | 42 | 43915 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1310KL-20200316-4L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD1310KL-20200316-4L.O.A.0.8181818199.6364OEWT-PA3-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1310 | KL-20200316-4 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-03-16 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open road by KM 30 and plow after snowfall | 9 | E-091 to E-102 | 600 Road | 0 | 43908 |  | 42 | 43915 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1310KL-20200316-4L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD1310KL-20200316-4L.O.A.1244OEWT-PA3-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1315 | KL-20200317-1 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open road on 600 around km 36 | 9 | E-091 to E-102 | 600 Road. | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1315KL-20200317-1L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD1315KL-20200317-1L.O.A.1244OEWT-PA3-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1324 | KL-20200318-2 | 53510911 | Access | 0 | L.O.A. | 244 | 1.7273 | Day |  | 0 |  |  | 421.4545 | 54.7891 | 476.2436 | 2020-03-18 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | PLOW OPEN ROAD AT 40KM AND WING BACK BANKS | 9 | E-091 to E-102 | 600 Road | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1324KL-20200318-2L.O.A.1.7272727421.4545 | KABI LAKE FOREST PRODUCTS LTD1324KL-20200318-2L.O.A.1.7272727421.4545OEWT-PA3-LEM | [5 empty] | 1 | 421.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1382 | KL-20200325-4 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-03-25 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open 600 road to gain access | 9 | E-091 to E-102 | 600 Road | 0 | 43922 |  | 45 | 43923 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1382KL-20200325-4L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD1382KL-20200325-4L.O.A.1244OEWT PA4-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1387 | KL-20200326-5 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-03-26 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open more access on 600 road aprox 50km | 9 | E-091 to E-102 | 600 Road | 0 | 43922 |  | 45 | 43923 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1387KL-20200326-5L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD1387KL-20200326-5L.O.A.1244OEWT PA4-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1400 | KL-20200327-5 | 53510911 | Access | 0 | L.O.A. | 244 | 1.7273 | Day |  | 0 |  |  | 421.4545 | 54.7891 | 476.2436 | 2020-03-27 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open 600 for WF-9 access and grade road | 9 | E-091 to E-102 | 600 Road | 0 | 43925 |  | 45 | 43924 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1400KL-20200327-5L.O.A.1.7272727421.4545 | KABI LAKE FOREST PRODUCTS LTD1400KL-20200327-5L.O.A.1.7272727421.4545OEWT PA4-LEM-R1 | [5 empty] | 1 | 421.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1411 | KL-20200329-5 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-03-29 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open up 600 raod (plow snow) | 9 | E-091 to E-102 | 600 Road | 0 | 43927 |  | 45 | 43924 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1411KL-20200329-5L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD1411KL-20200329-5L.O.A.1244OEWT PA4-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1418 | KL-20200330-6 | 53510911 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-03-30 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Open up 600 Road (plow snow) | 9 |  | 600 Road | 0 | 43928 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD1418KL-20200330-6L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD1418KL-20200330-6L.O.A.2488OEWT PA4-LEM-R1 | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1427 | KL-20200331-7 | 53510911 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-03-31 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow off road | 9 | E091-E102 | 600 Road | 0 | 43928 |  | 45 | 43929 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1427KL-20200331-7L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD1427KL-20200331-7L.O.A.0.4545455110.9091OEWT PA4-LEM-R1 | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3903 | KL-20201025-7 | 53510911 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-10-25 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Prep KM20 pit on 600 road for Sander | 9 | E-091 to E-102 | 600 Road | 0 | 44133 |  | 50 | 44134 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3903KL-20201025-7L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD3903KL-20201025-7L.O.A.0.181818244.3636OEWT-PA10-LEM | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3904 | KL-20201025-8 | 53510911 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-10-25 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Mob Cat 320D Excavator to 20km pit for loading winter maintenance Sand | 9 | E-091 to E-102 | 600 Road | 0 | 44133 |  | 50 | 44134 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3904KL-20201025-8L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD3904KL-20201025-8L.O.A.0.272727366.5455OEWT-PA10-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3988 | KL-20201026-13 | 53510911 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-10-26 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading sander truck and sorting material , sanding 600 road | 9 | E091-E102 | 600 Rd | 0 | 44147 |  | 50 | 44161 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3988KL-20201026-13L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD3988KL-20201026-13L.O.A.2488OEWT-PA11-LEM | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4081 | KL-20201031-7 | 53510911 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2020-10-31 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading sand truck an sorting material, sanding 600 road. | 9 | E091-E102 | 600 Rd | 0 | 44152 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4081KL-20201031-7L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD4081KL-20201031-7L.O.A.0.9545455232.9091OEWT-PA11-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4081 | KL-20201031-7 | 53510911 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2020-10-31 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading sand truck an sorting material, sanding 600 road. | 9 | E091-E102 | 600 Rd | 0 | 44152 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4081KL-20201031-7L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD4081KL-20201031-7L.O.A.0.9545455232.9091OEWT-PA11-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4113 | KL-20201102-9 | 53510911 | Access | 0 | L.O.A. | 244 | 1.5455 | Day |  | 0 |  |  | 377.0909 | 49.0218 | 426.1127 | 2020-11-02 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading sander truck and sorting materials at km 20 an km 6 pits on the 600 road and 100 road | 9 | E091-E102 | 600 Rd | 0 | 44153 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4113KL-20201102-9L.O.A.1.5454545377.0909 | KABI LAKE FOREST PRODUCTS LTD4113KL-20201102-9L.O.A.1.5454545377.0909OEWT-PA11-LEM | [5 empty] | 1 | 377.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4113 | KL-20201102-9 | 53510911 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-11-02 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading sander truck and sorting materials at km 20 an km 6 pits on the 600 road and 100 road | 9 | E091-E102 | 600 Rd | 0 | 44153 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4113KL-20201102-9L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD4113KL-20201102-9L.O.A.0.5454545133.0909OEWT-PA11-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4135 | KL-20201103-5 | 53510911 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading Sand Truck and sorting material at 20km pit and 6km pit on 600 road, sanding 600, 700 and 100 roads | 9 | E-091 to E-102 | 600 Rd | 0 | 44153 |  | 50 | 44159 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4135KL-20201103-5L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD4135KL-20201103-5L.O.A.0.363636488.7273OEWT-PA11-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4135 | KL-20201103-5 | 53510911 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading Sand Truck and sorting material at 20km pit and 6km pit on 600 road, sanding 600, 700 and 100 roads | 9 | E-091 to E-102 | 600 Rd | 0 | 44153 |  | 50 | 44159 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4135KL-20201103-5L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD4135KL-20201103-5L.O.A.0.7272727177.4545OEWT-PA11-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4135 | KL-20201103-5 | 53510911 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading Sand Truck and sorting material at 20km pit and 6km pit on 600 road, sanding 600, 700 and 100 roads | 9 | E-091 to E-102 | 600 Rd | 0 | 44153 |  | 50 | 44159 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4135KL-20201103-5L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD4135KL-20201103-5L.O.A.0.6363636155.2727OEWT-PA11-LEM | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4135 | KL-20201103-5 | 53510911 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading Sand Truck and sorting material at 20km pit and 6km pit on 600 road, sanding 600, 700 and 100 roads | 9 | E-091 to E-102 | 600 Rd | 0 | 44153 |  | 50 | 44159 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4135KL-20201103-5L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD4135KL-20201103-5L.O.A.0.272727366.5455OEWT-PA11-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4417 | KL-20201116-16 | 53510911 | Access | 0 | L.O.A. | 244 | 1.3636 | Day |  | 0 |  |  | 332.7273 | 43.2545 | 375.9818 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road and 100 road to km5 pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4417KL-20201116-16L.O.A.1.3636364332.7273 | KABI LAKE FOREST PRODUCTS LTD4417KL-20201116-16L.O.A.1.3636364332.7273OEWT-PA11-LEM | [5 empty] | 1 | 332.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4417 | KL-20201116-16 | 53510911 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road and 100 road to km5 pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4417KL-20201116-16L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD4417KL-20201116-16L.O.A.0.5454545133.0909OEWT-PA11-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4430 | KL-20201117-9 | 53510911 | Access | 0 | L.O.A. | 244 | 1.3636 | Day |  | 0 |  |  | 332.7273 | 43.2545 | 375.9818 | 2020-11-17 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 Rd and 100 Rd to km5 pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4430KL-20201117-9L.O.A.1.3636364332.7273 | KABI LAKE FOREST PRODUCTS LTD4430KL-20201117-9L.O.A.1.3636364332.7273OEWT-PA11-LEM | [5 empty] | 1 | 332.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4430 | KL-20201117-9 | 53510911 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-11-17 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 Rd and 100 Rd to km5 pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4430KL-20201117-9L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD4430KL-20201117-9L.O.A.0.5454545133.0909OEWT-PA11-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4439 | KL-20201118-11 | 53510911 | Access | 0 | L.O.A. | 244 | 1.5455 | Day |  | 0 |  |  | 377.0909 | 49.0218 | 426.1127 | 2020-11-18 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road and 100 road to 5km pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4439KL-20201118-11L.O.A.1.5454545377.0909 | KABI LAKE FOREST PRODUCTS LTD4439KL-20201118-11L.O.A.1.5454545377.0909OEWT-PA11-LEM | [5 empty] | 1 | 377.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4439 | KL-20201118-11 | 53510911 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-11-18 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road and 100 road to 5km pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4439KL-20201118-11L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD4439KL-20201118-11L.O.A.0.5454545133.0909OEWT-PA11-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4462 | KL-20201119-8 | 53510911 | Access | 0 | L.O.A. | 244 | 1.9091 | Day |  | 0 |  |  | 465.8182 | 60.5564 | 526.3746 | 2020-11-19 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road and 100 road to 5km pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4462KL-20201119-8L.O.A.1.9090909465.8182 | KABI LAKE FOREST PRODUCTS LTD4462KL-20201119-8L.O.A.1.9090909465.8182OEWT-PA11-LEM | [5 empty] | 1 | 465.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4462 | KL-20201119-8 | 53510911 | Access | 0 | L.O.A. | 244 | 0.090909 | Day |  | 0 |  |  | 22.1818 | 2.8836 | 25.0654 | 2020-11-19 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road and 100 road to 5km pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4462KL-20201119-8L.O.A.0.090909122.1818 | KABI LAKE FOREST PRODUCTS LTD4462KL-20201119-8L.O.A.0.090909122.1818OEWT-PA11-LEM | [5 empty] | 1 | 22.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4513 | KL-20201121-14 | 53510911 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-11-21 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 rd and 100 rd to km5 pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4513KL-20201121-14L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD4513KL-20201121-14L.O.A.0.272727366.5455OEWT-PA11-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4513 | KL-20201121-14 | 53510911 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-11-21 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 rd and 100 rd to km5 pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4513KL-20201121-14L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD4513KL-20201121-14L.O.A.0.5454545133.0909OEWT-PA11-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4514 | KL-20201121-15 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-11-21 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road, 100 Road, and Access Roads in WF 9 | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4514KL-20201121-15L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4514KL-20201121-15L.O.A.1244OEWT-PA11-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4574 | KL-20201123-12 | 53510911 | Access | 0 | L.O.A. | 244 | 1.5455 | Day |  | 0 |  |  | 377.0909 | 49.0218 | 426.1127 | 2020-11-23 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 roads and 100 road to 5km pit | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 15 | 44176 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4574KL-20201123-12L.O.A.1.5454545377.0909 | KABI LAKE FOREST PRODUCTS LTD4574KL-20201123-12L.O.A.1.5454545377.0909OEWT-PA12-LEM-R1 | [5 empty] | 1 | 377.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4574 | KL-20201123-12 | 53510911 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-11-23 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 roads and 100 road to 5km pit | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 15 | 44176 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4574KL-20201123-12L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD4574KL-20201123-12L.O.A.0.7272727177.4545OEWT-PA12-LEM-R1 | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4609 | KL-20201124-12 | 53510911 | Access | 0 | L.O.A. | 244 | 1.5455 | Day |  | 0 |  |  | 377.0909 | 49.0218 | 426.1127 | 2020-11-24 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road, 700 road and 100 road to 5km pit and town pit | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4609KL-20201124-12L.O.A.1.5454545377.0909 | KABI LAKE FOREST PRODUCTS LTD4609KL-20201124-12L.O.A.1.5454545377.0909OEWT-PA12-LEM-R1 | [5 empty] | 1 | 377.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4609 | KL-20201124-12 | 53510911 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-11-24 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road, 700 road and 100 road to 5km pit and town pit | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4609KL-20201124-12L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD4609KL-20201124-12L.O.A.0.272727366.5455OEWT-PA12-LEM-R1 | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4636 | KL-20201125-13 | 53510911 | Access | 0 | L.O.A. | 244 | 1.5455 | Day |  | 0 |  |  | 377.0909 | 49.0218 | 426.1127 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, and 100 rd to km5 pit and town pit | 9 | E091-E102 | 600 Road | 0 | 44173 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4636KL-20201125-13L.O.A.1.5454545377.0909 | KABI LAKE FOREST PRODUCTS LTD4636KL-20201125-13L.O.A.1.5454545377.0909OEWT-PA12-LEM-R1 | [5 empty] | 1 | 377.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4659 | KL-20201126-12 | 53510911 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 and 100 road and access roads in WF 9 | 9 | E091-E102 | 600 Road | 0 | 44178 |  | 47 | 44183 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD4659KL-20201126-12L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD4659KL-20201126-12L.O.A.0.9090909221.8182OEWT-PA12-LEM-R1 | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4661 | KL-20201126-14 | 53510911 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 road to km5 pit and town pit | 9 | E091-E102 | 600 Road | 0 | 44178 |  | 50 | 44208 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4661KL-20201126-14L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD4661KL-20201126-14L.O.A.0.9090909221.8182OEWT-PA12-LEM-R1 | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4661 | KL-20201126-14 | 53510911 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 road to km5 pit and town pit | 9 | E091-E102 | 600 Road | 0 | 44178 |  | 50 | 44208 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4661KL-20201126-14L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD4661KL-20201126-14L.O.A.0.5454545133.0909OEWT-PA12-LEM-R1 | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4661 | KL-20201126-14 | 53510911 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 road to km5 pit and town pit | 9 | E091-E102 | 600 Road | 0 | 44178 |  | 50 | 44208 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4661KL-20201126-14L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD4661KL-20201126-14L.O.A.0.7272727177.4545OEWT-PA12-LEM-R1 | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4685 | KL-20201127-11 | 53510911 | Access | 0 | L.O.A. | 244 | 1.8182 | Day |  | 0 |  |  | 443.6364 | 57.6727 | 501.3091 | 2020-11-27 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 , 100 and Paint Lake Road 2 | 9 | E091-E102 | 600 Road | 0 | 44180 |  | 50 | 44201 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4685KL-20201127-11L.O.A.1.8181818443.6364 | KABI LAKE FOREST PRODUCTS LTD4685KL-20201127-11L.O.A.1.8181818443.6364OEWT-PA12-LEM-R1 | [5 empty] | 1 | 443.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4685 | KL-20201127-11 | 53510911 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-11-27 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 , 100 and Paint Lake Road 2 | 9 | E091-E102 | 600 Road | 0 | 44180 |  | 50 | 44201 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4685KL-20201127-11L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD4685KL-20201127-11L.O.A.0.181818244.3636OEWT-PA12-LEM-R1 | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4699 | KL-20201128-7 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-11-28 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 , 100 and Paint Lake Road 2 | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44201 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4699KL-20201128-7L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4699KL-20201128-7L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4703 | KL-20201128-11 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-11-28 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600rd, 100rd, and access in WF9 | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44201 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4703KL-20201128-11L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4703KL-20201128-11L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4709 | KL-20201129-10 | 53510911 | Access | 0 | L.O.A. | 244 | 1.5455 | Day |  | 0 |  |  | 377.0909 | 49.0218 | 426.1127 | 2020-11-29 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600Rd, 700, 100 roads | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44203 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4709KL-20201129-10L.O.A.1.5454545377.0909 | KABI LAKE FOREST PRODUCTS LTD4709KL-20201129-10L.O.A.1.5454545377.0909OEWT-PA12-LEM-R1 | [5 empty] | 1 | 377.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4723 | KL-20201130-6 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-11-30 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600, 100 roads and access roads in WF9 | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44203 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4723KL-20201130-6L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4723KL-20201130-6L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4724 | KL-20201130-7 | 53510911 | Access | 0 | L.O.A. | 244 | 1.3636 | Day |  | 0 |  |  | 332.7273 | 43.2545 | 375.9818 | 2020-11-30 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, 100, and Paint Lake 2 Roads | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44203 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4724KL-20201130-7L.O.A.1.3636364332.7273 | KABI LAKE FOREST PRODUCTS LTD4724KL-20201130-7L.O.A.1.3636364332.7273OEWT-PA12-LEM-R1 | [5 empty] | 1 | 332.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4742 | KL-20201201-11 | 53510911 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-12-01 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, 100, and Paint Lake 2 Rd | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4742KL-20201201-11L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD4742KL-20201201-11L.O.A.0.181818244.3636OEWT-PA12-LEM-R1 | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4742 | KL-20201201-11 | 53510911 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-12-01 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, 100, and Paint Lake 2 Rd | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4742KL-20201201-11L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD4742KL-20201201-11L.O.A.0.4545455110.9091OEWT-PA12-LEM-R1 | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4745 | KL-20201201-17 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-12-01 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600rd, 100rd, and access roads in WF9 | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4745KL-20201201-17L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4745KL-20201201-17L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4775 | KL-20201202-18 | 53510911 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-12-02 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, 100, and Paint Lake 2 Rds | 9 |  | 600 Road | 0 | 44193 |  | 53 | 44205 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4775KL-20201202-18L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD4775KL-20201202-18L.O.A.0.363636488.7273OEWT-PA12-LEM-R1 | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4775 | KL-20201202-18 | 53510911 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-12-02 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, 100, and Paint Lake 2 Rds | 9 |  | 600 Road | 0 | 44193 |  | 53 | 44205 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4775KL-20201202-18L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD4775KL-20201202-18L.O.A.0.4545455110.9091OEWT-PA12-LEM-R1 | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4775 | KL-20201202-18 | 53510911 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2020-12-02 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, 100, and Paint Lake 2 Rds | 9 |  | 600 Road | 0 | 44193 |  | 53 | 44205 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4775KL-20201202-18L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD4775KL-20201202-18L.O.A.0.8181818199.6364OEWT-PA12-LEM-R1 | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4810 | KL-20201209-12 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-12-09 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, and 100 roads. | 9 | E091-E102 | 600 Road | 0 | 44194 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4810KL-20201209-12L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4810KL-20201209-12L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4813 | KL-20201209-15 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-12-09 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 and 700 Road | 9 | E091-E102 | 600 Road | 0 | 44194 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4813KL-20201209-15L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4813KL-20201209-15L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4829 | KL-20201211-7 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-12-11 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4829KL-20201211-7L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4829KL-20201211-7L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4844 | KL-20201212-9 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-12-12 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 & 700 Roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44208 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4844KL-20201212-9L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4844KL-20201212-9L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4889 | KL-20201204-12 | 53510911 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-12-04 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 100 Rd | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4889KL-20201204-12L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD4889KL-20201204-12L.O.A.0.363636488.7273OEWT-PA12-LEM-R1 | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4889 | KL-20201204-12 | 53510911 | Access | 0 | L.O.A. | 244 | 0.090909 | Day |  | 0 |  |  | 22.1818 | 2.8836 | 25.0654 | 2020-12-04 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 100 Rd | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4889KL-20201204-12L.O.A.0.090909122.1818 | KABI LAKE FOREST PRODUCTS LTD4889KL-20201204-12L.O.A.0.090909122.1818OEWT-PA12-LEM-R1 | [5 empty] | 1 | 22.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4891 | KL-20201204-14 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-12-04 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 23 | Approved | KABI LAKE - Standby - For Permits & Misc - ONGOING | 8002 | Standby due to Valard not requiring equipment . | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4891KL-20201204-14L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4891KL-20201204-14L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4906 | KL-20201205-9 | 53510911 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-12-05 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, and 100 roads. | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4906KL-20201205-9L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD4906KL-20201205-9L.O.A.0.7272727177.4545OEWT-PA12-LEM-R1 | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4906 | KL-20201205-9 | 53510911 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-12-05 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, and 100 roads. | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4906KL-20201205-9L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD4906KL-20201205-9L.O.A.0.272727366.5455OEWT-PA12-LEM-R1 | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4906 | KL-20201205-9 | 53510911 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2020-12-05 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, and 100 roads. | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4906KL-20201205-9L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD4906KL-20201205-9L.O.A.0.6363636155.2727OEWT-PA12-LEM-R1 | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4920 | KL-20201206-7 | 53510911 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-12-06 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44206 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4920KL-20201206-7L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD4920KL-20201206-7L.O.A.0.181818244.3636OEWT-PA12-LEM-R1 | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4920 | KL-20201206-7 | 53510911 | Access | 0 | L.O.A. | 244 | 0.090909 | Day |  | 0 |  |  | 22.1818 | 2.8836 | 25.0654 | 2020-12-06 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44206 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4920KL-20201206-7L.O.A.0.090909122.1818 | KABI LAKE FOREST PRODUCTS LTD4920KL-20201206-7L.O.A.0.090909122.1818OEWT-PA12-LEM-R1 | [5 empty] | 1 | 22.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4936 | KL-20201207-11 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 Roads | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44206 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4936KL-20201207-11L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4936KL-20201207-11L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4936 | KL-20201207-11 | 53510911 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 Roads | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44206 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4936KL-20201207-11L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD4936KL-20201207-11L.O.A.0.4545455110.9091OEWT-PA12-LEM-R1 | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4938 | KL-20201207-13 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 and 700 roads | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44206 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4938KL-20201207-13L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4938KL-20201207-13L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4950 | KL-20201208-8 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-12-08 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 road | 9 | E091-E102 | 600 Road | 0 | 44194 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4950KL-20201208-8L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4950KL-20201208-8L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4950 | KL-20201208-8 | 53510911 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-12-08 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 road | 9 | E091-E102 | 600 Road | 0 | 44194 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4950KL-20201208-8L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD4950KL-20201208-8L.O.A.0.4545455110.9091OEWT-PA12-LEM-R1 | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4952 | KL-20201208-10 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-12-08 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44194 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4952KL-20201208-10L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4952KL-20201208-10L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4970 | KL-20201210-9 | 53510911 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-12-10 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600/700 and 100 Roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4970KL-20201210-9L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD4970KL-20201210-9L.O.A.0.363636488.7273OEWT-PA12-LEM-R1 | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4970 | KL-20201210-9 | 53510911 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-12-10 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600/700 and 100 Roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4970KL-20201210-9L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD4970KL-20201210-9L.O.A.0.181818244.3636OEWT-PA12-LEM-R1 | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4973 | KL-20201210-12 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-12-10 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700, and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4973KL-20201210-12L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4973KL-20201210-12L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4983 | KL-20201213-8 | 53510911 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-12-13 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4983KL-20201213-8L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD4983KL-20201213-8L.O.A.0.9090909221.8182OEWT-PA12-LEM-R1 | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5002 | KL-20201214-5 | 53510911 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5002KL-20201214-5L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD5002KL-20201214-5L.O.A.0.7727273188.5455OEWT-PA12-LEM-R1 | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5004 | KL-20201214-7 | 53510911 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5004KL-20201214-7L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD5004KL-20201214-7L.O.A.0.7272727177.4545OEWT-PA12-LEM-R1 | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5004 | KL-20201214-7 | 53510911 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5004KL-20201214-7L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD5004KL-20201214-7L.O.A.0.272727366.5455OEWT-PA12-LEM-R1 | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5018 | KL-20201215-6 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-12-15 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44198 |  | 53 | 44210 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5018KL-20201215-6L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD5018KL-20201215-6L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5021 | KL-20201215-9 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-12-15 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44198 |  | 53 | 44210 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5021KL-20201215-9L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD5021KL-20201215-9L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5031 | KL-20201216-3 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-12-16 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44210 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5031KL-20201216-3L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD5031KL-20201216-3L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5042 | KL-20201218-3 | 53510911 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-12-18 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700 Roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5042KL-20201218-3L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD5042KL-20201218-3L.O.A.0.5454545133.0909OEWT-PA12-LEM-R1 | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5044 | KL-20201218-5 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-12-18 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700, and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5044KL-20201218-5L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD5044KL-20201218-5L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5056 | KL-20201219-3 | 53510911 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-12-19 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 & 700 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5056KL-20201219-3L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD5056KL-20201219-3L.O.A.0.7272727177.4545OEWT-PA12-LEM-R1 | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5098 | KL-20201217-6 | 53510911 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5098KL-20201217-6L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD5098KL-20201217-6L.O.A.0.5454545133.0909OEWT-PA12-LEM-R1 | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5098 | KL-20201217-6 | 53510911 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5098KL-20201217-6L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD5098KL-20201217-6L.O.A.0.181818244.3636OEWT-PA12-LEM-R1 | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5099 | KL-20201217-7 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5099KL-20201217-7L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD5099KL-20201217-7L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5129 | KL-20201221-4 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-12-21 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader on 600, 700, and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5129KL-20201221-4L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD5129KL-20201221-4L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5130 | KL-20201221-5 | 53510911 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-12-21 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Stripping km 6 Pit | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5130KL-20201221-5L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD5130KL-20201221-5L.O.A.0.5454545133.0909OEWT-PA12-LEM-R1 | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5152 | KL-20201228-3 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-12-28 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44202 |  | 36 | 44213 | [5 empty] | Mike Lecocq | 09 | KABI LAKE FOREST PRODUCTS LTD5152KL-20201228-3L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD5152KL-20201228-3L.O.A.1244OEWT-PA13-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5196 | KL-20210102-3 | 53510911 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-01-02 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 100 road to km5 pit | 9 | E091-E102 | 600 Road | 0 | 44204 |  | 36 | 44217 | [5 empty] | Mike Lecocq | 09 | KABI LAKE FOREST PRODUCTS LTD5196KL-20210102-3L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD5196KL-20210102-3L.O.A.0.363636488.7273OEWT-PA13-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5413 | KL-20210117-1 | 53510911 | Access | 0 | L.O.A. | 244 | 0.090909 | Day |  | 0 |  |  | 22.1818 | 2.8836 | 25.0654 | 2021-01-17 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding hills on 600 Road between km 52 and Km 22, float truck was stuck on 47km hill | 9 | E091-E102 | 600 Road | 0 | 44216 |  | 53 | 44229 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5413KL-20210117-1L.O.A.0.090909122.1818 | KABI LAKE FOREST PRODUCTS LTD5413KL-20210117-1L.O.A.0.090909122.1818OEWT-PA13-LEM | [5 empty] | 1 | 22.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5413 | KL-20210117-1 | 53510911 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-01-17 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding hills on 600 Road between km 52 and Km 22, float truck was stuck on 47km hill | 9 | E091-E102 | 600 Road | 0 | 44216 |  | 53 | 44229 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5413KL-20210117-1L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD5413KL-20210117-1L.O.A.0.363636488.7273OEWT-PA13-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7899 | KL-20220217-4 | 53510911 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2022-02-17 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from Km 9 to Km 25 on 600 Road | 9 | E092-F009 | 600 Road | 0 | 44614 |  | 61 | 44614 | [6 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD7899KL-20220217-4L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7899KL-20220217-4L.O.A.0.7727273188.5455OEWT-PA26-LEM | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7902 | KL-20220218-3 | 53510911 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2022-02-18 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working snow removal from Km 9 to Km 35 on 600 Road | 9 | E092-F009 | 600 Road | 0 | 44614 |  | 61 | 44614 | [6 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD7902KL-20220218-3L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7902KL-20220218-3L.O.A.0.9545455232.9091OEWT-PA26-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7924 | KL-20220224-5 | 53510911 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2022-02-24 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader Starting Working Snow Removal From 9 Km To 12 Km On 600 Road | 9 | E092-F009 | 600 Road | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 09 | KABI LAKE FOREST PRODUCTS LTD7924KL-20220224-5L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD7924KL-20220224-5L.O.A.0.181818244.3636OEWT-PA26-LEM | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7927 | KL-20220225-3 | 53510911 | Access | 0 | L.O.A. | 244 | 1.8182 | Day |  | 0 |  |  | 443.6364 | 57.6727 | 501.3091 | 2022-02-25 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader and dozer finishing snow removal fro 9km to E-182 on 600 Road | 9 | E092-F009 | 600 Raod | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 09 | KABI LAKE FOREST PRODUCTS LTD7927KL-20220225-3L.O.A.1.8181818443.6364 | KABI LAKE FOREST PRODUCTS LTD7927KL-20220225-3L.O.A.1.8181818443.6364OEWT-PA26-LEM | [5 empty] | 1 | 443.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7937 | KL-20220226-3 | 53510911 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2022-02-26 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Float Kabi Dozer from Km 20 on 600 Road to Kabi Yard | 9 | E092-F009 | 600 Road | 0 | 44628 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD7937KL-20220226-3L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7937KL-20220226-3L.O.A.0.272727366.5455 | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7964 | KL-20220303-3 | 53510911 | Access | 0 | L.O.A. | 244 | 0.22727 | Day |  | 0 |  |  | 55.4545 | 7.2091 | 62.6636 | 2022-03-03 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Run Cat 962M Loader From Kabi Yard & Start Snow Removal To E193 On 600 Road | 9 | E092-F009 | 600 Road | 0 | 44630 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD7964KL-20220303-3L.O.A.0.227272755.4545 | KABI LAKE FOREST PRODUCTS LTD7964KL-20220303-3L.O.A.0.227272755.4545 | [5 empty] | 1 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7965 | KL-20220303-4 | 53510911 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2022-03-03 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Float Cat 962M Loader From 7 Km On Anjigami Road To Kabi Yard For Snow Removal To E193 On 600 Road | 9 | E092-F009 | 600 Road | 0 | 44630 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD7965KL-20220303-4L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD7965KL-20220303-4L.O.A.0.409090999.8182 | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7968 | KL-20220304-3 | 53510911 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2022-03-04 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader Finishing Snow Removal To E193 On 600 Road & Run Loader Back To Kabi Yard | 9 | E092-F009 | 600 Road | 0 | 44630 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD7968KL-20220304-3L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD7968KL-20220304-3L.O.A.1244 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1538 | KL-20200520-9 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-05-20 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road to KM 30 | 9 | E091-E102 | 600 Road | 0 | 43976 |  | 15 | 43977 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1538KL-20200520-9L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD1538KL-20200520-9L.O.A.1244OEWT-PA5-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1552 | KL-20200521-4 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-05-21 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road to 40 km | 9 | E091-E102 | 600 Road | 0 | 43977 |  | 15 | 43977 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1552KL-20200521-4L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD1552KL-20200521-4L.O.A.1244OEWT-PA5-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1559 | KL-20200519-3 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-05-19 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start grading 600 Road at Km 9 | 9 | E091-E102 | 600 Road | 0 | 43976 |  | 15 | 43977 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1559KL-20200519-3L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD1559KL-20200519-3L.O.A.1244OEWT-PA5-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1623 | KL-20200531-4 | 53510912 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-05-31 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Unclogg cross drain culverts @13.5, 30.5, 34.2, and 39.5 kms | 9 | E091-E102 | 600 Road | 0 | 43985 |  | 42 | 43986 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1623KL-20200531-4L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD1623KL-20200531-4L.O.A.0.9090909221.8182OEWT-PA6-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1623 | KL-20200531-4 | 53510912 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-05-31 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Unclogg cross drain culverts @13.5, 30.5, 34.2, and 39.5 kms | 9 | E091-E102 | 600 Road | 0 | 43985 |  | 42 | 43986 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1623KL-20200531-4L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD1623KL-20200531-4L.O.A.0.9090909221.8182OEWT-PA6-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1726 | KL-20200614-2 | 53510912 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-06-14 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Unclog cross drain culvert @ 13.5 Km on 600 Road. Ditching and shaping access to E-134. RV-40033 | 9 | E091-E102 | 600 Road | 0 | 44000 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD1726KL-20200614-2L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD1726KL-20200614-2L.O.A.0.181818244.3636OEWT-PA6-LEM | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1726 | KL-20200614-2 | 53510912 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-06-14 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Unclog cross drain culvert @ 13.5 Km on 600 Road. Ditching and shaping access to E-134. RV-40033 | 9 | E091-E102 | 600 Road | 0 | 44000 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD1726KL-20200614-2L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD1726KL-20200614-2L.O.A.0.181818244.3636OEWT-PA6-LEM | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1778 | KL-20200618-4 | 53510912 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-06-18 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 road to 9 KM | 9 | E-091 to E-102 | 600 Road | 0 | 44005 |  | 15 | 44004 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1778KL-20200618-4L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD1778KL-20200618-4L.O.A.0.5454545133.0909OEWT-PA6-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1795 | KL-20200619-5 | 53510912 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2020-06-19 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade sections on 100 Road to 5KM pit for Gravel Haul (2 hours) & 600 Road to 15KM (5 Hours) | 9 | E-091 to E-102 | 600 Road | 0 | 44006 |  | 15 | 44005 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1795KL-20200619-5L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD1795KL-20200619-5L.O.A.0.6363636155.2727OEWT-PA6-LEM | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1829 | KL-20200622-4 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-06-22 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road from 12m to 20km | 9 |  | 600 Road | 0 | 44007 |  | 15 | 44008 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1829KL-20200622-4L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD1829KL-20200622-4L.O.A.1244OEWT-PA6-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1850 | KL-20200623-13 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-06-23 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road from 20 km to 26km | 9 |  | 600 Road | 0 | 44007 |  | 14 | 44009 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD1850KL-20200623-13L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD1850KL-20200623-13L.O.A.1244OEWT-PA6-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1864 | KL-20200624-14 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-06-24 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Approver- William Ouiet, not in data base as of June 27th |  | Approved |  |  | Continue grading 600 road from 25km to 32 km | 9 |  | 600 Road | 0 | 44008 |  | 14 | 44011 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD1864KL-20200624-14L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD1864KL-20200624-14L.O.A.1244OEWT-PA6-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1919 | KL-20200630-8 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-06-30 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road from 31 Km to 40 Km | 9 |  | 600 Road | 0 | 44012 |  | 50 | 44015 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD1919KL-20200630-8L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD1919KL-20200630-8L.O.A.1244OEWT-PA7-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1963 | KL-20200708-10 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-07-08 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Backup - pickup 12 hrs, only allowed 10 - charged for only 10 on LEM |  | Approved |  |  | Grade 600 Road from 9km to 17km | 9 | E-091 to E-102 | 600 Road | 0 | 44025 |  | 50 | 44026 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD1963KL-20200708-10L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD1963KL-20200708-10L.O.A.1244OEWT-PA7-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1973 | KL-20200702-9 | 53510912 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-07-02 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road from 47km to 51km | 9 | E-091 to E-102 | 600 Road | 0 | 44021 |  | 50 | 44027 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD1973KL-20200702-9L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD1973KL-20200702-9L.O.A.0.4545455110.9091OEWT-PA7-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2004 | KL-20200711-10 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-07-11 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road Repair 126 to 128 | 9 | E-091 to E-102 | 600 Road | 0 | 44027 |  | 50 | 44028 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2004KL-20200711-10L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD2004KL-20200711-10L.O.A.1244OEWT-PA7-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2004 | KL-20200711-10 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-07-11 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road Repair 126 to 128 | 9 | E-091 to E-102 | 600 Road | 0 | 44027 |  | 50 | 44028 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2004KL-20200711-10L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD2004KL-20200711-10L.O.A.1244OEWT-PA7-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2005 | KL-20200711-11 | 53510912 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2020-07-11 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 Road from Km17 to Km23 | 9 | E-091 to E-102 | 600 Road` | 0 | 44027 |  | 50 | 44028 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2005KL-20200711-11L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD2005KL-20200711-11L.O.A.0.7727273188.5455OEWT-PA7-LEM | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2029 | KL-20200713-7 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-07-13 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road Repair 126 to 128 | 9 | E-091 to E-102 | 600 Road | 0 | 44027 |  | 50 | 44029 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2029KL-20200713-7L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD2029KL-20200713-7L.O.A.1244OEWT-PA7-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2029 | KL-20200713-7 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-07-13 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road Repair 126 to 128 | 9 | E-091 to E-102 | 600 Road | 0 | 44027 |  | 50 | 44029 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2029KL-20200713-7L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD2029KL-20200713-7L.O.A.1244OEWT-PA7-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2099 | KL-20200717-11 | 53510912 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-07-17 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade E106 Access Road | 9 | E091-E106 | 600 Road | 0 | 44034 |  | 15 | 44034 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2099KL-20200717-11L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD2099KL-20200717-11L.O.A.0.272727366.5455OEWT-PA7-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2128 | KL-20200701-12 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-07-01 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road from 40km to 47km | 9 | E-091 to E-102 | 600 Road | 0 | 44019 |  | 50 | 44020 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2128KL-20200701-12L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD2128KL-20200701-12L.O.A.1244OEWT-PA7-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2176 | KL-20200703-1 | 53510912 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-07-03 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade AU1 Access to E-126/E-124 | 9 | E-091 to E-102 | 600 road | 0 | 44020 |  | 50 | 44020 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2176KL-20200703-1L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD2176KL-20200703-1L.O.A.0.272727366.5455OEWT-PA7-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2180 | KL-20200703-5 | 53510912 | Access | 0 | L.O.A. | 244 | 0.5 | Day |  | 0 |  |  | 122 | 15.86 | 137.86 | 2020-07-03 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 road from 2 Km to 9 Km | 9 | E-091 to E-102 | 600 Road | 0 | 44020 |  | 50 | 44020 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2180KL-20200703-5L.O.A.0.5122 | KABI LAKE FOREST PRODUCTS LTD2180KL-20200703-5L.O.A.0.5122OEWT-PA7-LEM | [5 empty] | 1 | 122 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2237 | KL-20200723-13 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-07-23 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Road from Hwy to Km 10 | 9 | E-091 to E-102 | 600 Road | 0 | 44040 |  | 15 | 44040 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2237KL-20200723-13L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD2237KL-20200723-13L.O.A.1244OEWT-PA7-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2305 | KL-20200729-8 | 53510912 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-07-29 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 road from Hwy to Km 11 | 9 | E091-E102 | 600 Road | 0 | 44047 |  | 14 | 44048 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD2305KL-20200729-8L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD2305KL-20200729-8L.O.A.0.9090909221.8182OEWT-PA8-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2322 | KL-20200730-14 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-07-30 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Hills on 600 road 11km to 53km | 9 | E091-E102 | 600 Road | 0 | 44048 |  | 50 | 44049 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2322KL-20200730-14L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD2322KL-20200730-14L.O.A.1244OEWT-PA8-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2336 | KL-20200731-11 | 53510912 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-07-31 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road 53km to 49km | 9 | E091-E102. | 600 Road | 0 | 44048 |  | 50 | 44049 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2336KL-20200731-11L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD2336KL-20200731-11L.O.A.0.5454545133.0909OEWT-PA8-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2396 | KL-20200808-3 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-08-08 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44057 |  | 47 | 44057 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2396KL-20200808-3L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD2396KL-20200808-3L.O.A.1244OEWT-PA8-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2405 | KL-20200809-5 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-08-09 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44057 |  | 47 | 44058 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2405KL-20200809-5L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD2405KL-20200809-5L.O.A.1244OEWT-PA8-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2412 | KL-20200810-5 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-08-10 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 Road | 9 | E091-E102 | 600 Road | 0 | 44057 |  | 47 | 44058 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2412KL-20200810-5L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD2412KL-20200810-5L.O.A.1244OEWT-PA8-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2419 | KL-20200811-2 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-08-11 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44060 |  | 47 | 44061 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2419KL-20200811-2L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD2419KL-20200811-2L.O.A.1244OEWT-PA8-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2425 | KL-20200812-1 | 53510912 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2020-08-12 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 Road!! | 9 | E091-E102 | 600 Road | 0 | 44060 |  | 47 | 44061 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2425KL-20200812-1L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD2425KL-20200812-1L.O.A.0.6363636155.2727OEWT-PA8-LEM | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2435 | KL-20200813-2 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-08-13 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44062 |  | 47 | 44062 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2435KL-20200813-2L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD2435KL-20200813-2L.O.A.1244OEWT-PA8-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2444 | KL-20200814-4 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-08-14 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44062 |  | 47 | 44062 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2444KL-20200814-4L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD2444KL-20200814-4L.O.A.1244OEWT-PA8-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2449 | KL-20200815-4 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-08-15 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Continue grading 600 Road @ 30 Km to 35 Km | 9 | E091-E102 | 600 Road | 0 | 44062 |  | 15 | 44066 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2449KL-20200815-4L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD2449KL-20200815-4L.O.A.1244OEWT-PA8-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2457 | KL-20200816-4 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-08-16 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E091-E | 600 Road | 0 | 44062 |  | 15 | 44066 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2457KL-20200816-4L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD2457KL-20200816-4L.O.A.1244OEWT-PA8-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2464 | KL-20200817-4 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-08-17 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E091-E102 | 600 Road | 0 | 44063 |  | 15 | 44064 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2464KL-20200817-4L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD2464KL-20200817-4L.O.A.1244OEWT-PA8-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2597 | KL-20200825-6 | 53510912 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2020-08-25 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44072 |  | 15 | 44074 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2597KL-20200825-6L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD2597KL-20200825-6L.O.A.0.8181818199.6364OEWT-PA8-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2605 | KL-20200827-2 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-08-27 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 road from Hwy to 9km | 9 | E091-E102 | 600 Road | 0 | 44074 |  | 15 | 44075 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2605KL-20200827-2L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD2605KL-20200827-2L.O.A.1244OEWT-PA9-Lem-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2606 | KL-20200828-1 | 53510912 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-08-28 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 road from Hwy to 14km | 9 | E091-E102 | 600 Road | 0 | 44076 |  | 15 | 44077 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2606KL-20200828-1L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD2606KL-20200828-1L.O.A.0.7272727177.4545OEWT-PA9-Lem-R1 | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2612 | KL-20200829-3 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-08-29 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44076 |  | 15 | 44077 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2612KL-20200829-3L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD2612KL-20200829-3L.O.A.1244OEWT-PA9-Lem-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2618 | KL-20200830-1 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-08-30 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44076 |  | 47 | 44077 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2618KL-20200830-1L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD2618KL-20200830-1L.O.A.1244OEWT-PA9-Lem-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2635 | KL-20200831-7 | 53510912 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-08-31 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E091-E102 | 600 Road | 0 | 44084 |  | 50 | 44087 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2635KL-20200831-7L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD2635KL-20200831-7L.O.A.0.9090909221.8182OEWT-PA9-Lem-R1 | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2647 | KL-20200901-10 | 53510912 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-09-01 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road Km 31 -33 | 9 | E092-E109 | 600 Road | 0 | 44084 |  | 50 | 44087 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2647KL-20200901-10L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD2647KL-20200901-10L.O.A.0.7272727177.4545OEWT-PA9-Lem-R1 | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2677 | KL-20200903-14 | 53510912 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-09-03 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E091-E102 | 600 Road | 0 | 44084 |  | 50 | 44088 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2677KL-20200903-14L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD2677KL-20200903-14L.O.A.0.7272727177.4545OEWT-PA9-Lem-R1 | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2689 | KL-20200904-10 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-09-04 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44088 |  | 50 | 44089 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2689KL-20200904-10L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD2689KL-20200904-10L.O.A.1244OEWT-PA9-Lem-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2736 | KL-20200907-13 | 53510912 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-09-07 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44089 |  | 15 | 44092 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2736KL-20200907-13L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD2736KL-20200907-13L.O.A.0.7272727177.4545OEWT-PA9-Lem-R1 | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2754 | KL-20200908-15 | 53510912 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-09-08 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44089 |  | 15 | 44092 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2754KL-20200908-15L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD2754KL-20200908-15L.O.A.2488OEWT-PA9-Lem-R1 | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2778 | KL-20200909-19 | 53510912 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-09-09 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44092 |  | 15 | 44092 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2778KL-20200909-19L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD2778KL-20200909-19L.O.A.2488OEWT-PA9-Lem-R1 | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2802 | KL-20200910-18 | 53510912 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-09-10 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44091 |  | 15 | 44094 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2802KL-20200910-18L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD2802KL-20200910-18L.O.A.2488OEWT-PA9-Lem-R1 | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2853 | KL-20200911-20 | 53510912 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-09-11 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44094 |  | 15 | 44095 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2853KL-20200911-20L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD2853KL-20200911-20L.O.A.0.4545455110.9091OEWT-PA9-Lem-R1 | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2853 | KL-20200911-20 | 53510912 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-09-11 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44094 |  | 15 | 44095 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2853KL-20200911-20L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD2853KL-20200911-20L.O.A.0.9090909221.8182OEWT-PA9-Lem-R1 | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2996 | KL-20200917-13 | 53510912 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-09-17 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44097 |  | 15 | 44098 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2996KL-20200917-13L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD2996KL-20200917-13L.O.A.0.9090909221.8182OEWT-PA9-Lem-R1 | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2997 | KL-20200917-14 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-09-17 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Scale pit at 690 | 9 | E-091 to E-102 | 600 Road | 0 | 44097 |  | 15 | 44098 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2997KL-20200917-14L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD2997KL-20200917-14L.O.A.1244OEWT-PA9-Lem-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3059 | KL-20200920-12 | 53510912 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-09-20 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44099 |  | 15 | 44101 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3059KL-20200920-12L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD3059KL-20200920-12L.O.A.0.7272727177.4545OEWT-PA9-Lem-R1 | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3131 | KL-20200922-16 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-09-22 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44103 |  | 15 | 44103 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3131KL-20200922-16L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD3131KL-20200922-16L.O.A.1244OEWT-PA9-Lem-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3171 | KL-20200923-12 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-09-23 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44103 |  | 15 | 44104 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3171KL-20200923-12L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD3171KL-20200923-12L.O.A.1244OEWT-PA9-Lem-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3268 | KL-20200927-12 | 53510912 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-09-27 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 43900 |  | 53 | 43900 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD3268KL-20200927-12L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD3268KL-20200927-12L.O.A.0.363636488.7273OEWT-PA10-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3289 | KL-20200928-12 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-09-28 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E091-E102 | 600 road | 0 | 44109 |  | 15 | 44121 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3289KL-20200928-12L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD3289KL-20200928-12L.O.A.1244OEWT-PA10-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3320 | KL-20200929-11 | 53510912 | Access | 0 | L.O.A. | 244 | 1.4545 | Day |  | 0 |  |  | 354.9091 | 46.1382 | 401.0473 | 2020-09-29 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44109 |  | 50 | 44115 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3320KL-20200929-11L.O.A.1.4545455354.9091 | KABI LAKE FOREST PRODUCTS LTD3320KL-20200929-11L.O.A.1.4545455354.9091OEWT-PA10-LEM | [5 empty] | 1 | 354.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3485 | KL-20201005-10 | 53510912 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-10-05 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Unplug Culverts at km 40 and 48 on 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44123 |  | 15 | 44125 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3485KL-20201005-10L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD3485KL-20201005-10L.O.A.0.5454545133.0909OEWT-PA10-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3487 | KL-20201005-12 | 53510912 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-10-05 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44123 |  | 15 | 44125 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3487KL-20201005-12L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD3487KL-20201005-12L.O.A.0.181818244.3636OEWT-PA10-LEM | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3487 | KL-20201005-12 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-10-05 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44123 |  | 15 | 44125 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3487KL-20201005-12L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD3487KL-20201005-12L.O.A.1244OEWT-PA10-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3517 | KL-20201006-13 | 53510912 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-10-06 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44124 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3517KL-20201006-13L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD3517KL-20201006-13L.O.A.2488OEWT-PA10-LEM | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3555 | KL-20201007-10 | 53510912 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-10-07 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Buncher from E110 to 650 pit and back to E139 | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3555KL-20201007-10L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD3555KL-20201007-10L.O.A.0.4545455110.9091OEWT-PA10-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3598 | KL-20201008-18 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-10-08 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3598KL-20201008-18L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD3598KL-20201008-18L.O.A.1244OEWT-PA10-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3599 | KL-20201008-19 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-10-08 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Stripping 650 pit | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3599KL-20201008-19L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD3599KL-20201008-19L.O.A.1244OEWT-PA10-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3623 | KL-20201009-12 | 53510912 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-10-09 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fix road and spread loads between E173 and E172, Haul gravel to E168 to E171 and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3623KL-20201009-12L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD3623KL-20201009-12L.O.A.0.4545455110.9091OEWT-PA10-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3623 | KL-20201009-12 | 53510912 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-10-09 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fix road and spread loads between E173 and E172, Haul gravel to E168 to E171 and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3623KL-20201009-12L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD3623KL-20201009-12L.O.A.2488OEWT-PA10-LEM | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3624 | KL-20201009-13 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-10-09 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3624KL-20201009-13L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD3624KL-20201009-13L.O.A.1244OEWT-PA10-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3624 | KL-20201009-13 | 53510912 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-10-09 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3624KL-20201009-13L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD3624KL-20201009-13L.O.A.0.5454545133.0909OEWT-PA10-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3647 | KL-20201010-11 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-10-10 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3647KL-20201010-11L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD3647KL-20201010-11L.O.A.1244OEWT-PA10-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3648 | KL-20201010-12 | 53510912 | Access | 0 | L.O.A. | 244 | 5 | Day |  | 0 |  |  | 1220 | 158.6 | 1378.6 | 2020-10-10 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trucks from 650 pit, fix rds, spread loads between E-173, E-172 and haul gravel to E-168/E-171and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3648KL-20201010-12L.O.A.51220 | KABI LAKE FOREST PRODUCTS LTD3648KL-20201010-12L.O.A.51220OEWT-PA10-LEM | [5 empty] | 1 | 1220 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3671 | KL-20201011-11 | 53510912 | Access | 0 | L.O.A. | 244 | 6 | Day |  | 0 |  |  | 1464 | 190.32 | 1654.32 | 2020-10-11 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trucks from 650 pit, fix road and haul gravel to E168 to E171 and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44157 |  | 15 | 44131 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3671KL-20201011-11L.O.A.61464 | KABI LAKE FOREST PRODUCTS LTD3671KL-20201011-11L.O.A.61464OEWT-PA10-LEM | [5 empty] | 1 | 1464 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3691 | KL-20201012-9 | 53510912 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2020-10-12 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float and use log loader to unclog culverts @ 49km on 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44126 |  | 15 | 44132 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3691KL-20201012-9L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD3691KL-20201012-9L.O.A.0.6363636155.2727OEWT-PA10-LEM | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3691 | KL-20201012-9 | 53510912 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-10-12 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float and use log loader to unclog culverts @ 49km on 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44126 |  | 15 | 44132 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3691KL-20201012-9L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD3691KL-20201012-9L.O.A.0.363636488.7273OEWT-PA10-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3698 | KL-20201012-16 | 53510912 | Access | 0 | L.O.A. | 244 | 6 | Day |  | 0 |  |  | 1464 | 190.32 | 1654.32 | 2020-10-12 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trucks from 650 pit, fix roads and haul gravel to E168 to E171 and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44126 |  | 15 | 44132 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3698KL-20201012-16L.O.A.61464 | KABI LAKE FOREST PRODUCTS LTD3698KL-20201012-16L.O.A.61464OEWT-PA10-LEM | [5 empty] | 1 | 1464 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3717 | KL-20201013-11 | 53510912 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-10-13 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44129 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3717KL-20201013-11L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD3717KL-20201013-11L.O.A.2488OEWT-PA10-LEM | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3741 | KL-20201014-12 | 53510912 | Access | 0 | L.O.A. | 244 | 4 | Day |  | 0 |  |  | 976 | 126.88 | 1102.88 | 2020-10-14 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load Trucks from 650 pit, fix roads and haul gravel to E168 to E171 and spread over corduroy, install cross drain at F6. | 9 | E-091 to E-102 | 600 Road | 0 | 44129 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3741KL-20201014-12L.O.A.4976 | KABI LAKE FOREST PRODUCTS LTD3741KL-20201014-12L.O.A.4976OEWT-PA10-LEM | [5 empty] | 1 | 976 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3741 | KL-20201014-12 | 53510912 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-10-14 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load Trucks from 650 pit, fix roads and haul gravel to E168 to E171 and spread over corduroy, install cross drain at F6. | 9 | E-091 to E-102 | 600 Road | 0 | 44129 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3741KL-20201014-12L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD3741KL-20201014-12L.O.A.0.181818244.3636OEWT-PA10-LEM | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3743 | KL-20201014-14 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-10-14 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44129 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3743KL-20201014-14L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD3743KL-20201014-14L.O.A.1244OEWT-PA10-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3765 | KL-20201015-13 | 53510912 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-10-15 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trucks from 650 pit and 25km pit, fix roads and hauled gravel to E168-E171 and spread over Corduroy, pile up gravel at Km33 | 9 | E-091 to E-102 | 600 Road | 0 | 44130 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3765KL-20201015-13L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD3765KL-20201015-13L.O.A.2488OEWT-PA10-LEM | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3765 | KL-20201015-13 | 53510912 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-10-15 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trucks from 650 pit and 25km pit, fix roads and hauled gravel to E168-E171 and spread over Corduroy, pile up gravel at Km33 | 9 | E-091 to E-102 | 600 Road | 0 | 44130 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3765KL-20201015-13L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD3765KL-20201015-13L.O.A.0.9090909221.8182OEWT-PA10-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3792 | KL-20201016-10 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-10-16 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44130 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3792KL-20201016-10L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD3792KL-20201016-10L.O.A.1244OEWT-PA10-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3845 | KL-20201019-10 | 53510912 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-10-19 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44130 |  | 50 | 44133 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3845KL-20201019-10L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD3845KL-20201019-10L.O.A.0.7272727177.4545OEWT-PA10-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3845 | KL-20201019-10 | 53510912 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-10-19 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44130 |  | 50 | 44133 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3845KL-20201019-10L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD3845KL-20201019-10L.O.A.0.4545455110.9091OEWT-PA10-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3877 | KL-20201021-6 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-10-21 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44131 |  | 15 | 44133 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3877KL-20201021-6L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD3877KL-20201021-6L.O.A.1244OEWT-PA10-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3888 | KL-20201023-7 | 53510912 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2020-10-23 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44133 |  | 50 | 44134 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3888KL-20201023-7L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD3888KL-20201023-7L.O.A.0.6363636155.2727OEWT-PA10-LEM | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3914 | KL-20201022-7 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-10-22 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44133 |  | 15 | 44134 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3914KL-20201022-7L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD3914KL-20201022-7L.O.A.1244OEWT-PA10-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3990 | KL-20201026-15 | 53510912 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-10-26 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E091-E102 | 600 Rd | 0 | 44147 |  | 50 | 44161 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3990KL-20201026-15L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD3990KL-20201026-15L.O.A.2488OEWT-PA11-LEM | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4005 | KL-20201027-10 | 53510912 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-10-27 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E091-E102 | 600 Rd | 0 | 44147 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4005KL-20201027-10L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD4005KL-20201027-10L.O.A.2488OEWT-PA11-LEM | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4021 | KL-20201028-8 | 53510912 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-10-28 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E091-E102 | 600 Rd | 0 | 44147 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4021KL-20201028-8L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD4021KL-20201028-8L.O.A.2488OEWT-PA11-LEM | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4048 | KL-20201029-14 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-10-29 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E091-E102 | 600 Rd | 0 | 44152 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4048KL-20201029-14L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4048KL-20201029-14L.O.A.1244OEWT-PA11-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4064 | KL-20201030-6 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-10-30 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fix Roads between E95 to E102 | 9 | E091-E102 | 600 Rd | 0 | 44152 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4064KL-20201030-6L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4064KL-20201030-6L.O.A.1244OEWT-PA11-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4065 | KL-20201030-7 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-10-30 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Paint Lake Road 2 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44152 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4065KL-20201030-7L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4065KL-20201030-7L.O.A.1244OEWT-PA11-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4073 | KL-20201030-15 | 53510912 | Access | 0 | L.O.A. | 244 | 1.5455 | Day |  |  |  |  | 377.0909 | 49.0218 | 426.1127 | 2020-10-30 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding the 600 road and 700 road to Km 13 ( Revised Hours) | 9 | E091-E102 | 600 Rd | 0 | 44152 |  | 56 | 44163 | [5 empty] | Mandy Sandhu | 09 | KABI LAKE FOREST PRODUCTS LTD4073KL-20201030-15L.O.A.1.5454545377.0909 | KABI LAKE FOREST PRODUCTS LTD4073KL-20201030-15L.O.A.1.5454545377.0909OEWT-PA11-LEM | [5 empty] | 1 | 377.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4101 | KL-20201101-10 | 53510912 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  |  |  |  | 44.3636 | 5.7673 | 50.1309 | 2020-11-01 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Move cat 335F Excavator to 6km on 600 Rd for loading of road maintenace sand | 9 | E091-E102 | 600 Rd | 0 | 44153 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4101KL-20201101-10L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD4101KL-20201101-10L.O.A.0.181818244.3636OEWT-PA11-LEM | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4164 | KL-20201104-19 | 53510912 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-11-04 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Rd | 9 | E091-E102 | 600 Road | 0 | 44160 |  | 50 | 44163 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4164KL-20201104-19L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD4164KL-20201104-19L.O.A.0.9090909221.8182OEWT-PA11-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4174 | KL-20201105-8 | 53510912 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-11-05 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float buncher from E122, E124 to E165 | 9 | E091-E102 | 600 Road | 0 | 44160 |  | 56 | 44163 | [5 empty] | Mandy Sandhu | 09 | KABI LAKE FOREST PRODUCTS LTD4174KL-20201105-8L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD4174KL-20201105-8L.O.A.0.272727366.5455OEWT-PA11-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4182 | KL-20201105-16 | 53510912 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-11-05 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float D6 fro Km 32 600 road to Km57 and 336 from 650 pit to km52 F216 | 9 | E091-E102 | 600 Road | 0 | 44160 |  | 50 | 44163 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4182KL-20201105-16L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD4182KL-20201105-16L.O.A.0.4545455110.9091OEWT-PA11-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4183 | KL-20201105-17 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-11-05 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road , 700 road and 100 road | 9 | E091-E102 | 600 Road | 0 | 44160 |  | 50 | 44163 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4183KL-20201105-17L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4183KL-20201105-17L.O.A.1244OEWT-PA11-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4199 | KL-20201106-11 | 53510912 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-11-06 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road and 100 road | 9 | E091-E102 | 600 Road | 0 | 44162 |  | 48 | 44162 | [5 empty] | Larse Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4199KL-20201106-11L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD4199KL-20201106-11L.O.A.0.7272727177.4545OEWT-PA11-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4237 | KL-20201108-16 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-11-08 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44162 |  | 50 | 44163 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4237KL-20201108-16L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4237KL-20201108-16L.O.A.1244OEWT-PA11-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4263 | KL-20201109-12 | 53510912 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-11-09 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E091-E102 | 600 Road | 0 | 44164 |  | 15 | 44171 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4263KL-20201109-12L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD4263KL-20201109-12L.O.A.2488OEWT-PA11-LEM | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4288 | KL-20201103-17 | 53510912 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road, 700 road and 100 road | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 50 | 44167 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4288KL-20201103-17L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD4288KL-20201103-17L.O.A.0.7272727177.4545OEWT-PA11-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4288 | KL-20201103-17 | 53510912 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road, 700 road and 100 road | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 50 | 44167 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4288KL-20201103-17L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD4288KL-20201103-17L.O.A.0.9090909221.8182OEWT-PA11-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4298 | KL-20201110-8 | 53510912 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-11-10 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Rd 2 graders | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44168 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4298KL-20201110-8L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD4298KL-20201110-8L.O.A.2488OEWT-PA11-LEM | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4316 | KL-20201111-12 | 53510912 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-11-11 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road and 100 Road | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44170 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4316KL-20201111-12L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD4316KL-20201111-12L.O.A.2488OEWT-PA11-LEM | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4329 | KL-20201112-12 | 53510912 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-11-12 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road and 100 Road | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44168 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4329KL-20201112-12L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD4329KL-20201112-12L.O.A.2488OEWT-PA11-LEM | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4340 | KL-20201113-8 | 53510912 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-11-13 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600rd and 100rd | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44170 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4340KL-20201113-8L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD4340KL-20201113-8L.O.A.2488OEWT-PA11-LEM | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4359 | KL-20201114-12 | 53510912 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-11-14 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float D6 from F9 to E168 to shape roads | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4359KL-20201114-12L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD4359KL-20201114-12L.O.A.0.363636488.7273OEWT-PA11-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4360 | KL-20201114-13 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-11-14 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4360KL-20201114-13L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4360KL-20201114-13L.O.A.1244OEWT-PA11-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4397 | KL-20201115-11 | 53510912 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-11-15 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road and 100 Road. | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 53 | 44171 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4397KL-20201115-11L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD4397KL-20201115-11L.O.A.2488OEWT-PA11-LEM | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4415 | KL-20201116-14 | 53510912 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fix roads E168 to E171 and E212 to E210 | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4415KL-20201116-14L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD4415KL-20201116-14L.O.A.0.5454545133.0909OEWT-PA11-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4415 | KL-20201116-14 | 53510912 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fix roads E168 to E171 and E212 to E210 | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4415KL-20201116-14L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD4415KL-20201116-14L.O.A.0.5454545133.0909OEWT-PA11-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4416 | KL-20201116-15 | 53510912 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road, 100 road, Paint Lake 2 Rd | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4416KL-20201116-15L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD4416KL-20201116-15L.O.A.2488OEWT-PA11-LEM | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4431 | KL-20201117-10 | 53510912 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-11-17 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 rd, 100 rd, and Paint Lake 2 road | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4431KL-20201117-10L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD4431KL-20201117-10L.O.A.2488OEWT-PA11-LEM | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4463 | KL-20201119-9 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-11-19 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shaping up and back blading access roads E217 to E194 | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4463KL-20201119-9L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4463KL-20201119-9L.O.A.1244OEWT-PA11-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4573 | KL-20201123-11 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-11-23 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shaping up and back blading access roads and pulling a drag F3 and F9 | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 15 | 44175 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4573KL-20201123-11L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4573KL-20201123-11L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4575 | KL-20201123-13 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-11-23 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Contine grading 600 road and 100 roadand access roads in WF 9 | 9 | E091-E102 | 600 road | 0 | 44172 |  | 15 | 44176 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4575KL-20201123-13L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4575KL-20201123-13L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4605 | KL-20201124-8 | 53510912 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2020-11-24 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shaping up and back blading access road and pulling a drag F3, F9 | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4605KL-20201124-8L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD4605KL-20201124-8L.O.A.0.8181818199.6364OEWT-PA12-LEM-R1 | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4607 | KL-20201124-10 | 53510912 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-11-24 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road, 100 road and access roads in WF 9 | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4607KL-20201124-10L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD4607KL-20201124-10L.O.A.0.9090909221.8182OEWT-PA12-LEM-R1 | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4634 | KL-20201125-11 | 53510912 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600rd, 100rd, and access rds in WF9 | 9 | E091-E102 | 600 Road | 0 | 44173 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4634KL-20201125-11L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD4634KL-20201125-11L.O.A.0.7272727177.4545OEWT-PA12-LEM-R1 | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4634 | KL-20201125-11 | 53510912 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600rd, 100rd, and access rds in WF9 | 9 | E091-E102 | 600 Road | 0 | 44173 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4634KL-20201125-11L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD4634KL-20201125-11L.O.A.0.9090909221.8182OEWT-PA12-LEM-R1 | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4637 | KL-20201125-14 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shaping up and back blading access roads and pulling a drag F3-F9 | 9 | E091-E102 | 600 Road | 0 | 44173 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4637KL-20201125-14L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4637KL-20201125-14L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6903 | KL-20210511-3 | 53510912 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2021-05-11 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float 250 link belt log loader from mill yard to 13km on 600 road/unplug culvert and float log loader back to mill yard | 9 | E091-E102 | 600 Road | 0 | 44337 |  | 56 | 44341 | [5 empty] | Mandy Sandhu | 09 | KABI LAKE FOREST PRODUCTS LTD6903KL-20210511-3L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD6903KL-20210511-3L.O.A.0.272727366.5455OEWT-PA17-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6903 | KL-20210511-3 | 53510912 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2021-05-11 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float 250 link belt log loader from mill yard to 13km on 600 road/unplug culvert and float log loader back to mill yard | 9 | E091-E102 | 600 Road | 0 | 44337 |  | 56 | 44341 | [5 empty] | Mandy Sandhu | 09 | KABI LAKE FOREST PRODUCTS LTD6903KL-20210511-3L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD6903KL-20210511-3L.O.A.0.272727366.5455OEWT-PA17-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6949 | KL-20210518-6 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2021-05-18 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T dozer leveling ruts and shaping road E200 to E216/ Supervisor while checking on Operator and process did pickup shuffle (Revised) | 9 | E091-E102 | 600 Road | 0 | 44345 |  | 14 | 44349 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD6949KL-20210518-6L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD6949KL-20210518-6L.O.A.1244OEWT-PA17-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6953 | KL-20210519-4 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2021-05-19 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 14M grader started road maintenance from Km 1 to Km 18 on 600 road labourers spotted pickup @Km 18 for grader operator (revised) | 9 | E091-E102 | 600 Road | 0 | 44345 |  | 14 | 44352 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD6953KL-20210519-4L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD6953KL-20210519-4L.O.A.1244OEWT-PA17-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6962 | KL-20210520-4 | 53510912 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 14M grader continuing grading of 600 road and repairing small wash out/ labourer spotting pickup @ 22km for grader operator ( revised ) | 9 | E091-E102 | 600 Road | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD6962KL-20210520-4L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD6962KL-20210520-4L.O.A.1244OEWT-PA17-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6968 | KL-20210521-3 | 53510912 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-05-21 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 14M grader continuing grading of 600 Road and repairing small wash outs | 9 | E091-E102 | 600 Road | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD6968KL-20210521-3L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD6968KL-20210521-3L.O.A.0.7727273188.5455OEWT-PA17-LEM | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6985 | KL-20210525-3 | 53510912 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2021-05-25 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 14M grader continuing grading of 600 road and repairing small washouts | 9 | E091-E102 | 600 Road | 0 | 44348 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 09 | KABI LAKE FOREST PRODUCTS LTD6985KL-20210525-3L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD6985KL-20210525-3L.O.A.0.409090999.8182OEWT-PA17-LEM | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7494 | KL-20211026-3 | 53510912 | Access | 0 | L.O.A. | 244 | 0.31818 | Day |  | 0 |  |  | 77.6364 | 10.0927 | 87.7291 | 2021-10-26 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Skagen Volvo Grader from Hensen Road for grading of the 600 Road. Grade from Km 1 on Paint Lake Road 2 to Km 52 on 600 road and grade towards Km 49 - SSF-14419 | 9 | E032-F009 | 600 Road | 0 | 44501 |  | 61 | 44502 | [6 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD7494KL-20211026-3L.O.A.0.318181877.6364 | KABI LAKE FOREST PRODUCTS LTD7494KL-20211026-3L.O.A.0.318181877.6364OEWT-PA23-Lem | [5 empty] | 1 | 77.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511003 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-09-20 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44466 |  | 50 | 44466 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1L.O.A.0.8636364210.7273OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.59731 | 125.8698 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511003 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-09-20 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44466 |  | 50 | 44466 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1L.O.A.0.7272727177.4545OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.59731 | 105.9955 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7361 | KL-20210919-1 | 53511003 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-19 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km and pulling pickups @ end of shift /Chapman rock truck hauling trees from F104 to Morin @ km 41 and 42. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44466 |  | 50 | 44466 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7379 | KL-20210923-1 | 53511003 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-23 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees@ 18 km, excavator 2 placing trees/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 61 | 44471 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7379 | KL-20210923-1 | 53511003 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-23 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees@ 18 km, excavator 2 placing trees/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 61 | 44471 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7379 | KL-20210923-1 | 53511003 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-23 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees@ 18 km, excavator 2 placing trees/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 61 | 44471 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7379 | KL-20210923-1 | 53511003 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-23 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees@ 18 km, excavator 2 placing trees/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 61 | 44471 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7384 | KL-20210924-1 | 53511003 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-24 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees, excavator 2 placing trees @km 16.5 and Km 21 hill/Chapman rock truck hauling Gravel From km 38 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 50 | 44470 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.51268 | 102.3497 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7384 | KL-20210924-1 | 53511003 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-24 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees, excavator 2 placing trees @km 16.5 and Km 21 hill/Chapman rock truck hauling Gravel From km 38 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 50 | 44470 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.51268 | 102.3497 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7200 | KL-20210804-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-04 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load existing material from 17Km on Hensen Road & Gravel road sections @ 46/45Km on Paint Lake road 2 as per Valard. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7200KL-20210804-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7200KL-20210804-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7200 | KL-20210804-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-04 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load existing material from 17Km on Hensen Road & Gravel road sections @ 46/45Km on Paint Lake road 2 as per Valard. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7200KL-20210804-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7200KL-20210804-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7200 | KL-20210804-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-04 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load existing material from 17Km on Hensen Road & Gravel road sections @ 46/45Km on Paint Lake road 2 as per Valard. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7200KL-20210804-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7200KL-20210804-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7201 | KL-20210808-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-08 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading existing material from 17Km on Hensen Road & Gravel road sections @ 46/44Km on Paint Lake road 2 as per Valard. 1 Kabi Rock Truck & 2 Valard Rock Trucks Hauling | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7201KL-20210808-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7201KL-20210808-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7201 | KL-20210808-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-08 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading existing material from 17Km on Hensen Road & Gravel road sections @ 46/44Km on Paint Lake road 2 as per Valard. 1 Kabi Rock Truck & 2 Valard Rock Trucks Hauling | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7201KL-20210808-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7201KL-20210808-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7201 | KL-20210808-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-08 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading existing material from 17Km on Hensen Road & Gravel road sections @ 46/44Km on Paint Lake road 2 as per Valard. 1 Kabi Rock Truck & 2 Valard Rock Trucks Hauling | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7201KL-20210808-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7201KL-20210808-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7202 | KL-20210805-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-05 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading existing material from 17Km on Hensen Road & Gravel road sections @ 45/44Km on Paint Lake road 2 as per Valard. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7202KL-20210805-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7202KL-20210805-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7202 | KL-20210805-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-05 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading existing material from 17Km on Hensen Road & Gravel road sections @ 45/44Km on Paint Lake road 2 as per Valard. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7202KL-20210805-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7202KL-20210805-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7202 | KL-20210805-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-05 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading existing material from 17Km on Hensen Road & Gravel road sections @ 45/44Km on Paint Lake road 2 as per Valard. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7202KL-20210805-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7202KL-20210805-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7204 | KL-20210806-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-06 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading existing material from 17Km on Hensen Road & Gravel road sections @ 46/44Km on Paint Lake road 2 as per Valard. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7204KL-20210806-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7204KL-20210806-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7204 | KL-20210806-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-06 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading existing material from 17Km on Hensen Road & Gravel road sections @ 46/44Km on Paint Lake road 2 as per Valard. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7204KL-20210806-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7204KL-20210806-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7204 | KL-20210806-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-06 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading existing material from 17Km on Hensen Road & Gravel road sections @ 46/44Km on Paint Lake road 2 as per Valard. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7204KL-20210806-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7204KL-20210806-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7207 | KL-20210809-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-09 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/loading mats on Valard Rock truck. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7207KL-20210809-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7207KL-20210809-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7207 | KL-20210809-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-09 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/loading mats on Valard Rock truck. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7207KL-20210809-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7207KL-20210809-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7207 | KL-20210809-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-09 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/loading mats on Valard Rock truck. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7207KL-20210809-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7207KL-20210809-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7211 | KL-20210810-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-10 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/loading mats on Valard Rock truck. | 10 | F033-F118 | Paint Lake Road2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7211KL-20210810-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7211KL-20210810-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7211 | KL-20210810-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-10 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/loading mats on Valard Rock truck. | 10 | F033-F118 | Paint Lake Road2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7211KL-20210810-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7211KL-20210810-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7211 | KL-20210810-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-10 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/loading mats on Valard Rock truck. | 10 | F033-F118 | Paint Lake Road2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7211KL-20210810-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7211KL-20210810-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7212 | KL-20210811-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-11 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 45/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/2 Valard Rock truck. Continue grading Paint Lake Road 2 from Km 7.5 to Km 11.5 - SSF-14324 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7212KL-20210811-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7212KL-20210811-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7212 | KL-20210811-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-11 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 45/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/2 Valard Rock truck. Continue grading Paint Lake Road 2 from Km 7.5 to Km 11.5 - SSF-14324 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7212KL-20210811-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7212KL-20210811-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7212 | KL-20210811-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-11 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 45/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/2 Valard Rock truck. Continue grading Paint Lake Road 2 from Km 7.5 to Km 11.5 - SSF-14324 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7212KL-20210811-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7212KL-20210811-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7213 | KL-20210812-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-12 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel access mat sections @ 45/44 km on Paint Lake Road 2/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on Valard 2nd rock truck. Finish grading Paint Lake Road 2 to Km 13 and touch up on way out to Paint Lake Road - SSF-14325 | 10 | F033-F118 | Paint ake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7213KL-20210812-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7213KL-20210812-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7213 | KL-20210812-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.68182 | Day |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2021-08-12 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel access mat sections @ 45/44 km on Paint Lake Road 2/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on Valard 2nd rock truck. Finish grading Paint Lake Road 2 to Km 13 and touch up on way out to Paint Lake Road - SSF-14325 | 10 | F033-F118 | Paint ake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7213KL-20210812-1L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD7213KL-20210812-1L.O.A.0.6818182166.3636OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 166.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7213 | KL-20210812-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-08-12 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel access mat sections @ 45/44 km on Paint Lake Road 2/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on Valard 2nd rock truck. Finish grading Paint Lake Road 2 to Km 13 and touch up on way out to Paint Lake Road - SSF-14325 | 10 | F033-F118 | Paint ake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7213KL-20210812-1L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7213KL-20210812-1L.O.A.0.7727273188.5455OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7214 | KL-20210813-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-13 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on 2nd Valard Rock truck | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7214KL-20210813-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7214KL-20210813-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7214 | KL-20210813-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-13 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on 2nd Valard Rock truck | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7214KL-20210813-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7214KL-20210813-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7214 | KL-20210813-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-13 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on 2nd Valard Rock truck | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7214KL-20210813-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7214KL-20210813-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7215 | KL-20210814-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-14 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/43 km/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on 2nd Valard Rock truck/Excavator working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7215KL-20210814-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7215KL-20210814-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7215 | KL-20210814-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-14 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/43 km/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on 2nd Valard Rock truck/Excavator working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7215KL-20210814-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7215KL-20210814-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7215 | KL-20210814-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-14 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/43 km/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on 2nd Valard Rock truck/Excavator working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7215KL-20210814-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7215KL-20210814-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7218 | KL-20210815-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-15 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/43 km/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on 2nd Valard Rock truck/Excavator 2 working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7218KL-20210815-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7218KL-20210815-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7218 | KL-20210815-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-15 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/43 km/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on 2nd Valard Rock truck/Excavator 2 working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7218KL-20210815-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7218KL-20210815-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7218 | KL-20210815-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-15 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/43 km/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on 2nd Valard Rock truck/Excavator 2 working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7218KL-20210815-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7218KL-20210815-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7221 | KL-20210816-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-08-16 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/43 km/ 1 Kabi Rock Truck, Corbiere and Valard Rock truck/Excavator 2 working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7221KL-20210816-1L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7221KL-20210816-1L.O.A.0.7727273188.5455OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7221 | KL-20210816-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-08-16 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/43 km/ 1 Kabi Rock Truck, Corbiere and Valard Rock truck/Excavator 2 working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7221KL-20210816-1L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7221KL-20210816-1L.O.A.0.7727273188.5455OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7221 | KL-20210816-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-08-16 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/43 km/ 1 Kabi Rock Truck, Corbiere and Valard Rock truck/Excavator 2 working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7221KL-20210816-1L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7221KL-20210816-1L.O.A.0.7727273188.5455OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7224 | KL-20210817-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-17 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/46 km/ 1 Kabi Rock Truck, Corbiere and Valard Rock truck/Excavator 2 working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7224KL-20210817-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7224KL-20210817-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7224 | KL-20210817-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-17 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/46 km/ 1 Kabi Rock Truck, Corbiere and Valard Rock truck/Excavator 2 working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7224KL-20210817-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7224KL-20210817-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7224 | KL-20210817-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-17 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/46 km/ 1 Kabi Rock Truck, Corbiere and Valard Rock truck/Excavator 2 working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7224KL-20210817-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7224KL-20210817-1L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7248 | KL-20210819-4 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-19 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44433 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7248KL-20210819-4L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7248KL-20210819-4L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7248 | KL-20210819-4 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-19 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44433 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7248KL-20210819-4L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7248KL-20210819-4L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7248 | KL-20210819-4 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-19 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44433 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7248KL-20210819-4L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7248KL-20210819-4L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7252 | KL-20210820-5 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-20 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44433 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-5L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-5L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7252 | KL-20210820-5 | 53511004 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-08-20 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44433 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-5L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-5L.O.A.0.7272727177.4545OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7252 | KL-20210820-5 | 53511004 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-08-20 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44433 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-5L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-5L.O.A.0.7272727177.4545OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7257 | KL-20210821-5 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-21 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/46/3 rock trucks Kabi, Corbiere and Valard/ 2nd Ex working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44434 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-5L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-5L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7257 | KL-20210821-5 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-21 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/46/3 rock trucks Kabi, Corbiere and Valard/ 2nd Ex working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44434 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-5L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-5L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7257 | KL-20210821-5 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-21 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/46/3 rock trucks Kabi, Corbiere and Valard/ 2nd Ex working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44434 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-5L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-5L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7267 | KL-20210822-4 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-22 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/4. One Kabi rock truck, one Corbiere, and 1 Valard. 2nd excavator working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 50 | 44440 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-4L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-4L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7267 | KL-20210822-4 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-22 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/4. One Kabi rock truck, one Corbiere, and 1 Valard. 2nd excavator working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 50 | 44440 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-4L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-4L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7267 | KL-20210822-4 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-22 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/4. One Kabi rock truck, one Corbiere, and 1 Valard. 2nd excavator working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 50 | 44440 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-4L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-4L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7271 | KL-20210823-5 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-23 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/44. One Kabi rock truck, Corbiere and Valard/ 2nd Ex working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 37 | 44439 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-5L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-5L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7271 | KL-20210823-5 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-23 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/44. One Kabi rock truck, Corbiere and Valard/ 2nd Ex working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 37 | 44439 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-5L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-5L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7271 | KL-20210823-5 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-23 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/44. One Kabi rock truck, Corbiere and Valard/ 2nd Ex working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 37 | 44439 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-5L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-5L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7275 | KL-20210824-3 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-24 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from km 17 on Hensen Road to Corbiere Dozer@km 44.5/43.5/3 rock trucks Kabi, Corbiere and Valard/ Excavator 2 working ahead @km 42 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-3L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7275 | KL-20210824-3 | 53511004 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-08-24 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from km 17 on Hensen Road to Corbiere Dozer@km 44.5/43.5/3 rock trucks Kabi, Corbiere and Valard/ Excavator 2 working ahead @km 42 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-3L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-3L.O.A.0.4545455110.9091OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7275 | KL-20210824-3 | 53511004 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-08-24 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from km 17 on Hensen Road to Corbiere Dozer@km 44.5/43.5/3 rock trucks Kabi, Corbiere and Valard/ Excavator 2 working ahead @km 42 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-3L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-3L.O.A.0.4545455110.9091OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7285 | KL-20210828-3 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-28 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from km49 to Skagen excavator @ 46/45 km - 1 Kabi , 1 Chapman and 2 Cobiere rock trucks | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7285KL-20210828-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7285KL-20210828-3L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7285 | KL-20210828-3 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-28 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from km49 to Skagen excavator @ 46/45 km - 1 Kabi , 1 Chapman and 2 Cobiere rock trucks | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7285KL-20210828-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7285KL-20210828-3L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7288 | KL-20210830-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-30 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks/ excavator 2 shaping and leveling slopes | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44439 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-Access |  | 0 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7288 | KL-20210830-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-30 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks/ excavator 2 shaping and leveling slopes | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44439 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-Access |  | 0 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7292 | KL-20210831-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-08-31 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from 49 Km to 44/43Km. 1 Kabi rock truck, 2 Corbiere Rock Trucks & 1 Chapman Rock Truck. Excavator 2 tracking from 49Km to F-086 for gravel haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44442 |  | 37 | 44445 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-2L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-2L.O.A.0.7727273188.5455OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7292 | KL-20210831-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-08-31 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from 49 Km to 44/43Km. 1 Kabi rock truck, 2 Corbiere Rock Trucks & 1 Chapman Rock Truck. Excavator 2 tracking from 49Km to F-086 for gravel haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44442 |  | 37 | 44445 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-2L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-2L.O.A.0.7727273188.5455OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7292 | KL-20210831-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-08-31 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from 49 Km to 44/43Km. 1 Kabi rock truck, 2 Corbiere Rock Trucks & 1 Chapman Rock Truck. Excavator 2 tracking from 49Km to F-086 for gravel haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44442 |  | 37 | 44445 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-2L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-2L.O.A.0.7727273188.5455OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7307 | KL-20210901-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-01 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from @ km49 to Skagen excavator @ km 43/ 2 Kabi , 1 Chapman and 3 Cobiere rock trucks/ excavator 2 preping access @km 35 to 34 for gravel Haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 37 | 44457 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7307 | KL-20210901-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-09-01 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from @ km49 to Skagen excavator @ km 43/ 2 Kabi , 1 Chapman and 3 Cobiere rock trucks/ excavator 2 preping access @km 35 to 34 for gravel Haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 37 | 44457 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-2L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-2L.O.A.0.7272727177.4545OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7307 | KL-20210901-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-01 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from @ km49 to Skagen excavator @ km 43/ 2 Kabi , 1 Chapman and 3 Cobiere rock trucks/ excavator 2 preping access @km 35 to 34 for gravel Haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 37 | 44457 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7307 | KL-20210901-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2021-09-01 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from @ km49 to Skagen excavator @ km 43/ 2 Kabi , 1 Chapman and 3 Cobiere rock trucks/ excavator 2 preping access @km 35 to 34 for gravel Haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 37 | 44457 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-2L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-2L.O.A.0.6363636155.2727OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7311 | KL-20210902-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-02 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from 38.5 km Morin excavator @ km 40/41 for road capping | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 37 | 44457 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7311KL-20210902-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7311KL-20210902-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7311 | KL-20210902-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-02 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from 38.5 km Morin excavator @ km 40/41 for road capping | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 37 | 44457 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7311KL-20210902-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7311KL-20210902-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7311 | KL-20210902-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  |  |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-02 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from 38.5 km Morin excavator @ km 40/41 for road capping | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 37 | 44457 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7311KL-20210902-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7311KL-20210902-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7312 | KL-20210903-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-03 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from 38.5 km Morin excavator @ km 40/41 for road capping | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 50 | 44450 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7312KL-20210903-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7312KL-20210903-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7312 | KL-20210903-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-09-03 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from 38.5 km Morin excavator @ km 40/41 for road capping | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 50 | 44450 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7312KL-20210903-2L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7312KL-20210903-2L.O.A.0.7272727177.4545OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7312 | KL-20210903-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-09-03 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from 38.5 km Morin excavator @ km 40/41 for road capping | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 50 | 44450 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7312KL-20210903-2L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7312KL-20210903-2L.O.A.0.7272727177.4545OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7330 | KL-20210910-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-10 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 12 and Km 5 to Km 19 / 1 rock truck hauling from 38 km to Morin Excavator @ 40/42 km/rock truck 2 driving from Hwy to Km 38 and haul gravel | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44454 |  | 50 | 44462 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.81072 | 161.8498 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7330 | KL-20210910-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-09-10 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 12 and Km 5 to Km 19 / 1 rock truck hauling from 38 km to Morin Excavator @ 40/42 km/rock truck 2 driving from Hwy to Km 38 and haul gravel | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44454 |  | 50 | 44462 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-2L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-2L.O.A.0.4545455110.9091OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.81072 | 89.9165 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7332 | KL-20210911-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.77276 | Day |  | 0 |  |  | 188.5528 | 24.5119 | 213.0647 | 2021-09-11 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck hauling from km 38 to km 40 with Skagen and Morin/Kabi rock truck driving from km .5 on Hensen to km 38 for gravel haul | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44460 |  | 50 | 44462 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2L.O.A.0.7727573188.5528 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2L.O.A.0.7727573188.5528OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.71555 | 134.9189 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7332 | KL-20210911-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-09-11 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck hauling from km 38 to km 40 with Skagen and Morin/Kabi rock truck driving from km .5 on Hensen to km 38 for gravel haul | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44460 |  | 50 | 44462 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2L.O.A.0.363636488.7273OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.71555 | 63.4888 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7347 | KL-20210915-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-09-15 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator working from 18 to 19.5 km leveling ruts and shaping road for pick up access /Chapman rock truck and Kabi 30 ton rock truck on site to haul with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44454 |  |  | 44464 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-1L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-1L.O.A.0.4545455110.9091OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 0.5 | 0.5 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7347 | KL-20210915-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-09-15 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator working from 18 to 19.5 km leveling ruts and shaping road for pick up access /Chapman rock truck and Kabi 30 ton rock truck on site to haul with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44454 |  |  | 44464 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-1L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-1L.O.A.0.4545455110.9091OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 0.5 | 0.5 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7350 | KL-20210916-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-09-16 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator loading and hauling from 18 to19.5 km /Chapman rock truck and Kabi 30 ton rock truck hauling from 38 to 42/43 km with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44463 |  |  | 44464 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1L.O.A.0.8636364210.7273OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.76183 | 160.5375 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7350 | KL-20210916-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-09-16 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator loading and hauling from 18 to19.5 km /Chapman rock truck and Kabi 30 ton rock truck hauling from 38 to 42/43 km with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44463 |  |  | 44464 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1L.O.A.0.8636364210.7273OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.76183 | 160.5375 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-09-17 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44463 |  | 50 | 44466 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1L.O.A.0.4545455110.9091OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.55803 | 61.8905 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-09-17 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44463 |  | 50 | 44466 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1L.O.A.0.4545455110.9091OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.55803 | 61.8905 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7334 | KL-20210912-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.5 | Day |  | 0 |  |  | 122 | 15.86 | 137.86 | 2021-09-12 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 19/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44460 |  | 50 | 44462 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-2L.O.A.0.5122 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-2L.O.A.0.5122OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.68622 | 83.7188 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7334 | KL-20210912-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-09-12 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 19/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44460 |  | 50 | 44462 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-2L.O.A.0.8636364210.7273OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.68622 | 144.6052 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-09-14 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 44460 |  |  | 44461 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2L.O.A.0.4545455110.9091OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-09-14 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 44460 |  |  | 44461 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2L.O.A.0.4545455110.9091OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-09-14 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 44460 |  |  | 44461 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2L.O.A.0.4545455110.9091OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511004 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-09-14 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 44460 |  |  | 44461 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2L.O.A.0.4545455110.9091OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7279 | KL-20210825-3 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-25 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 42 to Morin Excavator/ Excavator 2 fixing up access from Km 44 to Km 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7279KL-20210825-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7279KL-20210825-3L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7279 | KL-20210825-3 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-25 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 42 to Morin Excavator/ Excavator 2 fixing up access from Km 44 to Km 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7279KL-20210825-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7279KL-20210825-3L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7279 | KL-20210825-3 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-25 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 42 to Morin Excavator/ Excavator 2 fixing up access from Km 44 to Km 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7279KL-20210825-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7279KL-20210825-3L.O.A.0.8181818199.6364OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7347 | KL-20210915-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-15 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator working from 18 to 19.5 km leveling ruts and shaping road for pick up access /Chapman rock truck and Kabi 30 ton rock truck on site to haul with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44454 |  |  | 44464 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 0.5 | 0.5 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7384 | KL-20210924-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-24 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees, excavator 2 placing trees @km 16.5 and Km 21 hill/Chapman rock truck hauling Gravel From km 38 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 50 | 44470 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.51268 | 102.3497 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7384 | KL-20210924-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-24 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees, excavator 2 placing trees @km 16.5 and Km 21 hill/Chapman rock truck hauling Gravel From km 38 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 50 | 44470 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.51268 | 102.3497 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-09-27 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44475 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1L.O.A.0.8636364210.7273OEWT-PA22-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511004 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-27 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44475 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-Access |  | 0 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7293 | KL-20210831-3 | 53511007 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2021-08-31 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Mob Cat 730 Rock Truck from North of White River to 0.5Km on Hensen Road for Gravel haul | 10 | F-033 to F-118 | Paint Lake Road 2 | 0 | 44442 |  | 37 | 44445 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7293KL-20210831-3L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7293KL-20210831-3L.O.A.0.5454545133.0909OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7443 | KL-20211011-2 | 53511007 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-10-11 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 725 Rock Truck from Three Finger Lake to Paint Lake Road 2 for gravel haul. Delivered to 0.5km on Hensen Road. | 10 | F-033 to F-118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7443KL-20211011-2L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7443KL-20211011-2L.O.A.0.4545455110.9091OEWT-PA22-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7477 | KL-20211019-3 | 53511007 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-10-19 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 330 Excavator from Kabi Yard to Km 49 Paint Lake Road 2 as per Valard | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7477KL-20211019-3L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7477KL-20211019-3L.O.A.0.4545455110.9091OEWT-PA22-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4663 | KL-20201126-16 | 53511011 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shaping and back blading access road and pulling a drag F09, F24 | 10 | F009-F020 | Paint Lake Road 1-A | 0 | 44178 |  | 50 | 44208 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD4663KL-20201126-16L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4663KL-20201126-16L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4708 | KL-20201129-7 | 53511011 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-11-29 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading Paint Lake 2 Road | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44181 |  | 47 | 44208 | [5 empty] | Bruce Bennett | 10 | KABI LAKE FOREST PRODUCTS LTD4708KL-20201129-7L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD4708KL-20201129-7L.O.A.0.9090909221.8182OEWT-PA12-LEM-R1 | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4792 | KL-20201203-12 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2020-12-03 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Pick up 40' bridge mats in Marathon, and deliver to Paint Lake RD 1-B | 10 | F021-F032 | Paint Lake Road 1-B | 0 | 44193 |  | 50 | 44206 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD4792KL-20201203-12L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD4792KL-20201203-12L.O.A.0.8181818199.6364OEWT-PA12-LEM-R1 | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5143 | KL-20201222-6 | 53511011 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-12-22 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Paint Lake 2 Road | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44200 |  | 56 | 44213 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD5143KL-20201222-6L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD5143KL-20201222-6L.O.A.1244OEWT-PA12-LEM-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5181 | KL-20201231-4 | 53511011 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-12-31 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Paint lake road 2 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44204 |  | 56 | 44216 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD5181KL-20201231-4L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD5181KL-20201231-4L.O.A.1244OEWT-PA13-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5188 | KL-20210101-1 | 53511011 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2021-01-01 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Paint Lake road 2 and 600 Road | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44204 |  | 56 | 44216 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD5188KL-20210101-1L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD5188KL-20210101-1L.O.A.1244OEWT-PA13-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5606 | KL-20210125-3 | 53511011 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2021-01-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow, Grade Paint Lake 2 Rd, haul gravel & corduroy. Drag 70' bridge in from km 9 lay down | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44225 |  | 50 | 44232 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5606KL-20210125-3L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD5606KL-20210125-3L.O.A.0.5454545133.0909OEWT-PA14-Lem-R1 | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5617 | KL-20210126-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-01-26 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Drag 70' bridge in from km 9 laydown, plow snow, grade PL2 Rd and F20-F10. Haul gravel and corduroy, sand roads, unload bridge, skidder drag mats to WC 11150 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44228 |  | 50 | 44232 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5617KL-20210126-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD5617KL-20210126-1L.O.A.0.9090909221.8182OEWT-PA14-Lem-R1 | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5678 | KL-20210130-15 | 53511011 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  |  |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-01-30 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow, haul gravel and corduroy, Sand roads. Drag in and unload bridge WC 11333.00 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44231 |  | 50 | 44232 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5678KL-20210130-15L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD5678KL-20210130-15L.O.A.0.9090909221.8182OEWT-PA14-Lem-R1 | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5684 | KL-20210129-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-01-29 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow, haul gravel and corduroy, sand, skid corduroy. CDSL laying corduroy. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44234 |  | 50 | 44236 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5684KL-20210129-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD5684KL-20210129-2L.O.A.0.9090909221.8182OEWT-PA14-Lem-R1 | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5703 | KL-20210131-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2021-01-31 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator making safety berm and sanding hill on F143 access | 11 | F135-F149 | Dore Lake Road | 0 | 44235 |  | 56 | 44236 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD5703KL-20210131-2L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD5703KL-20210131-2L.O.A.0.181818244.3636OEWT-PA14-Lem-R1 | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5778 | KL-20210205-4 | 53511011 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2021-02-05 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Paint Lake 2 Rd, plow snow, haul gravel. Ditch and load rock trucks. Haul & spread material, trim road, and track out plow. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44243 |  | 50 | 44248 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5778KL-20210205-4L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD5778KL-20210205-4L.O.A.0.5454545133.0909OEWT-PA14-Lem-R1 | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5841 | KL-20210210-3 | 53511011 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2021-02-10 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer plow snow & open road between F21 to F32 | 10 | F021-F032 | Paint Lake Road 1-B | 0 | 44244 |  | 50 | 44249 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5841KL-20210210-3L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD5841KL-20210210-3L.O.A.0.5454545133.0909OEWT-PA14-Lem-R1 | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5976 | KL-20210220-3 | 53511011 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-02-20 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Paint Lake 2 Road, Plow snow on access road. Corduroy F62-F63 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44252 |  | 57 | 44252 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD5976KL-20210220-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD5976KL-20210220-3L.O.A.0.9090909221.8182OEWT-PA14-Lem-R1 | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5976 | KL-20210220-3 | 53511011 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-02-20 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Paint Lake 2 Road, Plow snow on access road. Corduroy F62-F63 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44252 |  | 57 | 44252 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD5976KL-20210220-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD5976KL-20210220-3L.O.A.0.9090909221.8182OEWT-PA14-Lem-R1 | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5990 | KL-20210221-8 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-02-21 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Paint Lake 2 Rd, plow snow on access rd, haul geo from km 9 to km 23, skid corduroy | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44252 |  | 57 | 44255 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD5990KL-20210221-8L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD5990KL-20210221-8L.O.A.0.8181818199.6364OEWT-PA14-Lem-R1 | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5990 | KL-20210221-8 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-02-21 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Paint Lake 2 Rd, plow snow on access rd, haul geo from km 9 to km 23, skid corduroy | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44252 |  | 57 | 44255 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD5990KL-20210221-8L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD5990KL-20210221-8L.O.A.0.8181818199.6364OEWT-PA14-Lem-R1 | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5997 | KL-20210222-3 | 53511011 | Access | 0 | L.O.A. | 244 | 1.3636 | Day |  | 0 |  |  | 332.7273 | 43.2545 | 375.9818 | 2021-02-22 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, skid corduroy, haul rig mats to snow crossing, work on snow crossing, place mats, track buncher to snow crossing, haul gravel. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44254 | . | 57 | 44255 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD5997KL-20210222-3L.O.A.1.3636364332.7273 | KABI LAKE FOREST PRODUCTS LTD5997KL-20210222-3L.O.A.1.3636364332.7273OEWT PA15-LEM | [5 empty] | 1 | 332.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5997 | KL-20210222-3 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-02-22 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, skid corduroy, haul rig mats to snow crossing, work on snow crossing, place mats, track buncher to snow crossing, haul gravel. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44254 | . | 57 | 44255 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD5997KL-20210222-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD5997KL-20210222-3L.O.A.0.8181818199.6364OEWT PA15-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6017 | KL-20210223-10 | 53511011 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-02-23 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, work on snow crossing, haul and place rig mats, load and haul gravel. Haul and spread gravel, roll out geo, hammer access road to F60 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44253 |  | 57 | 44257 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD6017KL-20210223-10L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD6017KL-20210223-10L.O.A.0.9090909221.8182OEWT-PA14-Lem-R1 | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6021 | KL-20210224-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-02-24 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, load and haul gravel. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44256 |  | 57 | 44259 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD6021KL-20210224-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD6021KL-20210224-1L.O.A.0.9090909221.8182OEWT-PA14-Lem-R1 | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6044 | KL-20210225-12-R1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-02-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, load and haul gravel, move bridge, and sand road. WC 12000.00 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44256 |  | 56 | 44259 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6044KL-20210225-12-R1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD6044KL-20210225-12-R1L.O.A.0.8181818199.6364OEWT-PA14-Lem-R1 | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6044 | KL-20210225-12-R1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-02-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, load and haul gravel, move bridge, and sand road. WC 12000.00 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44256 |  | 56 | 44259 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6044KL-20210225-12-R1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD6044KL-20210225-12-R1L.O.A.0.9090909221.8182OEWT-PA14-Lem-R1 | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6101 | KL-20210226-11 | 53511011 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-02-26 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow, load and haul gravel, sand rd, unload and move legos, skid and place corduroy,Buncher was cutting wood and tracking wood to place on road | 10 | F-033 to F-118 | Paint Lake Road 2 | 0 | 44262 |  | 57 | 44277 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD6101KL-20210226-11L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD6101KL-20210226-11L.O.A.0.9090909221.8182OEWT PA15-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6109 | KL-20210227-7 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-02-27 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, load and haul gravel, sand road. Skid corduroy, move mats, place corduroy. | 10 | F-033 to F-118 | Paint Lake Road 2 | 0 | 44262 |  | 57 | 44266 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD6109KL-20210227-7L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD6109KL-20210227-7L.O.A.0.8181818199.6364OEWT-PA16-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6129 | KL-20210301-5 | 53511011 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2021-03-01 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, load and haul gravel, sand road, skid corduroy, placing corduroy, cut bundles in half | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44263 |  | 57 | 44266 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD6129KL-20210301-5L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD6129KL-20210301-5L.O.A.0.5454545133.0909OEWT PA15-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5877 | KL-20210212-8 | 53511011 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2021-02-12 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul Gravel, pull bridges and legos in, plow snow, sand roads, skid corduroy | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44244 |  | 50 | 44250 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5877KL-20210212-8L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD5877KL-20210212-8L.O.A.1244OEWT-PA14-Lem-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6290 | KL-20210310-3 | 53511011 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-03-10 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying Paint Lake 2 Rd/Loader pushing out snow banks in low areas for drainage. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44278 |  | 56 | 44280 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6290KL-20210310-3L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD6290KL-20210310-3L.O.A.0.7272727177.4545OEWT PA15-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6290 | KL-20210310-3 | 53511011 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-03-10 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying Paint Lake 2 Rd/Loader pushing out snow banks in low areas for drainage. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44278 |  | 56 | 44280 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6290KL-20210310-3L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD6290KL-20210310-3L.O.A.0.4545455110.9091OEWT PA15-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6301 | KL-20210311-2 | 53511011 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2021-03-11 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal & scarifying Paint Lake 2 Rd. JJR pushing snowbanks back. CDSL excavator walking out to float access. | 10 | F033-F118 | Paint Lake Raod 2 | 0 | 44278 |  | 56 | 44280 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6301KL-20210311-2L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD6301KL-20210311-2L.O.A.1244OEWT PA15-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6309 | KL-20210312-6 | 53511011 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-03-12 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal & scarifying Paint Lake 2 Rd | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44278 |  | 56 | 44280 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6309KL-20210312-6L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD6309KL-20210312-6L.O.A.0.7272727177.4545OEWT PA15-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6336 | KL-20210315-4 | 53511011 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-03-15 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Scarifying hills and corners on Paint Lake Road 2 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44279 |  | 56 | 44280 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6336KL-20210315-4L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD6336KL-20210315-4L.O.A.0.363636488.7273OEWT PA15-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7593 | KL-20211125-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-11-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road @ F118, scraping and sanding hill @ Km 48. Excavator filling ruts and shaping road from km 24 to 21 for freezing - JJR-70306 | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7593KL-20211125-2L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7593KL-20211125-2L.O.A.0.4545455110.9091OEWT-PA23-Lem | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7620 | KL-20211202-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Km 49 to Km 40/ loader sanding road from Km 48 to Km 46.5 with existing material | 10 | F066-F118 | Paint Lake 2 | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7620KL-20211202-2L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7620KL-20211202-2L.O.A.0.4545455110.9091OEWT-PA24-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7620 | KL-20211202-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Km 49 to Km 40/ loader sanding road from Km 48 to Km 46.5 with existing material | 10 | F066-F118 | Paint Lake 2 | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7620KL-20211202-2L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7620KL-20211202-2L.O.A.0.363636488.7273OEWT-PA24-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7621 | KL-20211202-3 | 53511011 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat 950M Loader from Anjigami to 10.5 Km 0n Hensen Road as per Valard / Chain up required | 10 | F066-F118 | Paint Lake 2 | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7621KL-20211202-3L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7621KL-20211202-3L.O.A.0.363636488.7273OEWT-PA24-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7628 | KL-20211203-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-12-03 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding and scraping road from Km 46.5 to Km 38 with existing material | 10 | F066-F118 | Paint Lake 2 | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7628KL-20211203-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7628KL-20211203-2L.O.A.0.8636364210.7273OEWT-PA24-LEM | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7637 | KL-20211204-5 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-04 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding and scraping road from Km 46 to Km 38 with existing material /dozer working from Km 49 to Km 13/ supervisior picking up dozer operator @ Km 13 at end of shift | 10 | F066-F118 | Paint Lake 2 | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7637KL-20211204-5L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7637KL-20211204-5L.O.A.0.8181818199.6364OEWT-PA24-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7637 | KL-20211204-5 | 53511011 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-12-04 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding and scraping road from Km 46 to Km 38 with existing material /dozer working from Km 49 to Km 13/ supervisior picking up dozer operator @ Km 13 at end of shift | 10 | F066-F118 | Paint Lake 2 | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7637KL-20211204-5L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7637KL-20211204-5L.O.A.0.9545455232.9091OEWT-PA24-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7639 | KL-20211205-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-05 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader piling existing material from Km 46 to Km 38 for upcoming snow fall/ dozer working on snow removal from km 13 to km 21 | 10 | F066-F118 | Paint Lake 2 | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7639KL-20211205-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7639KL-20211205-2L.O.A.0.8181818199.6364OEWT-PA24-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7639 | KL-20211205-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-05 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader piling existing material from Km 46 to Km 38 for upcoming snow fall/ dozer working on snow removal from km 13 to km 21 | 10 | F066-F118 | Paint Lake 2 | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7639KL-20211205-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7639KL-20211205-2L.O.A.0.8181818199.6364OEWT-PA24-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7643 | KL-20211206-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-06 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working on snow removal and sanding from Km 49 to Km 35 | 10 | F066-F118 | Paint Lake 2 | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7643KL-20211206-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7643KL-20211206-2L.O.A.0.8181818199.6364OEWT-PA24-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7646 | KL-20211206-5 | 53511011 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2021-12-06 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking out from Km 13 to Km 2 for loading of sand truck with existing material in support of Valard fuel tank demob | 10 | F066-F118 | Paint Lake 2 | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7646KL-20211206-5L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD7646KL-20211206-5L.O.A.0.409090999.8182OEWT-PA24-LEM | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7647 | KL-20211207-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-07 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding from Km 48 to Km 40 | 10 | F066-F118 | Paint Lake 2 | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7647KL-20211207-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7647KL-20211207-1L.O.A.0.8181818199.6364OEWT-PA24-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7652 | KL-20211208-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.59091 | Day |  | 0 |  |  | 144.1818 | 18.7436 | 162.9254 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding from Km 48 to Km 45. Dozer working from 13km to 18km. Sand truck sanding from 0km to 12km in support of Valard Fuel Tank Demob. Excavator loading existing material. Skagen grader on PLR 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-1L.O.A.0.5909091144.1818 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-1L.O.A.0.5909091144.1818OEWT-PA24-LEM | [5 empty] | 1 | 144.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7652 | KL-20211208-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding from Km 48 to Km 45. Dozer working from 13km to 18km. Sand truck sanding from 0km to 12km in support of Valard Fuel Tank Demob. Excavator loading existing material. Skagen grader on PLR 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-1L.O.A.0.8181818199.6364OEWT-PA24-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7652 | KL-20211208-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding from Km 48 to Km 45. Dozer working from 13km to 18km. Sand truck sanding from 0km to 12km in support of Valard Fuel Tank Demob. Excavator loading existing material. Skagen grader on PLR 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-1L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-1L.O.A.0.7272727177.4545OEWT-PA24-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7652 | KL-20211208-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding from Km 48 to Km 45. Dozer working from 13km to 18km. Sand truck sanding from 0km to 12km in support of Valard Fuel Tank Demob. Excavator loading existing material. Skagen grader on PLR 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-1L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-1L.O.A.0.181818244.3636OEWT-PA24-LEM | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7657 | KL-20211209-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working from 48km to 34km sanding & clearing pull offs. Dozer working to F057, F058 & F058 access. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7657KL-20211209-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7657KL-20211209-1L.O.A.0.8181818199.6364OEWT-PA24-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7657 | KL-20211209-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working from 48km to 34km sanding & clearing pull offs. Dozer working to F057, F058 & F058 access. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7657KL-20211209-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7657KL-20211209-1L.O.A.0.8181818199.6364OEWT-PA24-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7658 | KL-20211209-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 14M grader from Kabi shop to 2Km on Paint Lake Road 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7658KL-20211209-2L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7658KL-20211209-2L.O.A.0.272727366.5455OEWT-PA24-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7659 | KL-20211209-3 | 53511011 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Demobilized Skagen's Champion 740 grader form Paint Lake Road 2 to Sault Ste Marie, ON. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7659KL-20211209-3L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7659KL-20211209-3L.O.A.0.8636364210.7273OEWT-PA24-LEM | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7665 | KL-20211210-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-12-10 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal and sanding from 48Km to 38Km. Grader working on snow removal from Paint Lake Road to 13Km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7665KL-20211210-1L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7665KL-20211210-1L.O.A.0.9545455232.9091OEWT-PA24-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7665 | KL-20211210-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-12-10 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal and sanding from 48Km to 38Km. Grader working on snow removal from Paint Lake Road to 13Km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7665KL-20211210-1L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7665KL-20211210-1L.O.A.0.7727273188.5455OEWT-PA24-LEM | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7670 | KL-20211211-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.59091 | Day |  | 0 |  |  | 144.1818 | 18.7436 | 162.9254 | 2021-12-11 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from 49Km to 40Km. Grader 1 working on snow removal 0Km to 23Km for Crane demob. Grader 2 scarifying from 49 to 45Km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7670KL-20211211-1L.O.A.0.5909091144.1818 | KABI LAKE FOREST PRODUCTS LTD7670KL-20211211-1L.O.A.0.5909091144.1818OEWT-PA24-LEM | [5 empty] | 1 | 144.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7670 | KL-20211211-1 | 53511011 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2021-12-11 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from 49Km to 40Km. Grader 1 working on snow removal 0Km to 23Km for Crane demob. Grader 2 scarifying from 49 to 45Km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7670KL-20211211-1L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD7670KL-20211211-1L.O.A.1244OEWT-PA24-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7670 | KL-20211211-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.22727 | Day |  | 0 |  |  | 55.4545 | 7.2091 | 62.6636 | 2021-12-11 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from 49Km to 40Km. Grader 1 working on snow removal 0Km to 23Km for Crane demob. Grader 2 scarifying from 49 to 45Km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7670KL-20211211-1L.O.A.0.227272755.4545 | KABI LAKE FOREST PRODUCTS LTD7670KL-20211211-1L.O.A.0.227272755.4545OEWT-PA24-LEM | [5 empty] | 1 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7681 | KL-20211212-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-12-12 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working from Km 2 to Km 49 for scarifying and clearing pull offs | 10 | F066-F118 | Paint Lake 2 | 0 | 44551 |  | 61 | 44561 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7681KL-20211212-1L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7681KL-20211212-1L.O.A.0.9545455232.9091OEWT-PA24-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7686 | KL-20211213-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-12-13 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer starting snow removal from F117 to F112 | 10 | F066-F118 | Paint Lake 2 | 0 | 44551 |  | 61 | 44560 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7686KL-20211213-1L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7686KL-20211213-1L.O.A.0.4545455110.9091OEWT-PA24-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7689 | KL-20211214-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.22727 | Day |  | 0 |  |  | 55.4545 | 7.2091 | 62.6636 | 2021-12-14 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Finishing snow removal from F117 to F112 | 10 | F066-F118 | Paint Lake 2 | 0 | 44551 |  | 61 | 44560 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7689KL-20211214-1L.O.A.0.227272755.4545 | KABI LAKE FOREST PRODUCTS LTD7689KL-20211214-1L.O.A.0.227272755.4545OEWT-PA24-LEM | [5 empty] | 1 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7703 | KL-20211217-3 | 53511011 | Access | 0 | L.O.A. | 244 | 0.31818 | Day |  | 0 |  |  | 77.6364 | 10.0927 | 87.7291 | 2021-12-17 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat D6 Dozer from Km 9 on Paint Lake Road 2 to Kabi Yard | 10 | F066-F118 | Paint Lake 2 | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7703KL-20211217-3L.O.A.0.318181877.6364 | KABI LAKE FOREST PRODUCTS LTD7703KL-20211217-3L.O.A.0.318181877.6364OEWT-PA24-LEM | [5 empty] | 1 | 77.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7705 | KL-20211218-3 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-18 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on shaping road and leveling ruts from F112 to F117 for freezing | 10 | F066-F118 | Paint Lake 2 | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7705KL-20211218-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7705KL-20211218-3L.O.A.0.8181818199.6364OEWT-PA24-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7707 | KL-20211219-3 | 53511011 | Access | 0 | L.O.A. | 244 | 0.31818 | Day |  | 0 |  |  | 77.6364 | 10.0927 | 87.7291 | 2021-12-19 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 330F Excavator fro Km 2 on Paint Lake Road 2 to Kabi Yard | 10 | F066-F118 | Paint Lake 2 | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7707KL-20211219-3L.O.A.0.318181877.6364 | KABI LAKE FOREST PRODUCTS LTD7707KL-20211219-3L.O.A.0.318181877.6364OEWT-PA24-LEM | [5 empty] | 1 | 77.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7709 | KL-20211220-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-20 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Demobilization of Morin 300 Excavator from Km 9 on Paint Lake Road 2 to Chapleau Ontario | 10 | F066-F118 | Paint Lake 2 | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7709KL-20211220-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7709KL-20211220-2L.O.A.0.8181818199.6364OEWT-PA24-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7718 | KL-20220101-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-01 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Km 49 on Paint Lake Road 2 to F111 | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7718KL-20220101-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7718KL-20220101-1L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7723 | KL-20220103-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.68182 | Day |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2022-01-03 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F117 to F112 | 10 | F066-F118 | Paint Lake 2 | 0 | 44568 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7723KL-20220103-1L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD7723KL-20220103-1L.O.A.0.6818182166.3636OEWT-PA25-Lem | [5 empty] | 1 | 166.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7728 | KL-20220104-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-04 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and widening road from Km 47 to Km 43.5, F109 to F111, F105 and F104 Access | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7728KL-20220104-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7728KL-20220104-1L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7731 | KL-20220105-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2022-01-05 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat 962M Loader from Kabi yard to 9.2 Km on Paint Lake Road 2 | 10 | F0066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7731KL-20220105-1L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7731KL-20220105-1L.O.A.0.363636488.7273OEWT-PA25-Lem | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7736 | KL-20220106-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2022-01-06 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Link Belt Log Loader from Km 49 to Km 9.2 on Paint Lake Road 2 and Cat 330 support excavator from Km 49 to Km 1 on Paint Lake Road and parked @ end of shift ( chain up required ) | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7736KL-20220106-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7736KL-20220106-1L.O.A.0.9090909221.8182OEWT-PA25-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7737 | KL-20220106-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2022-01-06 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Working on Snow Removal and Widening road from Km 46 to F111/ Loader working on snow removal from F037 to F033 and sanding km 10.5 Hill | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7737KL-20220106-2L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD7737KL-20220106-2L.O.A.0.409090999.8182OEWT-PA25-Lem | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7737 | KL-20220106-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.68182 | Day |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2022-01-06 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Working on Snow Removal and Widening road from Km 46 to F111/ Loader working on snow removal from F037 to F033 and sanding km 10.5 Hill | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7737KL-20220106-2L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD7737KL-20220106-2L.O.A.0.6818182166.3636OEWT-PA25-Lem | [5 empty] | 1 | 166.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7739 | KL-20220107-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.68182 | Day |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2022-01-07 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 330 support excavator from Km 1 on Paint Lake Road to Km 9.2 on Paint Lake Road 2 and Peterson Grinder from 17 on Hensen Road to Km 9.2 on Paint Lake Road 2 ( chain up required ) | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7739KL-20220107-1L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD7739KL-20220107-1L.O.A.0.6818182166.3636OEWT-PA25-Lem | [5 empty] | 1 | 166.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7740 | KL-20220107-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-07 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working from Km 12 to Km 49 clearing pull offs and scraping hills from km 34 to km 41 | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7740KL-20220107-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7740KL-20220107-2L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7744 | KL-20220108-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-08 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working from Km 48 to Km 41 pushing back snow banks, clearing pull offs and F105/F104 access | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7744KL-20220108-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7744KL-20220108-1L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7751 | KL-20220110-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-10 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working on snow removal from Km 49 to Km 36 and clearing pull offs | 10 | F066-F118 | Paint Lake 2 | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7751KL-20220110-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7751KL-20220110-1L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7755 | KL-20220111-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-11 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and widening roads from Km 48 to Km 38 | 10 | F066-F118 | Paint Lake 2 | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7755KL-20220111-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7755KL-20220111-1L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7758 | KL-20220112-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-12 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and widening roads from Km 42 to Km 34/ Supervisor doing pick up shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7758KL-20220112-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7758KL-20220112-1L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7763 | KL-20220113-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-13 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and widening roads from Km 38 to Km 32 | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7763KL-20220113-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7763KL-20220113-1L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7768 | KL-20220114-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2022-01-14 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal and widening roads from Km 32 to Km 36 /Clearing spur roads on way out | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7768KL-20220114-1L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7768KL-20220114-1L.O.A.0.4545455110.9091OEWT-PA25-Lem | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7772 | KL-20220115-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2022-01-15 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal and widening roads from Km 32 to Km 36 /Clearing spur roads on way out. Excavator setting up @ 12Km for loader access to sand. | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7772KL-20220115-1L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7772KL-20220115-1L.O.A.0.272727366.5455OEWT-PA25-Lem | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7772 | KL-20220115-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2022-01-15 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal and widening roads from Km 32 to Km 36 /Clearing spur roads on way out. Excavator setting up @ 12Km for loader access to sand. | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7772KL-20220115-1L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD7772KL-20220115-1L.O.A.0.181818244.3636OEWT-PA25-Lem | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7774 | KL-20220115-3 | 53511011 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2022-01-15 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float ACI Cat 938M loader from .5 Km on Hensen road to Km 9.2 on Paint Lake Road 2 as per Valard | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7774KL-20220115-3L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD7774KL-20220115-3L.O.A.0.409090999.8182OEWT-PA25-Lem | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7776 | KL-20220116-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.68182 | Day |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2022-01-16 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continue working on widening roads from Km 33 to Km 42 /Loader Clearing pull offs / Grader Scarifying from Km 49 to Km 42 | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7776KL-20220116-1L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD7776KL-20220116-1L.O.A.0.6818182166.3636OEWT-PA25-Lem | [5 empty] | 1 | 166.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7776 | KL-20220116-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2022-01-16 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continue working on widening roads from Km 33 to Km 42 /Loader Clearing pull offs / Grader Scarifying from Km 49 to Km 42 | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7776KL-20220116-1L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD7776KL-20220116-1L.O.A.0.181818244.3636OEWT-PA25-Lem | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7776 | KL-20220116-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2022-01-16 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continue working on widening roads from Km 33 to Km 42 /Loader Clearing pull offs / Grader Scarifying from Km 49 to Km 42 | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7776KL-20220116-1L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7776KL-20220116-1L.O.A.0.272727366.5455OEWT-PA25-Lem | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7779 | KL-20220117-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2022-01-17 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Finish working on widening roads and clearing pull offs from Km 42 to Km 49 /Grader Scarifying from Km 49 to Km 39 and F117 to F112/ supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7779KL-20220117-1L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7779KL-20220117-1L.O.A.0.6363636155.2727OEWT-PA25-Lem | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7779 | KL-20220117-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2022-01-17 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Finish working on widening roads and clearing pull offs from Km 42 to Km 49 /Grader Scarifying from Km 49 to Km 39 and F117 to F112/ supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7779KL-20220117-1L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7779KL-20220117-1L.O.A.0.363636488.7273OEWT-PA25-Lem | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7785 | KL-20220119-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.22727 | Day |  | 0 |  |  | 55.4545 | 7.2091 | 62.6636 | 2022-01-19 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from 49Km to 42Km on Paint Lake Road 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7785KL-20220119-1L.O.A.0.227272755.4545 | KABI LAKE FOREST PRODUCTS LTD7785KL-20220119-1L.O.A.0.227272755.4545OEWT-PA25-Lem | [5 empty] | 1 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7877 | KL-20220213-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2022-02-13 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat 140M Grader from Kabi Yard to Km 2 on Paint Lake Road 2 | 10 | F066-F118 | Paint Lake | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7877KL-20220213-1L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7877KL-20220213-1L.O.A.0.272727366.5455OEWT-PA26-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7878 | KL-20220213-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-13 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F021 to F032 and clearing pad @ F032 | 10 | F009-F065 | Paint Lake | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7878KL-20220213-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7878KL-20220213-2L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7883 | KL-20220214-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-14 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal, scarifying and benching snowbanks from Paint Lake Road to Km 19 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7883KL-20220214-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7883KL-20220214-1L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7884 | KL-20220214-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2022-02-14 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer finishing snow removal and widening from F021 to F032 and clearing pad @ F032 | 10 | F009-F065 | Paint Lake | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7884KL-20220214-2L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7884KL-20220214-2L.O.A.0.7272727177.4545OEWT-PA26-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7888 | KL-20220215-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2022-02-15 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal, scarifying from Km 49 to Km 38 on Paint Lake Road 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7888KL-20220215-1L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7888KL-20220215-1L.O.A.0.4545455110.9091OEWT-PA26-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7893 | KL-20220216-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.68182 | Day |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2022-02-16 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from Km 49 to Km 19 / grader 2 working on snow removal and pushing back snowbanks from Paint Lake Road to Km 19 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7893KL-20220216-1L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD7893KL-20220216-1L.O.A.0.6818182166.3636OEWT-PA26-LEM | [5 empty] | 1 | 166.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7893 | KL-20220216-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-16 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from Km 49 to Km 19 / grader 2 working on snow removal and pushing back snowbanks from Paint Lake Road to Km 19 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7893KL-20220216-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7893KL-20220216-1L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7896 | KL-20220217-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2022-02-17 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal and scarifying from Km 49 to Km 41 / grader 2 working on snow removal and benching snowbanks from Paint Lake Road to Km 41 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7896KL-20220217-1L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7896KL-20220217-1L.O.A.0.363636488.7273OEWT-PA26-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7896 | KL-20220217-1 | 53511011 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2022-02-17 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal and scarifying from Km 49 to Km 41 / grader 2 working on snow removal and benching snowbanks from Paint Lake Road to Km 41 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7896KL-20220217-1L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD7896KL-20220217-1L.O.A.1244OEWT-PA26-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7897 | KL-20220217-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2022-02-17 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from Paint Lake Road 2, work on snow removal from F021 to F032 after hours and run grader back to Paint Lake Road 2 / Supervisor stayed after hours due to Operator working alone | 10 | F009-F065 | Paint Lake | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7897KL-20220217-2L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7897KL-20220217-2L.O.A.0.4545455110.9091OEWT-PA26-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7900 | KL-20220218-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2022-02-18 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying and benching snowbanks from Paint Lake Road to Km 13 and snow removal from F037 to F033 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7900KL-20220218-1L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7900KL-20220218-1L.O.A.0.7727273188.5455OEWT-PA26-LEM | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7904 | KL-20220220-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-20 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 29km. Grader 2 working on snow removal from Paint Lake Road to 29km. Loader pushing back snow banks & pull offs from 45km to 38km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44617 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7904KL-20220220-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7904KL-20220220-1L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7904 | KL-20220220-1 | 53511011 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2022-02-20 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 29km. Grader 2 working on snow removal from Paint Lake Road to 29km. Loader pushing back snow banks & pull offs from 45km to 38km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44617 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7904KL-20220220-1L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD7904KL-20220220-1L.O.A.1244OEWT-PA26-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7904 | KL-20220220-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2022-02-20 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 29km. Grader 2 working on snow removal from Paint Lake Road to 29km. Loader pushing back snow banks & pull offs from 45km to 38km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44617 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7904KL-20220220-1L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7904KL-20220220-1L.O.A.0.9545455232.9091OEWT-PA26-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7905 | KL-20220219-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2022-02-19 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 39km. Grader 2 working on snow removal from Paint Lake Road to 39km. Loader sanding & clearing pull offs to 34km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7905KL-20220219-1L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7905KL-20220219-1L.O.A.0.363636488.7273OEWT-PA26-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7905 | KL-20220219-1 | 53511011 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2022-02-19 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 39km. Grader 2 working on snow removal from Paint Lake Road to 39km. Loader sanding & clearing pull offs to 34km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7905KL-20220219-1L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD7905KL-20220219-1L.O.A.1244OEWT-PA26-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7905 | KL-20220219-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-19 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 39km. Grader 2 working on snow removal from Paint Lake Road to 39km. Loader sanding & clearing pull offs to 34km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7905KL-20220219-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7905KL-20220219-1L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7911 | KL-20220221-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2022-02-21 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 40km. Grader 2 working on snow removal from Paint Lake Road to 40km. Loader pushing back snow banks & pull offs from 49km to 40km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44617 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7911KL-20220221-1L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7911KL-20220221-1L.O.A.0.5454545133.0909OEWT-PA26-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7911 | KL-20220221-1 | 53511011 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2022-02-21 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 40km. Grader 2 working on snow removal from Paint Lake Road to 40km. Loader pushing back snow banks & pull offs from 49km to 40km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44617 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7911KL-20220221-1L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD7911KL-20220221-1L.O.A.1244OEWT-PA26-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7911 | KL-20220221-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2022-02-21 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 40km. Grader 2 working on snow removal from Paint Lake Road to 40km. Loader pushing back snow banks & pull offs from 49km to 40km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44617 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7911KL-20220221-1L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7911KL-20220221-1L.O.A.0.5454545133.0909OEWT-PA26-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7913 | KL-20220222-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.5 | Day |  | 0 |  |  | 122 | 15.86 | 137.86 | 2022-02-22 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 38km. Grader 2 benchig snow banks from Paint Lake Road to 49km. Loader assisting with Demob of 50 Ton Crane from 32Km to Hensen Road. | 10 | F-066 to F-118 | Paint Lake Road 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7913KL-20220222-1L.O.A.0.5122 | KABI LAKE FOREST PRODUCTS LTD7913KL-20220222-1L.O.A.0.5122OEWT-PA26-LEM | [5 empty] | 1 | 122 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7913 | KL-20220222-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2022-02-22 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 38km. Grader 2 benchig snow banks from Paint Lake Road to 49km. Loader assisting with Demob of 50 Ton Crane from 32Km to Hensen Road. | 10 | F-066 to F-118 | Paint Lake Road 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7913KL-20220222-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7913KL-20220222-1L.O.A.0.8636364210.7273OEWT-PA26-LEM | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7913 | KL-20220222-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-22 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 38km. Grader 2 benchig snow banks from Paint Lake Road to 49km. Loader assisting with Demob of 50 Ton Crane from 32Km to Hensen Road. | 10 | F-066 to F-118 | Paint Lake Road 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7913KL-20220222-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7913KL-20220222-1L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7919 | KL-20220223-4 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-23 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from 49km to 29km. Loader working ahead of grader due to deep snow drifts | 10 | F066-F118 | Paint Lake 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7919KL-20220223-4L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7919KL-20220223-4L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7919 | KL-20220223-4 | 53511011 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2022-02-23 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from 49km to 29km. Loader working ahead of grader due to deep snow drifts | 10 | F066-F118 | Paint Lake 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7919KL-20220223-4L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7919KL-20220223-4L.O.A.0.6363636155.2727OEWT-PA26-LEM | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7920 | KL-20220224-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-24 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working on snow removal from 9.2Km to F-033 & to 23Km on Paint Lake Road #2. Supervisor doing pickup shuffle. | 10 | F066-F118 | Paint Lake 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7920KL-20220224-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7920KL-20220224-1L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7925 | KL-20220225-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-25 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 18km. Grader 2 working from Paint Lake Road to 18Km. Loader clearing pulloffs on Paint lake Road 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7925KL-20220225-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7925KL-20220225-1L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7925 | KL-20220225-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2022-02-25 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 18km. Grader 2 working from Paint Lake Road to 18Km. Loader clearing pulloffs on Paint lake Road 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7925KL-20220225-1L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7925KL-20220225-1L.O.A.0.6363636155.2727OEWT-PA26-LEM | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7925 | KL-20220225-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.31818 | Day |  | 0 |  |  | 77.6364 | 10.0927 | 87.7291 | 2022-02-25 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 18km. Grader 2 working from Paint Lake Road to 18Km. Loader clearing pulloffs on Paint lake Road 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7925KL-20220225-1L.O.A.0.318181877.6364 | KABI LAKE FOREST PRODUCTS LTD7925KL-20220225-1L.O.A.0.318181877.6364OEWT-PA26-LEM | [5 empty] | 1 | 77.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7935 | KL-20220226-1 | 53511011 | Access | 0 | L.O.A. | 244 | 1.8636 | Day |  | 0 |  |  | 454.7273 | 59.1145 | 513.8418 | 2022-02-26 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader working from Paint Lake Road to Km 34 benching and widening / Loader clearing pull offs on Paint Lake Road 2 and widening @ Km 27 | 10 | F066-F118 | Paint Lake 2 | 0 | 44628 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7935KL-20220226-1L.O.A.1.8636364454.7273 | KABI LAKE FOREST PRODUCTS LTD7935KL-20220226-1L.O.A.1.8636364454.7273 | [5 empty] | 1 | 454.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7938 | KL-20220227-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader 1 working from 49km to 26km. Grader 2 working from Paint Lake Road to 8km. Loader working on clearing pull offs between 9.2Km & 5Km on Paint Lake Road #2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44628 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7938KL-20220227-1L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7938KL-20220227-1L.O.A.0.6363636155.2727 | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7938 | KL-20220227-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.31818 | Day |  | 0 |  |  | 77.6364 | 10.0927 | 87.7291 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader 1 working from 49km to 26km. Grader 2 working from Paint Lake Road to 8km. Loader working on clearing pull offs between 9.2Km & 5Km on Paint Lake Road #2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44628 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7938KL-20220227-1L.O.A.0.318181877.6364 | KABI LAKE FOREST PRODUCTS LTD7938KL-20220227-1L.O.A.0.318181877.6364 | [5 empty] | 1 | 77.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7938 | KL-20220227-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.59091 | Day |  | 0 |  |  | 144.1818 | 18.7436 | 162.9254 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader 1 working from 49km to 26km. Grader 2 working from Paint Lake Road to 8km. Loader working on clearing pull offs between 9.2Km & 5Km on Paint Lake Road #2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44628 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7938KL-20220227-1L.O.A.0.5909091144.1818 | KABI LAKE FOREST PRODUCTS LTD7938KL-20220227-1L.O.A.0.5909091144.1818 | [5 empty] | 1 | 144.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7944 | KL-20220228-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2022-02-28 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader Working On Snow Removal From 29 Km To 2 Km On Paint Lake Road 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44628 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7944KL-20220228-1L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7944KL-20220228-1L.O.A.0.7272727177.4545 | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7954 | KL-20220301-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2022-03-01 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader working on Snow Removal and benching snow banks from Km 1 to Km 13 on Paint Lake Road 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7954KL-20220301-2L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7954KL-20220301-2L.O.A.0.7727273188.5455 | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7957 | KL-20220302-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-03-02 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader working on Snow Removal from Km 49 to Km 13 on Paint Lake Road 2 @ park Grader at Km 2/Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7957KL-20220302-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7957KL-20220302-2L.O.A.0.8181818199.6364 | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7963 | KL-20220303-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2022-03-03 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Float Kabi Cat 950M Loader Back To 9.2 Km On Paint Lake Road 2 From F170 After Completion Of Snow Removal. Access/Mob/Demob (Cost Code: 67776007556.591100.57010107) | 10 | F066-F118 | Paint Lake 2 | 1 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7963KL-20220303-2L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD7963KL-20220303-2L.O.A.0.409090999.8182 | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7966 | KL-20220303-5 | 53511011 | Access | 0 | L.O.A. | 244 | 0.59091 | Day |  | 0 |  |  | 144.1818 | 18.7436 | 162.9254 | 2022-03-03 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader working on snow removal from Paint Lake Road to F-033 | 10 | F009 - F065 | Paint Lake | 0 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7966KL-20220303-5L.O.A.0.5909091144.1818 | KABI LAKE FOREST PRODUCTS LTD7966KL-20220303-5L.O.A.0.5909091144.1818 | [5 empty] | 1 | 144.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7967 | KL-20220304-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.31818 | Day |  | 0 |  |  | 77.6364 | 10.0927 | 87.7291 | 2022-03-04 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Float Kabi Cat 140M Grader From 2 Km On Paint Lake Road 2 Back To Kabi Yard | 10 | F009 - F065 | Paint Lake | 0 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7967KL-20220304-2L.O.A.0.318181877.6364 | KABI LAKE FOREST PRODUCTS LTD7967KL-20220304-2L.O.A.0.318181877.6364 | [5 empty] | 1 | 77.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7969 | KL-20220304-4 | 53511011 | Access | 0 | L.O.A. | 244 | 0.59091 | Day |  | 0 |  |  | 144.1818 | 18.7436 | 162.9254 | 2022-03-04 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader Continuing Working On Snow Removal From Paint Lake Road 2 To F033 | 10 | F009 - F065 | Paint Lake | 0 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7969KL-20220304-4L.O.A.0.5909091144.1818 | KABI LAKE FOREST PRODUCTS LTD7969KL-20220304-4L.O.A.0.5909091144.1818 | [5 empty] | 1 | 144.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7970 | KL-20220305-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2022-03-05 |  |  |  |  | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Loader Working On Snow Removal From Paint Lake Road 2 To F033 | 10 | F009 - F065 | Paint Lake | 0 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7970KL-20220305-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7970KL-20220305-2L.O.A.0.8636364210.7273 | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7977 | KL-20220309-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2022-03-09 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Float Kabi Cat 12M Grader From 2 Km On Paint Lake Road 2 Back To Kabi Yard | 10 | F066-F118 | Paint Lake 2 | 0 | 44634 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7977KL-20220309-2L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7977KL-20220309-2L.O.A.0.363636488.7273 | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7978 | KL-20220306-3 | 53511011 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2022-03-06 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader Working On Snow Removal From Paint Lake Road To 12.5 Km On Paint Lake Road 2/Graded 3 Times Due To Winter Storm/Loader Working From F037 To F034 | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44637 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7978KL-20220306-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7978KL-20220306-3L.O.A.0.9090909221.8182 | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7978 | KL-20220306-3 | 53511011 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2022-03-06 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader Working On Snow Removal From Paint Lake Road To 12.5 Km On Paint Lake Road 2/Graded 3 Times Due To Winter Storm/Loader Working From F037 To F034 | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44637 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7978KL-20220306-3L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD7978KL-20220306-3L.O.A.0.409090999.8182 | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7788 | KL-20220120-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.22727 | Day |  | 0 |  |  | 55.4545 | 7.2091 | 62.6636 | 2022-01-20 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F112 to F117 | 10 | F066-F118 | Paint Lake 2 | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7788KL-20220120-1L.O.A.0.227272755.4545 | KABI LAKE FOREST PRODUCTS LTD7788KL-20220120-1L.O.A.0.227272755.4545OEWT-PA25-Lem | [5 empty] | 1 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7793 | KL-20220121-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2022-01-21 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer starting from Km 49 Km 45 clearing pull offs and widening where required/Delay Due to Stringers having road closed @ F118/ supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44588 |  | 61 | 44593 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7793KL-20220121-1L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD7793KL-20220121-1L.O.A.0.409090999.8182OEWT-PA25-Lem | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7799 | KL-20220123-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.22727 | Day |  | 0 |  |  | 55.4545 | 7.2091 | 62.6636 | 2022-01-23 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on access and F112 to F117 | 10 | F066-F118 | Paint Lake 2 | 0 | 44588 |  | 61 | 44593 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7799KL-20220123-1L.O.A.0.227272755.4545 | KABI LAKE FOREST PRODUCTS LTD7799KL-20220123-1L.O.A.0.227272755.4545OEWT-PA25-Lem | [5 empty] | 1 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7801 | KL-20220124-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-24 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening F112 to F117, clearing snow @ F109 to F111, F105 access, widening and cleaning pulloffs from Km 48 to 41.5/Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44588 |  | 61 | 44593 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7801KL-20220124-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7801KL-20220124-1L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7805 | KL-20220125-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2022-01-25 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road and cleaning pulloffs from Km 41 to 38.5/Snow removal on spur roads from F104 to F095 /Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44588 |  | 61 | 44593 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7805KL-20220125-1L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7805KL-20220125-1L.O.A.0.7272727177.4545OEWT-PA25-Lem | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7809 | KL-20220126-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2022-01-26 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road and cleaning pulloffs from Km 38 to 35/Snow removal on spur roads /Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7809KL-20220126-1L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7809KL-20220126-1L.O.A.0.7727273188.5455OEWT-PA26-LEM | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7814 | KL-20220129-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2022-01-29 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road , clearing pull offs and spur roads from Km 38 to Km 35/Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7814KL-20220129-1L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7814KL-20220129-1L.O.A.0.5454545133.0909OEWT-PA26-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7816 | KL-20220130-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.59091 | Day |  | 0 |  |  | 144.1818 | 18.7436 | 162.9254 | 2022-01-30 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 49 to Km 36 for stringing crews equipment move /Dozer working from Km 35 to Km 32 widening road , clearing pull offs and spur | 10 | F066-F118 | Paint Lake 2 | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7816KL-20220130-1L.O.A.0.5909091144.1818 | KABI LAKE FOREST PRODUCTS LTD7816KL-20220130-1L.O.A.0.5909091144.1818OEWT-PA26-LEM | [5 empty] | 1 | 144.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7816 | KL-20220130-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2022-01-30 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 49 to Km 36 for stringing crews equipment move /Dozer working from Km 35 to Km 32 widening road , clearing pull offs and spur | 10 | F066-F118 | Paint Lake 2 | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7816KL-20220130-1L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7816KL-20220130-1L.O.A.0.6363636155.2727OEWT-PA26-LEM | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7818 | KL-20220131-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-31 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working from Km 35 to Km 32 widening road , clearing pull offs and spur roads from Km 35 to Km 29 / Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7818KL-20220131-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7818KL-20220131-1L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7822 | KL-20220201-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-01 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road, clearing pull offs, spur roads from 29km to 25km & access road to F057. Supervisor doing pickup shuffle. | 10 | F066-F118 | Paint Lake 2 | 0 | 44601 |  | 37 | 44597 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7822KL-20220201-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7822KL-20220201-1L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7826 | KL-20220202-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-02 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road, clearing pull offs, spur roads from 25km to 21km. Supervisor doing pickup shuffle. | 10 | F066-F118 | Paint Lake 2 | 0 | 44601 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7826KL-20220202-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7826KL-20220202-1L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7828 | KL-20220203-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.59091 | Day |  | 0 |  |  | 144.1818 | 18.7436 | 162.9254 | 2022-02-03 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader benching snow banks & scarifying road from 49 to 40km. Dozer widening road, clearing pull offs & spur roads from 21km to 12.5km. Supervisor doing pickup shuffle. | 10 | F066-F118 | Paint Lake 2 | 0 | 44601 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7828KL-20220203-1L.O.A.0.5909091144.1818 | KABI LAKE FOREST PRODUCTS LTD7828KL-20220203-1L.O.A.0.5909091144.1818OEWT-PA26-LEM | [5 empty] | 1 | 144.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7828 | KL-20220203-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-03 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader benching snow banks & scarifying road from 49 to 40km. Dozer widening road, clearing pull offs & spur roads from 21km to 12.5km. Supervisor doing pickup shuffle. | 10 | F066-F118 | Paint Lake 2 | 0 | 44601 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7828KL-20220203-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7828KL-20220203-1L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7832 | KL-20220204-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-04 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F077 to F073 and clearing laydown at 12km. Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44603 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7832KL-20220204-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7832KL-20220204-1L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7833 | KL-20220204-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2022-02-04 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat D6T dozer from 12Km on Paint Lake Road to F021 on Paint Lake Road. | 10 | F009-F065 | Paint Lake | 0 | 44603 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7833KL-20220204-2L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD7833KL-20220204-2L.O.A.0.409090999.8182OEWT-PA26-LEM | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7836 | KL-20220205-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-05 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F020 to F009 and clearing pull offs. | 10 | F009-F065 | Paint Lake | 0 | 44603 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7836KL-20220205-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7836KL-20220205-1L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7841 | KL-20220206-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.59091 | Day |  | 0 |  |  | 144.1818 | 18.7436 | 162.9254 | 2022-02-06 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F020 to F009 for removal of repeater tower trailer. | 10 | F009-F065 | Paint Lake | 0 | 44603 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7841KL-20220206-1L.O.A.0.5909091144.1818 | KABI LAKE FOREST PRODUCTS LTD7841KL-20220206-1L.O.A.0.5909091144.1818OEWT-PA26-LEM | [5 empty] | 1 | 144.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7843 | KL-20220206-3 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-06 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from 49km to 25km on Paint Lake Road #2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44603 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7843KL-20220206-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7843KL-20220206-3L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7844 | KL-20220207-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F021 to F028 | 10 | F009 - F0665 | Paint Lake | 0 | 44604 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7844KL-20220207-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7844KL-20220207-1L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7846 | KL-20220207-3 | 53511011 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from 49km to 36km on Paint Lake Road #2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44604 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7846KL-20220207-3L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD7846KL-20220207-3L.O.A.0.409090999.8182OEWT-PA26-LEM | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7852 | KL-20220208-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-08 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F021 to F030 | 10 | F009-F065 | Paint Lake | 0 | 44604 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7852KL-20220208-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7852KL-20220208-1L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7854 | KL-20220208-3 Field Ticket No. P.O. Box 508, 10 Industrial Park Rd White River ON POM 3G0 Frank Ferland Telephone: 807-822-2532 08-Feb-2022 Email: office@kabilake.com SUMMARY INFORMATION Page 1 of 1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2022-02-08 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from 49km to 30km on Paint Lake Road #2 & snow removal from F116 to F112. | 10 | F066-F118 | Paint Lake | 0 | 44604 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7854KL-20220208-3 Field Ticket No. P.O. Box 508, 10 Industrial Park Rd White River ON POM 3G0 Frank Ferland Telephone: 807-822-2532 08-Feb-2022 Email: office@kabilake.com SUMMARY INFORMATION Page 1 of 1L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7854KL-20220208-3 Field Ticket No. P.O. Box 508, 10 Industrial Park Rd White River ON POM 3G0 Frank Ferland Telephone: 807-822-2532 08-Feb-2022 Email: office@kabilake.com SUMMARY INFORMATION Page 1 of 1L.O.A.0.5454545133.0909OEWT-PA26-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7859 | KL-20220209-2 | 53511011 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2022-02-09 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader benching snowbanks and scarifying sections from Km 49 to Km 32 on Paint Lake Road 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44604 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7859KL-20220209-2L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7859KL-20220209-2L.O.A.0.7272727177.4545OEWT-PA26-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7864 | KL-20220210-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2022-02-10 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Km 49 to Km 32 on Paint Lake Road 2 /Dozer pushing snowbanks and widening road from Km 9.2 to Km 11/Supervisors doing pickup shuffle | 10 | F066-F118 | Paint Lake | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7864KL-20220210-1L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7864KL-20220210-1L.O.A.0.4545455110.9091OEWT-PA26-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7864 | KL-20220210-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2022-02-10 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Km 49 to Km 32 on Paint Lake Road 2 /Dozer pushing snowbanks and widening road from Km 9.2 to Km 11/Supervisors doing pickup shuffle | 10 | F066-F118 | Paint Lake | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7864KL-20220210-1L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7864KL-20220210-1L.O.A.0.7272727177.4545OEWT-PA26-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7866 | KL-20220210-3 | 53511011 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2022-02-10 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat D6 Dozer from Paint Lake Road 1-B to Km 9.2 on Paint Lake Road 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7866KL-20220210-3L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7866KL-20220210-3L.O.A.0.272727366.5455OEWT-PA26-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7869 | KL-20220211-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.59091 | Day |  | 0 |  |  | 144.1818 | 18.7436 | 162.9254 | 2022-02-11 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 49 to Km 35 /Dozer pushing snowbanks and widening road from Km 11 to Km 15/Supervisors doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7869KL-20220211-1L.O.A.0.5909091144.1818 | KABI LAKE FOREST PRODUCTS LTD7869KL-20220211-1L.O.A.0.5909091144.1818OEWT-PA26-LEM | [5 empty] | 1 | 144.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7869 | KL-20220211-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2022-02-11 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 49 to Km 35 /Dozer pushing snowbanks and widening road from Km 11 to Km 15/Supervisors doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7869KL-20220211-1L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7869KL-20220211-1L.O.A.0.6363636155.2727OEWT-PA26-LEM | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7873 | KL-20220212-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2022-02-12 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 49 to Km 29 /Dozer tracking from Km 15 to Km 9.2 for float access/Supervisors doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7873KL-20220212-1L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7873KL-20220212-1L.O.A.0.5454545133.0909OEWT-PA26-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7873 | KL-20220212-1 | 53511011 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2022-02-12 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 49 to Km 29 /Dozer tracking from Km 15 to Km 9.2 for float access/Supervisors doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7873KL-20220212-1L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD7873KL-20220212-1L.O.A.0.181818244.3636OEWT-PA26-LEM | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7875 | KL-20220212-3 | 53511011 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2022-02-12 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F021 to F027 | 10 | F009-F065 | Paint Lake | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7875KL-20220212-3L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7875KL-20220212-3L.O.A.0.6363636155.2727OEWT-PA26-LEM | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4077 | KL-20201031-9 | 53511012 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-10-31 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Paint Lake Road 2 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44152 |  | 47 | 44156 | [5 empty] | Bruce Bennett | 10 | KABI LAKE FOREST PRODUCTS LTD4077KL-20201031-9L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD4077KL-20201031-9L.O.A.0.7272727177.4545OEWT-PA11-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4524 | KL-20201102-17 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-11-02 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E091-E102 | 600 Road | 0 | 44174 |  | 15 | 44175 | [5 empty] | Martin Hunt | 10 | KABI LAKE FOREST PRODUCTS LTD4524KL-20201102-17L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD4524KL-20201102-17L.O.A.0.9090909221.8182OEWT-PA11-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6963 | KL-20210520-5 | 53511012 | Access | 0 | L.O.A. | 244 | 0.68182 | Day |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T Dozer starting leveling ruts and shaping road from Km 2 to Km 9.5 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD6963KL-20210520-5L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD6963KL-20210520-5L.O.A.0.6818182166.3636OEWT-PA17-LEM | [5 empty] | 1 | 166.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6987 | KL-20210525-5 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-05-25 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator Starting road maintenance to F038 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44348 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD6987KL-20210525-5L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD6987KL-20210525-5L.O.A.0.8181818199.6364OEWT-PA17-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6990 | KL-20210526-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2021-05-26 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator working on road maintenance to F40/ Grader starting on Paint Lake Road 2 to Km 4 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD6990KL-20210526-3L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD6990KL-20210526-3L.O.A.0.6363636155.2727OEWT-PA18-Lem | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6990 | KL-20210526-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-05-26 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator working on road maintenance to F40/ Grader starting on Paint Lake Road 2 to Km 4 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD6990KL-20210526-3L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD6990KL-20210526-3L.O.A.0.7727273188.5455OEWT-PA18-Lem | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6992 | KL-20210527-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-05-27 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator working on road maintenance to F040 / Grader working on Paint Lake Road 2 at km4 to km 10 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD6992KL-20210527-2L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD6992KL-20210527-2L.O.A.0.4545455110.9091OEWT-PA18-Lem | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6992 | KL-20210527-2 | 53511012 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2021-05-27 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator working on road maintenance to F040 / Grader working on Paint Lake Road 2 at km4 to km 10 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD6992KL-20210527-2L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD6992KL-20210527-2L.O.A.1244OEWT-PA18-Lem | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6994 | KL-20210528-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.68182 | Day |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2021-05-28 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator working on road maintenance from Km 15.5 to Km 19/ Grader working on Paint Lake Road 2 at Km 7 to 12 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD6994KL-20210528-2L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD6994KL-20210528-2L.O.A.0.6818182166.3636OEWT-PA18-Lem | [5 empty] | 1 | 166.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6994 | KL-20210528-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-05-28 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator working on road maintenance from Km 15.5 to Km 19/ Grader working on Paint Lake Road 2 at Km 7 to 12 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD6994KL-20210528-2L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD6994KL-20210528-2L.O.A.0.9545455232.9091OEWT-PA18-Lem | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7001 | KL-20210531-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-05-31 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator working on road maintenance and drainage from Km 16.5 to Km 19 /grader working on Paint Lake Road 2 from Km 12 to KM4 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44358 |  | 36 | 44360 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7001KL-20210531-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7001KL-20210531-3L.O.A.0.9090909221.8182OEWT-PA18-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7001 | KL-20210531-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-05-31 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator working on road maintenance and drainage from Km 16.5 to Km 19 /grader working on Paint Lake Road 2 from Km 12 to KM4 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44358 |  | 36 | 44360 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7001KL-20210531-3L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7001KL-20210531-3L.O.A.0.9545455232.9091OEWT-PA18-Lem | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7004 | KL-20210601-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-06-01 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator continue working on road maintenance and drainage from km 17 to km 18/ Grader finishing on Paint Lake Road 2 to Km 0 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44358 |  | 14 | 44359 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7004KL-20210601-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7004KL-20210601-3L.O.A.0.9090909221.8182OEWT-PA18-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7004 | KL-20210601-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2021-06-01 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator continue working on road maintenance and drainage from km 17 to km 18/ Grader finishing on Paint Lake Road 2 to Km 0 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44358 |  | 14 | 44359 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7004KL-20210601-3L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7004KL-20210601-3L.O.A.0.5454545133.0909OEWT-PA18-Lem | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7066 | KL-20210530-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-05-30 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator working road maintenance and drainage to F044/045 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44372 |  | 36 | 44373 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7066KL-20210530-2L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7066KL-20210530-2L.O.A.0.9545455232.9091OEWT-PA18-Lem | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7427 | KL-20211005-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-05 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F112. Excavator 2 working @ 43/42km. Rock trucks hauling from 37.5km to Skagen @ 36km. Labourer hauling fuel to 35km as per Valard. Supervision of Skagen/Morin. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7427 | KL-20211005-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-05 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F112. Excavator 2 working @ 43/42km. Rock trucks hauling from 37.5km to Skagen @ 36km. Labourer hauling fuel to 35km as per Valard. Supervision of Skagen/Morin. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7427 | KL-20211005-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-05 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F112. Excavator 2 working @ 43/42km. Rock trucks hauling from 37.5km to Skagen @ 36km. Labourer hauling fuel to 35km as per Valard. Supervision of Skagen/Morin. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7427 | KL-20211005-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2021-10-05 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F112. Excavator 2 working @ 43/42km. Rock trucks hauling from 37.5km to Skagen @ 36km. Labourer hauling fuel to 35km as per Valard. Supervision of Skagen/Morin. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-1L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-1L.O.A.0.6363636155.2727OEWT-PA22-Lem | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7457 | KL-20211015-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-15 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Flll toFlOO level ruts & drainage isting material from F088 to 34.SKm as per Valard. Supervise Morin, Skagen, Pleson, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7457 | KL-20211015-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-15 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Flll toFlOO level ruts & drainage isting material from F088 to 34.SKm as per Valard. Supervise Morin, Skagen, Pleson, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7457 | KL-20211015-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-15 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Flll toFlOO level ruts & drainage isting material from F088 to 34.SKm as per Valard. Supervise Morin, Skagen, Pleson, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1L.O.A.0.8636364210.7273OEWT-PA22-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7457 | KL-20211015-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-15 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Flll toFlOO level ruts & drainage isting material from F088 to 34.SKm as per Valard. Supervise Morin, Skagen, Pleson, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1L.O.A.0.8636364210.7273OEWT-PA22-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7457 | KL-20211015-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-15 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Flll toFlOO level ruts & drainage isting material from F088 to 34.SKm as per Valard. Supervise Morin, Skagen, Pleson, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1L.O.A.0.8636364210.7273OEWT-PA22-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7460 | KL-20211016-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-10-16 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F194 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1L.O.A.0.7727273188.5455OEWT-PA22-Lem | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7460 | KL-20211016-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-10-16 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F194 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1L.O.A.0.7727273188.5455OEWT-PA22-Lem | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7460 | KL-20211016-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-16 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F194 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1L.O.A.0.8636364210.7273OEWT-PA22-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7414 | KL-20211001-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-01 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7414 | KL-20211001-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-01 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7414 | KL-20211001-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-01 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-1L.O.A.0.9090909221.8182OEWT-PA22-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7414 | KL-20211001-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-01 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-1L.O.A.0.9090909221.8182OEWT-PA22-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7419 | KL-20211002-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-02 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7419 | KL-20211002-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-02 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7419 | KL-20211002-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.5 | Day |  | 0 |  |  | 122 | 15.86 | 137.86 | 2021-10-02 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-1L.O.A.0.5122 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-1L.O.A.0.5122OEWT-PA22-Lem | [5 empty] | 1 | 122 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7419 | KL-20211002-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-02 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7421 | KL-20211003-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-10-03 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading & hauling from 46km to 45km. Labourers hauling fuel to 35km & installing silt fencing as per Valard. Supervision o Skagen & Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-1L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-1L.O.A.0.7727273188.5455OEWT-PA22-Lem | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7421 | KL-20211003-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-10-03 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading & hauling from 46km to 45km. Labourers hauling fuel to 35km & installing silt fencing as per Valard. Supervision o Skagen & Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-1L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-1L.O.A.0.7727273188.5455OEWT-PA22-Lem | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7421 | KL-20211003-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-10-03 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading & hauling from 46km to 45km. Labourers hauling fuel to 35km & installing silt fencing as per Valard. Supervision o Skagen & Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-1L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-1L.O.A.0.7727273188.5455OEWT-PA22-Lem | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7424 | KL-20211004-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-04 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working from Paint 2 to F115. excavator 2 working from 45km to 43km. Rock truck hauling existing material from 37.5km to Skagen @36km. Supervision of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7424KL-20211004-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7424KL-20211004-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7424 | KL-20211004-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-04 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working from Paint 2 to F115. excavator 2 working from 45km to 43km. Rock truck hauling existing material from 37.5km to Skagen @36km. Supervision of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7424KL-20211004-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7424KL-20211004-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7424 | KL-20211004-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-04 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working from Paint 2 to F115. excavator 2 working from 45km to 43km. Rock truck hauling existing material from 37.5km to Skagen @36km. Supervision of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7424KL-20211004-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7424KL-20211004-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7431 | KL-20211006-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-06 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7431 | KL-20211006-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-06 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7431 | KL-20211006-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-06 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7431 | KL-20211006-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-06 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-1L.O.A.0.9090909221.8182OEWT-PA22-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7434 | KL-20211007-1-R1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-07 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7434 | KL-20211007-1-R1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-07 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7434 | KL-20211007-1-R1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-07 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R1L.O.A.0.9090909221.8182OEWT-PA22-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7434 | KL-20211007-1-R1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.68182 | Day |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2021-10-07 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R1L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R1L.O.A.0.6818182166.3636OEWT-PA22-Lem | [5 empty] | 1 | 166.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7439 | KL-20211009-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-09 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km. Rock trucks on site for gravel haul. Supervision of Morin & Skagen. | 10 | F033 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7439 | KL-20211009-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-09 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km. Rock trucks on site for gravel haul. Supervision of Morin & Skagen. | 10 | F033 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7439 | KL-20211009-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-10-09 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km. Rock trucks on site for gravel haul. Supervision of Morin & Skagen. | 10 | F033 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-1L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-1L.O.A.0.4545455110.9091OEWT-PA22-Lem | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7439 | KL-20211009-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-10-09 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km. Rock trucks on site for gravel haul. Supervision of Morin & Skagen. | 10 | F033 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-1L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-1L.O.A.0.4545455110.9091OEWT-PA22-Lem | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7441 | KL-20211010-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-10 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, corduroy & cap 43km hill. Rock trucks on site for gravel haul. Supervise Morin & Skagen. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7441 | KL-20211010-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-10 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, corduroy & cap 43km hill. Rock trucks on site for gravel haul. Supervise Morin & Skagen. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7441 | KL-20211010-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-10-10 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, corduroy & cap 43km hill. Rock trucks on site for gravel haul. Supervise Morin & Skagen. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-1L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-1L.O.A.0.363636488.7273OEWT-PA22-Lem | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7441 | KL-20211010-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-10-10 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, corduroy & cap 43km hill. Rock trucks on site for gravel haul. Supervise Morin & Skagen. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-1L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-1L.O.A.0.363636488.7273OEWT-PA22-Lem | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7442 | KL-20211011-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-11 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, levelling ruts & drainage. Rock trucks on site for gravel haul. Supervisor touring for blasting locations. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7442 | KL-20211011-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-11 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, levelling ruts & drainage. Rock trucks on site for gravel haul. Supervisor touring for blasting locations. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7442 | KL-20211011-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-10-11 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, levelling ruts & drainage. Rock trucks on site for gravel haul. Supervisor touring for blasting locations. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-1L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-1L.O.A.0.363636488.7273OEWT-PA22-Lem | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7442 | KL-20211011-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-10-11 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, levelling ruts & drainage. Rock trucks on site for gravel haul. Supervisor touring for blasting locations. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-1L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-1L.O.A.0.363636488.7273OEWT-PA22-Lem | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7444 | KL-20211008-1-R1 | 53511012 | Access | 0 | L.O.A. | 244 | 2.8182 | Day |  | 0 |  |  | 687.6364 | 89.3927 | 777.0291 | 2021-10-08 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7444KL-20211008-1-R1L.O.A.2.8181818687.6364 | KABI LAKE FOREST PRODUCTS LTD7444KL-20211008-1-R1L.O.A.2.8181818687.6364OEWT-PA22-Lem | [5 empty] | 1 | 687.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7445 | KL-20211012-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-12 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45 to 43km. Excavator 2 working from 43 to 40.5km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervisor site visit with blaster. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7445 | KL-20211012-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-12 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45 to 43km. Excavator 2 working from 43 to 40.5km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervisor site visit with blaster. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7445 | KL-20211012-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-10-12 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45 to 43km. Excavator 2 working from 43 to 40.5km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervisor site visit with blaster. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-1L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-1L.O.A.0.363636488.7273OEWT-PA22-Lem | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7445 | KL-20211012-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-10-12 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45 to 43km. Excavator 2 working from 43 to 40.5km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervisor site visit with blaster. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-1L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-1L.O.A.0.363636488.7273OEWT-PA22-Lem | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7445 | KL-20211012-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-10-12 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45 to 43km. Excavator 2 working from 43 to 40.5km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervisor site visit with blaster. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-1L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-1L.O.A.0.363636488.7273OEWT-PA22-Lem | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7448 | KL-20211013-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-13 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 46 to 43km. Excavator 2 working from 43 to 39km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervision of Morin, Skagen, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7448 | KL-20211013-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-13 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 46 to 43km. Excavator 2 working from 43 to 39km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervision of Morin, Skagen, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7448 | KL-20211013-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-10-13 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 46 to 43km. Excavator 2 working from 43 to 39km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervision of Morin, Skagen, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-1L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-1L.O.A.0.363636488.7273OEWT-PA22-Lem | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7448 | KL-20211013-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-10-13 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 46 to 43km. Excavator 2 working from 43 to 39km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervision of Morin, Skagen, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-1L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-1L.O.A.0.363636488.7273OEWT-PA22-Lem | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7448 | KL-20211013-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-10-13 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 46 to 43km. Excavator 2 working from 43 to 39km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervision of Morin, Skagen, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-1L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-1L.O.A.0.363636488.7273OEWT-PA22-Lem | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7453 | KL-20211014-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-14 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from 46 to 39Km, levelling ruts & drainage. Rock trucks haulig existing material from F088 to 34.5Km. Labourer hauling fuel as per Valard. Supervision of Morin, Skagen & Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7453 | KL-20211014-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-14 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from 46 to 39Km, levelling ruts & drainage. Rock trucks haulig existing material from F088 to 34.5Km. Labourer hauling fuel as per Valard. Supervision of Morin, Skagen & Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7453 | KL-20211014-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-14 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from 46 to 39Km, levelling ruts & drainage. Rock trucks haulig existing material from F088 to 34.5Km. Labourer hauling fuel as per Valard. Supervision of Morin, Skagen & Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-1L.O.A.0.9090909221.8182OEWT-PA22-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7453 | KL-20211014-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-14 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from 46 to 39Km, levelling ruts & drainage. Rock trucks haulig existing material from F088 to 34.5Km. Labourer hauling fuel as per Valard. Supervision of Morin, Skagen & Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-1L.O.A.0.9090909221.8182OEWT-PA22-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7460 | KL-20211016-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-16 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F194 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1L.O.A.0.8636364210.7273OEWT-PA22-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7460 | KL-20211016-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-16 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F194 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1L.O.A.0.8636364210.7273OEWT-PA22-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7465 | KL-20211017-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-17 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F108, F105,and F103 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | PAINT Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7465 | KL-20211017-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-17 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F108, F105,and F103 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | PAINT Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7465 | KL-20211017-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-17 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F108, F105,and F103 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | PAINT Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-1L.O.A.0.8636364210.7273OEWT-PA22-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7465 | KL-20211017-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-17 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F108, F105,and F103 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | PAINT Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-1L.O.A.0.8636364210.7273OEWT-PA22-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7465 | KL-20211017-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-17 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F108, F105,and F103 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | PAINT Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-1L.O.A.0.8636364210.7273OEWT-PA22-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7471 | KL-20211018-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-18 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34 as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7471 | KL-20211018-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-18 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34 as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7471 | KL-20211018-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-18 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34 as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1L.O.A.0.8636364210.7273OEWT-PA22-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7471 | KL-20211018-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-18 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34 as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1L.O.A.0.8636364210.7273OEWT-PA22-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7471 | KL-20211018-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-18 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34 as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1L.O.A.0.8636364210.7273OEWT-PA22-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7475 | KL-20211019-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-19 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts, laying Geo and spreading existing material @ Km 42 hill/rock trucks hauling existing material from F088 to Km 34 as per Valard. Labourers picking up 4 roll of Geo @12km on Paint Lake Road 2and deliver it to km 42/worked late to finish capping @km 42 for pickup access/Supervision of Morin, Skagen, Pleson and Opas | 10 |  | Paint | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1L.O.A.0.8636364210.7273OEWT-PA22-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7475 | KL-20211019-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-19 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts, laying Geo and spreading existing material @ Km 42 hill/rock trucks hauling existing material from F088 to Km 34 as per Valard. Labourers picking up 4 roll of Geo @12km on Paint Lake Road 2and deliver it to km 42/worked late to finish capping @km 42 for pickup access/Supervision of Morin, Skagen, Pleson and Opas | 10 |  | Paint | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1L.O.A.0.9090909221.8182OEWT-PA22-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7475 | KL-20211019-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-19 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts, laying Geo and spreading existing material @ Km 42 hill/rock trucks hauling existing material from F088 to Km 34 as per Valard. Labourers picking up 4 roll of Geo @12km on Paint Lake Road 2and deliver it to km 42/worked late to finish capping @km 42 for pickup access/Supervision of Morin, Skagen, Pleson and Opas | 10 |  | Paint | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1L.O.A.0.9090909221.8182OEWT-PA22-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7475 | KL-20211019-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-19 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts, laying Geo and spreading existing material @ Km 42 hill/rock trucks hauling existing material from F088 to Km 34 as per Valard. Labourers picking up 4 roll of Geo @12km on Paint Lake Road 2and deliver it to km 42/worked late to finish capping @km 42 for pickup access/Supervision of Morin, Skagen, Pleson and Opas | 10 |  | Paint | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1L.O.A.0.9090909221.8182OEWT-PA22-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7475 | KL-20211019-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-19 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts, laying Geo and spreading existing material @ Km 42 hill/rock trucks hauling existing material from F088 to Km 34 as per Valard. Labourers picking up 4 roll of Geo @12km on Paint Lake Road 2and deliver it to km 42/worked late to finish capping @km 42 for pickup access/Supervision of Morin, Skagen, Pleson and Opas | 10 |  | Paint | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1L.O.A.0.9090909221.8182OEWT-PA22-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7478 | KL-20211020-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-20 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material @ Km 42.5/rock trucks hauling existing material from F088 to Km 34 and Km 42.5 as per Valard. Excavator 3 tracking from Km 49, starting @ F112 to F114 leveling ruts,shaping and drainage/725 rock truck driving to Km .5 for float/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7478 | KL-20211020-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-20 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material @ Km 42.5/rock trucks hauling existing material from F088 to Km 34 and Km 42.5 as per Valard. Excavator 3 tracking from Km 49, starting @ F112 to F114 leveling ruts,shaping and drainage/725 rock truck driving to Km .5 for float/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7478 | KL-20211020-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-20 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material @ Km 42.5/rock trucks hauling existing material from F088 to Km 34 and Km 42.5 as per Valard. Excavator 3 tracking from Km 49, starting @ F112 to F114 leveling ruts,shaping and drainage/725 rock truck driving to Km .5 for float/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1L.O.A.0.8636364210.7273OEWT-PA22-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7478 | KL-20211020-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-20 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material @ Km 42.5/rock trucks hauling existing material from F088 to Km 34 and Km 42.5 as per Valard. Excavator 3 tracking from Km 49, starting @ F112 to F114 leveling ruts,shaping and drainage/725 rock truck driving to Km .5 for float/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1L.O.A.0.8636364210.7273OEWT-PA22-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7478 | KL-20211020-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-20 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material @ Km 42.5/rock trucks hauling existing material from F088 to Km 34 and Km 42.5 as per Valard. Excavator 3 tracking from Km 49, starting @ F112 to F114 leveling ruts,shaping and drainage/725 rock truck driving to Km .5 for float/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1L.O.A.0.8636364210.7273OEWT-PA22-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7478 | KL-20211020-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-20 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material @ Km 42.5/rock trucks hauling existing material from F088 to Km 34 and Km 42.5 as per Valard. Excavator 3 tracking from Km 49, starting @ F112 to F114 leveling ruts,shaping and drainage/725 rock truck driving to Km .5 for float/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1L.O.A.0.9090909221.8182OEWT-PA22-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7480 | KL-20211021-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-21 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material on sections/rock trucks hauling existing material from F088 as per Valard. Excavator 3 continuing @ F113 to F115 leveling ruts,shaping and drainage for freezing/ Supervision of Morin, Skagen, Pleson and Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7480 | KL-20211021-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-21 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material on sections/rock trucks hauling existing material from F088 as per Valard. Excavator 3 continuing @ F113 to F115 leveling ruts,shaping and drainage for freezing/ Supervision of Morin, Skagen, Pleson and Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7480 | KL-20211021-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-21 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material on sections/rock trucks hauling existing material from F088 as per Valard. Excavator 3 continuing @ F113 to F115 leveling ruts,shaping and drainage for freezing/ Supervision of Morin, Skagen, Pleson and Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7480 | KL-20211021-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-21 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material on sections/rock trucks hauling existing material from F088 as per Valard. Excavator 3 continuing @ F113 to F115 leveling ruts,shaping and drainage for freezing/ Supervision of Morin, Skagen, Pleson and Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7482 | KL-20211022-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-22 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 working from Km 43 to Km 40 and F105 access Shaping road/ excavator 2 working from Km 43 to Km 45 and F111 shaping road. Excavator 3 Finishing @ F115 to F117 leveling ruts,shaping for freezing and track to F123/ Supervision of Morin, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44495 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7482KL-20211022-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7482KL-20211022-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7482 | KL-20211022-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-22 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 working from Km 43 to Km 40 and F105 access Shaping road/ excavator 2 working from Km 43 to Km 45 and F111 shaping road. Excavator 3 Finishing @ F115 to F117 leveling ruts,shaping for freezing and track to F123/ Supervision of Morin, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44495 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7482KL-20211022-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7482KL-20211022-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7482 | KL-20211022-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-22 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 working from Km 43 to Km 40 and F105 access Shaping road/ excavator 2 working from Km 43 to Km 45 and F111 shaping road. Excavator 3 Finishing @ F115 to F117 leveling ruts,shaping for freezing and track to F123/ Supervision of Morin, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44495 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7482KL-20211022-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7482KL-20211022-1L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7483 | KL-20211023-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-23 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 shaping road from Km 43 to Km 40 anf F098/ Excavator 2 shaping road from 45 to 49 km and starting in F123 access/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44495 |  | 61 | 44496 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7483KL-20211023-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7483KL-20211023-1L.O.A.0.8636364210.7273OEWT-PA22-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7483 | KL-20211023-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-23 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 shaping road from Km 43 to Km 40 anf F098/ Excavator 2 shaping road from 45 to 49 km and starting in F123 access/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44495 |  | 61 | 44496 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7483KL-20211023-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7483KL-20211023-1L.O.A.0.8636364210.7273OEWT-PA22-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7485 | KL-20211024-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from Km 46 and F105 access/supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44496 |  | 61 | 44497 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7485KL-20211024-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7485KL-20211024-1L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7488 | KL-20211025-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from Km 44 to Km 40 and F105 access/supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44496 |  | 61 | 44497 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7488KL-20211025-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7488KL-20211025-1L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7492 | KL-20211026-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-26 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from F110 to Km 41 /supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7492KL-20211026-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7492KL-20211026-1L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7496 | KL-20211027-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 44, laying Geo and spreading existing material/Excavtor 2 loading existing material@ km 17 on Hensen/rock truck hauling existing material to Km 44 supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-1L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7496 | KL-20211027-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 44, laying Geo and spreading existing material/Excavtor 2 loading existing material@ km 17 on Hensen/rock truck hauling existing material to Km 44 supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-1L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-1L.O.A.0.4545455110.9091OEWT-PA23-Lem | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7496 | KL-20211027-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 44, laying Geo and spreading existing material/Excavtor 2 loading existing material@ km 17 on Hensen/rock truck hauling existing material to Km 44 supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-1L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-1L.O.A.0.4545455110.9091OEWT-PA23-Lem | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7496 | KL-20211027-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 44, laying Geo and spreading existing material/Excavtor 2 loading existing material@ km 17 on Hensen/rock truck hauling existing material to Km 44 supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-1L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-1L.O.A.0.4545455110.9091OEWT-PA23-Lem | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7502 | KL-20211028-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-10-28 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 laying Geo and spreading existing material @ Km 44 and shaping road to Km 45/Excavtor 2 cleaning up excavation @ km 17 on Hensen road and shaping road to F114 rock truck2 hauling from F088 to Km 34-33 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-1L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-1L.O.A.0.4545455110.9091OEWT-PA23-Lem | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7502 | KL-20211028-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-28 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 laying Geo and spreading existing material @ Km 44 and shaping road to Km 45/Excavtor 2 cleaning up excavation @ km 17 on Hensen road and shaping road to F114 rock truck2 hauling from F088 to Km 34-33 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-1L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7502 | KL-20211028-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.5 | Day |  | 0 |  |  | 122 | 15.86 | 137.86 | 2021-10-28 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 laying Geo and spreading existing material @ Km 44 and shaping road to Km 45/Excavtor 2 cleaning up excavation @ km 17 on Hensen road and shaping road to F114 rock truck2 hauling from F088 to Km 34-33 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-1L.O.A.0.5122 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-1L.O.A.0.5122OEWT-PA23-Lem | [5 empty] | 1 | 122 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7502 | KL-20211028-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-28 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 laying Geo and spreading existing material @ Km 44 and shaping road to Km 45/Excavtor 2 cleaning up excavation @ km 17 on Hensen road and shaping road to F114 rock truck2 hauling from F088 to Km 34-33 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-1L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7506 | KL-20211029-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-10-29 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing clean up of excavation @ Km 17 on Hensen road and start shaping road to Km 45.5. Rock truck hauling existing material from F088 to Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44502 |  | 61 | 44503 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7506KL-20211029-1L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7506KL-20211029-1L.O.A.0.7272727177.4545OEWT-PA23-Lem | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7506 | KL-20211029-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-29 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing clean up of excavation @ Km 17 on Hensen road and start shaping road to Km 45.5. Rock truck hauling existing material from F088 to Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44502 |  | 61 | 44503 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7506KL-20211029-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7506KL-20211029-1L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7510 | KL-20211030-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-30 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road to Km 45 to Km 43 and spreading spotted rock trucks loads. Rock truck hauling existing material from F088 to Morin @ Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas. | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44502 |  | 61 | 44503 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7510KL-20211030-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7510KL-20211030-1L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7510 | KL-20211030-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-30 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road to Km 45 to Km 43 and spreading spotted rock trucks loads. Rock truck hauling existing material from F088 to Morin @ Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas. | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44502 |  | 61 | 44503 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7510KL-20211030-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7510KL-20211030-1L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7517 | KL-20211031-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-31 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 43 to Km 40.5 and spreading spotted rock trucks loads /Excavator 2 leveling ruts and shaping road from F116 to F112 rock truck hauling existing material from F088 to Morin @ Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F033 - F071 | Paint Lake 2 | 0 | 44505 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7517KL-20211031-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7517KL-20211031-1L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7517 | KL-20211031-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.68182 | Day |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2021-10-31 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 43 to Km 40.5 and spreading spotted rock trucks loads /Excavator 2 leveling ruts and shaping road from F116 to F112 rock truck hauling existing material from F088 to Morin @ Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F033 - F071 | Paint Lake 2 | 0 | 44505 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7517KL-20211031-1L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD7517KL-20211031-1L.O.A.0.6818182166.3636OEWT-PA23-Lem | [5 empty] | 1 | 166.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7517 | KL-20211031-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-31 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 43 to Km 40.5 and spreading spotted rock trucks loads /Excavator 2 leveling ruts and shaping road from F116 to F112 rock truck hauling existing material from F088 to Morin @ Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F033 - F071 | Paint Lake 2 | 0 | 44505 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7517KL-20211031-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7517KL-20211031-1L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7519 | KL-20211101-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-11-01 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 43 to Km 40.5 and spreading spotted rock trucks loads. Rock truck hauling existing material from F-088 to Morin @ 33.5Km as per Valard. Supervision of Morin, Skagen, JJR & Opas | 10 | F033 - F071 | Paint Lake 2 | 0 | 44501 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7519KL-20211101-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7519KL-20211101-1L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7519 | KL-20211101-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-11-01 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 43 to Km 40.5 and spreading spotted rock trucks loads. Rock truck hauling existing material from F-088 to Morin @ 33.5Km as per Valard. Supervision of Morin, Skagen, JJR & Opas | 10 | F033 - F071 | Paint Lake 2 | 0 | 44501 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7519KL-20211101-1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7519KL-20211101-1L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7547 | KL-20211102-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2021-11-02 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking from Km 43 to Km 17 on Hensen Road for float access /Rock truck hauling existing material from F088 to Morin@Km 33 as per Valard. Supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-2L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-2L.O.A.0.181818244.3636OEWT-PA23-Lem | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7547 | KL-20211102-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-11-02 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking from Km 43 to Km 17 on Hensen Road for float access /Rock truck hauling existing material from F088 to Morin@Km 33 as per Valard. Supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-2L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7547 | KL-20211102-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-11-02 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking from Km 43 to Km 17 on Hensen Road for float access /Rock truck hauling existing material from F088 to Morin@Km 33 as per Valard. Supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-2L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7549 | KL-20211103-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-11-03 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 41 shape road. Rock trucks haul existing material from F088 to Morin @ Km 33 as per Valard /Supervision of Morin, Skagen, JJR, Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-2L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7549 | KL-20211103-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-11-03 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 41 shape road. Rock trucks haul existing material from F088 to Morin @ Km 33 as per Valard /Supervision of Morin, Skagen, JJR, Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-2L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7549 | KL-20211103-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-11-03 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 41 shape road. Rock trucks haul existing material from F088 to Morin @ Km 33 as per Valard /Supervision of Morin, Skagen, JJR, Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-2L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7566 | KL-20211111-4 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-11-11 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-4L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-4L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7566 | KL-20211111-4 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-11-11 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-4L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-4L.O.A.0.9090909221.8182OEWT-PA23-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7570 | KL-20211112-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.5 | Day |  | 0 |  |  | 122 | 15.86 | 137.86 | 2021-11-12 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44520 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7570KL-20211112-2L.O.A.0.5122 | KABI LAKE FOREST PRODUCTS LTD7570KL-20211112-2L.O.A.0.5122OEWT-PA23-Lem | [5 empty] | 1 | 122 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7570 | KL-20211112-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-11-12 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44520 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7570KL-20211112-2L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7570KL-20211112-2L.O.A.0.4545455110.9091OEWT-PA23-Lem | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7571 | KL-20211113-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-11-13 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Rock truck on site for hauling of existing material @ 24km. Supervision of Morin, Skagen, JJR & Opas. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7571KL-20211113-3L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7571KL-20211113-3L.O.A.0.363636488.7273OEWT-PA23-Lem | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7572 | KL-20211114-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-11-14 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from 44Km to 41Km levelling ruts and shaping road. Rock truck on site for hauling of existing material @ 27Km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7572KL-20211114-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7572KL-20211114-2L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7572 | KL-20211114-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-11-14 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from 44Km to 41Km levelling ruts and shaping road. Rock truck on site for hauling of existing material @ 27Km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7572KL-20211114-2L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7572KL-20211114-2L.O.A.0.363636488.7273OEWT-PA23-Lem | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7565 | KL-20211110-4 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-11-10 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 42 access leveling ruts and shaping road rock trucks hauling from Km 27 to JJR @ Km 26/24 repairing road sections /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-4L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-4L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7565 | KL-20211110-4 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-11-10 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 42 access leveling ruts and shaping road rock trucks hauling from Km 27 to JJR @ Km 26/24 repairing road sections /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-4L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-4L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7565 | KL-20211110-4 | 53511012 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-11-10 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 42 access leveling ruts and shaping road rock trucks hauling from Km 27 to JJR @ Km 26/24 repairing road sections /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-4L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-4L.O.A.0.4545455110.9091OEWT-PA23-Lem | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7573 | KL-20211115-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-11-15 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road. Rock truck hauling existing material from 25Km and spotting dumping @ 22/23Km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7573KL-20211115-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7573KL-20211115-2L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7573 | KL-20211115-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-11-15 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road. Rock truck hauling existing material from 25Km and spotting dumping @ 22/23Km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7573KL-20211115-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7573KL-20211115-2L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7575 | KL-20211116-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-11-16 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road for freezing. Rock truck hauling existing material from 27Km to 23/24Km & dricing out to 9Km at end of shift for float accesss. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-3L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7575 | KL-20211116-3 | 53511012 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2021-11-16 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road for freezing. Rock truck hauling existing material from 27Km to 23/24Km & dricing out to 9Km at end of shift for float accesss. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-3L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-3L.O.A.1244OEWT-PA23-Lem | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7576 | KL-20211117-4 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-11-17 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road & snow removal @ 44km to 43km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7576KL-20211117-4L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7576KL-20211117-4L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7577 | KL-20211118-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-11-18 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 43 to Km 46 due to icy conditions /Supervision of Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44525 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7577KL-20211118-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7577KL-20211118-3L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7550 | KL-20211104-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-11-04 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 42 shaping road and spreading existing material on road surfaces Rock trucks hauling existing material from F088 to @ Km 43/42 as per Valard /Supervision of Morin, Skagen, JJR and OPAS | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-2L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7550 | KL-20211104-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-11-04 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 42 shaping road and spreading existing material on road surfaces Rock trucks hauling existing material from F088 to @ Km 43/42 as per Valard /Supervision of Morin, Skagen, JJR and OPAS | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-2L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7550 | KL-20211104-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-11-04 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 42 shaping road and spreading existing material on road surfaces Rock trucks hauling existing material from F088 to @ Km 43/42 as per Valard /Supervision of Morin, Skagen, JJR and OPAS | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-2L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7551 | KL-20211105-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-11-05 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 42 to Km 41 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F088 to @ Km 42/41 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-2L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7551 | KL-20211105-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-11-05 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 42 to Km 41 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F088 to @ Km 42/41 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-2L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7551 | KL-20211105-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-11-05 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 42 to Km 41 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F088 to @ Km 42/41 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-2L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7553 | KL-20211107-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-11-07 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working fro Km 41 to Km 39 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 41/39 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-2L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7553 | KL-20211107-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-11-07 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working fro Km 41 to Km 39 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 41/39 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-2L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7553 | KL-20211107-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-11-07 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working fro Km 41 to Km 39 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 41/39 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-2L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7562 | KL-20211106-2-R1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-11-06 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 41 to Km 40 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F093 to @ Km 41/40 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44522 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R1L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7562 | KL-20211106-2-R1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-11-06 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 41 to Km 40 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F093 to @ Km 41/40 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44522 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R1L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7562 | KL-20211106-2-R1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-11-06 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 41 to Km 40 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F093 to @ Km 41/40 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44522 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R1L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R1L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7563 | KL-20211108-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-11-08 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 42 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-3L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-3L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7563 | KL-20211108-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-11-08 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 42 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-3L.O.A.0.9090909221.8182OEWT-PA23-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7563 | KL-20211108-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-11-08 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 42 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-3L.O.A.0.9090909221.8182OEWT-PA23-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7564 | KL-20211109-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-11-09 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 44 leveling ruts and shaping road Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-3L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7564 | KL-20211109-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-11-09 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 44 leveling ruts and shaping road Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-3L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7564 | KL-20211109-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-11-09 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 44 leveling ruts and shaping road Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-3L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7583 | KL-20211119-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-11-19 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 43 to Km 40 due to icy conditions/Supervision of Morin, Skagen, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7583KL-20211119-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7583KL-20211119-3L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7584 | KL-20211120-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-11-20 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 42 to Km 46 due to slippery conditions/Supervision of Morin, Skagen, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7584KL-20211120-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7584KL-20211120-3L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7585 | KL-20211121-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-11-21 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and sanding road @ Km 42 to Km 46 due to slippery conditions/Supervision of Morin, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7585KL-20211121-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7585KL-20211121-2L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7587 | KL-20211123-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-11-23 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 scraping and shaping @ Km 42 to Km 46 /Excavator 2 scraping and sanding Km 13.5 to 17 for stringing crews/Supervision of Skagen and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7587KL-20211123-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7587KL-20211123-2L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7587 | KL-20211123-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-11-23 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 scraping and shaping @ Km 42 to Km 46 /Excavator 2 scraping and sanding Km 13.5 to 17 for stringing crews/Supervision of Skagen and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7587KL-20211123-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7587KL-20211123-2L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7590 | KL-20211124-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-11-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 scraping and shaping @ Km 45 to Km 48 /Excavator 2 scraping and sanding Km 16 to 18 for stringing crews demob | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7590KL-20211124-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7590KL-20211124-2L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7590 | KL-20211124-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-11-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 scraping and shaping @ Km 45 to Km 48 /Excavator 2 scraping and sanding Km 16 to 18 for stringing crews demob | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7590KL-20211124-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7590KL-20211124-2L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7932 | KL-20220305-1-RCL | 53541001 | Reclamation | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-03-05 |  | OEWT-PA27-RCL | 2022-03-31 |  | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 330 excavator clearing snow from ditches, and spreading ripped material. 336 excavator ripping frozen roadway F033-F034 | 10 | F066-F118 | Paint Lake 2 | 0 | 44625 |  | 37 | 44625 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7932KL-20220305-1-RCLL.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7932KL-20220305-1-RCLL.O.A.0.8181818199.6364 | WF10-Access | WF10-Access | WF10-Access | 1 | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7932 | KL-20220305-1-RCL | 53541001 | Reclamation | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-03-05 |  | OEWT-PA27-RCL | 2022-03-31 |  | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 330 excavator clearing snow from ditches, and spreading ripped material. 336 excavator ripping frozen roadway F033-F034 | 10 | F066-F118 | Paint Lake 2 | 0 | 44625 |  | 37 | 44625 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7932KL-20220305-1-RCLL.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7932KL-20220305-1-RCLL.O.A.0.8181818199.6364 | WF10-Access | WF10-Access | WF10-Access | 1 | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3631 | KL-20201009-20 | 53511102 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2020-10-09 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Shaping Road and Widing Areas | 11 | F-119 to F-134 | Hensen Road | 0 | 44125 |  | 55 | 44129 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD3631KL-20201009-20L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD3631KL-20201009-20L.O.A.0.5454545133.0909OEWT-PA10-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5248 | KL-20210106-12 | 53511102 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2021-01-06 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track Excavator from F117 to F127 due to no float Access/ Operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44209 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5248KL-20210106-12L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD5248KL-20210106-12L.O.A.0.181818244.3636OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5330 | KL-20210112-17 | 53511102 | Access | 0 | L.O.A. | 244 | 0.22727 | Day |  | 0 |  |  | 55.4545 | 7.2091 | 62.6636 | 2021-01-12 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track from 17km to F127.5 due to no float access. | 11 | f119-F134 | Hensen Road | 0 | 44214 |  | 15 | 44219 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5330KL-20210112-17L.O.A.0.227272755.4545 | KABI LAKE FOREST PRODUCTS LTD5330KL-20210112-17L.O.A.0.227272755.4545OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5442 | KL-20210118-16 | 53511102 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-01-18 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator filling gorge with trees for fill @ F144/F143 Access (Revised | 11 | F135-F149 | Dore Lake Road | 0 | 44216 |  | 56 | 44229 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5442KL-20210118-16L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD5442KL-20210118-16L.O.A.0.7272727177.4545OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5475 | KL-20210119-26 | 53511102 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2021-01-19 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator starting to make ramp with trees for F133 Hub | 11 | F119-F134 | Hensen Road | 0 | 44222 |  | 15 | 44238 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5475KL-20210119-26L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD5475KL-20210119-26L.O.A.0.272727366.5455OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5496 | KL-20210120-18 | 53511102 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Exc finishing making ramp with trees and capping for F133 Hub Access & track to F114/Operator Extra travel/Based out of White River. | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5496KL-20210120-18L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD5496KL-20210120-18L.O.A.0.7272727177.4545OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5497 | KL-20210120-19 | 53511102 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336F excavator building new road around F128 structure as per Valard/Operator extra travel/based out of White River | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5497KL-20210120-19L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD5497KL-20210120-19L.O.A.0.7272727177.4545OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5539 | KL-20210122-17 | 53511102 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-01-22 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator using existing material to minimize steep grade at F117/F116 Access, as per Valard (Revised) | 11 | F119--F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5539KL-20210122-17L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD5539KL-20210122-17L.O.A.0.7727273188.5455OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5368 | KL-20210114-14 | 53511103 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-01-14 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Carry Corduroy for wetlands on F147 Access. Buncher rate from Const. Amend #4. | 11 | F135-F149 | Dore Lake Road | 0 | 44218 |  | 56 | 44220 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5368KL-20210114-14L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD5368KL-20210114-14L.O.A.0.363636488.7273OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5380 | KL-20210115-11 | 53511103 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2021-01-15 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Buncher track in and out from F147 access to F145 Junction. Morin track and place corduroy. Buncher rate from Const. Amend #4 | 11 | F135-F149 | Dore Lake Road | 0 | 44218 |  | 56 | 44220 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5380KL-20210115-11L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD5380KL-20210115-11L.O.A.0.181818244.3636OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5474 | KL-20210119-25 | 53511103 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-01-19 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 335F Boom Brusher tracking from F124 to F133 & start to grind & freeze corduroy for pick up access. | 11 | F119-F134 | Hensen Road | 0 | 44222 |  | 15 | 44237 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5474KL-20210119-25L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD5474KL-20210119-25L.O.A.0.363636488.7273OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5499 | KL-20210120-21 | 53511103 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 335F boom brusher finishing to grind & freeze corduroy for Pick up access & tracking back to F124 | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5499KL-20210120-21L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD5499KL-20210120-21L.O.A.0.363636488.7273OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5339 | KL-20210113-5 | 53511103 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-01-13 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Corduroy at F132 access | 11 | F119-F134 | Hensen Road | 0 | 44214 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5339KL-20210113-5L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD5339KL-20210113-5L.O.A.0.363636488.7273OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3273 | KL-20200927-17 | 53511104 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-09-27 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pit runfrom Provost pit #5/Dozer spreading | 11 | F-119 to F-134 | Hensen Road | 0 | 43900 |  | 48 | 43871 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3273KL-20200927-17L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD3273KL-20200927-17L.O.A.2488OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3300 | KL-20200928-23 | 53511104 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-09-28 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauling pit run from Provost Pit #5 to AE1 on Henson Road /Dozer spreading and widening areas | 11 | F-119 to F-134 | Hensen Road | 0 | 44109 |  | 50 | 44110 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD3300KL-20200928-23L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD3300KL-20200928-23L.O.A.1244OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3300 | KL-20200928-23 | 53511104 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-09-28 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauling pit run from Provost Pit #5 to AE1 on Henson Road /Dozer spreading and widening areas | 11 | F-119 to F-134 | Hensen Road | 0 | 44109 |  | 50 | 44110 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD3300KL-20200928-23L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD3300KL-20200928-23L.O.A.0.4545455110.9091OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3300 | KL-20200928-23 | 53511104 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-09-28 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauling pit run from Provost Pit #5 to AE1 on Henson Road /Dozer spreading and widening areas | 11 | F-119 to F-134 | Hensen Road | 0 | 44109 |  | 50 | 44110 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD3300KL-20200928-23L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD3300KL-20200928-23L.O.A.0.4545455110.9091OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3376 | KL-20201001-22 | 53511104 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-10-01 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Triaxles hauling Pit Run from Provost pit #5 , Dozer spreading and widening areas.Grade Hensen road for gravel Haul - SSF-14029.Haul Pit Run from Provost Pit #5 to AE1 on Hensen Road - JJR-70095. Hauled Gravel to Hensen Road from Provost Pit #5 - BMC-30121 | 11 | F-119 to F-134 | Hensen Road | 0 | 44118 |  | 48 | 44123 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3376KL-20201001-22L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD3376KL-20201001-22L.O.A.2488OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3376 | KL-20201001-22 | 53511104 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2020-10-01 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Triaxles hauling Pit Run from Provost pit #5 , Dozer spreading and widening areas.Grade Hensen road for gravel Haul - SSF-14029.Haul Pit Run from Provost Pit #5 to AE1 on Hensen Road - JJR-70095. Hauled Gravel to Hensen Road from Provost Pit #5 - BMC-30121 | 11 | F-119 to F-134 | Hensen Road | 0 | 44118 |  | 48 | 44123 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3376KL-20201001-22L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD3376KL-20201001-22L.O.A.0.8636364210.7273OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3404 | KL-20201002-24 | 53511104 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-10-02 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Tri axles hauling pit run from Provost Pit 5 - Dozer spreading and widening road. Haul Pit Run from Provost pit #5 to AE1 on Hensen Road - JJR-70096 | 11 | F-119 to F-134 | Hensen Road | 0 | 44106 |  | 48 | 44123 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3404KL-20201002-24L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD3404KL-20201002-24L.O.A.1244OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3404 | KL-20201002-24 | 53511104 | Access | 0 | L.O.A. | 244 | 0.68182 | Day |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2020-10-02 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Tri axles hauling pit run from Provost Pit 5 - Dozer spreading and widening road. Haul Pit Run from Provost pit #5 to AE1 on Hensen Road - JJR-70096 | 11 | F-119 to F-134 | Hensen Road | 0 | 44106 |  | 48 | 44123 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3404KL-20201002-24L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD3404KL-20201002-24L.O.A.0.6818182166.3636OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 166.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3404 | KL-20201002-24 | 53511104 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2020-10-02 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Tri axles hauling pit run from Provost Pit 5 - Dozer spreading and widening road. Haul Pit Run from Provost pit #5 to AE1 on Hensen Road - JJR-70096 | 11 | F-119 to F-134 | Hensen Road | 0 | 44106 |  | 48 | 44123 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3404KL-20201002-24L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD3404KL-20201002-24L.O.A.0.409090999.8182OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3411 | KL-20200930-19 | 53511104 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-09-30 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer spreading Pit Run from Provost Pit #5 and widening areas. Trucks hauling gravel from Provost Pit | 11 | F-119 to F-134 | Hensen Road | 0 | 44119 |  | 48 | 44120 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3411KL-20200930-19L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD3411KL-20200930-19L.O.A.1244OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3831 | KL-20201018-15 | 53511104 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2020-10-18 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauled 2 load pit run from Provost pit 5 to Km 3 on hensen road Culverts. Cress install cross drain culverts. 330 excavator installed 3 200mm culverts, Km 6.5, 4.5, 2 - A lot of travelling with Machine -travelled Km 10 to 2 - CR-10821 | 11 | F-119 to F-134 | Hensen Road | 0 | 44130 |  | 55 | 44132 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD3831KL-20201018-15L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD3831KL-20201018-15L.O.A.0.409090999.8182OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4084 | KL-20201031-12 | 53511111 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2020-10-31 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sand Hills and corners on Hensen Road for float truck hauling in a buncher/Sanding hauled from provost pit in Wawa | 11 | F203-F211 | Hensen Rd | 0 | 44152 |  | 48 | 44154 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4084KL-20201031-12L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD4084KL-20201031-12L.O.A.1244OEWT-PA11-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4992 | KL-20201211-12 | 53511111 | Access | 0 | L.O.A. | 244 | 1.0909 | Day |  | 0 |  |  | 266.1818 | 34.6036 | 300.7854 | 2020-12-11 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load partial load @6km pit on 600 road for sanding of hill laydown 1/ load sand from F119 and sand road for float access as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 48 | 44203 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4992KL-20201211-12L.O.A.1.0909091266.1818 | KABI LAKE FOREST PRODUCTS LTD4992KL-20201211-12L.O.A.1.0909091266.1818OEWT-PA12-LEM-R1 | [5 empty] | 1 | 266.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5160 | KL-20201228-11 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2020-12-28 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding Hills & Corners on Hensen Rd from Hwy to Km 17 for 60' bridge delivery. Dozer and grader clearing different sections of Hensen Rd. | 11 | F119-F134 | Hensen Road | 0 | 44202 |  | 56 | 44214 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5160KL-20201228-11L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD5160KL-20201228-11L.O.A.0.9090909221.8182OEWT-PA13-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5207 | KL-20210103-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.13636 | Day |  | 0 |  |  | 33.2727 | 4.3255 | 37.5982 | 2021-01-03 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load of sand from White River town pit/ sanding hills and corners on hensen road from hwy to 17km with existing material as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5207KL-20210103-5L.O.A.0.136363633.2727 | KABI LAKE FOREST PRODUCTS LTD5207KL-20210103-5L.O.A.0.136363633.2727OEWT-PA13-LEM | [5 empty] | 1 | 33.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5207 | KL-20210103-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-01-03 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load of sand from White River town pit/ sanding hills and corners on hensen road from hwy to 17km with existing material as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5207KL-20210103-5L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD5207KL-20210103-5L.O.A.0.9090909221.8182OEWT-PA13-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5283 | KL-20210109-6 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-01-09 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Take 1 load of screened sand from town pit, and finish sanding Hensen Rd to km 17. Floats with existing sand as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44211 |  | 15 | 44219 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5283KL-20210109-6L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD5283KL-20210109-6L.O.A.0.9090909221.8182OEWT-PA13-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5283 | KL-20210109-6 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-01-09 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Take 1 load of screened sand from town pit, and finish sanding Hensen Rd to km 17. Floats with existing sand as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44211 |  | 15 | 44219 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5283KL-20210109-6L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD5283KL-20210109-6L.O.A.0.363636488.7273OEWT-PA13-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5363 | KL-20210114-9 | 53511111 | Access | 0 | L.O.A. | 244 | 0.090909 | Day |  | 0 |  |  | 22.1818 | 2.8836 | 25.0654 | 2021-01-14 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load screened sand from town pit and finished sanding Hensen Road to 17km with existing sand as per Valard/ Excavator cleaning up @ F119 for Sand | 11 | F119-F134 | Hensen Road | 0 | 44218 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5363KL-20210114-9L.O.A.0.090909122.1818 | KABI LAKE FOREST PRODUCTS LTD5363KL-20210114-9L.O.A.0.090909122.1818OEWT-PA13-LEM | [5 empty] | 1 | 22.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5363 | KL-20210114-9 | 53511111 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2021-01-14 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load screened sand from town pit and finished sanding Hensen Road to 17km with existing sand as per Valard/ Excavator cleaning up @ F119 for Sand | 11 | F119-F134 | Hensen Road | 0 | 44218 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5363KL-20210114-9L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD5363KL-20210114-9L.O.A.0.181818244.3636OEWT-PA13-LEM | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5363 | KL-20210114-9 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-01-14 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load screened sand from town pit and finished sanding Hensen Road to 17km with existing sand as per Valard/ Excavator cleaning up @ F119 for Sand | 11 | F119-F134 | Hensen Road | 0 | 44218 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5363KL-20210114-9L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD5363KL-20210114-9L.O.A.0.9090909221.8182OEWT-PA13-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5439 | KL-20210118-13 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-01-18 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6K Dozer Clearing snow from Anjigami Rd to Anjigami River for Bridge delivery as per Valard. | 11 | F228 | F-228 Road | 0 | 44216 |  | 56 | 44229 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5439KL-20210118-13L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD5439KL-20210118-13L.O.A.0.9090909221.8182OEWT-PA13-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5510 | KL-20210121-9 | 53511111 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-01-21 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer doing snow removal from km 17 on Hensen Rd to F133/Operator extra travel/Based out of White River. | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5510KL-20210121-9L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD5510KL-20210121-9L.O.A.0.7727273188.5455OEWT-PA13-LEM | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5555 | KL-20210123-14 | 53511111 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3637 | 5.7673 | 50.131 | 2021-01-23 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336F tracking out from F127 to 17km on Hensen due to no float access. Plowed out all pullouts and F117 Access | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5555KL-20210123-14L.O.A.0.181818344.3637 | KABI LAKE FOREST PRODUCTS LTD5555KL-20210123-14L.O.A.0.181818344.3637OEWT-PA13-LEM | [5 empty] | 1 | 44.3637 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5614 | KL-20210125-11 | 53511111 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-01-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | D6K dozer starting snow removal from km 17 on Hensen Rd to F133. | 11 | F119-F134 | Hensen Road | 0 | 44225 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5614KL-20210125-11L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD5614KL-20210125-11L.O.A.0.9545455232.9091OEWT-PA14-Lem-R1 | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5632 | KL-20210126-16 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-01-26 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | D6K Dozer finishing snow removal from km 17 on Hensen to F133. | 11 | F119-F134 | Hensen Road | 0 | 44222 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5632KL-20210126-16L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD5632KL-20210126-16L.O.A.0.9090909221.8182OEWT-PA14-Lem-R1 | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5700 | KL-20210201-8 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-02-01 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Drive from White River/Load Screened sand from Provost Pit #5/Sand hills and corners to 17km on hensen road/drive back to White River | 11 | F119-F134 | Hensen Road | 0 | 44235 |  | 53 | 44241 | [5 empty] | Clint Maerz | 11 | KABI LAKE FOREST PRODUCTS LTD5700KL-20210201-8L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD5700KL-20210201-8L.O.A.0.9090909221.8182OEWT-PA14-Lem-R1 | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5838 | KL-20210209-15 | 53511111 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2021-02-09 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Drive from White River/load 5 loads of screened sand from Provost Pit 5/Sand hills & corners to km 17 then drive back to White River. | 11 | F119-F134 | Hensen Road | 0 | 44243 |  | 15 | 44250 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5838KL-20210209-15L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD5838KL-20210209-15L.O.A.1244OEWT-PA14-Lem-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5874 | KL-20210212-5 | 53511111 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2021-02-12 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load 4 loads screen sand from Provost pit #5/ sand hills and corners to 17km on Hensen Road. Grader work form Hwy 17 to 17Km, loader open road to F110 to F112. | 11 | F119-F134 | Hensen Road | 0 | 44244 |  | 15 | 44254 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5874KL-20210212-5L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD5874KL-20210212-5L.O.A.1244OEWT-PA14-Lem-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5916 | KL-20210215-11 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-02-15 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat D5K Dozer to F169 for snow removal. Dozer remove snow from F169 to F165. | 11 | F165-F169 | Magpie Hills Road | 0 | 44249 |  | 14 | 44250 | [5 empty] | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD5916KL-20210215-11L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD5916KL-20210215-11L.O.A.0.363636488.7273OEWT-PA14-Lem-R1 | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6039 | KL-20210225-7 | 53511111 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2021-02-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator moving trees & levelling snow banks for snowmobile trail @ F232 | 11 | F232 | F-232 Road | 0 | 44256 |  | 56 | 44259 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6039KL-20210225-7L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD6039KL-20210225-7L.O.A.0.272727366.5455OEWT-PA14-Lem-R1 | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6048 | KL-20210225-16 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-02-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load of screeded sand from Town Pit/Haul 2 loads of screened sand from MacIntyre Pit/Sand hills & corners to km 17 on Hensen, drive back to White River | 11 | F119-F134 | Hensen Road | 0 | 44256 |  | 56 | 44262 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6048KL-20210225-16L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD6048KL-20210225-16L.O.A.0.9090909221.8182OEWT-PA14-Lem-R1 | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6100 | KL-20210226-10 | 53511111 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-02-26 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking to F212 access pushing snow back and clearing pull outs. Excavator brushing AE1 Access for F-228 and F-212 | 11 | F-212 to F-214 | Michipicoten Road- 1 | 0 | 44262 |  | 56 | 44265 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6100KL-20210226-10L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD6100KL-20210226-10L.O.A.0.4545455110.9091OEWT PA15-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6100 | KL-20210226-10 | 53511111 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-02-26 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking to F212 access pushing snow back and clearing pull outs. Excavator brushing AE1 Access for F-228 and F-212 | 11 | F-212 to F-214 | Michipicoten Road- 1 | 0 | 44262 |  | 56 | 44265 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6100KL-20210226-10L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD6100KL-20210226-10L.O.A.0.4545455110.9091OEWT PA15-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6124 | KL-20210228-10 | 53511111 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2021-02-28 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue snow removal on AE1 access to F212 | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44263 |  | 56 | 44265 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6124KL-20210228-10L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD6124KL-20210228-10L.O.A.0.5454545133.0909OEWT PA15-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6140 | KL-20210222-14 | 53511111 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2021-02-22 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer clearing roads km20 to km15, loader clearing km 0 to 5 Hensen West. | 11 | F119-F134 | Hensen Road | 0 | 44269 |  | 56 | 44270 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6140KL-20210222-14L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD6140KL-20210222-14L.O.A.0.5454545133.0909OEWT PA15-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6140 | KL-20210222-14 | 53511111 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-02-22 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer clearing roads km20 to km15, loader clearing km 0 to 5 Hensen West. | 11 | F119-F134 | Hensen Road | 0 | 44269 |  | 56 | 44270 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6140KL-20210222-14L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD6140KL-20210222-14L.O.A.0.7727273188.5455OEWT PA15-LEM | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5829 | KL-20210209-6 | 53511111 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2021-02-09 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul gravel, pull bridges and legos in, plow and sand roads. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44243 |  | 50 | 44249 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD5829KL-20210209-6L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD5829KL-20210209-6L.O.A.1244OEWT-PA14-Lem-R1 | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6346 | KL-20210316-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-03-16 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish tracking 2 excavators out from F215 to 9km on Ajigami road/pushing snow back for drainage (revised | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44281 |  | 56 | 44282 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6346KL-20210316-5L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD6346KL-20210316-5L.O.A.0.363636488.7273OEWT PA15-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6346 | KL-20210316-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-03-16 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish tracking 2 excavators out from F215 to 9km on Ajigami road/pushing snow back for drainage (revised | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44281 |  | 56 | 44282 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6346KL-20210316-5L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD6346KL-20210316-5L.O.A.0.363636488.7273OEWT PA15-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6347 | KL-20210316-6 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-03-16 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | D6T Dozer pushing snow banks back and clearing debris off the road fro F121/F215 access on Anjigami road | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44281 |  | 56 | 44282 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6347KL-20210316-6L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD6347KL-20210316-6L.O.A.0.9090909221.8182OEWT PA15-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6352 | KL-20210317-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-03-17 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track to F123/F124 from Km 17 on Hensen Road and repair hills for pick up use | 11 | F119-F134 | Hensen Road | 0 | 44281 |  | 56 | 44282 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6352KL-20210317-5L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD6352KL-20210317-5L.O.A.0.363636488.7273OEWT PA15-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6357 | KL-20210318-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-03-18 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair hills from F123 to F127 for pick up access | 11 | F119-F134 | Hensen Road | 0 | 44281 |  | 56 | 44282 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6357KL-20210318-3L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD6357KL-20210318-3L.O.A.0.363636488.7273OEWT PA15-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7598 | KL-20211126-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2021-11-26 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Skagen Volvo Grader from Anjigami to Km 13 on High Falls Road. Grader doing snow removal and widening road from Km 13 on High Falls Road to F207 and F199 - SSF- 14452 | 11 | F170 - F211 | High Falls | 0 | 44532 |  | 61 | 44534 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7598KL-20211126-2L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD7598KL-20211126-2L.O.A.0.409090999.8182OEWT-PA24-LEM | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7599 | KL-20211127-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-11-27 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float D6 Dozer from Robert's Road to Km 13 on High Falls Road | 11 | F170 - F211 | High Falls | 0 | 44532 |  | 61 | 44534 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7599KL-20211127-2L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7599KL-20211127-2L.O.A.0.4545455110.9091OEWT-PA24-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7592 | KL-20211124-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-11-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader continuing to scraping and sand road to F213/F214 for stringing crews | 11 | F212-F235 | Ainjigame | 0 | 44529 |  | 61 | 44530 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7592KL-20211124-4L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7592KL-20211124-4L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7594 | KL-20211125-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-11-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader continuing to scraping and sand road to F213, F217 and to F218 for stringing crews/ Supervision of Skagen | 11 | F212-F235 | Anjigame | 0 | 44525 |  | 61 | 44530 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7594KL-20211125-3L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7594KL-20211125-3L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7602 | KL-20211128-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-11-28 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and shaping road from F204 to F211 and to F200 / supervision of Skagen | 11 | F170-F211 | High Falls Road | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7602KL-20211128-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7602KL-20211128-2L.O.A.0.8636364210.7273OEWT-PA24-LEM | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7603 | KL-20211128-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-11-28 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 140M grader from Harte Gold Road to Hensen Road for snow removalas per Valard | 11 | F118-F127 | Hensen Road | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7603KL-20211128-3L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7603KL-20211128-3L.O.A.0.363636488.7273OEWT-PA24-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7605 | KL-20211129-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-11-29 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F203 to F185 / supervision of Skagen | 11 | F170-F211 | High Falls Road | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7605KL-20211129-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7605KL-20211129-2L.O.A.0.9090909221.8182OEWT-PA24-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7606 | KL-20211129-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-11-29 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17.5 on Hensen Road | 11 | F118-F127 | Hensen Road | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7606KL-20211129-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7606KL-20211129-3L.O.A.0.9090909221.8182OEWT-PA24-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7607 | KL-20211129-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-11-29 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader starting scraping and sanding road to F213/F214 for stringing crews | 11 | F212-F235 | Ainjigame Road | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7607KL-20211129-4L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7607KL-20211129-4L.O.A.0.363636488.7273OEWT-PA24-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7610 | KL-20211130-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-11-30 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader continuing scraping and sanding road to F213/F214 for stringing crews | 11 | F212-F235 | Anjigame Road | 0 | 44537 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7610KL-20211130-3L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7610KL-20211130-3L.O.A.0.8636364210.7273OEWT-PA24-LEM | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7611 | KL-20211130-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-11-30 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F184 to F181 and F177 to F171 / supervision of Skagen | 11 | F170-F211 | High Falls | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7611KL-20211130-4L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7611KL-20211130-4L.O.A.0.9090909221.8182OEWT-PA24-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7612 | KL-20211201-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-12-01 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal @ F179 to F180 and F193 to F181 / supervision of Skagen | 11 | F170-F212 | High Falls | 0 | 44537 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7612KL-20211201-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7612KL-20211201-2L.O.A.0.9090909221.8182OEWT-PA24-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7613 | KL-20211201-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2021-12-01 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat D6 Dozer from F185 to F196 Access | 11 | F170-F211 | High Falls | 0 | 44537 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7613KL-20211201-3L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD7613KL-20211201-3L.O.A.0.181818244.3636OEWT-PA24-LEM | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7615 | KL-20211201-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-01 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader starting scraping and sanding road to F213/F214 and access to F216 for stringing crews | 11 | F212-F235 | Anjigami | 0 | 44537 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7615KL-20211201-5L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7615KL-20211201-5L.O.A.0.8181818199.6364OEWT-PA24-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7616 | KL-20211201-6 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-12-01 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17.5 km on Hensen Road | 11 | F118-F127 | Henson | 0 | 44537 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7616KL-20211201-6L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7616KL-20211201-6L.O.A.0.9090909221.8182OEWT-PA24-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7617 | KL-20211201-7 | 53511111 | Access | 0 | L.O.A. | 244 | 0.5 | Day |  | 0 |  |  | 122 | 15.86 | 137.86 | 2021-12-01 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat D6 Dozer from White River to 17 Km on Hensen Road as per Valard / Chain up required | 11 | F118-F127 | Henson | 0 | 44537 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7617KL-20211201-7L.O.A.0.5122 | KABI LAKE FOREST PRODUCTS LTD7617KL-20211201-7L.O.A.0.5122OEWT-PA24-LEM | [5 empty] | 1 | 122 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7622 | KL-20211202-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17.5 on Hensen road/ Dozer working on snow removal and shaping road from F122 to F132 | 11 | F118 - F127 | Henson | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7622KL-20211202-4L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7622KL-20211202-4L.O.A.0.9090909221.8182OEWT-PA24-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7622 | KL-20211202-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17.5 on Hensen road/ Dozer working on snow removal and shaping road from F122 to F132 | 11 | F118 - F127 | Henson | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7622KL-20211202-4L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7622KL-20211202-4L.O.A.0.4545455110.9091OEWT-PA24-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7623 | KL-20211202-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader doing snow removal from Anjigami road to F218 | 11 | F212-F235 | Anjigame | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7623KL-20211202-5L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7623KL-20211202-5L.O.A.0.4545455110.9091OEWT-PA24-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7624 | KL-20211202-6 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 330 Excavator from North Regan Road for Winter Access to F151 | 11 | F128-F158 | MFN | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7624KL-20211202-6L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7624KL-20211202-6L.O.A.0.363636488.7273OEWT-PA24-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7626 | KL-20211202-8 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and shaping road @ F203 to F211 | 11 | F170-F211 | High Falls | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7626KL-20211202-8L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7626KL-20211202-8L.O.A.0.9090909221.8182OEWT-PA24-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7629 | KL-20211203-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2726 | 20.1854 | 175.458 | 2021-12-03 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and shaping road @ F198 to F202 and track to Km 11 on High Falls Raod/ Supervision of Skagen | 11 | F170 - F211 | High Falls | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7629KL-20211203-3L.O.A.0.636363155.2726 | KABI LAKE FOREST PRODUCTS LTD7629KL-20211203-3L.O.A.0.636363155.2726OEWT-PA24-LEM | [5 empty] | 1 | 155.2726 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7630 | KL-20211203-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2021-12-03 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on sections from Hwy 17 to Km 17.5 on Hensen road filling rough sections with snow | 11 | F118 - F127 | Henson | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7630KL-20211203-4L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7630KL-20211203-4L.O.A.0.6363636155.2727OEWT-PA24-LEM | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7634 | KL-20211204-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-04 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer tracking from Km 11 to 1.5, scraping road from F177 to F171 and assist stringing crews/ Supervision of Skagen | 11 | F170-F211 | High Falls | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7634KL-20211204-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7634KL-20211204-2L.O.A.0.8181818199.6364OEWT-PA24-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7635 | KL-20211204-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-12-04 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Graderworking on snow removal from Hwy 17 to Km 17 | 11 | F118 - F127 | Henson | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7635KL-20211204-3L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7635KL-20211204-3L.O.A.0.8636364210.7273OEWT-PA24-LEM | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7640 | KL-20211205-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.31818 | Day |  | 0 |  |  | 77.6364 | 10.0927 | 87.7291 | 2021-12-05 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 12M grader to 5.5 km on High Falls for snow removal | 11 | F170-F211 | High Falls | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7640KL-20211205-3L.O.A.0.318181877.6364 | KABI LAKE FOREST PRODUCTS LTD7640KL-20211205-3L.O.A.0.318181877.6364OEWT-PA24-LEM | [5 empty] | 1 | 77.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7642 | KL-20211206-1 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-06 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 | 11 | F118-F127 | Henson | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7642KL-20211206-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7642KL-20211206-1L.O.A.0.8181818199.6364OEWT-PA24-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7645 | KL-20211206-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-12-06 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F175 to F171 and from F185 to F193/ Grader working on High Falls Road and to F203 | 11 | F170-F211 | High Falls | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7645KL-20211206-4L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7645KL-20211206-4L.O.A.0.9090909221.8182OEWT-PA24-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7645 | KL-20211206-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-12-06 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F175 to F171 and from F185 to F193/ Grader working on High Falls Road and to F203 | 11 | F170-F211 | High Falls | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7645KL-20211206-4L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7645KL-20211206-4L.O.A.0.363636488.7273OEWT-PA24-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7648 | KL-20211207-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-12-07 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on benching snow banks from Hwy 17 to Km 17 and clearing pull offs | 11 | F118-F127 | Henson | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7648KL-20211207-2L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7648KL-20211207-2L.O.A.0.7727273188.5455OEWT-PA24-LEM | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7649 | KL-20211207-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-12-07 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F185 to F181 and from F198 to F208/ Grader working on High Falls Road, F200 and F195 access | 11 | F170-F211 | High Falls | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7649KL-20211207-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7649KL-20211207-3L.O.A.0.9090909221.8182OEWT-PA24-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7649 | KL-20211207-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-12-07 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F185 to F181 and from F198 to F208/ Grader working on High Falls Road, F200 and F195 access | 11 | F170-F211 | High Falls | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7649KL-20211207-3L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7649KL-20211207-3L.O.A.0.4545455110.9091OEWT-PA24-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7651 | KL-20211207-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-12-07 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal @ Trembley Road and F161 to F164 | 11 | F161-F164 | Trembley Falls | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7651KL-20211207-5L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7651KL-20211207-5L.O.A.0.4545455110.9091OEWT-PA24-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7653 | KL-20211208-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Hensen Road from Hwy 17 to 17Km & widening corners. | 11 | F118-F127 | Henson | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7653KL-20211208-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7653KL-20211208-2L.O.A.0.8181818199.6364OEWT-PA24-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7654 | KL-20211208-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F198 to F208 & support of stringing equipment. Grader working on High Falls Road, F170, F175, F176, F185 to F181 & F207 access. | 11 | F170-F211 | High Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7654KL-20211208-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7654KL-20211208-3L.O.A.0.9090909221.8182OEWT-PA24-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7654 | KL-20211208-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F198 to F208 & support of stringing equipment. Grader working on High Falls Road, F170, F175, F176, F185 to F181 & F207 access. | 11 | F170-F211 | High Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7654KL-20211208-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7654KL-20211208-3L.O.A.0.8181818199.6364OEWT-PA24-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7656 | KL-20211208-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.22727 | Day |  | 0 |  |  | 55.4545 | 7.2091 | 62.6636 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal @ F169 to F165 | 11 | F165-F169 | Magpie Hills | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7656KL-20211208-5L.O.A.0.227272755.4545 | KABI LAKE FOREST PRODUCTS LTD7656KL-20211208-5L.O.A.0.227272755.4545OEWT-PA24-LEM | [5 empty] | 1 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7661 | KL-20211209-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying Hensen Road from hwy 17 to 17km. Sand truck sanding hills & corners with existing sand from 17km. Excavator used for loading sand. | 11 | F118-F127 | Henson | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7661KL-20211209-4L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7661KL-20211209-4L.O.A.0.7727273188.5455OEWT-PA24-LEM | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7661 | KL-20211209-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying Hensen Road from hwy 17 to 17km. Sand truck sanding hills & corners with existing sand from 17km. Excavator used for loading sand. | 11 | F118-F127 | Henson | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7661KL-20211209-4L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7661KL-20211209-4L.O.A.0.6363636155.2727OEWT-PA24-LEM | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7661 | KL-20211209-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying Hensen Road from hwy 17 to 17km. Sand truck sanding hills & corners with existing sand from 17km. Excavator used for loading sand. | 11 | F118-F127 | Henson | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7661KL-20211209-4L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD7661KL-20211209-4L.O.A.0.181818244.3636OEWT-PA24-LEM | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7662 | KL-20211209-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.5 | Day |  | 0 |  |  | 122 | 15.86 | 137.86 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 330 excavator from MFN to 17km on Hensen Road. Chain up required. | 11 | F118-F127 | Henson | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7662KL-20211209-5L.O.A.0.5122 | KABI LAKE FOREST PRODUCTS LTD7662KL-20211209-5L.O.A.0.5122OEWT-PA24-LEM | [5 empty] | 1 | 122 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7664 | KL-20211209-7 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal @ F180, F172, F171, F173 & F208 to F211. Grader working on High Falls Road, F185 to F181 & access to F207 | 11 | F170-F211 | High Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7664KL-20211209-7L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7664KL-20211209-7L.O.A.0.8181818199.6364OEWT-PA24-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7664 | KL-20211209-7 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal @ F180, F172, F171, F173 & F208 to F211. Grader working on High Falls Road, F185 to F181 & access to F207 | 11 | F170-F211 | High Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7664KL-20211209-7L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7664KL-20211209-7L.O.A.0.8181818199.6364OEWT-PA24-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7667 | KL-20211210-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-12-10 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow remvoal and scarifying Hensen Road from hwy 17 to 17Km. | 11 | F118-F127 | Henson | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7667KL-20211210-3L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7667KL-20211210-3L.O.A.0.7727273188.5455OEWT-PA24-LEM | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7668 | KL-20211210-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-12-10 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal to F198, F202 & F2003 to F211. Grader working on High Falls road, F180, F194 to F197 & access to F207. | 11 | F170-F211 | High Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7668KL-20211210-4L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7668KL-20211210-4L.O.A.0.8636364210.7273OEWT-PA24-LEM | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7668 | KL-20211210-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-12-10 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal to F198, F202 & F2003 to F211. Grader working on High Falls road, F180, F194 to F197 & access to F207. | 11 | F170-F211 | High Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7668KL-20211210-4L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7668KL-20211210-4L.O.A.0.363636488.7273OEWT-PA24-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7669 | KL-20211210-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-12-10 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal @ Trembley Road & F161 to F164 | 11 | F161 - F164 | Trembley Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7669KL-20211210-5L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7669KL-20211210-5L.O.A.0.4545455110.9091OEWT-PA24-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7672 | KL-20211211-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2021-12-11 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow remvoal from Hwy 17 to 17Km. | 11 | F118-F127 | Henson | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7672KL-20211211-3L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7672KL-20211211-3L.O.A.0.6363636155.2727OEWT-PA24-LEM | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7673 | KL-20211211-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-12-11 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working from F171 to F193 & on High Falls Road to 13Km. | 11 | F170-F211 | High Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7673KL-20211211-4L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7673KL-20211211-4L.O.A.0.8636364210.7273OEWT-PA24-LEM | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7683 | KL-20211212-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-12 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Scarifying from Hwy 17 to Km 17 and clearing pull offs | 11 | F118-F127 | Henson | 0 | 44551 |  | 61 | 44561 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7683KL-20211212-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7683KL-20211212-3L.O.A.0.8181818199.6364OEWT-PA24-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7684 | KL-20211212-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-12-12 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on High Falls Road to Km 13 and F200/ Dozer working from F206 to F211 | 11 | F170-F211 | High Falls | 0 | 44551 |  | 61 | 44561 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7684KL-20211212-4L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7684KL-20211212-4L.O.A.0.363636488.7273OEWT-PA24-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7684 | KL-20211212-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2021-12-12 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on High Falls Road to Km 13 and F200/ Dozer working from F206 to F211 | 11 | F170-F211 | High Falls | 0 | 44551 |  | 61 | 44561 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7684KL-20211212-4L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7684KL-20211212-4L.O.A.0.5454545133.0909OEWT-PA24-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7685 | KL-20211212-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-12-12 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Snow removal and trembley road and F161 to F164 | 11 | F161 - F164 | Trembley Falls | 0 | 44551 |  | 61 | 44560 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7685KL-20211212-5L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7685KL-20211212-5L.O.A.0.363636488.7273OEWT-PA24-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7687 | KL-20211213-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2021-12-13 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat D6 Dozer from Km 13 on High Falls Road to Km 17 on Hensen Road and float Cat 140M grader from Km .5 on Hensen Road to Kabi Yard/Chain Up required | 11 | F118-F127 | Henson | 0 | 44551 |  | 61 | 44560 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7687KL-20211213-2L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7687KL-20211213-2L.O.A.0.5454545133.0909OEWT-PA24-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7688 | KL-20211213-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-12-13 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Finish snow removal from F198 to F201 | 11 | F170-F211 | High Falls | 0 | 44551 |  | 61 | 44560 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7688KL-20211213-3L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7688KL-20211213-3L.O.A.0.363636488.7273OEWT-PA24-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7690 | KL-20211214-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-14 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working from @ F173 to F171 and on High Falls Road to Km 13 | 11 | F170-F211 | High Falls | 0 | 44551 |  | 61 | 44560 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7690KL-20211214-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7690KL-20211214-2L.O.A.0.8181818199.6364OEWT-PA24-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7691 | KL-20211214-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-12-14 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Scarifying hills and corners from Km 12 to Hwy 17/Dozer starting snow removal from Hensen road to F128 | 11 | F118-F127 | Henson | 0 | 44551 |  | 61 | 44560 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7691KL-20211214-3L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7691KL-20211214-3L.O.A.0.363636488.7273OEWT-PA24-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7691 | KL-20211214-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2021-12-14 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Scarifying hills and corners from Km 12 to Hwy 17/Dozer starting snow removal from Hensen road to F128 | 11 | F118-F127 | Henson | 0 | 44551 |  | 61 | 44560 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7691KL-20211214-3L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7691KL-20211214-3L.O.A.0.6363636155.2727OEWT-PA24-LEM | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7692 | KL-20211214-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2021-12-14 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 14M Grader from Km .5 on Hensen Road to Kabi Yard | 11 | F118-F127 | Henson | 0 | 44551 |  | 61 | 44560 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7692KL-20211214-4L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7692KL-20211214-4L.O.A.0.272727366.5455OEWT-PA24-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7696 | KL-20211215-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2021-12-15 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working High Falls Road and from @ F173 to F171 | 11 | F170 - F211 | High Falls | 0 |  |  | 46 | 44218 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7696KL-20211215-3L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7696KL-20211215-3L.O.A.0.272727366.5455OEWT-PA24-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7697 | KL-20211215-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-15 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer finishing snow removal from Hensen road to F132 | 11 | F118-F127 | Henson | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7697KL-20211215-4L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7697KL-20211215-4L.O.A.0.8181818199.6364OEWT-PA24-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7698 | KL-20211215-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2021-12-15 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Scarifying Trembley Road | 11 | F161 - F164 | Trembley Falls | 0 |  |  | 46 | 44583 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7698KL-20211215-5L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7698KL-20211215-5L.O.A.0.5454545133.0909OEWT-PA24-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7700 | KL-20211216-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-16 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F037 to F033 | 10 | F066-F118 | Paint Lake 2 | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7700KL-20211216-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7700KL-20211216-3L.O.A.0.8181818199.6364OEWT-PA24-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7701 | KL-20211216-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2021-12-16 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Stringer Support |  | Approved |  |  | Grader @ High Falls Road in Support of Stringing crew | 11 | F170-F211 | High Falls | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7701KL-20211216-4L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7701KL-20211216-4L.O.A.0.6363636155.2727OEWT-PA24-LEM | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7708 | KL-20211219-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-19 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hensen Road to F127 | 11 | F118-F127 | Henson | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7708KL-20211219-4L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7708KL-20211219-4L.O.A.0.8181818199.6364OEWT-PA24-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7714 | KL-20211229-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-29 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hensen Road to F132 | 11 | F119-F127 | Henson | 0 |  |  | 61 | 44572 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7714KL-20211229-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7714KL-20211229-2L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7716 | KL-20211230-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-12-30 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal from Hensen Road to F132 for freezing | 11 | F119-F127 | Henson | 0 |  |  | 61 | 44572 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7716KL-20211230-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7716KL-20211230-2L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7717 | KL-20211231-1 | 53511111 | Access | 0 | L.O.A. | 244 | 0.59091 | Day |  | 0 |  |  | 144.1818 | 18.7436 | 162.9254 | 2021-12-31 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hensen Road to F132 | 11 | F119-F127 | Henson | 0 |  |  | 61 | 44572 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7717KL-20211231-1L.O.A.0.5909091144.1818 | KABI LAKE FOREST PRODUCTS LTD7717KL-20211231-1L.O.A.0.5909091144.1818OEWT-PA25-Lem | [5 empty] | 1 | 144.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7720 | KL-20220102-1 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-02 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal, widening road and clearing pull offs from Hensen road to F132 for freezing | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7720KL-20220102-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7720KL-20220102-1L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7721 | KL-20220102-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2022-01-02 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on Trembley Road from Harbour Road to Hwy 17 | 11 | F161-F164 | Trembley Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7721KL-20220102-2L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7721KL-20220102-2L.O.A.0.4545455110.9091OEWT-PA25-Lem | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7722 | KL-20220102-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.5 | Day |  | 0 |  |  | 122 | 15.86 | 137.86 | 2022-01-02 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 3.5 on High Falls Road and F171 to F177 | 11 | F118-F127 | Henson | 0 | 44568 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7722KL-20220102-3L.O.A.0.5122 | KABI LAKE FOREST PRODUCTS LTD7722KL-20220102-3L.O.A.0.5122OEWT-PA25-Lem | [5 empty] | 1 | 122 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7725 | KL-20220103-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2022-01-03 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F164 to F161 | 11 | F161-F164 | Trembley Falls | 0 | 44568 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7725KL-20220103-3L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7725KL-20220103-3L.O.A.0.272727366.5455OEWT-PA25-Lem | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7726 | KL-20220103-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2022-01-03 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F171 to F188 | 11 | F170-F211 | High Falls | 0 | 44568 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7726KL-20220103-4L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7726KL-20220103-4L.O.A.0.5454545133.0909OEWT-PA25-Lem | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7727 | KL-20220103-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.22727 | Day |  | 0 |  |  | 55.4545 | 7.2091 | 62.6636 | 2022-01-03 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F169 to F165 | 11 | F165-F169 | Magpie Hills | 0 | 44568 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7727KL-20220103-5L.O.A.0.227272755.4545 | KABI LAKE FOREST PRODUCTS LTD7727KL-20220103-5L.O.A.0.227272755.4545OEWT-PA25-Lem | [5 empty] | 1 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7729 | KL-20220104-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2022-01-04 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working out from F131 to F125 fixing rough areas and shaping road | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7729KL-20220104-2L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7729KL-20220104-2L.O.A.0.272727366.5455OEWT-PA25-Lem | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7730 | KL-20220104-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2022-01-04 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F171, F180, F165 and High Falls Road to Km 13 | 11 | F170-F211 | High Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7730KL-20220104-3L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7730KL-20220104-3L.O.A.0.7727273188.5455OEWT-PA25-Lem | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7732 | KL-20220105-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-05 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hensen Road to F132 and assisting stringing crews/Excavatorcleaning up and setting up a face @Km 17 for sand access | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7732KL-20220105-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7732KL-20220105-2L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7732 | KL-20220105-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2022-01-05 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hensen Road to F132 and assisting stringing crews/Excavatorcleaning up and setting up a face @Km 17 for sand access | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7732KL-20220105-2L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD7732KL-20220105-2L.O.A.0.181818244.3636OEWT-PA25-Lem | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7733 | KL-20220105-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2022-01-05 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  |  | 11 | F161 - F164 | Trembley Falls | 0 | 44572 |  | 46 | 44562 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7733KL-20220105-3L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD7733KL-20220105-3L.O.A.0.409090999.8182OEWT-PA25-Lem | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7734 | KL-20220105-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2022-01-05 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F171 to F188 | 11 | F170-F211 | High Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7734KL-20220105-4L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7734KL-20220105-4L.O.A.0.363636488.7273OEWT-PA25-Lem | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7735 | KL-20220105-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2022-01-05 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F169 to F165 | 11 | F165 - F169 | Magpie Hills | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7735KL-20220105-5L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD7735KL-20220105-5L.O.A.0.181818244.3636OEWT-PA25-Lem | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7738 | KL-20220106-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2022-01-06 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on filling water holes with snow, widening road and corners to F127 for stringing crews | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7738KL-20220106-3L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD7738KL-20220106-3L.O.A.0.409090999.8182OEWT-PA25-Lem | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7741 | KL-20220107-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2022-01-07 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road and corners to F132 for stringing crews | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7741KL-20220107-3L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7741KL-20220107-3L.O.A.0.7727273188.5455OEWT-PA25-Lem | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7742 | KL-20220107-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2022-01-07 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Trembley Road from Km 6 to Km 1 abd F161 to F164 | 11 | F161 - F164 | Trembley Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7742KL-20220107-4L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7742KL-20220107-4L.O.A.0.5454545133.0909OEWT-PA25-Lem | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7743 | KL-20220107-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.22727 | Day |  | 0 |  |  | 55.4545 | 7.2091 | 62.6636 | 2022-01-07 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working from F171 to F177 | 11 | F170-F211 | High Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7743KL-20220107-5L.O.A.0.227272755.4545 | KABI LAKE FOREST PRODUCTS LTD7743KL-20220107-5L.O.A.0.227272755.4545OEWT-PA25-Lem | [5 empty] | 1 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7745 | KL-20220108-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-08 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working from Hensen Road to F131, dragging road with blast mat, scraping hills and assisting stringers hauling in material | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7745KL-20220108-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7745KL-20220108-2L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7746 | KL-20220108-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2022-01-08 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Trembley Road from Km 6 to Km 1 and F161 to F164 | 11 | F161-F164 | Trembley Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7746KL-20220108-3L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7746KL-20220108-3L.O.A.0.6363636155.2727OEWT-PA25-Lem | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7747 | KL-20220108-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2022-01-08 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working from F171 to F177 | 11 | F170-F211 | High Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7747KL-20220108-4L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD7747KL-20220108-4L.O.A.0.181818244.3636OEWT-PA25-Lem | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7748 | KL-20220108-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2022-01-08 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F169 to F165 | 11 | F165 - F169 | Magpie Hills | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7748KL-20220108-5L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD7748KL-20220108-5L.O.A.0.181818244.3636OEWT-PA25-Lem | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7749 | KL-20220109-1 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-09 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working on snow removal from Km 17 on Hensen to Hwy 17 and clearing pull offs/Dozer pushing back snow banks from Km 17 to Km 1 on Hensen Road | 11 | F118-F127 | Henson | 0 | 44575 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7749KL-20220109-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7749KL-20220109-1L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7749 | KL-20220109-1 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2022-01-09 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working on snow removal from Km 17 on Hensen to Hwy 17 and clearing pull offs/Dozer pushing back snow banks from Km 17 to Km 1 on Hensen Road | 11 | F118-F127 | Henson | 0 | 44575 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7749KL-20220109-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7749KL-20220109-1L.O.A.0.9090909221.8182OEWT-PA25-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7750 | KL-20220109-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2022-01-09 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Snow removal from F171 to F188 and clearing pads and pull offs | 11 | F170-F211 | High Falls | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7750KL-20220109-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7750KL-20220109-2L.O.A.0.9090909221.8182OEWT-PA25-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7752 | KL-20220110-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2022-01-10 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer pushing back snow banks and clearing pull offs from Km .5 to Km 17 on Hensen Road | 11 | F118-F127 | Henson | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7752KL-20220110-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7752KL-20220110-2L.O.A.0.8636364210.7273OEWT-PA25-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7753 | KL-20220110-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2022-01-10 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Trembley Road from Km 7 to Km 1 and F161 to F164 | 11 | F161 - F164 | Trembley Falls | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7753KL-20220110-3L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7753KL-20220110-3L.O.A.0.5454545133.0909OEWT-PA25-Lem | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7754 | KL-20220110-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2022-01-10 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F169 to F165 and pads | 11 | F165 - F169 | Magpie Hills | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7754KL-20220110-4L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7754KL-20220110-4L.O.A.0.272727366.5455OEWT-PA25-Lem | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7756 | KL-20220111-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2022-01-11 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader dragging road with blast mat, scraping hills and filling in rough areas | 11 | F118-F127 | Henson | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7756KL-20220111-2L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7756KL-20220111-2L.O.A.0.7727273188.5455OEWT-PA25-Lem | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7757 | KL-20220111-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2022-01-11 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F171 to F188 | 11 | F171 - F211 | High Falls | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7757KL-20220111-3L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7757KL-20220111-3L.O.A.0.6363636155.2727OEWT-PA25-Lem | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7760 | KL-20220112-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2022-01-12 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader scraping hills, clearing spur roads and sanding Hills to F127 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7760KL-20220112-3L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7760KL-20220112-3L.O.A.0.4545455110.9091OEWT-PA25-Lem | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7761 | KL-20220112-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2022-01-12 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Scarifying road from F171 to F177 | 11 | F170-F211 | High Falls | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7761KL-20220112-4L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD7761KL-20220112-4L.O.A.0.181818244.3636OEWT-PA25-Lem | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7762 | KL-20220112-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2022-01-12 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader driving from High Falls, scarifing hills and corners Trembley Road from Km 7 to Km 1 and F161 to F164 | 11 | F161 - F164 | Trembley Falls | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7762KL-20220112-5L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD7762KL-20220112-5L.O.A.0.181818244.3636OEWT-PA25-Lem | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7765 | KL-20220113-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2022-01-13 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding and dragging blast mat to F132 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7765KL-20220113-3L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7765KL-20220113-3L.O.A.0.6363636155.2727OEWT-PA25-Lem | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7766 | KL-20220113-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2022-01-13 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader for support of stringing crews @ F171 | 11 | F170-F211 | High Falls | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7766KL-20220113-4L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7766KL-20220113-4L.O.A.0.4545455110.9091OEWT-PA25-Lem | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7767 | KL-20220113-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2022-01-13 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader driving from High Falls, scarifing hills and corners Trembley Road from Km 7 to Km 1 | 11 | F161 - F164 | Trembley Falls | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7767KL-20220113-5L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7767KL-20220113-5L.O.A.0.363636488.7273OEWT-PA25-Lem | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7770 | KL-20220114-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.31818 | Day |  | 0 |  |  | 77.6364 | 10.0927 | 87.7291 | 2022-01-14 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 12M Grader from 3.5 Km on High Falls Road to .5 Km on Hensen road | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7770KL-20220114-3L.O.A.0.318181877.6364 | KABI LAKE FOREST PRODUCTS LTD7770KL-20220114-3L.O.A.0.318181877.6364OEWT-PA25-Lem | [5 empty] | 1 | 77.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7771 | KL-20220114-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-14 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader finishing sanding and dragging blast mat from Hensen Road to F132 for stringing crews and start sanding Hensen Road with existing material from Km 10.5 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7771KL-20220114-4L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7771KL-20220114-4L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7775 | KL-20220115-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2022-01-15 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding hills on Hensen Road with existing material from Km 10.5 / Grader scarifying and benching snow banks on Hensen road from Km .5 to Km 17 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7775KL-20220115-4L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7775KL-20220115-4L.O.A.0.7727273188.5455OEWT-PA25-Lem | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7775 | KL-20220115-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-15 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding hills on Hensen Road with existing material from Km 10.5 / Grader scarifying and benching snow banks on Hensen road from Km .5 to Km 17 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7775KL-20220115-4L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7775KL-20220115-4L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7778 | KL-20220116-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2022-01-16 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader clearing pull offs and sanding in Hensen East / Grader working on snow removal on Hensen road from Km .5 to Km 17 and Hensen East to F132 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7778KL-20220116-3L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7778KL-20220116-3L.O.A.0.5454545133.0909OEWT-PA25-Lem | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7778 | KL-20220116-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2022-01-16 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader clearing pull offs and sanding in Hensen East / Grader working on snow removal on Hensen road from Km .5 to Km 17 and Hensen East to F132 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7778KL-20220116-3L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7778KL-20220116-3L.O.A.0.7272727177.4545OEWT-PA25-Lem | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7781 | KL-20220117-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2022-01-17 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding in Hensen East / Grader working on snow removal on Hensen road from Km .5 to Km 17 and Hensen East to F132 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7781KL-20220117-3L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD7781KL-20220117-3L.O.A.0.409090999.8182OEWT-PA25-Lem | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7781 | KL-20220117-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2022-01-17 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding in Hensen East / Grader working on snow removal on Hensen road from Km .5 to Km 17 and Hensen East to F132 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7781KL-20220117-3L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7781KL-20220117-3L.O.A.0.6363636155.2727OEWT-PA25-Lem | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7783 | KL-20220118-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2022-01-18 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat 962M Loader from 0.5Km on Hensen Road to 7Km on Anjigami Road. | 11 | F212-F235 | Anjigame | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7783KL-20220118-2L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD7783KL-20220118-2L.O.A.0.409090999.8182OEWT-PA25-Lem | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7784 | KL-20220118-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2022-01-18 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding in Hensen East & driving out to 0.5Km for float. Grader working on benching & pushing back on Hensen road to 15Km. | 11 | F118-F127 | Henson | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7784KL-20220118-3L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7784KL-20220118-3L.O.A.0.7272727177.4545OEWT-PA25-Lem | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7784 | KL-20220118-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2022-01-18 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding in Hensen East & driving out to 0.5Km for float. Grader working on benching & pushing back on Hensen road to 15Km. | 11 | F118-F127 | Henson | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7784KL-20220118-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7784KL-20220118-3L.O.A.0.9090909221.8182OEWT-PA25-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7879 | KL-20220213-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2022-02-13 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat 12M grader from .5 Km on Hensen Road to Km 1 on Trembley Road | 11 | F161-F164 | Trembley Falls | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7879KL-20220213-3L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7879KL-20220213-3L.O.A.0.272727366.5455OEWT-PA26-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7880 | KL-20220213-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2022-02-13 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 1 to Km 6 on Trembley road and from Trembley Road to F161 | 11 | F161 - F164 | Trembley Falls | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7880KL-20220213-4L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7880KL-20220213-4L.O.A.0.7272727177.4545OEWT-PA26-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7881 | KL-20220213-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2022-02-13 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat 12M grader frim Km 1 on Trembley road back to Km .5 on Hensen Road | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7881KL-20220213-5L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7881KL-20220213-5L.O.A.0.272727366.5455OEWT-PA26-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7889 | KL-20220215-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2022-02-15 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal and scarifying from Hwy 17 to Km 17 on Hensen Road | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7889KL-20220215-2L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7889KL-20220215-2L.O.A.0.4545455110.9091OEWT-PA26-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7894 | KL-20220216-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2022-02-16 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen Road / Loader clearing entrance @ Hwy 17 and Hensen Road | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7894KL-20220216-2L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7894KL-20220216-2L.O.A.0.363636488.7273OEWT-PA26-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7894 | KL-20220216-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.090909 | Day |  | 0 |  |  | 22.1818 | 2.8836 | 25.0654 | 2022-02-16 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen Road / Loader clearing entrance @ Hwy 17 and Hensen Road | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7894KL-20220216-2L.O.A.0.090909122.1818 | KABI LAKE FOREST PRODUCTS LTD7894KL-20220216-2L.O.A.0.090909122.1818OEWT-PA26-LEM | [5 empty] | 1 | 22.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7898 | KL-20220217-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-17 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen Road and to F131 in Hensen East / Loader clearing pull off on Hensen Road and F126 Access | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7898KL-20220217-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7898KL-20220217-3L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7898 | KL-20220217-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2022-02-17 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen Road and to F131 in Hensen East / Loader clearing pull off on Hensen Road and F126 Access | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7898KL-20220217-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7898KL-20220217-3L.O.A.0.9090909221.8182OEWT-PA26-LEM | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7901 | KL-20220218-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2022-02-18 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader finishing clearing pull off, widening corners and sanding from Km 5 to Km 17/ Supervisor doing pickup shuffle | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7901KL-20220218-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7901KL-20220218-2L.O.A.0.8636364210.7273OEWT-PA26-LEM | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7906 | KL-20220219-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2022-02-19 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17km on Hensen Road & start benching snow banks | 11 | F118-F127 | Henson | 0 | 44617 |  | 61 | 44617 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7906KL-20220219-2L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7906KL-20220219-2L.O.A.0.7272727177.4545OEWT-PA26-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7910 | KL-20220220-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2022-02-20 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17Km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44617 |  | 61 | 44617 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7910KL-20220220-2L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7910KL-20220220-2L.O.A.0.4545455110.9091OEWT-PA26-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7912 | KL-20220221-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.59091 | Day |  | 0 |  |  | 144.1818 | 18.7436 | 162.9254 | 2022-02-21 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal & benching snow banks from Hwy 17 to 17Km on Hensen Road. Loader starting clearing of pull offs on Hensen Road & widening corners | 11 | F118-F127 | Henson | 0 | 44617 |  | 61 | 44617 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7912KL-20220221-2L.O.A.0.5909091144.1818 | KABI LAKE FOREST PRODUCTS LTD7912KL-20220221-2L.O.A.0.5909091144.1818OEWT-PA26-LEM | [5 empty] | 1 | 144.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7912 | KL-20220221-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.31818 | Day |  | 0 |  |  | 77.6364 | 10.0927 | 87.7291 | 2022-02-21 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal & benching snow banks from Hwy 17 to 17Km on Hensen Road. Loader starting clearing of pull offs on Hensen Road & widening corners | 11 | F118-F127 | Henson | 0 | 44617 |  | 61 | 44617 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7912KL-20220221-2L.O.A.0.318181877.6364 | KABI LAKE FOREST PRODUCTS LTD7912KL-20220221-2L.O.A.0.318181877.6364OEWT-PA26-LEM | [5 empty] | 1 | 77.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7914 | KL-20220222-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2022-02-22 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen Road /Grader 2 benching snow banks from Km 17 to Hwy 17 | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7914KL-20220222-2L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7914KL-20220222-2L.O.A.0.4545455110.9091OEWT-PA26-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7914 | KL-20220222-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2022-02-22 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen Road /Grader 2 benching snow banks from Km 17 to Hwy 17 | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7914KL-20220222-2L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7914KL-20220222-2L.O.A.0.272727366.5455OEWT-PA26-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7917 | KL-20220223-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2022-02-23 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17km on Hensen Road. Loader widening corners & assisting float trucks | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7917KL-20220223-2L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7917KL-20220223-2L.O.A.0.5454545133.0909OEWT-PA26-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7917 | KL-20220223-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2022-02-23 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17km on Hensen Road. Loader widening corners & assisting float trucks | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7917KL-20220223-2L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7917KL-20220223-2L.O.A.0.4545455110.9091OEWT-PA26-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7917 | KL-20220223-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2022-02-23 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17km on Hensen Road. Loader widening corners & assisting float trucks | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7917KL-20220223-2L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7917KL-20220223-2L.O.A.0.363636488.7273OEWT-PA26-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7921 | KL-20220224-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2022-02-24 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal, benching snowbanks and widening road from Hwy 17 to 17km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7921KL-20220224-2L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7921KL-20220224-2L.O.A.0.9545455232.9091OEWT-PA26-LEM | [5 empty] | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7926 | KL-20220225-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2022-02-25 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying sections from Hwy 17 to 17km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7926KL-20220225-2L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7926KL-20220225-2L.O.A.0.272727366.5455OEWT-PA26-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7939 | KL-20220227-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader working on snow removal from Hwy 17 to 17Km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7939KL-20220227-2L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7939KL-20220227-2L.O.A.0.363636488.7273 | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7940 | KL-20220227-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Float Kabi Cat 950M Loader From 9.2 Km On Paint Lake Road 2 To Magpie Hills Road. (Cost Code: 67776007556.591100.57010107) | 11 | F165-F169 | Magpie Hills | 0 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7940KL-20220227-3L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD7940KL-20220227-3L.O.A.0.409090999.8182 | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7941 | KL-20220227-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader Starting Snow Removal From F168 To F165. Access/Winter Access Maintenance (Cost Code: 67776007556.591100.57010107) | 11 | F165 - F169 | Magpie Hills | 0 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7941KL-20220227-4L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7941KL-20220227-4L.O.A.0.272727366.5455 | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7945 | KL-20220228-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2022-02-28 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader Scarifying Sections From Hwy 17 To 17 Km On Hensen Road | 11 | F118-F127 | Henson | 0 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7945KL-20220228-2L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7945KL-20220228-2L.O.A.0.272727366.5455 | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7946 | KL-20220228-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2022-02-28 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loader Finishing Snow Removal From F165 To F169. Access/Winter Access Maintenance (Cost Code: 67776007556.591100.57010107) | 11 | F165 - F169 | Magpie Hills | 1 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7946KL-20220228-3L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7946KL-20220228-3L.O.A.0.4545455110.9091 | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7948 | KL-20220228-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2022-02-28 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loaders Working On Snow Removal From F184 To F181 & Starting @ F175 To F171. Access/Winter Access Maintenance (Cost Code: 67776007556.591100.57010107) | 11 | F170 - F211 | High Falls | 1 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7948KL-20220228-5L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7948KL-20220228-5L.O.A.0.4545455110.9091 | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7948 | KL-20220228-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.59091 | Day |  | 0 |  |  | 144.1818 | 18.7436 | 162.9254 | 2022-02-28 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loaders Working On Snow Removal From F184 To F181 & Starting @ F175 To F171. Access/Winter Access Maintenance (Cost Code: 67776007556.591100.57010107) | 11 | F170 - F211 | High Falls | 1 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7948KL-20220228-5L.O.A.0.5909091144.1818 | KABI LAKE FOREST PRODUCTS LTD7948KL-20220228-5L.O.A.0.5909091144.1818 | [5 empty] | 1 | 144.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7949 | KL-20220228-6 | 53511111 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2022-02-28 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Float Cat 962M Loader From Kabi Shop To 3 Km On High Falls Road & Float Cat 950M Loader From Magpie Hills Road To 5 Km On High Falls Road (Cost Code: 67776007556.591100.57010107) | 11 | F170 - F211 | High Falls | 1 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7949KL-20220228-6L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7949KL-20220228-6L.O.A.0.4545455110.9091 | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7956 | KL-20220301-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2022-03-01 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loaders finishing on snow removal from F175 to F171 Cost Code: 67776007556.591100.57010107 ) | 11 | F170 - F211 | High Falls | 1 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7956KL-20220301-3L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7956KL-20220301-3L.O.A.0.4545455110.9091 | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7956 | KL-20220301-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2022-03-01 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loaders finishing on snow removal from F175 to F171 Cost Code: 67776007556.591100.57010107 ) | 11 | F170 - F211 | High Falls | 1 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7956KL-20220301-3L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7956KL-20220301-3L.O.A.0.4545455110.9091 | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7958 | KL-20220302-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2022-03-02 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader working on snow removal from Hwy to Km 17 on Hensen Road | 11 | F118-F127 | Henson | 0 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7958KL-20220302-3L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD7958KL-20220302-3L.O.A.0.181818244.3636 | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7959 | KL-20220302-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2022-03-02 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Float Cat 950M loader from High Falls Road to F170/ Traffic control required ( Cost Code: 67776007556.591100.57010107 ) | 11 | F170-F211 | High Falls | 1 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7959KL-20220302-4L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD7959KL-20220302-4L.O.A.0.181818244.3636 | [5 empty] | 1 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7960 | KL-20220302-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2022-03-02 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loaders finishing on snow removal and turn around @ F170 / Traffic control required for clearing of Entrance ( Cost Code: 67776007556.591100.57010107 ) | 11 | F170 - F211 | High Falls | 1 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7960KL-20220302-5L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7960KL-20220302-5L.O.A.0.6363636155.2727 | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7961 | KL-20220302-6 | 53511111 | Access | 0 | L.O.A. | 244 | 0.31818 | Day |  | 0 |  |  | 77.6364 | 10.0927 | 87.7291 | 2022-03-02 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Float Cat 962M loader from High Falls Road to Km 7 on Anjigami Road | 11 | F212-F235 | Anjigame | 0 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7961KL-20220302-6L.O.A.0.318181877.6364 | KABI LAKE FOREST PRODUCTS LTD7961KL-20220302-6L.O.A.0.318181877.6364 | [5 empty] | 1 | 77.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7962 | KL-20220302-7 | 53511111 | Access | 0 | L.O.A. | 244 | 0.59091 | Day |  | 0 |  |  | 144.1818 | 18.7436 | 162.9254 | 2022-03-02 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader working on snow removal from Anjigami to F228 | 11 | F212-F235 | Anjigame | 0 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7962KL-20220302-7L.O.A.0.5909091144.1818 | KABI LAKE FOREST PRODUCTS LTD7962KL-20220302-7L.O.A.0.5909091144.1818 | [5 empty] | 1 | 144.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7971 | KL-20220306-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.5 | Day |  | 0 |  |  | 122 | 15.86 | 137.86 | 2022-03-06 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Float Kabi Cat 950M from 9.2Km on Paint Lake Road #2 to High Falls road. Delay due to bad weather. | 11 | F170-F211 | High Falls | 1 | 44634 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7971KL-20220306-2L.O.A.0.5122 | KABI LAKE FOREST PRODUCTS LTD7971KL-20220306-2L.O.A.0.5122 | [5 empty] | 1 | 122 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7972 | KL-20220307-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2022-03-07 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader Working On Snow Removal From Anjigami Road To F228 & F235 To F233 | 11 | F212-F235 | Anjigame | 0 | 44634 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7972KL-20220307-2L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7972KL-20220307-2L.O.A.0.7727273188.5455 | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7973 | KL-20220307-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2022-03-07 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Float Cat 962M Loader From Kabi Yard To 7 Km On Anjigami Road | 11 | F212-F235 | Anjigame | 0 | 44634 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7973KL-20220307-3L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD7973KL-20220307-3L.O.A.0.409090999.8182 | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7974 | KL-20220307-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-03-07 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loader Working On Snow Removal From High Falls Road To F175, F174, F172 & F171 ( Cost Code: 67776007556.591100.57010107 ) | 11 | F170-F211 | High Falls | 1 | 44634 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7974KL-20220307-4L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7974KL-20220307-4L.O.A.0.8181818199.6364 | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7975 | KL-20220308-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2022-03-08 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Float Cat 962M Loader From 7 Km On Anjigami Road To Kabi Yard | 11 | F212-F235 | Anjigame | 0 | 44634 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7975KL-20220308-2L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD7975KL-20220308-2L.O.A.0.409090999.8182 | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7976 | KL-20220309-1 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2022-03-09 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Float Kabi Cat 950M From High Falls Road Back To Kabi Yard. (Cost Code: 67776007556.591100.57010107) | 11 | F170-F211 | High Falls | 1 | 44634 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7976KL-20220309-1L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7976KL-20220309-1L.O.A.0.363636488.7273 | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7786 | KL-20220119-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-19 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working on snow removal from F231 to F235 & clearing pads. | 11 | F212-F235 | Anjigame | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7786KL-20220119-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7786KL-20220119-2L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7787 | KL-20220119-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-19 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road, clearing pull offs & spur roads from Hensen to F131. grader working on snow removal on Hensen to 17Km and Hensen East to F131. | 11 | F118-F127 | Henson | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7787KL-20220119-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7787KL-20220119-3L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7787 | KL-20220119-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-19 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road, clearing pull offs & spur roads from Hensen to F131. grader working on snow removal on Hensen to 17Km and Hensen East to F131. | 11 | F118-F127 | Henson | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7787KL-20220119-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7787KL-20220119-3L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7789 | KL-20220120-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.68182 | Day |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2022-01-20 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader finishing snow removal from F231 to F235 & clearing pads. Start snow removal from F231 to F226. | 11 | F212-F235 | Anjigame | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7789KL-20220120-2L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD7789KL-20220120-2L.O.A.0.6818182166.3636OEWT-PA25-Lem | [5 empty] | 1 | 166.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7790 | KL-20220120-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2022-01-20 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat D6T Dozer from Kabi yard to 11Km on High Falls Road. | 11 | F170-F211 | High Falls | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7790KL-20220120-3L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7790KL-20220120-3L.O.A.0.363636488.7273OEWT-PA25-Lem | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7791 | KL-20220120-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-20 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on Hensen road to F121, hensen East to F131 & start benching snow banks from 17Km to 13Km. | 11 | F118-F127 | Henson | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7791KL-20220120-4L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7791KL-20220120-4L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7792 | KL-20220120-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2022-01-20 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer tracking from 11 Km on High Falls road & Working on Snow Removal to F207. | 11 | F170 - F211 | High Falls | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7792KL-20220120-5L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7792KL-20220120-5L.O.A.0.7727273188.5455OEWT-PA25-Lem | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7794 | KL-20220121-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2022-01-21 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader finishing benching and pushing snow banks from Km .5 to Km 13 | 11 | F118 - F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7794KL-20220121-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7794KL-20220121-2L.O.A.0.8636364210.7273OEWT-PA25-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7795 | KL-20220121-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2022-01-21 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat 962 Loader from Km 7 on Anjigami Road to Km .5 on Hensen Road | 11 | F118-F127 | Henson | 0 | 44589 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7795KL-20220121-3L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7795KL-20220121-3L.O.A.0.4545455110.9091OEWT-PA25-Lem | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7796 | KL-20220121-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-21 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader snow removal from F231 to F226 and F232 to F235 | 11 | F212-F235 | Anjigame | 0 | 44589 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7796KL-20220121-4L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7796KL-20220121-4L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7797 | KL-20220122-1 | 53511111 | Access | 0 | L.O.A. | 244 | 1.8636 | Day |  | 0 |  |  | 454.7273 | 59.1145 | 513.8418 | 2022-01-22 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on Hensen Road to Km 17 and Hensen East to F132(plowed Hensen Road 3 times due to winter storm) /Loader clearing pulloffs and widening corners to Km 12 | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7797KL-20220122-1L.O.A.1.8636364454.7273 | KABI LAKE FOREST PRODUCTS LTD7797KL-20220122-1L.O.A.1.8636364454.7273OEWT-PA25-Lem | [5 empty] | 1 | 454.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7798 | KL-20220122-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.68182 | Day |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2022-01-22 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer tracking from km 11 on High Falls Road and working on snow removal from High Falls Road to F207/track back to Km 11 | 11 | F170-F211 | High Falls | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7798KL-20220122-2L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD7798KL-20220122-2L.O.A.0.6818182166.3636OEWT-PA25-Lem | [5 empty] | 1 | 166.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7800 | KL-20220123-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2022-01-23 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on Hensen Road to F121 and Hensen East to F132/Loader clearing pulloffs and widening corners | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7800KL-20220123-2L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7800KL-20220123-2L.O.A.0.7727273188.5455OEWT-PA25-Lem | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7800 | KL-20220123-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-23 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on Hensen Road to F121 and Hensen East to F132/Loader clearing pulloffs and widening corners | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7800KL-20220123-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7800KL-20220123-2L.O.A.0.8181818199.6364OEWT-PA25-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7802 | KL-20220124-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2022-01-24 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working benching snowbanks and widening road from Hwy 17 to Km 10/ Loader continuing clearing pulloffs and widening corners | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7802KL-20220124-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7802KL-20220124-2L.O.A.0.9090909221.8182OEWT-PA25-Lem | [5 empty] | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7802 | KL-20220124-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2022-01-24 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working benching snowbanks and widening road from Hwy 17 to Km 10/ Loader continuing clearing pulloffs and widening corners | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7802KL-20220124-2L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7802KL-20220124-2L.O.A.0.363636488.7273OEWT-PA25-Lem | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7803 | KL-20220124-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2022-01-24 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat 962M Loader from .5 on Hensen Road to Km 7 on Anjigami Road | 11 | F212-F235 | Anjigame | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7803KL-20220124-3L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD7803KL-20220124-3L.O.A.0.409090999.8182OEWT-PA25-Lem | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7804 | KL-20220124-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2022-01-24 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from Anjigami Road to F231 and clearing pads in support of stringing crew | 11 |  | Anjigame | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7804KL-20220124-4L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD7804KL-20220124-4L.O.A.0.409090999.8182OEWT-PA25-Lem | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7807 | KL-20220125-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2022-01-25 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Finishing benching snowbanks, scarifying and widening road from Hwy 17 to Km 10 | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7807KL-20220125-3L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7807KL-20220125-3L.O.A.0.8636364210.7273OEWT-PA25-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7808 | KL-20220125-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.31818 | Day |  | 0 |  |  | 77.6364 | 10.0927 | 87.7291 | 2022-01-25 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal and Heli Pads in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7808KL-20220125-4L.O.A.0.318181877.6364 | KABI LAKE FOREST PRODUCTS LTD7808KL-20220125-4L.O.A.0.318181877.6364OEWT-PA25-Lem | [5 empty] | 1 | 77.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7810 | KL-20220126-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.5 | Day |  | 0 |  |  | 122 | 15.86 | 137.86 | 2022-01-26 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying road from Hwy 17 to Km 10 | 11 | F118-F127 | Henson | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7810KL-20220126-2L.O.A.0.5122 | KABI LAKE FOREST PRODUCTS LTD7810KL-20220126-2L.O.A.0.5122OEWT-PA26-LEM | [5 empty] | 1 | 122 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7811 | KL-20220126-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-26 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader continuing working snow removal and Heli Pads in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7811KL-20220126-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7811KL-20220126-3L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7812 | KL-20220128-1 | 53511111 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2022-01-28 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 and Hensen east to F131 | 11 | F118-F127 | Hensen | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7812KL-20220128-1L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD7812KL-20220128-1L.O.A.1244OEWT-PA26-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7813 | KL-20220128-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2022-01-28 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from F235 to F230 and Pads in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7813KL-20220128-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7813KL-20220128-2L.O.A.0.8636364210.7273OEWT-PA26-LEM | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7815 | KL-20220129-2 | 53511111 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2022-01-29 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal and scarifying from Hwy 17 to Km 17 on Hensen road and Hensen east to F131 | 11 | F118-F127 | Henson | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7815KL-20220129-2L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD7815KL-20220129-2L.O.A.1244OEWT-PA26-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7817 | KL-20220130-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.59091 | Day |  | 0 |  |  | 144.1818 | 18.7436 | 162.9254 | 2022-01-30 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal and scarifying from Hwy 17 to Km 17 on Hensen road | 11 | F118-F127 | Henson | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7817KL-20220130-2L.O.A.0.5909091144.1818 | KABI LAKE FOREST PRODUCTS LTD7817KL-20220130-2L.O.A.0.5909091144.1818OEWT-PA26-LEM | [5 empty] | 1 | 144.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7820 | KL-20220131-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2022-01-31 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader started benching snowbanks and scarifying from Hwy 17 to Km 6 on Hensen road | 11 | F118-F127 | Henson | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7820KL-20220131-3L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7820KL-20220131-3L.O.A.0.6363636155.2727OEWT-PA26-LEM | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7821 | KL-20220131-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-01-31 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from F235 to F230 and Pads in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7821KL-20220131-4L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7821KL-20220131-4L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7823 | KL-20220201-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2022-02-01 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi Cat D6T dozer from 11Km on High Falls Road back to Kabi Yard. | 11 | F170 - F211 | High Falls | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7823KL-20220201-2L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7823KL-20220201-2L.O.A.0.363636488.7273OEWT-PA26-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7824 | KL-20220201-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2022-02-01 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader benching snow banks, widening road, scarifying from 6km to 10km & clearing snow drifts @ 14Km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7824KL-20220201-3L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7824KL-20220201-3L.O.A.0.7727273188.5455OEWT-PA26-LEM | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7825 | KL-20220201-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2022-02-01 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from F235 to F230 and Pads in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7825KL-20220201-4L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7825KL-20220201-4L.O.A.0.6363636155.2727OEWT-PA26-LEM | [5 empty] | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7827 | KL-20220202-2 | 53511111 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2022-02-02 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader finishing benching snow banks, widening road, scarifying from 10km to 17km & clearing snow drifts @ 17Km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7827KL-20220202-2L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD7827KL-20220202-2L.O.A.1244OEWT-PA26-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7829 | KL-20220203-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2022-02-03 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to 17km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7829KL-20220203-2L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7829KL-20220203-2L.O.A.0.363636488.7273OEWT-PA26-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7831 | KL-20220202-3 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-02 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7831KL-20220202-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7831KL-20220202-3L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7834 | KL-20220204-3 | 53511111 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2022-02-04 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader widening road and scarifying from Hwy 17 to 17km on Hensen Road and Hensen East to F-131. | 11 | F118-F127 | Henson | 0 | 44603 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7834KL-20220204-3L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD7834KL-20220204-3L.O.A.1244OEWT-PA26-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7835 | KL-20220204-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-04 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7835KL-20220204-4L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7835KL-20220204-4L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7837 | KL-20220205-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2022-02-05 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Kabi 950 Loader from 7km on Anjigami road to 0.5km on Hensen road. | 11 | F118-F127 | Henson | 0 | 44603 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7837KL-20220205-2L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7837KL-20220205-2L.O.A.0.363636488.7273OEWT-PA26-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7838 | KL-20220205-3 | 53511111 | Access | 0 | L.O.A. | 244 | 1 | Day |  | 0 |  |  | 244 | 31.72 | 275.72 | 2022-02-05 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader benching snowbanks and scarifying from Hwy 17 to 17km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44603 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7838KL-20220205-3L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD7838KL-20220205-3L.O.A.1244OEWT-PA26-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7842 | KL-20220206-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-06 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17Km on Hensen Road (cleared road 2 times due to heavy snow. | 11 | F118-F127 | Henson | 0 | 44603 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7842KL-20220206-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7842KL-20220206-2L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7845 | KL-20220207-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44604 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7845KL-20220207-2L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7845KL-20220207-2L.O.A.0.363636488.7273OEWT-PA26-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7853 | KL-20220208-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2022-02-08 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to 17Km on Hensen Road & snow removal to F131 on Hensen East. Loader clearing pull offs & widening corners to 7km. Supervisor doing pickup shuffle. | 11 | F118 - F127 | Henson | 0 | 44604 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7853KL-20220208-2L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7853KL-20220208-2L.O.A.0.5454545133.0909OEWT-PA26-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7853 | KL-20220208-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2022-02-08 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to 17Km on Hensen Road & snow removal to F131 on Hensen East. Loader clearing pull offs & widening corners to 7km. Supervisor doing pickup shuffle. | 11 | F118 - F127 | Henson | 0 | 44604 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7853KL-20220208-2L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7853KL-20220208-2L.O.A.0.7272727177.4545OEWT-PA26-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7858 | KL-20220209-1 | 53511111 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2022-02-09 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer finishing snow removal from F021 to F032 and clear pads @ F032 | 10 | F009-F065 | Paint Lake | 0 | 44604 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7858KL-20220209-1L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7858KL-20220209-1L.O.A.0.7272727177.4545OEWT-PA26-LEM | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7862 | KL-20220209-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2022-02-09 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to Km 17 on Hensen road /Loader clearing pull offs and widening corners and sanding to Km 12 /Supervisor doing pickup shuffle | 11 | F118-F127 | Henson | 0 | 44604 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7862KL-20220209-5L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7862KL-20220209-5L.O.A.0.363636488.7273OEWT-PA26-LEM | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7862 | KL-20220209-5 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-09 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to Km 17 on Hensen road /Loader clearing pull offs and widening corners and sanding to Km 12 /Supervisor doing pickup shuffle | 11 | F118-F127 | Henson | 0 | 44604 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7862KL-20220209-5L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7862KL-20220209-5L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7867 | KL-20220210-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.5 | Day |  | 0 |  |  | 122 | 15.86 | 137.86 | 2022-02-10 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to Km 17 on Hensen road and benching snowbanks from Km .5 to Km 5/Loader clearing pull offs and widening corners and sanding from Km 5 to Km 17 | 11 | F118-F127 | Henson | 0 | 44605 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7867KL-20220210-4L.O.A.0.5122 | KABI LAKE FOREST PRODUCTS LTD7867KL-20220210-4L.O.A.0.5122OEWT-PA26-LEM | [5 empty] | 1 | 122 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7867 | KL-20220210-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2022-02-10 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to Km 17 on Hensen road and benching snowbanks from Km .5 to Km 5/Loader clearing pull offs and widening corners and sanding from Km 5 to Km 17 | 11 | F118-F127 | Henson | 0 | 44605 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7867KL-20220210-4L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7867KL-20220210-4L.O.A.0.8181818199.6364OEWT-PA26-LEM | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7870 | KL-20220211-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.59091 | Day |  | 0 |  |  | 144.1818 | 18.7436 | 162.9254 | 2022-02-11 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen road /Loader clearing pull offs and sanding from Km 10 to Km 17 | 11 | F118-F127 | Henson | 0 | 44605 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7870KL-20220211-2L.O.A.0.5909091144.1818 | KABI LAKE FOREST PRODUCTS LTD7870KL-20220211-2L.O.A.0.5909091144.1818OEWT-PA26-LEM | [5 empty] | 1 | 144.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7870 | KL-20220211-2 | 53511111 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2022-02-11 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen road /Loader clearing pull offs and sanding from Km 10 to Km 17 | 11 | F118-F127 | Henson | 0 | 44605 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7870KL-20220211-2L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7870KL-20220211-2L.O.A.0.4545455110.9091OEWT-PA26-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7876 | KL-20220212-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2022-02-12 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen road and Hensen Road East to F123/Loader clearing pull offs and sanding from Km 10 to Km 4 | 11 | F118-F127 | Henson | 0 | 44605 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7876KL-20220212-4L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7876KL-20220212-4L.O.A.0.5454545133.0909OEWT-PA26-LEM | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7876 | KL-20220212-4 | 53511111 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2022-02-12 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen road and Hensen Road East to F123/Loader clearing pull offs and sanding from Km 10 to Km 4 | 11 | F118-F127 | Henson | 0 | 44605 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7876KL-20220212-4L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD7876KL-20220212-4L.O.A.0.409090999.8182OEWT-PA26-LEM | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3415 | KL-20200930-23 | 53511112 | Access | 0 | L.O.A. | 244 | 2 | Day |  | 0 |  |  | 488 | 63.44 | 551.44 | 2020-09-30 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pitrun from Provost pit #5 to F204 access | 11 | F-203 to F-211 | High Falls Road | 0 | 44119 |  | 48 | 44120 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3415KL-20200930-23L.O.A.2488 | KABI LAKE FOREST PRODUCTS LTD3415KL-20200930-23L.O.A.2488OEWT-PA10-LEM | [5 empty] | 1 | 488 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7012 | KL-20210611-1 | 53511112 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2021-06-11 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators shaping road, working on drainage from F190 to F191 for pickup access & grinder. | 11 | F185-C193 | High Falls Road - 5 | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7012KL-20210611-1L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7012KL-20210611-1L.O.A.0.272727366.5455OEWT-PA18-Lem | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7013 | KL-20210612-1 | 53511112 | Access | 0 | L.O.A. | 244 | 0.5 | Day |  | 0 |  |  | 122 | 15.86 | 137.86 | 2021-06-12 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator starting road maintenance from 11Km on Hensen to 0.5Km on Hensen East as per Valard. Supervisor doing pickup shuffle. | 11 | F119-F134 | Hensen Road | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7013KL-20210612-1L.O.A.0.5122 | KABI LAKE FOREST PRODUCTS LTD7013KL-20210612-1L.O.A.0.5122OEWT-PA18-Lem | [5 empty] | 1 | 122 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7015 | KL-20210612-3 | 53511112 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2021-06-16 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators shaping road, working on drainage from F191 to F192.5 for pickup access & grinder. | 11 | F185-F193 | High Falls Road - 5 | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7015KL-20210612-3L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7015KL-20210612-3L.O.A.0.272727366.5455OEWT-PA18-Lem | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7016 | KL-20210613-1 | 53511112 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-06-13 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator working on shaping & drainage to 1Km on Hensen East. | 11 | F119-F134 | Hensen Road | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7016KL-20210613-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7016KL-20210613-1L.O.A.0.8181818199.6364OEWT-PA18-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7018 | KL-20210614-1 | 53511112 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-06-14 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator working on shaping & drainage to F122 on Hensen East. | 11 | F119-F134 | Hensen Road | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7018KL-20210614-1L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7018KL-20210614-1L.O.A.0.7727273188.5455OEWT-PA18-Lem | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7019 | KL-20210614-2 | 53511112 | Access | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-06-14 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road, working on drainage out from F193 to F189. | 11 | F185-F193 | High Falls Road - 5 | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7019KL-20210614-2L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7019KL-20210614-2L.O.A.0.7272727177.4545OEWT-PA18-Lem | [5 empty] | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7023 | KL-20210607-1 | 53511112 | Access | 0 | L.O.A. | 244 | 0.68182 | Day |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2021-06-07 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators shaping road, working on drainage & fixing hills from F188 to F190 for pickup access. | 11 | F185-F193 | High Falls Road | 0 | 44365 |  | 50 | 44366 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7023KL-20210607-1L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD7023KL-20210607-1L.O.A.0.6818182166.3636OEWT-PA18-Lem | [5 empty] | 1 | 166.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7024 | KL-20210608-1 | 53511112 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-06-08 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators continuing shaping road, working on drainage & fixing hills from F188 to F190 for pickup access and grinder | 11 | F-185 to F-193 | High Falls Road - 5 | 0 | 44365 |  | 50 | 44366 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7024KL-20210608-1L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7024KL-20210608-1L.O.A.0.4545455110.9091OEWT-PA18-Lem | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7026 | KL-20210615-1 | 53511112 | Access | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-06-15 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator working on shaping & drainage to F127/stockpiling existing material for covering of corduroy sections | 11 | F119-F134 | Hensen Road | 0 | 44365 |  | 50 | 44366 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7026KL-20210615-1L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7026KL-20210615-1L.O.A.0.7727273188.5455OEWT-PA18-Lem | [5 empty] | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7028 | KL-20210615-3 | 53511112 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-06-15 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing shaping road & levelling ruts from F189 to F185. | 11 | F185-F193 | High Falls Road - 5 | 0 | 44365 |  | 50 | 44366 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7028KL-20210615-3L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7028KL-20210615-3L.O.A.0.4545455110.9091OEWT-PA18-Lem | [5 empty] | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7034 | KL-20210616-1 | 53511112 | Access | 0 | L.O.A. | 244 | 0.5 | Day |  | 0 |  |  | 122 | 15.86 | 137.86 | 2021-06-16 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator working on shaping & drainage to F-127 / Stockpiling existing material fro covering of corduroy sections. | 11 | F119-F134 | Hensen Road | 0 | 44368 |  | 50 | 44369 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7034KL-20210616-1L.O.A.0.5122 | KABI LAKE FOREST PRODUCTS LTD7034KL-20210616-1L.O.A.0.5122OEWT-PA18-Lem | [5 empty] | 1 | 122 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7044 | KL-20210620-1 | 53511112 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-06-20 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator repairing washout on hill at WC 12570.00 and access to F171 for pickup access. | 11 | F171-F176 | High Falls Road 1 | 0 | 44369 |  | 50 | 44369 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7044KL-20210620-1L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7044KL-20210620-1L.O.A.0.363636488.7273OEWT-PA18-Lem | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7058 | KL-20210621-1 | 53511112 | Access | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2021-06-21 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Levelling ruts and shaping access from F-171 to F-177 | 11 | F171-F176 | High Falls Road - 1 | 0 | 44370 |  | 50 | 44371 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7058KL-20210621-1L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7058KL-20210621-1L.O.A.0.5454545133.0909OEWT-PA18-Lem | [5 empty] | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7194 | KL-20210803-1 | 53511112 | Access | 0 | L.O.A. | 244 | 0.13636 | Day |  | 0 |  |  | 33.2727 | 4.3255 | 37.5982 | 2021-08-03 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer & Operator moving rock truck from F-037 to F-119 & tracking Cat 330 excavator from 17Km on Hensen to 46Km on paint lake road 2 for gravel haul | 11 | F118-F127 | Hensen Road | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD7194KL-20210803-1L.O.A.0.136363633.2727 | KABI LAKE FOREST PRODUCTS LTD7194KL-20210803-1L.O.A.0.136363633.2727OEWT-PA20-Lem | [5 empty] | 1 | 33.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7194 | KL-20210803-1 | 53511112 | Access | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-08-03 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer & Operator moving rock truck from F-037 to F-119 & tracking Cat 330 excavator from 17Km on Hensen to 46Km on paint lake road 2 for gravel haul | 11 | F118-F127 | Hensen Road | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD7194KL-20210803-1L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7194KL-20210803-1L.O.A.0.363636488.7273OEWT-PA20-Lem | [5 empty] | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7601 | KL-20211029-2 | 53511112 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-29 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continue working on drainage, tracking material and shaping road @ F126 / F125 | 11 | F118 - F134 | Henson | 0 | 44501 |  | 61 | 44503 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7601KL-20211029-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7601KL-20211029-2L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7484 | KL-20211023-2 | 53511112 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-23 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul trees for fill and start capping with existing material @ F123 to F124 access realignment | 11 | F119-F134 | Hensen Road | 0 | 44495 |  | 61 | 44496 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7484KL-20211023-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7484KL-20211023-2L.O.A.0.8636364210.7273OEWT-PA22-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7484 | KL-20211023-2 | 53511112 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-23 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul trees for fill and start capping with existing material @ F123 to F124 access realignment | 11 | F119-F134 | Hensen Road | 0 | 44495 |  | 61 | 44496 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7484KL-20211023-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7484KL-20211023-2L.O.A.0.8181818199.6364OEWT-PA22-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7486 | KL-20211024-2 | 53511112 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from F123 access to F124 access realignment capping and start raising road and 1.5 km for crane access | 11 | F119-F134 | Hensen Road | 0 | 44495 |  | 61 | 44497 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7486KL-20211024-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7486KL-20211024-2L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7486 | KL-20211024-2 | 53511112 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from F123 access to F124 access realignment capping and start raising road and 1.5 km for crane access | 11 | F119-F134 | Hensen Road | 0 | 44495 |  | 61 | 44497 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7486KL-20211024-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7486KL-20211024-2L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7486 | KL-20211024-2 | 53511112 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from F123 access to F124 access realignment capping and start raising road and 1.5 km for crane access | 11 | F119-F134 | Hensen Road | 0 | 44495 |  | 61 | 44497 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7486KL-20211024-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7486KL-20211024-2L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7489 | KL-20211025-2 | 53511112 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to 1.5 km for raising of road | 11 | F119-F134 | Hensen Road | 0 | 44496 |  | 61 | 44497 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7489KL-20211025-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7489KL-20211025-2L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7489 | KL-20211025-2 | 53511112 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to 1.5 km for raising of road | 11 | F119-F134 | Hensen Road | 0 | 44496 |  | 61 | 44497 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7489KL-20211025-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7489KL-20211025-2L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7489 | KL-20211025-2 | 53511112 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to 1.5 km for raising of road | 11 | F119-F134 | Hensen Road | 0 | 44496 |  | 61 | 44497 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7489KL-20211025-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7489KL-20211025-2L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7493 | KL-20211026-2 | 53511112 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-26 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul existing material from Km 17 on Hensen Road to F124 for capping | 11 | F118-F127 | Hensen | 0 | 44501 |  | 61 | 44502 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7493KL-20211026-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7493KL-20211026-2L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7493 | KL-20211026-2 | 53511112 | Access | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-10-26 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul existing material from Km 17 on Hensen Road to F124 for capping | 11 | F118-F127 | Hensen | 0 | 44501 |  | 61 | 44502 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7493KL-20211026-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7493KL-20211026-2L.O.A.0.8636364210.7273OEWT-PA23-Lem | [5 empty] | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7493 | KL-20211026-2 | 53511112 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-26 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul existing material from Km 17 on Hensen Road to F124 for capping | 11 | F118-F127 | Hensen | 0 | 44501 |  | 61 | 44502 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7493KL-20211026-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7493KL-20211026-2L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7493 | KL-20211026-2 | 53511112 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-26 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul existing material from Km 17 on Hensen Road to F124 for capping | 11 | F118-F127 | Hensen | 0 | 44501 |  | 61 | 44502 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7493KL-20211026-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7493KL-20211026-2L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7497 | KL-20211027-2 | 53511112 | Access | 0 | L.O.A. | 244 | 0.68182 | Day |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul existing material from Km 17 on Hensen Road to F124 for capping/excavator speading existing material and shaping road from Hensen Road to F123 | 11 | F118-F127 | Hensen | 0 | 44501 |  | 61 | 44502 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7497KL-20211027-2L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD7497KL-20211027-2L.O.A.0.6818182166.3636OEWT-PA23-Lem | [5 empty] | 1 | 166.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7497 | KL-20211027-2 | 53511112 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul existing material from Km 17 on Hensen Road to F124 for capping/excavator speading existing material and shaping road from Hensen Road to F123 | 11 | F118-F127 | Hensen | 0 | 44501 |  | 61 | 44502 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7497KL-20211027-2L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD7497KL-20211027-2L.O.A.0.409090999.8182OEWT-PA23-Lem | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7497 | KL-20211027-2 | 53511112 | Access | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul existing material from Km 17 on Hensen Road to F124 for capping/excavator speading existing material and shaping road from Hensen Road to F123 | 11 | F118-F127 | Hensen | 0 | 44501 |  | 61 | 44502 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7497KL-20211027-2L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD7497KL-20211027-2L.O.A.0.409090999.8182OEWT-PA23-Lem | [5 empty] | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7497 | KL-20211027-2 | 53511112 | Access | 0 | L.O.A. | 244 | 0.22727 | Day |  | 0 |  |  | 55.4545 | 7.2091 | 62.6636 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul existing material from Km 17 on Hensen Road to F124 for capping/excavator speading existing material and shaping road from Hensen Road to F123 | 11 | F118-F127 | Hensen | 0 | 44501 |  | 61 | 44502 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7497KL-20211027-2L.O.A.0.227272755.4545 | KABI LAKE FOREST PRODUCTS LTD7497KL-20211027-2L.O.A.0.227272755.4545OEWT-PA23-Lem | [5 empty] | 1 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7503 | KL-20211028-2 | 53511112 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-28 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking from F123 to F127 working on drainage and shaping road to F126 | 11 | F118-F127 | Hensen Road | 0 | 44501 |  | 61 | 44502 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7503KL-20211028-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7503KL-20211028-2L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7511 | KL-20211030-2 | 53511112 | Access | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-10-30 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing working on drainage, shaping road and sloping excavation @ Km .5 on Hensen Road East | 11 | F119-F127 | Hensen Road | 0 | 44502 |  | 61 | 44503 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7511KL-20211030-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7511KL-20211030-2L.O.A.0.8181818199.6364OEWT-PA23-Lem | [5 empty] | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7589 | KL-20211123-4 | 53511112 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2021-11-23 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader starting to scrape and sand road to Km 14 for stringing crews | 11 | F212-F235 | Ainjigame | 0 | 44529 |  | 61 | 44530 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7589KL-20211123-4L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD7589KL-20211123-4L.O.A.0.272727366.5455OEWT-PA23-Lem | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6610 | KL-20210402-2-R1 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.68182 | Day |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2021-04-02 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track out to Km 1 on Hensen East for refueling and back to F132/ Continue reclamation @ F132/ ATV used due to no pickup access. Excavator time reduced from signed ticket for tracking as per Valard direction. Remaining excavator time will be submitted on KL-20210402-2-S1 | 11 | F119-F134 | Hensen Road | 0 | 44298 |  | 56 | 44329 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6610KL-20210402-2-R1L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD6610KL-20210402-2-R1L.O.A.0.6818182166.3636OEWT-PA17-LEM |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 166.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6611 | KL-20210402-3 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-04-02 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start Reclamation @ F135 to F136 | 11 | F135-F149 | Dore Lake Road | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6611KL-20210402-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD6611KL-20210402-3L.O.A.0.8181818199.6364OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6614 | KL-20210403-3 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2021-04-03 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F136 to F137/ side by side used due to no pickup access | 11 | F-135 to F-149 | Dore Lake Road | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6614KL-20210403-3L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD6614KL-20210403-3L.O.A.0.5454545133.0909OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6615 | KL-20210403-4 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-04-03 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F133 to F132/ ATV used due to no pickup access | 11 | F-119 to F-134 | Hensen Road | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6615KL-20210403-4L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD6615KL-20210403-4L.O.A.0.7727273188.5455OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6619 | KL-20210404-4 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.77274 | Day |  | 0 |  |  | 188.5479 | 24.5112 | 213.0591 | 2021-04-04 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish reclamation from F133/ F131 and track out to Km 17 on Hensen Road/ ATV used due to no pickup access | 11 | F119-F134 | Hensen Road | 0 | 44298 |  | 15 | 44303 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD6619KL-20210404-4L.O.A.0.7727373188.5479 | KABI LAKE FOREST PRODUCTS LTD6619KL-20210404-4L.O.A.0.7727373188.5479OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 188.5479 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6620 | KL-20210404-5 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2021-04-04 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 336 Excavator to Km 3 on Dore Lake road for Reclamation of Dore Lake Road West | 11 | F-135 to F-149 | Dore Lake Road | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6620KL-20210404-5L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD6620KL-20210404-5L.O.A.0.409090999.8182OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6624 | KL-20210405-4-R1 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2021-04-05 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F137 to F138/ Cat 336 excavator tracking in from km 3 on Dore Road and starting @ F140. Chapman Reclamation of Dore lake Road East - CE-195. Excavator/pickup hours reduced for tracking time from signed ticket per Valard direction. Tracking time will be submitted on LEM KL-20210405-4-S1 | 11 | F-135 to F-149 | Dore lake Road | 0 | 44298 |  | 56 | 44329 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6624KL-20210405-4-R1L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD6624KL-20210405-4-R1L.O.A.0.409090999.8182OEWT-PA17-LEM |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 99.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6624 | KL-20210405-4-R1 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-04-05 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F137 to F138/ Cat 336 excavator tracking in from km 3 on Dore Road and starting @ F140. Chapman Reclamation of Dore lake Road East - CE-195. Excavator/pickup hours reduced for tracking time from signed ticket per Valard direction. Tracking time will be submitted on LEM KL-20210405-4-S1 | 11 | F-135 to F-149 | Dore lake Road | 0 | 44298 |  | 56 | 44329 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6624KL-20210405-4-R1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD6624KL-20210405-4-R1L.O.A.0.9090909221.8182OEWT-PA17-LEM |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6661 | KL-20210406-5-R1 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-04-06 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F138 to F141. Two hours of equipment/live out and pick up time removed from each excavator/operator from approved field ticket as per Valard direction. Those charges now listed on LEM KL-20210406-5-S1. | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | 44328 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6661KL-20210406-5-R1L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD6661KL-20210406-5-R1L.O.A.0.7272727177.4545OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6661 | KL-20210406-5-R1 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-04-06 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F138 to F141. Two hours of equipment/live out and pick up time removed from each excavator/operator from approved field ticket as per Valard direction. Those charges now listed on LEM KL-20210406-5-S1. | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | 44328 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6661KL-20210406-5-R1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD6661KL-20210406-5-R1L.O.A.0.8181818199.6364OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6662 | KL-20210406-6 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-04-06 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F150 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44292 |  | 56 | 44305 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6662KL-20210406-6L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD6662KL-20210406-6L.O.A.0.9090909221.8182OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6674 | KL-20210407-6 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-04-07 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 1 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  | 29 | Approved | STR & PAD SITE RECLAIM | 8008 | Start Reclamation @ F151/Sloping crane pad amd assembley pad (Revised) | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44305 |  | 56 | 44309 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6674KL-20210407-6L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD6674KL-20210407-6L.O.A.0.8181818199.6364OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6677 | KL-20210408-2 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.86364 | Day |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-04-08 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 1 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  | 29 | Approved | STR & PAD SITE RECLAIM | 8008 | Continue Reclamation @ F151/ sloping crane pads and assembly pad | 11 | F150-F151 | Michipicoten Harbour Road -1 | 1 | 44305 |  | 56 | 44307 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6677KL-20210408-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD6677KL-20210408-2L.O.A.0.8636364210.7273OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 210.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6680 | KL-20210408-5-R1 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-04-08 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Skagen 350 Excavator from Ajigami for Reclamation. Start Reclamation @F152. Supervisor and pickup hours from signed ticket removed per Valard direction, will be listed on KL-20210408-5-S1. | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44305 |  | 56 | 44329 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6680KL-20210408-5-R1L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD6680KL-20210408-5-R1L.O.A.0.4545455110.9091OEWT-PA17-LEM |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6687 | KL-20210409-7 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-04-09 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 1 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  | 29 | Approved | STR & PAD SITE RECLAIM | 8008 | Continue Reclamation @F151/ Sloping crane pad and assembley pad | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44306 |  | 56 | 44309 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6687KL-20210409-7L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD6687KL-20210409-7L.O.A.0.4545455110.9091OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6704 | KL-20210412-6 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-04-12 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @F151 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44308 |  | 56 | 44309 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6704KL-20210412-6L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD6704KL-20210412-6L.O.A.0.9090909221.8182OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6757 | KL-20210414-6 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-04-14 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue reclamation @ F151 and F150. | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44309 |  | 56 | 44312 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6757KL-20210414-6L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD6757KL-20210414-6L.O.A.0.9545455232.9091OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6781 | KL-20210415-2 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-04-15 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F151 and F150 (Revised ). Removing wood, re-contouring road area. | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44317 |  | 56 | 44319 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6781KL-20210415-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD6781KL-20210415-2L.O.A.0.8181818199.6364OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6784 | KL-20210415-5 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-04-15 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator Working on Reclamation@ F143/ F144 (Second Revision as per Valard ) | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44319 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6784KL-20210415-5L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD6784KL-20210415-5L.O.A.0.7727273188.5455OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6786 | KL-20210407-8 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-04-07 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F139 to F143 (third revision.) Quad was used for operator travel to excavator, no tracking of excavator. | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44320 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6786KL-20210407-8L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD6786KL-20210407-8L.O.A.0.8181818199.6364OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6787 | KL-20210407-9 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.63636 | Day |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2021-04-07 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation of structure pads @ F141 to F143 (fourth revision.) | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44320 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6787KL-20210407-9L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD6787KL-20210407-9L.O.A.0.6363636155.2727OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 155.2727 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6788 | KL-20210408-6 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.90909 | Day |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-04-08 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator working on Reclamation @F139 to F140. Quad used for operator travel, no tracking of excavator. | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6788KL-20210408-6L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD6788KL-20210408-6L.O.A.0.9090909221.8182OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 221.8182 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6789 | KL-20210408-7 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-04-08 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator working on Reclamationof structure pads and access @ F145/F144 (fourth revision) | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44320 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6789KL-20210408-7L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD6789KL-20210408-7L.O.A.0.8181818199.6364OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6790 | KL-20210409-8 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-04-09 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator working on reclamation @f139 to F140. (Third Revision). Quad used for operator travel, no tracking time for equipment. | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44320 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6790KL-20210409-8L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD6790KL-20210409-8L.O.A.0.4545455110.9091OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6791 | KL-20210409-9 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.31818 | Day |  | 0 |  |  | 77.6364 | 10.0927 | 87.7291 | 2021-04-09 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator working on reclamation @f139 to F140. (Third Revision). Quad used for operator travel, no tracking time for equipment. | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44320 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6791KL-20210409-9L.O.A.0.318181877.6364 | KABI LAKE FOREST PRODUCTS LTD6791KL-20210409-9L.O.A.0.318181877.6364OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 77.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6793 | KL-20210412-8 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-04-12 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 excavator working on Reclamation @ F141/F142 (fourth revision) | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6793KL-20210412-8L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD6793KL-20210412-8L.O.A.0.7272727177.4545OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6795 | KL-20210413-6 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-04-13 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 and Cat 330 Excavators workimg on Reclamation @F141 and F143 (4th Revision) | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6795KL-20210413-6L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD6795KL-20210413-6L.O.A.0.4545455110.9091OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6795 | KL-20210413-6 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-04-13 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 and Cat 330 Excavators workimg on Reclamation @F141 and F143 (4th Revision) | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6795KL-20210413-6L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD6795KL-20210413-6L.O.A.0.7272727177.4545OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 177.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6797 | KL-20210414-9 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-04-14 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 and Cat 336 excavators working on Reclamation @ F142 and F143 (3rd revision) | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6797KL-20210414-9L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD6797KL-20210414-9L.O.A.0.4545455110.9091OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6799 | KL-20210416-2 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2021-04-16 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator working on Reclamation @F142 and F143. Skidder removing WC-12150 | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6799KL-20210416-2L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD6799KL-20210416-2L.O.A.0.5454545133.0909OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6800 | KL-20210416-3 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.95455 | Day |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-04-16 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @F150 and F151 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6800KL-20210416-3L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD6800KL-20210416-3L.O.A.0.9545455232.9091OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 232.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6802 | KL-20210417-2 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.68182 | Day |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2021-04-17 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator working on Reclamation @F143 and F144 | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6802KL-20210417-2L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD6802KL-20210417-2L.O.A.0.6818182166.3636OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 166.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6808 | KL-20210418-1 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-04-18 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator working on reclamation @F144 and F145 ( Second revision). Chapman access reclamation at 7.5Km. | 11 | F135-F149 | Dore Lake Road | 0 | 44322 |  | 56 | 44323 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6808KL-20210418-1L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD6808KL-20210418-1L.O.A.0.7727273188.5455OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6810 | KL-20210419-1 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.68182 | Day |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2021-04-19 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 excavator working on reclamation on access to F145 (revised). Chapman removing access material from 7km to 4km Dore Lake Road. | 11 | F135-F149 | Dore Lake Road | 0 | 44322 |  | 57 | 44323 | [5 empty] | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6810KL-20210419-1L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD6810KL-20210419-1L.O.A.0.6818182166.3636OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 166.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6811 | KL-20210420-1 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.54545 | Day |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2021-04-20 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator completing reclamation on access to F145 ( revised as per Valard ) | 11 | F135-F149 | Dore lake Road | 0 | 44322 |  | 57 | 44323 | [5 empty] | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6811KL-20210420-1L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD6811KL-20210420-1L.O.A.0.5454545133.0909OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 133.0909 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6840 | KL-20210331-5 | 53541101 | Reclamation | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-03-31 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track to F133 from Km 17 on Hensen and start reclaimation @ F133/F132. ATV used for crew due to no pickup access | 11 | F119-F134 | Hensen Road | 0 | 44326 |  | 57 | 44327 | [5 empty] | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6840KL-20210331-5L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD6840KL-20210331-5L.O.A.0.7727273188.5455OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 188.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6607 | KL-20210401-6 | 53541104 | Reclamation | 0 | L.O.A. | 244 | 0.81818 | Day |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-04-01 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Gravel Removal (Access) |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclaimation @ F133/ F132/ ATV used due to no pickup access | 11 | F119-F134 | Hensen Road | 0 | 44298 |  | 57 | 44305 | [5 empty] | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6607KL-20210401-6L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD6607KL-20210401-6L.O.A.0.8181818199.6364OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 199.6364 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6628 | KL-20210405-8 | 53541105 | Reclamation | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-04-05 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Erosion Cont Inst/Mon/Rem |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start Reclamation @ F150 | 11 | F-150 to F-151 | Michipicoten Harbour Road -1 | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6628KL-20210405-8L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD6628KL-20210405-8L.O.A.0.363636488.7273OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4849 | KL-20201212-14 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2020-12-12 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic Breaker & support excavator starting on F123 Access breaking outcrops on steep grades /straighten corners/ operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 48 | 44203 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4849KL-20201212-14L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD4849KL-20201212-14L.O.A.0.4545455110.9091OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4849 | KL-20201212-14 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.40909 | Day |  | 0 |  |  | 99.8182 | 12.9764 | 112.7946 | 2020-12-12 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic Breaker & support excavator starting on F123 Access breaking outcrops on steep grades /straighten corners/ operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 48 | 44203 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4849KL-20201212-14L.O.A.0.409090999.8182 | KABI LAKE FOREST PRODUCTS LTD4849KL-20201212-14L.O.A.0.409090999.8182OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 49.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4988 | KL-20201213-13 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2020-12-13 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic breaker and support Excavator working on F123 access breaking outcrops on steep grade and straighten corners/ oper. travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 55 | 44209 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4988KL-20201213-13L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD4988KL-20201213-13L.O.A.0.7727273188.5455OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 94.2728 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4988 | KL-20201213-13 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2020-12-13 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic breaker and support Excavator working on F123 access breaking outcrops on steep grade and straighten corners/ oper. travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 55 | 44209 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4988KL-20201213-13L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD4988KL-20201213-13L.O.A.0.7727273188.5455OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 94.2728 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5010 | KL-20201214-13 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator hydaulic breaker and support excavator working onF123 access breaking outcrops on steep grades and straighten corners / operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44196 |  | 55 | 44209 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5010KL-20201214-13L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD5010KL-20201214-13L.O.A.0.7727273188.5455OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 94.2728 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5010 | KL-20201214-13 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator hydaulic breaker and support excavator working onF123 access breaking outcrops on steep grades and straighten corners / operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44196 |  | 55 | 44209 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5010KL-20201214-13L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD5010KL-20201214-13L.O.A.0.7727273188.5455OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 94.2728 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5038 | KL-20201216-10 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2020-12-16 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic Breaker and Support Excavator working on F127 access breaking outcrops on steep grades and straighten corners/ operator travel as per valard | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5038KL-20201216-10L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD5038KL-20201216-10L.O.A.0.7727273188.5455OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 94.2728 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5038 | KL-20201216-10 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2020-12-16 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic Breaker and Support Excavator working on F127 access breaking outcrops on steep grades and straighten corners/ operator travel as per valard | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5038KL-20201216-10L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD5038KL-20201216-10L.O.A.0.7727273188.5455OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 94.2728 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5062 | KL-20201219-9 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.68182 | Day |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2020-12-19 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc with hydraulic breaker & support exc working on F127 Access breaking outcrops on steep grades. Straighten corners. Operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5062KL-20201219-9L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD5062KL-20201219-9L.O.A.0.6818182166.3636OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 83.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5062 | KL-20201219-9 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.68182 | Day |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2020-12-19 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc with hydraulic breaker & support exc working on F127 Access breaking outcrops on steep grades. Straighten corners. Operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5062KL-20201219-9L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD5062KL-20201219-9L.O.A.0.6818182166.3636OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 83.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5110 | KL-20201217-18 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic breaker and support excavator working on F127 access Breaking outcrops on steep grades and straighten corners/ operators as per valard | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5110KL-20201217-18L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD5110KL-20201217-18L.O.A.0.7272727177.4545OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 88.7272 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5110 | KL-20201217-18 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic breaker and support excavator working on F127 access Breaking outcrops on steep grades and straighten corners/ operators as per valard | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5110KL-20201217-18L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD5110KL-20201217-18L.O.A.0.7272727177.4545OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 88.7272 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5122 | KL-20201220-9 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2020-12-20 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker & support exc working on F127 Access breaking outcrops on steep grades & straighten corners/operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5122KL-20201220-9L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD5122KL-20201220-9L.O.A.0.363636488.7273OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5122 | KL-20201220-9 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.27273 | Day |  | 0 |  |  | 66.5455 | 8.6509 | 75.1964 | 2020-12-20 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker & support exc working on F127 Access breaking outcrops on steep grades & straighten corners/operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5122KL-20201220-9L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD5122KL-20201220-9L.O.A.0.272727366.5455OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 33.2728 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5217 | KL-20210104-6 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-01-04 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker and support excavator working on F117 access breaking outcrops on steep grades and laying trees/ Operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5217KL-20210104-6L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD5217KL-20210104-6L.O.A.0.7727273188.5455OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 94.2728 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5217 | KL-20210104-6 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-01-04 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker and support excavator working on F117 access breaking outcrops on steep grades and laying trees/ Operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5217KL-20210104-6L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD5217KL-20210104-6L.O.A.0.7727273188.5455OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 94.2728 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5230 | KL-20210105-9 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-01-05 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker and support excavator working on F117 access breaking outcrops an steep grades/ Operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5230KL-20210105-9L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD5230KL-20210105-9L.O.A.0.7727273188.5455OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 94.2728 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5230 | KL-20210105-9 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-01-05 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker and support excavator working on F117 access breaking outcrops an steep grades/ Operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5230KL-20210105-9L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD5230KL-20210105-9L.O.A.0.7727273188.5455OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 94.2728 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5243 | KL-20210106-7 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-01-06 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker working on F117 access breaking outcrops on steep grades/ operator travel as per valard | 11 | F119-F134 | Hensen Road | 0 | 44209 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5243KL-20210106-7L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD5243KL-20210106-7L.O.A.0.7727273188.5455OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 94.2728 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5267 | KL-20210107-16 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-01-07 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker working on F117 Access breaking outcrops on steep grades/operator travel as per Valard. Skagen excavator supporting breaker. | 11 | F119-F134 | Hensen Road | 0 | 44209 |  | 15 | 44219 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5267KL-20210107-16L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD5267KL-20210107-16L.O.A.0.7727273188.5455OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 94.2728 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5280 | KL-20210109-3 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.18182 | Day |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2021-01-09 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc with hydraulic breaker breaking rock on Access @ 12070.01 WC | 11 | F119-F134 | Hensen Road | 0 | 44211 |  | 15 | 44219 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5280KL-20210109-3L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD5280KL-20210109-3L.O.A.0.181818244.3636OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 22.1818 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5628 | KL-20210126-12 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.5 | Day |  | 0 |  |  | 122 | 15.86 | 137.86 | 2021-01-26 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | EXC with breaker & support excavator working on F111 Access breaking outcrops & laying trees. Operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44228 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5628KL-20210126-12L.O.A.0.5122 | KABI LAKE FOREST PRODUCTS LTD5628KL-20210126-12L.O.A.0.5122OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 61 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5628 | KL-20210126-12 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.77273 | Day |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-01-26 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | EXC with breaker & support excavator working on F111 Access breaking outcrops & laying trees. Operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44228 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5628KL-20210126-12L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD5628KL-20210126-12L.O.A.0.7727273188.5455OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 94.2728 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5648 | KL-20210127-16 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-01-27 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc with hydraulic breaker & support excavator working on F111 Access breaking outcrops & laying trees/operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44228 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5648KL-20210127-16L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD5648KL-20210127-16L.O.A.0.4545455110.9091OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5648 | KL-20210127-16 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-01-27 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc with hydraulic breaker & support excavator working on F111 Access breaking outcrops & laying trees/operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44228 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5648KL-20210127-16L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD5648KL-20210127-16L.O.A.0.4545455110.9091OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 55.4545 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5656 | KL-20210128-8 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2021-01-28 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc w breaker & support exc working on F111 Access breaking outcrops & laying trees/ operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5656KL-20210128-8L.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD5656KL-20210128-8L.O.A.0.363636488.7273OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 44.3636 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5656 | KL-20210128-8 | 53551103 | Earthworks | 0 | L.O.A. | 244 | 0.72727 | Day |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-01-28 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc w breaker & support exc working on F111 Access breaking outcrops & laying trees/ operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5656KL-20210128-8L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD5656KL-20210128-8L.O.A.0.7272727177.4545OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 88.7272 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7928 | KL-20220301-1-RCL | 53541007 | Reclamation | 0 | L.O.A. | 244 | 0.45455 | Day |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2022-03-01 |  | OEWT-PA27-RCL | 2022-03-31 |  | 0 | 0 | Nathan Kyme | Reclamation Mob/Demob | Reclamation Mob/Demob | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float moved 330 excavator from White Lake West to 9.2km on Paint Lake 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44623 |  | 37 | 44621 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7928KL-20220301-1-RCLL.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7928KL-20220301-1-RCLL.O.A.0.4545455110.9091 | WF10-Access | WF10-Access | WF10-Access | 1 | 1 | 1 | 110.9091 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7929 | KL-20220302-1-RCL | 53541007 | Reclamation | 0 | L.O.A. | 244 | 0.5 | Day |  | 0 |  |  | 122 | 15.86 | 137.86 | 2022-03-02 |  | OEWT-PA27-RCL | 2022-03-31 |  | 0 | 0 | Nathan Kyme | Reclamation Mob/Demob | Reclamation Mob/Demob | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float moved 336 excavator from Dubreuilville Mine to 9.2km on Paint Lake 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44623 |  | 37 | 44623 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7929KL-20220302-1-RCLL.O.A.0.5122 | KABI LAKE FOREST PRODUCTS LTD7929KL-20220302-1-RCLL.O.A.0.5122 | WF10-Access | WF10-Access | WF10-Access | 1 | 1 | 1 | 122 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7950 | KL-20220307-1-RCL | 53541007 | Reclamation | 0 | L.O.A. | 244 | 0.5 | Day |  | 0 |  |  | 122 | 15.86 | 137.86 | 2022-03-07 |  | OEWT-PA27-RCL | 2022-03-31 |  | 0 | 0 | Nathan Kyme | Reclamation Mob/Demob | Reclamation Mob/Demob | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float 336 excavator from 9.2km Paint Lake 2 back to Dubreuilville | 10 | F066-F118 | Paint Lake 2 | 0 | 44627 |  | 37 | 44627 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7950KL-20220307-1-RCLL.O.A.0.5122 | KABI LAKE FOREST PRODUCTS LTD7950KL-20220307-1-RCLL.O.A.0.5122 | WF10-Access | WF10-Access | WF10-Access | 1 | 1 | 1 | 122 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7952 | KL-20220308-1-RCL | 53541007 | Reclamation | 0 | L.O.A. | 244 | 0.36364 | Day |  | 0 |  |  | 88.7273 | 11.5345 | 100.2618 | 2022-03-08 |  | OEWT-PA27-RCL | 2022-03-31 |  | 0 | 0 | Nathan Kyme | Reclamation Mob/Demob | Reclamation Mob/Demob | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float 330 excavator from 9.2km Paint Lake 2 to Kabi yard | 10 | F066-F118 | Paint Lake 2 | 0 | 44628 |  | 37 | 44628 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7952KL-20220308-1-RCLL.O.A.0.363636488.7273 | KABI LAKE FOREST PRODUCTS LTD7952KL-20220308-1-RCLL.O.A.0.363636488.7273 | WF10-Access | WF10-Access | WF10-Access | 1 | 1 | 1 | 88.7273 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5368 | KL-20210114-14 | 53511103 | Access | 0 | CAT 5218 Buncher - MFN WF11 Only | 326.93 | 4 | HR | 246 | 0 |  |  | 1307.72 | 170.0036 | 1477.7236 | 2021-01-14 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Carry Corduroy for wetlands on F147 Access. Buncher rate from Const. Amend #4. | 11 | F135-F149 | Dore Lake Road | 0 | 44218 |  | 56 | 44220 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5368KL-20210114-14CAT 5218 Buncher - MFN WF11 Only41307.72 | KABI LAKE FOREST PRODUCTS LTD5368KL-20210114-14CAT 5218 Buncher - MFN WF11 Only41307.72OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 1307.72 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5380 | KL-20210115-11 | 53511103 | Access | 0 | CAT 5218 Buncher - MFN WF11 Only | 326.93 | 2 | HR | 246 | 0 |  |  | 653.86 | 85.0018 | 738.8618 | 2021-01-15 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Buncher track in and out from F147 access to F145 Junction. Morin track and place corduroy. Buncher rate from Const. Amend #4 | 11 | F135-F149 | Dore Lake Road | 0 | 44218 |  | 56 | 44220 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5380KL-20210115-11CAT 5218 Buncher - MFN WF11 Only2653.86 | KABI LAKE FOREST PRODUCTS LTD5380KL-20210115-11CAT 5218 Buncher - MFN WF11 Only2653.86OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 653.86 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7123 | 31587 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 7 | Day |  | 0 |  |  | 1575 | 204.75 | 1779.75 | 2021-06-30 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel In. Travel to jobsite. Complete site walkthrough, toolbox talk and safety talk with Valard. Unload and rack 261 Mats. Ensure mat safety. Travel out. ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44382 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712331587Crew Truck71575 | Northern Mat & Bridge712331587Crew Truck71575ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1575 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7124 | 21603 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 7 | Day |  | 0 |  |  | 1575 | 204.75 | 1779.75 | 2021-07-01 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Should have stat holiday rates, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | Jason, Cutler travel to site. Safety meeting with Valard. Load G&G flatbeds from laydown to km 17 Henson Rd. Rest of crew awaiting covid test results and travelling from Thunder Bay. Crew arrived, started shuttling mats to ROW. Crew travelled out. ## Covid 19 protocols in place ## | 10 | F109 | Hensen Road | 0 | 44383 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712421603Crew Truck71575 | Northern Mat & Bridge712421603Crew Truck71575ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1575 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7125 | 21604 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 6 | Day |  | 0 |  |  | 1350 | 175.5 | 1525.5 | 2021-07-02 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Entered with regular rates however LEM had stat holiday rates, sent back for revision, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks at km1 laydown. Haulmats from laydown to km 17 Henson rd. shuttle mats from km 17 to Row. Lay mats as per valard intruction. Crew travelled out. ## COVID-19 protocols in effect ## | 10 | F109 | Hensen Road | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712521604Crew Truck61350 | Northern Mat & Bridge712521604Crew Truck61350ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1350 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7126 | 21607 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 6 | Day |  | 0 |  |  | 1350 | 175.5 | 1525.5 | 2021-07-03 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travel to site. Safety meeting. Load, unload trucks. Haul mats onsite from laydown to KM17. shuttle and lay mats as per Valard instruction. ## COVID 19 protocol in effect ## | 10 | F065-F118 | Paint Lake 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712621607Crew Truck61350 | Northern Mat & Bridge712621607Crew Truck61350ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1350 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7128 | 20611 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 6 | Day |  | 0 |  |  | 1350 | 175.5 | 1525.5 | 2021-07-05 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | Crew travelled in. safety meeting. Load unload trucks, shuttle mats, lay mats as per Valard instructions. Corey Trembett finished covid test in Thunder Bay and travelled to site to run 2nd shuttle ## COVID 19 policies in effect ## | 10 | F065-F118 | Paint lake Road 2 | 0 | 44384 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712820611Crew Truck61350 | Northern Mat & Bridge712820611Crew Truck61350ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1350 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7129 | 21613 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 6 | Day |  | 0 |  |  | 1350 | 175.5 | 1525.5 | 2021-07-06 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew traveled to location, safety meeting, Load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew traveled out. ## COVID-19 policies in effect ## Dylan Thompson travelling to Thunder Bay for Valard COVID test. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712921613Crew Truck61350 | Northern Mat & Bridge712921613Crew Truck61350ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1350 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7130 | 21615 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 6 | Day |  | 0 |  |  | 1350 | 175.5 | 1525.5 | 2021-07-07 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew travelled in, safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Shuttle one load of mats with roll off, determined high potential for a spill, use roll off to move mats to Paint lake road as per Valard, moved 28 mats to Paint Lake road. Dylan Thompson enroute to Thunder Bay for Valard covid test. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa fore work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge713021615Crew Truck61350 | Northern Mat & Bridge713021615Crew Truck61350ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1350 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7142 | 21619 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 6 | Day |  | 0 |  |  | 1350 | 175.5 | 1525.5 | 2021-07-09 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in. safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Deliver another load of 10 mats to km 7-8 on paint lake with roll-off for road repair. Total of 32 mats at km 7-8 on Paint Lake Rd. crew travelled out. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa for work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44387 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714221619Crew Truck61350 | Northern Mat & Bridge714221619Crew Truck61350ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1350 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 5 | Day |  | 0 |  |  | 1125 | 146.25 | 1271.25 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Crew Truck51125 | Northern Mat & Bridge714321620Crew Truck51125ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1125 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7144 | 21621 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 5 | Day |  | 0 |  |  | 1125 | 146.25 | 1271.25 | 2021-07-11 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | crew travelled in, safety meeting,load unload trucks, shuttle mats, lay mats as per Valard instructions. ## covid 19 policies in effect ## crew travelled out | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44389 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714421621Crew Truck51125 | Northern Mat & Bridge714421621Crew Truck51125ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1125 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7145 | 21622 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 5 | Day |  | 0 |  |  | 1125 | 146.25 | 1271.25 | 2021-07-12 | 0 | ESI10770 | 44452 | 68 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44390 |  | 14 | 44449 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714521622Crew Truck51125 | Northern Mat & Bridge714521622Crew Truck51125ESI10770 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1125 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7146 | 21623 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 5 | Day |  | 0 |  |  | 1125 | 146.25 | 1271.25 | 2021-07-13 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44391 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714621623Crew Truck51125 | Northern Mat & Bridge714621623Crew Truck51125ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1125 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7147 | 21624 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 5 | Day |  | 0 |  |  | 1125 | 146.25 | 1271.25 | 2021-07-14 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled to site, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instructiions, crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slowly with over a 25km round trip. Released on site haulers. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44392 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714721624Crew Truck51125 | Northern Mat & Bridge714721624Crew Truck51125ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1125 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7148 | 21625 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 5 | Day |  | 0 |  |  | 1125 | 146.25 | 1271.25 | 2021-07-15 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load shuttles, shuttlemats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44393 |  | 36 | 44394 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714821625Crew Truck51125 | Northern Mat & Bridge714821625Crew Truck51125ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1125 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7149 | 21626 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 5 | Day |  | 0 |  |  | 1125 | 146.25 | 1271.25 | 2021-07-16 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44394 |  | 36 | 44395 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714921626Crew Truck51125 | Northern Mat & Bridge714921626Crew Truck51125ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1125 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7150 | 21627 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 4 | Day |  | 0 |  |  | 900 | 117 | 1017 | 2021-07-17 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instructions. Crew tavelled out. ## covid 19 policies in effect ## Jason got Shane set up laying mats at valard camp in WaWa then Travel to marathon to scout next jobsite with Mike Lecocq, Then returned to crews | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44395 |  | 36 | 44396 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715021627Crew Truck4900 | Northern Mat & Bridge715021627Crew Truck4900ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 900 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7151 | 21629 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 4 | Day |  | 0 |  |  | 900 | 117 | 1017 | 2021-07-18 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per valard instructions. Crew travelled out. ## covid 19 policies in effect ## very rough terrian, very hot and dusty, taking a long time to get mats in. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44396 |  | 36 | 44397 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715121629Crew Truck4900 | Northern Mat & Bridge715121629Crew Truck4900ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 900 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7152 | 21631 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 4 | Day |  | 0 |  |  | 900 | 117 | 1017 | 2021-07-19 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting. Load shuttles, shuttle mats, lay mats as per Valard instructions. Crew travelled out. ## Covid 19 policies in effect ## very hot, dusty and rugged terrian, taking a long time to shuttle mats to excavator. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44397 |  | 36 | 44398 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715221631Crew Truck4900 | Northern Mat & Bridge715221631Crew Truck4900ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 900 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7153 | 21633 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 3 | Day |  | 0 |  |  | 675 | 87.75 | 762.75 | 2021-07-20 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, Safety, load shuttles, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## COVID 19 policies in effect ## very hot, dusty and rough terrian taking a long time to shuttle mats. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44398 |  | 36 | 44399 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715321633Crew Truck3675 | Northern Mat & Bridge715321633Crew Truck3675ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 675 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7168 | 31593 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 5 | Day |  | 0 |  |  | 1125 | 146.25 | 1271.25 | 2021-06-28 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | NO description on LEM however it appears that it is all travel time to mobilize in to the job. Sent email to NMB requesting more detail | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44385 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge716831593Crew Truck51125 | Northern Mat & Bridge716831593Crew Truck51125ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1125 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7169 | 31585 R1 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 5 | Day |  | 0 |  |  | 1125 | 146.25 | 1271.25 | 2021-06-29 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel and standby time for Jason and Cutler. Travel to Thunder Bay, wait on and receive Covid tests. Myself, Aaron and Dylan worked on site. Essentially I was wrangling Kawartha trucks about 5KM’s from site. Aaron Jones was unloading trucks at the laydown pad. Dylan escorted Andre into KM17 with the excavator and then assisted Aaron with unloading trucks and getting them turned around to head out ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge716931585 R1Crew Truck51125 | Northern Mat & Bridge716931585 R1Crew Truck51125ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1125 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7127 | 21608 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 6 | Day |  | 0 |  |  | 1350 | 175.5 | 1525.5 | 2021-07-04 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks. Haul mats on site, shuttle and lay mats as per Valard instuction. Crew travelled out. ## covid 19 policies in effect ## Cory Trembeltt travel time 18 hrs total for mob in and drive to TB for COVID test and drive to site Wawa. | 10 | F065-F118 | Paint Lake Road 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712721608Crew Truck61350 | Northern Mat & Bridge712721608Crew Truck61350ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1350 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7141 | 21617 | 53531001 | Rig/Access Mats | 0 | Crew Truck | 225 | 5 | Day |  | 0 |  |  | 1125 | 146.25 | 1271.25 | 2021-07-08 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew Travelled to site, Safety meeting, load unload trucks, shuttle mats, lays mats as per Valard instruction. Crew travelled out. ## Covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714121617Crew Truck51125 | Northern Mat & Bridge714121617Crew Truck51125ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1125 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7124 | 21603 | 53531001 | Rig/Access Mats | 0 | Excavator | 127.81 | 8 | Hr |  | 0 |  |  | 1022.48 | 132.9224 | 1155.4024 | 2021-07-01 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Should have stat holiday rates, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | Jason, Cutler travel to site. Safety meeting with Valard. Load G&G flatbeds from laydown to km 17 Henson Rd. Rest of crew awaiting covid test results and travelling from Thunder Bay. Crew arrived, started shuttling mats to ROW. Crew travelled out. ## Covid 19 protocols in place ## | 10 | F109 | Hensen Road | 0 | 44383 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712421603Excavator81022.48 | Northern Mat & Bridge712421603Excavator81022.48ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1022.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7125 | 21604 | 53531001 | Rig/Access Mats | 0 | Excavator | 127.81 | 8 | Hr |  | 0 |  |  | 1022.48 | 132.9224 | 1155.4024 | 2021-07-02 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Entered with regular rates however LEM had stat holiday rates, sent back for revision, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks at km1 laydown. Haulmats from laydown to km 17 Henson rd. shuttle mats from km 17 to Row. Lay mats as per valard intruction. Crew travelled out. ## COVID-19 protocols in effect ## | 10 | F109 | Hensen Road | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712521604Excavator81022.48 | Northern Mat & Bridge712521604Excavator81022.48ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1022.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7126 | 21607 | 53531001 | Rig/Access Mats | 0 | Excavator | 127.81 | 9 | Hr |  | 0 |  |  | 1150.29 | 149.5377 | 1299.8277 | 2021-07-03 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travel to site. Safety meeting. Load, unload trucks. Haul mats onsite from laydown to KM17. shuttle and lay mats as per Valard instruction. ## COVID 19 protocol in effect ## | 10 | F065-F118 | Paint Lake 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712621607Excavator91150.29 | Northern Mat & Bridge712621607Excavator91150.29ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1150.29 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7127 | 21608 | 53531001 | Rig/Access Mats | 0 | Excavator | 127.81 | 8 | Hr |  | 0 |  |  | 1022.48 | 132.9224 | 1155.4024 | 2021-07-04 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks. Haul mats on site, shuttle and lay mats as per Valard instuction. Crew travelled out. ## covid 19 policies in effect ## Cory Trembeltt travel time 18 hrs total for mob in and drive to TB for COVID test and drive to site Wawa. | 10 | F065-F118 | Paint Lake Road 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712721608Excavator81022.48 | Northern Mat & Bridge712721608Excavator81022.48ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1022.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7128 | 20611 | 53531001 | Rig/Access Mats | 0 | Excavator | 127.81 | 8 | Hr |  | 0 |  |  | 1022.48 | 132.9224 | 1155.4024 | 2021-07-05 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | Crew travelled in. safety meeting. Load unload trucks, shuttle mats, lay mats as per Valard instructions. Corey Trembett finished covid test in Thunder Bay and travelled to site to run 2nd shuttle ## COVID 19 policies in effect ## | 10 | F065-F118 | Paint lake Road 2 | 0 | 44384 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712820611Excavator81022.48 | Northern Mat & Bridge712820611Excavator81022.48ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1022.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7129 | 21613 | 53531001 | Rig/Access Mats | 0 | Excavator | 127.81 | 8 | Hr |  | 0 |  |  | 1022.48 | 132.9224 | 1155.4024 | 2021-07-06 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew traveled to location, safety meeting, Load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew traveled out. ## COVID-19 policies in effect ## Dylan Thompson travelling to Thunder Bay for Valard COVID test. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712921613Excavator81022.48 | Northern Mat & Bridge712921613Excavator81022.48ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1022.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7130 | 21615 | 53531001 | Rig/Access Mats | 0 | Excavator | 127.81 | 8 | Hr |  | 0 |  |  | 1022.48 | 132.9224 | 1155.4024 | 2021-07-07 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew travelled in, safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Shuttle one load of mats with roll off, determined high potential for a spill, use roll off to move mats to Paint lake road as per Valard, moved 28 mats to Paint Lake road. Dylan Thompson enroute to Thunder Bay for Valard covid test. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa fore work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge713021615Excavator81022.48 | Northern Mat & Bridge713021615Excavator81022.48ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1022.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7141 | 21617 | 53531001 | Rig/Access Mats | 0 | Excavator | 127.81 | 8 | Hr |  | 0 |  |  | 1022.48 | 132.9224 | 1155.4024 | 2021-07-08 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew Travelled to site, Safety meeting, load unload trucks, shuttle mats, lays mats as per Valard instruction. Crew travelled out. ## Covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714121617Excavator81022.48 | Northern Mat & Bridge714121617Excavator81022.48ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1022.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7142 | 21619 | 53531001 | Rig/Access Mats | 0 | Excavator | 127.81 | 8 | Hr |  | 0 |  |  | 1022.48 | 132.9224 | 1155.4024 | 2021-07-09 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in. safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Deliver another load of 10 mats to km 7-8 on paint lake with roll-off for road repair. Total of 32 mats at km 7-8 on Paint Lake Rd. crew travelled out. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa for work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44387 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714221619Excavator81022.48 | Northern Mat & Bridge714221619Excavator81022.48ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1022.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Excavator | 127.81 | 8 | Hr |  | 0 |  |  | 1022.48 | 132.9224 | 1155.4024 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Excavator81022.48 | Northern Mat & Bridge714321620Excavator81022.48ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1022.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7144 | 21621 | 53531001 | Rig/Access Mats | 0 | Excavator | 127.81 | 8 | Hr |  | 0 |  |  | 1022.48 | 132.9224 | 1155.4024 | 2021-07-11 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | crew travelled in, safety meeting,load unload trucks, shuttle mats, lay mats as per Valard instructions. ## covid 19 policies in effect ## crew travelled out | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44389 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714421621Excavator81022.48 | Northern Mat & Bridge714421621Excavator81022.48ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1022.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7145 | 21622 | 53531001 | Rig/Access Mats | 0 | Excavator | 127.81 | 8 | Hr |  | 0 |  |  | 1022.48 | 132.9224 | 1155.4024 | 2021-07-12 | 0 | ESI10770 | 44452 | 68 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44390 |  | 14 | 44449 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714521622Excavator81022.48 | Northern Mat & Bridge714521622Excavator81022.48ESI10770 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1022.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7146 | 21623 | 53531001 | Rig/Access Mats | 0 | Excavator | 127.81 | 8 | Hr |  | 0 |  |  | 1022.48 | 132.9224 | 1155.4024 | 2021-07-13 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44391 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714621623Excavator81022.48 | Northern Mat & Bridge714621623Excavator81022.48ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1022.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7147 | 21624 | 53531001 | Rig/Access Mats | 0 | Excavator | 127.81 | 8 | Hr |  | 0 |  |  | 1022.48 | 132.9224 | 1155.4024 | 2021-07-14 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled to site, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instructiions, crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slowly with over a 25km round trip. Released on site haulers. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44392 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714721624Excavator81022.48 | Northern Mat & Bridge714721624Excavator81022.48ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1022.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7148 | 21625 | 53531001 | Rig/Access Mats | 0 | Excavator | 127.81 | 8 | Hr |  | 0 |  |  | 1022.48 | 132.9224 | 1155.4024 | 2021-07-15 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load shuttles, shuttlemats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44393 |  | 36 | 44394 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714821625Excavator81022.48 | Northern Mat & Bridge714821625Excavator81022.48ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1022.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7149 | 21626 | 53531001 | Rig/Access Mats | 0 | Excavator | 127.81 | 8 | Hr |  | 0 |  |  | 1022.48 | 132.9224 | 1155.4024 | 2021-07-16 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44394 |  | 36 | 44395 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714921626Excavator81022.48 | Northern Mat & Bridge714921626Excavator81022.48ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1022.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7150 | 21627 | 53531001 | Rig/Access Mats | 0 | Excavator | 127.81 | 8 | Hr |  | 0 |  |  | 1022.48 | 132.9224 | 1155.4024 | 2021-07-17 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instructions. Crew tavelled out. ## covid 19 policies in effect ## Jason got Shane set up laying mats at valard camp in WaWa then Travel to marathon to scout next jobsite with Mike Lecocq, Then returned to crews | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44395 |  | 36 | 44396 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715021627Excavator81022.48 | Northern Mat & Bridge715021627Excavator81022.48ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1022.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7151 | 21629 | 53531001 | Rig/Access Mats | 0 | Excavator | 127.81 | 8 | Hr |  | 0 |  |  | 1022.48 | 132.9224 | 1155.4024 | 2021-07-18 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per valard instructions. Crew travelled out. ## covid 19 policies in effect ## very rough terrian, very hot and dusty, taking a long time to get mats in. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44396 |  | 36 | 44397 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715121629Excavator81022.48 | Northern Mat & Bridge715121629Excavator81022.48ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1022.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7152 | 21631 | 53531001 | Rig/Access Mats | 0 | Excavator | 127.81 | 8 | Hr |  | 0 |  |  | 1022.48 | 132.9224 | 1155.4024 | 2021-07-19 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting. Load shuttles, shuttle mats, lay mats as per Valard instructions. Crew travelled out. ## Covid 19 policies in effect ## very hot, dusty and rugged terrian, taking a long time to shuttle mats to excavator. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44397 |  | 36 | 44398 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715221631Excavator81022.48 | Northern Mat & Bridge715221631Excavator81022.48ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1022.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7153 | 21633 | 53531001 | Rig/Access Mats | 0 | Excavator | 127.81 | 8 | Hr |  | 0 |  |  | 1022.48 | 132.9224 | 1155.4024 | 2021-07-20 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, Safety, load shuttles, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## COVID 19 policies in effect ## very hot, dusty and rough terrian taking a long time to shuttle mats. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44398 |  | 36 | 44399 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715321633Excavator81022.48 | Northern Mat & Bridge715321633Excavator81022.48ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1022.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7123 | 31587 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 4 | Hr |  | 0 |  |  | 395.32 | 51.3916 | 446.7116 | 2021-06-30 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel In. Travel to jobsite. Complete site walkthrough, toolbox talk and safety talk with Valard. Unload and rack 261 Mats. Ensure mat safety. Travel out. ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44382 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712331587Loader4395.32 | Northern Mat & Bridge712331587Loader4395.32ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 395.32 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7123 | 31587 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 3 | Hr |  | 0 |  |  | 296.49 | 38.5437 | 335.0337 | 2021-06-30 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel In. Travel to jobsite. Complete site walkthrough, toolbox talk and safety talk with Valard. Unload and rack 261 Mats. Ensure mat safety. Travel out. ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44382 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712331587Loader3296.49 | Northern Mat & Bridge712331587Loader3296.49ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 296.49 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7124 | 21603 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 6 | Hr |  | 0 |  |  | 592.98 | 77.0874 | 670.0674 | 2021-07-01 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Should have stat holiday rates, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | Jason, Cutler travel to site. Safety meeting with Valard. Load G&G flatbeds from laydown to km 17 Henson Rd. Rest of crew awaiting covid test results and travelling from Thunder Bay. Crew arrived, started shuttling mats to ROW. Crew travelled out. ## Covid 19 protocols in place ## | 10 | F109 | Hensen Road | 0 | 44383 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712421603Loader6592.98 | Northern Mat & Bridge712421603Loader6592.98ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 592.98 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7124 | 21603 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 4 | Hr |  | 0 |  |  | 395.32 | 51.3916 | 446.7116 | 2021-07-01 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Should have stat holiday rates, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | Jason, Cutler travel to site. Safety meeting with Valard. Load G&G flatbeds from laydown to km 17 Henson Rd. Rest of crew awaiting covid test results and travelling from Thunder Bay. Crew arrived, started shuttling mats to ROW. Crew travelled out. ## Covid 19 protocols in place ## | 10 | F109 | Hensen Road | 0 | 44383 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712421603Loader4395.32 | Northern Mat & Bridge712421603Loader4395.32ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 395.32 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7125 | 21604 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 20.5 | Hr |  | 0 |  |  | 2026.015 | 263.382 | 2289.3969 | 2021-07-02 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Entered with regular rates however LEM had stat holiday rates, sent back for revision, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks at km1 laydown. Haulmats from laydown to km 17 Henson rd. shuttle mats from km 17 to Row. Lay mats as per valard intruction. Crew travelled out. ## COVID-19 protocols in effect ## | 10 | F109 | Hensen Road | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712521604Loader20.52026.015 | Northern Mat & Bridge712521604Loader20.52026.015ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2026.015 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7126 | 21607 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 9 | Hr |  | 0 |  |  | 889.47 | 115.6311 | 1005.1011 | 2021-07-03 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travel to site. Safety meeting. Load, unload trucks. Haul mats onsite from laydown to KM17. shuttle and lay mats as per Valard instruction. ## COVID 19 protocol in effect ## | 10 | F065-F118 | Paint Lake 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712621607Loader9889.47 | Northern Mat & Bridge712621607Loader9889.47ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 889.47 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7126 | 21607 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 10 | Hr |  | 0 |  |  | 988.3 | 128.479 | 1116.779 | 2021-07-03 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travel to site. Safety meeting. Load, unload trucks. Haul mats onsite from laydown to KM17. shuttle and lay mats as per Valard instruction. ## COVID 19 protocol in effect ## | 10 | F065-F118 | Paint Lake 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712621607Loader10988.3 | Northern Mat & Bridge712621607Loader10988.3ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 988.3 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7127 | 21608 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 10 | Hr |  | 0 |  |  | 988.3 | 128.479 | 1116.779 | 2021-07-04 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks. Haul mats on site, shuttle and lay mats as per Valard instuction. Crew travelled out. ## covid 19 policies in effect ## Cory Trembeltt travel time 18 hrs total for mob in and drive to TB for COVID test and drive to site Wawa. | 10 | F065-F118 | Paint Lake Road 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712721608Loader10988.3 | Northern Mat & Bridge712721608Loader10988.3ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 988.3 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7127 | 21608 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 10.5 | Hr |  | 0 |  |  | 1037.715 | 134.903 | 1172.618 | 2021-07-04 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks. Haul mats on site, shuttle and lay mats as per Valard instuction. Crew travelled out. ## covid 19 policies in effect ## Cory Trembeltt travel time 18 hrs total for mob in and drive to TB for COVID test and drive to site Wawa. | 10 | F065-F118 | Paint Lake Road 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712721608Loader10.51037.715 | Northern Mat & Bridge712721608Loader10.51037.715ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1037.715 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7128 | 20611 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 10 | Hr |  | 0 |  |  | 988.3 | 128.479 | 1116.779 | 2021-07-05 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | Crew travelled in. safety meeting. Load unload trucks, shuttle mats, lay mats as per Valard instructions. Corey Trembett finished covid test in Thunder Bay and travelled to site to run 2nd shuttle ## COVID 19 policies in effect ## | 10 | F065-F118 | Paint lake Road 2 | 0 | 44384 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712820611Loader10988.3 | Northern Mat & Bridge712820611Loader10988.3ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 988.3 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7128 | 20611 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 11 | Hr |  | 0 |  |  | 1087.13 | 141.3269 | 1228.4569 | 2021-07-05 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | Crew travelled in. safety meeting. Load unload trucks, shuttle mats, lay mats as per Valard instructions. Corey Trembett finished covid test in Thunder Bay and travelled to site to run 2nd shuttle ## COVID 19 policies in effect ## | 10 | F065-F118 | Paint lake Road 2 | 0 | 44384 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712820611Loader111087.13 | Northern Mat & Bridge712820611Loader111087.13ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1087.13 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7129 | 21613 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 11 | Hr |  | 0 |  |  | 1087.13 | 141.3269 | 1228.4569 | 2021-07-06 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew traveled to location, safety meeting, Load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew traveled out. ## COVID-19 policies in effect ## Dylan Thompson travelling to Thunder Bay for Valard COVID test. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712921613Loader111087.13 | Northern Mat & Bridge712921613Loader111087.13ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1087.13 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7129 | 21613 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 10.5 | Hr |  | 0 |  |  | 1037.715 | 134.903 | 1172.618 | 2021-07-06 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew traveled to location, safety meeting, Load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew traveled out. ## COVID-19 policies in effect ## Dylan Thompson travelling to Thunder Bay for Valard COVID test. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712921613Loader10.51037.715 | Northern Mat & Bridge712921613Loader10.51037.715ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1037.715 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7130 | 21615 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 10.5 | Hr |  | 0 |  |  | 1037.715 | 134.903 | 1172.618 | 2021-07-07 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew travelled in, safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Shuttle one load of mats with roll off, determined high potential for a spill, use roll off to move mats to Paint lake road as per Valard, moved 28 mats to Paint Lake road. Dylan Thompson enroute to Thunder Bay for Valard covid test. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa fore work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge713021615Loader10.51037.715 | Northern Mat & Bridge713021615Loader10.51037.715ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1037.715 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7130 | 21615 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 10.5 | Hr |  | 0 |  |  | 1037.715 | 134.903 | 1172.618 | 2021-07-07 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew travelled in, safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Shuttle one load of mats with roll off, determined high potential for a spill, use roll off to move mats to Paint lake road as per Valard, moved 28 mats to Paint Lake road. Dylan Thompson enroute to Thunder Bay for Valard covid test. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa fore work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge713021615Loader10.51037.715 | Northern Mat & Bridge713021615Loader10.51037.715ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1037.715 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7141 | 21617 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 10 | Hr |  | 0 |  |  | 988.3 | 128.479 | 1116.779 | 2021-07-08 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew Travelled to site, Safety meeting, load unload trucks, shuttle mats, lays mats as per Valard instruction. Crew travelled out. ## Covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714121617Loader10988.3 | Northern Mat & Bridge714121617Loader10988.3ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 988.3 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7141 | 21617 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 11 | Hr |  | 0 |  |  | 1087.13 | 141.3269 | 1228.4569 | 2021-07-08 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew Travelled to site, Safety meeting, load unload trucks, shuttle mats, lays mats as per Valard instruction. Crew travelled out. ## Covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714121617Loader111087.13 | Northern Mat & Bridge714121617Loader111087.13ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1087.13 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7142 | 21619 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 12 | Hr |  | 0 |  |  | 1185.96 | 154.1748 | 1340.1348 | 2021-07-09 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in. safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Deliver another load of 10 mats to km 7-8 on paint lake with roll-off for road repair. Total of 32 mats at km 7-8 on Paint Lake Rd. crew travelled out. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa for work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44387 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714221619Loader121185.96 | Northern Mat & Bridge714221619Loader121185.96ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.96 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7142 | 21619 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 10 | Hr |  | 0 |  |  | 988.3 | 128.479 | 1116.779 | 2021-07-09 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in. safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Deliver another load of 10 mats to km 7-8 on paint lake with roll-off for road repair. Total of 32 mats at km 7-8 on Paint Lake Rd. crew travelled out. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa for work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44387 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714221619Loader10988.3 | Northern Mat & Bridge714221619Loader10988.3ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 988.3 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 11 | Hr |  | 0 |  |  | 1087.13 | 141.3269 | 1228.4569 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Loader111087.13 | Northern Mat & Bridge714321620Loader111087.13ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1087.13 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 10.5 | Hr |  | 0 |  |  | 1037.715 | 134.903 | 1172.618 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Loader10.51037.715 | Northern Mat & Bridge714321620Loader10.51037.715ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1037.715 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7144 | 21621 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 11 | Hr |  | 0 |  |  | 1087.13 | 141.3269 | 1228.4569 | 2021-07-11 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | crew travelled in, safety meeting,load unload trucks, shuttle mats, lay mats as per Valard instructions. ## covid 19 policies in effect ## crew travelled out | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44389 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714421621Loader111087.13 | Northern Mat & Bridge714421621Loader111087.13ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1087.13 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7144 | 21621 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 11 | Hr |  | 0 |  |  | 1087.13 | 141.3269 | 1228.4569 | 2021-07-11 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | crew travelled in, safety meeting,load unload trucks, shuttle mats, lay mats as per Valard instructions. ## covid 19 policies in effect ## crew travelled out | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44389 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714421621Loader111087.13 | Northern Mat & Bridge714421621Loader111087.13ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1087.13 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7145 | 21622 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 22 | Hr |  | 0 |  |  | 2174.26 | 282.6538 | 2456.9138 | 2021-07-12 | 0 | ESI10770 | 44452 | 68 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44390 |  | 14 | 44449 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714521622Loader222174.26 | Northern Mat & Bridge714521622Loader222174.26ESI10770 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2174.26 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7146 | 21623 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 20.5 | Hr |  | 0 |  |  | 2026.015 | 263.382 | 2289.3969 | 2021-07-13 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44391 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714621623Loader20.52026.015 | Northern Mat & Bridge714621623Loader20.52026.015ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2026.015 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7147 | 21624 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 18 | Hr |  | 0 |  |  | 1778.94 | 231.2622 | 2010.2022 | 2021-07-14 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled to site, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instructiions, crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slowly with over a 25km round trip. Released on site haulers. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44392 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714721624Loader181778.94 | Northern Mat & Bridge714721624Loader181778.94ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1778.94 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7148 | 21625 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 9 | Hr |  | 0 |  |  | 889.47 | 115.6311 | 1005.1011 | 2021-07-15 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load shuttles, shuttlemats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44393 |  | 36 | 44394 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714821625Loader9889.47 | Northern Mat & Bridge714821625Loader9889.47ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 889.47 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7149 | 21626 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 11 | Hr |  | 0 |  |  | 1087.13 | 141.3269 | 1228.4569 | 2021-07-16 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44394 |  | 36 | 44395 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714921626Loader111087.13 | Northern Mat & Bridge714921626Loader111087.13ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1087.13 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7150 | 21627 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 11 | Hr |  | 0 |  |  | 1087.13 | 141.3269 | 1228.4569 | 2021-07-17 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instructions. Crew tavelled out. ## covid 19 policies in effect ## Jason got Shane set up laying mats at valard camp in WaWa then Travel to marathon to scout next jobsite with Mike Lecocq, Then returned to crews | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44395 |  | 36 | 44396 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715021627Loader111087.13 | Northern Mat & Bridge715021627Loader111087.13ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1087.13 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7151 | 21629 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 11 | Hr |  | 0 |  |  | 1087.13 | 141.3269 | 1228.4569 | 2021-07-18 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per valard instructions. Crew travelled out. ## covid 19 policies in effect ## very rough terrian, very hot and dusty, taking a long time to get mats in. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44396 |  | 36 | 44397 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715121629Loader111087.13 | Northern Mat & Bridge715121629Loader111087.13ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1087.13 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7152 | 21631 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 11 | Hr |  | 0 |  |  | 1087.13 | 141.3269 | 1228.4569 | 2021-07-19 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting. Load shuttles, shuttle mats, lay mats as per Valard instructions. Crew travelled out. ## Covid 19 policies in effect ## very hot, dusty and rugged terrian, taking a long time to shuttle mats to excavator. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44397 |  | 36 | 44398 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715221631Loader111087.13 | Northern Mat & Bridge715221631Loader111087.13ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1087.13 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7153 | 21633 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 11 | Hr |  | 0 |  |  | 1087.13 | 141.3269 | 1228.4569 | 2021-07-20 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, Safety, load shuttles, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## COVID 19 policies in effect ## very hot, dusty and rough terrian taking a long time to shuttle mats. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44398 |  | 36 | 44399 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715321633Loader111087.13 | Northern Mat & Bridge715321633Loader111087.13ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1087.13 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7169 | 31585 R1 | 53531001 | Rig/Access Mats | 0 | Loader | 98.83 | 8.5 | Hr |  | 0 |  |  | 840.055 | 109.2071 | 949.2622 | 2021-06-29 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel and standby time for Jason and Cutler. Travel to Thunder Bay, wait on and receive Covid tests. Myself, Aaron and Dylan worked on site. Essentially I was wrangling Kawartha trucks about 5KM’s from site. Aaron Jones was unloading trucks at the laydown pad. Dylan escorted Andre into KM17 with the excavator and then assisted Aaron with unloading trucks and getting them turned around to head out ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge716931585 R1Loader8.5840.055 | Northern Mat & Bridge716931585 R1Loader8.5840.055ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 840.055 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7124 | 21603 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 3 | Hr |  | 0 |  |  | 517.68 | 67.2984 | 584.9784 | 2021-07-01 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Should have stat holiday rates, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | Jason, Cutler travel to site. Safety meeting with Valard. Load G&G flatbeds from laydown to km 17 Henson Rd. Rest of crew awaiting covid test results and travelling from Thunder Bay. Crew arrived, started shuttling mats to ROW. Crew travelled out. ## Covid 19 protocols in place ## | 10 | F109 | Hensen Road | 0 | 44383 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712421603Track Carrier3517.68 | Northern Mat & Bridge712421603Track Carrier3517.68ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 517.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7125 | 21604 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 9 | Hr |  | 0 |  |  | 1553.04 | 201.8952 | 1754.9352 | 2021-07-02 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Entered with regular rates however LEM had stat holiday rates, sent back for revision, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks at km1 laydown. Haulmats from laydown to km 17 Henson rd. shuttle mats from km 17 to Row. Lay mats as per valard intruction. Crew travelled out. ## COVID-19 protocols in effect ## | 10 | F109 | Hensen Road | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712521604Track Carrier91553.04 | Northern Mat & Bridge712521604Track Carrier91553.04ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1553.04 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7126 | 21607 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 10 | Hr |  | 0 |  |  | 1725.6 | 224.328 | 1949.928 | 2021-07-03 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travel to site. Safety meeting. Load, unload trucks. Haul mats onsite from laydown to KM17. shuttle and lay mats as per Valard instruction. ## COVID 19 protocol in effect ## | 10 | F065-F118 | Paint Lake 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712621607Track Carrier101725.6 | Northern Mat & Bridge712621607Track Carrier101725.6ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1725.6 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7127 | 21608 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 10 | Hr |  | 0 |  |  | 1725.6 | 224.328 | 1949.928 | 2021-07-04 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks. Haul mats on site, shuttle and lay mats as per Valard instuction. Crew travelled out. ## covid 19 policies in effect ## Cory Trembeltt travel time 18 hrs total for mob in and drive to TB for COVID test and drive to site Wawa. | 10 | F065-F118 | Paint Lake Road 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712721608Track Carrier101725.6 | Northern Mat & Bridge712721608Track Carrier101725.6ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1725.6 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7128 | 20611 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 10 | Hr |  | 0 |  |  | 1725.6 | 224.328 | 1949.928 | 2021-07-05 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | Crew travelled in. safety meeting. Load unload trucks, shuttle mats, lay mats as per Valard instructions. Corey Trembett finished covid test in Thunder Bay and travelled to site to run 2nd shuttle ## COVID 19 policies in effect ## | 10 | F065-F118 | Paint lake Road 2 | 0 | 44384 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712820611Track Carrier101725.6 | Northern Mat & Bridge712820611Track Carrier101725.6ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1725.6 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7129 | 21613 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 10 | Hr |  | 0 |  |  | 1725.6 | 224.328 | 1949.928 | 2021-07-06 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew traveled to location, safety meeting, Load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew traveled out. ## COVID-19 policies in effect ## Dylan Thompson travelling to Thunder Bay for Valard COVID test. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712921613Track Carrier101725.6 | Northern Mat & Bridge712921613Track Carrier101725.6ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1725.6 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7130 | 21615 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 10 | Hr |  | 0 |  |  | 1725.6 | 224.328 | 1949.928 | 2021-07-07 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew travelled in, safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Shuttle one load of mats with roll off, determined high potential for a spill, use roll off to move mats to Paint lake road as per Valard, moved 28 mats to Paint Lake road. Dylan Thompson enroute to Thunder Bay for Valard covid test. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa fore work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge713021615Track Carrier101725.6 | Northern Mat & Bridge713021615Track Carrier101725.6ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1725.6 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7141 | 21617 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 10 | Hr |  | 0 |  |  | 1725.6 | 224.328 | 1949.928 | 2021-07-08 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew Travelled to site, Safety meeting, load unload trucks, shuttle mats, lays mats as per Valard instruction. Crew travelled out. ## Covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714121617Track Carrier101725.6 | Northern Mat & Bridge714121617Track Carrier101725.6ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1725.6 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7141 | 21617 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 10 | Hr |  | 0 |  |  | 1725.6 | 224.328 | 1949.928 | 2021-07-08 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew Travelled to site, Safety meeting, load unload trucks, shuttle mats, lays mats as per Valard instruction. Crew travelled out. ## Covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714121617Track Carrier101725.6 | Northern Mat & Bridge714121617Track Carrier101725.6ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1725.6 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7142 | 21619 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 10 | Hr |  | 0 |  |  | 1725.6 | 224.328 | 1949.928 | 2021-07-09 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in. safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Deliver another load of 10 mats to km 7-8 on paint lake with roll-off for road repair. Total of 32 mats at km 7-8 on Paint Lake Rd. crew travelled out. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa for work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44387 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714221619Track Carrier101725.6 | Northern Mat & Bridge714221619Track Carrier101725.6ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1725.6 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7142 | 21619 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 11.5 | Hr |  | 0 |  |  | 1984.44 | 257.9772 | 2242.4172 | 2021-07-09 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in. safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Deliver another load of 10 mats to km 7-8 on paint lake with roll-off for road repair. Total of 32 mats at km 7-8 on Paint Lake Rd. crew travelled out. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa for work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44387 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714221619Track Carrier11.51984.44 | Northern Mat & Bridge714221619Track Carrier11.51984.44ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1984.44 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 10 | Hr |  | 0 |  |  | 1725.6 | 224.328 | 1949.928 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Track Carrier101725.6 | Northern Mat & Bridge714321620Track Carrier101725.6ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1725.6 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 11 | Hr |  | 0 |  |  | 1898.16 | 246.7608 | 2144.9208 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Track Carrier111898.16 | Northern Mat & Bridge714321620Track Carrier111898.16ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1898.16 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 8 | Hr |  | 0 |  |  | 1380.48 | 179.4624 | 1559.9424 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Track Carrier81380.48 | Northern Mat & Bridge714321620Track Carrier81380.48ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1380.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7144 | 21621 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 30.5 | Hr |  | 0 |  |  | 5263.08 | 684.2004 | 5947.2804 | 2021-07-11 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | crew travelled in, safety meeting,load unload trucks, shuttle mats, lay mats as per Valard instructions. ## covid 19 policies in effect ## crew travelled out | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44389 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714421621Track Carrier30.55263.08 | Northern Mat & Bridge714421621Track Carrier30.55263.08ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 5263.08 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7145 | 21622 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 30.5 | Hr |  | 0 |  |  | 5263.08 | 684.2004 | 5947.2804 | 2021-07-12 | 0 | ESI10770 | 44452 | 68 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44390 |  | 14 | 44449 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714521622Track Carrier30.55263.08 | Northern Mat & Bridge714521622Track Carrier30.55263.08ESI10770 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 5263.08 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7146 | 21623 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 28.5 | Hr |  | 0 |  |  | 4917.96 | 639.3348 | 5557.2948 | 2021-07-13 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44391 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714621623Track Carrier28.54917.96 | Northern Mat & Bridge714621623Track Carrier28.54917.96ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 4917.96 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7147 | 21624 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 31 | Hr |  | 0 |  |  | 5349.36 | 695.4168 | 6044.7768 | 2021-07-14 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled to site, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instructiions, crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slowly with over a 25km round trip. Released on site haulers. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44392 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714721624Track Carrier315349.36 | Northern Mat & Bridge714721624Track Carrier315349.36ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 5349.36 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7148 | 21625 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 27 | Hr |  | 0 |  |  | 4659.12 | 605.6856 | 5264.8056 | 2021-07-15 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load shuttles, shuttlemats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44393 |  | 36 | 44394 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714821625Track Carrier274659.12 | Northern Mat & Bridge714821625Track Carrier274659.12ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 4659.12 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7149 | 21626 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 30 | Hr |  | 0 |  |  | 5176.8 | 672.984 | 5849.784 | 2021-07-16 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44394 |  | 36 | 44395 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714921626Track Carrier305176.8 | Northern Mat & Bridge714921626Track Carrier305176.8ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 5176.8 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7150 | 21627 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 30 | Hr |  | 0 |  |  | 5176.8 | 672.984 | 5849.784 | 2021-07-17 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instructions. Crew tavelled out. ## covid 19 policies in effect ## Jason got Shane set up laying mats at valard camp in WaWa then Travel to marathon to scout next jobsite with Mike Lecocq, Then returned to crews | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44395 |  | 36 | 44396 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715021627Track Carrier305176.8 | Northern Mat & Bridge715021627Track Carrier305176.8ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 5176.8 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7151 | 21629 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 31.5 | Hr |  | 0 |  |  | 5435.64 | 706.6332 | 6142.2732 | 2021-07-18 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per valard instructions. Crew travelled out. ## covid 19 policies in effect ## very rough terrian, very hot and dusty, taking a long time to get mats in. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44396 |  | 36 | 44397 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715121629Track Carrier31.55435.64 | Northern Mat & Bridge715121629Track Carrier31.55435.64ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 5435.64 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7152 | 21631 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 30 | Hr |  | 0 |  |  | 5176.8 | 672.984 | 5849.784 | 2021-07-19 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting. Load shuttles, shuttle mats, lay mats as per Valard instructions. Crew travelled out. ## Covid 19 policies in effect ## very hot, dusty and rugged terrian, taking a long time to shuttle mats to excavator. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44397 |  | 36 | 44398 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715221631Track Carrier305176.8 | Northern Mat & Bridge715221631Track Carrier305176.8ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 5176.8 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7153 | 21633 | 53531001 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 30 | Hr |  | 0 |  |  | 5176.8 | 672.984 | 5849.784 | 2021-07-20 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, Safety, load shuttles, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## COVID 19 policies in effect ## very hot, dusty and rough terrian taking a long time to shuttle mats. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44398 |  | 36 | 44399 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715321633Track Carrier305176.8 | Northern Mat & Bridge715321633Track Carrier305176.8ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 5176.8 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7130 | 21615 | 53531001 | Rig/Access Mats | 0 | Float Truck | 199.14 | 11.5 | Hr |  | 0 |  |  | 2290.11 | 297.7143 | 2587.8243 | 2021-07-07 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew travelled in, safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Shuttle one load of mats with roll off, determined high potential for a spill, use roll off to move mats to Paint lake road as per Valard, moved 28 mats to Paint Lake road. Dylan Thompson enroute to Thunder Bay for Valard covid test. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa fore work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge713021615Float Truck11.52290.11 | Northern Mat & Bridge713021615Float Truck11.52290.11ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2290.11 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7169 | 31585 R1 | 53531001 | Rig/Access Mats | 0 | Float Truck | 199.14 | 19.8855 | Hr |  | 0 |  |  | 3959.9999 | 514.8 | 4474.7999 | 2021-06-29 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel and standby time for Jason and Cutler. Travel to Thunder Bay, wait on and receive Covid tests. Myself, Aaron and Dylan worked on site. Essentially I was wrangling Kawartha trucks about 5KM’s from site. Aaron Jones was unloading trucks at the laydown pad. Dylan escorted Andre into KM17 with the excavator and then assisted Aaron with unloading trucks and getting them turned around to head out ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge716931585 R1Float Truck19.8855073959.9999 | Northern Mat & Bridge716931585 R1Float Truck19.8855073959.9999ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 3959.9999 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7169 | 31585 R1 | 53531001 | Rig/Access Mats | 0 | Float Truck | 199.14 | 20.4379 | Hr |  | 0 |  |  | 4069.9994 | 529.0999 | 4599.0993 | 2021-06-29 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel and standby time for Jason and Cutler. Travel to Thunder Bay, wait on and receive Covid tests. Myself, Aaron and Dylan worked on site. Essentially I was wrangling Kawartha trucks about 5KM’s from site. Aaron Jones was unloading trucks at the laydown pad. Dylan escorted Andre into KM17 with the excavator and then assisted Aaron with unloading trucks and getting them turned around to head out ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge716931585 R1Float Truck20.437884069.9994 | Northern Mat & Bridge716931585 R1Float Truck20.437884069.9994ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 4069.9994 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7169 | 31585 R1 | 53531001 | Rig/Access Mats | 0 | Float Truck | 199.14 | 14.5 | Hr |  | 0 |  |  | 2887.53 | 375.3789 | 3262.9089 | 2021-06-29 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel and standby time for Jason and Cutler. Travel to Thunder Bay, wait on and receive Covid tests. Myself, Aaron and Dylan worked on site. Essentially I was wrangling Kawartha trucks about 5KM’s from site. Aaron Jones was unloading trucks at the laydown pad. Dylan escorted Andre into KM17 with the excavator and then assisted Aaron with unloading trucks and getting them turned around to head out ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge716931585 R1Float Truck14.52887.53 | Northern Mat & Bridge716931585 R1Float Truck14.52887.53ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2887.53 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7169 | 31585 R1 | 53531001 | Rig/Access Mats | 0 | Float Truck | 199.14 | 13.5 | Hr |  | 0 |  |  | 2688.39 | 349.4907 | 3037.8807 | 2021-06-29 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel and standby time for Jason and Cutler. Travel to Thunder Bay, wait on and receive Covid tests. Myself, Aaron and Dylan worked on site. Essentially I was wrangling Kawartha trucks about 5KM’s from site. Aaron Jones was unloading trucks at the laydown pad. Dylan escorted Andre into KM17 with the excavator and then assisted Aaron with unloading trucks and getting them turned around to head out ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge716931585 R1Float Truck13.52688.39 | Northern Mat & Bridge716931585 R1Float Truck13.52688.39ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2688.39 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7169 | 31585 R1 | 53531001 | Rig/Access Mats | 0 | Float Truck | 199.14 | 14.75 | Hr |  | 0 |  |  | 2937.315 | 381.851 | 3319.166 | 2021-06-29 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel and standby time for Jason and Cutler. Travel to Thunder Bay, wait on and receive Covid tests. Myself, Aaron and Dylan worked on site. Essentially I was wrangling Kawartha trucks about 5KM’s from site. Aaron Jones was unloading trucks at the laydown pad. Dylan escorted Andre into KM17 with the excavator and then assisted Aaron with unloading trucks and getting them turned around to head out ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge716931585 R1Float Truck14.752937.315 | Northern Mat & Bridge716931585 R1Float Truck14.752937.315ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2937.315 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7169 | 31585 R1 | 53531001 | Rig/Access Mats | 0 | Float Truck | 199.14 | 11 | Hr |  | 0 |  |  | 2190.54 | 284.7702 | 2475.3102 | 2021-06-29 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel and standby time for Jason and Cutler. Travel to Thunder Bay, wait on and receive Covid tests. Myself, Aaron and Dylan worked on site. Essentially I was wrangling Kawartha trucks about 5KM’s from site. Aaron Jones was unloading trucks at the laydown pad. Dylan escorted Andre into KM17 with the excavator and then assisted Aaron with unloading trucks and getting them turned around to head out ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge716931585 R1Float Truck112190.54 | Northern Mat & Bridge716931585 R1Float Truck112190.54ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2190.54 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Float Truck - Overtime (Excluding Sunday/Stat Holidays) | 229 | 11.1961 | Hr |  | 0 |  |  | 2563.8977 | 333.3067 | 2897.2044 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Float Truck - Overtime (Excluding Sunday/Stat Holidays)11.196062563.8977 | Northern Mat & Bridge714321620Float Truck - Overtime (Excluding Sunday/Stat Holidays)11.196062563.8977ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2563.8977 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Float Truck - Overtime (Excluding Sunday/Stat Holidays) | 229 | 11.4461 | Hr |  | 0 |  |  | 2621.1477 | 340.7492 | 2961.8969 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Float Truck - Overtime (Excluding Sunday/Stat Holidays)11.446062621.1477 | Northern Mat & Bridge714321620Float Truck - Overtime (Excluding Sunday/Stat Holidays)11.446062621.1477ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2621.1477 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7124 | 21603 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 7 | Hr |  | 0 |  |  | 1312.5 | 170.625 | 1483.125 | 2021-07-01 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Should have stat holiday rates, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | Jason, Cutler travel to site. Safety meeting with Valard. Load G&G flatbeds from laydown to km 17 Henson Rd. Rest of crew awaiting covid test results and travelling from Thunder Bay. Crew arrived, started shuttling mats to ROW. Crew travelled out. ## Covid 19 protocols in place ## | 10 | F109 | Hensen Road | 0 | 44383 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712421603Flatbed Truck71312.5 | Northern Mat & Bridge712421603Flatbed Truck71312.5ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1312.5 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7124 | 21603 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 13 | Hr |  | 0 |  |  | 2437.5 | 316.875 | 2754.375 | 2021-07-01 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Should have stat holiday rates, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | Jason, Cutler travel to site. Safety meeting with Valard. Load G&G flatbeds from laydown to km 17 Henson Rd. Rest of crew awaiting covid test results and travelling from Thunder Bay. Crew arrived, started shuttling mats to ROW. Crew travelled out. ## Covid 19 protocols in place ## | 10 | F109 | Hensen Road | 0 | 44383 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712421603Flatbed Truck132437.5 | Northern Mat & Bridge712421603Flatbed Truck132437.5ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2437.5 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7124 | 21603 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 7 | Hr |  | 0 |  |  | 1312.5 | 170.625 | 1483.125 | 2021-07-01 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Should have stat holiday rates, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | Jason, Cutler travel to site. Safety meeting with Valard. Load G&G flatbeds from laydown to km 17 Henson Rd. Rest of crew awaiting covid test results and travelling from Thunder Bay. Crew arrived, started shuttling mats to ROW. Crew travelled out. ## Covid 19 protocols in place ## | 10 | F109 | Hensen Road | 0 | 44383 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712421603Flatbed Truck71312.5 | Northern Mat & Bridge712421603Flatbed Truck71312.5ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1312.5 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7124 | 21603 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 13 | Hr |  | 0 |  |  | 2437.5 | 316.875 | 2754.375 | 2021-07-01 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Should have stat holiday rates, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | Jason, Cutler travel to site. Safety meeting with Valard. Load G&G flatbeds from laydown to km 17 Henson Rd. Rest of crew awaiting covid test results and travelling from Thunder Bay. Crew arrived, started shuttling mats to ROW. Crew travelled out. ## Covid 19 protocols in place ## | 10 | F109 | Hensen Road | 0 | 44383 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712421603Flatbed Truck132437.5 | Northern Mat & Bridge712421603Flatbed Truck132437.5ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2437.5 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7125 | 21604 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 6 | Hr |  | 0 |  |  | 1125 | 146.25 | 1271.25 | 2021-07-02 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Entered with regular rates however LEM had stat holiday rates, sent back for revision, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks at km1 laydown. Haulmats from laydown to km 17 Henson rd. shuttle mats from km 17 to Row. Lay mats as per valard intruction. Crew travelled out. ## COVID-19 protocols in effect ## | 10 | F109 | Hensen Road | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712521604Flatbed Truck61125 | Northern Mat & Bridge712521604Flatbed Truck61125ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1125 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7126 | 21607 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 12 | Hr |  | 0 |  |  | 2250 | 292.5 | 2542.5 | 2021-07-03 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travel to site. Safety meeting. Load, unload trucks. Haul mats onsite from laydown to KM17. shuttle and lay mats as per Valard instruction. ## COVID 19 protocol in effect ## | 10 | F065-F118 | Paint Lake 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712621607Flatbed Truck122250 | Northern Mat & Bridge712621607Flatbed Truck122250ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2250 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7126 | 21607 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 12 | Hr |  | 0 |  |  | 2250 | 292.5 | 2542.5 | 2021-07-03 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travel to site. Safety meeting. Load, unload trucks. Haul mats onsite from laydown to KM17. shuttle and lay mats as per Valard instruction. ## COVID 19 protocol in effect ## | 10 | F065-F118 | Paint Lake 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712621607Flatbed Truck122250 | Northern Mat & Bridge712621607Flatbed Truck122250ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2250 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7126 | 21607 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 3 | Hr |  | 0 |  |  | 562.5 | 73.125 | 635.625 | 2021-07-03 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travel to site. Safety meeting. Load, unload trucks. Haul mats onsite from laydown to KM17. shuttle and lay mats as per Valard instruction. ## COVID 19 protocol in effect ## | 10 | F065-F118 | Paint Lake 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712621607Flatbed Truck3562.5 | Northern Mat & Bridge712621607Flatbed Truck3562.5ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 562.5 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7128 | 20611 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 13.5 | Hr |  | 0 |  |  | 2531.25 | 329.0625 | 2860.3125 | 2021-07-05 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | Crew travelled in. safety meeting. Load unload trucks, shuttle mats, lay mats as per Valard instructions. Corey Trembett finished covid test in Thunder Bay and travelled to site to run 2nd shuttle ## COVID 19 policies in effect ## | 10 | F065-F118 | Paint lake Road 2 | 0 | 44384 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712820611Flatbed Truck13.52531.25 | Northern Mat & Bridge712820611Flatbed Truck13.52531.25ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2531.25 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7128 | 20611 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 13.5 | Hr |  | 0 |  |  | 2531.25 | 329.0625 | 2860.3125 | 2021-07-05 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | Crew travelled in. safety meeting. Load unload trucks, shuttle mats, lay mats as per Valard instructions. Corey Trembett finished covid test in Thunder Bay and travelled to site to run 2nd shuttle ## COVID 19 policies in effect ## | 10 | F065-F118 | Paint lake Road 2 | 0 | 44384 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712820611Flatbed Truck13.52531.25 | Northern Mat & Bridge712820611Flatbed Truck13.52531.25ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2531.25 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7128 | 20611 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 13.5 | Hr |  | 0 |  |  | 2531.25 | 329.0625 | 2860.3125 | 2021-07-05 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | Crew travelled in. safety meeting. Load unload trucks, shuttle mats, lay mats as per Valard instructions. Corey Trembett finished covid test in Thunder Bay and travelled to site to run 2nd shuttle ## COVID 19 policies in effect ## | 10 | F065-F118 | Paint lake Road 2 | 0 | 44384 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712820611Flatbed Truck13.52531.25 | Northern Mat & Bridge712820611Flatbed Truck13.52531.25ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2531.25 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7129 | 21613 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 11 | Hr |  | 0 |  |  | 2062.5 | 268.125 | 2330.625 | 2021-07-06 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew traveled to location, safety meeting, Load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew traveled out. ## COVID-19 policies in effect ## Dylan Thompson travelling to Thunder Bay for Valard COVID test. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712921613Flatbed Truck112062.5 | Northern Mat & Bridge712921613Flatbed Truck112062.5ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2062.5 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7129 | 21613 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 5.5 | Hr |  | 0 |  |  | 1031.25 | 134.0625 | 1165.3125 | 2021-07-06 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew traveled to location, safety meeting, Load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew traveled out. ## COVID-19 policies in effect ## Dylan Thompson travelling to Thunder Bay for Valard COVID test. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712921613Flatbed Truck5.51031.25 | Northern Mat & Bridge712921613Flatbed Truck5.51031.25ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1031.25 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7129 | 21613 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 11 | Hr |  | 0 |  |  | 2062.5 | 268.125 | 2330.625 | 2021-07-06 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew traveled to location, safety meeting, Load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew traveled out. ## COVID-19 policies in effect ## Dylan Thompson travelling to Thunder Bay for Valard COVID test. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712921613Flatbed Truck112062.5 | Northern Mat & Bridge712921613Flatbed Truck112062.5ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2062.5 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7129 | 21613 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 10.5 | Hr |  | 0 |  |  | 1968.75 | 255.9375 | 2224.6875 | 2021-07-06 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew traveled to location, safety meeting, Load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew traveled out. ## COVID-19 policies in effect ## Dylan Thompson travelling to Thunder Bay for Valard COVID test. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712921613Flatbed Truck10.51968.75 | Northern Mat & Bridge712921613Flatbed Truck10.51968.75ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1968.75 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7129 | 21613 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 10 | Hr |  | 0 |  |  | 1875 | 243.75 | 2118.75 | 2021-07-06 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew traveled to location, safety meeting, Load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew traveled out. ## COVID-19 policies in effect ## Dylan Thompson travelling to Thunder Bay for Valard COVID test. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712921613Flatbed Truck101875 | Northern Mat & Bridge712921613Flatbed Truck101875ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1875 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7129 | 21613 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 10.5 | Hr |  | 0 |  |  | 1968.75 | 255.9375 | 2224.6875 | 2021-07-06 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew traveled to location, safety meeting, Load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew traveled out. ## COVID-19 policies in effect ## Dylan Thompson travelling to Thunder Bay for Valard COVID test. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712921613Flatbed Truck10.51968.75 | Northern Mat & Bridge712921613Flatbed Truck10.51968.75ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1968.75 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7129 | 21613 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 13 | Hr |  | 0 |  |  | 2437.5 | 316.875 | 2754.375 | 2021-07-06 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew traveled to location, safety meeting, Load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew traveled out. ## COVID-19 policies in effect ## Dylan Thompson travelling to Thunder Bay for Valard COVID test. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712921613Flatbed Truck132437.5 | Northern Mat & Bridge712921613Flatbed Truck132437.5ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2437.5 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7130 | 21615 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 10 | Hr |  | 0 |  |  | 1875 | 243.75 | 2118.75 | 2021-07-07 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew travelled in, safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Shuttle one load of mats with roll off, determined high potential for a spill, use roll off to move mats to Paint lake road as per Valard, moved 28 mats to Paint Lake road. Dylan Thompson enroute to Thunder Bay for Valard covid test. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa fore work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge713021615Flatbed Truck101875 | Northern Mat & Bridge713021615Flatbed Truck101875ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1875 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7130 | 21615 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 11 | Hr |  | 0 |  |  | 2062.5 | 268.125 | 2330.625 | 2021-07-07 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew travelled in, safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Shuttle one load of mats with roll off, determined high potential for a spill, use roll off to move mats to Paint lake road as per Valard, moved 28 mats to Paint Lake road. Dylan Thompson enroute to Thunder Bay for Valard covid test. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa fore work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge713021615Flatbed Truck112062.5 | Northern Mat & Bridge713021615Flatbed Truck112062.5ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2062.5 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7130 | 21615 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 4 | Hr |  | 0 |  |  | 750 | 97.5 | 847.5 | 2021-07-07 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew travelled in, safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Shuttle one load of mats with roll off, determined high potential for a spill, use roll off to move mats to Paint lake road as per Valard, moved 28 mats to Paint Lake road. Dylan Thompson enroute to Thunder Bay for Valard covid test. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa fore work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge713021615Flatbed Truck4750 | Northern Mat & Bridge713021615Flatbed Truck4750ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 750 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7130 | 21615 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 7 | Hr |  | 0 |  |  | 1312.5 | 170.625 | 1483.125 | 2021-07-07 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew travelled in, safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Shuttle one load of mats with roll off, determined high potential for a spill, use roll off to move mats to Paint lake road as per Valard, moved 28 mats to Paint Lake road. Dylan Thompson enroute to Thunder Bay for Valard covid test. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa fore work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge713021615Flatbed Truck71312.5 | Northern Mat & Bridge713021615Flatbed Truck71312.5ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1312.5 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7142 | 21619 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 11 | Hr |  | 0 |  |  | 2062.5 | 268.125 | 2330.625 | 2021-07-09 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in. safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Deliver another load of 10 mats to km 7-8 on paint lake with roll-off for road repair. Total of 32 mats at km 7-8 on Paint Lake Rd. crew travelled out. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa for work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44387 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714221619Flatbed Truck112062.5 | Northern Mat & Bridge714221619Flatbed Truck112062.5ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2062.5 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 15 | Hr |  | 0 |  |  | 2812.5 | 365.625 | 3178.125 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Flatbed Truck152812.5 | Northern Mat & Bridge714321620Flatbed Truck152812.5ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2812.5 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 7 | Hr |  | 0 |  |  | 1312.5 | 170.625 | 1483.125 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Flatbed Truck71312.5 | Northern Mat & Bridge714321620Flatbed Truck71312.5ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1312.5 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 11 | Hr |  | 0 |  |  | 2062.5 | 268.125 | 2330.625 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Flatbed Truck112062.5 | Northern Mat & Bridge714321620Flatbed Truck112062.5ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2062.5 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 7.5 | Hr |  | 0 |  |  | 1406.25 | 182.8125 | 1589.0625 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Flatbed Truck7.51406.25 | Northern Mat & Bridge714321620Flatbed Truck7.51406.25ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1406.25 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 12 | Hr |  | 0 |  |  | 2250 | 292.5 | 2542.5 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Flatbed Truck122250 | Northern Mat & Bridge714321620Flatbed Truck122250ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2250 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7144 | 21621 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 11 | Hr |  | 0 |  |  | 2062.5 | 268.125 | 2330.625 | 2021-07-11 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | crew travelled in, safety meeting,load unload trucks, shuttle mats, lay mats as per Valard instructions. ## covid 19 policies in effect ## crew travelled out | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44389 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714421621Flatbed Truck112062.5 | Northern Mat & Bridge714421621Flatbed Truck112062.5ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2062.5 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7144 | 21621 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 13 | Hr |  | 0 |  |  | 2437.5 | 316.875 | 2754.375 | 2021-07-11 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | crew travelled in, safety meeting,load unload trucks, shuttle mats, lay mats as per Valard instructions. ## covid 19 policies in effect ## crew travelled out | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44389 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714421621Flatbed Truck132437.5 | Northern Mat & Bridge714421621Flatbed Truck132437.5ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2437.5 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7145 | 21622 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 14 | Hr |  | 0 |  |  | 2625 | 341.25 | 2966.25 | 2021-07-12 | 0 | ESI10770 | 44452 | 68 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44390 |  | 14 | 44449 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714521622Flatbed Truck142625 | Northern Mat & Bridge714521622Flatbed Truck142625ESI10770 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2625 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7145 | 21622 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 11 | Hr |  | 0 |  |  | 2062.5 | 268.125 | 2330.625 | 2021-07-12 | 0 | ESI10770 | 44452 | 68 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44390 |  | 14 | 44449 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714521622Flatbed Truck112062.5 | Northern Mat & Bridge714521622Flatbed Truck112062.5ESI10770 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2062.5 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7146 | 21623 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 13 | Hr |  | 0 |  |  | 2437.5 | 316.875 | 2754.375 | 2021-07-13 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44391 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714621623Flatbed Truck132437.5 | Northern Mat & Bridge714621623Flatbed Truck132437.5ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2437.5 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7147 | 21624 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 22 | Hr |  | 0 |  |  | 4125 | 536.25 | 4661.25 | 2021-07-14 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled to site, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instructiions, crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slowly with over a 25km round trip. Released on site haulers. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44392 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714721624Flatbed Truck224125 | Northern Mat & Bridge714721624Flatbed Truck224125ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 4125 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7169 | 31585 R1 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 6 | Hr |  | 0 |  |  | 1125 | 146.25 | 1271.25 | 2021-06-29 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel and standby time for Jason and Cutler. Travel to Thunder Bay, wait on and receive Covid tests. Myself, Aaron and Dylan worked on site. Essentially I was wrangling Kawartha trucks about 5KM’s from site. Aaron Jones was unloading trucks at the laydown pad. Dylan escorted Andre into KM17 with the excavator and then assisted Aaron with unloading trucks and getting them turned around to head out ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge716931585 R1Flatbed Truck61125 | Northern Mat & Bridge716931585 R1Flatbed Truck61125ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1125 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7125 | 21604 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck - Sunday/Stat Holidays | 249.75 | 12.3575 | Hr |  | 0 |  |  | 3086.2856 | 401.2171 | 3487.5027 | 2021-07-02 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Entered with regular rates however LEM had stat holiday rates, sent back for revision, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks at km1 laydown. Haulmats from laydown to km 17 Henson rd. shuttle mats from km 17 to Row. Lay mats as per valard intruction. Crew travelled out. ## COVID-19 protocols in effect ## | 10 | F109 | Hensen Road | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712521604Flatbed Truck - Sunday/Stat Holidays12.35753086.2856 | Northern Mat & Bridge712521604Flatbed Truck - Sunday/Stat Holidays12.35753086.2856ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 3086.2856 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7125 | 21604 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck - Sunday/Stat Holidays | 249.75 | 13.3873 | Hr |  | 0 |  |  | 3343.4782 | 434.6522 | 3778.1304 | 2021-07-02 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Entered with regular rates however LEM had stat holiday rates, sent back for revision, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks at km1 laydown. Haulmats from laydown to km 17 Henson rd. shuttle mats from km 17 to Row. Lay mats as per valard intruction. Crew travelled out. ## COVID-19 protocols in effect ## | 10 | F109 | Hensen Road | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712521604Flatbed Truck - Sunday/Stat Holidays13.38733343.4782 | Northern Mat & Bridge712521604Flatbed Truck - Sunday/Stat Holidays13.38733343.4782ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 3343.4782 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7127 | 21608 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck - Sunday/Stat Holidays | 249.75 | 12.0784 | Hr |  | 0 |  |  | 3016.5879 | 392.1564 | 3408.7443 | 2021-07-04 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks. Haul mats on site, shuttle and lay mats as per Valard instuction. Crew travelled out. ## covid 19 policies in effect ## Cory Trembeltt travel time 18 hrs total for mob in and drive to TB for COVID test and drive to site Wawa. | 10 | F065-F118 | Paint Lake Road 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712721608Flatbed Truck - Sunday/Stat Holidays12.078433016.5879 | Northern Mat & Bridge712721608Flatbed Truck - Sunday/Stat Holidays12.078433016.5879ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 3016.5879 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7127 | 21608 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck - Sunday/Stat Holidays | 249.75 | 12.0784 | Hr |  | 0 |  |  | 3016.5879 | 392.1564 | 3408.7443 | 2021-07-04 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks. Haul mats on site, shuttle and lay mats as per Valard instuction. Crew travelled out. ## covid 19 policies in effect ## Cory Trembeltt travel time 18 hrs total for mob in and drive to TB for COVID test and drive to site Wawa. | 10 | F065-F118 | Paint Lake Road 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712721608Flatbed Truck - Sunday/Stat Holidays12.078433016.5879 | Northern Mat & Bridge712721608Flatbed Truck - Sunday/Stat Holidays12.078433016.5879ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 3016.5879 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7144 | 21621 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck - Sunday/Stat Holidays | 249.75 | 9.0522 | Hr |  |  |  |  | 2260.7894 | 293.9026 | 2554.692 | 2021-07-11 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | crew travelled in, safety meeting,load unload trucks, shuttle mats, lay mats as per Valard instructions. ## covid 19 policies in effect ## crew travelled out | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44389 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714421621Flatbed Truck - Sunday/Stat Holidays9.052212260.7894 | Northern Mat & Bridge714421621Flatbed Truck - Sunday/Stat Holidays9.052212260.7894ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2260.7894 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7127 | 21608 | 53531001 | Rig/Access Mats | 0 | Flatbed Truck - Sunday/Stat Holidays | 249.75 | 12.0784 | Hr |  | 0 |  |  | 3016.5879 | 392.1564 | 3408.7443 | 2021-07-04 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks. Haul mats on site, shuttle and lay mats as per Valard instuction. Crew travelled out. ## covid 19 policies in effect ## Cory Trembeltt travel time 18 hrs total for mob in and drive to TB for COVID test and drive to site Wawa. | 10 | F065-F118 | Paint Lake Road 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712721608Flatbed Truck - Sunday/Stat Holidays12.078433016.5879 | Northern Mat & Bridge712721608Flatbed Truck - Sunday/Stat Holidays12.078433016.5879ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 3016.5879 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7130 | 21615 | 53531001 | Rig/Access Mats | 0 | Shuttle | 187.5 | 11 | Hr |  | 0 |  |  | 2062.5 | 268.125 | 2330.625 | 2021-07-07 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew travelled in, safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Shuttle one load of mats with roll off, determined high potential for a spill, use roll off to move mats to Paint lake road as per Valard, moved 28 mats to Paint Lake road. Dylan Thompson enroute to Thunder Bay for Valard covid test. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa fore work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge713021615Shuttle112062.5 | Northern Mat & Bridge713021615Shuttle112062.5ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2062.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6062 | AGCE-20210205-2 | 53511111 | Access | 0 | Grader 780 | 165 | 5.5 | HR | 123.75 | 0 |  |  | 907.5 | 117.975 | 1025.475 | 2021-02-05 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Alfred C, not eligible, local |  | Approved |  |  | Winter Access Maint Grade wings and back on Dore Rd. | 11 | F135-F147 | Dore Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6062AGCE-20210205-2Grader 7805.5907.5 | AG Chapman Enterprises6062AGCE-20210205-2Grader 7805.5907.5AGCE-2021-02-10 | [5 empty] | 1 | 907.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6063 | AGCE-20210204-1 | 53511111 | Access | 0 | Grader 780 | 165 | 4 | HR | 123.75 | 0 |  |  | 660 | 85.8 | 745.8 | 2021-02-04 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Equipment on standby | 11 |  |  | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6063AGCE-20210204-1Grader 7804660 | AG Chapman Enterprises6063AGCE-20210204-1Grader 7804660AGCE-2021-02-10 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6064 | AGCE-20210126-2 | 53511111 | Access | 0 | Grader 780 | 165 | 4.5 | HR | 123.75 | 0 |  |  | 742.5 | 96.525 | 839.025 | 2021-01-26 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Alfred Chapman, removed |  | Approved |  |  | Grade and wing back banks on Tremblay Flats Rd, Access roads F163 to F162 | 11 | F163, F162 | Trembley Flats Rd | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6064AGCE-20210126-2Grader 7804.5742.5 | AG Chapman Enterprises6064AGCE-20210126-2Grader 7804.5742.5AGCE-2021-01-30 | [5 empty] | 1 | 742.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6065 | AGCE-20210126-1 | 53511111 | Access | 0 | Grader 780 | 165 | 4 | HR | 123.75 | 0 |  |  | 660 | 85.8 | 745.8 | 2021-01-26 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Alfred Chapman, removed |  | Approved |  |  | Grade Dore Lake Road | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6065AGCE-20210126-1Grader 7804660 | AG Chapman Enterprises6065AGCE-20210126-1Grader 7804660AGCE-2021-01-30 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6068 | AGCE-20210201-01 | 53511111 | Access | 0 | Grader 780 | 165 | 4 | HR | 123.75 | 0 |  |  | 660 | 85.8 | 745.8 | 2021-02-01 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Grader on standby | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6068AGCE-20210201-01Grader 7804660 | AG Chapman Enterprises6068AGCE-20210201-01Grader 7804660AGCE-2021-02-10 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6069 | AGCE-20210202-1 | 53511111 | Access | 0 | Grader 780 | 165 | 4 | HR | 123.75 | 0 |  |  | 660 | 85.8 | 745.8 | 2021-02-02 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Grader on standby | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6069AGCE-20210202-1Grader 7804660 | AG Chapman Enterprises6069AGCE-20210202-1Grader 7804660AGCE-2021-02-10 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6070 | AGCE-20210203-1 | 53511111 | Access | 0 | Grader 780 | 165 | 4 | HR | 123.75 | 0 |  |  | 660 | 85.8 | 745.8 | 2021-02-03 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Grader on standby | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6070AGCE-20210203-1Grader 7804660 | AG Chapman Enterprises6070AGCE-20210203-1Grader 7804660AGCE-2021-02-10 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6341 | AGCE-20210114-01-R1 | 53511111 | Access | 0 | Grader 780 | 165 | 7 | HR | 123.75 | 0 |  |  | 1155 | 150.15 | 1305.15 | 2021-01-29 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | Is treated sand in the contract? If not where are they getting it from? |  | Approved |  |  | Sanding Tremblay Flats road with treated sand. 2 TON treated sand. | 11 |  | MFN | 0 |  |  | 54 | 44328 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6341AGCE-20210114-01-R1Grader 78071155 | AG Chapman Enterprises6341AGCE-20210114-01-R1Grader 78071155AGCE-2021-01-30 | [5 empty] | 1 | 1155 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6369 | AGCE-20210121-4 | 53511111 | Access | 0 | Grader 780 | 165 | 6 | HR | 123.75 | 0 |  |  | 990 | 128.7 | 1118.7 | 2021-01-21 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | 1 LOA for Alfred Chapman, removed |  | Approved |  |  | Grade Trembley Flats Road 3 am to 9 am | 11 |  | Trembley Flats Road | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6369AGCE-20210121-4Grader 7806990 | AG Chapman Enterprises6369AGCE-20210121-4Grader 7806990AGCE-2021-01-30 | [5 empty] | 1 | 990 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6370 | AGCE-20210121-5 | 53511111 | Access | 0 | Grader 780 | 165 | 1 | HR | 123.75 | 0 |  |  | 165 | 21.45 | 186.45 | 2021-01-21 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | 1 LOA for Alfred Chapman, removed |  | Approved |  |  | Grade Road 5 F159-F160 | 11 | F159-F160 | Harbour Road 5 | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6370AGCE-20210121-5Grader 7801165 | AG Chapman Enterprises6370AGCE-20210121-5Grader 7801165AGCE-2021-01-30 | [5 empty] | 1 | 165 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6372 | AGCE-20210125-2 | 53511111 | Access | 0 | Grader 780 | 165 | 4 | HR | 123.75 | 0 |  |  | 660 | 85.8 | 745.8 | 2021-01-25 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Alfred Chapman and Ryan MacIntyre, removed |  | Approved |  |  | Grade and sand Trembley Flats Road | 11 |  | Trembley Flats Road | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6372AGCE-20210125-2Grader 7804660 | AG Chapman Enterprises6372AGCE-20210125-2Grader 7804660AGCE-2021-01-30 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6378 | AGCE-20210206-3 | 53511111 | Access | 0 | Grader 780 | 165 | 4 | HR | 123.75 | 0 |  |  | 660 | 85.8 | 745.8 | 2021-02-06 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Grader on stndby | 11 |  | Trembley Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6378AGCE-20210206-3Grader 7804660 | AG Chapman Enterprises6378AGCE-20210206-3Grader 7804660AGCE-2021-02-10 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6379 | AGCE-20210207-1 | 53511111 | Access | 0 | Grader 780 | 165 | 4 | HR | 123.75 | 0 |  |  | 660 | 85.8 | 745.8 | 2021-02-07 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Grader on stndby | 11 |  | Trembley Rd, Harbour Rd's | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6379AGCE-20210207-1Grader 7804660 | AG Chapman Enterprises6379AGCE-20210207-1Grader 7804660AGCE-2021-02-10 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6381 | AGCE-20210208-2 | 53511111 | Access | 0 | Grader 780 | 165 | 5.5 | HR | 123.75 | 0 |  |  | 907.5 | 117.975 | 1025.475 | 2021-02-08 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Alfred C, not eligible, Local |  | Approved |  |  | Graded Trembley Rd | 11 |  | Trembley Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6381AGCE-20210208-2Grader 7805.5907.5 | AG Chapman Enterprises6381AGCE-20210208-2Grader 7805.5907.5AGCE-2021-02-10 | [5 empty] | 1 | 907.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6384 | AGCE-20210209-2 | 53511111 | Access | 0 | Grader 780 | 165 | 10 | HR | 123.75 | 0 |  |  | 1650 | 214.5 | 1864.5 | 2021-02-09 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D |  | Approved |  |  | Grade roads from office to trembley rd and return | 11 |  | Trembley Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6384AGCE-20210209-2Grader 780101650 | AG Chapman Enterprises6384AGCE-20210209-2Grader 780101650AGCE-2021-02-10 | [5 empty] | 1 | 1650 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6387 | AGCE-20210210-2 | 53511111 | Access | 0 | Grader 780 | 165 | 7 | HR | 123.75 | 0 |  |  | 1155 | 150.15 | 1305.15 | 2021-02-10 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D |  | Approved |  |  | Grade Harbour Rd 1, Dore Rd, | 11 |  | Harbour Rd 1, Dore Rd, | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6387AGCE-20210210-2Grader 78071155 | AG Chapman Enterprises6387AGCE-20210210-2Grader 78071155AGCE-2021-02-10 | [5 empty] | 1 | 1155 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6389 | AGCE-20210211-1 | 53511111 | Access | 0 | Grader 780 | 165 | 4 | HR | 123.75 | 0 |  |  | 660 | 85.8 | 745.8 | 2021-02-11 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D |  | Approved |  |  | Graded Dore, Harbour Rd | 11 |  | Dore, Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6389AGCE-20210211-1Grader 7804660 | AG Chapman Enterprises6389AGCE-20210211-1Grader 7804660AGCE-2021-02-11-20 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6398 | AGCE-20210213-3 | 53511111 | Access | 0 | Grader 780 | 165 | 8.5 | HR | 123.75 | 0 |  |  | 1402.5 | 182.325 | 1584.825 | 2021-02-13 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D Supervisor and truck removed |  | Approved |  |  | Grading Dore Rd, Trembley Rd, Harbour Rd | 11 | F119-F160 | Dore Lake Rd, Trembley Rd, Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6398AGCE-20210213-3Grader 7808.51402.5 | AG Chapman Enterprises6398AGCE-20210213-3Grader 7808.51402.5AGCE-2021-02-11-20 | [5 empty] | 1 | 1402.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6403 | AGCE-20210214-4 | 53511111 | Access | 0 | Grader 780 | 165 | 4 | HR | 123.75 | 0 |  |  | 660 | 85.8 | 745.8 | 2021-02-14 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Grader on stndby | 11 |  | Trembley Rd, Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6403AGCE-20210214-4Grader 7804660 | AG Chapman Enterprises6403AGCE-20210214-4Grader 7804660AGCE-2021-02-11-20 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6404 | AGCE-20210215-1 | 53511111 | Access | 0 | Grader 780 | 165 | 4 | HR | 123.75 | 0 |  |  | 660 | 85.8 | 745.8 | 2021-02-15 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Grader on stndby | 11 |  | Trembley Rd, Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6404AGCE-20210215-1Grader 7804660 | AG Chapman Enterprises6404AGCE-20210215-1Grader 7804660AGCE-2021-02-11-20 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6411 | AGCE-20210216-4 | 53511111 | Access | 0 | Grader 780 | 165 | 6 | HR | 123.75 | 0 |  |  | 990 | 128.7 | 1118.7 | 2021-02-16 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D Supervisor and truck removed |  | Approved |  |  | Grade Trembley Rd | 11 | F160-F164 | Trembley Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6411AGCE-20210216-4Grader 7806990 | AG Chapman Enterprises6411AGCE-20210216-4Grader 7806990AGCE-2021-02-11-20 | [5 empty] | 1 | 990 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6417 | AGCE-20210217-5 | 53511111 | Access | 0 | Grader 780 | 165 | 8 | HR | 123.75 | 0 |  |  | 1320 | 171.6 | 1491.6 | 2021-02-17 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D Supervisor and truck removed |  | Approved |  |  | Grading High Falls Road 1, 2, 3, 5 | 11 | F172-F211 | High Falls Road 1, 2, 3, 5 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6417AGCE-20210217-5Grader 78081320 | AG Chapman Enterprises6417AGCE-20210217-5Grader 78081320AGCE-2021-02-11-20 | [5 empty] | 1 | 1320 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6421 | AGCE-20210218-5 | 53511111 | Access | 0 | Grader 780 | 165 | 4 | HR | 123.75 | 0 |  |  | 660 | 85.8 | 745.8 | 2021-02-18 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Grader on Stndby | 11 |  | Trembley Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6421AGCE-20210218-5Grader 7804660 | AG Chapman Enterprises6421AGCE-20210218-5Grader 7804660AGCE-2021-02-11-20 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6426 | AGCE-20210219-5 | 53511111 | Access | 0 | Grader 780 | 165 | 4 | HR | 123.75 | 0 |  |  | 660 | 85.8 | 745.8 | 2021-02-19 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D Supervisor and truck removed |  | Approved |  |  | Grade harbour rd | 11 | F148-F159 | Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6426AGCE-20210219-5Grader 7804660 | AG Chapman Enterprises6426AGCE-20210219-5Grader 7804660AGCE-2021-02-11-20 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6438 | AGCE-20210223-4 | 53511111 | Access | 0 | Grader 780 | 165 | 10.5 | HR | 123.75 | 0 |  |  | 1732.5 | 225.225 | 1957.725 | 2021-02-23 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S Supervisor and truck removed |  | Approved |  |  | Grade Trembley Rd, Harbour Rd, Dore Lake Rd | 11 | F128-F164 | Trembley Road, Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6438AGCE-20210223-4Grader 78010.51732.5 | AG Chapman Enterprises6438AGCE-20210223-4Grader 78010.51732.5AGCE-2021-02-21-28 | [5 empty] | 1 | 1732.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6445 | AGCE-20210224-01-R1 | 53511111 | Access | 0 | Grader 780 | 165 | 6.5 | HR | 123.75 | 0 |  |  | 1072.5 | 139.425 | 1211.925 | 2021-02-24 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D |  | Approved |  |  | Graded Trembley rd to Harbour rd 1 | 11 | F128-F164 | Trembley Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6445AGCE-20210224-01-R1Grader 7806.51072.5 | AG Chapman Enterprises6445AGCE-20210224-01-R1Grader 7806.51072.5AGCE-2021-02-21-28 | [5 empty] | 1 | 1072.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6457 | AGCE-20210226-01-R1 | 53511111 | Access | 0 | Grader 780 | 165 | 8.5 | HR | 123.75 | 0 |  |  | 1402.5 | 182.325 | 1584.825 | 2021-02-26 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S, no LOA for Andy N |  | Approved |  |  | Grade and sand roads dore lake road - Trembley | 11 | F161 | Trembley Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6457AGCE-20210226-01-R1Grader 7808.51402.5 | AG Chapman Enterprises6457AGCE-20210226-01-R1Grader 7808.51402.5AGCE-2021-02-21-28 | [5 empty] | 1 | 1402.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6474 | AGCE-20210301-02-R1 | 53511111 | Access | 0 | Grader 780 | 165 | 5 | HR | 123.75 | 0 |  |  | 825 | 107.25 | 932.25 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Joe B |  | Approved |  |  | Grade Dore LK Rd to to Km 4 | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6474AGCE-20210301-02-R1Grader 7805825 | AG Chapman Enterprises6474AGCE-20210301-02-R1Grader 7805825AGCE-2021-03-01-10 | [5 empty] | 1 | 825 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6475 | AGCE-20210301-03-R1 | 53511111 | Access | 0 | Grader 780 | 165 | 8 | HR | 123.75 | 0 |  |  | 1320 | 171.6 | 1491.6 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D No truck on ticket |  | Approved |  |  | Grade harbour to trembley | 11 | F148-F160 | Harbour Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6475AGCE-20210301-03-R1Grader 78081320 | AG Chapman Enterprises6475AGCE-20210301-03-R1Grader 78081320AGCE-2021-03-01-10 | [5 empty] | 1 | 1320 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6483 | AGCE-20210302-02-R1 | 53511111 | Access | 0 | Grader 780 | 165 | 11 | HR | 123.75 | 0 |  |  | 1815 | 235.95 | 2050.95 | 2021-03-02 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Joe B |  | Approved |  |  | Graded main rd to Dore Lk Rd km 4 | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6483AGCE-20210302-02-R1Grader 780111815 | AG Chapman Enterprises6483AGCE-20210302-02-R1Grader 780111815AGCE-2021-03-01-10 | [5 empty] | 1 | 1815 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6495 | AGCE-20210303-06-R1 | 53511111 | Access | 0 | Grader 780 | 165 | 11.5 | HR | 123.75 | 0 |  |  | 1897.5 | 246.675 | 2144.175 | 2021-03-03 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Joe B |  | Approved |  |  | Graded roads in harbour to dore km 1 to km 4.5 | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6495AGCE-20210303-06-R1Grader 78011.51897.5 | AG Chapman Enterprises6495AGCE-20210303-06-R1Grader 78011.51897.5AGCE-2021-03-01-10 | [5 empty] | 1 | 1897.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6507 | AGCE-20210305-03 | 53511111 | Access | 0 | Grader 780 | 165 | 7 | HR | 123.75 | 0 |  |  | 1155 | 150.15 | 1305.15 | 2021-03-05 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | No LOA for Joe B, billed out already |  | Approved |  |  | Grading of Trembely Road | 11 | F128-F164 | Trembley Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6507AGCE-20210305-03Grader 78071155 | AG Chapman Enterprises6507AGCE-20210305-03Grader 78071155AGCE-2021-03-01-10 | [5 empty] | 1 | 1155 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6509 | AGCE-20210306-02 | 53511111 | Access | 0 | Grader 780 | 165 | 5 | HR | 123.75 | 0 |  |  | 825 | 107.25 | 932.25 | 2021-03-06 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Joe B |  | Approved |  |  | Grade and support on Trembley Rd | 11 | F160 | Trembley Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6509AGCE-20210306-02Grader 7805825 | AG Chapman Enterprises6509AGCE-20210306-02Grader 7805825AGCE-2021-03-01-10 | [5 empty] | 1 | 825 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6517 | AGCE-20210308-05 | 53511111 | Access | 0 | Grader 780 | 165 | 5 | HR | 123.75 | 0 |  |  | 825 | 107.25 | 932.25 | 2021-03-08 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andrew B |  | Approved |  |  | Grade Trembley Rd | 11 | F160 | Trembley Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6517AGCE-20210308-05Grader 7805825 | AG Chapman Enterprises6517AGCE-20210308-05Grader 7805825AGCE-2021-03-01-10 | [5 empty] | 1 | 825 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6521 | AGCE-20210310-05 | 53511111 | Access | 0 | Grader 780 | 165 | 4 | HR | 123.75 | 0 |  |  | 660 | 85.8 | 745.8 | 2021-03-10 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andrew B |  | Approved |  |  | Cut snow banks for water drainage with grader | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6521AGCE-20210310-05Grader 7804660 | AG Chapman Enterprises6521AGCE-20210310-05Grader 7804660AGCE-2021-03-01-10 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6523 | AGCE-20210311-01 | 53511111 | Access | 0 | Grader 780 | 165 | 6 | HR | 123.75 | 0 |  |  | 990 | 128.7 | 1118.7 | 2021-03-11 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andrew B |  | Approved |  |  | Grade and push back banks | 11 | F160 | Trembley Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6523AGCE-20210311-01Grader 7806990 | AG Chapman Enterprises6523AGCE-20210311-01Grader 7806990AGCE-2021-03-11-20 | [5 empty] | 1 | 990 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6528 | AGCE-20210315-05 | 53511111 | Access | 0 | Grader 780 | 165 | 4 | HR | 123.75 |  |  |  | 660 | 85.8 | 745.8 | 2021-03-15 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Grader on stndby | 11 |  |  | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6528AGCE-20210315-05Grader 7804660 | AG Chapman Enterprises6528AGCE-20210315-05Grader 7804660AGCE-2021-03-11-20 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6530 | AGCE-20210316-06 | 53511111 | Access | 0 | Grader 780 | 165 | 4 | HR | 123.75 |  |  |  | 660 | 85.8 | 745.8 | 2021-03-16 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Grader on stndby | 11 |  |  | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6530AGCE-20210316-06Grader 7804660 | AG Chapman Enterprises6530AGCE-20210316-06Grader 7804660AGCE-2021-03-11-20 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6531 | AGCE-20210317-02 | 53511111 | Access | 0 | Grader 780 | 165 | 6 | HR | 123.75 | 0 |  |  | 990 | 128.7 | 1118.7 | 2021-03-17 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Grade Roads Dore | 11 | F135-F149 | Dore Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6531AGCE-20210317-02Grader 7806990 | AG Chapman Enterprises6531AGCE-20210317-02Grader 7806990AGCE-2021-03-11-20 | [5 empty] | 1 | 990 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6535 | AGCE-20210319-01 | 53511111 | Access | 0 | Grader 780 | 165 | 7 | HR | 123.75 | 0 |  |  | 1155 | 150.15 | 1305.15 | 2021-03-19 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert M No truck on ticket |  | Approved |  |  | Grade Harbour Rd | 11 | F150-F159 | Harbour Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6535AGCE-20210319-01Grader 78071155 | AG Chapman Enterprises6535AGCE-20210319-01Grader 78071155AGCE-2021-03-11-20 | [5 empty] | 1 | 1155 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6539 | AGCE-20210320-02 | 53511111 | Access | 0 | Grader 780 | 165 | 4 | HR | 123.75 |  |  |  | 660 | 85.8 | 745.8 | 2021-03-20 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Grader on stndby | 11 |  |  | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6539AGCE-20210320-02Grader 7804660 | AG Chapman Enterprises6539AGCE-20210320-02Grader 7804660AGCE-2021-03-11-20 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6541 | AGCE-20210321-03 | 53511111 | Access | 0 | Grader 780 | 165 | 4 | HR | 123.75 | 0 |  |  | 660 | 85.8 | 745.8 | 2021-03-21 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Pending |  |  | Grader on stndby | 11 |  |  | 0 | [10 empty] | 11 | AG Chapman Enterprises6541AGCE-20210321-03Grader 7804660 | AG Chapman Enterprises6541AGCE-20210321-03Grader 7804660 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7047 | AGCE-20210311-02 | 53511111 | Access | 0 | Grader 780 | 165 | 4 | HR | 123.75 | 0 |  |  | 660 | 85.8 | 745.8 | 2021-03-11 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | No LOA for Andrew B as it was already billed out on this day |  | Approved |  |  | Grading Washboard | 11 | F150 | Harbour Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7047AGCE-20210311-02Grader 7804660 | AG Chapman Enterprises7047AGCE-20210311-02Grader 7804660AGCE-2021-03-11-20 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7049 | AGCE-20210313-01 | 53511111 | Access | 0 | Grader 780 | 165 | 5.5 | HR | 123.75 | 0 |  |  | 907.5 | 117.975 | 1025.475 | 2021-03-13 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Grading of Michipicoten and Trembley Rds | 11 | F150-F164 | Michipicoten to Trembley | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7049AGCE-20210313-01Grader 7805.5907.5 | AG Chapman Enterprises7049AGCE-20210313-01Grader 7805.5907.5AGCE-2021-03-11-20 | [5 empty] | 1 | 907.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7050 | AGCE-20210313-04 | 53511111 | Access | 0 | Grader 780 | 165 | 3 | HR | 123.75 | 0 |  |  | 495 | 64.35 | 559.35 | 2021-03-13 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Early morning shift grading and then another operator took over | 11 | F120-F160 | Harbour, Trembley, Dore | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7050AGCE-20210313-04Grader 7803495 | AG Chapman Enterprises7050AGCE-20210313-04Grader 7803495AGCE-2021-03-11-20 | [5 empty] | 1 | 495 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7051 | AGCE-20210314-01 | 53511111 | Access | 0 | Grader 780 | 165 | 3 | HR | 123.75 | 0 |  |  | 495 | 64.35 | 559.35 | 2021-03-14 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | No LOA for Andy Neyland No Loa for Alfed C |  | Approved |  |  | Grading and Sanding Harbour and trembley Rd, and Dore | 11 | F120-F160 | Harbour, Trembley, Dore | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7051AGCE-20210314-01Grader 7803495 | AG Chapman Enterprises7051AGCE-20210314-01Grader 7803495AGCE-2021-03-11-20 | [5 empty] | 1 | 495 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7052 | AGCE-20210314-04 | 53511111 | Access | 0 | Grader 780 | 165 | 5.5 | HR | 123.75 | 0 |  |  | 907.5 | 117.975 | 1025.475 | 2021-03-14 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Pending |  |  | Graded roads, not enough description sent back to Chapman | 11 |  |  | 0 | [10 empty] | 11 | AG Chapman Enterprises7052AGCE-20210314-04Grader 7805.5907.5 | AG Chapman Enterprises7052AGCE-20210314-04Grader 7805.5907.5 | [5 empty] | 1 | 907.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7053 | AGCE-20210314-05 | 53511111 | Access | 0 | Grader 780 | 165 | 8 | HR | 123.75 | 0 |  |  | 1320 | 171.6 | 1491.6 | 2021-03-14 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert M, turns out he is not local |  | Approved |  |  | Grade roads as per email from Mandy | 11 | F120-F160 | Harbour, Trembley, Dore | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7053AGCE-20210314-05Grader 78081320 | AG Chapman Enterprises7053AGCE-20210314-05Grader 78081320AGCE-2021-03-11-20 | [5 empty] | 1 | 1320 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7057 | AGCE-20210318-02 | 53511111 | Access | 0 | Grader 780 | 165 | 4 | HR | 123.75 | 0 |  |  | 660 | 85.8 | 745.8 | 2021-03-18 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert M |  | Approved |  |  | Grading harbour Road in morning and afternoon | 11 | F150-F159 | Harbour Road | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7057AGCE-20210318-02Grader 7804660 | AG Chapman Enterprises7057AGCE-20210318-02Grader 7804660AGCE-2021-03-11-20 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7140 | AGCE-20210315-06 | 53511111 | Access | 0 | Grader 780 | 165 | 5.5 | HR | 123.75 | 0 |  |  | 907.5 | 117.975 | 1025.475 | 2021-03-15 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert mcCabe |  | Approved |  |  | Grading Hensen Road | 11 | F118-F127 | Hensen Road | 0 |  |  | 54 | 44398 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7140AGCE-20210315-06Grader 7805.5907.5 | AG Chapman Enterprises7140AGCE-20210315-06Grader 7805.5907.5AGCE-2021-03-11-20 | [5 empty] | 1 | 907.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6066 | AGCE-20210129-1 | 53511111 | Access | 0 | Sander Truck F550 | 125 | 3 | HR | 93.75 | 0 |  |  | 375 | 48.75 | 423.75 | 2021-01-29 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andy N, removed |  | Approved |  |  | Sand michhipicoten turn off, Harbour Rd to Dore Lake Road | 11 | F135-F150 | Harbour Road / Dore Lake Road | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6066AGCE-20210129-1Sander Truck F5503375 | AG Chapman Enterprises6066AGCE-20210129-1Sander Truck F5503375AGCE-2021-01-30 | [5 empty] | 1 | 375 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6067 | AGCE-20210201-2 | 53511111 | Access | 0 | Sander Truck F550 | 125 | 6 | HR | 93.75 | 0 |  |  | 750 | 97.5 | 847.5 | 2021-02-01 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andy N, not eligible, Local |  | Approved |  |  | Sanded roads: Michipicoten Harbour Rd, Dore Lake Road, Trembley Flats Rd | 11 | F160-F164 | Trembley Falls Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6067AGCE-20210201-2Sander Truck F5506750 | AG Chapman Enterprises6067AGCE-20210201-2Sander Truck F5506750AGCE-2021-02-10 | [5 empty] | 1 | 750 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6341 | AGCE-20210114-01-R1 | 53511111 | Access | 0 | Sander Truck F550 | 125 | 3 | HR | 93.75 | 0 |  |  | 375 | 48.75 | 423.75 | 2021-01-29 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | Is treated sand in the contract? If not where are they getting it from? |  | Approved |  |  | Sanding Tremblay Flats road with treated sand. 2 TON treated sand. | 11 |  | MFN | 0 |  |  | 54 | 44328 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6341AGCE-20210114-01-R1Sander Truck F5503375 | AG Chapman Enterprises6341AGCE-20210114-01-R1Sander Truck F5503375AGCE-2021-01-30 | [5 empty] | 1 | 375 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6363 | AGCE-20210116-1 | 53511111 | Access | 0 | Sander Truck F550 | 125 | 3 | HR | 93.75 | 0 |  |  | 375 | 48.75 | 423.75 | 2021-01-16 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Sanding Trembley Flats road with treated sand | 11 |  | Trembley Flats Rd | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6363AGCE-20210116-1Sander Truck F5503375 | AG Chapman Enterprises6363AGCE-20210116-1Sander Truck F5503375AGCE-2021-01-30 | [5 empty] | 1 | 375 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6364 | AGCE-20210120-1 | 53511111 | Access | 0 | Sander Truck F550 | 125 | 6 | HR | 93.75 | 0 |  |  | 750 | 97.5 | 847.5 | 2021-01-20 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Sanding roads: Dore, Harbour. Note Chapman was told they had to use treated sand from reserve resources. | 11 |  | MFN - Harbour Rd 1, 2, 3, 4, 5 | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6364AGCE-20210120-1Sander Truck F5506750 | AG Chapman Enterprises6364AGCE-20210120-1Sander Truck F5506750AGCE-2021-01-30 | [5 empty] | 1 | 750 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6371 | AGCE-20210125-1 | 53511111 | Access | 0 | Sander Truck F550 | 125 | 6 | HR | 93.75 | 0 |  |  | 750 | 97.5 | 847.5 | 2021-01-25 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Plowe and sanded from the mission harbour road to the end of dore | 11 | F135-F160 | Habour Road 1, 2, 3, 4, 5, | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6371AGCE-20210125-1Sander Truck F5506750 | AG Chapman Enterprises6371AGCE-20210125-1Sander Truck F5506750AGCE-2021-01-30 | [5 empty] | 1 | 750 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6372 | AGCE-20210125-2 | 53511111 | Access | 0 | Sander Truck F550 | 125 | 4 | HR | 93.75 | 0 |  |  | 500 | 65 | 565 | 2021-01-25 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Alfred Chapman and Ryan MacIntyre, removed |  | Approved |  |  | Grade and sand Trembley Flats Road | 11 |  | Trembley Flats Road | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6372AGCE-20210125-2Sander Truck F5504500 | AG Chapman Enterprises6372AGCE-20210125-2Sander Truck F5504500AGCE-2021-01-30 | [5 empty] | 1 | 500 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6382 | AGCE-20210208-3 | 53511111 | Access | 0 | Sander Truck F550 | 125 | 5.5 | HR | 93.75 | 0 |  |  | 687.5 | 89.375 | 776.875 | 2021-02-08 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andy N |  | Approved |  |  | Sanded to KM 4 on Dore and Trembley | 11 |  | Dore Rd, Tremlbey Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6382AGCE-20210208-3Sander Truck F5505.5687.5 | AG Chapman Enterprises6382AGCE-20210208-3Sander Truck F5505.5687.5AGCE-2021-02-10 | [5 empty] | 1 | 687.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6385 | AGCE-20210209-3 | 53511111 | Access | 0 | Sander Truck F550 | 125 | 6 | HR | 93.75 | 0 |  |  | 750 | 97.5 | 847.5 | 2021-02-09 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andy N, not eligible |  | Approved |  |  | Plowed and sanded Harbour Rd, Trembley Rd, Dore Rd | 11 |  | Harbour Rd, Trembley Rd, Dore Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6385AGCE-20210209-3Sander Truck F5506750 | AG Chapman Enterprises6385AGCE-20210209-3Sander Truck F5506750AGCE-2021-02-10 | [5 empty] | 1 | 750 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6395 | AGCE-20210212-3 | 53511111 | Access | 0 | Sander Truck F550 | 125 | 6 | HR | 93.75 | 0 |  |  | 750 | 97.5 | 847.5 | 2021-02-12 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andy N Supervisor and truck removed |  | Approved |  |  | Sanding Dore Lake, Trembley, Harbour Rd's | 11 | F135-F160 | Dore Lake, Trembley, Harbour Rd's | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6395AGCE-20210212-3Sander Truck F5506750 | AG Chapman Enterprises6395AGCE-20210212-3Sander Truck F5506750AGCE-2021-02-11-20 | [5 empty] | 1 | 750 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6412 | AGCE-20210216-5 | 53511111 | Access | 0 | Sander Truck F550 | 125 | 6 | HR | 93.75 | 0 |  |  | 750 | 97.5 | 847.5 | 2021-02-16 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andy N Supervisor and truck removed |  | Approved |  |  | Sanded Trembley Rd, Harbour Rd and Dore Lake Rd | 11 | F149-F164 | Trembley Rd, Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6412AGCE-20210216-5Sander Truck F5506750 | AG Chapman Enterprises6412AGCE-20210216-5Sander Truck F5506750AGCE-2021-02-11-20 | [5 empty] | 1 | 750 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6427 | AGCE-20210219-8 | 53511111 | Access | 0 | Sander Truck F550 | 125 | 6 | HR | 93.75 | 0 |  |  | 750 | 97.5 | 847.5 | 2021-02-19 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | Supervisor and truck removed |  | Approved |  |  | Plowed and sanded Trembley Rd, Harbour Rd, Dore | 11 | F128-F164 | Trembley Rd, Harbour Rd, Dore | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6427AGCE-20210219-8Sander Truck F5506750 | AG Chapman Enterprises6427AGCE-20210219-8Sander Truck F5506750AGCE-2021-02-11-20 | [5 empty] | 1 | 750 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6457 | AGCE-20210226-01-R1 | 53511111 | Access | 0 | Sander Truck F550 | 125 | 6 | HR | 93.75 | 0 |  |  | 750 | 97.5 | 847.5 | 2021-02-26 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S, no LOA for Andy N |  | Approved |  |  | Grade and sand roads dore lake road - Trembley | 11 | F161 | Trembley Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6457AGCE-20210226-01-R1Sander Truck F5506750 | AG Chapman Enterprises6457AGCE-20210226-01-R1Sander Truck F5506750AGCE-2021-02-21-28 | [5 empty] | 1 | 750 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6508 | AGCE-20210306-01 | 53511111 | Access | 0 | Sander Truck F550 | 125 | 3 | HR | 93.75 | 0 |  |  | 375 | 48.75 | 423.75 | 2021-03-06 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | NO Loa for Andy N |  | Approved |  |  | Sand Roads Dore Lk Road to Harbour to Trembley Rd | 11 | F128--F160 | Trembley Rd - Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6508AGCE-20210306-01Sander Truck F5503375 | AG Chapman Enterprises6508AGCE-20210306-01Sander Truck F5503375AGCE-2021-03-01-10 | [5 empty] | 1 | 375 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6513 | AGCE-20210307-01 | 53511111 | Access | 0 | Sander Truck F550 | 125 | 3 | HR | 93.75 | 0 |  |  | 375 | 48.75 | 423.75 | 2021-03-07 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Sanded Rds Dore Lk - Harbour Rd - Trembley Rd | 11 | F128-F160 | Trembley Rd - Dore Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6513AGCE-20210307-01Sander Truck F5503375 | AG Chapman Enterprises6513AGCE-20210307-01Sander Truck F5503375AGCE-2021-03-01-10 | [5 empty] | 1 | 375 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7051 | AGCE-20210314-01 | 53511111 | Access | 0 | Sander Truck F550 | 125 | 3 | HR | 93.75 | 0 |  |  | 375 | 48.75 | 423.75 | 2021-03-14 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | No LOA for Andy Neyland No Loa for Alfed C |  | Approved |  |  | Grading and Sanding Harbour and trembley Rd, and Dore | 11 | F120-F160 | Harbour, Trembley, Dore | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7051AGCE-20210314-01Sander Truck F5503375 | AG Chapman Enterprises7051AGCE-20210314-01Sander Truck F5503375AGCE-2021-03-11-20 | [5 empty] | 1 | 375 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7055 | AGCE-20210315-01 | 53511111 | Access | 0 | Sander Truck F550 | 125 | 4.5 | HR | 93.75 | 0 |  |  | 562.5 | 73.125 | 635.625 | 2021-03-15 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | No LOA for Andy N |  | Approved |  |  | Grade and Sand Trembley Rd | 11 | F161-F164 | Trembley Road | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7055AGCE-20210315-01Sander Truck F5504.5562.5 | AG Chapman Enterprises7055AGCE-20210315-01Sander Truck F5504.5562.5AGCE-2021-03-11-20 | [5 empty] | 1 | 562.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7056 | AGCE-20210316-01 | 53511111 | Access | 0 | Sander Truck F550 | 125 | 4.5 | HR | 93.75 | 0 |  |  | 562.5 | 73.125 | 635.625 | 2021-03-16 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Sanding of harbour, trembley and dore | 11 | F135-F160 | Harbour, Trembley, Dore | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7056AGCE-20210316-01Sander Truck F5504.5562.5 | AG Chapman Enterprises7056AGCE-20210316-01Sander Truck F5504.5562.5AGCE-2021-03-11-20 | [5 empty] | 1 | 562.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6371 | AGCE-20210125-1 | 53511111 | Access | 0 | Plow Truck F550 | 125 | 6 | HR | 93.75 | 0 |  |  | 750 | 97.5 | 847.5 | 2021-01-25 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Plowe and sanded from the mission harbour road to the end of dore | 11 | F135-F160 | Habour Road 1, 2, 3, 4, 5, | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6371AGCE-20210125-1Plow Truck F5506750 | AG Chapman Enterprises6371AGCE-20210125-1Plow Truck F5506750AGCE-2021-01-30 | [5 empty] | 1 | 750 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6385 | AGCE-20210209-3 | 53511111 | Access | 0 | Plow Truck F550 | 125 | 5.5 | HR | 93.75 | 0 |  |  | 687.5 | 89.375 | 776.875 | 2021-02-09 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andy N, not eligible |  | Approved |  |  | Plowed and sanded Harbour Rd, Trembley Rd, Dore Rd | 11 |  | Harbour Rd, Trembley Rd, Dore Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6385AGCE-20210209-3Plow Truck F5505.5687.5 | AG Chapman Enterprises6385AGCE-20210209-3Plow Truck F5505.5687.5AGCE-2021-02-10 | [5 empty] | 1 | 687.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6427 | AGCE-20210219-8 | 53511111 | Access | 0 | Plow Truck F550 | 125 | 5.5 | HR | 93.75 | 0 |  |  | 687.5 | 89.375 | 776.875 | 2021-02-19 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | Supervisor and truck removed |  | Approved |  |  | Plowed and sanded Trembley Rd, Harbour Rd, Dore | 11 | F128-F164 | Trembley Rd, Harbour Rd, Dore | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6427AGCE-20210219-8Plow Truck F5505.5687.5 | AG Chapman Enterprises6427AGCE-20210219-8Plow Truck F5505.5687.5AGCE-2021-02-11-20 | [5 empty] | 1 | 687.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6061 | AGCE-20210205-1 | 53511111 | Access | 0 | Pickup | 21.94 | 3 | HR | 16.455 | 0 |  |  | 65.82 | 8.5566 | 74.3766 | 2021-02-05 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | This will need to be billed out through Kabi to capture escort time |  | Pending |  |  | Walk dozer from High Falls Rd to Michipicoten Habour Rd 4 | 11 | F150 | Harbour Rd 4 | 0 | [10 empty] | 11 | AG Chapman Enterprises6061AGCE-20210205-1Pickup365.82 | AG Chapman Enterprises6061AGCE-20210205-1Pickup365.82 | [5 empty] | 1 | 65.82 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6062 | AGCE-20210205-2 | 53511111 | Access | 0 | Pickup | 21.94 | 5.5 | HR | 16.455 | 0 |  |  | 120.67 | 15.6871 | 136.3571 | 2021-02-05 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Alfred C, not eligible, local |  | Approved |  |  | Winter Access Maint Grade wings and back on Dore Rd. | 11 | F135-F147 | Dore Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6062AGCE-20210205-2Pickup5.5120.67 | AG Chapman Enterprises6062AGCE-20210205-2Pickup5.5120.67AGCE-2021-02-10 | [5 empty] | 1 | 120.67 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6064 | AGCE-20210126-2 | 53511111 | Access | 0 | Pickup | 21.94 | 4.5 | HR | 16.455 | 0 |  |  | 98.73 | 12.8349 | 111.5649 | 2021-01-26 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Alfred Chapman, removed |  | Approved |  |  | Grade and wing back banks on Tremblay Flats Rd, Access roads F163 to F162 | 11 | F163, F162 | Trembley Flats Rd | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6064AGCE-20210126-2Pickup4.598.73 | AG Chapman Enterprises6064AGCE-20210126-2Pickup4.598.73AGCE-2021-01-30 | [5 empty] | 1 | 98.73 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6065 | AGCE-20210126-1 | 53511111 | Access | 0 | Pickup | 21.94 | 4 | HR | 16.455 | 0 |  |  | 87.76 | 11.4088 | 99.1688 | 2021-01-26 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Alfred Chapman, removed |  | Approved |  |  | Grade Dore Lake Road | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6065AGCE-20210126-1Pickup487.76 | AG Chapman Enterprises6065AGCE-20210126-1Pickup487.76AGCE-2021-01-30 | [5 empty] | 1 | 87.76 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6066 | AGCE-20210129-1 | 53511111 | Access | 0 | Pickup | 21.94 | 0.5 | HR | 16.455 | 0 |  |  | 10.97 | 1.4261 | 12.3961 | 2021-01-29 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andy N, removed |  | Approved |  |  | Sand michhipicoten turn off, Harbour Rd to Dore Lake Road | 11 | F135-F150 | Harbour Road / Dore Lake Road | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6066AGCE-20210129-1Pickup0.510.97 | AG Chapman Enterprises6066AGCE-20210129-1Pickup0.510.97AGCE-2021-01-30 | [5 empty] | 1 | 10.97 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6067 | AGCE-20210201-2 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-02-01 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andy N, not eligible, Local |  | Approved |  |  | Sanded roads: Michipicoten Harbour Rd, Dore Lake Road, Trembley Flats Rd | 11 | F160-F164 | Trembley Falls Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6067AGCE-20210201-2Pickup121.94 | AG Chapman Enterprises6067AGCE-20210201-2Pickup121.94AGCE-2021-02-10 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6341 | AGCE-20210114-01-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 7 | HR | 16.455 | 0 |  |  | 153.58 | 19.9654 | 173.5454 | 2021-01-29 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | Is treated sand in the contract? If not where are they getting it from? |  | Approved |  |  | Sanding Tremblay Flats road with treated sand. 2 TON treated sand. | 11 |  | MFN | 0 |  |  | 54 | 44328 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6341AGCE-20210114-01-R1Pickup7153.58 | AG Chapman Enterprises6341AGCE-20210114-01-R1Pickup7153.58AGCE-2021-01-30 | [5 empty] | 1 | 153.58 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6341 | AGCE-20210114-01-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-01-29 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | Is treated sand in the contract? If not where are they getting it from? |  | Approved |  |  | Sanding Tremblay Flats road with treated sand. 2 TON treated sand. | 11 |  | MFN | 0 |  |  | 54 | 44328 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6341AGCE-20210114-01-R1Pickup121.94 | AG Chapman Enterprises6341AGCE-20210114-01-R1Pickup121.94AGCE-2021-01-30 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6363 | AGCE-20210116-1 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-01-16 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Sanding Trembley Flats road with treated sand | 11 |  | Trembley Flats Rd | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6363AGCE-20210116-1Pickup121.94 | AG Chapman Enterprises6363AGCE-20210116-1Pickup121.94AGCE-2021-01-30 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6364 | AGCE-20210120-1 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-01-20 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Sanding roads: Dore, Harbour. Note Chapman was told they had to use treated sand from reserve resources. | 11 |  | MFN - Harbour Rd 1, 2, 3, 4, 5 | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6364AGCE-20210120-1Pickup121.94 | AG Chapman Enterprises6364AGCE-20210120-1Pickup121.94AGCE-2021-01-30 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6365 | AGCE-20210121-1 | 53511111 | Access | 0 | Pickup | 21.94 | 9 | HR | 16.455 | 0 |  |  | 197.46 | 25.6698 | 223.1298 | 2021-01-21 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA Phil S |  | Approved |  |  | D6 dozer clear Dore Lake Road 7 am to 4 pm. LOA for Phil Swanson | 11 | F149-F135 | Dore Lake Road | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6365AGCE-20210121-1Pickup9197.46 | AG Chapman Enterprises6365AGCE-20210121-1Pickup9197.46AGCE-2021-01-30 | [5 empty] | 1 | 197.46 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6365 | AGCE-20210121-1 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-01-21 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA Phil S |  | Approved |  |  | D6 dozer clear Dore Lake Road 7 am to 4 pm. LOA for Phil Swanson | 11 | F149-F135 | Dore Lake Road | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6365AGCE-20210121-1Pickup121.94 | AG Chapman Enterprises6365AGCE-20210121-1Pickup121.94AGCE-2021-01-30 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6367 | AGCE-20210121-2 | 53511111 | Access | 0 | Pickup | 21.94 | 3.5 | HR | 16.455 | 0 |  |  | 76.79 | 9.9827 | 86.7727 | 2021-01-21 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | 1 LOA on ticket for Robert Eshkibad |  | Approved |  |  | D6 clear road of snow, back blade and pack snow. | 11 | F146-F148 | Harbour Road 4 | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6367AGCE-20210121-2Pickup3.576.79 | AG Chapman Enterprises6367AGCE-20210121-2Pickup3.576.79AGCE-2021-01-30 | [5 empty] | 1 | 76.79 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6368 | AGCE-20210121-3 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-01-21 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | D6 clear snow and back blade | 11 | F155 | Harbour Road 3 | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6368AGCE-20210121-3Pickup121.94 | AG Chapman Enterprises6368AGCE-20210121-3Pickup121.94AGCE-2021-01-30 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6369 | AGCE-20210121-4 | 53511111 | Access | 0 | Pickup | 21.94 | 6 | HR | 16.455 | 0 |  |  | 131.64 | 17.1132 | 148.7532 | 2021-01-21 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | 1 LOA for Alfred Chapman, removed |  | Approved |  |  | Grade Trembley Flats Road 3 am to 9 am | 11 |  | Trembley Flats Road | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6369AGCE-20210121-4Pickup6131.64 | AG Chapman Enterprises6369AGCE-20210121-4Pickup6131.64AGCE-2021-01-30 | [5 empty] | 1 | 131.64 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6370 | AGCE-20210121-5 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-01-21 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | 1 LOA for Alfred Chapman, removed |  | Approved |  |  | Grade Road 5 F159-F160 | 11 | F159-F160 | Harbour Road 5 | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6370AGCE-20210121-5Pickup121.94 | AG Chapman Enterprises6370AGCE-20210121-5Pickup121.94AGCE-2021-01-30 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6372 | AGCE-20210125-2 | 53511111 | Access | 0 | Pickup | 21.94 | 4 | HR | 16.455 | 0 |  |  | 87.76 | 11.4088 | 99.1688 | 2021-01-25 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Alfred Chapman and Ryan MacIntyre, removed |  | Approved |  |  | Grade and sand Trembley Flats Road | 11 |  | Trembley Flats Road | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6372AGCE-20210125-2Pickup487.76 | AG Chapman Enterprises6372AGCE-20210125-2Pickup487.76AGCE-2021-01-30 | [5 empty] | 1 | 87.76 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6376 | AGCE-20210206-1 | 53511111 | Access | 0 | Pickup | 21.94 | 2 | HR | 16.455 | 0 |  |  | 43.88 | 5.7044 | 49.5844 | 2021-02-06 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S |  | Approved |  |  | Back Blade harbour rd 4 | 11 |  | Harbour Rd 4 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6376AGCE-20210206-1Pickup243.88 | AG Chapman Enterprises6376AGCE-20210206-1Pickup243.88AGCE-2021-02-10 | [5 empty] | 1 | 43.88 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6377 | AGCE-20210206-2 | 53511111 | Access | 0 | Pickup | 21.94 | 3 | HR | 16.455 | 0 |  |  | 65.82 | 8.5566 | 74.3766 | 2021-02-06 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Track Harbour Rd 2 | 11 |  | Harbour Rd 2 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6377AGCE-20210206-2Pickup365.82 | AG Chapman Enterprises6377AGCE-20210206-2Pickup365.82AGCE-2021-02-10 | [5 empty] | 1 | 65.82 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6377 | AGCE-20210206-2 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-02-06 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Track Harbour Rd 2 | 11 |  | Harbour Rd 2 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6377AGCE-20210206-2Pickup121.94 | AG Chapman Enterprises6377AGCE-20210206-2Pickup121.94AGCE-2021-02-10 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6380 | AGCE-20210208-1 | 53511111 | Access | 0 | Pickup | 21.94 | 5 | HR | 16.455 | 0 |  |  | 109.7 | 14.261 | 123.961 | 2021-02-08 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S |  | Approved |  |  | Walkk dzr from Harbour Rd 1 to Harbour Rd 2, plow and track rd | 11 | F150-F151 | Harbour Rd's | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6380AGCE-20210208-1Pickup5109.7 | AG Chapman Enterprises6380AGCE-20210208-1Pickup5109.7AGCE-2021-02-10 | [5 empty] | 1 | 109.7 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6380 | AGCE-20210208-1 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-02-08 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S |  | Approved |  |  | Walkk dzr from Harbour Rd 1 to Harbour Rd 2, plow and track rd | 11 | F150-F151 | Harbour Rd's | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6380AGCE-20210208-1Pickup121.94 | AG Chapman Enterprises6380AGCE-20210208-1Pickup121.94AGCE-2021-02-10 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6381 | AGCE-20210208-2 | 53511111 | Access | 0 | Pickup | 21.94 | 5.5 | HR | 16.455 | 0 |  |  | 120.67 | 15.6871 | 136.3571 | 2021-02-08 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Alfred C, not eligible, Local |  | Approved |  |  | Graded Trembley Rd | 11 |  | Trembley Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6381AGCE-20210208-2Pickup5.5120.67 | AG Chapman Enterprises6381AGCE-20210208-2Pickup5.5120.67AGCE-2021-02-10 | [5 empty] | 1 | 120.67 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6383 | AGCE-20210209-1 | 53511111 | Access | 0 | Pickup | 21.94 | 5.5 | HR | 16.455 | 0 |  |  | 120.67 | 15.6871 | 136.3571 | 2021-02-09 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S |  | Approved |  |  | Plowed and tracked Harb Rd 2 | 11 | F152-F154 | Harbour Rd 2 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6383AGCE-20210209-1Pickup5.5120.67 | AG Chapman Enterprises6383AGCE-20210209-1Pickup5.5120.67AGCE-2021-02-10 | [5 empty] | 1 | 120.67 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6383 | AGCE-20210209-1 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-02-09 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S |  | Approved |  |  | Plowed and tracked Harb Rd 2 | 11 | F152-F154 | Harbour Rd 2 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6383AGCE-20210209-1Pickup121.94 | AG Chapman Enterprises6383AGCE-20210209-1Pickup121.94AGCE-2021-02-10 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6386 | AGCE-20210210-1 | 53511111 | Access | 0 | Pickup | 21.94 | 9.5 | HR | 16.455 | 0 |  |  | 208.43 | 27.0959 | 235.5259 | 2021-02-10 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Open up and track Harbour Rd 1, 3, 4, 5 | 11 | F150-F160 | Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6386AGCE-20210210-1Pickup9.5208.43 | AG Chapman Enterprises6386AGCE-20210210-1Pickup9.5208.43AGCE-2021-02-10 | [5 empty] | 1 | 208.43 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6386 | AGCE-20210210-1 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-02-10 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Open up and track Harbour Rd 1, 3, 4, 5 | 11 | F150-F160 | Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6386AGCE-20210210-1Pickup121.94 | AG Chapman Enterprises6386AGCE-20210210-1Pickup121.94AGCE-2021-02-10 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6387 | AGCE-20210210-2 | 53511111 | Access | 0 | Pickup | 21.94 | 7 | HR | 16.455 | 0 |  |  | 153.58 | 19.9654 | 173.5454 | 2021-02-10 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D |  | Approved |  |  | Grade Harbour Rd 1, Dore Rd, | 11 |  | Harbour Rd 1, Dore Rd, | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6387AGCE-20210210-2Pickup7153.58 | AG Chapman Enterprises6387AGCE-20210210-2Pickup7153.58AGCE-2021-02-10 | [5 empty] | 1 | 153.58 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6388 | AGCE-20210210-3 | 53511111 | Access | 0 | Pickup | 21.94 | 4 | HR | 16.455 | 0 |  |  | 87.76 | 11.4088 | 99.1688 | 2021-02-10 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S |  | Approved |  |  | Plowed and tracked Harbour Rd | 11 | F152-F154 | Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6388AGCE-20210210-3Pickup487.76 | AG Chapman Enterprises6388AGCE-20210210-3Pickup487.76AGCE-2021-02-10 | [5 empty] | 1 | 87.76 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6389 | AGCE-20210211-1 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-02-11 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D |  | Approved |  |  | Graded Dore, Harbour Rd | 11 |  | Dore, Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6389AGCE-20210211-1Pickup121.94 | AG Chapman Enterprises6389AGCE-20210211-1Pickup121.94AGCE-2021-02-11-20 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6390 | AGCE-20210211-2 | 53511111 | Access | 0 | Pickup | 21.94 | 10 | HR | 16.455 | 0 |  |  | 219.4 | 28.522 | 247.922 | 2021-02-11 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Dan P, Removed supervisor and truck |  | Approved |  |  | Push back banks and pack roads | 11 |  | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6390AGCE-20210211-2Pickup10219.4 | AG Chapman Enterprises6390AGCE-20210211-2Pickup10219.4AGCE-2021-02-11-20 | [5 empty] | 1 | 219.4 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6392 | AGCE-20210211-4 | 53511111 | Access | 0 | Pickup | 21.94 | 11 | HR | 16.455 | 0 |  |  | 241.34 | 31.3742 | 272.7142 | 2021-02-11 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N Supervisor and truck removed |  | Approved |  |  | Open roads and parking at F150 | 11 | F150-F151 | Harbour Rd 1 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6392AGCE-20210211-4Pickup11241.34 | AG Chapman Enterprises6392AGCE-20210211-4Pickup11241.34AGCE-2021-02-11-20 | [5 empty] | 1 | 241.34 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6394 | AGCE-20210212-2 | 53511111 | Access | 0 | Pickup | 21.94 | 10 | HR | 16.455 | 0 |  |  | 219.4 | 28.522 | 247.922 | 2021-02-12 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Widen Roads Dore Lake and then float to Hensen Road | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6394AGCE-20210212-2Pickup10219.4 | AG Chapman Enterprises6394AGCE-20210212-2Pickup10219.4AGCE-2021-02-11-20 | [5 empty] | 1 | 219.4 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6394 | AGCE-20210212-2 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-02-12 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Widen Roads Dore Lake and then float to Hensen Road | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6394AGCE-20210212-2Pickup121.94 | AG Chapman Enterprises6394AGCE-20210212-2Pickup121.94AGCE-2021-02-11-20 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6396 | AGCE-20210213-1 | 53511111 | Access | 0 | Pickup | 21.94 | 12 | HR | 16.455 | 0 |  |  | 263.28 | 34.2264 | 297.5064 | 2021-02-13 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Cleared and wiiden Hensen Road | 11 | F119-F134 | Hensen Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6396AGCE-20210213-1Pickup12263.28 | AG Chapman Enterprises6396AGCE-20210213-1Pickup12263.28AGCE-2021-02-11-20 | [5 empty] | 1 | 263.28 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6397 | AGCE-20210213-2 | 53511111 | Access | 0 | Pickup | 21.94 | 9 | HR | 16.455 | 0 |  |  | 197.46 | 25.6698 | 223.1298 | 2021-02-13 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Cllear and widen Harbour Rd 3, 4, 5 | 11 |  | Harbour Rd 3, 4, 5 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6397AGCE-20210213-2Pickup9197.46 | AG Chapman Enterprises6397AGCE-20210213-2Pickup9197.46AGCE-2021-02-11-20 | [5 empty] | 1 | 197.46 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6398 | AGCE-20210213-3 | 53511111 | Access | 0 | Pickup | 21.94 | 8.5 | HR | 16.455 | 0 |  |  | 186.49 | 24.2437 | 210.7337 | 2021-02-13 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D Supervisor and truck removed |  | Approved |  |  | Grading Dore Rd, Trembley Rd, Harbour Rd | 11 | F119-F160 | Dore Lake Rd, Trembley Rd, Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6398AGCE-20210213-3Pickup8.5186.49 | AG Chapman Enterprises6398AGCE-20210213-3Pickup8.5186.49AGCE-2021-02-11-20 | [5 empty] | 1 | 186.49 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6399 | AGCE-20210213-4 | 53511111 | Access | 0 | Pickup | 21.94 | 11 | HR | 16.455 | 0 |  |  | 241.34 | 31.3742 | 272.7142 | 2021-02-13 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Widen Dore Lake Rd | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6399AGCE-20210213-4Pickup11241.34 | AG Chapman Enterprises6399AGCE-20210213-4Pickup11241.34AGCE-2021-02-11-20 | [5 empty] | 1 | 241.34 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6400 | AGCE-20210214-1 | 53511111 | Access | 0 | Pickup | 21.94 | 12 | HR | 16.455 | 0 |  |  | 263.28 | 34.2264 | 297.5064 | 2021-02-14 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Open up road and truck turnarounds Harbour Rd 2, 3, 4, 5 | 11 |  | Harbour Rd 2, 3, 4, 5 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6400AGCE-20210214-1Pickup12263.28 | AG Chapman Enterprises6400AGCE-20210214-1Pickup12263.28AGCE-2021-02-11-20 | [5 empty] | 1 | 263.28 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6400 | AGCE-20210214-1 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-02-14 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Open up road and truck turnarounds Harbour Rd 2, 3, 4, 5 | 11 |  | Harbour Rd 2, 3, 4, 5 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6400AGCE-20210214-1Pickup121.94 | AG Chapman Enterprises6400AGCE-20210214-1Pickup121.94AGCE-2021-02-11-20 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6401 | AGCE-20210214-2 | 53511111 | Access | 0 | Pickup | 21.94 | 11 | HR | 16.455 | 0 |  |  | 241.34 | 31.3742 | 272.7142 | 2021-02-14 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | No work description, may need to bill throough kabi | 11 |  | Dore Lake Rd E & W | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6401AGCE-20210214-2Pickup11241.34 | AG Chapman Enterprises6401AGCE-20210214-2Pickup11241.34AGCE-2021-02-11-20 | [5 empty] | 1 | 241.34 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6402 | AGCE-20210214-3 | 53511111 | Access | 0 | Pickup | 21.94 | 10 | HR | 16.455 | 0 |  |  | 219.4 | 28.522 | 247.922 | 2021-02-14 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C Supervisor and truck removed |  | Approved |  |  | Plow and open up roads Hensnen Rd | 11 | F119-F134 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6402AGCE-20210214-3Pickup10219.4 | AG Chapman Enterprises6402AGCE-20210214-3Pickup10219.4AGCE-2021-02-11-20 | [5 empty] | 1 | 219.4 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6405 | AGCE-20210215-2 | 53511111 | Access | 0 | Pickup | 21.94 | 12 | HR | 16.455 | 0 |  |  | 263.28 | 34.2264 | 297.5064 | 2021-02-15 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Clear roads and scrape ice Hensen Road | 11 | F112-F117 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6405AGCE-20210215-2Pickup12263.28 | AG Chapman Enterprises6405AGCE-20210215-2Pickup12263.28AGCE-2021-02-11-20 | [5 empty] | 1 | 263.28 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6405 | AGCE-20210215-2 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-02-15 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Clear roads and scrape ice Hensen Road | 11 | F112-F117 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6405AGCE-20210215-2Pickup121.94 | AG Chapman Enterprises6405AGCE-20210215-2Pickup121.94AGCE-2021-02-11-20 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6406 | AGCE-20210215-3 | 53511111 | Access | 0 | Pickup | 21.94 | 12 | HR | 16.455 | 0 |  |  | 263.28 | 34.2264 | 297.5064 | 2021-02-15 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E Supervisor and truck removed |  | Approved |  |  | Widen roads at F146-F149 Dore | 11 | F146-F149 | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6406AGCE-20210215-3Pickup12263.28 | AG Chapman Enterprises6406AGCE-20210215-3Pickup12263.28AGCE-2021-02-11-20 | [5 empty] | 1 | 263.28 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6407 | AGCE-20210215-4 | 53511111 | Access | 0 | Pickup | 21.94 | 10 | HR | 16.455 | 0 |  |  | 219.4 | 28.522 | 247.922 | 2021-02-15 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Dan P Supervisor and truck removed |  | Approved |  |  | Push snow on harbour rd 1 | 11 | F150-F151 | Harbour Rd 1 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6407AGCE-20210215-4Pickup10219.4 | AG Chapman Enterprises6407AGCE-20210215-4Pickup10219.4AGCE-2021-02-11-20 | [5 empty] | 1 | 219.4 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6409 | AGCE-20210216-2 | 53511111 | Access | 0 | Pickup | 21.94 | 12 | HR | 16.455 | 0 |  |  | 263.28 | 34.2264 | 297.5064 | 2021-02-16 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Widen roads Dore Lake East and West. | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6409AGCE-20210216-2Pickup12263.28 | AG Chapman Enterprises6409AGCE-20210216-2Pickup12263.28AGCE-2021-02-11-20 | [5 empty] | 1 | 263.28 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6411 | AGCE-20210216-4 | 53511111 | Access | 0 | Pickup | 21.94 | 6 | HR | 16.455 | 0 |  |  | 131.64 | 17.1132 | 148.7532 | 2021-02-16 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D Supervisor and truck removed |  | Approved |  |  | Grade Trembley Rd | 11 | F160-F164 | Trembley Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6411AGCE-20210216-4Pickup6131.64 | AG Chapman Enterprises6411AGCE-20210216-4Pickup6131.64AGCE-2021-02-11-20 | [5 empty] | 1 | 131.64 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6413 | AGCE-20210217-1 | 53511111 | Access | 0 | Pickup | 21.94 | 8 | HR | 16.455 | 0 |  |  | 175.52 | 22.8176 | 198.3376 | 2021-02-17 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Scott M |  | Approved |  |  | Back blade Habour Rd 2 | 11 | F152-F154 | Harbour Rd 2 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6413AGCE-20210217-1Pickup8175.52 | AG Chapman Enterprises6413AGCE-20210217-1Pickup8175.52AGCE-2021-02-11-20 | [5 empty] | 1 | 175.52 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6413 | AGCE-20210217-1 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-02-17 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Scott M |  | Approved |  |  | Back blade Habour Rd 2 | 11 | F152-F154 | Harbour Rd 2 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6413AGCE-20210217-1Pickup121.94 | AG Chapman Enterprises6413AGCE-20210217-1Pickup121.94AGCE-2021-02-11-20 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6414 | AGCE-20210217-2 | 53511111 | Access | 0 | Pickup | 21.94 | 11 | HR | 16.455 | 0 |  |  | 241.34 | 31.3742 | 272.7142 | 2021-02-17 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E Supervisor and truck removed |  | Approved |  |  | Plowed and widened Dore lake Rd | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6414AGCE-20210217-2Pickup11241.34 | AG Chapman Enterprises6414AGCE-20210217-2Pickup11241.34AGCE-2021-02-11-20 | [5 empty] | 1 | 241.34 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6415 | AGCE-20210217-3 | 53511111 | Access | 0 | Pickup | 21.94 | 9 | HR | 16.455 | 0 |  |  | 197.46 | 25.6698 | 223.1298 | 2021-02-17 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | Supervisor and truck removed |  | Approved |  |  | Plow roads at High Falls Rd 1 and 2 | 11 | F172-F211 | High Falls Road 1, 2 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6415AGCE-20210217-3Pickup9197.46 | AG Chapman Enterprises6415AGCE-20210217-3Pickup9197.46AGCE-2021-02-11-20 | [5 empty] | 1 | 197.46 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6416 | AGCE-20210217-4 | 53511111 | Access | 0 | Pickup | 21.94 | 11 | HR | 16.455 | 0 |  |  | 241.34 | 31.3742 | 272.7142 | 2021-02-17 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C Supervisor and truck removed |  | Approved |  |  | Scrape roads on Hensen | 11 | F118-F133 | Hensen Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6416AGCE-20210217-4Pickup11241.34 | AG Chapman Enterprises6416AGCE-20210217-4Pickup11241.34AGCE-2021-02-11-20 | [5 empty] | 1 | 241.34 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6417 | AGCE-20210217-5 | 53511111 | Access | 0 | Pickup | 21.94 | 8 | HR | 16.455 | 0 |  |  | 175.52 | 22.8176 | 198.3376 | 2021-02-17 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D Supervisor and truck removed |  | Approved |  |  | Grading High Falls Road 1, 2, 3, 5 | 11 | F172-F211 | High Falls Road 1, 2, 3, 5 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6417AGCE-20210217-5Pickup8175.52 | AG Chapman Enterprises6417AGCE-20210217-5Pickup8175.52AGCE-2021-02-11-20 | [5 empty] | 1 | 175.52 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6418 | AGCE-20210218-2 | 53511111 | Access | 0 | Pickup | 21.94 | 2 | HR | 16.455 | 0 |  |  | 43.88 | 5.7044 | 49.5844 | 2021-02-18 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Push snow on High Falls road | 11 | F172-F211 | High Falls Rd 1, 2, 3 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6418AGCE-20210218-2Pickup243.88 | AG Chapman Enterprises6418AGCE-20210218-2Pickup243.88AGCE-2021-02-11-20 | [5 empty] | 1 | 43.88 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6419 | AGCE-20210218-3 | 53511111 | Access | 0 | Pickup | 21.94 | 11 | HR | 16.455 | 0 |  |  | 241.34 | 31.3742 | 272.7142 | 2021-02-18 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E Supervisor and truck removed |  | Approved |  |  | Pushed out Dore Lake Rd and back bladed the turn around | 11 |  | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6419AGCE-20210218-3Pickup11241.34 | AG Chapman Enterprises6419AGCE-20210218-3Pickup11241.34AGCE-2021-02-11-20 | [5 empty] | 1 | 241.34 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6420 | AGCE-20210218-4 | 53511111 | Access | 0 | Pickup | 21.94 | 11 | HR | 16.455 | 0 |  |  | 241.34 | 31.3742 | 272.7142 | 2021-02-18 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C Supervisor and truck removed |  | Approved |  |  | Scraped Hensen Rd East | 11 | F117-F134 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6420AGCE-20210218-4Pickup11241.34 | AG Chapman Enterprises6420AGCE-20210218-4Pickup11241.34AGCE-2021-02-11-20 | [5 empty] | 1 | 241.34 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6422 | AGCE-20210219-1 | 53511111 | Access | 0 | Pickup | 21.94 | 11.5 | HR | 16.455 | 0 |  |  | 252.31 | 32.8003 | 285.1103 | 2021-02-19 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Back blade hills, widen rds, plowed to Km 6 | 11 |  | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6422AGCE-20210219-1Pickup11.5252.31 | AG Chapman Enterprises6422AGCE-20210219-1Pickup11.5252.31AGCE-2021-02-11-20 | [5 empty] | 1 | 252.31 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6422 | AGCE-20210219-1 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-02-19 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Back blade hills, widen rds, plowed to Km 6 | 11 |  | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6422AGCE-20210219-1Pickup121.94 | AG Chapman Enterprises6422AGCE-20210219-1Pickup121.94AGCE-2021-02-11-20 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6423 | AGCE-20210219-2 | 53511111 | Access | 0 | Pickup | 21.94 | 8 | HR | 16.455 | 0 |  |  | 175.52 | 22.8176 | 198.3376 | 2021-02-19 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N Supervisor and truck removed |  | Approved |  |  | Cleared all roads at Dore Lake | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6423AGCE-20210219-2Pickup8175.52 | AG Chapman Enterprises6423AGCE-20210219-2Pickup8175.52AGCE-2021-02-11-20 | [5 empty] | 1 | 175.52 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6424 | AGCE-20210219-3 | 53511111 | Access | 0 | Pickup | 21.94 | 7 | HR | 16.455 | 0 |  |  | 153.58 | 19.9654 | 173.5454 | 2021-02-19 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | Supervisor and truck removed |  | Approved |  |  | Push snow and clean up around bridges High Falls Rd 1, 2 F171 | 11 | F171 | High Falls Rd 1, 2 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6424AGCE-20210219-3Pickup7153.58 | AG Chapman Enterprises6424AGCE-20210219-3Pickup7153.58AGCE-2021-02-11-20 | [5 empty] | 1 | 153.58 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6425 | AGCE-20210219-4 | 53511111 | Access | 0 | Pickup | 21.94 | 11.5 | HR | 16.455 | 0 |  |  | 252.31 | 32.8003 | 285.1103 | 2021-02-19 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C Supervisor and truck removed |  | Approved |  |  | Scraped hensen rd | 11 | F117-F135 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6425AGCE-20210219-4Pickup11.5252.31 | AG Chapman Enterprises6425AGCE-20210219-4Pickup11.5252.31AGCE-2021-02-11-20 | [5 empty] | 1 | 252.31 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6426 | AGCE-20210219-5 | 53511111 | Access | 0 | Pickup | 21.94 | 4 | HR | 16.455 | 0 |  |  | 87.76 | 11.4088 | 99.1688 | 2021-02-19 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D Supervisor and truck removed |  | Approved |  |  | Grade harbour rd | 11 | F148-F159 | Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6426AGCE-20210219-5Pickup487.76 | AG Chapman Enterprises6426AGCE-20210219-5Pickup487.76AGCE-2021-02-11-20 | [5 empty] | 1 | 87.76 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6428 | AGCE-20210220-1 | 53511111 | Access | 0 | Pickup | 21.94 | 11.5 | HR | 16.455 | 0 |  |  | 252.31 | 32.8003 | 285.1103 | 2021-02-20 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Widen Dore Rd and clear turn arounds | 11 |  | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6428AGCE-20210220-1Pickup11.5252.31 | AG Chapman Enterprises6428AGCE-20210220-1Pickup11.5252.31AGCE-2021-02-11-20 | [5 empty] | 1 | 252.31 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6428 | AGCE-20210220-1 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-02-20 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Widen Dore Rd and clear turn arounds | 11 |  | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6428AGCE-20210220-1Pickup121.94 | AG Chapman Enterprises6428AGCE-20210220-1Pickup121.94AGCE-2021-02-11-20 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6429 | AGCE-20210220-2 | 53511111 | Access | 0 | Pickup | 21.94 | 9 | HR | 16.455 | 0 |  |  | 197.46 | 25.6698 | 223.1298 | 2021-02-20 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Dan P Supervisor and truck removed |  | Approved |  |  | Push snow on High Falls Rd | 11 | F172-F211 | High Falls Road 1, 2, 3 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6429AGCE-20210220-2Pickup9197.46 | AG Chapman Enterprises6429AGCE-20210220-2Pickup9197.46AGCE-2021-02-11-20 | [5 empty] | 1 | 197.46 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6430 | AGCE-20210220-4 | 53511111 | Access | 0 | Pickup | 21.94 | 11 | HR | 16.455 | 0 |  |  | 241.34 | 31.3742 | 272.7142 | 2021-02-20 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C Supervisor and truck removed |  | Approved |  |  | Scraped road on Hensen E | 11 | F115-F133 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6430AGCE-20210220-4Pickup11241.34 | AG Chapman Enterprises6430AGCE-20210220-4Pickup11241.34AGCE-2021-02-11-20 | [5 empty] | 1 | 241.34 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6431 | AGCE-20210221-1 | 53511111 | Access | 0 | Pickup | 21.94 | 8 | HR | 16.455 | 0 |  |  | 175.52 | 22.8176 | 198.3376 | 2021-02-21 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Push snow on Harbour Rd 2 | 11 | F150-F157 | Harbour Rd 2 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6431AGCE-20210221-1Pickup8175.52 | AG Chapman Enterprises6431AGCE-20210221-1Pickup8175.52AGCE-2021-02-21-28 | [5 empty] | 1 | 175.52 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6431 | AGCE-20210221-1 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-02-21 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Push snow on Harbour Rd 2 | 11 | F150-F157 | Harbour Rd 2 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6431AGCE-20210221-1Pickup121.94 | AG Chapman Enterprises6431AGCE-20210221-1Pickup121.94AGCE-2021-02-21-28 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6432 | AGCE-20210221-2 | 53511111 | Access | 0 | Pickup | 21.94 | 12 | HR | 16.455 | 0 |  |  | 263.28 | 34.2264 | 297.5064 | 2021-02-21 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C Superviosr and truck removed |  | Approved |  |  | Scraped Hensen Rd | 11 | F117-F133 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6432AGCE-20210221-2Pickup12263.28 | AG Chapman Enterprises6432AGCE-20210221-2Pickup12263.28AGCE-2021-02-21-28 | [5 empty] | 1 | 263.28 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6433 | AGCE-20210221-3 | 53511111 | Access | 0 | Pickup | 21.94 | 12 | HR | 16.455 | 0 |  |  | 263.28 | 34.2264 | 297.5064 | 2021-02-21 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E Supervisor and truck removed |  | Approved |  |  | push snow from Km 6 to Km 9.5 Dore Rd | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6433AGCE-20210221-3Pickup12263.28 | AG Chapman Enterprises6433AGCE-20210221-3Pickup12263.28AGCE-2021-02-21-28 | [5 empty] | 1 | 263.28 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6434 | AGCE-20210222-1 | 53511111 | Access | 0 | Pickup | 21.94 | 11 | HR | 16.455 | 0 |  |  | 241.34 | 31.3742 | 272.7142 | 2021-02-22 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Plowing High Falls Rd | 11 | F172-F211 | High Falls Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6434AGCE-20210222-1Pickup11241.34 | AG Chapman Enterprises6434AGCE-20210222-1Pickup11241.34AGCE-2021-02-21-28 | [5 empty] | 1 | 241.34 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6434 | AGCE-20210222-1 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-02-22 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Plowing High Falls Rd | 11 | F172-F211 | High Falls Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6434AGCE-20210222-1Pickup121.94 | AG Chapman Enterprises6434AGCE-20210222-1Pickup121.94AGCE-2021-02-21-28 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6436 | AGCE-20210223-2 | 53511111 | Access | 0 | Pickup | 21.94 | 10 | HR | 16.455 | 0 |  |  | 219.4 | 28.522 | 247.922 | 2021-02-23 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Steve B Supervisor and truck removed |  | Approved |  |  | Cleaned and plowed Dore Lake Rd | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6436AGCE-20210223-2Pickup10219.4 | AG Chapman Enterprises6436AGCE-20210223-2Pickup10219.4AGCE-2021-02-21-28 | [5 empty] | 1 | 219.4 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6437 | AGCE-20210223-3 | 53511111 | Access | 0 | Pickup | 21.94 | 11 | HR | 16.455 | 0 |  |  | 241.34 | 31.3742 | 272.7142 | 2021-02-23 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E Supervisor and truck removed |  | Approved |  |  | Plowed Dore Lake Rd | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6437AGCE-20210223-3Pickup11241.34 | AG Chapman Enterprises6437AGCE-20210223-3Pickup11241.34AGCE-2021-02-21-28 | [5 empty] | 1 | 241.34 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6438 | AGCE-20210223-4 | 53511111 | Access | 0 | Pickup | 21.94 | 10.5 | HR | 16.455 | 0 |  |  | 230.37 | 29.9481 | 260.3181 | 2021-02-23 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S Supervisor and truck removed |  | Approved |  |  | Grade Trembley Rd, Harbour Rd, Dore Lake Rd | 11 | F128-F164 | Trembley Road, Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6438AGCE-20210223-4Pickup10.5230.37 | AG Chapman Enterprises6438AGCE-20210223-4Pickup10.5230.37AGCE-2021-02-21-28 | [5 empty] | 1 | 230.37 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6439 | AGCE-20210223-5 | 53511111 | Access | 0 | Pickup | 21.94 | 10 | HR | 16.455 | 0 |  |  | 219.4 | 28.522 | 247.922 | 2021-02-23 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N Supervisor and truck removed |  | Approved |  |  | Pow and widen Harbour Rd and Dore Lake Rd | 11 |  | Dore Lake Rd, Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6439AGCE-20210223-5Pickup10219.4 | AG Chapman Enterprises6439AGCE-20210223-5Pickup10219.4AGCE-2021-02-21-28 | [5 empty] | 1 | 219.4 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6440 | AGCE-20210223-6 | 53511111 | Access | 0 | Pickup | 21.94 | 13.5 | HR | 16.455 | 0 |  |  | 296.19 | 38.5047 | 334.6947 | 2021-02-23 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C Supervisor and truck removed |  | Approved |  |  | Scraped Hensen Rd East | 11 | F115-F133 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6440AGCE-20210223-6Pickup13.5296.19 | AG Chapman Enterprises6440AGCE-20210223-6Pickup13.5296.19AGCE-2021-02-21-28 | [5 empty] | 1 | 296.19 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6441 | AGCE-20210223-7 | 53511111 | Access | 0 | Pickup | 21.94 | 2.5 | HR | 16.455 | 0 |  |  | 54.85 | 7.1305 | 61.9805 | 2021-02-23 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Plow Dore Road and fix road surface | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6441AGCE-20210223-7Pickup2.554.85 | AG Chapman Enterprises6441AGCE-20210223-7Pickup2.554.85AGCE-2021-02-21-28 | [5 empty] | 1 | 54.85 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6442 | AGCE-20210223-8 | 53511111 | Access | 0 | Pickup | 21.94 | 9 | HR | 16.455 | 0 |  |  | 197.46 | 25.6698 | 223.1298 | 2021-02-23 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andrew B Supervisor and truck removed |  | Approved |  |  | Plow and level off roads on Dore Lake Rd | 11 | F135-F149 | Dore Lake Rd East | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6442AGCE-20210223-8Pickup9197.46 | AG Chapman Enterprises6442AGCE-20210223-8Pickup9197.46AGCE-2021-02-21-28 | [5 empty] | 1 | 197.46 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6443 | AGCE-20210223-9 | 53511111 | Access | 0 | Pickup | 21.94 | 6 | HR | 16.455 | 0 |  |  | 131.64 | 17.1132 | 148.7532 | 2021-02-23 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Plowed road and fixed holes | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6443AGCE-20210223-9Pickup6131.64 | AG Chapman Enterprises6443AGCE-20210223-9Pickup6131.64AGCE-2021-02-21-28 | [5 empty] | 1 | 131.64 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6445 | AGCE-20210224-01-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 7.5 | HR | 16.455 | 0 |  |  | 164.55 | 21.3915 | 185.9415 | 2021-02-24 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D |  | Approved |  |  | Graded Trembley rd to Harbour rd 1 | 11 | F128-F164 | Trembley Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6445AGCE-20210224-01-R1Pickup7.5164.55 | AG Chapman Enterprises6445AGCE-20210224-01-R1Pickup7.5164.55AGCE-2021-02-21-28 | [5 empty] | 1 | 164.55 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6446 | AGCE-20210224-02-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 12.5 | HR | 16.455 | 0 |  |  | 274.25 | 35.6525 | 309.9025 | 2021-02-24 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | back Blade and touch up michtpicoten Harbour roads 1234 | 11 | F150-F159 | Harbour Roads | 0 |  |  | 54 | 44252 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6446AGCE-20210224-02-R1Pickup12.5274.25 | AG Chapman Enterprises6446AGCE-20210224-02-R1Pickup12.5274.25AGCE-2021-02-21-28 | [5 empty] | 1 | 274.25 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6447 | AGCE-20210224-03 | 53511111 | Access | 0 | Pickup | 21.94 | 10 | HR | 16.455 | 0 |  |  | 219.4 | 28.522 | 247.922 | 2021-02-24 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | Supervisor removed |  | Approved |  |  | Plowed to F187 access to tower site Road 9 access, F206, F207, F208 | 11 | F206-F209 | High Falls | 0 |  |  | 54 | 44252 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6447AGCE-20210224-03Pickup10219.4 | AG Chapman Enterprises6447AGCE-20210224-03Pickup10219.4AGCE-2021-02-21-28 | [5 empty] | 1 | 219.4 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6450 | AGCE-20210224-05 | 53511111 | Access | 0 | Pickup | 21.94 | 12 | HR | 16.455 | 0 |  |  | 263.28 | 34.2264 | 297.5064 | 2021-02-24 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Plowed Dore Lake Rd 8.5 KM west to end of road | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 54 | 44252 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6450AGCE-20210224-05Pickup12263.28 | AG Chapman Enterprises6450AGCE-20210224-05Pickup12263.28AGCE-2021-02-21-28 | [5 empty] | 1 | 263.28 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6452 | AGCE-20210225-01-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 11.5 | HR | 16.455 | 0 |  |  | 252.31 | 32.8003 | 285.1103 | 2021-02-25 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Scrape and widen roads in Hensen | 11 | F117-F133 | Hensen Rd | 0 |  |  | 54 | 44345 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6452AGCE-20210225-01-R1Pickup11.5252.31 | AG Chapman Enterprises6452AGCE-20210225-01-R1Pickup11.5252.31AGCE-2021-02-21-28 | [5 empty] | 1 | 252.31 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6453 | AGCE-20210225-03 | 53511111 | Access | 0 | Pickup | 21.94 | 11 | HR | 16.455 | 0 |  |  | 241.34 | 31.3742 | 272.7142 | 2021-02-25 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Stephen B |  | Approved |  |  | Clean snow off road and fix up hill. | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 54 | 44345 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6453AGCE-20210225-03Pickup11241.34 | AG Chapman Enterprises6453AGCE-20210225-03Pickup11241.34AGCE-2021-02-21-28 | [5 empty] | 1 | 241.34 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6454 | AGCE-20210225-04 | 53511111 | Access | 0 | Pickup | 21.94 | 11.5 | HR | 16.455 | 0 |  |  | 252.31 | 32.8003 | 285.1103 | 2021-02-25 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Plowed and widened harbour rd 1, 2 ,3 ,4 5 | 11 | F150-F159 | Harbour Rd | 0 |  |  | 54 | 44345 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6454AGCE-20210225-04Pickup11.5252.31 | AG Chapman Enterprises6454AGCE-20210225-04Pickup11.5252.31AGCE-2021-02-21-28 | [5 empty] | 1 | 252.31 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6455 | AGCE-20210225-05 | 53511111 | Access | 1 | Pickup | 21.94 | 11.5 | HR | 16.455 | 0 |  |  | 252.31 | 32.8003 | 285.1103 | 2021-02-25 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andrew B |  | Approved |  |  | Plowed Dore lake Rd | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 54 | 44345 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6455AGCE-20210225-05Pickup11.5252.31 | AG Chapman Enterprises6455AGCE-20210225-05Pickup11.5252.31AGCE-2021-02-21-28 | [5 empty] | 1 | 252.31 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6456 | AGCE-20210225-02 | 53511111 | Access | 0 | Pickup | 21.94 | 9.5 | HR | 16.455 | 0 |  |  | 208.43 | 27.0959 | 235.5259 | 2021-02-25 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Back blade to Dore west | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 54 | 44345 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6456AGCE-20210225-02Pickup9.5208.43 | AG Chapman Enterprises6456AGCE-20210225-02Pickup9.5208.43AGCE-2021-02-21-28 | [5 empty] | 1 | 208.43 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6457 | AGCE-20210226-01-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 8.5 | HR | 16.455 | 0 |  |  | 186.49 | 24.2437 | 210.7337 | 2021-02-26 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S, no LOA for Andy N |  | Approved |  |  | Grade and sand roads dore lake road - Trembley | 11 | F161 | Trembley Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6457AGCE-20210226-01-R1Pickup8.5186.49 | AG Chapman Enterprises6457AGCE-20210226-01-R1Pickup8.5186.49AGCE-2021-02-21-28 | [5 empty] | 1 | 186.49 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6458 | AGCE-20210226-02-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 12 | HR | 16.455 | 0 |  |  | 263.28 | 34.2264 | 297.5064 | 2021-02-26 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Scrape and repair Hensen rd | 11 | F119-F134 | Hensen Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6458AGCE-20210226-02-R1Pickup12263.28 | AG Chapman Enterprises6458AGCE-20210226-02-R1Pickup12263.28AGCE-2021-02-21-28 | [5 empty] | 1 | 263.28 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6459 | AGCE-20210226-03-R1 | 53511111 | Access | 1 | Pickup | 21.94 | 12 | HR | 16.455 | 0 |  |  | 263.28 | 34.2264 | 297.5064 | 2021-02-26 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andrew B |  | Approved |  |  | Touch and plow rds on Dore Lake Rd | 11 | F135-F149 | Dore lake Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6459AGCE-20210226-03-R1Pickup12263.28 | AG Chapman Enterprises6459AGCE-20210226-03-R1Pickup12263.28AGCE-2021-02-21-28 | [5 empty] | 1 | 263.28 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6461 | AGCE-20210226-05-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 12 | HR | 16.455 | 0 |  |  | 263.28 | 34.2264 | 297.5064 | 2021-02-26 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Ploe and push back bank on Dore Lake Rd | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6461AGCE-20210226-05-R1Pickup12263.28 | AG Chapman Enterprises6461AGCE-20210226-05-R1Pickup12263.28AGCE-2021-02-21-28 | [5 empty] | 1 | 263.28 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6462 | AGCE-20210226-06-R1 | 53511111 | Access | 1 | Pickup | 21.94 | 11 | HR | 16.455 | 0 |  |  | 241.34 | 31.3742 | 272.7142 | 2021-02-26 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Stephen B |  | Approved |  |  | Clean and fix Dore Lake Road | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6462AGCE-20210226-06-R1Pickup11241.34 | AG Chapman Enterprises6462AGCE-20210226-06-R1Pickup11241.34AGCE-2021-02-21-28 | [5 empty] | 1 | 241.34 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6463 | AGCE-20210226-07-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 8 | HR | 16.455 | 0 |  |  | 175.52 | 22.8176 | 198.3376 | 2021-02-26 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | No LOA for Dan P |  | Approved |  |  | Pushed snow on High Falls Rd | 11 | F172-F211 | High Falls Road | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6463AGCE-20210226-07-R1Pickup8175.52 | AG Chapman Enterprises6463AGCE-20210226-07-R1Pickup8175.52AGCE-2021-02-21-28 | [5 empty] | 1 | 175.52 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6465 | AGCE-20210227-02-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-02-27 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Dan P Remove shuttle charges for Katrina Adams, |  | Approved |  |  | Clear Rd and fix, track rd, | 11 | F150-F159 | Harbour Rd 4 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6465AGCE-20210227-02-R1Pickup121.94 | AG Chapman Enterprises6465AGCE-20210227-02-R1Pickup121.94AGCE-2021-02-21-28 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6466 | AGCE-20210227-03-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 12 | HR | 16.455 | 0 |  |  | 263.28 | 34.2264 | 297.5064 | 2021-02-27 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Back blade and push snow. | 11 | F172-F211 | Harbour Rd 1 - 5 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6466AGCE-20210227-03-R1Pickup12263.28 | AG Chapman Enterprises6466AGCE-20210227-03-R1Pickup12263.28AGCE-2021-02-21-28 | [5 empty] | 1 | 263.28 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6467 | AGCE-20210227-04-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 10.5 | HR | 16.455 | 0 |  |  | 230.37 | 29.9481 | 260.3181 | 2021-02-27 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Greg B Loa for Stephen B |  | Approved |  |  | Fix roads and back blade Dore Lake Rd | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6467AGCE-20210227-04-R1Pickup10.5230.37 | AG Chapman Enterprises6467AGCE-20210227-04-R1Pickup10.5230.37AGCE-2021-02-21-28 | [5 empty] | 1 | 230.37 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6467 | AGCE-20210227-04-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 12 | HR | 16.455 | 0 |  |  | 263.28 | 34.2264 | 297.5064 | 2021-02-27 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Greg B Loa for Stephen B |  | Approved |  |  | Fix roads and back blade Dore Lake Rd | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6467AGCE-20210227-04-R1Pickup12263.28 | AG Chapman Enterprises6467AGCE-20210227-04-R1Pickup12263.28AGCE-2021-02-21-28 | [5 empty] | 1 | 263.28 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6469 | AGCE-20210227-06-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 12 | HR | 16.455 | 0 |  |  | 263.28 | 34.2264 | 297.5064 | 2021-02-27 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | Mike Woods LOA |  | Approved |  |  | Plow roads dore east | 11 | F135-F149 | Dore lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6469AGCE-20210227-06-R1Pickup12263.28 | AG Chapman Enterprises6469AGCE-20210227-06-R1Pickup12263.28AGCE-2021-02-21-28 | [5 empty] | 1 | 263.28 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6470 | AGCE-20210228-01-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 12 | HR | 16.455 | 0 |  |  | 263.28 | 34.2264 | 297.5064 | 2021-02-28 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Push snow and repair Hills, scrape and fix dore, Plow road and clear parking spots | 11 | F135-F149 | Dore lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6470AGCE-20210228-01-R1Pickup12263.28 | AG Chapman Enterprises6470AGCE-20210228-01-R1Pickup12263.28AGCE-2021-02-21-28 | [5 empty] | 1 | 263.28 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6470 | AGCE-20210228-01-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 12 | HR | 16.455 | 0 |  |  | 263.28 | 34.2264 | 297.5064 | 2021-02-28 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Push snow and repair Hills, scrape and fix dore, Plow road and clear parking spots | 11 | F135-F149 | Dore lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6470AGCE-20210228-01-R1Pickup12263.28 | AG Chapman Enterprises6470AGCE-20210228-01-R1Pickup12263.28AGCE-2021-02-21-28 | [5 empty] | 1 | 263.28 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6471 | AGCE-20210228-02-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 12 | HR | 16.455 | 0 |  |  | 263.28 | 34.2264 | 297.5064 | 2021-02-28 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Mike W |  | Approved |  |  | Creape roads and push snow Hensen Rd | 11 | F119-F134 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6471AGCE-20210228-02-R1Pickup12263.28 | AG Chapman Enterprises6471AGCE-20210228-02-R1Pickup12263.28AGCE-2021-02-21-28 | [5 empty] | 1 | 263.28 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6473 | AGCE-20210301-01-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 12 | HR | 16.455 | 0 |  |  | 263.28 | 34.2264 | 297.5064 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Mike W |  | Approved |  |  | Push snow to km 5 on Hensen rd | 11 | F119-F135 | Hensen Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6473AGCE-20210301-01-R1Pickup12263.28 | AG Chapman Enterprises6473AGCE-20210301-01-R1Pickup12263.28AGCE-2021-03-01-10 | [5 empty] | 1 | 263.28 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6474 | AGCE-20210301-02-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 5 | HR | 16.455 | 0 |  |  | 109.7 | 14.261 | 123.961 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Joe B |  | Approved |  |  | Grade Dore LK Rd to to Km 4 | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6474AGCE-20210301-02-R1Pickup5109.7 | AG Chapman Enterprises6474AGCE-20210301-02-R1Pickup5109.7AGCE-2021-03-01-10 | [5 empty] | 1 | 109.7 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6476 | AGCE-20210301-04-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 11.5 | HR | 16.455 | 0 |  |  | 252.31 | 32.8003 | 285.1103 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert M |  | Approved |  |  | Plowed roads on Dore Lk Rd | 11 | F1353-F149 | Dore Lake Road | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6476AGCE-20210301-04-R1Pickup11.5252.31 | AG Chapman Enterprises6476AGCE-20210301-04-R1Pickup11.5252.31AGCE-2021-03-01-10 | [5 empty] | 1 | 252.31 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6477 | AGCE-20210301-05-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 11.5 | HR | 16.455 | 0 |  |  | 252.31 | 32.8003 | 285.1103 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | NO LOA for Dan P |  | Approved |  |  | Pushed snow on Harbour Rd 4 | 11 | F156-F158 | Harbour Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6477AGCE-20210301-05-R1Pickup11.5252.31 | AG Chapman Enterprises6477AGCE-20210301-05-R1Pickup11.5252.31AGCE-2021-03-01-10 | [5 empty] | 1 | 252.31 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6479 | AGCE-20210301-05.1-R1 | 53511111 | Access | 1 | Pickup | 21.94 | 11.5 | HR | 16.455 | 0 |  |  | 252.31 | 32.8003 | 285.1103 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Back Blade Rds on Dore | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6479AGCE-20210301-05.1-R1Pickup11.5252.31 | AG Chapman Enterprises6479AGCE-20210301-05.1-R1Pickup11.5252.31AGCE-2021-03-01-10 | [5 empty] | 1 | 252.31 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6480 | AGCE-20210301-06-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 11.5 | HR | 16.455 | 0 |  |  | 252.31 | 32.8003 | 285.1103 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Ben R |  | Approved |  |  | Push snow and clean turn arounds on Dore lk rd | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6480AGCE-20210301-06-R1Pickup11.5252.31 | AG Chapman Enterprises6480AGCE-20210301-06-R1Pickup11.5252.31AGCE-2021-03-01-10 | [5 empty] | 1 | 252.31 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6481 | AGCE-20210301-07-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 11.5 | HR | 16.455 | 0 |  |  | 252.31 | 32.8003 | 285.1103 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N LOA for Alfred C Same dozer billed 14.5 hours, might have been partial night shift |  | Approved |  |  | Plow Harbour Rd 1, 2, 3 and fix hills, partial night shift for dozer | 11 |  | Harbour Rd 1, 2, 3 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6481AGCE-20210301-07-R1Pickup11.5252.31 | AG Chapman Enterprises6481AGCE-20210301-07-R1Pickup11.5252.31AGCE-2021-03-01-10 | [5 empty] | 1 | 252.31 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6485 | AGCE-20210302-04-R1 | 53511111 | Access | 1 | Pickup | 21.94 | 11.5 | HR | 16.455 | 0 |  |  | 252.31 | 32.8003 | 285.1103 | 2021-03-02 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Paul K |  | Approved |  |  | Back blade Dore Lk Rd West to east | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6485AGCE-20210302-04-R1Pickup11.5252.31 | AG Chapman Enterprises6485AGCE-20210302-04-R1Pickup11.5252.31AGCE-2021-03-01-10 | [5 empty] | 1 | 252.31 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6487 | AGCE-20210302-06-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 8.5 | HR | 16.455 | 0 |  |  | 186.49 | 24.2437 | 210.7337 | 2021-03-02 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | No LOA for Dan P |  | Approved |  |  | Pushing snow on Harbour Rd. | 11 | F155-F160 | Harbour Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6487AGCE-20210302-06-R1Pickup8.5186.49 | AG Chapman Enterprises6487AGCE-20210302-06-R1Pickup8.5186.49AGCE-2021-03-01-10 | [5 empty] | 1 | 186.49 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6489 | AGCE-20210302-08-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 11.5 | HR | 16.455 | 0 |  |  | 252.31 | 32.8003 | 285.1103 | 2021-03-02 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Wided roads and clear parking | 11 | F150-F159 | Harbour Rd 1, 2 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6489AGCE-20210302-08-R1Pickup11.5252.31 | AG Chapman Enterprises6489AGCE-20210302-08-R1Pickup11.5252.31AGCE-2021-03-01-10 | [5 empty] | 1 | 252.31 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6495 | AGCE-20210303-06-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 11.5 | HR | 16.455 | 0 |  |  | 252.31 | 32.8003 | 285.1103 | 2021-03-03 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Joe B |  | Approved |  |  | Graded roads in harbour to dore km 1 to km 4.5 | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6495AGCE-20210303-06-R1Pickup11.5252.31 | AG Chapman Enterprises6495AGCE-20210303-06-R1Pickup11.5252.31AGCE-2021-03-01-10 | [5 empty] | 1 | 252.31 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6496 | AGCE-20210303-07-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 8 | HR | 16.455 | 0 |  |  | 175.52 | 22.8176 | 198.3376 | 2021-03-03 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | No LOA for Dan P |  | Approved |  |  | Plow roads at harbour rd 4, 5 | 11 | F156-F160 | Harbour Rd 4, 5 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6496AGCE-20210303-07-R1Pickup8175.52 | AG Chapman Enterprises6496AGCE-20210303-07-R1Pickup8175.52AGCE-2021-03-01-10 | [5 empty] | 1 | 175.52 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6497 | AGCE-20210303-08-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 11.5 | HR | 16.455 | 0 |  |  | 252.31 | 32.8003 | 285.1103 | 2021-03-03 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Maint and fix rds on Harbour rd 1, 2 | 11 | F150-F154 | Harbour Rd 1,2 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6497AGCE-20210303-08-R1Pickup11.5252.31 | AG Chapman Enterprises6497AGCE-20210303-08-R1Pickup11.5252.31AGCE-2021-03-01-10 | [5 empty] | 1 | 252.31 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6498 | AGCE-20210303-09-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 11.5 | HR | 16.455 | 0 |  |  | 252.31 | 32.8003 | 285.1103 | 2021-03-03 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert M |  | Approved |  |  | Maint rd on Dore Lk | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6498AGCE-20210303-09-R1Pickup11.5252.31 | AG Chapman Enterprises6498AGCE-20210303-09-R1Pickup11.5252.31AGCE-2021-03-01-10 | [5 empty] | 1 | 252.31 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6499 | AGCE-20210303-10-R1 | 53511111 | Access | 0 | Pickup | 21.94 | 11.5 | HR | 16.455 | 0 |  |  | 252.31 | 32.8003 | 285.1103 | 2021-03-03 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Greg B |  | Approved |  |  | Plowed and did regular rd maint on Dore Lk Rd | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6499AGCE-20210303-10-R1Pickup11.5252.31 | AG Chapman Enterprises6499AGCE-20210303-10-R1Pickup11.5252.31AGCE-2021-03-01-10 | [5 empty] | 1 | 252.31 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6501 | AGCE-20210304-05-R1 | 53511111 | Access | 1 | Pickup | 21.94 | 11.5 | HR | 16.455 | 0 |  |  | 252.31 | 32.8003 | 285.1103 | 2021-03-04 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E LOA for Paul K |  | Approved |  |  | Reg Rd maint and repair on dore | 11 | F135-F149 | Dore lake Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6501AGCE-20210304-05-R1Pickup11.5252.31 | AG Chapman Enterprises6501AGCE-20210304-05-R1Pickup11.5252.31AGCE-2021-03-01-10 | [5 empty] | 1 | 252.31 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6501 | AGCE-20210304-05-R1 | 53511111 | Access | 1 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-03-04 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E LOA for Paul K |  | Approved |  |  | Reg Rd maint and repair on dore | 11 | F135-F149 | Dore lake Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6501AGCE-20210304-05-R1Pickup121.94 | AG Chapman Enterprises6501AGCE-20210304-05-R1Pickup121.94AGCE-2021-03-01-10 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6505 | AGCE-20210305-01 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-03-05 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Joe B |  | Approved |  |  | Dozing abnd back blading the road HR 4 | 11 | F154 | Harbour Rd 4 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6505AGCE-20210305-01Pickup121.94 | AG Chapman Enterprises6505AGCE-20210305-01Pickup121.94AGCE-2021-03-01-10 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6511 | AGCE-20210306-04 | 53511111 | Access | 0 | Pickup | 21.94 | 3 | HR | 16.455 | 0 |  |  | 65.82 | 8.5566 | 74.3766 | 2021-03-06 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Walk dozer out to be floated awat, Pick up eco diesel | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6511AGCE-20210306-04Pickup365.82 | AG Chapman Enterprises6511AGCE-20210306-04Pickup365.82AGCE-2021-03-01-10 | [5 empty] | 1 | 65.82 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6529 | AGCE-20210316-05 | 53511111 | Access | 0 | Pickup | 21.94 | 2 | HR | 16.455 | 0 |  |  | 43.88 | 5.7044 | 49.5844 | 2021-03-16 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Greg B Escort time removed |  | Approved |  |  | Move d6 to Dore Lk for support | 11 |  | Dore | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6529AGCE-20210316-05Pickup243.88 | AG Chapman Enterprises6529AGCE-20210316-05Pickup243.88AGCE-2021-03-11-20 | [5 empty] | 1 | 43.88 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6536 | AGCE-20210319-02 | 53511111 | Access | 0 | Pickup | 21.94 | 3 | HR | 16.455 | 0 |  |  | 65.82 | 8.5566 | 74.3766 | 2021-03-19 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Ben R Escort time removed |  | Approved |  |  | Walked D5 from east to west dore km 7 morning shift | 11 | F135-F149 | Dore Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6536AGCE-20210319-02Pickup365.82 | AG Chapman Enterprises6536AGCE-20210319-02Pickup365.82AGCE-2021-03-11-20 | [5 empty] | 1 | 65.82 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6537 | AGCE-20210319-03 | 53511111 | Access | 0 | Pickup | 21.94 | 6 | HR | 16.455 | 0 |  |  | 131.64 | 17.1132 | 148.7532 | 2021-03-19 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Ben R |  | Approved |  |  | Fix and back blade road | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6537AGCE-20210319-03Pickup6131.64 | AG Chapman Enterprises6537AGCE-20210319-03Pickup6131.64AGCE-2021-03-11-20 | [5 empty] | 1 | 131.64 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6538 | AGCE-20210320-01 | 53511111 | Access | 0 | Pickup | 21.94 | 7 | HR | 16.455 | 0 |  |  | 153.58 | 19.9654 | 173.5454 | 2021-03-20 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Back blade Dore Lk rd km 6.5 | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6538AGCE-20210320-01Pickup7153.58 | AG Chapman Enterprises6538AGCE-20210320-01Pickup7153.58AGCE-2021-03-11-20 | [5 empty] | 1 | 153.58 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6449 | AGCE-20210224-04 | 53511111 | Access | 0 | Pickup | 21.94 | 11.5 | HR | 16.455 | 0 |  |  | 252.31 | 32.8003 | 285.1103 | 2021-02-24 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Scraped Hensen Road east. Need to pull Rock truck off and bill to Kabi | 11 | F135-F149 | Hensen Road E | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6449AGCE-20210224-04Pickup11.5252.31 | AG Chapman Enterprises6449AGCE-20210224-04Pickup11.5252.31AGCE-2021-02-21-28 | [5 empty] | 1 | 252.31 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7048 | AGCE-20210312-04 | 53511111 | Access | 0 | Pickup | 21.94 | 6 | HR | 16.455 | 0 |  |  | 131.64 | 17.1132 | 148.7532 | 2021-03-12 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andrew Blackmore |  | Approved |  |  | Graded Washboard | 11 | F161-F164 | Trembley Flats Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7048AGCE-20210312-04Pickup6131.64 | AG Chapman Enterprises7048AGCE-20210312-04Pickup6131.64AGCE-2021-03-11-20 | [5 empty] | 1 | 131.64 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7050 | AGCE-20210313-04 | 53511111 | Access | 0 | Pickup | 21.94 | 3 | HR | 16.455 | 0 |  |  | 65.82 | 8.5566 | 74.3766 | 2021-03-13 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Early morning shift grading and then another operator took over | 11 | F120-F160 | Harbour, Trembley, Dore | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7050AGCE-20210313-04Pickup365.82 | AG Chapman Enterprises7050AGCE-20210313-04Pickup365.82AGCE-2021-03-11-20 | [5 empty] | 1 | 65.82 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7051 | AGCE-20210314-01 | 53511111 | Access | 0 | Pickup | 21.94 | 3 | HR | 16.455 | 0 |  |  | 65.82 | 8.5566 | 74.3766 | 2021-03-14 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | No LOA for Andy Neyland No Loa for Alfed C |  | Approved |  |  | Grading and Sanding Harbour and trembley Rd, and Dore | 11 | F120-F160 | Harbour, Trembley, Dore | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7051AGCE-20210314-01Pickup365.82 | AG Chapman Enterprises7051AGCE-20210314-01Pickup365.82AGCE-2021-03-11-20 | [5 empty] | 1 | 65.82 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7053 | AGCE-20210314-05 | 53511111 | Access | 0 | Pickup | 21.94 | 8 | HR | 16.455 | 0 |  |  | 175.52 | 22.8176 | 198.3376 | 2021-03-14 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert M, turns out he is not local |  | Approved |  |  | Grade roads as per email from Mandy | 11 | F120-F160 | Harbour, Trembley, Dore | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7053AGCE-20210314-05Pickup8175.52 | AG Chapman Enterprises7053AGCE-20210314-05Pickup8175.52AGCE-2021-03-11-20 | [5 empty] | 1 | 175.52 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7054 | AGCE-20210314-07 | 53511111 | Access | 0 | Pickup | 21.94 | 1 | HR | 16.455 | 0 |  |  | 21.94 | 2.8522 | 24.7922 | 2021-03-14 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Walk Dozer out to Trembley Rd from Dore area to be demobed to Salt Ste | 11 | F135 | Dore | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7054AGCE-20210314-07Pickup121.94 | AG Chapman Enterprises7054AGCE-20210314-07Pickup121.94AGCE-2021-03-11-20 | [5 empty] | 1 | 21.94 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7057 | AGCE-20210318-02 | 53511111 | Access | 0 | Pickup | 21.94 | 4 | HR | 16.455 | 0 |  |  | 87.76 | 11.4088 | 99.1688 | 2021-03-18 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert M |  | Approved |  |  | Grading harbour Road in morning and afternoon | 11 | F150-F159 | Harbour Road | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7057AGCE-20210318-02Pickup487.76 | AG Chapman Enterprises7057AGCE-20210318-02Pickup487.76AGCE-2021-03-11-20 | [5 empty] | 1 | 87.76 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6365 | AGCE-20210121-1 | 53511111 | Access | 0 | D6 Dozer | 177 | 9 | HR | 132.75 | 0 |  |  | 1593 | 207.09 | 1800.09 | 2021-01-21 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA Phil S |  | Approved |  |  | D6 dozer clear Dore Lake Road 7 am to 4 pm. LOA for Phil Swanson | 11 | F149-F135 | Dore Lake Road | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6365AGCE-20210121-1D6 Dozer91593 | AG Chapman Enterprises6365AGCE-20210121-1D6 Dozer91593AGCE-2021-01-30 | [5 empty] | 1 | 1593 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6367 | AGCE-20210121-2 | 53511111 | Access | 0 | D6 Dozer | 177 | 3.5 | HR | 132.75 | 0 |  |  | 619.5 | 80.535 | 700.035 | 2021-01-21 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | 1 LOA on ticket for Robert Eshkibad |  | Approved |  |  | D6 clear road of snow, back blade and pack snow. | 11 | F146-F148 | Harbour Road 4 | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6367AGCE-20210121-2D6 Dozer3.5619.5 | AG Chapman Enterprises6367AGCE-20210121-2D6 Dozer3.5619.5AGCE-2021-01-30 | [5 empty] | 1 | 619.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6368 | AGCE-20210121-3 | 53511111 | Access | 0 | D6 Dozer | 177 | 1 | HR | 132.75 | 0 |  |  | 177 | 23.01 | 200.01 | 2021-01-21 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | D6 clear snow and back blade | 11 | F155 | Harbour Road 3 | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6368AGCE-20210121-3D6 Dozer1177 | AG Chapman Enterprises6368AGCE-20210121-3D6 Dozer1177AGCE-2021-01-30 | [5 empty] | 1 | 177 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6061 | AGCE-20210205-1 | 53511111 | Access | 0 | D6 Dozer | 177 | 3 | HR | 132.75 | 0 |  |  | 531 | 69.03 | 600.03 | 2021-02-05 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | This will need to be billed out through Kabi to capture escort time |  | Pending |  |  | Walk dozer from High Falls Rd to Michipicoten Habour Rd 4 | 11 | F150 | Harbour Rd 4 | 0 | [10 empty] | 11 | AG Chapman Enterprises6061AGCE-20210205-1D6 Dozer3531 | AG Chapman Enterprises6061AGCE-20210205-1D6 Dozer3531 | [5 empty] | 1 | 531 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6376 | AGCE-20210206-1 | 53511111 | Access | 0 | D6 Dozer | 177 | 2 | HR | 132.75 | 0 |  |  | 354 | 46.02 | 400.02 | 2021-02-06 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S |  | Approved |  |  | Back Blade harbour rd 4 | 11 |  | Harbour Rd 4 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6376AGCE-20210206-1D6 Dozer2354 | AG Chapman Enterprises6376AGCE-20210206-1D6 Dozer2354AGCE-2021-02-10 | [5 empty] | 1 | 354 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6377 | AGCE-20210206-2 | 53511111 | Access | 0 | D6 Dozer | 177 | 3 | HR | 132.75 | 0 |  |  | 531 | 69.03 | 600.03 | 2021-02-06 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Track Harbour Rd 2 | 11 |  | Harbour Rd 2 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6377AGCE-20210206-2D6 Dozer3531 | AG Chapman Enterprises6377AGCE-20210206-2D6 Dozer3531AGCE-2021-02-10 | [5 empty] | 1 | 531 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6380 | AGCE-20210208-1 | 53511111 | Access | 0 | D6 Dozer | 177 | 5 | HR | 132.75 | 0 |  |  | 885 | 115.05 | 1000.05 | 2021-02-08 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S |  | Approved |  |  | Walkk dzr from Harbour Rd 1 to Harbour Rd 2, plow and track rd | 11 | F150-F151 | Harbour Rd's | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6380AGCE-20210208-1D6 Dozer5885 | AG Chapman Enterprises6380AGCE-20210208-1D6 Dozer5885AGCE-2021-02-10 | [5 empty] | 1 | 885 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6383 | AGCE-20210209-1 | 53511111 | Access | 0 | D6 Dozer | 177 | 5.5 | HR | 132.75 | 0 |  |  | 973.5 | 126.555 | 1100.055 | 2021-02-09 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S |  | Approved |  |  | Plowed and tracked Harb Rd 2 | 11 | F152-F154 | Harbour Rd 2 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6383AGCE-20210209-1D6 Dozer5.5973.5 | AG Chapman Enterprises6383AGCE-20210209-1D6 Dozer5.5973.5AGCE-2021-02-10 | [5 empty] | 1 | 973.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6386 | AGCE-20210210-1 | 53511111 | Access | 0 | D6 Dozer | 177 | 9.5 | HR | 132.75 | 0 |  |  | 1681.5 | 218.595 | 1900.095 | 2021-02-10 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Open up and track Harbour Rd 1, 3, 4, 5 | 11 | F150-F160 | Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6386AGCE-20210210-1D6 Dozer9.51681.5 | AG Chapman Enterprises6386AGCE-20210210-1D6 Dozer9.51681.5AGCE-2021-02-10 | [5 empty] | 1 | 1681.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6388 | AGCE-20210210-3 | 53511111 | Access | 0 | D6 Dozer | 177 | 4 | HR | 132.75 | 0 |  |  | 708 | 92.04 | 800.04 | 2021-02-10 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S |  | Approved |  |  | Plowed and tracked Harbour Rd | 11 | F152-F154 | Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6388AGCE-20210210-3D6 Dozer4708 | AG Chapman Enterprises6388AGCE-20210210-3D6 Dozer4708AGCE-2021-02-10 | [5 empty] | 1 | 708 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6392 | AGCE-20210211-4 | 53511111 | Access | 0 | D6 Dozer | 177 | 11 | HR | 132.75 | 0 |  |  | 1947 | 253.11 | 2200.11 | 2021-02-11 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N Supervisor and truck removed |  | Approved |  |  | Open roads and parking at F150 | 11 | F150-F151 | Harbour Rd 1 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6392AGCE-20210211-4D6 Dozer111947 | AG Chapman Enterprises6392AGCE-20210211-4D6 Dozer111947AGCE-2021-02-11-20 | [5 empty] | 1 | 1947 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6397 | AGCE-20210213-2 | 53511111 | Access | 0 | D6 Dozer | 177 | 9 | HR | 132.75 | 0 |  |  | 1593 | 207.09 | 1800.09 | 2021-02-13 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Cllear and widen Harbour Rd 3, 4, 5 | 11 |  | Harbour Rd 3, 4, 5 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6397AGCE-20210213-2D6 Dozer91593 | AG Chapman Enterprises6397AGCE-20210213-2D6 Dozer91593AGCE-2021-02-11-20 | [5 empty] | 1 | 1593 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6400 | AGCE-20210214-1 | 53511111 | Access | 0 | D6 Dozer | 177 | 12 | HR | 132.75 | 0 |  |  | 2124 | 276.12 | 2400.12 | 2021-02-14 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Open up road and truck turnarounds Harbour Rd 2, 3, 4, 5 | 11 |  | Harbour Rd 2, 3, 4, 5 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6400AGCE-20210214-1D6 Dozer122124 | AG Chapman Enterprises6400AGCE-20210214-1D6 Dozer122124AGCE-2021-02-11-20 | [5 empty] | 1 | 2124 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6413 | AGCE-20210217-1 | 53511111 | Access | 0 | D6 Dozer | 177 | 8 | HR | 132.75 | 0 |  |  | 1416 | 184.08 | 1600.08 | 2021-02-17 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Scott M |  | Approved |  |  | Back blade Habour Rd 2 | 11 | F152-F154 | Harbour Rd 2 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6413AGCE-20210217-1D6 Dozer81416 | AG Chapman Enterprises6413AGCE-20210217-1D6 Dozer81416AGCE-2021-02-11-20 | [5 empty] | 1 | 1416 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6429 | AGCE-20210220-2 | 53511111 | Access | 0 | D6 Dozer | 177 | 9 | HR | 132.75 | 0 |  |  | 1593 | 207.09 | 1800.09 | 2021-02-20 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Dan P Supervisor and truck removed |  | Approved |  |  | Push snow on High Falls Rd | 11 | F172-F211 | High Falls Road 1, 2, 3 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6429AGCE-20210220-2D6 Dozer91593 | AG Chapman Enterprises6429AGCE-20210220-2D6 Dozer91593AGCE-2021-02-11-20 | [5 empty] | 1 | 1593 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6431 | AGCE-20210221-1 | 53511111 | Access | 0 | D6 Dozer | 177 | 8 | HR | 132.75 | 0 |  |  | 1416 | 184.08 | 1600.08 | 2021-02-21 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Push snow on Harbour Rd 2 | 11 | F150-F157 | Harbour Rd 2 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6431AGCE-20210221-1D6 Dozer81416 | AG Chapman Enterprises6431AGCE-20210221-1D6 Dozer81416AGCE-2021-02-21-28 | [5 empty] | 1 | 1416 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6439 | AGCE-20210223-5 | 53511111 | Access | 0 | D6 Dozer | 177 | 10 | HR | 132.75 | 0 |  |  | 1770 | 230.1 | 2000.1 | 2021-02-23 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N Supervisor and truck removed |  | Approved |  |  | Pow and widen Harbour Rd and Dore Lake Rd | 11 |  | Dore Lake Rd, Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6439AGCE-20210223-5D6 Dozer101770 | AG Chapman Enterprises6439AGCE-20210223-5D6 Dozer101770AGCE-2021-02-21-28 | [5 empty] | 1 | 1770 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6446 | AGCE-20210224-02-R1 | 53511111 | Access | 0 | D6 Dozer | 177 | 12.5 | HR | 132.75 | 0 |  |  | 2212.5 | 287.625 | 2500.125 | 2021-02-24 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | back Blade and touch up michtpicoten Harbour roads 1234 | 11 | F150-F159 | Harbour Roads | 0 |  |  | 54 | 44252 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6446AGCE-20210224-02-R1D6 Dozer12.52212.5 | AG Chapman Enterprises6446AGCE-20210224-02-R1D6 Dozer12.52212.5AGCE-2021-02-21-28 | [5 empty] | 1 | 2212.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6454 | AGCE-20210225-04 | 53511111 | Access | 0 | D6 Dozer | 177 | 11.5 | HR | 132.75 | 0 |  |  | 2035.5 | 264.615 | 2300.115 | 2021-02-25 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Plowed and widened harbour rd 1, 2 ,3 ,4 5 | 11 | F150-F159 | Harbour Rd | 0 |  |  | 54 | 44345 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6454AGCE-20210225-04D6 Dozer11.52035.5 | AG Chapman Enterprises6454AGCE-20210225-04D6 Dozer11.52035.5AGCE-2021-02-21-28 | [5 empty] | 1 | 2035.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6466 | AGCE-20210227-03-R1 | 53511111 | Access | 0 | D6 Dozer | 177 | 12 | HR | 132.75 | 0 |  |  | 2124 | 276.12 | 2400.12 | 2021-02-27 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Back blade and push snow. | 11 | F172-F211 | Harbour Rd 1 - 5 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6466AGCE-20210227-03-R1D6 Dozer122124 | AG Chapman Enterprises6466AGCE-20210227-03-R1D6 Dozer122124AGCE-2021-02-21-28 | [5 empty] | 1 | 2124 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6470 | AGCE-20210228-01-R1 | 53511111 | Access | 0 | D6 Dozer | 177 | 12 | HR | 132.75 | 0 |  |  | 2124 | 276.12 | 2400.12 | 2021-02-28 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Push snow and repair Hills, scrape and fix dore, Plow road and clear parking spots | 11 | F135-F149 | Dore lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6470AGCE-20210228-01-R1D6 Dozer122124 | AG Chapman Enterprises6470AGCE-20210228-01-R1D6 Dozer122124AGCE-2021-02-21-28 | [5 empty] | 1 | 2124 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6470 | AGCE-20210228-01-R1 | 53511111 | Access | 0 | D6 Dozer | 177 | 2 | HR | 132.75 | 0 |  |  | 354 | 46.02 | 400.02 | 2021-02-28 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Push snow and repair Hills, scrape and fix dore, Plow road and clear parking spots | 11 | F135-F149 | Dore lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6470AGCE-20210228-01-R1D6 Dozer2354 | AG Chapman Enterprises6470AGCE-20210228-01-R1D6 Dozer2354AGCE-2021-02-21-28 | [5 empty] | 1 | 354 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6481 | AGCE-20210301-07-R1 | 53511111 | Access | 0 | D6 Dozer | 177 | 12 | HR | 132.75 | 0 |  |  | 2124 | 276.12 | 2400.12 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N LOA for Alfred C Same dozer billed 14.5 hours, might have been partial night shift |  | Approved |  |  | Plow Harbour Rd 1, 2, 3 and fix hills, partial night shift for dozer | 11 |  | Harbour Rd 1, 2, 3 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6481AGCE-20210301-07-R1D6 Dozer122124 | AG Chapman Enterprises6481AGCE-20210301-07-R1D6 Dozer122124AGCE-2021-03-01-10 | [5 empty] | 1 | 2124 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6481 | AGCE-20210301-07-R1 | 53511111 | Access | 0 | D6 Dozer | 177 | 2 | HR | 132.75 | 0 |  |  | 354 | 46.02 | 400.02 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N LOA for Alfred C Same dozer billed 14.5 hours, might have been partial night shift |  | Approved |  |  | Plow Harbour Rd 1, 2, 3 and fix hills, partial night shift for dozer | 11 |  | Harbour Rd 1, 2, 3 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6481AGCE-20210301-07-R1D6 Dozer2354 | AG Chapman Enterprises6481AGCE-20210301-07-R1D6 Dozer2354AGCE-2021-03-01-10 | [5 empty] | 1 | 354 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6489 | AGCE-20210302-08-R1 | 53511111 | Access | 0 | D6 Dozer | 177 | 11.5 | HR | 132.75 | 0 |  |  | 2035.5 | 264.615 | 2300.115 | 2021-03-02 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Wided roads and clear parking | 11 | F150-F159 | Harbour Rd 1, 2 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6489AGCE-20210302-08-R1D6 Dozer11.52035.5 | AG Chapman Enterprises6489AGCE-20210302-08-R1D6 Dozer11.52035.5AGCE-2021-03-01-10 | [5 empty] | 1 | 2035.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6497 | AGCE-20210303-08-R1 | 53511111 | Access | 0 | D6 Dozer | 177 | 11.5 | HR | 132.75 | 0 |  |  | 2035.5 | 264.615 | 2300.115 | 2021-03-03 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Maint and fix rds on Harbour rd 1, 2 | 11 | F150-F154 | Harbour Rd 1,2 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6497AGCE-20210303-08-R1D6 Dozer11.52035.5 | AG Chapman Enterprises6497AGCE-20210303-08-R1D6 Dozer11.52035.5AGCE-2021-03-01-10 | [5 empty] | 1 | 2035.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6524 | AGCE-20210311-08 | 53511111 | Access | 0 | D6 Dozer | 177 | 4 | HR | 132.75 | 0 |  |  | 708 | 92.04 | 800.04 | 2021-03-11 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | Disputed standby charges |  | Pending |  |  | Dozer on stndby | 11 |  |  | 0 | [10 empty] | 11 | AG Chapman Enterprises6524AGCE-20210311-08D6 Dozer4708 | AG Chapman Enterprises6524AGCE-20210311-08D6 Dozer4708 | [5 empty] | 1 | 708 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6525 | AGCE-20210312-05 | 53511111 | Access | 0 | D6 Dozer | 177 |  | HR | 132.75 | 4 |  |  | 531 | 69.03 | 600.03 | 2021-03-12 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Pending |  |  | Dozer on stndby | 11 |  |  | 0 | [10 empty] | 11 | AG Chapman Enterprises6525AGCE-20210312-05D6 Dozer531 | AG Chapman Enterprises6525AGCE-20210312-05D6 Dozer531 | [5 empty] | 1 | 531 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6526 | AGCE-20210313-05 | 53511111 | Access | 0 | D6 Dozer | 177 |  | HR | 132.75 | 4 |  |  | 531 | 69.03 | 600.03 | 2021-03-13 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Pending |  |  | D6 dozer on stndby | 11 |  |  | 0 | [10 empty] | 11 | AG Chapman Enterprises6526AGCE-20210313-05D6 Dozer531 | AG Chapman Enterprises6526AGCE-20210313-05D6 Dozer531 | [5 empty] | 1 | 531 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6529 | AGCE-20210316-05 | 53511111 | Access | 0 | D6 Dozer | 177 | 2 | HR | 132.75 | 0 |  |  | 354 | 46.02 | 400.02 | 2021-03-16 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Greg B Escort time removed |  | Approved |  |  | Move d6 to Dore Lk for support | 11 |  | Dore | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6529AGCE-20210316-05D6 Dozer2354 | AG Chapman Enterprises6529AGCE-20210316-05D6 Dozer2354AGCE-2021-03-11-20 | [5 empty] | 1 | 354 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6534 | AGCE-20210318-03 | 53511111 | Access | 0 | D6 Dozer | 177 | 4 | HR | 132.75 | 0 |  |  | 708 | 92.04 | 800.04 | 2021-03-18 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | D6 Dozer on Stndby | 11 |  |  | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6534AGCE-20210318-03D6 Dozer4708 | AG Chapman Enterprises6534AGCE-20210318-03D6 Dozer4708AGCE-2021-03-11-20 | [5 empty] | 1 | 708 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6437 | AGCE-20210223-3 | 53511111 | Access | 0 | D5 Dozer | 165 | 11 | HR | 0 | 0 |  |  | 1815 | 235.95 | 2050.95 | 2021-02-23 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E Supervisor and truck removed |  | Approved |  |  | Plowed Dore Lake Rd | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6437AGCE-20210223-3D5 Dozer111815 | AG Chapman Enterprises6437AGCE-20210223-3D5 Dozer111815AGCE-2021-02-21-28 | [5 empty] | 1 | 1815 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6442 | AGCE-20210223-8 | 53511111 | Access | 0 | D5 Dozer | 165 | 9 | HR | 0 | 0 |  |  | 1485 | 193.05 | 1678.05 | 2021-02-23 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andrew B Supervisor and truck removed |  | Approved |  |  | Plow and level off roads on Dore Lake Rd | 11 | F135-F149 | Dore Lake Rd East | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6442AGCE-20210223-8D5 Dozer91485 | AG Chapman Enterprises6442AGCE-20210223-8D5 Dozer91485AGCE-2021-02-21-28 | [5 empty] | 1 | 1485 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6450 | AGCE-20210224-05 | 53511111 | Access | 0 | D5 Dozer | 165 | 12 | HR | 0 | 0 |  |  | 1980 | 257.4 | 2237.4 | 2021-02-24 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Plowed Dore Lake Rd 8.5 KM west to end of road | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 54 | 44252 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6450AGCE-20210224-05D5 Dozer121980 | AG Chapman Enterprises6450AGCE-20210224-05D5 Dozer121980AGCE-2021-02-21-28 | [5 empty] | 1 | 1980 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6451 | AGCE-20210224-07-R1 | 53511111 | Access | 0 | D5 Dozer | 165 | 10 | HR | 0 | 0 |  |  | 1650 | 214.5 | 1864.5 | 2021-02-24 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andrew B, Split exc time off to Kabi |  | Approved |  |  | Clean up banks around km 2, Pack holes in road with snow, widen road. | 11 | F135 | Dore Lake Rd | 0 |  |  | 54 | 44345 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6451AGCE-20210224-07-R1D5 Dozer101650 | AG Chapman Enterprises6451AGCE-20210224-07-R1D5 Dozer101650AGCE-2021-02-21-28 | [5 empty] | 1 | 1650 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6453 | AGCE-20210225-03 | 53511111 | Access | 0 | D5 Dozer | 165 | 11 | HR | 0 | 0 |  |  | 1815 | 235.95 | 2050.95 | 2021-02-25 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Stephen B |  | Approved |  |  | Clean snow off road and fix up hill. | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 54 | 44345 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6453AGCE-20210225-03D5 Dozer111815 | AG Chapman Enterprises6453AGCE-20210225-03D5 Dozer111815AGCE-2021-02-21-28 | [5 empty] | 1 | 1815 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6455 | AGCE-20210225-05 | 53511111 | Access | 1 | D5 Dozer | 165 | 11.5 | HR | 0 |  |  |  | 1897.5 | 246.675 | 2144.175 | 2021-02-25 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andrew B |  | Approved |  |  | Plowed Dore lake Rd | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 54 | 44345 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6455AGCE-20210225-05D5 Dozer11.51897.5 | AG Chapman Enterprises6455AGCE-20210225-05D5 Dozer11.51897.5AGCE-2021-02-21-28 | [5 empty] | 1 | 1897.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6459 | AGCE-20210226-03-R1 | 53511111 | Access | 1 | D5 Dozer | 165 | 12 | HR | 0 | 0 |  |  | 1980 | 257.4 | 2237.4 | 2021-02-26 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andrew B |  | Approved |  |  | Touch and plow rds on Dore Lake Rd | 11 | F135-F149 | Dore lake Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6459AGCE-20210226-03-R1D5 Dozer121980 | AG Chapman Enterprises6459AGCE-20210226-03-R1D5 Dozer121980AGCE-2021-02-21-28 | [5 empty] | 1 | 1980 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6461 | AGCE-20210226-05-R1 | 53511111 | Access | 0 | D5 Dozer | 165 | 12 | HR | 0 | 0 |  |  | 1980 | 257.4 | 2237.4 | 2021-02-26 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Ploe and push back bank on Dore Lake Rd | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6461AGCE-20210226-05-R1D5 Dozer121980 | AG Chapman Enterprises6461AGCE-20210226-05-R1D5 Dozer121980AGCE-2021-02-21-28 | [5 empty] | 1 | 1980 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6467 | AGCE-20210227-04-R1 | 53511111 | Access | 0 | D5 Dozer | 165 | 12 | HR | 0 | 0 |  |  | 1980 | 257.4 | 2237.4 | 2021-02-27 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Greg B Loa for Stephen B |  | Approved |  |  | Fix roads and back blade Dore Lake Rd | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6467AGCE-20210227-04-R1D5 Dozer121980 | AG Chapman Enterprises6467AGCE-20210227-04-R1D5 Dozer121980AGCE-2021-02-21-28 | [5 empty] | 1 | 1980 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6470 | AGCE-20210228-01-R1 | 53511111 | Access | 0 | D5 Dozer | 165 | 10.5 | HR | 0 | 0 |  |  | 1732.5 | 225.225 | 1957.725 | 2021-02-28 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Push snow and repair Hills, scrape and fix dore, Plow road and clear parking spots | 11 | F135-F149 | Dore lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6470AGCE-20210228-01-R1D5 Dozer10.51732.5 | AG Chapman Enterprises6470AGCE-20210228-01-R1D5 Dozer10.51732.5AGCE-2021-02-21-28 | [5 empty] | 1 | 1732.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6472 | AGCE-20210228-03-R1 | 53511111 | Access | 0 | D5 Dozer | 165 | 12 | HR | 0 | 0 |  |  | 1980 | 257.4 | 2237.4 | 2021-02-28 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E No truck on ticket |  | Approved |  |  | Plow roads on Dore Lake | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6472AGCE-20210228-03-R1D5 Dozer121980 | AG Chapman Enterprises6472AGCE-20210228-03-R1D5 Dozer121980AGCE-2021-02-21-28 | [5 empty] | 1 | 1980 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6476 | AGCE-20210301-04-R1 | 53511111 | Access | 0 | D5 Dozer | 165 | 11.5 | HR | 0 | 0 |  |  | 1897.5 | 246.675 | 2144.175 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert M |  | Approved |  |  | Plowed roads on Dore Lk Rd | 11 | F1353-F149 | Dore Lake Road | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6476AGCE-20210301-04-R1D5 Dozer11.51897.5 | AG Chapman Enterprises6476AGCE-20210301-04-R1D5 Dozer11.51897.5AGCE-2021-03-01-10 | [5 empty] | 1 | 1897.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6479 | AGCE-20210301-05.1-R1 | 53511111 | Access | 1 | D5 Dozer | 165 | 11.5 | HR | 0 | 0 |  |  | 1897.5 | 246.675 | 2144.175 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Back Blade Rds on Dore | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6479AGCE-20210301-05.1-R1D5 Dozer11.51897.5 | AG Chapman Enterprises6479AGCE-20210301-05.1-R1D5 Dozer11.51897.5AGCE-2021-03-01-10 | [5 empty] | 1 | 1897.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6486 | AGCE-20210302-05-R1 | 53511111 | Access | 0 | D5 Dozer | 165 | 11.5 | HR | 0 | 0 |  |  | 1897.5 | 246.675 | 2144.175 | 2021-03-02 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert M No truck on ticket |  | Approved |  |  | Plow and rd maint | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6486AGCE-20210302-05-R1D5 Dozer11.51897.5 | AG Chapman Enterprises6486AGCE-20210302-05-R1D5 Dozer11.51897.5AGCE-2021-03-01-10 | [5 empty] | 1 | 1897.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6488 | AGCE-20210302-07-R1 | 53511111 | Access | 0 | D5 Dozer | 165 | 11.5 | HR | 0 | 0 |  |  | 1897.5 | 246.675 | 2144.175 | 2021-03-02 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Back blade from Km 4 to km 8.5 Dore Lk Rd | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6488AGCE-20210302-07-R1D5 Dozer11.51897.5 | AG Chapman Enterprises6488AGCE-20210302-07-R1D5 Dozer11.51897.5AGCE-2021-03-01-10 | [5 empty] | 1 | 1897.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6493 | AGCE-20210303-04-R1 | 53511111 | Access | 1 | D5 Dozer | 165 | 11.5 | HR | 0 | 0 |  |  | 1897.5 | 246.675 | 2144.175 | 2021-03-03 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Pack snow on to roads to fix and track pack | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6493AGCE-20210303-04-R1D5 Dozer11.51897.5 | AG Chapman Enterprises6493AGCE-20210303-04-R1D5 Dozer11.51897.5AGCE-2021-03-01-10 | [5 empty] | 1 | 1897.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6498 | AGCE-20210303-09-R1 | 53511111 | Access | 0 | D5 Dozer | 165 | 11.5 | HR | 0 | 0 |  |  | 1897.5 | 246.675 | 2144.175 | 2021-03-03 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert M |  | Approved |  |  | Maint rd on Dore Lk | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6498AGCE-20210303-09-R1D5 Dozer11.51897.5 | AG Chapman Enterprises6498AGCE-20210303-09-R1D5 Dozer11.51897.5AGCE-2021-03-01-10 | [5 empty] | 1 | 1897.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6501 | AGCE-20210304-05-R1 | 53511111 | Access | 1 | D5 Dozer | 165 | 11.5 | HR | 0 | 0 |  |  | 1897.5 | 246.675 | 2144.175 | 2021-03-04 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E LOA for Paul K |  | Approved |  |  | Reg Rd maint and repair on dore | 11 | F135-F149 | Dore lake Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6501AGCE-20210304-05-R1D5 Dozer11.51897.5 | AG Chapman Enterprises6501AGCE-20210304-05-R1D5 Dozer11.51897.5AGCE-2021-03-01-10 | [5 empty] | 1 | 1897.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6527 | AGCE-20210315-04 | 53511111 | Access | 0 | D5 Dozer | 165 | 4 | HR | 0 | 0 |  |  | 660 | 85.8 | 745.8 | 2021-03-15 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | D5 dozer on stndby | 11 |  |  | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6527AGCE-20210315-04D5 Dozer4660 | AG Chapman Enterprises6527AGCE-20210315-04D5 Dozer4660AGCE-2021-03-11-20 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6532 | AGCE-20210317-03 | 53511111 | Access | 0 | D5 Dozer | 165 | 4 | HR | 0 | 0 |  |  | 660 | 85.8 | 745.8 | 2021-03-17 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | D5 dozer on stndby | 11 |  |  | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6532AGCE-20210317-03D5 Dozer4660 | AG Chapman Enterprises6532AGCE-20210317-03D5 Dozer4660AGCE-2021-03-11-20 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6536 | AGCE-20210319-02 | 53511111 | Access | 0 | D5 Dozer | 165 | 3 | HR | 0 | 0 |  |  | 495 | 64.35 | 559.35 | 2021-03-19 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Ben R Escort time removed |  | Approved |  |  | Walked D5 from east to west dore km 7 morning shift | 11 | F135-F149 | Dore Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6536AGCE-20210319-02D5 Dozer3495 | AG Chapman Enterprises6536AGCE-20210319-02D5 Dozer3495AGCE-2021-03-11-20 | [5 empty] | 1 | 495 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6537 | AGCE-20210319-03 | 53511111 | Access | 0 | D5 Dozer | 165 | 6 | HR | 0 | 0 |  |  | 990 | 128.7 | 1118.7 | 2021-03-19 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Ben R |  | Approved |  |  | Fix and back blade road | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6537AGCE-20210319-03D5 Dozer6990 | AG Chapman Enterprises6537AGCE-20210319-03D5 Dozer6990AGCE-2021-03-11-20 | [5 empty] | 1 | 990 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6538 | AGCE-20210320-01 | 53511111 | Access | 0 | D5 Dozer | 165 | 7 | HR | 0 | 0 |  |  | 1155 | 150.15 | 1305.15 | 2021-03-20 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Back blade Dore Lk rd km 6.5 | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6538AGCE-20210320-01D5 Dozer71155 | AG Chapman Enterprises6538AGCE-20210320-01D5 Dozer71155AGCE-2021-03-11-20 | [5 empty] | 1 | 1155 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6540 | AGCE-20210321-02 | 53511111 | Access | 0 | D5 Dozer | 165 | 4 | HR | 0 | 0 |  |  | 660 | 85.8 | 745.8 | 2021-03-21 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | No stndby rate provided by chapman for the D5 |  | Pending |  |  | D5 on stndby, No stndby rate provided by chapman for the D5 | 11 |  |  | 0 | [10 empty] | 11 | AG Chapman Enterprises6540AGCE-20210321-02D5 Dozer4660 | AG Chapman Enterprises6540AGCE-20210321-02D5 Dozer4660 | [5 empty] | 1 | 660 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6390 | AGCE-20210211-2 | 53511111 | Access | 0 | D4 Dozer | 155 | 10 | HR | 0 | 0 |  |  | 1550 | 201.5 | 1751.5 | 2021-02-11 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Dan P, Removed supervisor and truck |  | Approved |  |  | Push back banks and pack roads | 11 |  | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6390AGCE-20210211-2D4 Dozer101550 | AG Chapman Enterprises6390AGCE-20210211-2D4 Dozer101550AGCE-2021-02-11-20 | [5 empty] | 1 | 1550 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6394 | AGCE-20210212-2 | 53511111 | Access | 0 | D4 Dozer | 155 | 10 | HR | 0 | 0 |  |  | 1550 | 201.5 | 1751.5 | 2021-02-12 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Widen Roads Dore Lake and then float to Hensen Road | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6394AGCE-20210212-2D4 Dozer101550 | AG Chapman Enterprises6394AGCE-20210212-2D4 Dozer101550AGCE-2021-02-11-20 | [5 empty] | 1 | 1550 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6396 | AGCE-20210213-1 | 53511111 | Access | 0 | D4 Dozer | 155 | 12 | HR | 0 | 0 |  |  | 1860 | 241.8 | 2101.8 | 2021-02-13 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Cleared and wiiden Hensen Road | 11 | F119-F134 | Hensen Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6396AGCE-20210213-1D4 Dozer121860 | AG Chapman Enterprises6396AGCE-20210213-1D4 Dozer121860AGCE-2021-02-11-20 | [5 empty] | 1 | 1860 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6399 | AGCE-20210213-4 | 53511111 | Access | 0 | D4 Dozer | 155 | 11 | HR | 0 | 0 |  |  | 1705 | 221.65 | 1926.65 | 2021-02-13 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Widen Dore Lake Rd | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6399AGCE-20210213-4D4 Dozer111705 | AG Chapman Enterprises6399AGCE-20210213-4D4 Dozer111705AGCE-2021-02-11-20 | [5 empty] | 1 | 1705 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6401 | AGCE-20210214-2 | 53511111 | Access | 0 | D4 Dozer | 155 | 11 | HR | 0 | 0 |  |  | 1705 | 221.65 | 1926.65 | 2021-02-14 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | No work description, may need to bill throough kabi | 11 |  | Dore Lake Rd E & W | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6401AGCE-20210214-2D4 Dozer111705 | AG Chapman Enterprises6401AGCE-20210214-2D4 Dozer111705AGCE-2021-02-11-20 | [5 empty] | 1 | 1705 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6402 | AGCE-20210214-3 | 53511111 | Access | 0 | D4 Dozer | 155 | 10 | HR | 0 | 0 |  |  | 1550 | 201.5 | 1751.5 | 2021-02-14 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C Supervisor and truck removed |  | Approved |  |  | Plow and open up roads Hensnen Rd | 11 | F119-F134 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6402AGCE-20210214-3D4 Dozer101550 | AG Chapman Enterprises6402AGCE-20210214-3D4 Dozer101550AGCE-2021-02-11-20 | [5 empty] | 1 | 1550 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6405 | AGCE-20210215-2 | 53511111 | Access | 0 | D4 Dozer | 155 | 12 | HR | 0 | 0 |  |  | 1860 | 241.8 | 2101.8 | 2021-02-15 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Clear roads and scrape ice Hensen Road | 11 | F112-F117 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6405AGCE-20210215-2D4 Dozer121860 | AG Chapman Enterprises6405AGCE-20210215-2D4 Dozer121860AGCE-2021-02-11-20 | [5 empty] | 1 | 1860 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6406 | AGCE-20210215-3 | 53511111 | Access | 0 | D4 Dozer | 155 | 12 | HR | 0 | 0 |  |  | 1860 | 241.8 | 2101.8 | 2021-02-15 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E Supervisor and truck removed |  | Approved |  |  | Widen roads at F146-F149 Dore | 11 | F146-F149 | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6406AGCE-20210215-3D4 Dozer121860 | AG Chapman Enterprises6406AGCE-20210215-3D4 Dozer121860AGCE-2021-02-11-20 | [5 empty] | 1 | 1860 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6407 | AGCE-20210215-4 | 53511111 | Access | 0 | D4 Dozer | 155 | 10 | HR | 0 | 0 |  |  | 1550 | 201.5 | 1751.5 | 2021-02-15 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Dan P Supervisor and truck removed |  | Approved |  |  | Push snow on harbour rd 1 | 11 | F150-F151 | Harbour Rd 1 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6407AGCE-20210215-4D4 Dozer101550 | AG Chapman Enterprises6407AGCE-20210215-4D4 Dozer101550AGCE-2021-02-11-20 | [5 empty] | 1 | 1550 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6409 | AGCE-20210216-2 | 53511111 | Access | 0 | D4 Dozer | 155 | 11 | HR | 0 | 0 |  |  | 1705 | 221.65 | 1926.65 | 2021-02-16 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Widen roads Dore Lake East and West. | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6409AGCE-20210216-2D4 Dozer111705 | AG Chapman Enterprises6409AGCE-20210216-2D4 Dozer111705AGCE-2021-02-11-20 | [5 empty] | 1 | 1705 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6414 | AGCE-20210217-2 | 53511111 | Access | 0 | D4 Dozer | 155 | 11 | HR | 0 | 0 |  |  | 1705 | 221.65 | 1926.65 | 2021-02-17 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E Supervisor and truck removed |  | Approved |  |  | Plowed and widened Dore lake Rd | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6414AGCE-20210217-2D4 Dozer111705 | AG Chapman Enterprises6414AGCE-20210217-2D4 Dozer111705AGCE-2021-02-11-20 | [5 empty] | 1 | 1705 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6415 | AGCE-20210217-3 | 53511111 | Access | 0 | D4 Dozer | 155 | 9 | HR | 0 | 0 |  |  | 1395 | 181.35 | 1576.35 | 2021-02-17 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | Supervisor and truck removed |  | Approved |  |  | Plow roads at High Falls Rd 1 and 2 | 11 | F172-F211 | High Falls Road 1, 2 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6415AGCE-20210217-3D4 Dozer91395 | AG Chapman Enterprises6415AGCE-20210217-3D4 Dozer91395AGCE-2021-02-11-20 | [5 empty] | 1 | 1395 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6416 | AGCE-20210217-4 | 53511111 | Access | 0 | D4 Dozer | 155 | 11 | HR | 0 | 0 |  |  | 1705 | 221.65 | 1926.65 | 2021-02-17 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C Supervisor and truck removed |  | Approved |  |  | Scrape roads on Hensen | 11 | F118-F133 | Hensen Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6416AGCE-20210217-4D4 Dozer111705 | AG Chapman Enterprises6416AGCE-20210217-4D4 Dozer111705AGCE-2021-02-11-20 | [5 empty] | 1 | 1705 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6418 | AGCE-20210218-2 | 53511111 | Access | 0 | D4 Dozer | 155 | 1 | HR | 0 | 0 |  |  | 155 | 20.15 | 175.15 | 2021-02-18 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Push snow on High Falls road | 11 | F172-F211 | High Falls Rd 1, 2, 3 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6418AGCE-20210218-2D4 Dozer1155 | AG Chapman Enterprises6418AGCE-20210218-2D4 Dozer1155AGCE-2021-02-11-20 | [5 empty] | 1 | 155 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6419 | AGCE-20210218-3 | 53511111 | Access | 0 | D4 Dozer | 155 | 11 | HR | 0 | 0 |  |  | 1705 | 221.65 | 1926.65 | 2021-02-18 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E Supervisor and truck removed |  | Approved |  |  | Pushed out Dore Lake Rd and back bladed the turn around | 11 |  | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6419AGCE-20210218-3D4 Dozer111705 | AG Chapman Enterprises6419AGCE-20210218-3D4 Dozer111705AGCE-2021-02-11-20 | [5 empty] | 1 | 1705 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6420 | AGCE-20210218-4 | 53511111 | Access | 0 | D4 Dozer | 155 | 11 | HR | 0 | 0 |  |  | 1705 | 221.65 | 1926.65 | 2021-02-18 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C Supervisor and truck removed |  | Approved |  |  | Scraped Hensen Rd East | 11 | F117-F134 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6420AGCE-20210218-4D4 Dozer111705 | AG Chapman Enterprises6420AGCE-20210218-4D4 Dozer111705AGCE-2021-02-11-20 | [5 empty] | 1 | 1705 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6422 | AGCE-20210219-1 | 53511111 | Access | 0 | D4 Dozer | 155 | 11.5 | HR | 0 | 0 |  |  | 1782.5 | 231.725 | 2014.225 | 2021-02-19 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Back blade hills, widen rds, plowed to Km 6 | 11 |  | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6422AGCE-20210219-1D4 Dozer11.51782.5 | AG Chapman Enterprises6422AGCE-20210219-1D4 Dozer11.51782.5AGCE-2021-02-11-20 | [5 empty] | 1 | 1782.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6423 | AGCE-20210219-2 | 53511111 | Access | 0 | D4 Dozer | 155 | 8 | HR | 0 | 0 |  |  | 1240 | 161.2 | 1401.2 | 2021-02-19 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N Supervisor and truck removed |  | Approved |  |  | Cleared all roads at Dore Lake | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6423AGCE-20210219-2D4 Dozer81240 | AG Chapman Enterprises6423AGCE-20210219-2D4 Dozer81240AGCE-2021-02-11-20 | [5 empty] | 1 | 1240 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6424 | AGCE-20210219-3 | 53511111 | Access | 0 | D4 Dozer | 155 | 7 | HR | 0 | 0 |  |  | 1085 | 141.05 | 1226.05 | 2021-02-19 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | Supervisor and truck removed |  | Approved |  |  | Push snow and clean up around bridges High Falls Rd 1, 2 F171 | 11 | F171 | High Falls Rd 1, 2 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6424AGCE-20210219-3D4 Dozer71085 | AG Chapman Enterprises6424AGCE-20210219-3D4 Dozer71085AGCE-2021-02-11-20 | [5 empty] | 1 | 1085 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6425 | AGCE-20210219-4 | 53511111 | Access | 0 | D4 Dozer | 155 | 11.5 | HR | 0 | 0 |  |  | 1782.5 | 231.725 | 2014.225 | 2021-02-19 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C Supervisor and truck removed |  | Approved |  |  | Scraped hensen rd | 11 | F117-F135 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6425AGCE-20210219-4D4 Dozer11.51782.5 | AG Chapman Enterprises6425AGCE-20210219-4D4 Dozer11.51782.5AGCE-2021-02-11-20 | [5 empty] | 1 | 1782.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6428 | AGCE-20210220-1 | 53511111 | Access | 0 | D4 Dozer | 155 | 11.5 | HR | 0 | 0 |  |  | 1782.5 | 231.725 | 2014.225 | 2021-02-20 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Widen Dore Rd and clear turn arounds | 11 |  | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6428AGCE-20210220-1D4 Dozer11.51782.5 | AG Chapman Enterprises6428AGCE-20210220-1D4 Dozer11.51782.5AGCE-2021-02-11-20 | [5 empty] | 1 | 1782.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6430 | AGCE-20210220-4 | 53511111 | Access | 0 | D4 Dozer | 155 | 11 | HR | 0 | 0 |  |  | 1705 | 221.65 | 1926.65 | 2021-02-20 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C Supervisor and truck removed |  | Approved |  |  | Scraped road on Hensen E | 11 | F115-F133 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6430AGCE-20210220-4D4 Dozer111705 | AG Chapman Enterprises6430AGCE-20210220-4D4 Dozer111705AGCE-2021-02-11-20 | [5 empty] | 1 | 1705 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6432 | AGCE-20210221-2 | 53511111 | Access | 0 | D4 Dozer | 155 | 12 | HR | 0 | 0 |  |  | 1860 | 241.8 | 2101.8 | 2021-02-21 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C Superviosr and truck removed |  | Approved |  |  | Scraped Hensen Rd | 11 | F117-F133 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6432AGCE-20210221-2D4 Dozer121860 | AG Chapman Enterprises6432AGCE-20210221-2D4 Dozer121860AGCE-2021-02-21-28 | [5 empty] | 1 | 1860 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6433 | AGCE-20210221-3 | 53511111 | Access | 0 | D4 Dozer | 155 | 12 | HR | 0 | 0 |  |  | 1860 | 241.8 | 2101.8 | 2021-02-21 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E Supervisor and truck removed |  | Approved |  |  | push snow from Km 6 to Km 9.5 Dore Rd | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6433AGCE-20210221-3D4 Dozer121860 | AG Chapman Enterprises6433AGCE-20210221-3D4 Dozer121860AGCE-2021-02-21-28 | [5 empty] | 1 | 1860 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6434 | AGCE-20210222-1 | 53511111 | Access | 0 | D4 Dozer | 155 | 11 | HR | 0 | 0 |  |  | 1705 | 221.65 | 1926.65 | 2021-02-22 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Plowing High Falls Rd | 11 | F172-F211 | High Falls Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6434AGCE-20210222-1D4 Dozer111705 | AG Chapman Enterprises6434AGCE-20210222-1D4 Dozer111705AGCE-2021-02-21-28 | [5 empty] | 1 | 1705 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6436 | AGCE-20210223-2 | 53511111 | Access | 0 | D4 Dozer | 155 | 10 | HR | 0 | 0 |  |  | 1550 | 201.5 | 1751.5 | 2021-02-23 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Steve B Supervisor and truck removed |  | Approved |  |  | Cleaned and plowed Dore Lake Rd | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6436AGCE-20210223-2D4 Dozer101550 | AG Chapman Enterprises6436AGCE-20210223-2D4 Dozer101550AGCE-2021-02-21-28 | [5 empty] | 1 | 1550 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6440 | AGCE-20210223-6 | 53511111 | Access | 0 | D4 Dozer | 155 | 13.5 | HR | 0 | 0 |  |  | 2092.5 | 272.025 | 2364.525 | 2021-02-23 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C Supervisor and truck removed |  | Approved |  |  | Scraped Hensen Rd East | 11 | F115-F133 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6440AGCE-20210223-6D4 Dozer13.52092.5 | AG Chapman Enterprises6440AGCE-20210223-6D4 Dozer13.52092.5AGCE-2021-02-21-28 | [5 empty] | 1 | 2092.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6441 | AGCE-20210223-7 | 53511111 | Access | 0 | D4 Dozer | 155 | 2.5 | HR | 0 | 0 |  |  | 387.5 | 50.375 | 437.875 | 2021-02-23 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Plow Dore Road and fix road surface | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6441AGCE-20210223-7D4 Dozer2.5387.5 | AG Chapman Enterprises6441AGCE-20210223-7D4 Dozer2.5387.5AGCE-2021-02-21-28 | [5 empty] | 1 | 387.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6443 | AGCE-20210223-9 | 53511111 | Access | 0 | D4 Dozer | 155 | 6 | HR | 0 | 0 |  |  | 930 | 120.9 | 1050.9 | 2021-02-23 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Plowed road and fixed holes | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6443AGCE-20210223-9D4 Dozer6930 | AG Chapman Enterprises6443AGCE-20210223-9D4 Dozer6930AGCE-2021-02-21-28 | [5 empty] | 1 | 930 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6447 | AGCE-20210224-03 | 53511111 | Access | 0 | D4 Dozer | 155 | 10 | HR | 0 | 0 |  |  | 1550 | 201.5 | 1751.5 | 2021-02-24 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | Supervisor removed |  | Approved |  |  | Plowed to F187 access to tower site Road 9 access, F206, F207, F208 | 11 | F206-F209 | High Falls | 0 |  |  | 54 | 44252 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6447AGCE-20210224-03D4 Dozer101550 | AG Chapman Enterprises6447AGCE-20210224-03D4 Dozer101550AGCE-2021-02-21-28 | [5 empty] | 1 | 1550 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6451 | AGCE-20210224-07-R1 | 53511111 | Access | 0 | D4 Dozer | 155 | 2 | HR | 0 | 0 |  |  | 310 | 40.3 | 350.3 | 2021-02-24 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andrew B, Split exc time off to Kabi |  | Approved |  |  | Clean up banks around km 2, Pack holes in road with snow, widen road. | 11 | F135 | Dore Lake Rd | 0 |  |  | 54 | 44345 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6451AGCE-20210224-07-R1D4 Dozer2310 | AG Chapman Enterprises6451AGCE-20210224-07-R1D4 Dozer2310AGCE-2021-02-21-28 | [5 empty] | 1 | 310 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6452 | AGCE-20210225-01-R1 | 53511111 | Access | 0 | D4 Dozer | 155 | 11.5 | HR | 0 | 0 |  |  | 1782.5 | 231.725 | 2014.225 | 2021-02-25 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Scrape and widen roads in Hensen | 11 | F117-F133 | Hensen Rd | 0 |  |  | 54 | 44345 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6452AGCE-20210225-01-R1D4 Dozer11.51782.5 | AG Chapman Enterprises6452AGCE-20210225-01-R1D4 Dozer11.51782.5AGCE-2021-02-21-28 | [5 empty] | 1 | 1782.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6456 | AGCE-20210225-02 | 53511111 | Access | 0 | D4 Dozer | 155 | 9.5 | HR | 0 | 0 |  |  | 1472.5 | 191.425 | 1663.925 | 2021-02-25 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Back blade to Dore west | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 54 | 44345 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6456AGCE-20210225-02D4 Dozer9.51472.5 | AG Chapman Enterprises6456AGCE-20210225-02D4 Dozer9.51472.5AGCE-2021-02-21-28 | [5 empty] | 1 | 1472.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6458 | AGCE-20210226-02-R1 | 53511111 | Access | 0 | D4 Dozer | 155 | 12 | HR | 0 | 0 |  |  | 1860 | 241.8 | 2101.8 | 2021-02-26 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Scrape and repair Hensen rd | 11 | F119-F134 | Hensen Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6458AGCE-20210226-02-R1D4 Dozer121860 | AG Chapman Enterprises6458AGCE-20210226-02-R1D4 Dozer121860AGCE-2021-02-21-28 | [5 empty] | 1 | 1860 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6462 | AGCE-20210226-06-R1 | 53511111 | Access | 1 | D4 Dozer | 155 | 11 | HR | 0 | 0 |  |  | 1705 | 221.65 | 1926.65 | 2021-02-26 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Stephen B |  | Approved |  |  | Clean and fix Dore Lake Road | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6462AGCE-20210226-06-R1D4 Dozer111705 | AG Chapman Enterprises6462AGCE-20210226-06-R1D4 Dozer111705AGCE-2021-02-21-28 | [5 empty] | 1 | 1705 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6463 | AGCE-20210226-07-R1 | 53511111 | Access | 0 | D4 Dozer | 155 | 8 | HR | 0 | 0 |  |  | 1240 | 161.2 | 1401.2 | 2021-02-26 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | No LOA for Dan P |  | Approved |  |  | Pushed snow on High Falls Rd | 11 | F172-F211 | High Falls Road | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6463AGCE-20210226-07-R1D4 Dozer81240 | AG Chapman Enterprises6463AGCE-20210226-07-R1D4 Dozer81240AGCE-2021-02-21-28 | [5 empty] | 1 | 1240 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6465 | AGCE-20210227-02-R1 | 53511111 | Access | 0 | D4 Dozer | 155 | 2 | HR | 0 | 0 |  |  | 310 | 40.3 | 350.3 | 2021-02-27 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Dan P Remove shuttle charges for Katrina Adams, |  | Approved |  |  | Clear Rd and fix, track rd, | 11 | F150-F159 | Harbour Rd 4 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6465AGCE-20210227-02-R1D4 Dozer2310 | AG Chapman Enterprises6465AGCE-20210227-02-R1D4 Dozer2310AGCE-2021-02-21-28 | [5 empty] | 1 | 310 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6467 | AGCE-20210227-04-R1 | 53511111 | Access | 0 | D4 Dozer | 155 | 10.5 | HR | 0 | 0 |  |  | 1627.5 | 211.575 | 1839.075 | 2021-02-27 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Greg B Loa for Stephen B |  | Approved |  |  | Fix roads and back blade Dore Lake Rd | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6467AGCE-20210227-04-R1D4 Dozer10.51627.5 | AG Chapman Enterprises6467AGCE-20210227-04-R1D4 Dozer10.51627.5AGCE-2021-02-21-28 | [5 empty] | 1 | 1627.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6469 | AGCE-20210227-06-R1 | 53511111 | Access | 0 | D4 Dozer | 155 | 12 | HR | 0 | 0 |  |  | 1860 | 241.8 | 2101.8 | 2021-02-27 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | Mike Woods LOA |  | Approved |  |  | Plow roads dore east | 11 | F135-F149 | Dore lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6469AGCE-20210227-06-R1D4 Dozer121860 | AG Chapman Enterprises6469AGCE-20210227-06-R1D4 Dozer121860AGCE-2021-02-21-28 | [5 empty] | 1 | 1860 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6470 | AGCE-20210228-01-R1 | 53511111 | Access | 0 | D4 Dozer | 155 | 10 | HR | 0 | 0 |  |  | 1550 | 201.5 | 1751.5 | 2021-02-28 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Push snow and repair Hills, scrape and fix dore, Plow road and clear parking spots | 11 | F135-F149 | Dore lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6470AGCE-20210228-01-R1D4 Dozer101550 | AG Chapman Enterprises6470AGCE-20210228-01-R1D4 Dozer101550AGCE-2021-02-21-28 | [5 empty] | 1 | 1550 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6471 | AGCE-20210228-02-R1 | 53511111 | Access | 0 | D4 Dozer | 155 | 12 | HR | 0 | 0 |  |  | 1860 | 241.8 | 2101.8 | 2021-02-28 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Mike W |  | Approved |  |  | Creape roads and push snow Hensen Rd | 11 | F119-F134 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6471AGCE-20210228-02-R1D4 Dozer121860 | AG Chapman Enterprises6471AGCE-20210228-02-R1D4 Dozer121860AGCE-2021-02-21-28 | [5 empty] | 1 | 1860 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6473 | AGCE-20210301-01-R1 | 53511111 | Access | 0 | D4 Dozer | 155 | 12 | HR | 0 | 0 |  |  | 1860 | 241.8 | 2101.8 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Mike W |  | Approved |  |  | Push snow to km 5 on Hensen rd | 11 | F119-F135 | Hensen Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6473AGCE-20210301-01-R1D4 Dozer121860 | AG Chapman Enterprises6473AGCE-20210301-01-R1D4 Dozer121860AGCE-2021-03-01-10 | [5 empty] | 1 | 1860 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6477 | AGCE-20210301-05-R1 | 53511111 | Access | 0 | D4 Dozer | 155 | 11.5 | HR | 0 | 0 |  |  | 1782.5 | 231.725 | 2014.225 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | NO LOA for Dan P |  | Approved |  |  | Pushed snow on Harbour Rd 4 | 11 | F156-F158 | Harbour Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6477AGCE-20210301-05-R1D4 Dozer11.51782.5 | AG Chapman Enterprises6477AGCE-20210301-05-R1D4 Dozer11.51782.5AGCE-2021-03-01-10 | [5 empty] | 1 | 1782.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6480 | AGCE-20210301-06-R1 | 53511111 | Access | 0 | D4 Dozer | 155 | 11.5 | HR | 0 | 0 |  |  | 1782.5 | 231.725 | 2014.225 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Ben R |  | Approved |  |  | Push snow and clean turn arounds on Dore lk rd | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6480AGCE-20210301-06-R1D4 Dozer11.51782.5 | AG Chapman Enterprises6480AGCE-20210301-06-R1D4 Dozer11.51782.5AGCE-2021-03-01-10 | [5 empty] | 1 | 1782.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6485 | AGCE-20210302-04-R1 | 53511111 | Access | 1 | D4 Dozer | 155 | 11.5 | HR | 0 | 0 |  |  | 1782.5 | 231.725 | 2014.225 | 2021-03-02 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Paul K |  | Approved |  |  | Back blade Dore Lk Rd West to east | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6485AGCE-20210302-04-R1D4 Dozer11.51782.5 | AG Chapman Enterprises6485AGCE-20210302-04-R1D4 Dozer11.51782.5AGCE-2021-03-01-10 | [5 empty] | 1 | 1782.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6487 | AGCE-20210302-06-R1 | 53511111 | Access | 0 | D4 Dozer | 155 | 8.5 | HR | 0 | 0 |  |  | 1317.5 | 171.275 | 1488.775 | 2021-03-02 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | No LOA for Dan P |  | Approved |  |  | Pushing snow on Harbour Rd. | 11 | F155-F160 | Harbour Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6487AGCE-20210302-06-R1D4 Dozer8.51317.5 | AG Chapman Enterprises6487AGCE-20210302-06-R1D4 Dozer8.51317.5AGCE-2021-03-01-10 | [5 empty] | 1 | 1317.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6492 | AGCE-20210303-03-R1 | 53511111 | Access | 0 | D4 Dozer | 155 | 11.5 | HR | 0 | 0 |  |  | 1782.5 | 231.725 | 2014.225 | 2021-03-03 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Ben R No truck on ticket |  | Approved |  |  | Push snow and banks on Hensen east | 11 | F119-F134 | Hensen Road | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6492AGCE-20210303-03-R1D4 Dozer11.51782.5 | AG Chapman Enterprises6492AGCE-20210303-03-R1D4 Dozer11.51782.5AGCE-2021-03-01-10 | [5 empty] | 1 | 1782.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6494 | AGCE-20210303-05-R1 | 53511111 | Access | 1 | D4 Dozer | 155 | 11.5 | HR | 0 | 0 |  |  | 1782.5 | 231.725 | 2014.225 | 2021-03-03 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Paul K |  | Approved |  |  | Plowed Rds and packed roads on Dore | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6494AGCE-20210303-05-R1D4 Dozer11.51782.5 | AG Chapman Enterprises6494AGCE-20210303-05-R1D4 Dozer11.51782.5AGCE-2021-03-01-10 | [5 empty] | 1 | 1782.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6496 | AGCE-20210303-07-R1 | 53511111 | Access | 0 | D4 Dozer | 155 | 8 | HR | 0 | 0 |  |  | 1240 | 161.2 | 1401.2 | 2021-03-03 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | No LOA for Dan P |  | Approved |  |  | Plow roads at harbour rd 4, 5 | 11 | F156-F160 | Harbour Rd 4, 5 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6496AGCE-20210303-07-R1D4 Dozer81240 | AG Chapman Enterprises6496AGCE-20210303-07-R1D4 Dozer81240AGCE-2021-03-01-10 | [5 empty] | 1 | 1240 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6499 | AGCE-20210303-10-R1 | 53511111 | Access | 0 | D4 Dozer | 155 | 11.5 | HR | 0 | 0 |  |  | 1782.5 | 231.725 | 2014.225 | 2021-03-03 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Greg B |  | Approved |  |  | Plowed and did regular rd maint on Dore Lk Rd | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6499AGCE-20210303-10-R1D4 Dozer11.51782.5 | AG Chapman Enterprises6499AGCE-20210303-10-R1D4 Dozer11.51782.5AGCE-2021-03-01-10 | [5 empty] | 1 | 1782.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6500 | AGCE-20210304-02-R1 | 53511111 | Access | 0 | D4 Dozer | 155 | 8 | HR | 0 | 0 |  |  | 1240 | 161.2 | 1401.2 | 2021-03-04 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Joe B |  | Approved |  |  | Widen roads on Harbour | 11 | F156-F160 | Harbour Rd 4, 5 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6500AGCE-20210304-02-R1D4 Dozer81240 | AG Chapman Enterprises6500AGCE-20210304-02-R1D4 Dozer81240AGCE-2021-03-01-10 | [5 empty] | 1 | 1240 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6501 | AGCE-20210304-05-R1 | 53511111 | Access | 1 | D4 Dozer | 155 | 11.5 | HR | 0 | 0 |  |  | 1782.5 | 231.725 | 2014.225 | 2021-03-04 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E LOA for Paul K |  | Approved |  |  | Reg Rd maint and repair on dore | 11 | F135-F149 | Dore lake Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6501AGCE-20210304-05-R1D4 Dozer11.51782.5 | AG Chapman Enterprises6501AGCE-20210304-05-R1D4 Dozer11.51782.5AGCE-2021-03-01-10 | [5 empty] | 1 | 1782.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6505 | AGCE-20210305-01 | 53511111 | Access | 0 | D4 Dozer | 155 | 4 | HR | 0 | 0 |  |  | 620 | 80.6 | 700.6 | 2021-03-05 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Joe B |  | Approved |  |  | Dozing abnd back blading the road HR 4 | 11 | F154 | Harbour Rd 4 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6505AGCE-20210305-01D4 Dozer4620 | AG Chapman Enterprises6505AGCE-20210305-01D4 Dozer4620AGCE-2021-03-01-10 | [5 empty] | 1 | 620 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6511 | AGCE-20210306-04 | 53511111 | Access | 0 | D4 Dozer | 155 | 3 | HR | 0 | 0 |  |  | 465 | 60.45 | 525.45 | 2021-03-06 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Walk dozer out to be floated awat, Pick up eco diesel | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6511AGCE-20210306-04D4 Dozer3465 | AG Chapman Enterprises6511AGCE-20210306-04D4 Dozer3465AGCE-2021-03-01-10 | [5 empty] | 1 | 465 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6449 | AGCE-20210224-04 | 53511111 | Access | 0 | D4 Dozer | 155 | 11.5 | HR | 0 | 0 |  |  | 1782.5 | 231.725 | 2014.225 | 2021-02-24 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Scraped Hensen Road east. Need to pull Rock truck off and bill to Kabi | 11 | F135-F149 | Hensen Road E | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6449AGCE-20210224-04D4 Dozer11.51782.5 | AG Chapman Enterprises6449AGCE-20210224-04D4 Dozer11.51782.5AGCE-2021-02-21-28 | [5 empty] | 1 | 1782.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7054 | AGCE-20210314-07 | 53511111 | Access | 0 | D4 Dozer | 155 | 5.5 | HR | 0 | 0 |  |  | 852.5 | 110.825 | 963.325 | 2021-03-14 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Walk Dozer out to Trembley Rd from Dore area to be demobed to Salt Ste | 11 | F135 | Dore | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7054AGCE-20210314-07D4 Dozer5.5852.5 | AG Chapman Enterprises7054AGCE-20210314-07D4 Dozer5.5852.5AGCE-2021-03-11-20 | [5 empty] | 1 | 852.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6064 | AGCE-20210126-2 | 53511111 | Access | 0 | Grader wing attachment | 35 | 4.5 | HR | 26.25 | 0 |  |  | 157.5 | 20.475 | 177.975 | 2021-01-26 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Alfred Chapman, removed |  | Approved |  |  | Grade and wing back banks on Tremblay Flats Rd, Access roads F163 to F162 | 11 | F163, F162 | Trembley Flats Rd | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6064AGCE-20210126-2Grader wing attachment4.5157.5 | AG Chapman Enterprises6064AGCE-20210126-2Grader wing attachment4.5157.5AGCE-2021-01-30 | [5 empty] | 1 | 157.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6062 | AGCE-20210205-2 | 53511111 | Access | 0 | Grader wing attachment | 35 | 5.5 | HR | 26.25 | 0 |  |  | 192.5 | 25.025 | 217.525 | 2021-02-05 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Alfred C, not eligible, local |  | Approved |  |  | Winter Access Maint Grade wings and back on Dore Rd. | 11 | F135-F147 | Dore Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6062AGCE-20210205-2Grader wing attachment5.5192.5 | AG Chapman Enterprises6062AGCE-20210205-2Grader wing attachment5.5192.5AGCE-2021-02-10 | [5 empty] | 1 | 192.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 881 | KL-20200108-1-R1 | 53510711 | Access | 0 | Supervisor | 84 | 6 | HR |  |  | 84 | 0 | 504 | 65.52 | 569.52 | 2020-01-10 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Buncher brushing road line on White Lake Rd., Float truck mobilizing mats from Thunder Bay. Supervisor on-site checking roads & ROW clearing. Buncher and skidder cleared estimated 0.8 Ha | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD881KL-20200108-1-R1Supervisor6504 | KABI LAKE FOREST PRODUCTS LTD881KL-20200108-1-R1Supervisor6504OEWT-PA1-LEM | [5 empty] | 1 | 504 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 888 | KL-20200114-2 | 53510711 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-01-17 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Winter Access Maintenance, dozer opening roads | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD888KL-20200114-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD888KL-20200114-2Supervisor3252OEWT-PA1-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 895 | KL-20200116-3-R1 | 53510711 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2020-01-23 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Winter road upgrade to site access | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43889 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD895KL-20200116-3-R1Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD895KL-20200116-3-R1Supervisor4336OEWT-PA1-LEM | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 902 | KL-20200121-2 | 53510711 | Access | 0 | Supervisor | 84 | 10 | HR |  |  | 84 | 0 | 840 | 109.2 | 949.2 | 2020-01-24 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Brushed 15M road ROW to D146. Dozer shaped & pushed snow back D-147 & D146 | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD902KL-20200121-2Supervisor10840 | KABI LAKE FOREST PRODUCTS LTD902KL-20200121-2Supervisor10840OEWT-PA1-LEM | [5 empty] | 1 | 840 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 934 | KL-20200126-3 | 53510711 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-01-26 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open Road from Hwy 17 to 3km on White Lake Road | 7 | D-142 to E-002 | White Lake | 0 | 43856 |  | 17 | 43861 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD934KL-20200126-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD934KL-20200126-3Supervisor2168OEWT-PA2-LEM-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 966 | KL-20200131-5 | 53510711 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-01-31 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clean and sweep off sand, gravel and snow off bridge | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 43867 |  | 41 | 43869 | [5 empty] | Tom Anderson | 07 | KABI LAKE FOREST PRODUCTS LTD966KL-20200131-5Supervisor184 | KABI LAKE FOREST PRODUCTS LTD966KL-20200131-5Supervisor184OEWT-PA2-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 975 | KL-20200131-10 | 53510711 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-01-31 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clean sand, gravel and snow from bridge on White Lake Road | 7 | D-142 to E-002 | White Lake | 0 | 43867 |  | 41 | 43869 | [5 empty] | Tom Anderson | 07 | KABI LAKE FOREST PRODUCTS LTD975KL-20200131-10Supervisor184 | KABI LAKE FOREST PRODUCTS LTD975KL-20200131-10Supervisor184OEWT-PA2-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1058 | KL-20200212-3 | 53510711 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-02-12 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Winter access - snow removal from D-142 to D-148 | 7 | D-142 to E-002 | White Lake | 0 | 43878 |  | 42 | 43882 | [5 empty] | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1058KL-20200212-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1058KL-20200212-3Supervisor2168OEWT-PA2-LEM-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1159 | KL-20200224-4 | 53510711 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-02-24 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Pick up buncher and drop off skidder | 7 | D-009 to D-017 | Three Finger Lake | 0 | 43889 |  | 43 | 43890 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1159KL-20200224-4Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1159KL-20200224-4Supervisor2168OEWT-PA2-LEM-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1291 | KL-20200313-1 | 53510711 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-03-13 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Grade road from HWY to D-038 and D-032 | 7 | D-032 to D-055 | Black River | 0 | 43908 |  | 42 | 43914 | [5 empty] | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1291KL-20200313-1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD1291KL-20200313-1Supervisor184OEWT-PA3-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1296 | KL-20200313-3 | 53510711 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-03-13 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade road from HWY and D038 to D054 | 7 | D-032 to D-055 | Black River | 0 | 43907 |  | 42 | 43914 | [5 empty] | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1296KL-20200313-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD1296KL-20200313-3Supervisor184OEWT-PA3-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1353 | KL-20200322-2 | 53510711 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-03-22 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | PICK UP BLASTING MAT FOR ROAD MAINTENANCE | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 43915 |  | 46 | 43919 | [5 empty] | Dave Ofukany | 07 | KABI LAKE FOREST PRODUCTS LTD1353KL-20200322-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1353KL-20200322-2Supervisor2168OEWT-PA3-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1369 | KL-20200323-5 | 53510711 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-03-23 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clearing Road and prep for log haul | 7 | D-032 to D-055 | Black River | 0 | 43917 |  | 46 | 43921 | [5 empty] | Dave Ofukany | 07 | KABI LAKE FOREST PRODUCTS LTD1369KL-20200323-5Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD1369KL-20200323-5Supervisor3252OEWT PA4-LEM-R1 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1378 | KL-20200324-8 | 53510711 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-03-24 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Prep and fix roads for log haul | 7 | D-032 to D-055 | Black River East | 0 | 43917 |  | 46 | 43921 | [5 empty] | Dave Ofukany | 07 | KABI LAKE FOREST PRODUCTS LTD1378KL-20200324-8Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1378KL-20200324-8Supervisor2168OEWT PA4-LEM-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1410 | KL-20200329-4 | 53510711 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-03-29 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Drag Road Black River East Main Access to D-051 | 7 | D-032 to D-055 | Black River | 0 | 43927 |  | 45 | 43924 | [5 empty] | Howard Beaudet | 07 | KABI LAKE FOREST PRODUCTS LTD1410KL-20200329-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD1410KL-20200329-4Supervisor184OEWT PA4-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1444 | KL-20200402-5 | 53510711 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-04-02 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair and maintain road from D054 to HWY 17 | 7 | D-032 to D-055 | Black River | 0 | 43930 |  | 43 | 43933 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1444KL-20200402-5Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1444KL-20200402-5Supervisor2168OEWT PA4-LEM-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4932 | KL-20201207-6 | 53510711 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Snow removal from D018 to D025 and filling ruts for freezing | 7 | D-018 to D-031 | Pie River | 0 | 44193 |  | 47 | 44202 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4932KL-20201207-6Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4932KL-20201207-6Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5040 | KL-20201218-1 | 53510711 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-12-18 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6K Dozer continuing road maintenance from D032 to D061 | 7 | D-032 to D-055 | Black River | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD5040KL-20201218-1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD5040KL-20201218-1Supervisor2168OEWT-PA12-LEM-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7851 | KL-20220207-9 | 53510711 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from White Lake West, clear hwy entrance, access & turn around for float access. | 7 | D100-D106 | 614 Road | 0 | 44604 |  | 61 | 44614 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7851KL-20220207-9Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7851KL-20220207-9Supervisor0.542OEWT-PA26-LEM | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7885 | KL-20220214-3 | 53510711 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-14 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run Grader from Kabi Yard to Alder Creek Road, clear snow @ entrance for float access and run grader back to Kabi Yard | 7 | D119-D141 | Alder Creek | 0 | 44614 |  | 61 | 44614 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7885KL-20220214-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7885KL-20220214-3Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7891 | KL-20220215-4 | 53510711 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-15 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on snow removal from Lay Down to D148 for wood grinding access and start snow removal to E002 for stringers | 7 | D142-E002 | White Lake West | 0 | 44614 |  | 61 | 44614 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7891KL-20220215-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7891KL-20220215-4Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7895 | KL-20220216-3 | 53510711 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-16 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing snow removal from Lay Down to D148 and to E002 for stringers | 7 | D142 - E002 | White Lake West | 0 | 44614 |  | 61 | 44614 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7895KL-20220216-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7895KL-20220216-3Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7951 | KL-20220207-8 | 53510711 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from 41 road to White Lake West & clear lay down for float turn around. | 7 | D142 - E002 | White Lake West | 0 |  |  | 61 | 44614 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7951KL-20220207-8Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7951KL-20220207-8Supervisor0.542OEWT-PA26-LEM | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 885 | KL-20200112-1-R2 | 53510712 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2020-01-23 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Terrance Bob | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Brush out White Lake Rd. for All season access | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD885KL-20200112-1-R2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD885KL-20200112-1-R2Supervisor4336OEWT-PA1-LEM | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 886 | KL-20200113-1-R1 | 53510712 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-01-23 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clear and brush existing road for equpiment access | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD886KL-20200113-1-R1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD886KL-20200113-1-R1Supervisor3252OEWT-PA1-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 941 | KL-20200128-2 | 53510712 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-01-28 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clear snow from access road. | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 43861 |  | 17 | 43863 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD941KL-20200128-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD941KL-20200128-2Supervisor184OEWT-PA2-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1404 | KL-20200328-2 | 53510712 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-03-28 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Push snow banks back on access road , scrape road and grade | 7 | D-119 to D-141 | Alder Creek | 0 | 43925 |  | 45 | 43924 | [5 empty] | Howard Beaudet | 07 | KABI LAKE FOREST PRODUCTS LTD1404KL-20200328-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD1404KL-20200328-2Supervisor184OEWT PA4-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1551 | KL-20200521-3 | 53510712 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-05-21 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Ditching and Shaping Road | 7 | D032-D055 | Black River East | 0 | 43977 |  | 15 | 43977 | [5 empty] | Martin Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD1551KL-20200521-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD1551KL-20200521-3Supervisor184OEWT-PA5-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1886 | KL-20200626-7 | 53510712 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-06-26 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade section on 100 road to 5km pit for gravel haul to Alder Creek | 7 | D-119 to D-141 | Alder Creek | 0 | 44038 |  | 47 | 44014 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD1886KL-20200626-7Supervisor184 | KABI LAKE FOREST PRODUCTS LTD1886KL-20200626-7Supervisor184OEWT-PA7-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2018 | KL-20200712-9 | 53510712 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-07-12 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 100 Road from Hwy to 5KM pit for gravel haul | 7 | D-119 to D-141 | Alder Creek | 0 | 44027 |  | 48 | 44028 | [5 empty] | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2018KL-20200712-9Supervisor184 | KABI LAKE FOREST PRODUCTS LTD2018KL-20200712-9Supervisor184OEWT-PA7-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2019 | KL-20200712-10 | 53510712 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-07-12 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Grade 600 road from Km 4 to Km 9 | 9 | E-091 to E-102 | 600 Road | 0 | 44027 | [9 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD2019KL-20200712-10Supervisor184 | KABI LAKE FOREST PRODUCTS LTD2019KL-20200712-10Supervisor184OEWT-PA7-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2092 | KL-20200717-4 | 53510712 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-07-17 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road to D055 to D053 | 7 | D-056 to D-073 | Umbatta Falls | 0 | 44034 |  | 48 | 44034 | [5 empty] | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2092KL-20200717-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD2092KL-20200717-4Supervisor184OEWT-PA7-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2101 | KL-20200717-13 | 53510712 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-07-17 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 100 road from Hwy to 5km pit for gravel Haul | 7 | D-100 to D-106 | 614 Road | 0 | 44034 |  | 48 | 44034 | [5 empty] | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2101KL-20200717-13Supervisor184 | KABI LAKE FOREST PRODUCTS LTD2101KL-20200717-13Supervisor184OEWT-PA7-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2108 | KL-20200718-6 | 53510712 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-07-18 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road from D053 to D043 | 7 | D-032 to D-055 | Black River | 0 | 44034 |  | 48 | 44034 | [5 empty] | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2108KL-20200718-6Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD2108KL-20200718-6Supervisor2168OEWT-PA7-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2275 | KL-20200726-6 | 53510712 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-07-26 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road maintenance from D109 to D112 | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 44041 |  | 48 | 44041 | [5 empty] | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2275KL-20200726-6Supervisor184 | KABI LAKE FOREST PRODUCTS LTD2275KL-20200726-6Supervisor184OEWT-PA8-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2300 | KL-20200729-3 | 53510712 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-07-29 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road Maintenance from D118 to D116 | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 44047 |  | 50 | 44048 | [5 empty] | Jim Budgell | 07 | KABI LAKE FOREST PRODUCTS LTD2300KL-20200729-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD2300KL-20200729-3Supervisor2168OEWT-PA8-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2426 | KL-20200812-2 | 53510712 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-08-12 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 2 Rock Trucks hauling from stock pile to D132/ Excavator loading | 7 | D-119 to D-141 | Alder Creek | 0 | 44060 |  | 47 | 44061 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD2426KL-20200812-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD2426KL-20200812-2Supervisor2168OEWT-PA8-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2430 | KL-20200812-6 | 53510712 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-08-12 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road Maintenance from D114 to D119 | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 44060 |  | 47 | 44061 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD2430KL-20200812-6Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD2430KL-20200812-6Supervisor2168OEWT-PA8-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3624 | KL-20201009-13 | 53510712 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-10-09 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD3624KL-20201009-13Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD3624KL-20201009-13Supervisor2168OEWT-PA10-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3820 | KL-20201018-4 | 53510712 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-10-18 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Level ruts in Access to D096 to D097 for Drainage | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44130 |  | 47 | 44131 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD3820KL-20201018-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD3820KL-20201018-4Supervisor184OEWT-PA10-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4293 | KL-20201110-3 | 53510712 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and spread gravel and chips D071-D073 BMC-30143 | 7 | D065-D066 | Camp 36 Road | 0 | 44166 |  | 53 | 44168 | [5 empty] | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD4293KL-20201110-3Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD4293KL-20201110-3Supervisor4336OEWT-PA11-LEM | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4352 | KL-20201114-5 | 53510712 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-14 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc working access from D125 to D129/1 hr excavator & grinder travel due to poor condition of access mats D121 to D132 | 7 | D-119 to D-141 | Alder Creek | 0 | 44166 |  | 53 | 44171 | [5 empty] | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD4352KL-20201114-5Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4352KL-20201114-5Supervisor184OEWT-PA11-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4456 | KL-20201119-2 | 53510712 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-19 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working access to ROW and from D074 to D078, leveling ruts and track packing road | 7 | D-074 to D-079 | Brett’s Road | 0 | 44167 |  | 47 | 44172 | [5 empty] | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4456KL-20201119-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4456KL-20201119-2Supervisor184OEWT-PA11-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7428 | KL-20211005-2 | 53510712 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-10-05 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road & hauling concrete anchors on a rig mat for LEG. Excavator levelling ruts, shaping road, assisting pickups & rock truck. | 7 | D018-D031 | Pic River | 0 | 44477 |  | 37 | 44478 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7428KL-20211005-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7428KL-20211005-2Supervisor3252OEWT-PA22-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7432 | KL-20211006-2 | 53510712 | Access | 0 | Supervisor | 84 | 3.5 | HR |  |  | 84 | 0 | 294 | 38.22 | 332.22 | 2021-10-06 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping road and pushing rock trucks hauling gravel to D025 /excavator leveling ruts and shaping road. | 7 | D018-D031 | Pic river | 0 | 44484 |  | 63 | 44484 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7432KL-20211006-2Supervisor3.5294 | KABI LAKE FOREST PRODUCTS LTD7432KL-20211006-2Supervisor3.5294OEWT-PA22-Lem | [5 empty] | 1 | 294 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7435 | KL-20211007-2 | 53510712 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-10-07 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer & excavator levelling ruts & shaping road from D-019 to D-025. | 7 | D018-D031 | Pic River | 0 | 44484 |  | 37 | 44495 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7435KL-20211007-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7435KL-20211007-2Supervisor2168OEWT-PA22-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7437 | KL-20211008-2 | 53510712 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-10-08 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer & excavator finishing levelling ruts & shaping road from D-019 to D-025 for pickup access. | 7 | D018-D031 | Pic River | 0 | 44484 |  | 37 | 44495 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7437KL-20211008-2Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7437KL-20211008-2Supervisor0.542OEWT-PA22-Lem | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7399 | KL-20210927-3 | 53510712 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-09-27 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue hauling pit run from Cress Pit & spreading on ROW access. Dozer levelling ruts after hours. | 7 | D018-D031 | Pic River | 0 | 44475 |  | 62 | 44478 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7399KL-20210927-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7399KL-20210927-3Supervisor2168OEWT-PA22-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7405 | KL-20210928-3 | 53510712 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-09-28 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue hauling pit run from Cress Pit & spreading on ROW access/excavator fixing soft areas & track packing for gravel trucks. Labourer sweeping dirt off Hwy 17 | 7 | D018-D031 | pic River West | 0 | 44475 |  | 62 | 44478 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7405KL-20210928-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7405KL-20210928-3Supervisor2168OEWT-PA22-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7425 | KL-20211004-2 | 53510712 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-10-04 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer & excavator levelling ruts, shaping road, pulling pickups & grout truck to D025 due to wet conditions. Excavator working after hours until all crews got out. | 7 | D018-D031 | Pic River | 0 | 44477 |  | 37 | 44478 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7425KL-20211004-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7425KL-20211004-2Supervisor3252OEWT-PA22-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7487 | KL-20211024-3 | 53510712 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-10-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer leveling ruts and shaping road from Hwy 17 to D018 and to D025 after completion of foundation work | 7 | D018-D031 | Pic River | 0 | 44493 |  | 61 | 44497 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7487KL-20211024-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7487KL-20211024-3Supervisor184OEWT-PA23-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1150 | KL-20200224-6 | 53510811 | Access | 0 | Supervisor | 84 | 1.5 | HR |  |  | 84 | 0 | 126 | 16.38 | 142.38 | 2020-02-24 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Flag to drop off Dozer D6 | 8 | E086 - E094 | Blue Cedar E | 0 | 43889 |  | 43 | 43890 | [5 empty] | Dean MacArthur | 08 | KABI LAKE FOREST PRODUCTS LTD1150KL-20200224-6Supervisor1.5126 | KABI LAKE FOREST PRODUCTS LTD1150KL-20200224-6Supervisor1.5126OEWT-PA2-LEM-R1 | [5 empty] | 1 | 126 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1244 | KL-20200308-1 | 53510811 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-03-08 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | E-042 to E-053 Open access road to ROW | 8 | E068 - E076 | Denis Lake W | 0 | 43903 |  | 42 | 43910 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1244KL-20200308-1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1244KL-20200308-1Supervisor2168OEWT-PA3-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1299 | KL-20200313-6 | 53510811 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-03-13 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open road from HWY to E-049 | 8 | E-042 to E-053 | Denis Lake W | 0 | 43907 |  | 42 | 43914 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1299KL-20200313-6Supervisor184 | KABI LAKE FOREST PRODUCTS LTD1299KL-20200313-6Supervisor184OEWT-PA3-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1333 | KL-20200319-7 | 53510811 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-03-19 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | PLOW OPEN (WIDEN) ACCESS RD | 8 | E-062 to E-067 | Buck Lake | 0 | 43913 |  | 42 | 43917 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1333KL-20200319-7Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1333KL-20200319-7Supervisor2168OEWT-PA3-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1496 | KL-20200401-7-R1 | 53510811 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-04-01 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair rutts on main access road | 8 | E042-E059 | Denis Lake Road West | 0 | 43933 |  | 45 | 43934 | [5 empty] | Howard Beaudet | 08 | KABI LAKE FOREST PRODUCTS LTD1496KL-20200401-7-R1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD1496KL-20200401-7-R1Supervisor184OEWT PA4-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4654 | KL-20201126-8 | 53510811 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load sand from 6km pit on 600 road and sand Access from Hwy to E073 for concrete haul as per discussion with Valard | 8 | E068-E076 | North Crockers Lake | 0 | 44178 |  | 47 | 44183 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4654KL-20201126-8Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4654KL-20201126-8Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4787 | KL-20201203-7 | 53510811 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-12-03 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Padda Roadlines hauling pit run from 5 km pit on 100 road to stockpile/labourers sanding access to stockpile with pickup and shovels. | 8 | E004-E016 | White Lake East | 0 | 44193 |  | 53 | 44207 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4787KL-20201203-7Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD4787KL-20201203-7Supervisor2168OEWT-PA12-LEM-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4902 | KL-20201205-5 | 53510811 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-05 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding Silver City AU1 Access to E025 as per Valard | 8 | E025-E036 | Silver City | 0 | 44193 |  | 53 | 44207 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4902KL-20201205-5Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4902KL-20201205-5Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5000 | KL-20201214-3 | 53510811 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding and Grading Access to E073 for concrete haul as per Valard | 8 | E004-E016 | White Lake East | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD5000KL-20201214-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5000KL-20201214-3Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5151 | KL-20201228-2 | 53510811 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-28 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6K Dozer working on snow removal from Hwy 17 to E014/E015 Access | 8 | E004-E016 | White Lake East | 0 | 43836 |  | 36 | 44213 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD5151KL-20201228-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5151KL-20201228-2Supervisor184OEWT-PA13-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5858 | KL-20210211-2 | 53510811 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-02-11 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer doing snow removal from 9020.00 WC to Hwy 17 | 8 | E004-E016 | White Lake East | 0 | 44244 |  | 36 | 44250 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD5858KL-20210211-2Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD5858KL-20210211-2Supervisor0.542OEWT-PA14-Lem-R1 | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7839 | KL-20220205-4 | 53510811 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-05 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from Kabi yard, clear snow around highway entrance and turn around for float access. | 8 | E042-E058 | Denis Lake W | 0 | 44603 |  | 61 | 44603 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7839KL-20220205-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7839KL-20220205-4Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7840 | KL-20220205-5 | 53510811 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-05 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run Grader From Denis Lake West to 41 Road, Clear Snow @ Hwy Entrance, Open Road & Turn Around For Float Access/Supervisor Doing Pickup Shuffle | 8 | E037 - E041 | Road 41 | 0 | 44603 |  | 61 | 44603 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7840KL-20220205-5Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7840KL-20220205-5Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7848 | KL-20220207-5 | 53510811 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader clearing hwy entrance, open road & turn around for float access. | 8 | E037-E041 | 41 Road | 0 | 44604 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7848KL-20220207-5Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7848KL-20220207-5Supervisor0.542OEWT-PA26-LEM | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7849 | KL-20220207-6 | 53510811 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from 614 road & clear entrance for float access. | 8 | E004 - E010 | White Lake East | 0 | 44604 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7849KL-20220207-6Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7849KL-20220207-6Supervisor0.542OEWT-PA26-LEM | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7850 | KL-20220207-7 | 53510811 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from White Lake East, clear hwy entrance & turn around for float access. Run grader to 41 road & park. | 8 | E011-E025 | North Regan | 0 | 44604 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7850KL-20220207-7Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7850KL-20220207-7Supervisor0.542OEWT-PA26-LEM | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7856 | KL-20220208-5 | 53510811 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-08 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run Grader From 41 Road,Clear Hwy Entrance, Open Road For Float Access & Run Grader Back To Kabi Yard | 8 | E025-E036 | Silver City | 0 | 44604 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7856KL-20220208-5Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7856KL-20220208-5Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7863 | KL-20220209-6 | 53510811 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-09 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hwy 17 to E002 | 10 |  | White Lake east | 0 | 44604 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7863KL-20220209-6Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7863KL-20220209-6Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7868 | KL-20220210-5 | 53510811 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-10 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal from Hwy 17 to E002 and to E008 | 8 | E004 - E010 | White Lake East | 0 | 44605 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7868KL-20220210-5Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7868KL-20220210-5Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7871 | KL-20220211-3 | 53510811 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-11 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal from Hwy 17 to E004 | 8 | E004 - E010 | White Lake East | 0 | 44605 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7871KL-20220211-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7871KL-20220211-3Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7872 | KL-20220211-4 | 53510811 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-11 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on snow removal from E034 to E035/E036 for wood grinding access | 8 | E025-E036 | SIlver City | 0 | 44605 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7872KL-20220211-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7872KL-20220211-4Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7882 | KL-20220213-6 | 53510811 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-13 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal and widening from Hwy 17 to E004 and clearing pad @ E005 | 8 | E004 - E010 | White Lake East | 0 | 44614 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7882KL-20220213-6Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7882KL-20220213-6Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7886 | KL-20220214-4 | 53510811 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-14 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and widening from Hwy 17 to E013 and clearing pad @ E013 | 8 | E004-E010 | White Lake East | 0 | 44614 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7886KL-20220214-4Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7886KL-20220214-4Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7890 | KL-20220215-3 | 53510811 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-15 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer finishing snow removal and widening from Hwy 17 to E013 | 8 | E004 - E010 | White Lake East | 0 | 44614 |  | 61 | 44614 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7890KL-20220215-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7890KL-20220215-3Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7907 | KL-20220219-3 | 53510811 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-19 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal & clearing pull offs from Hwy 17 to E051. | 8 | E042 - E058 | Denis Lake W | 0 | 44617 |  | 61 | 44617 | [6 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7907KL-20220219-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7907KL-20220219-3Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7916 | KL-20220223-1 | 53510811 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-23 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hwy 17 to E013 & to E005. | 8 | E004 - E010 | White Lake East | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 08 | KABI LAKE FOREST PRODUCTS LTD7916KL-20220223-1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7916KL-20220223-1Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7943 | KL-20220227-6 | 53510811 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Dozer working on snow removal & clearing pull offs from Hwy 17 to E-051 | 8 | E042 - E058 | Denis Lake W | 0 | 44628 | [9 empty] | 08 | KABI LAKE FOREST PRODUCTS LTD7943KL-20220227-6Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7943KL-20220227-6Supervisor0.542 | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1322 | KL-20200317-7 | 53510812 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | RV-40002 SPREAD GRAVEL; HAUL GRAVEL IN SOFT SOPT ACROSS HONI LINE AND TO GAIN ACCESS OVER ROCK IN EXISTING ENTRANCE RD | 8 | E-077 to E-091 | Blue Cedar W | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7Supervisor3252OEWT-PA3-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1542 | KL-20200520-13 | 53510812 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-05-20 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start Ditching main access road | 8 | E068-E076 | North Crockers Lake | 0 | 43976 |  | 15 | 43977 | [5 empty] | Martin Hunt | 08 | KABI LAKE FOREST PRODUCTS LTD1542KL-20200520-13Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1542KL-20200520-13Supervisor2168OEWT-PA5-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1640 | KL-20200602-10 | 53510812 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-06-02 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 100 road to 5 KM Pit gor Blue Cedar Gravel Haul | 8 | E077-E091 | Blue Cedar Road | 0 | 43987 |  | 15 | 43988 | [5 empty] | Martin Hunt | 08 | KABI LAKE FOREST PRODUCTS LTD1640KL-20200602-10Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1640KL-20200602-10Supervisor2168OEWT-PA6-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2941 | KL-20200915-12 | 53510812 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-15 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 100 road to 5Km pit for gravel haul | 8 | E068 - E076 | Denis Lake W | 0 | 44096 |  | 15 | 44097 | [5 empty] | Martin Hunt | 08 | KABI LAKE FOREST PRODUCTS LTD2941KL-20200915-12Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2941KL-20200915-12Supervisor3252OEWT-PA9-Lem-R1 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3900 | KL-20201025-4 | 53510812 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-10-25 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator starting maintenance on access for concrete truck as per Valard | 8 | E-077 to E-091 | Blue Cedar Road | 0 | 44133 |  | 47 | 44133 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3900KL-20201025-4Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD3900KL-20201025-4Supervisor2168OEWT-PA10-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3982 | KL-20201026-7 | 53510812 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-10-26 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 excavator doing maintenance on access for concrete trucks as per Valard | 8 | E077-E091 | Blue Cedar | 0 | 44147 |  | 47 | 44151 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3982KL-20201026-7Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD3982KL-20201026-7Supervisor3252OEWT-PA11-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3999 | KL-20201027-4 | 53510812 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-10-27 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 excavator doing road maintenance on access for Concrete trucks as per Valard | 8 | E-077 to E-091 | Blue Cedar W | 0 | 44147 |  | 47 | 44151 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3999KL-20201027-4Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD3999KL-20201027-4Supervisor3252OEWT-PA11-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4096 | KL-20201101-5 | 53510812 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-01 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator doing Road Maintenance on Access per Valard | 8 | E077-E091 | Blue Cedar W | 0 | 44152 |  | 47 | 44163 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4096KL-20201101-5Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4096KL-20201101-5Supervisor184OEWT-PA11-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4207 | KL-20201107-1 | 53510812 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-07 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Scrape Mud from exiting vehicles to hwy 17 at entrance to silver sity. Pickup with beacon, flag paddle and radio contact watching traffic | 8 | E025-E036 | Silver City | 0 | 44162 |  | 56 | 44163 | [5 empty] | Mandy Sandhu | 08 | KABI LAKE FOREST PRODUCTS LTD4207KL-20201107-1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4207KL-20201107-1Supervisor184OEWT-PA11-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4409 | KL-20201116-8 | 53510812 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T dozer working on road, levelling ruts from E069 to E073 as per Valard. (Cost Code as per Frank 53510812) | 8 | E068-E076 | North Crockers Lake | 0 | 44167 |  | 47 | 44171 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4409KL-20201116-8Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4409KL-20201116-8Supervisor184OEWT-PA11-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4410 | KL-20201116-9 | 53510812 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Charged to move Cat D6T dozer to E069/due to Adam from foundations (Cost Code 53510812 as per Frank) | 8 | E068-E076 | North Crockers Lake | 0 | 44167 |  | 47 | 44171 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4410KL-20201116-9Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4410KL-20201116-9Supervisor184OEWT-PA11-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4425 | KL-20201117-5 | 53510812 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-11-17 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T dozer working on road, levelling ruts from E069 to E073 as per Valard/Support for Foundations (CC as per Frank 53510812) | 8 | E068-E076 | North Crockers Lake | 0 | 44167 |  | 47 | 44172 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4425KL-20201117-5Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD4425KL-20201117-5Supervisor2168OEWT-PA11-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4460 | KL-20201119-6 | 53510812 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-11-19 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T dozer working on road leveling ruts from E069 to E073 as per valard/ Support for foundations | 8 | E068-E076 | North Crockers Lake | 0 | 44167 |  | 47 | 44172 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4460KL-20201119-6Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD4460KL-20201119-6Supervisor2168OEWT-PA11-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4485 | KL-20201120-11 | 53510812 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-11-20 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | (CC 53510812 as per Frank) needs cost code changed. |  | Approved |  |  | Cat D6T dozer working on road, levelling ruts from E069 to E073 as per Valard/support for Foundations (CC 53510812 as per Frank) | 8 | E068-E076 | North Regan | 0 | 44167 |  | 47 | 44173 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4485KL-20201120-11Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD4485KL-20201120-11Supervisor2168OEWT-PA11-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4507 | KL-20201121-8 | 53510812 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-21 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working access from E077 to E086, levelling ruts & track packing road | 8 | E077-E091 | Blue Cedar Road | 0 | 44167 |  | 47 | 44174 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4507KL-20201121-8Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4507KL-20201121-8Supervisor184OEWT-PA11-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4550 | KL-20201122-8 | 53510812 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-22 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working access from E086 to E091, leveling ruts and track packing road for freezing | 8 | E077-E091 | Blue Cedar W | 0 | 44172 |  | 47 | 44184 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4550KL-20201122-8Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4550KL-20201122-8Supervisor184OEWT-PA11-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4551 | KL-20201122-9 | 53510812 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-22 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T dozer working on AU1 Access shaping and leveling ruts/cleaning up the turn around | 8 | E062-E067 | Buck Lake Road | 0 | 44172 |  | 47 | 44183 | [5 empty] | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4551KL-20201122-9Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4551KL-20201122-9Supervisor184OEWT-PA11-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6900 | KL-20210510-3 | 53510812 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-05-10 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 962M loader repairing washout @Blue Cedar entrance/Labourer escorting loader on Hwy 17 from Kabi Yard and back | 8 | E077-E091 | Blue Cedar | 0 | 44337 |  | 56 | 44341 | [5 empty] | Mandy Sandhu | 08 | KABI LAKE FOREST PRODUCTS LTD6900KL-20210510-3Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD6900KL-20210510-3Supervisor0.542OEWT-PA17-LEM | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6922 | KL-20210515-6 | 53510812 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-05-15 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading, hauling and spreading pit run from stock pile to E007/E006 access/loading and hauling trees for soft sections/dozer leveling ruts and excavator placing corduroy | 8 | E004-E016 | White Lake East | 0 | 44337 |  | 56 | 44342 | [5 empty] | Mandy Sandhu | 08 | KABI LAKE FOREST PRODUCTS LTD6922KL-20210515-6Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD6922KL-20210515-6Supervisor3252OEWT-PA17-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6925 | KL-20210516-2 | 53510812 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-05-16 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator ditching along access @ E006 to E007 for capping material | 8 | E004-E016 | White Lake East | 0 | 44337 |  | 56 | 44343 | [5 empty] | Mandy Sandhu | 08 | KABI LAKE FOREST PRODUCTS LTD6925KL-20210516-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD6925KL-20210516-2Supervisor2168OEWT-PA17-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6945 | KL-20210518-2 | 53510812 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-05-18 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | loading , hauling and spreading existing material @ E014 for road repairs from E014.5 to E016 to maintain pickup access | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44349 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6945KL-20210518-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD6945KL-20210518-2Supervisor184OEWT-PA17-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6947 | KL-20210518-4 | 53510812 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-05-18 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Original route was reclaimed, total supervision 7 hours. |  | Approved |  |  | Excavator leveling ruts and shapes access to E007 for drainage | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44349 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6947KL-20210518-4Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD6947KL-20210518-4Supervisor0.542OEWT-PA17-LEM | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6951 | KL-20210519-2 | 53510812 | Access | 0 | Supervisor | 84 | 1.5 | HR |  |  | 84 | 0 | 126 | 16.38 | 142.38 | 2021-05-19 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading, hauling and spreading exsiting material @ E014 for road repairs from E016 to E013.5 (revised) | 8 | E034 - E036 | White Lake East | 0 | 44345 |  | 14 | 44352 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6951KL-20210519-2Supervisor1.5126 | KABI LAKE FOREST PRODUCTS LTD6951KL-20210519-2Supervisor1.5126OEWT-PA17-LEM | [5 empty] | 1 | 126 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6959 | KL-20210520-1 | 53510812 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread existing material @ 1.5 km and pit run from stock pile for road repair on E007/E006 main access road/ Laboures laying Geo ( revised) | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6959KL-20210520-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD6959KL-20210520-1Supervisor3252OEWT-PA17-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6960 | KL-20210520-2 | 53510812 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat excavator Leveling ruts and shaping road from E016 to E010 | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6960KL-20210520-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD6960KL-20210520-2Supervisor2168OEWT-PA17-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6965 | KL-20210520-7 | 53510812 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourers shovelling, sweeping bridges & signage repairs @ 9020.00-WC, 801.00-WC, 9010.00-WC & 9040.00-WC. | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6965KL-20210520-7Supervisor184 | KABI LAKE FOREST PRODUCTS LTD6965KL-20210520-7Supervisor184OEWT-PA17-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6967 | KL-20210521-2 | 53510812 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-05-21 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material from stockpile for road repairs to the access going into E005. Dozer spreading loads from from rock truck and fixing ruts. | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6967KL-20210521-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD6967KL-20210521-2Supervisor3252OEWT-PA17-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6970 | KL-20210522-1 | 53510812 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-05-22 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material from stock pile and bundles of wood from the main road to E006 for road repairs, dozer spreading loads and pushing up bundle of wood | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44348 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6970KL-20210522-1Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD6970KL-20210522-1Supervisor4336OEWT-PA17-LEM | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6977 | KL-20210523-4 | 53510812 | Access | 0 | Supervisor | 84 | 3.5 | HR |  |  | 84 | 0 | 294 | 38.22 | 332.22 | 2021-05-23 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread material for road repairs near E011, 330 loading material and dozer spreading loads from rock truck and fixing punch outs | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6977KL-20210523-4Supervisor3.5294 | KABI LAKE FOREST PRODUCTS LTD6977KL-20210523-4Supervisor3.5294OEWT-PA17-LEM | [5 empty] | 1 | 294 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6980 | KL-20210524-1 | 53510812 | Access | 0 | Supervisor | 84 | 2.5 | HR |  |  | 84 | 0 | 210 | 27.3 | 237.3 | 2021-05-24 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 excavator working on drainage out of E016/Dozer leveling ruts and back blading out from E016 to E006 | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6980KL-20210524-1Supervisor2.5210 | KABI LAKE FOREST PRODUCTS LTD6980KL-20210524-1Supervisor2.5210OEWT-PA17-LEM | [5 empty] | 1 | 210 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6983 | KL-20210525-2 | 53510812 | Access | 0 | Supervisor | 84 | 3.5 | HR |  |  | 84 | 0 | 294 | 38.22 | 332.22 | 2021-05-25 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load Haul and spread existing material @ E014 for Road repairs from E015 to E016/Excavator and Dozer working on Road maintenance E013 to E006 | 8 | E004-E016 | White Lake East | 0 | 44343 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6983KL-20210525-2Supervisor3.5294 | KABI LAKE FOREST PRODUCTS LTD6983KL-20210525-2Supervisor3.5294OEWT-PA17-LEM | [5 empty] | 1 | 294 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6988 | KL-20210526-1 | 53510812 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-05-26 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer working on road maintenance leveling ruts and drainage E011 to E016 | 8 | E004-E016 | White Lake East | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6988KL-20210526-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD6988KL-20210526-1Supervisor3252OEWT-PA18-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6991 | KL-20210527-1 | 53510812 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-05-27 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer working on road maintenance leveling ruts and drainage E006 to E016/ Supervisor site visit with Valard ROW and directing Operators | 8 | E004-E016 | White Lake East | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6991KL-20210527-1Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD6991KL-20210527-1Supervisor4336OEWT-PA18-Lem | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6993 | KL-20210528-1 | 53510812 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-05-28 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer working on road maintenance leveling ruts and drainage E006 to E016/ Start shaping hill @E017 Access | 8 | E004-E016 | White Lake East | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6993KL-20210528-1Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD6993KL-20210528-1Supervisor4336OEWT-PA18-Lem | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6999 | KL-20210531-1 | 53510812 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-05-31 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauling existing material for covering of soft sections on E005 access | 8 | E004-E016 | White Lake East | 0 | 44358 |  | 36 | 44359 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD6999KL-20210531-1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD6999KL-20210531-1Supervisor184OEWT-PA18-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7002 | KL-20210601-1 | 53510812 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-06-01 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road and leveling ruts from 8907.01 WC to Hwy 17/Cleaning up old access road from E007 to E006 as new route was built | 8 | E004-E016 | White Lake East | 0 | 44358 |  | 14 | 44359 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD7002KL-20210601-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7002KL-20210601-1Supervisor3252OEWT-PA18-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7068 | KL-20210529-2 | 53510812 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-05-29 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and Dozer shaping hill and filling ruts on E017 access from E016 | 8 | E004-E016 | White Lake East | 0 | 44372 |  | 36 | 44373 | [5 empty] | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD7068KL-20210529-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7068KL-20210529-2Supervisor184OEWT-PA18-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7268 | KL-20210823-2 | 53510812 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-08-23 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair & shape road from 9049.00 WC to E-017. Loader loading rig mats on float for return to Valard Marathon yard | 8 | E017-E024 | North Regan | 0 | 44438 |  | 50 | 44440 | [5 empty] | Jim Budgell | 08 | KABI LAKE FOREST PRODUCTS LTD7268KL-20210823-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7268KL-20210823-2Supervisor2168OEWT-PA20-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1153 | KL-20200225-3 | 53510911 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-02-25 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open 600 Road KM 10-15 | 9 | E-091-E102 | 600 rd | 0 | 43889 |  | 43 | 43890 | [5 empty] | Dean MacArthur | 09 | KABI LAKE FOREST PRODUCTS LTD1153KL-20200225-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1153KL-20200225-3Supervisor2168OEWT-PA2-LEM-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1173 | KL-20200226-10 | 53510911 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-03-26 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 600 RD - Continue to plow road to gain access to 20KM | 9 | E091-E121 | 600 Road | 0 | 43894 |  | 43 | 43896 | [5 empty] | Dean MacArthur | 09 | KABI LAKE FOREST PRODUCTS LTD1173KL-20200226-10Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1173KL-20200226-10Supervisor2168OEWT-PA3-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1178 | KL-20200227-3 | 53510911 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-02-27 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 600 Rd winter road maintenance - continue to open 600 rd @ 22km | 9 | E091-E121 | 600 Road | 0 | 43894 |  | 43 | 43896 | [5 empty] | Dean MacArthur | 09 | KABI LAKE FOREST PRODUCTS LTD1178KL-20200227-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1178KL-20200227-3Supervisor2168OEWT-PA3-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1184 | KL-20200228-3 | 53510911 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-02-28 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 600 Rd - plow 600 rd for access @30km. | 9 | E091-E102 | 600 road | 0 | 43896 |  | 45 | 43914 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1184KL-20200228-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1184KL-20200228-3Supervisor2168OEWT-PA3-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1189 | KL-20200229-3 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-02-29 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 600 Rd - open 600 road to 32KM | 9 | E091-E102 | 600 Road | 0 | 43896 |  | 45 | 43914 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1189KL-20200229-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD1189KL-20200229-3Supervisor184OEWT-PA3-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1234 | KL-20200306-5 | 53510911 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-03-06 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open 600 road to 32 KM | 9 | E-091 to E-102 | 600 Road | 0 | 43901 |  | 42 | 43910 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1234KL-20200306-5Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1234KL-20200306-5Supervisor2168OEWT-PA3-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1310 | KL-20200316-4 | 53510911 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-03-16 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open road by KM 30 and plow after snowfall | 9 | E-091 to E-102 | 600 Road | 0 | 43908 |  | 42 | 43915 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1310KL-20200316-4Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1310KL-20200316-4Supervisor2168OEWT-PA3-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1315 | KL-20200317-1 | 53510911 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open road on 600 around km 36 | 9 | E-091 to E-102 | 600 Road. | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1315KL-20200317-1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1315KL-20200317-1Supervisor2168OEWT-PA3-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1324 | KL-20200318-2 | 53510911 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2020-03-18 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | PLOW OPEN ROAD AT 40KM AND WING BACK BANKS | 9 | E-091 to E-102 | 600 Road | 0 | 43911 |  | 42 | 43915 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1324KL-20200318-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD1324KL-20200318-2Supervisor4336OEWT-PA3-LEM | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1382 | KL-20200325-4 | 53510911 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-03-25 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow open 600 road to gain access | 9 | E-091 to E-102 | 600 Road | 0 | 43922 |  | 45 | 43923 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1382KL-20200325-4Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD1382KL-20200325-4Supervisor3252OEWT PA4-LEM-R1 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1400 | KL-20200327-5 | 53510911 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-03-27 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open 600 for WF-9 access and grade road | 9 | E-091 to E-102 | 600 Road | 0 | 43925 |  | 45 | 43924 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1400KL-20200327-5Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1400KL-20200327-5Supervisor2168OEWT PA4-LEM-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1411 | KL-20200329-5 | 53510911 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-03-29 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open up 600 raod (plow snow) | 9 | E-091 to E-102 | 600 Road | 0 | 43927 |  | 45 | 43924 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1411KL-20200329-5Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1411KL-20200329-5Supervisor2168OEWT PA4-LEM-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1418 | KL-20200330-6 | 53510911 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-03-30 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Open up 600 Road (plow snow) | 9 |  | 600 Road | 0 | 43928 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD1418KL-20200330-6Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD1418KL-20200330-6Supervisor3252OEWT PA4-LEM-R1 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1427 | KL-20200331-7 | 53510911 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-03-31 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow off road | 9 | E091-E102 | 600 Road | 0 | 43928 |  | 45 | 43929 | [5 empty] | Howard Beaudet | 09 | KABI LAKE FOREST PRODUCTS LTD1427KL-20200331-7Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1427KL-20200331-7Supervisor2168OEWT PA4-LEM-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4113 | KL-20201102-9 | 53510911 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-11-02 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading sander truck and sorting materials at km 20 an km 6 pits on the 600 road and 100 road | 9 | E091-E102 | 600 Rd | 0 | 44153 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4113KL-20201102-9Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD4113KL-20201102-9Supervisor3252OEWT-PA11-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4135 | KL-20201103-5 | 53510911 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading Sand Truck and sorting material at 20km pit and 6km pit on 600 road, sanding 600, 700 and 100 roads | 9 | E-091 to E-102 | 600 Rd | 0 | 44153 |  | 50 | 44159 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4135KL-20201103-5Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD4135KL-20201103-5Supervisor2168OEWT-PA11-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4417 | KL-20201116-16 | 53510911 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road and 100 road to km5 pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4417KL-20201116-16Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD4417KL-20201116-16Supervisor2168OEWT-PA11-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4430 | KL-20201117-9 | 53510911 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-11-17 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 Rd and 100 Rd to km5 pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4430KL-20201117-9Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD4430KL-20201117-9Supervisor2168OEWT-PA11-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4439 | KL-20201118-11 | 53510911 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-11-18 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road and 100 road to 5km pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4439KL-20201118-11Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD4439KL-20201118-11Supervisor2168OEWT-PA11-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4462 | KL-20201119-8 | 53510911 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-11-19 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding 600 road and 100 road to 5km pit | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4462KL-20201119-8Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD4462KL-20201119-8Supervisor2168OEWT-PA11-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4578 | KL-20201123-16 | 53510911 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-11-23 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanders 600 road, 700 road and 100 Road | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 15 | 44176 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4578KL-20201123-16Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD4578KL-20201123-16Supervisor2168OEWT-PA12-LEM-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4610 | KL-20201124-13 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-24 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanders for 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4610KL-20201124-13Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4610KL-20201124-13Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4660 | KL-20201126-13 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of grader 600, 700 and 100 roads. | 9 | E091-E102 | 600 Road | 0 | 44178 |  | 50 | 44208 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4660KL-20201126-13Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4660KL-20201126-13Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4662 | KL-20201126-15 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sander for 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44178 |  | 50 | 44208 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4662KL-20201126-15Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4662KL-20201126-15Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4686 | KL-20201127-12 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-27 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanding 600, 700 , 100 and Paint Lake Road 2 | 9 | E091-E102 | 600 Road | 0 | 44180 |  | 50 | 44201 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4686KL-20201127-12Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4686KL-20201127-12Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4700 | KL-20201128-8 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-28 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanding 600, 700 , 100 and Paint Lake Road 2 | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44201 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4700KL-20201128-8Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4700KL-20201128-8Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4704 | KL-20201128-12 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-28 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of grader on 600rd, 700rd, 100rd | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44201 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4704KL-20201128-12Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4704KL-20201128-12Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4710 | KL-20201129-11 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-29 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of sanders for 600, 700, 100, and Paint Lake 2Rd | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44203 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4710KL-20201129-11Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4710KL-20201129-11Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4722 | KL-20201130-5 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-30 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervise grader on 600, 700, and 100 Roads | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44203 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4722KL-20201130-5Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4722KL-20201130-5Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4725 | KL-20201130-8 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-30 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision for Sanders for 600, 700, 100, and Paint Lake 2 Roads | 9 | E0914-E102 | 600 Road | 0 | 44181 |  | 50 | 44203 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4725KL-20201130-8Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4725KL-20201130-8Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4739 | KL-20201201-8 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-01 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanders for 600, 700, 100, and Paint Lake 2 RDs. | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44202 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4739KL-20201201-8Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4739KL-20201201-8Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4740 | KL-20201201-9 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-01 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervison of grader 600, 700, 100 roads | 9 | E091-E102 | 600 Road | 0 | 44181 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4740KL-20201201-9Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4740KL-20201201-9Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4777 | KL-20201202-20 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-02 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanders for 600, 700, 100, and Paint Lake 2 Road. | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44206 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4777KL-20201202-20Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4777KL-20201202-20Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4811 | KL-20201209-13 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-09 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanders 600, 700, and 100 roads. | 9 | E091-E102 | 600 Road | 0 | 44194 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4811KL-20201209-13Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4811KL-20201209-13Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4812 | KL-20201209-14 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-09 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of graders on 600, 700, roads. | 9 | E061-E102 | 600 Road | 0 | 44194 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4812KL-20201209-14Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4812KL-20201209-14Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4830 | KL-20201211-8 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-11 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4830KL-20201211-8Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4830KL-20201211-8Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4845 | KL-20201212-10 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-12 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervise Grading 600 & 700 Roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44208 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4845KL-20201212-10Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4845KL-20201212-10Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4907 | KL-20201205-10 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-05 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanding 600, 700, and 100 roads. | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4907KL-20201205-10Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4907KL-20201205-10Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4921 | KL-20201206-8 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-06 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44206 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4921KL-20201206-8Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4921KL-20201206-8Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4937 | KL-20201207-12 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanding 600, 700 and 100 Roads | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44209 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4937KL-20201207-12Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4937KL-20201207-12Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4939 | KL-20201207-14 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Grader 600, 700 and 100 Roads | 9 | E091-E102 | 600 Road | 0 | 44193 |  | 50 | 44206 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4939KL-20201207-14Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4939KL-20201207-14Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4951 | KL-20201208-9 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-08 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision Sanding 600, 700 and 100 road | 9 | E091-E102 | 600 Road | 0 | 44194 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4951KL-20201208-9Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4951KL-20201208-9Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4971 | KL-20201210-10 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-10 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanders for 600, 700, and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4971KL-20201210-10Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4971KL-20201210-10Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4972 | KL-20201210-11 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-10 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of graders 600, 700, and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44207 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4972KL-20201210-11Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4972KL-20201210-11Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4984 | KL-20201213-9 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-13 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision Grade 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4984KL-20201213-9Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4984KL-20201213-9Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4989 | KL-20201211-17 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-11 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of float truck for bridge mats pick up and delivery | 9 | E091-E102 | 600 Road | 0 | 44195 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4989KL-20201211-17Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4989KL-20201211-17Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5003 | KL-20201214-6 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5003KL-20201214-6Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5003KL-20201214-6Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5005 | KL-20201214-8 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44196 |  | 53 | 44209 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5005KL-20201214-8Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5005KL-20201214-8Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5019 | KL-20201215-7 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-15 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Grading 600, 700 and 100 roads | 9 | E019-E102 | 600 Road | 0 | 44198 |  | 53 | 44210 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5019KL-20201215-7Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5019KL-20201215-7Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5020 | KL-20201215-8 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-12 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervison of Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44198 |  | 53 | 44210 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5020KL-20201215-8Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5020KL-20201215-8Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5032 | KL-20201216-4 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-16 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Grading 600, 700 roads | 9 | E091-E102 | 600 Raod | 0 | 44200 |  | 53 | 44210 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5032KL-20201216-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5032KL-20201216-4Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5043 | KL-20201218-4 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-18 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of grader | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5043KL-20201218-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5043KL-20201218-4Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5045 | KL-20201218-6 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-18 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of sanders on 600 rd. | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5045KL-20201218-6Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5045KL-20201218-6Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5057 | KL-20201219-4 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-19 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervison for Grading 600 & 700 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5057KL-20201219-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5057KL-20201219-4Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5100 | KL-20201217-8 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Grading 600, 700 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5100KL-20201217-8Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5100KL-20201217-8Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5101 | KL-20201217-9 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanding 600, 700 and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5101KL-20201217-9Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5101KL-20201217-9Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5128 | KL-20201221-3 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-21 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of grader on 600, 700, and 100 roads | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5128KL-20201221-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5128KL-20201221-3Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5130 | KL-20201221-5 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-21 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Stripping km 6 Pit | 9 | E091-E102 | 600 Road | 0 | 44200 |  | 53 | 44211 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5130KL-20201221-5Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5130KL-20201221-5Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5153 | KL-20201228-4 | 53510911 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-28 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Grading | 9 | E091-E102 | 600 Road | 0 | 44202 |  | 36 | 44213 | [5 empty] | Mike Lecocq | 09 | KABI LAKE FOREST PRODUCTS LTD5153KL-20201228-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5153KL-20201228-4Supervisor184OEWT-PA13-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7899 | KL-20220217-4 | 53510911 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-17 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from Km 9 to Km 25 on 600 Road | 9 | E092-F009 | 600 Road | 0 | 44614 |  | 61 | 44614 | [6 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD7899KL-20220217-4Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7899KL-20220217-4Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7902 | KL-20220218-3 | 53510911 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-18 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working snow removal from Km 9 to Km 35 on 600 Road | 9 | E092-F009 | 600 Road | 0 | 44614 |  | 61 | 44614 | [6 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD7902KL-20220218-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7902KL-20220218-3Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7927 | KL-20220225-3 | 53510911 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-25 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader and dozer finishing snow removal fro 9km to E-182 on 600 Road | 9 | E092-F009 | 600 Raod | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 09 | KABI LAKE FOREST PRODUCTS LTD7927KL-20220225-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7927KL-20220225-3Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7964 | KL-20220303-3 | 53510911 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2022-03-03 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Run Cat 962M Loader From Kabi Yard & Start Snow Removal To E193 On 600 Road | 9 | E092-F009 | 600 Road | 0 | 44630 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD7964KL-20220303-3Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7964KL-20220303-3Supervisor0.542 | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7968 | KL-20220304-3 | 53510911 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-03-04 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader Finishing Snow Removal To E193 On 600 Road & Run Loader Back To Kabi Yard | 9 | E092-F009 | 600 Road | 0 | 44630 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD7968KL-20220304-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7968KL-20220304-3Supervisor3252 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1538 | KL-20200520-9 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-05-20 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road to KM 30 | 9 | E091-E102 | 600 Road | 0 | 43976 |  | 15 | 43977 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1538KL-20200520-9Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1538KL-20200520-9Supervisor2168OEWT-PA5-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1552 | KL-20200521-4 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-05-21 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road to 40 km | 9 | E091-E102 | 600 Road | 0 | 43977 |  | 15 | 43977 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1552KL-20200521-4Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1552KL-20200521-4Supervisor2168OEWT-PA5-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1559 | KL-20200519-3 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-05-19 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start grading 600 Road at Km 9 | 9 | E091-E102 | 600 Road | 0 | 43976 |  | 15 | 43977 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1559KL-20200519-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1559KL-20200519-3Supervisor2168OEWT-PA5-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1623 | KL-20200531-4 | 53510912 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2020-05-31 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Unclogg cross drain culverts @13.5, 30.5, 34.2, and 39.5 kms | 9 | E091-E102 | 600 Road | 0 | 43985 |  | 42 | 43986 | [5 empty] | Glen Greening | 09 | KABI LAKE FOREST PRODUCTS LTD1623KL-20200531-4Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD1623KL-20200531-4Supervisor4336OEWT-PA6-LEM | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1726 | KL-20200614-2 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-06-14 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Unclog cross drain culvert @ 13.5 Km on 600 Road. Ditching and shaping access to E-134. RV-40033 | 9 | E091-E102 | 600 Road | 0 | 44000 | [9 empty] | 09 | KABI LAKE FOREST PRODUCTS LTD1726KL-20200614-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD1726KL-20200614-2Supervisor184OEWT-PA6-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1778 | KL-20200618-4 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-06-18 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 road to 9 KM | 9 | E-091 to E-102 | 600 Road | 0 | 44005 |  | 15 | 44004 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1778KL-20200618-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD1778KL-20200618-4Supervisor184OEWT-PA6-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1795 | KL-20200619-5 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-06-19 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade sections on 100 Road to 5KM pit for Gravel Haul (2 hours) & 600 Road to 15KM (5 Hours) | 9 | E-091 to E-102 | 600 Road | 0 | 44006 |  | 15 | 44005 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1795KL-20200619-5Supervisor184 | KABI LAKE FOREST PRODUCTS LTD1795KL-20200619-5Supervisor184OEWT-PA6-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1829 | KL-20200622-4 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-06-22 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road from 12m to 20km | 9 |  | 600 Road | 0 | 44007 |  | 15 | 44008 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD1829KL-20200622-4Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD1829KL-20200622-4Supervisor3252OEWT-PA6-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1850 | KL-20200623-13 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-06-23 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road from 20 km to 26km | 9 |  | 600 Road | 0 | 44007 |  | 14 | 44009 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD1850KL-20200623-13Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1850KL-20200623-13Supervisor2168OEWT-PA6-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1864 | KL-20200624-14 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-06-24 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Approver- William Ouiet, not in data base as of June 27th |  | Approved |  |  | Continue grading 600 road from 25km to 32 km | 9 |  | 600 Road | 0 | 44008 |  | 14 | 44011 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD1864KL-20200624-14Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1864KL-20200624-14Supervisor2168OEWT-PA6-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1919 | KL-20200630-8 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-06-30 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road from 31 Km to 40 Km | 9 |  | 600 Road | 0 | 44012 |  | 50 | 44015 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD1919KL-20200630-8Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1919KL-20200630-8Supervisor2168OEWT-PA7-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1963 | KL-20200708-10 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-07-08 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Backup - pickup 12 hrs, only allowed 10 - charged for only 10 on LEM |  | Approved |  |  | Grade 600 Road from 9km to 17km | 9 | E-091 to E-102 | 600 Road | 0 | 44025 |  | 50 | 44026 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD1963KL-20200708-10Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD1963KL-20200708-10Supervisor2168OEWT-PA7-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1973 | KL-20200702-9 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-07-02 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road from 47km to 51km | 9 | E-091 to E-102 | 600 Road | 0 | 44021 |  | 50 | 44027 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD1973KL-20200702-9Supervisor184 | KABI LAKE FOREST PRODUCTS LTD1973KL-20200702-9Supervisor184OEWT-PA7-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2004 | KL-20200711-10 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-07-11 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road Repair 126 to 128 | 9 | E-091 to E-102 | 600 Road | 0 | 44027 |  | 50 | 44028 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2004KL-20200711-10Supervisor184 | KABI LAKE FOREST PRODUCTS LTD2004KL-20200711-10Supervisor184OEWT-PA7-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2005 | KL-20200711-11 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-07-11 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 Road from Km17 to Km23 | 9 | E-091 to E-102 | 600 Road` | 0 | 44027 |  | 50 | 44028 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2005KL-20200711-11Supervisor184 | KABI LAKE FOREST PRODUCTS LTD2005KL-20200711-11Supervisor184OEWT-PA7-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2029 | KL-20200713-7 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-07-13 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road Repair 126 to 128 | 9 | E-091 to E-102 | 600 Road | 0 | 44027 |  | 50 | 44029 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2029KL-20200713-7Supervisor184 | KABI LAKE FOREST PRODUCTS LTD2029KL-20200713-7Supervisor184OEWT-PA7-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2099 | KL-20200717-11 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-07-17 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade E106 Access Road | 9 | E091-E106 | 600 Road | 0 | 44034 |  | 15 | 44034 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2099KL-20200717-11Supervisor184 | KABI LAKE FOREST PRODUCTS LTD2099KL-20200717-11Supervisor184OEWT-PA7-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2128 | KL-20200701-12 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-07-01 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road from 40km to 47km | 9 | E-091 to E-102 | 600 Road | 0 | 44019 |  | 50 | 44020 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2128KL-20200701-12Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD2128KL-20200701-12Supervisor2168OEWT-PA7-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2176 | KL-20200703-1 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-07-03 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade AU1 Access to E-126/E-124 | 9 | E-091 to E-102 | 600 road | 0 | 44020 |  | 50 | 44020 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2176KL-20200703-1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD2176KL-20200703-1Supervisor184OEWT-PA7-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2180 | KL-20200703-5 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-07-03 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 road from 2 Km to 9 Km | 9 | E-091 to E-102 | 600 Road | 0 | 44020 |  | 50 | 44020 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2180KL-20200703-5Supervisor184 | KABI LAKE FOREST PRODUCTS LTD2180KL-20200703-5Supervisor184OEWT-PA7-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2237 | KL-20200723-13 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-07-23 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Road from Hwy to Km 10 | 9 | E-091 to E-102 | 600 Road | 0 | 44040 |  | 15 | 44040 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2237KL-20200723-13Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD2237KL-20200723-13Supervisor2168OEWT-PA7-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2305 | KL-20200729-8 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-07-29 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 road from Hwy to Km 11 | 9 | E091-E102 | 600 Road | 0 | 44047 |  | 14 | 44048 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD2305KL-20200729-8Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD2305KL-20200729-8Supervisor2168OEWT-PA8-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2322 | KL-20200730-14 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-07-30 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Hills on 600 road 11km to 53km | 9 | E091-E102 | 600 Road | 0 | 44048 |  | 50 | 44049 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2322KL-20200730-14Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2322KL-20200730-14Supervisor3252OEWT-PA8-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2336 | KL-20200731-11 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-07-31 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road 53km to 49km | 9 | E091-E102. | 600 Road | 0 | 44048 |  | 50 | 44049 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2336KL-20200731-11Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD2336KL-20200731-11Supervisor2168OEWT-PA8-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2396 | KL-20200808-3 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-08-08 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44057 |  | 47 | 44057 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2396KL-20200808-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2396KL-20200808-3Supervisor3252OEWT-PA8-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2405 | KL-20200809-5 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-08-09 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44057 |  | 47 | 44058 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2405KL-20200809-5Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2405KL-20200809-5Supervisor3252OEWT-PA8-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2407 | KL-20200809-7 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-08-09 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Opas Contracting for structure pad E103 | 9 | E091-E102 | 600 Road | 0 | 44057 |  | 47 | 44058 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2407KL-20200809-7Supervisor184 | KABI LAKE FOREST PRODUCTS LTD2407KL-20200809-7Supervisor184OEWT-PA8-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2412 | KL-20200810-5 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-08-10 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 Road | 9 | E091-E102 | 600 Road | 0 | 44057 |  | 47 | 44058 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2412KL-20200810-5Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2412KL-20200810-5Supervisor3252OEWT-PA8-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2419 | KL-20200811-2 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-08-11 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44060 |  | 47 | 44061 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2419KL-20200811-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2419KL-20200811-2Supervisor3252OEWT-PA8-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2425 | KL-20200812-1 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-08-12 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 Road!! | 9 | E091-E102 | 600 Road | 0 | 44060 |  | 47 | 44061 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2425KL-20200812-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2425KL-20200812-1Supervisor3252OEWT-PA8-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2435 | KL-20200813-2 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-08-13 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44062 |  | 47 | 44062 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2435KL-20200813-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2435KL-20200813-2Supervisor3252OEWT-PA8-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2444 | KL-20200814-4 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-08-14 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44062 |  | 47 | 44062 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2444KL-20200814-4Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2444KL-20200814-4Supervisor3252OEWT-PA8-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2449 | KL-20200815-4 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-08-15 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Continue grading 600 Road @ 30 Km to 35 Km | 9 | E091-E102 | 600 Road | 0 | 44062 |  | 15 | 44066 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2449KL-20200815-4Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2449KL-20200815-4Supervisor3252OEWT-PA8-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2457 | KL-20200816-4 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-08-16 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E091-E | 600 Road | 0 | 44062 |  | 15 | 44066 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2457KL-20200816-4Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2457KL-20200816-4Supervisor3252OEWT-PA8-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2464 | KL-20200817-4 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-08-17 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E091-E102 | 600 Road | 0 | 44063 |  | 15 | 44064 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2464KL-20200817-4Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2464KL-20200817-4Supervisor3252OEWT-PA8-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2565 | KL-20200823-6 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-08-23 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road maintenance work from E-165 to E-167 | 9 | E-091 to E-102 | 600 Road | 0 | 44068 |  | 15 | 44071 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2565KL-20200823-6Supervisor184 | KABI LAKE FOREST PRODUCTS LTD2565KL-20200823-6Supervisor184OEWT-PA8-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2585 | KL-20200824-6 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-08-24 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road from 9 to 13 Km | 9 | E-091 to E-102 | 600 Road | 0 | 44069 |  | 15 | 44071 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2585KL-20200824-6Supervisor184 | KABI LAKE FOREST PRODUCTS LTD2585KL-20200824-6Supervisor184OEWT-PA8-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2597 | KL-20200825-6 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-08-25 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44072 |  | 15 | 44074 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2597KL-20200825-6Supervisor184 | KABI LAKE FOREST PRODUCTS LTD2597KL-20200825-6Supervisor184OEWT-PA8-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2605 | KL-20200827-2 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-08-27 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 road from Hwy to 9km | 9 | E091-E102 | 600 Road | 0 | 44074 |  | 15 | 44075 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2605KL-20200827-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD2605KL-20200827-2Supervisor184OEWT-PA9-Lem-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2606 | KL-20200828-1 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-08-28 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade 600 road from Hwy to 14km | 9 | E091-E102 | 600 Road | 0 | 44076 |  | 15 | 44077 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2606KL-20200828-1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD2606KL-20200828-1Supervisor2168OEWT-PA9-Lem-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2612 | KL-20200829-3 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-08-29 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44076 |  | 15 | 44077 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2612KL-20200829-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2612KL-20200829-3Supervisor3252OEWT-PA9-Lem-R1 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2618 | KL-20200830-1 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-08-30 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44076 |  | 47 | 44077 | [5 empty] | Bruce Bennett | 09 | KABI LAKE FOREST PRODUCTS LTD2618KL-20200830-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2618KL-20200830-1Supervisor3252OEWT-PA9-Lem-R1 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2635 | KL-20200831-7 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-08-31 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E091-E102 | 600 Road | 0 | 44084 |  | 50 | 44087 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2635KL-20200831-7Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2635KL-20200831-7Supervisor3252OEWT-PA9-Lem-R1 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2647 | KL-20200901-10 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-01 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road Km 31 -33 | 9 | E092-E109 | 600 Road | 0 | 44084 |  | 50 | 44087 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2647KL-20200901-10Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2647KL-20200901-10Supervisor3252OEWT-PA9-Lem-R1 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2677 | KL-20200903-14 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-03 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E091-E102 | 600 Road | 0 | 44084 |  | 50 | 44088 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2677KL-20200903-14Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2677KL-20200903-14Supervisor3252OEWT-PA9-Lem-R1 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2689 | KL-20200904-10 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-04 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44088 |  | 50 | 44089 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD2689KL-20200904-10Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2689KL-20200904-10Supervisor3252OEWT-PA9-Lem-R1 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2736 | KL-20200907-13 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-07 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44089 |  | 15 | 44092 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2736KL-20200907-13Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2736KL-20200907-13Supervisor3252OEWT-PA9-Lem-R1 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2754 | KL-20200908-15 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-08 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44089 |  | 15 | 44092 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2754KL-20200908-15Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2754KL-20200908-15Supervisor3252OEWT-PA9-Lem-R1 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2778 | KL-20200909-19 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-09 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44092 |  | 15 | 44092 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2778KL-20200909-19Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2778KL-20200909-19Supervisor3252OEWT-PA9-Lem-R1 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2802 | KL-20200910-18 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-10 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44091 |  | 15 | 44094 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2802KL-20200910-18Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2802KL-20200910-18Supervisor3252OEWT-PA9-Lem-R1 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2853 | KL-20200911-20 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-11 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44094 |  | 15 | 44095 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2853KL-20200911-20Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2853KL-20200911-20Supervisor3252OEWT-PA9-Lem-R1 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2932 | KL-20200915-3 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-15 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of CDSL Logging Inc. for cross drain installs and fixing access roads. Cress floating equipment to 600 Rd | 9 | E-091 to E-102 | 600 Road | 0 | 44096 |  | 15 | 44097 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2932KL-20200915-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2932KL-20200915-3Supervisor3252OEWT-PA9-Lem-R1 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2937 | KL-20200915-8 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-09-15 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44096 |  | 15 | 44097 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2937KL-20200915-8Supervisor184 | KABI LAKE FOREST PRODUCTS LTD2937KL-20200915-8Supervisor184OEWT-PA9-Lem-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2968 | KL-20200916-11 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-09-16 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44096 |  | 15 | 44098 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2968KL-20200916-11Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD2968KL-20200916-11Supervisor2168OEWT-PA9-Lem-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2996 | KL-20200917-13 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-17 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44097 |  | 15 | 44098 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2996KL-20200917-13Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD2996KL-20200917-13Supervisor3252OEWT-PA9-Lem-R1 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3036 | KL-20200918-16 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-18 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | KL-20200918-16 | 600 Road | 0 | 44098 |  | 15 | 44099 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3036KL-20200918-16Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD3036KL-20200918-16Supervisor3252OEWT-PA9-Lem-R1 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3059 | KL-20200920-12 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-20 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44099 |  | 15 | 44101 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3059KL-20200920-12Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD3059KL-20200920-12Supervisor3252OEWT-PA9-Lem-R1 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3131 | KL-20200922-16 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-22 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44103 |  | 15 | 44103 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3131KL-20200922-16Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD3131KL-20200922-16Supervisor3252OEWT-PA9-Lem-R1 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3171 | KL-20200923-12 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-23 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44103 |  | 15 | 44104 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3171KL-20200923-12Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD3171KL-20200923-12Supervisor3252OEWT-PA9-Lem-R1 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3268 | KL-20200927-12 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-09-27 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 43900 |  | 53 | 43900 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD3268KL-20200927-12Supervisor184 | KABI LAKE FOREST PRODUCTS LTD3268KL-20200927-12Supervisor184OEWT-PA10-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3289 | KL-20200928-12 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-28 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E091-E102 | 600 road | 0 | 44109 |  | 15 | 44121 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3289KL-20200928-12Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD3289KL-20200928-12Supervisor3252OEWT-PA10-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3320 | KL-20200929-11 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-29 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road | 9 | E091-E102 | 600 Road | 0 | 44109 |  | 50 | 44115 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3320KL-20200929-11Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD3320KL-20200929-11Supervisor3252OEWT-PA10-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3485 | KL-20201005-10 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-10-05 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Unplug Culverts at km 40 and 48 on 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44123 |  | 15 | 44125 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3485KL-20201005-10Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD3485KL-20201005-10Supervisor2168OEWT-PA10-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3487 | KL-20201005-12 | 53510912 | Access | 0 | Supervisor | 84 | 0 | HR |  |  | 84 | 0 | 0 | 0 | 0 | 2020-10-05 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44123 |  | 15 | 44125 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3487KL-20201005-12Supervisor00 | KABI LAKE FOREST PRODUCTS LTD3487KL-20201005-12Supervisor00OEWT-PA10-LEM | [5 empty] | 1 | 0 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3517 | KL-20201006-13 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-10-06 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44124 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3517KL-20201006-13Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD3517KL-20201006-13Supervisor2168OEWT-PA10-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3555 | KL-20201007-10 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-10-07 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Buncher from E110 to 650 pit and back to E139 | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3555KL-20201007-10Supervisor184 | KABI LAKE FOREST PRODUCTS LTD3555KL-20201007-10Supervisor184OEWT-PA10-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3557 | KL-20201007-12 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-10-07 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3557KL-20201007-12Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD3557KL-20201007-12Supervisor2168OEWT-PA10-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3598 | KL-20201008-18 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-10-08 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3598KL-20201008-18Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD3598KL-20201008-18Supervisor2168OEWT-PA10-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3599 | KL-20201008-19 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-10-08 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Stripping 650 pit | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3599KL-20201008-19Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD3599KL-20201008-19Supervisor2168OEWT-PA10-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3623 | KL-20201009-12 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-10-09 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fix road and spread loads between E173 and E172, Haul gravel to E168 to E171 and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3623KL-20201009-12Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD3623KL-20201009-12Supervisor3252OEWT-PA10-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3647 | KL-20201010-11 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-10-10 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3647KL-20201010-11Supervisor184 | KABI LAKE FOREST PRODUCTS LTD3647KL-20201010-11Supervisor184OEWT-PA10-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3648 | KL-20201010-12 | 53510912 | Access | 0 | Supervisor | 84 | 0 | HR |  |  | 84 | 0 | 0 | 0 | 0 | 2020-10-10 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trucks from 650 pit, fix rds, spread loads between E-173, E-172 and haul gravel to E-168/E-171and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44125 |  | 15 | 44129 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3648KL-20201010-12Supervisor00 | KABI LAKE FOREST PRODUCTS LTD3648KL-20201010-12Supervisor00OEWT-PA10-LEM | [5 empty] | 1 | 0 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3671 | KL-20201011-11 | 53510912 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2020-10-11 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trucks from 650 pit, fix road and haul gravel to E168 to E171 and spread over corduroy | 9 | E-091 to E-102 | 600 Road | 0 | 44157 |  | 15 | 44131 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3671KL-20201011-11Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD3671KL-20201011-11Supervisor4336OEWT-PA10-LEM | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3691 | KL-20201012-9 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-10-12 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float and use log loader to unclog culverts @ 49km on 600 road | 9 | E-091 to E-102 | 600 Road | 0 | 44126 |  | 15 | 44132 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3691KL-20201012-9Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD3691KL-20201012-9Supervisor2168OEWT-PA10-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3699 | KL-20201012-17 | 53510912 | Access | 0 | Supervisor | 84 | 13 | HR |  |  | 84 | 0 | 1092 | 141.96 | 1233.96 | 2020-10-12 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of WF 9 gravel haul and road maintenance | 9 | E-091 to E-102 | 600 Road | 0 | 44126 |  | 15 | 44132 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD3699KL-20201012-17Supervisor131092 | KABI LAKE FOREST PRODUCTS LTD3699KL-20201012-17Supervisor131092OEWT-PA10-LEM | [5 empty] | 1 | 1092 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3743 | KL-20201014-14 | 53510912 | Access | 0 | Supervisor | 84 | 0 | HR |  |  | 84 | 0 | 0 | 0 | 0 | 2020-10-14 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road | 9 | E-091 to E-102 | 600 Road | 0 | 44129 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3743KL-20201014-14Supervisor00 | KABI LAKE FOREST PRODUCTS LTD3743KL-20201014-14Supervisor00OEWT-PA10-LEM | [5 empty] | 1 | 0 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3770 | KL-20201015-18 | 53510912 | Access | 0 | Supervisor | 84 | 12 | HR |  |  | 84 | 0 | 1008 | 131.04 | 1139.04 | 2020-10-15 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of WF 9 | 9 | E-091 to E-102 | 600 Road | 0 | 44130 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3770KL-20201015-18Supervisor121008 | KABI LAKE FOREST PRODUCTS LTD3770KL-20201015-18Supervisor121008OEWT-PA10-LEM | [5 empty] | 1 | 1008 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3857 | KL-20201020-6 | 53510912 | Access | 0 | Supervisor | 84 | 12 | HR |  |  | 84 | 0 | 1008 | 131.04 | 1139.04 | 2020-10-20 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of WF 9 | 9 | E-091 to E-102 | 600 Road | 0 | 44131 |  | 50 | 44132 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3857KL-20201020-6Supervisor121008 | KABI LAKE FOREST PRODUCTS LTD3857KL-20201020-6Supervisor121008OEWT-PA10-LEM | [5 empty] | 1 | 1008 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3886 | KL-20201023-5 | 53510912 | Access | 0 | Supervisor | 84 | 10 | HR |  |  | 84 | 0 | 840 | 109.2 | 949.2 | 2020-10-23 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of WF 9 | 9 | E-091 to E-102 | 600 Road | 0 | 44133 |  | 50 | 44134 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3886KL-20201023-5Supervisor10840 | KABI LAKE FOREST PRODUCTS LTD3886KL-20201023-5Supervisor10840OEWT-PA10-LEM | [5 empty] | 1 | 840 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3986 | KL-20201026-11-R1 | 53510912 | Access | 0 | Supervisor | 84 | 12 | HR |  |  | 84 | 0 | 1008 | 131.04 | 1139.04 | 2020-10-26 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of WF 9 | 9 | E091-E102 | 600 Rd | 0 | 44147 |  | 50 | 44162 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3986KL-20201026-11-R1Supervisor121008 | KABI LAKE FOREST PRODUCTS LTD3986KL-20201026-11-R1Supervisor121008OEWT-PA11-LEM | [5 empty] | 1 | 1008 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4072 | KL-20201030-14 | 53510912 | Access | 0 | Supervisor | 84 | 10 | HR |  |  | 84 | 0 | 840 | 109.2 | 949.2 | 2020-10-30 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of WF 9 (revised Hours) | 9 | E091-E102 | 600 Rd | 0 | 44152 |  | 56 | 44163 | [5 empty] | Mandy Sandhu | 09 | KABI LAKE FOREST PRODUCTS LTD4072KL-20201030-14Supervisor10840 | KABI LAKE FOREST PRODUCTS LTD4072KL-20201030-14Supervisor10840OEWT-PA11-LEM | [5 empty] | 1 | 840 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4299 | KL-20201110-9 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-10 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load 1 roll of Geo @ Kabi Laydown & Deliver @ E-139 | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 50 | 44168 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4299KL-20201110-9Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4299KL-20201110-9Supervisor184OEWT-PA11-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4329 | KL-20201112-12 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-12 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road and 100 Road | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44168 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4329KL-20201112-12Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4329KL-20201112-12Supervisor184OEWT-PA11-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4359 | KL-20201114-12 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-14 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float D6 from F9 to E168 to shape roads | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4359KL-20201114-12Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4359KL-20201114-12Supervisor184OEWT-PA11-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4397 | KL-20201115-11 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-15 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road and 100 Road. | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 53 | 44171 | [5 empty] | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD4397KL-20201115-11Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4397KL-20201115-11Supervisor184OEWT-PA11-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4415 | KL-20201116-14 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fix roads E168 to E171 and E212 to E210 | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4415KL-20201116-14Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD4415KL-20201116-14Supervisor2168OEWT-PA11-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4416 | KL-20201116-15 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 road, 100 road, Paint Lake 2 Rd | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4416KL-20201116-15Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4416KL-20201116-15Supervisor184OEWT-PA11-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4431 | KL-20201117-10 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-17 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 rd, 100 rd, and Paint Lake 2 road | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44172 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4431KL-20201117-10Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4431KL-20201117-10Supervisor184OEWT-PA11-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4463 | KL-20201119-9 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-11-19 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shaping up and back blading access roads E217 to E194 | 9 | E091-E102 | 600 Road | 0 | 44167 |  | 15 | 44174 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4463KL-20201119-9Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD4463KL-20201119-9Supervisor2168OEWT-PA11-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4522 | KL-20201031-16 | 53510912 | Access | 0 | Supervisor | 84 | 10 | HR |  |  | 84 | 0 | 840 | 109.2 | 949.2 | 2020-10-31 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of WF 9 and WF 10 (Revised Hours) | 9 | E091-E102 | 600 Road | 0 | 44174 |  | 56 | 44174 | [5 empty] | Mandy Sandhu | 09 | KABI LAKE FOREST PRODUCTS LTD4522KL-20201031-16Supervisor10840 | KABI LAKE FOREST PRODUCTS LTD4522KL-20201031-16Supervisor10840OEWT-PA11-LEM | [5 empty] | 1 | 840 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4573 | KL-20201123-11 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-11-23 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shaping up and back blading access roads and pulling a drag F3 and F9 | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 15 | 44175 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4573KL-20201123-11Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD4573KL-20201123-11Supervisor2168OEWT-PA12-LEM-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4577 | KL-20201123-15 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-23 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Grader 600 road, 700 road and 100 Road | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 15 | 44176 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD4577KL-20201123-15Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4577KL-20201123-15Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4605 | KL-20201124-8 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-11-24 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shaping up and back blading access road and pulling a drag F3, F9 | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4605KL-20201124-8Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD4605KL-20201124-8Supervisor2168OEWT-PA12-LEM-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4608 | KL-20201124-11 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-24 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Grading 600 road, 100 road and 700 road | 9 | E091-E102 | 600 Road | 0 | 44172 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4608KL-20201124-11Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4608KL-20201124-11Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4635 | KL-20201125-12 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Sanders For 600 700 and 100 roads. | 9 | E091-E102 | 600 Road | 0 | 44173 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4635KL-20201125-12Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4635KL-20201125-12Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4637 | KL-20201125-14 | 53510912 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shaping up and back blading access roads and pulling a drag F3-F9 | 9 | E091-E102 | 600 Road | 0 | 44173 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4637KL-20201125-14Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD4637KL-20201125-14Supervisor2168OEWT-PA12-LEM-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4638 | KL-20201125-15 | 53510912 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of grader 600, 700, and 100 Roads | 9 | E091-E102 | 600 Road | 0 | 44173 |  | 50 | 44207 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4638KL-20201125-15Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4638KL-20201125-15Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6903 | KL-20210511-3 | 53510912 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-05-11 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float 250 link belt log loader from mill yard to 13km on 600 road/unplug culvert and float log loader back to mill yard | 9 | E091-E102 | 600 Road | 0 | 44337 |  | 56 | 44341 | [5 empty] | Mandy Sandhu | 09 | KABI LAKE FOREST PRODUCTS LTD6903KL-20210511-3Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD6903KL-20210511-3Supervisor0.542OEWT-PA17-LEM | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6949 | KL-20210518-6 | 53510912 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-05-18 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T dozer leveling ruts and shaping road E200 to E216/ Supervisor while checking on Operator and process did pickup shuffle (Revised) | 9 | E091-E102 | 600 Road | 0 | 44345 |  | 14 | 44349 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD6949KL-20210518-6Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD6949KL-20210518-6Supervisor3252OEWT-PA17-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7379 | KL-20210923-1 | 53511003 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-09-23 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees@ 18 km, excavator 2 placing trees/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 61 | 44471 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-1Supervisor8672OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7384 | KL-20210924-1 | 53511003 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-09-24 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees, excavator 2 placing trees @km 16.5 and Km 21 hill/Chapman rock truck hauling Gravel From km 38 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 50 | 44470 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-1Supervisor8672OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.51268 | 344.5214 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7200 | KL-20210804-1 | 53511004 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-04 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load existing material from 17Km on Hensen Road & Gravel road sections @ 46/45Km on Paint Lake road 2 as per Valard. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7200KL-20210804-1Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7200KL-20210804-1Supervisor4336OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7201 | KL-20210808-1 | 53511004 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-08 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading existing material from 17Km on Hensen Road & Gravel road sections @ 46/44Km on Paint Lake road 2 as per Valard. 1 Kabi Rock Truck & 2 Valard Rock Trucks Hauling | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7201KL-20210808-1Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7201KL-20210808-1Supervisor4336OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7202 | KL-20210805-1 | 53511004 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-05 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading existing material from 17Km on Hensen Road & Gravel road sections @ 45/44Km on Paint Lake road 2 as per Valard. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7202KL-20210805-1Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7202KL-20210805-1Supervisor4336OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7204 | KL-20210806-1 | 53511004 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-06 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading existing material from 17Km on Hensen Road & Gravel road sections @ 46/44Km on Paint Lake road 2 as per Valard. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7204KL-20210806-1Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7204KL-20210806-1Supervisor4336OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7207 | KL-20210809-1 | 53511004 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-09 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/loading mats on Valard Rock truck. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7207KL-20210809-1Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7207KL-20210809-1Supervisor4336OEWT-PA20-Lem | WF10-Access |  | WF10-Access | 1 |  | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7211 | KL-20210810-1 | 53511004 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-10 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/loading mats on Valard Rock truck. | 10 | F033-F118 | Paint Lake Road2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7211KL-20210810-1Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7211KL-20210810-1Supervisor4336OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7212 | KL-20210811-1 | 53511004 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-11 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 45/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/2 Valard Rock truck. Continue grading Paint Lake Road 2 from Km 7.5 to Km 11.5 - SSF-14324 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7212KL-20210811-1Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7212KL-20210811-1Supervisor4336OEWT-PA20-Lem | WF10-Access |  | WF10-Access | 1 |  | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7213 | KL-20210812-1 | 53511004 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-12 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel access mat sections @ 45/44 km on Paint Lake Road 2/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on Valard 2nd rock truck. Finish grading Paint Lake Road 2 to Km 13 and touch up on way out to Paint Lake Road - SSF-14325 | 10 | F033-F118 | Paint ake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7213KL-20210812-1Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7213KL-20210812-1Supervisor4336OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7214 | KL-20210813-1 | 53511004 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-13 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on 2nd Valard Rock truck | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7214KL-20210813-1Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7214KL-20210813-1Supervisor4336OEWT-PA20-Lem | WF10-Access |  | WF10-Access | 1 |  | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7215 | KL-20210814-1 | 53511004 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-14 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/43 km/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on 2nd Valard Rock truck/Excavator working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7215KL-20210814-1Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7215KL-20210814-1Supervisor4336OEWT-PA20-Lem | WF10-Access |  | WF10-Access | 1 |  | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7218 | KL-20210815-1 | 53511004 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-15 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/43 km/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on 2nd Valard Rock truck/Excavator 2 working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7218KL-20210815-1Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7218KL-20210815-1Supervisor4336OEWT-PA20-Lem | WF10-Access |  | WF10-Access | 1 |  | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7221 | KL-20210816-1 | 53511004 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-16 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/43 km/ 1 Kabi Rock Truck, Corbiere and Valard Rock truck/Excavator 2 working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7221KL-20210816-1Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7221KL-20210816-1Supervisor4336OEWT-PA20-Lem | WF10-Access |  | WF10-Access | 1 |  | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7224 | KL-20210817-1 | 53511004 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-17 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and Haul Existing material from KM 17 on Hensen Road to Corbiere Dozer @ 45/46 km/ 1 Kabi Rock Truck, Corbiere and Valard Rock truck/Excavator 2 working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44427 |  | 50 | 44428 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7224KL-20210817-1Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7224KL-20210817-1Supervisor4336OEWT-PA20-Lem | WF10-Access |  | WF10-Access | 1 |  | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7248 | KL-20210819-4 | 53511004 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-08-19 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44433 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7248KL-20210819-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7248KL-20210819-4Supervisor184OEWT-PA20-Lem | WF10-Access |  | WF10-Access | 1 |  | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7252 | KL-20210820-5 | 53511004 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-08-20 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44433 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-5Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-5Supervisor184OEWT-PA20-Lem | WF10-Access |  | WF10-Access | 1 |  | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7257 | KL-20210821-5 | 53511004 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-21 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/46/3 rock trucks Kabi, Corbiere and Valard/ 2nd Ex working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44434 |  | 50 | 44435 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-5Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-5Supervisor4336OEWT-PA20-Lem | WF10-Access |  | WF10-Access | 1 |  | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7267 | KL-20210822-4 | 53511004 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-08-22 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/4. One Kabi rock truck, one Corbiere, and 1 Valard. 2nd excavator working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 50 | 44440 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-4Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-4Supervisor3252OEWT-PA20-Lem | WF10-Access |  | WF10-Access | 1 |  | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7271 | KL-20210823-5 | 53511004 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-08-23 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/44. One Kabi rock truck, Corbiere and Valard/ 2nd Ex working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 37 | 44439 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-5Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-5Supervisor3252OEWT-PA20-Lem | WF10-Access |  | WF10-Access | 1 |  | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7275 | KL-20210824-3 | 53511004 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-24 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from km 17 on Hensen Road to Corbiere Dozer@km 44.5/43.5/3 rock trucks Kabi, Corbiere and Valard/ Excavator 2 working ahead @km 42 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-3Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-3Supervisor4336OEWT-PA20-Lem | WF10-Access |  | WF10-Access | 1 |  | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7285 | KL-20210828-3 | 53511004 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-28 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from km49 to Skagen excavator @ 46/45 km - 1 Kabi , 1 Chapman and 2 Cobiere rock trucks | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7285KL-20210828-3Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7285KL-20210828-3Supervisor4336OEWT-PA21-LEM | WF10-Access |  | WF10-Access | 1 |  | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7292 | KL-20210831-2 | 53511004 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-31 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from 49 Km to 44/43Km. 1 Kabi rock truck, 2 Corbiere Rock Trucks & 1 Chapman Rock Truck. Excavator 2 tracking from 49Km to F-086 for gravel haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44442 |  | 37 | 44445 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-2Supervisor4336OEWT-PA21-LEM | WF10-Access |  | WF10-Access | 1 |  | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7307 | KL-20210901-2 | 53511004 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-09-01 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from @ km49 to Skagen excavator @ km 43/ 2 Kabi , 1 Chapman and 3 Cobiere rock trucks/ excavator 2 preping access @km 35 to 34 for gravel Haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 37 | 44457 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-2Supervisor4336OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7311 | KL-20210902-2 | 53511004 | Access | 0 | Supervisor | 84 | 5 | HR |  |  | 84 | 0 | 420 | 54.6 | 474.6 | 2021-09-02 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from 38.5 km Morin excavator @ km 40/41 for road capping | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 37 | 44457 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7311KL-20210902-2Supervisor5420 | KABI LAKE FOREST PRODUCTS LTD7311KL-20210902-2Supervisor5420OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 420 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7312 | KL-20210903-2 | 53511004 | Access | 0 | Supervisor | 84 | 5 | HR |  |  | 84 | 0 | 420 | 54.6 | 474.6 | 2021-09-03 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from 38.5 km Morin excavator @ km 40/41 for road capping | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 50 | 44450 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7312KL-20210903-2Supervisor5420 | KABI LAKE FOREST PRODUCTS LTD7312KL-20210903-2Supervisor5420OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 420 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7279 | KL-20210825-3 | 53511004 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-25 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 42 to Morin Excavator/ Excavator 2 fixing up access from Km 44 to Km 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7279KL-20210825-3Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7279KL-20210825-3Supervisor4336OEWT-PA20-Lem | WF10-Access |  | WF10-Access | 1 |  | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4663 | KL-20201126-16 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shaping and back blading access road and pulling a drag F09, F24 | 10 | F009-F020 | Paint Lake Road 1-A | 0 | 44178 |  | 50 | 44208 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD4663KL-20201126-16Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD4663KL-20201126-16Supervisor2168OEWT-PA12-LEM-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4791 | KL-20201203-11 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-03 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of float truck for picking up 40' bridge mats in Marathon, and deliver to Paint Lake RD 1-B | 10 | F021-F032 | Paint Lake Road 1-B | 0 | 44193 |  | 50 | 44206 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD4791KL-20201203-11Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4791KL-20201203-11Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4896 | KL-20201204-19 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-04 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervise float truck. Picked up 20 ' bridge mats in Marathon for Paint Lake 2 Rd | 10 | F021-F032 | Paint Lake Road 1-B | 0 | 44193 |  | 50 | 44209 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD4896KL-20201204-19Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4896KL-20201204-19Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5606 | KL-20210125-3 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-01-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow, Grade Paint Lake 2 Rd, haul gravel & corduroy. Drag 70' bridge in from km 9 lay down | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44225 |  | 50 | 44232 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5606KL-20210125-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD5606KL-20210125-3Supervisor2168OEWT-PA14-Lem-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5703 | KL-20210131-2 | 53511011 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-01-31 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator making safety berm and sanding hill on F143 access | 11 | F135-F149 | Dore Lake Road | 0 | 44235 |  | 56 | 44236 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD5703KL-20210131-2Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD5703KL-20210131-2Supervisor0.542OEWT-PA14-Lem-R1 | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5841 | KL-20210210-3 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-02-10 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer plow snow & open road between F21 to F32 | 10 | F021-F032 | Paint Lake Road 1-B | 0 | 44244 |  | 50 | 44249 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5841KL-20210210-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5841KL-20210210-3Supervisor184OEWT-PA14-Lem-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5842 | KL-20210210-4 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-02-10 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul gravel, pull bridges and legos in, plow and sand roads. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44244 |  | 50 | 44249 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5842KL-20210210-4Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD5842KL-20210210-4Supervisor2168OEWT-PA14-Lem-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5976 | KL-20210220-3 | 53511011 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-02-20 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Paint Lake 2 Road, Plow snow on access road. Corduroy F62-F63 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44252 |  | 57 | 44252 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD5976KL-20210220-3Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD5976KL-20210220-3Supervisor4336OEWT-PA14-Lem-R1 | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5997 | KL-20210222-3 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-02-22 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, skid corduroy, haul rig mats to snow crossing, work on snow crossing, place mats, track buncher to snow crossing, haul gravel. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44254 | . | 57 | 44255 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD5997KL-20210222-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD5997KL-20210222-3Supervisor2168OEWT PA15-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5678 | KL-20210130-15 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-01-30 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow, haul gravel and corduroy, Sand roads. Drag in and unload bridge WC 11333.00 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44231 |  | 50 | 44232 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5678KL-20210130-15Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD5678KL-20210130-15Supervisor2168OEWT-PA14-Lem-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5861 | KL-20210211-5 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-02-11 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul, and spread Gravel, pull legos and bridge in, plow snow, sand roads, corduroy | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44244 |  | 50 | 44249 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5861KL-20210211-5Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5861KL-20210211-5Supervisor184OEWT-PA14-Lem-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5877 | KL-20210212-8 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-02-12 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul Gravel, pull bridges and legos in, plow snow, sand roads, skid corduroy | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44244 |  | 50 | 44250 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5877KL-20210212-8Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5877KL-20210212-8Supervisor184OEWT-PA14-Lem-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5899 | KL-20210214-3 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-02-14 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Skid corduroy, grade Paint Lake Road 2, unload and load legos, load and haul Gravel. Loading , Hauling and spreading gravel, drag in 50' bridge WC 11190,- | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44245 |  | 50 | 44251 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5899KL-20210214-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5899KL-20210214-3Supervisor184OEWT-PA14-Lem-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5908 | KL-20210215-3 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-02-15 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Skid corduroy, grade Paint Lake Road 2, load and haul legos, load and haul gravel, sand hills, install 800mm culvert WC 11160 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44249 |  | 50 | 44251 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5908KL-20210215-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5908KL-20210215-3Supervisor184OEWT-PA14-Lem-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5990 | KL-20210221-8 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-02-21 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Paint Lake 2 Rd, plow snow on access rd, haul geo from km 9 to km 23, skid corduroy | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44252 |  | 57 | 44255 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD5990KL-20210221-8Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5990KL-20210221-8Supervisor184OEWT-PA14-Lem-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6017 | KL-20210223-10 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-02-23 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, work on snow crossing, haul and place rig mats, load and haul gravel. Haul and spread gravel, roll out geo, hammer access road to F60 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44253 |  | 57 | 44257 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD6017KL-20210223-10Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD6017KL-20210223-10Supervisor3252OEWT-PA14-Lem-R1 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6021 | KL-20210224-1 | 53511011 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-02-24 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, load and haul gravel. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44256 |  | 57 | 44259 | [5 empty] | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD6021KL-20210224-1Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD6021KL-20210224-1Supervisor4336OEWT-PA14-Lem-R1 | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6044 | KL-20210225-12-R1 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-02-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, load and haul gravel, move bridge, and sand road. WC 12000.00 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44256 |  | 56 | 44259 | [5 empty] | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6044KL-20210225-12-R1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD6044KL-20210225-12-R1Supervisor2168OEWT-PA14-Lem-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7593 | KL-20211125-2 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-11-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road @ F118, scraping and sanding hill @ Km 48. Excavator filling ruts and shaping road from km 24 to 21 for freezing - JJR-70306 | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7593KL-20211125-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7593KL-20211125-2Supervisor184OEWT-PA23-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7620 | KL-20211202-2 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Km 49 to Km 40/ loader sanding road from Km 48 to Km 46.5 with existing material | 10 | F066-F118 | Paint Lake 2 | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7620KL-20211202-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7620KL-20211202-2Supervisor184OEWT-PA24-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7628 | KL-20211203-2 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 |  | 252 | 32.76 | 284.76 | 2021-12-03 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding and scraping road from Km 46.5 to Km 38 with existing material | 10 | F066-F118 | Paint Lake 2 | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7628KL-20211203-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7628KL-20211203-2Supervisor3252OEWT-PA24-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7637 | KL-20211204-5 | 53511011 | Access | 0 | Supervisor | 84 | 6 | HR |  |  | 84 | 0 | 504 | 65.52 | 569.52 | 2021-12-04 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding and scraping road from Km 46 to Km 38 with existing material /dozer working from Km 49 to Km 13/ supervisior picking up dozer operator @ Km 13 at end of shift | 10 | F066-F118 | Paint Lake 2 | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7637KL-20211204-5Supervisor6504 | KABI LAKE FOREST PRODUCTS LTD7637KL-20211204-5Supervisor6504OEWT-PA24-LEM | [5 empty] | 1 | 504 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7639 | KL-20211205-2 | 53511011 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-12-05 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader piling existing material from Km 46 to Km 38 for upcoming snow fall/ dozer working on snow removal from km 13 to km 21 | 10 | F066-F118 | Paint Lake 2 | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7639KL-20211205-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7639KL-20211205-2Supervisor4336OEWT-PA24-LEM | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7643 | KL-20211206-2 | 53511011 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-12-06 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working on snow removal and sanding from Km 49 to Km 35 | 10 | F066-F118 | Paint Lake 2 | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7643KL-20211206-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7643KL-20211206-2Supervisor4336OEWT-PA24-LEM | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7647 | KL-20211207-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-12-07 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding from Km 48 to Km 40 | 10 | F066-F118 | Paint Lake 2 | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7647KL-20211207-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7647KL-20211207-1Supervisor3252OEWT-PA24-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7652 | KL-20211208-1 | 53511011 | Access | 0 | Supervisor | 84 | 5 | HR |  |  | 84 | 0 | 420 | 54.6 | 474.6 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding from Km 48 to Km 45. Dozer working from 13km to 18km. Sand truck sanding from 0km to 12km in support of Valard Fuel Tank Demob. Excavator loading existing material. Skagen grader on PLR 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-1Supervisor5420 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-1Supervisor5420OEWT-PA24-LEM | [5 empty] | 1 | 420 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7657 | KL-20211209-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working from 48km to 34km sanding & clearing pull offs. Dozer working to F057, F058 & F058 access. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7657KL-20211209-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7657KL-20211209-1Supervisor3252OEWT-PA24-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7665 | KL-20211210-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-12-10 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal and sanding from 48Km to 38Km. Grader working on snow removal from Paint Lake Road to 13Km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7665KL-20211210-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7665KL-20211210-1Supervisor3252OEWT-PA24-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7681 | KL-20211212-1 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-12-12 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working from Km 2 to Km 49 for scarifying and clearing pull offs | 10 | F066-F118 | Paint Lake 2 | 0 | 44551 |  | 61 | 44561 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7681KL-20211212-1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7681KL-20211212-1Supervisor2168OEWT-PA24-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7686 | KL-20211213-1 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-12-13 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer starting snow removal from F117 to F112 | 10 | F066-F118 | Paint Lake 2 | 0 | 44551 |  | 61 | 44560 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7686KL-20211213-1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7686KL-20211213-1Supervisor184OEWT-PA24-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7689 | KL-20211214-1 | 53511011 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-12-14 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Finishing snow removal from F117 to F112 | 10 | F066-F118 | Paint Lake 2 | 0 | 44551 |  | 61 | 44560 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7689KL-20211214-1Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7689KL-20211214-1Supervisor0.542OEWT-PA24-LEM | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7705 | KL-20211218-3 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-12-18 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on shaping road and leveling ruts from F112 to F117 for freezing | 10 | F066-F118 | Paint Lake 2 | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7705KL-20211218-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7705KL-20211218-3Supervisor2168OEWT-PA24-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7718 | KL-20220101-1 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-01 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Km 49 on Paint Lake Road 2 to F111 | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7718KL-20220101-1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7718KL-20220101-1Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7723 | KL-20220103-1 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-03 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F117 to F112 | 10 | F066-F118 | Paint Lake 2 | 0 | 44568 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7723KL-20220103-1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7723KL-20220103-1Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7728 | KL-20220104-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-01-04 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and widening road from Km 47 to Km 43.5, F109 to F111, F105 and F104 Access | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7728KL-20220104-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7728KL-20220104-1Supervisor3252OEWT-PA25-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7737 | KL-20220106-2 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-06 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Working on Snow Removal and Widening road from Km 46 to F111/ Loader working on snow removal from F037 to F033 and sanding km 10.5 Hill | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7737KL-20220106-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7737KL-20220106-2Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7740 | KL-20220107-2 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-01-07 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working from Km 12 to Km 49 clearing pull offs and scraping hills from km 34 to km 41 | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7740KL-20220107-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7740KL-20220107-2Supervisor3252OEWT-PA25-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7744 | KL-20220108-1 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-08 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working from Km 48 to Km 41 pushing back snow banks, clearing pull offs and F105/F104 access | 10 | F066-F118 | Paint Lake 2 | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7744KL-20220108-1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7744KL-20220108-1Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7751 | KL-20220110-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-01-10 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working on snow removal from Km 49 to Km 36 and clearing pull offs | 10 | F066-F118 | Paint Lake 2 | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7751KL-20220110-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7751KL-20220110-1Supervisor3252OEWT-PA25-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7755 | KL-20220111-1 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-11 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and widening roads from Km 48 to Km 38 | 10 | F066-F118 | Paint Lake 2 | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7755KL-20220111-1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7755KL-20220111-1Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7758 | KL-20220112-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 |  | 252 | 32.76 | 284.76 | 2022-01-12 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and widening roads from Km 42 to Km 34/ Supervisor doing pick up shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7758KL-20220112-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7758KL-20220112-1Supervisor3252OEWT-PA25-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7763 | KL-20220113-1 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-13 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and widening roads from Km 38 to Km 32 | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7763KL-20220113-1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7763KL-20220113-1Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7768 | KL-20220114-1 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-14 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal and widening roads from Km 32 to Km 36 /Clearing spur roads on way out | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7768KL-20220114-1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7768KL-20220114-1Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7772 | KL-20220115-1 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-15 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing working on snow removal and widening roads from Km 32 to Km 36 /Clearing spur roads on way out. Excavator setting up @ 12Km for loader access to sand. | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7772KL-20220115-1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7772KL-20220115-1Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7776 | KL-20220116-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-01-16 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continue working on widening roads from Km 33 to Km 42 /Loader Clearing pull offs / Grader Scarifying from Km 49 to Km 42 | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7776KL-20220116-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7776KL-20220116-1Supervisor3252OEWT-PA25-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7779 | KL-20220117-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-01-17 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Finish working on widening roads and clearing pull offs from Km 42 to Km 49 /Grader Scarifying from Km 49 to Km 39 and F117 to F112/ supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7779KL-20220117-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7779KL-20220117-1Supervisor3252OEWT-PA25-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7785 | KL-20220119-1 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-19 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from 49Km to 42Km on Paint Lake Road 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7785KL-20220119-1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7785KL-20220119-1Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7788 | KL-20220120-1 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-20 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F112 to F117 | 10 | F066-F118 | Paint Lake 2 | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7788KL-20220120-1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7788KL-20220120-1Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7793 | KL-20220121-1 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-21 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer starting from Km 49 Km 45 clearing pull offs and widening where required/Delay Due to Stringers having road closed @ F118/ supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44588 |  | 61 | 44593 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7793KL-20220121-1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7793KL-20220121-1Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7799 | KL-20220123-1 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-23 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on access and F112 to F117 | 10 | F066-F118 | Paint Lake 2 | 0 | 44588 |  | 61 | 44593 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7799KL-20220123-1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7799KL-20220123-1Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7801 | KL-20220124-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-01-24 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening F112 to F117, clearing snow @ F109 to F111, F105 access, widening and cleaning pulloffs from Km 48 to 41.5/Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44588 |  | 61 | 44593 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7801KL-20220124-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7801KL-20220124-1Supervisor3252OEWT-PA25-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7805 | KL-20220125-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-01-25 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road and cleaning pulloffs from Km 41 to 38.5/Snow removal on spur roads from F104 to F095 /Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44588 |  | 61 | 44593 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7805KL-20220125-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7805KL-20220125-1Supervisor3252OEWT-PA25-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7809 | KL-20220126-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-01-26 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road and cleaning pulloffs from Km 38 to 35/Snow removal on spur roads /Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7809KL-20220126-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7809KL-20220126-1Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7814 | KL-20220129-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-01-29 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road , clearing pull offs and spur roads from Km 38 to Km 35/Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7814KL-20220129-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7814KL-20220129-1Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7816 | KL-20220130-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-01-30 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 49 to Km 36 for stringing crews equipment move /Dozer working from Km 35 to Km 32 widening road , clearing pull offs and spur | 10 | F066-F118 | Paint Lake 2 | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7816KL-20220130-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7816KL-20220130-1Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7818 | KL-20220131-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-01-31 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working from Km 35 to Km 32 widening road , clearing pull offs and spur roads from Km 35 to Km 29 / Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7818KL-20220131-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7818KL-20220131-1Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7822 | KL-20220201-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-01 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road, clearing pull offs, spur roads from 29km to 25km & access road to F057. Supervisor doing pickup shuffle. | 10 | F066-F118 | Paint Lake 2 | 0 | 44601 |  | 37 | 44597 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7822KL-20220201-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7822KL-20220201-1Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7826 | KL-20220202-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-02 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road, clearing pull offs, spur roads from 25km to 21km. Supervisor doing pickup shuffle. | 10 | F066-F118 | Paint Lake 2 | 0 | 44601 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7826KL-20220202-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7826KL-20220202-1Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7828 | KL-20220203-1 | 53511011 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2022-02-03 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader benching snow banks & scarifying road from 49 to 40km. Dozer widening road, clearing pull offs & spur roads from 21km to 12.5km. Supervisor doing pickup shuffle. | 10 | F066-F118 | Paint Lake 2 | 0 | 44601 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7828KL-20220203-1Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7828KL-20220203-1Supervisor4336OEWT-PA26-LEM | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7832 | KL-20220204-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-04 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F077 to F073 and clearing laydown at 12km. Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44603 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7832KL-20220204-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7832KL-20220204-1Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7836 | KL-20220205-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-05 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F020 to F009 and clearing pull offs. | 10 | F009-F065 | Paint Lake | 0 | 44603 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7836KL-20220205-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7836KL-20220205-1Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7841 | KL-20220206-1 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-06 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F020 to F009 for removal of repeater tower trailer. | 10 | F009-F065 | Paint Lake | 0 | 44603 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7841KL-20220206-1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7841KL-20220206-1Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7843 | KL-20220206-3 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 |  | 168 | 21.84 | 189.84 | 2022-02-06 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from 49km to 25km on Paint Lake Road #2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44603 |  | 61 | 44603 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7843KL-20220206-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7843KL-20220206-3Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7844 | KL-20220207-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F021 to F028 | 10 | F009 - F0665 | Paint Lake | 0 | 44604 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7844KL-20220207-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7844KL-20220207-1Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7846 | KL-20220207-3 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from 49km to 36km on Paint Lake Road #2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44604 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7846KL-20220207-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7846KL-20220207-3Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7852 | KL-20220208-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-08 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F021 to F030 | 10 | F009-F065 | Paint Lake | 0 | 44604 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7852KL-20220208-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7852KL-20220208-1Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7854 | KL-20220208-3 Field Ticket No. P.O. Box 508, 10 Industrial Park Rd White River ON POM 3G0 Frank Ferland Telephone: 807-822-2532 08-Feb-2022 Email: office@kabilake.com SUMMARY INFORMATION Page 1 of 1 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-08 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from 49km to 30km on Paint Lake Road #2 & snow removal from F116 to F112. | 10 | F066-F118 | Paint Lake | 0 | 44604 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7854KL-20220208-3 Field Ticket No. P.O. Box 508, 10 Industrial Park Rd White River ON POM 3G0 Frank Ferland Telephone: 807-822-2532 08-Feb-2022 Email: office@kabilake.com SUMMARY INFORMATION Page 1 of 1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7854KL-20220208-3 Field Ticket No. P.O. Box 508, 10 Industrial Park Rd White River ON POM 3G0 Frank Ferland Telephone: 807-822-2532 08-Feb-2022 Email: office@kabilake.com SUMMARY INFORMATION Page 1 of 1Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7859 | KL-20220209-2 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-09 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader benching snowbanks and scarifying sections from Km 49 to Km 32 on Paint Lake Road 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44604 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7859KL-20220209-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7859KL-20220209-2Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7864 | KL-20220210-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-10 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Km 49 to Km 32 on Paint Lake Road 2 /Dozer pushing snowbanks and widening road from Km 9.2 to Km 11/Supervisors doing pickup shuffle | 10 | F066-F118 | Paint Lake | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7864KL-20220210-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7864KL-20220210-1Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7869 | KL-20220211-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-11 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 49 to Km 35 /Dozer pushing snowbanks and widening road from Km 11 to Km 15/Supervisors doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7869KL-20220211-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7869KL-20220211-1Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7873 | KL-20220212-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-12 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 49 to Km 29 /Dozer tracking from Km 15 to Km 9.2 for float access/Supervisors doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7873KL-20220212-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7873KL-20220212-1Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7875 | KL-20220212-3 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-12 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F021 to F027 | 10 | F009-F065 | Paint Lake | 0 | 44605 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7875KL-20220212-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7875KL-20220212-3Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7878 | KL-20220213-2 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-13 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F021 to F032 and clearing pad @ F032 | 10 | F009-F065 | Paint Lake | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7878KL-20220213-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7878KL-20220213-2Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7883 | KL-20220214-1 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-14 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal, scarifying and benching snowbanks from Paint Lake Road to Km 19 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7883KL-20220214-1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7883KL-20220214-1Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7884 | KL-20220214-2 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-14 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer finishing snow removal and widening from F021 to F032 and clearing pad @ F032 | 10 | F009-F065 | Paint Lake | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7884KL-20220214-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7884KL-20220214-2Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7888 | KL-20220215-1 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-15 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal, scarifying from Km 49 to Km 38 on Paint Lake Road 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7888KL-20220215-1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7888KL-20220215-1Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7893 | KL-20220216-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-16 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from Km 49 to Km 19 / grader 2 working on snow removal and pushing back snowbanks from Paint Lake Road to Km 19 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7893KL-20220216-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7893KL-20220216-1Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7896 | KL-20220217-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-17 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal and scarifying from Km 49 to Km 41 / grader 2 working on snow removal and benching snowbanks from Paint Lake Road to Km 41 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7896KL-20220217-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7896KL-20220217-1Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7897 | KL-20220217-2 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-17 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run grader from Paint Lake Road 2, work on snow removal from F021 to F032 after hours and run grader back to Paint Lake Road 2 / Supervisor stayed after hours due to Operator working alone | 10 | F009-F065 | Paint Lake | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7897KL-20220217-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7897KL-20220217-2Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7900 | KL-20220218-1 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-18 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying and benching snowbanks from Paint Lake Road to Km 13 and snow removal from F037 to F033 | 10 | F066-F118 | Paint Lake 2 | 0 | 44614 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7900KL-20220218-1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7900KL-20220218-1Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7904 | KL-20220220-1 | 53511011 | Access | 0 | Supervisor | 84 | 5 | HR |  |  | 84 | 0 | 420 | 54.6 | 474.6 | 2022-02-20 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 29km. Grader 2 working on snow removal from Paint Lake Road to 29km. Loader pushing back snow banks & pull offs from 45km to 38km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44617 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7904KL-20220220-1Supervisor5420 | KABI LAKE FOREST PRODUCTS LTD7904KL-20220220-1Supervisor5420OEWT-PA26-LEM | [5 empty] | 1 | 420 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7905 | KL-20220219-1 | 53511011 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2022-02-19 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 39km. Grader 2 working on snow removal from Paint Lake Road to 39km. Loader sanding & clearing pull offs to 34km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44614 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7905KL-20220219-1Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7905KL-20220219-1Supervisor4336OEWT-PA26-LEM | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7911 | KL-20220221-1 | 53511011 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2022-02-21 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 40km. Grader 2 working on snow removal from Paint Lake Road to 40km. Loader pushing back snow banks & pull offs from 49km to 40km. | 10 | F066-F118 | Paint Lake 2 | 0 | 44617 |  | 61 | 44617 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7911KL-20220221-1Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7911KL-20220221-1Supervisor4336OEWT-PA26-LEM | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7913 | KL-20220222-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-22 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 38km. Grader 2 benchig snow banks from Paint Lake Road to 49km. Loader assisting with Demob of 50 Ton Crane from 32Km to Hensen Road. | 10 | F-066 to F-118 | Paint Lake Road 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7913KL-20220222-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7913KL-20220222-1Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7919 | KL-20220223-4 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-23 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from 49km to 29km. Loader working ahead of grader due to deep snow drifts | 10 | F066-F118 | Paint Lake 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7919KL-20220223-4Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7919KL-20220223-4Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7920 | KL-20220224-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-24 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working on snow removal from 9.2Km to F-033 & to 23Km on Paint Lake Road #2. Supervisor doing pickup shuffle. | 10 | F066-F118 | Paint Lake 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7920KL-20220224-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7920KL-20220224-1Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7925 | KL-20220225-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-25 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 working on snow removal from 49km to 18km. Grader 2 working from Paint Lake Road to 18Km. Loader clearing pulloffs on Paint lake Road 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7925KL-20220225-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7925KL-20220225-1Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7935 | KL-20220226-1 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-26 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader working from Paint Lake Road to Km 34 benching and widening / Loader clearing pull offs on Paint Lake Road 2 and widening @ Km 27 | 10 | F066-F118 | Paint Lake 2 | 0 | 44628 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7935KL-20220226-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7935KL-20220226-1Supervisor3252 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7938 | KL-20220227-1 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader 1 working from 49km to 26km. Grader 2 working from Paint Lake Road to 8km. Loader working on clearing pull offs between 9.2Km & 5Km on Paint Lake Road #2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44628 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7938KL-20220227-1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7938KL-20220227-1Supervisor184 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7944 | KL-20220228-1 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-28 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader Working On Snow Removal From 29 Km To 2 Km On Paint Lake Road 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44628 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7944KL-20220228-1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7944KL-20220228-1Supervisor2168 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7954 | KL-20220301-2 | 53511011 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-03-01 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader working on Snow Removal and benching snow banks from Km 1 to Km 13 on Paint Lake Road 2 | 10 | F066-F118 | Paint Lake 2 | 0 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7954KL-20220301-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7954KL-20220301-2Supervisor2168 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7957 | KL-20220302-2 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-03-02 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader working on Snow Removal from Km 49 to Km 13 on Paint Lake Road 2 @ park Grader at Km 2/Supervisor doing pickup shuffle | 10 | F066-F118 | Paint Lake 2 | 0 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7957KL-20220302-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7957KL-20220302-2Supervisor3252 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7966 | KL-20220303-5 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-03-03 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader working on snow removal from Paint Lake Road to F-033 | 10 | F009 - F065 | Paint Lake | 0 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7966KL-20220303-5Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7966KL-20220303-5Supervisor184 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7969 | KL-20220304-4 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-03-04 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader Continuing Working On Snow Removal From Paint Lake Road 2 To F033 | 10 | F009 - F065 | Paint Lake | 0 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7969KL-20220304-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7969KL-20220304-4Supervisor184 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7970 | KL-20220305-2 | 53511011 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-03-05 |  |  |  |  | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Loader Working On Snow Removal From Paint Lake Road 2 To F033 | 10 | F009 - F065 | Paint Lake | 0 | 44630 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7970KL-20220305-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7970KL-20220305-2Supervisor184 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7978 | KL-20220306-3 | 53511011 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-03-06 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader Working On Snow Removal From Paint Lake Road To 12.5 Km On Paint Lake Road 2/Graded 3 Times Due To Winter Storm/Loader Working From F037 To F034 | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44637 | [9 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7978KL-20220306-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7978KL-20220306-3Supervisor3252 | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3130 | KL-20200922-15 | 53511012 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-09-22 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of JJR Contracting for unloading Bridge and fixing wet areas on Paint Lake Road | 10 | F-033 to F-118 | Paint Lake Road 2 | 0 | 44103 |  | 15 | 44103 | [5 empty] | Martin Hunt | 10 | KABI LAKE FOREST PRODUCTS LTD3130KL-20200922-15Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD3130KL-20200922-15Supervisor2168OEWT-PA9-Lem-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3780 | KL-20201015-27 | 53511012 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-10-15 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Take broken 3" pump to Marathon Valard Yard | 10 | F-021 to F-032 | Paint Lake Raod 1-B | 0 | 44130 |  | 50 | 44132 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD3780KL-20201015-27Supervisor184 | KABI LAKE FOREST PRODUCTS LTD3780KL-20201015-27Supervisor184OEWT-PA10-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4050 | KL-20201029-16 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2020-10-29 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervisor of WF 10 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44152 |  | 50 | 44162 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD4050KL-20201029-16Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD4050KL-20201029-16Supervisor8672OEWT-PA11-LEM | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4177 | KL-20201105-11 | 53511012 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2020-11-05 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of CDSL logging and JJR | 10 | F033-F118 | Paint lake Road 2 | 0 | 44160 |  | 50 | 44163 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD4177KL-20201105-11Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD4177KL-20201105-11Supervisor4336OEWT-PA11-LEM | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6963 | KL-20210520-5 | 53511012 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6T Dozer starting leveling ruts and shaping road from Km 2 to Km 9.5 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD6963KL-20210520-5Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD6963KL-20210520-5Supervisor2168OEWT-PA17-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6987 | KL-20210525-5 | 53511012 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-05-25 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator Starting road maintenance to F038 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44348 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD6987KL-20210525-5Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD6987KL-20210525-5Supervisor2168OEWT-PA17-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6990 | KL-20210526-3 | 53511012 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-05-26 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator working on road maintenance to F40/ Grader starting on Paint Lake Road 2 to Km 4 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD6990KL-20210526-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD6990KL-20210526-3Supervisor2168OEWT-PA18-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6992 | KL-20210527-2 | 53511012 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-05-27 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator working on road maintenance to F040 / Grader working on Paint Lake Road 2 at km4 to km 10 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD6992KL-20210527-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD6992KL-20210527-2Supervisor3252OEWT-PA18-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6994 | KL-20210528-2 | 53511012 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-05-28 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator working on road maintenance from Km 15.5 to Km 19/ Grader working on Paint Lake Road 2 at Km 7 to 12 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44350 |  | 36 | 44355 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD6994KL-20210528-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD6994KL-20210528-2Supervisor4336OEWT-PA18-Lem | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7001 | KL-20210531-3 | 53511012 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-05-31 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator working on road maintenance and drainage from Km 16.5 to Km 19 /grader working on Paint Lake Road 2 from Km 12 to KM4 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44358 |  | 36 | 44360 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7001KL-20210531-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7001KL-20210531-3Supervisor3252OEWT-PA18-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7004 | KL-20210601-3 | 53511012 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-06-01 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator continue working on road maintenance and drainage from km 17 to km 18/ Grader finishing on Paint Lake Road 2 to Km 0 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44358 |  | 14 | 44359 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7004KL-20210601-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7004KL-20210601-3Supervisor3252OEWT-PA18-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7066 | KL-20210530-2 | 53511012 | Access | 0 | Supervisor | 84 | 3.5 | HR |  |  | 84 | 0 | 294 | 38.22 | 332.22 | 2021-05-30 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator working road maintenance and drainage to F044/045 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44372 |  | 36 | 44373 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7066KL-20210530-2Supervisor3.5294 | KABI LAKE FOREST PRODUCTS LTD7066KL-20210530-2Supervisor3.5294OEWT-PA18-Lem | [5 empty] | 1 | 294 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7427 | KL-20211005-1 | 53511012 | Access | 0 | Supervisor | 84 | 8.5 | HR |  |  | 84 | 0 | 714 | 92.82 | 806.82 | 2021-10-05 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F112. Excavator 2 working @ 43/42km. Rock trucks hauling from 37.5km to Skagen @ 36km. Labourer hauling fuel to 35km as per Valard. Supervision of Skagen/Morin. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-1Supervisor8.5714 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-1Supervisor8.5714OEWT-PA22-Lem | [5 empty] | 1 | 714 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7431 | KL-20211006-1 | 53511012 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-10-06 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-1Supervisor2168OEWT-PA22-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7434 | KL-20211007-1-R1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-10-07 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R1Supervisor8672OEWT-PA22-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7439 | KL-20211009-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-10-09 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km. Rock trucks on site for gravel haul. Supervision of Morin & Skagen. | 10 | F033 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-1Supervisor8672OEWT-PA22-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7441 | KL-20211010-1 | 53511012 | Access | 0 | Supervisor | 84 | 7.5 | HR |  |  | 84 | 0 | 630 | 81.9 | 711.9 | 2021-10-10 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, corduroy & cap 43km hill. Rock trucks on site for gravel haul. Supervise Morin & Skagen. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-1Supervisor7.5630 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-1Supervisor7.5630OEWT-PA22-Lem | [5 empty] | 1 | 630 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7442 | KL-20211011-1 | 53511012 | Access | 0 | Supervisor | 84 | 8.5 | HR |  |  | 84 | 0 | 714 | 92.82 | 806.82 | 2021-10-11 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, levelling ruts & drainage. Rock trucks on site for gravel haul. Supervisor touring for blasting locations. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-1Supervisor8.5714 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-1Supervisor8.5714OEWT-PA22-Lem | [5 empty] | 1 | 714 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7444 | KL-20211008-1-R1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-10-08 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7444KL-20211008-1-R1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7444KL-20211008-1-R1Supervisor8672OEWT-PA22-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7445 | KL-20211012-1 | 53511012 | Access | 0 | Supervisor | 84 | 6 | HR |  |  | 84 | 0 | 504 | 65.52 | 569.52 | 2021-10-12 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45 to 43km. Excavator 2 working from 43 to 40.5km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervisor site visit with blaster. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-1Supervisor6504 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-1Supervisor6504OEWT-PA22-Lem | [5 empty] | 1 | 504 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7448 | KL-20211013-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-10-13 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 46 to 43km. Excavator 2 working from 43 to 39km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervision of Morin, Skagen, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-1Supervisor8672OEWT-PA22-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7453 | KL-20211014-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-10-14 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from 46 to 39Km, levelling ruts & drainage. Rock trucks haulig existing material from F088 to 34.5Km. Labourer hauling fuel as per Valard. Supervision of Morin, Skagen & Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-1Supervisor8672OEWT-PA22-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7457 | KL-20211015-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-10-15 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Flll toFlOO level ruts & drainage isting material from F088 to 34.SKm as per Valard. Supervise Morin, Skagen, Pleson, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-1Supervisor8672OEWT-PA22-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7460 | KL-20211016-1 | 53511012 | Access | 0 | Supervisor | 84 | 9 | HR |  |  | 84 | 0 | 756 | 98.28 | 854.28 | 2021-10-16 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F194 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1Supervisor9756 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-1Supervisor9756OEWT-PA22-Lem | [5 empty] | 1 | 756 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7465 | KL-20211017-1 | 53511012 | Access | 0 | Supervisor | 84 | 7 | HR |  |  | 84 | 0 | 588 | 76.44 | 664.44 | 2021-10-17 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F108, F105,and F103 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | PAINT Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-1Supervisor7588 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-1Supervisor7588OEWT-PA22-Lem | [5 empty] | 1 | 588 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7471 | KL-20211018-1 | 53511012 | Access | 0 | Supervisor | 84 | 10 | HR |  |  | 84 | 0 | 840 | 109.2 | 949.2 | 2021-10-18 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34 as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1Supervisor10840 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-1Supervisor10840OEWT-PA22-Lem | [5 empty] | 1 | 840 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7475 | KL-20211019-1 | 53511012 | Access | 0 | Supervisor | 84 | 10 | HR |  |  | 84 | 0 | 840 | 109.2 | 949.2 | 2021-10-19 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts, laying Geo and spreading existing material @ Km 42 hill/rock trucks hauling existing material from F088 to Km 34 as per Valard. Labourers picking up 4 roll of Geo @12km on Paint Lake Road 2and deliver it to km 42/worked late to finish capping @km 42 for pickup access/Supervision of Morin, Skagen, Pleson and Opas | 10 |  | Paint | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1Supervisor10840 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1Supervisor10840OEWT-PA22-Lem | [5 empty] | 1 | 840 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7478 | KL-20211020-1 | 53511012 | Access | 0 | Supervisor | 84 | 10 | HR |  |  | 84 | 0 | 840 | 109.2 | 949.2 | 2021-10-20 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material @ Km 42.5/rock trucks hauling existing material from F088 to Km 34 and Km 42.5 as per Valard. Excavator 3 tracking from Km 49, starting @ F112 to F114 leveling ruts,shaping and drainage/725 rock truck driving to Km .5 for float/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1Supervisor10840 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-1Supervisor10840OEWT-PA22-Lem | [5 empty] | 1 | 840 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7414 | KL-20211001-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-10-01 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-1Supervisor8672OEWT-PA22-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7419 | KL-20211002-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-10-02 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-1Supervisor8672OEWT-PA22-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7421 | KL-20211003-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-10-03 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading & hauling from 46km to 45km. Labourers hauling fuel to 35km & installing silt fencing as per Valard. Supervision o Skagen & Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-1Supervisor8672OEWT-PA22-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7424 | KL-20211004-1 | 53511012 | Access | 0 | Supervisor | 84 | 8.5 | HR |  |  | 84 | 0 | 714 | 92.82 | 806.82 | 2021-10-04 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working from Paint 2 to F115. excavator 2 working from 45km to 43km. Rock truck hauling existing material from 37.5km to Skagen @36km. Supervision of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7424KL-20211004-1Supervisor8.5714 | KABI LAKE FOREST PRODUCTS LTD7424KL-20211004-1Supervisor8.5714OEWT-PA22-Lem | [5 empty] | 1 | 714 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7480 | KL-20211021-1 | 53511012 | Access | 0 | Supervisor | 84 | 10 | HR |  |  | 84 | 0 | 840 | 109.2 | 949.2 | 2021-10-21 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material on sections/rock trucks hauling existing material from F088 as per Valard. Excavator 3 continuing @ F113 to F115 leveling ruts,shaping and drainage for freezing/ Supervision of Morin, Skagen, Pleson and Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-1Supervisor10840 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-1Supervisor10840OEWT-PA22-Lem | [5 empty] | 1 | 840 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7482 | KL-20211022-1 | 53511012 | Access | 0 | Supervisor | 84 | 10 | HR |  |  | 84 | 0 | 840 | 109.2 | 949.2 | 2021-10-22 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 working from Km 43 to Km 40 and F105 access Shaping road/ excavator 2 working from Km 43 to Km 45 and F111 shaping road. Excavator 3 Finishing @ F115 to F117 leveling ruts,shaping for freezing and track to F123/ Supervision of Morin, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44495 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7482KL-20211022-1Supervisor10840 | KABI LAKE FOREST PRODUCTS LTD7482KL-20211022-1Supervisor10840OEWT-PA22-Lem | [5 empty] | 1 | 840 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7483 | KL-20211023-1 | 53511012 | Access | 0 | Supervisor | 84 | 7 | HR |  |  | 84 | 0 | 588 | 76.44 | 664.44 | 2021-10-23 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 shaping road from Km 43 to Km 40 anf F098/ Excavator 2 shaping road from 45 to 49 km and starting in F123 access/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44495 |  | 61 | 44496 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7483KL-20211023-1Supervisor7588 | KABI LAKE FOREST PRODUCTS LTD7483KL-20211023-1Supervisor7588OEWT-PA22-Lem | [5 empty] | 1 | 588 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7485 | KL-20211024-1 | 53511012 | Access | 0 | Supervisor | 84 | 7 | HR |  |  | 84 | 0 | 588 | 76.44 | 664.44 | 2021-10-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from Km 46 and F105 access/supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44496 |  | 61 | 44497 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7485KL-20211024-1Supervisor7588 | KABI LAKE FOREST PRODUCTS LTD7485KL-20211024-1Supervisor7588OEWT-PA23-Lem | [5 empty] | 1 | 588 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7488 | KL-20211025-1 | 53511012 | Access | 0 | Supervisor | 84 | 7 | HR |  |  | 84 | 0 | 588 | 76.44 | 664.44 | 2021-10-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from Km 44 to Km 40 and F105 access/supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44496 |  | 61 | 44497 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7488KL-20211025-1Supervisor7588 | KABI LAKE FOREST PRODUCTS LTD7488KL-20211025-1Supervisor7588OEWT-PA23-Lem | [5 empty] | 1 | 588 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7492 | KL-20211026-1 | 53511012 | Access | 0 | Supervisor | 84 | 7 | HR |  |  | 84 | 0 | 588 | 76.44 | 664.44 | 2021-10-26 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from F110 to Km 41 /supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7492KL-20211026-1Supervisor7588 | KABI LAKE FOREST PRODUCTS LTD7492KL-20211026-1Supervisor7588OEWT-PA23-Lem | [5 empty] | 1 | 588 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7496 | KL-20211027-1 | 53511012 | Access | 0 | Supervisor | 84 | 9 | HR |  |  | 84 | 0 | 756 | 98.28 | 854.28 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 44, laying Geo and spreading existing material/Excavtor 2 loading existing material@ km 17 on Hensen/rock truck hauling existing material to Km 44 supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-1Supervisor9756 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-1Supervisor9756OEWT-PA23-Lem | [5 empty] | 1 | 756 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7500 | KL-20211027-5 | 53511012 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Pick up 3 rolls of Geo in Pic River West and 6 partial rolls @ Marathon Yard and deliver to Km 44 on Paint Lake Road 2/Supervisor loading Geo with Labourer@Pic River West | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7500KL-20211027-5Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7500KL-20211027-5Supervisor3252OEWT-PA23-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7502 | KL-20211028-1 | 53511012 | Access | 0 | Supervisor | 84 | 10 | HR |  |  | 84 | 0 | 840 | 109.2 | 949.2 | 2021-10-28 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 laying Geo and spreading existing material @ Km 44 and shaping road to Km 45/Excavtor 2 cleaning up excavation @ km 17 on Hensen road and shaping road to F114 rock truck2 hauling from F088 to Km 34-33 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-1Supervisor10840 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-1Supervisor10840OEWT-PA23-Lem | [5 empty] | 1 | 840 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7506 | KL-20211029-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-10-29 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing clean up of excavation @ Km 17 on Hensen road and start shaping road to Km 45.5. Rock truck hauling existing material from F088 to Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44502 |  | 61 | 44503 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7506KL-20211029-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7506KL-20211029-1Supervisor8672OEWT-PA23-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7510 | KL-20211030-1 | 53511012 | Access | 0 | Supervisor | 84 | 9 | HR |  |  | 84 | 0 | 756 | 98.28 | 854.28 | 2021-10-30 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road to Km 45 to Km 43 and spreading spotted rock trucks loads. Rock truck hauling existing material from F088 to Morin @ Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas. | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44502 |  | 61 | 44503 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7510KL-20211030-1Supervisor9756 | KABI LAKE FOREST PRODUCTS LTD7510KL-20211030-1Supervisor9756OEWT-PA23-Lem | [5 empty] | 1 | 756 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7517 | KL-20211031-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-10-31 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 43 to Km 40.5 and spreading spotted rock trucks loads /Excavator 2 leveling ruts and shaping road from F116 to F112 rock truck hauling existing material from F088 to Morin @ Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F033 - F071 | Paint Lake 2 | 0 | 44505 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7517KL-20211031-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7517KL-20211031-1Supervisor8672OEWT-PA23-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7519 | KL-20211101-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-11-01 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 43 to Km 40.5 and spreading spotted rock trucks loads. Rock truck hauling existing material from F-088 to Morin @ 33.5Km as per Valard. Supervision of Morin, Skagen, JJR & Opas | 10 | F033 - F071 | Paint Lake 2 | 0 | 44501 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7519KL-20211101-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7519KL-20211101-1Supervisor8672OEWT-PA23-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7547 | KL-20211102-2 | 53511012 | Access | 0 | Supervisor | 84 | 9 | HR |  |  | 84 | 0 | 756 | 98.28 | 854.28 | 2021-11-02 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking from Km 43 to Km 17 on Hensen Road for float access /Rock truck hauling existing material from F088 to Morin@Km 33 as per Valard. Supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-2Supervisor9756 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-2Supervisor9756OEWT-PA23-Lem | [5 empty] | 1 | 756 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7549 | KL-20211103-2 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-11-03 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 41 shape road. Rock trucks haul existing material from F088 to Morin @ Km 33 as per Valard /Supervision of Morin, Skagen, JJR, Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-2Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-2Supervisor8672OEWT-PA23-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7550 | KL-20211104-2 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-11-04 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 42 shaping road and spreading existing material on road surfaces Rock trucks hauling existing material from F088 to @ Km 43/42 as per Valard /Supervision of Morin, Skagen, JJR and OPAS | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-2Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-2Supervisor8672OEWT-PA23-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7551 | KL-20211105-2 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-11-05 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 42 to Km 41 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F088 to @ Km 42/41 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint lake Road 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-2Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-2Supervisor8672OEWT-PA23-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7553 | KL-20211107-2 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-11-07 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working fro Km 41 to Km 39 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 41/39 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44519 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-2Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-2Supervisor8672OEWT-PA23-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7562 | KL-20211106-2-R1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-11-06 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 41 to Km 40 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F093 to @ Km 41/40 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44522 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R1Supervisor8672OEWT-PA23-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7563 | KL-20211108-3 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-11-08 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 42 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-3Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-3Supervisor8672OEWT-PA23-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7564 | KL-20211109-3 | 53511012 | Access | 0 | Supervisor | 84 | 10 | HR |  |  | 84 | 0 | 840 | 109.2 | 949.2 | 2021-11-09 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 44 leveling ruts and shaping road Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-3Supervisor10840 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-3Supervisor10840OEWT-PA23-Lem | [5 empty] | 1 | 840 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7565 | KL-20211110-4 | 53511012 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-11-10 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 42 access leveling ruts and shaping road rock trucks hauling from Km 27 to JJR @ Km 26/24 repairing road sections /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-4Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-4Supervisor3252OEWT-PA23-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7566 | KL-20211111-4 | 53511012 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-11-11 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-4Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-4Supervisor3252OEWT-PA23-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7570 | KL-20211112-2 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-11-12 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44520 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7570KL-20211112-2Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7570KL-20211112-2Supervisor8672OEWT-PA23-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7571 | KL-20211113-3 | 53511012 | Access | 0 | Supervisor | 84 | 5 | HR |  |  | 84 | 0 | 420 | 54.6 | 474.6 | 2021-11-13 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Rock truck on site for hauling of existing material @ 24km. Supervision of Morin, Skagen, JJR & Opas. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7571KL-20211113-3Supervisor5420 | KABI LAKE FOREST PRODUCTS LTD7571KL-20211113-3Supervisor5420OEWT-PA23-Lem | [5 empty] | 1 | 420 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7572 | KL-20211114-2 | 53511012 | Access | 0 | Supervisor | 84 | 7 | HR |  |  | 84 | 0 | 588 | 76.44 | 664.44 | 2021-11-14 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from 44Km to 41Km levelling ruts and shaping road. Rock truck on site for hauling of existing material @ 27Km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7572KL-20211114-2Supervisor7588 | KABI LAKE FOREST PRODUCTS LTD7572KL-20211114-2Supervisor7588OEWT-PA23-Lem | [5 empty] | 1 | 588 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7573 | KL-20211115-2 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-11-15 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road. Rock truck hauling existing material from 25Km and spotting dumping @ 22/23Km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7573KL-20211115-2Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7573KL-20211115-2Supervisor8672OEWT-PA23-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7575 | KL-20211116-3 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-11-16 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road for freezing. Rock truck hauling existing material from 27Km to 23/24Km & dricing out to 9Km at end of shift for float accesss. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-3Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-3Supervisor8672OEWT-PA23-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7576 | KL-20211117-4 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-11-17 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road & snow removal @ 44km to 43km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | [5 empty] | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7576KL-20211117-4Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7576KL-20211117-4Supervisor8672OEWT-PA23-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7577 | KL-20211118-3 | 53511012 | Access | 0 | Supervisor | 84 | 7 | HR |  |  | 84 | 0 | 588 | 76.44 | 664.44 | 2021-11-18 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 43 to Km 46 due to icy conditions /Supervision of Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44525 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7577KL-20211118-3Supervisor7588 | KABI LAKE FOREST PRODUCTS LTD7577KL-20211118-3Supervisor7588OEWT-PA23-Lem | [5 empty] | 1 | 588 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7583 | KL-20211119-3 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-11-19 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 43 to Km 40 due to icy conditions/Supervision of Morin, Skagen, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7583KL-20211119-3Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7583KL-20211119-3Supervisor8672OEWT-PA23-Lem | [5 empty] | 1 | 672 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7584 | KL-20211120-3 | 53511012 | Access | 0 | Supervisor | 84 | 7 | HR |  |  | 84 | 0 | 588 | 76.44 | 664.44 | 2021-11-20 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 42 to Km 46 due to slippery conditions/Supervision of Morin, Skagen, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7584KL-20211120-3Supervisor7588 | KABI LAKE FOREST PRODUCTS LTD7584KL-20211120-3Supervisor7588OEWT-PA23-Lem | [5 empty] | 1 | 588 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7585 | KL-20211121-2 | 53511012 | Access | 0 | Supervisor | 84 | 7 | HR |  |  | 84 | 0 | 588 | 76.44 | 664.44 | 2021-11-21 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and sanding road @ Km 42 to Km 46 due to slippery conditions/Supervision of Morin, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7585KL-20211121-2Supervisor7588 | KABI LAKE FOREST PRODUCTS LTD7585KL-20211121-2Supervisor7588OEWT-PA23-Lem | [5 empty] | 1 | 588 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7587 | KL-20211123-2 | 53511012 | Access | 0 | Supervisor | 84 | 7 | HR |  |  | 84 | 0 | 588 | 76.44 | 664.44 | 2021-11-23 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 scraping and shaping @ Km 42 to Km 46 /Excavator 2 scraping and sanding Km 13.5 to 17 for stringing crews/Supervision of Skagen and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7587KL-20211123-2Supervisor7588 | KABI LAKE FOREST PRODUCTS LTD7587KL-20211123-2Supervisor7588OEWT-PA23-Lem | [5 empty] | 1 | 588 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7590 | KL-20211124-2 | 53511012 | Access | 0 | Supervisor | 84 | 6 | HR |  |  | 84 | 0 | 504 | 65.52 | 569.52 | 2021-11-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 scraping and shaping @ Km 45 to Km 48 /Excavator 2 scraping and sanding Km 16 to 18 for stringing crews demob | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7590KL-20211124-2Supervisor6504 | KABI LAKE FOREST PRODUCTS LTD7590KL-20211124-2Supervisor6504OEWT-PA23-Lem | [5 empty] | 1 | 504 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3631 | KL-20201009-20 | 53511102 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-10-09 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Shaping Road and Widing Areas | 11 | F-119 to F-134 | Hensen Road | 0 | 44125 |  | 55 | 44129 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD3631KL-20201009-20Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD3631KL-20201009-20Supervisor3252OEWT-PA10-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5475 | KL-20210119-26 | 53511102 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-01-19 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator starting to make ramp with trees for F133 Hub | 11 | F119-F134 | Hensen Road | 0 | 44222 |  | 15 | 44238 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5475KL-20210119-26Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5475KL-20210119-26Supervisor184OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5496 | KL-20210120-18 | 53511102 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Exc finishing making ramp with trees and capping for F133 Hub Access & track to F114/Operator Extra travel/Based out of White River. | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5496KL-20210120-18Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5496KL-20210120-18Supervisor184OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5497 | KL-20210120-19 | 53511102 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336F excavator building new road around F128 structure as per Valard/Operator extra travel/based out of White River | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5497KL-20210120-19Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5497KL-20210120-19Supervisor184OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5539 | KL-20210122-17 | 53511102 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-01-22 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator using existing material to minimize steep grade at F117/F116 Access, as per Valard (Revised) | 11 | F119--F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5539KL-20210122-17Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5539KL-20210122-17Supervisor184OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4143 | KL-20201103-13 | 53511103 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Go down to Hensen Road and pick up 8 rolls of Geo and take back to White River Yard | 11 | F119-F134 | Hensen Road | 0 | 44153 |  | 56 | 44163 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD4143KL-20201103-13Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4143KL-20201103-13Supervisor184OEWT-PA11-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5474 | KL-20210119-25 | 53511103 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-01-19 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 335F Boom Brusher tracking from F124 to F133 & start to grind & freeze corduroy for pick up access. | 11 | F119-F134 | Hensen Road | 0 | 44222 |  | 15 | 44237 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5474KL-20210119-25Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5474KL-20210119-25Supervisor184OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5499 | KL-20210120-21 | 53511103 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 335F boom brusher finishing to grind & freeze corduroy for Pick up access & tracking back to F124 | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5499KL-20210120-21Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5499KL-20210120-21Supervisor184OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3273 | KL-20200927-17 | 53511104 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-27 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pit runfrom Provost pit #5/Dozer spreading | 11 | F-119 to F-134 | Hensen Road | 0 | 43900 |  | 48 | 43871 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3273KL-20200927-17Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD3273KL-20200927-17Supervisor3252OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3274 | KL-20200927-18 | 53511104 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-27 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Gord Enders Trucking gravel haul | 11 | F-119 to F-134 | Hensen Road | 0 | 43900 |  | 48 | 43871 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3274KL-20200927-18Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD3274KL-20200927-18Supervisor3252OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3300 | KL-20200928-23 | 53511104 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-28 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauling pit run from Provost Pit #5 to AE1 on Henson Road /Dozer spreading and widening areas | 11 | F-119 to F-134 | Hensen Road | 0 | 44109 |  | 50 | 44110 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD3300KL-20200928-23Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD3300KL-20200928-23Supervisor3252OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3301 | KL-20200928-24 | 53511104 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-28 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of JJR Contracting Gravel Haul | 11 | F-119 to F-134 | Hensen Road | 0 | 44109 |  | 50 | 44110 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD3301KL-20200928-24Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD3301KL-20200928-24Supervisor3252OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3334 | KL-20200929-25 | 53511104 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-09-29 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of JJR Contracting Gravel Haul | 11 | F119-F134 | Hensen Road | 0 | 44109 |  | 50 | 44115 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD3334KL-20200929-25Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD3334KL-20200929-25Supervisor2168OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3376 | KL-20201001-22 | 53511104 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-10-01 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Triaxles hauling Pit Run from Provost pit #5 , Dozer spreading and widening areas.Grade Hensen road for gravel Haul - SSF-14029.Haul Pit Run from Provost Pit #5 to AE1 on Hensen Road - JJR-70095. Hauled Gravel to Hensen Road from Provost Pit #5 - BMC-30121 | 11 | F-119 to F-134 | Hensen Road | 0 | 44118 |  | 48 | 44123 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3376KL-20201001-22Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD3376KL-20201001-22Supervisor3252OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3379 | KL-20201001-25 | 53511104 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-10-01 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of JJR Contracting Gravel haul | 11 | F-119 to F-134 | Hensen Road | 0 | 44118 |  | 48 | 44123 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3379KL-20201001-25Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD3379KL-20201001-25Supervisor2168OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3404 | KL-20201002-24 | 53511104 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-10-02 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Tri axles hauling pit run from Provost Pit 5 - Dozer spreading and widening road. Haul Pit Run from Provost pit #5 to AE1 on Hensen Road - JJR-70096 | 11 | F-119 to F-134 | Hensen Road | 0 | 44106 |  | 48 | 44123 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3404KL-20201002-24Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD3404KL-20201002-24Supervisor3252OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3405 | KL-20201002-25 | 53511104 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-10-02 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of JJR contracting Gravel haul | 11 | F-119 to F-134 | Hensen Road | 0 | 44118 |  | 48 | 44123 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3405KL-20201002-25Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD3405KL-20201002-25Supervisor2168OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3406 | KL-20201002-26 | 53511104 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-10-02 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of CBT Excavating Gravel haul | 11 | F-119 to F-134 | Hensen Road | 0 | 44118 |  | 48 | 44123 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3406KL-20201002-26Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD3406KL-20201002-26Supervisor2168OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3411 | KL-20200930-19 | 53511104 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-30 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer spreading Pit Run from Provost Pit #5 and widening areas. Trucks hauling gravel from Provost Pit | 11 | F-119 to F-134 | Hensen Road | 0 | 44119 |  | 48 | 44120 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3411KL-20200930-19Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD3411KL-20200930-19Supervisor3252OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3413 | KL-20200930-21 | 53511104 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-09-30 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of JJR Contracting Gravel Haul | 11 | F-119 to F-134 | Hensen Road | 0 | 44119 |  | 48 | 44120 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3413KL-20200930-21Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD3413KL-20200930-21Supervisor2168OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3831 | KL-20201018-15 | 53511104 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-10-18 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauled 2 load pit run from Provost pit 5 to Km 3 on hensen road Culverts. Cress install cross drain culverts. 330 excavator installed 3 200mm culverts, Km 6.5, 4.5, 2 - A lot of travelling with Machine -travelled Km 10 to 2 - CR-10821 | 11 | F-119 to F-134 | Hensen Road | 0 | 44130 |  | 55 | 44132 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD3831KL-20201018-15Supervisor184 | KABI LAKE FOREST PRODUCTS LTD3831KL-20201018-15Supervisor184OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4084 | KL-20201031-12 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-10-31 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sand Hills and corners on Hensen Road for float truck hauling in a buncher/Sanding hauled from provost pit in Wawa | 11 | F203-F211 | Hensen Rd | 0 | 44152 |  | 48 | 44154 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4084KL-20201031-12Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD4084KL-20201031-12Supervisor3252OEWT-PA11-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4713 | KL-20201129-14 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-11-29 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervisor of Grading on Paint Lake 2 Road | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44181 |  | 50 | 44203 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD4713KL-20201129-14Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4713KL-20201129-14Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4992 | KL-20201211-12 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-12-11 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load partial load @6km pit on 600 road for sanding of hill laydown 1/ load sand from F119 and sand road for float access as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 48 | 44203 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4992KL-20201211-12Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD4992KL-20201211-12Supervisor2168OEWT-PA12-LEM-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5037 | KL-20201216-9 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-16 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Skagen and Son Forestry snow removal | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5037KL-20201216-9Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5037KL-20201216-9Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5059 | KL-20201219-6 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-19 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Skagen & Son Forestry snow removal on Hensen to Km 17. | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5059KL-20201219-6Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5059KL-20201219-6Supervisor184OEWT-PA12-LEM-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5160 | KL-20201228-11 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-28 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding Hills & Corners on Hensen Rd from Hwy to Km 17 for 60' bridge delivery. Dozer and grader clearing different sections of Hensen Rd. | 11 | F119-F134 | Hensen Road | 0 | 44202 |  | 56 | 44214 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5160KL-20201228-11Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5160KL-20201228-11Supervisor184OEWT-PA13-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5207 | KL-20210103-5 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-01-03 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load of sand from White River town pit/ sanding hills and corners on hensen road from hwy to 17km with existing material as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5207KL-20210103-5Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5207KL-20210103-5Supervisor184OEWT-PA13-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5283 | KL-20210109-6 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-01-09 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Take 1 load of screened sand from town pit, and finish sanding Hensen Rd to km 17. Floats with existing sand as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44211 |  | 15 | 44219 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5283KL-20210109-6Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5283KL-20210109-6Supervisor184OEWT-PA13-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5363 | KL-20210114-9 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-01-14 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load screened sand from town pit and finished sanding Hensen Road to 17km with existing sand as per Valard/ Excavator cleaning up @ F119 for Sand | 11 | F119-F134 | Hensen Road | 0 | 44218 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5363KL-20210114-9Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD5363KL-20210114-9Supervisor2168OEWT-PA13-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5439 | KL-20210118-13 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-01-18 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat D6K Dozer Clearing snow from Anjigami Rd to Anjigami River for Bridge delivery as per Valard. | 11 | F228 | F-228 Road | 0 | 44216 |  | 56 | 44229 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5439KL-20210118-13Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD5439KL-20210118-13Supervisor2168OEWT-PA13-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5614 | KL-20210125-11 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-01-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | D6K dozer starting snow removal from km 17 on Hensen Rd to F133. | 11 | F119-F134 | Hensen Road | 0 | 44225 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5614KL-20210125-11Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5614KL-20210125-11Supervisor184OEWT-PA14-Lem-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5700 | KL-20210201-8 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-02-01 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Drive from White River/Load Screened sand from Provost Pit #5/Sand hills and corners to 17km on hensen road/drive back to White River | 11 | F119-F134 | Hensen Road | 0 | 44235 |  | 53 | 44241 | [5 empty] | Clint Maerz | 11 | KABI LAKE FOREST PRODUCTS LTD5700KL-20210201-8Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD5700KL-20210201-8Supervisor2168OEWT-PA14-Lem-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5838 | KL-20210209-15 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-02-09 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Drive from White River/load 5 loads of screened sand from Provost Pit 5/Sand hills & corners to km 17 then drive back to White River. | 11 | F119-F134 | Hensen Road | 0 | 44243 |  | 15 | 44250 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5838KL-20210209-15Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD5838KL-20210209-15Supervisor2168OEWT-PA14-Lem-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5846 | KL-20210210-8 | 53511111 | Access | 0 | Supervisor | 84 | 5 | HR |  |  | 84 | 0 | 420 | 54.6 | 474.6 | 2021-02-10 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Go to Hensen Rd and steam a culvert @ km 3.5. Cover corduroy in shoefly past F73. Clear snow from road from 0 to 15Km on Hensen West and from Hwy17 to 17Km. | 11 | F119-F134 | Hensen Road | 0 | 44244 |  | 15 | 44250 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5846KL-20210210-8Supervisor5420 | KABI LAKE FOREST PRODUCTS LTD5846KL-20210210-8Supervisor5420OEWT-PA14-Lem-R1 | [5 empty] | 1 | 420 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5874 | KL-20210212-5 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 |  | 168 | 21.84 | 189.84 | 2021-02-12 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load 4 loads screen sand from Provost pit #5/ sand hills and corners to 17km on Hensen Road. Grader work form Hwy 17 to 17Km, loader open road to F110 to F112. | 11 | F119-F134 | Hensen Road | 0 | 44244 |  | 15 | 44254 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5874KL-20210212-5Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD5874KL-20210212-5Supervisor2168OEWT-PA14-Lem-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5916 | KL-20210215-11 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-02-15 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat D5K Dozer to F169 for snow removal. Dozer remove snow from F169 to F165. | 11 | F165-F169 | Magpie Hills Road | 0 | 44249 |  | 14 | 44250 | [5 empty] | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD5916KL-20210215-11Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5916KL-20210215-11Supervisor184OEWT-PA14-Lem-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5945 | KL-20210217-9 | 53511111 | Access | 0 | Supervisor | 84 | 7 | HR |  |  | 84 | 0 | 588 | 76.44 | 664.44 | 2021-02-17 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Steam Pipe at km 3.5 on Hensen Rd | 11 | F119-F134 | Hensen Road | 0 | 44251 |  | 15 | 44254 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5945KL-20210217-9Supervisor7588 | KABI LAKE FOREST PRODUCTS LTD5945KL-20210217-9Supervisor7588OEWT-PA14-Lem-R1 | [5 empty] | 1 | 588 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6048 | KL-20210225-16 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-02-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load of screeded sand from Town Pit/Haul 2 loads of screened sand from MacIntyre Pit/Sand hills & corners to km 17 on Hensen, drive back to White River | 11 | F119-F134 | Hensen Road | 0 | 44256 |  | 56 | 44262 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6048KL-20210225-16Supervisor184 | KABI LAKE FOREST PRODUCTS LTD6048KL-20210225-16Supervisor184OEWT-PA14-Lem-R1 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6096 | KL-20210226-6 | 53511111 | Access | 0 | Supervisor | 84 | 6 | HR |  |  | 84 | 0 | 504 | 65.52 | 569.52 | 2021-02-26 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Go down to Hensen Road and steamed pipe at Km 3.6 and install heat trace top | 11 | F119-F134 | Hensen Road | 0 | 44262 |  | 56 | 44265 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6096KL-20210226-6Supervisor6504 | KABI LAKE FOREST PRODUCTS LTD6096KL-20210226-6Supervisor6504OEWT PA15-LEM | [5 empty] | 1 | 504 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6100 | KL-20210226-10 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-02-26 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking to F212 access pushing snow back and clearing pull outs. Excavator brushing AE1 Access for F-228 and F-212 | 11 | F-212 to F-214 | Michipicoten Road- 1 | 0 | 44262 |  | 56 | 44265 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6100KL-20210226-10Supervisor184 | KABI LAKE FOREST PRODUCTS LTD6100KL-20210226-10Supervisor184OEWT PA15-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6124 | KL-20210228-10 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-02-28 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue snow removal on AE1 access to F212 | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44263 |  | 56 | 44265 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6124KL-20210228-10Supervisor184 | KABI LAKE FOREST PRODUCTS LTD6124KL-20210228-10Supervisor184OEWT PA15-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6140 | KL-20210222-14 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-02-22 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer clearing roads km20 to km15, loader clearing km 0 to 5 Hensen West. | 11 | F119-F134 | Hensen Road | 0 | 44269 |  | 56 | 44270 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6140KL-20210222-14Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD6140KL-20210222-14Supervisor2168OEWT PA15-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6352 | KL-20210317-5 | 53511111 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-03-17 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track to F123/F124 from Km 17 on Hensen Road and repair hills for pick up use | 11 | F119-F134 | Hensen Road | 0 | 44281 |  | 56 | 44282 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6352KL-20210317-5Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD6352KL-20210317-5Supervisor0.542OEWT PA15-LEM | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6357 | KL-20210318-3 | 53511111 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-03-18 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair hills from F123 to F127 for pick up access | 11 | F119-F134 | Hensen Road | 0 | 44281 |  | 56 | 44282 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6357KL-20210318-3Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD6357KL-20210318-3Supervisor0.542OEWT PA15-LEM | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7697 | KL-20211215-4 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-12-15 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer finishing snow removal from Hensen road to F132 | 11 | F118-F127 | Henson | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7697KL-20211215-4Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7697KL-20211215-4Supervisor2168OEWT-PA24-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7698 | KL-20211215-5 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-12-15 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Scarifying Trembley Road | 11 | F161 - F164 | Trembley Falls | 0 |  |  | 46 | 44583 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7698KL-20211215-5Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7698KL-20211215-5Supervisor184OEWT-PA24-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7592 | KL-20211124-4 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-11-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader continuing to scraping and sand road to F213/F214 for stringing crews | 11 | F212-F235 | Ainjigame | 0 | 44529 |  | 61 | 44530 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7592KL-20211124-4Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7592KL-20211124-4Supervisor2168OEWT-PA23-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7594 | KL-20211125-3 | 53511111 | Access | 0 | Supervisor | 84 | 5 | HR |  |  | 84 | 0 | 420 | 54.6 | 474.6 | 2021-11-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader continuing to scraping and sand road to F213, F217 and to F218 for stringing crews/ Supervision of Skagen | 11 | F212-F235 | Anjigame | 0 | 44525 |  | 61 | 44530 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7594KL-20211125-3Supervisor5420 | KABI LAKE FOREST PRODUCTS LTD7594KL-20211125-3Supervisor5420OEWT-PA23-Lem | [5 empty] | 1 | 420 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7602 | KL-20211128-2 | 53511111 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-11-28 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and shaping road from F204 to F211 and to F200 / supervision of Skagen | 11 | F170-F211 | High Falls Road | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7602KL-20211128-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7602KL-20211128-2Supervisor4336OEWT-PA24-LEM | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7605 | KL-20211129-2 | 53511111 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-11-29 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F203 to F185 / supervision of Skagen | 11 | F170-F211 | High Falls Road | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7605KL-20211129-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7605KL-20211129-2Supervisor4336OEWT-PA24-LEM | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7606 | KL-20211129-3 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-11-29 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17.5 on Hensen Road | 11 | F118-F127 | Hensen Road | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7606KL-20211129-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7606KL-20211129-3Supervisor184OEWT-PA24-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7607 | KL-20211129-4 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-11-29 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader starting scraping and sanding road to F213/F214 for stringing crews | 11 | F212-F235 | Ainjigame Road | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7607KL-20211129-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7607KL-20211129-4Supervisor184OEWT-PA24-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7610 | KL-20211130-3 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-11-30 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader continuing scraping and sanding road to F213/F214 for stringing crews | 11 | F212-F235 | Anjigame Road | 0 | 44537 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7610KL-20211130-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7610KL-20211130-3Supervisor3252OEWT-PA24-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7611 | KL-20211130-4 | 53511111 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-11-30 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F184 to F181 and F177 to F171 / supervision of Skagen | 11 | F170-F211 | High Falls | 0 | 44536 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7611KL-20211130-4Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7611KL-20211130-4Supervisor4336OEWT-PA24-LEM | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7612 | KL-20211201-2 | 53511111 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-12-01 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal @ F179 to F180 and F193 to F181 / supervision of Skagen | 11 | F170-F212 | High Falls | 0 | 44537 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7612KL-20211201-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7612KL-20211201-2Supervisor4336OEWT-PA24-LEM | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7615 | KL-20211201-5 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-12-01 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader starting scraping and sanding road to F213/F214 and access to F216 for stringing crews | 11 | F212-F235 | Anjigami | 0 | 44537 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7615KL-20211201-5Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7615KL-20211201-5Supervisor2168OEWT-PA24-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7616 | KL-20211201-6 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-12-01 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17.5 km on Hensen Road | 11 | F118-F127 | Henson | 0 | 44537 |  | 61 | 44538 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7616KL-20211201-6Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7616KL-20211201-6Supervisor184OEWT-PA24-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7622 | KL-20211202-4 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17.5 on Hensen road/ Dozer working on snow removal and shaping road from F122 to F132 | 11 | F118 - F127 | Henson | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7622KL-20211202-4Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7622KL-20211202-4Supervisor2168OEWT-PA24-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7623 | KL-20211202-5 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader doing snow removal from Anjigami road to F218 | 11 | F212-F235 | Anjigame | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7623KL-20211202-5Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7623KL-20211202-5Supervisor2168OEWT-PA24-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7626 | KL-20211202-8 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and shaping road @ F203 to F211 | 11 | F170-F211 | High Falls | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7626KL-20211202-8Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7626KL-20211202-8Supervisor3252OEWT-PA24-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7629 | KL-20211203-3 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-12-03 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and shaping road @ F198 to F202 and track to Km 11 on High Falls Raod/ Supervision of Skagen | 11 | F170 - F211 | High Falls | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7629KL-20211203-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7629KL-20211203-3Supervisor3252OEWT-PA24-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7630 | KL-20211203-4 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-12-03 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on sections from Hwy 17 to Km 17.5 on Hensen road filling rough sections with snow | 11 | F118 - F127 | Henson | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7630KL-20211203-4Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7630KL-20211203-4Supervisor2168OEWT-PA24-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7634 | KL-20211204-2 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-12-04 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer tracking from Km 11 to 1.5, scraping road from F177 to F171 and assist stringing crews/ Supervision of Skagen | 11 | F170-F211 | High Falls | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7634KL-20211204-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7634KL-20211204-2Supervisor3252OEWT-PA24-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7635 | KL-20211204-3 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-12-04 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Graderworking on snow removal from Hwy 17 to Km 17 | 11 | F118 - F127 | Henson | 0 | 44539 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7635KL-20211204-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7635KL-20211204-3Supervisor184OEWT-PA24-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7642 | KL-20211206-1 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-12-06 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 | 11 | F118-F127 | Henson | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7642KL-20211206-1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7642KL-20211206-1Supervisor184OEWT-PA24-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7645 | KL-20211206-4 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-12-06 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F175 to F171 and from F185 to F193/ Grader working on High Falls Road and to F203 | 11 | F170-F211 | High Falls | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7645KL-20211206-4Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7645KL-20211206-4Supervisor3252OEWT-PA24-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7648 | KL-20211207-2 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-12-07 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on benching snow banks from Hwy 17 to Km 17 and clearing pull offs | 11 | F118-F127 | Henson | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7648KL-20211207-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7648KL-20211207-2Supervisor184OEWT-PA24-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7649 | KL-20211207-3 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-12-07 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F185 to F181 and from F198 to F208/ Grader working on High Falls Road, F200 and F195 access | 11 | F170-F211 | High Falls | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7649KL-20211207-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7649KL-20211207-3Supervisor3252OEWT-PA24-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7651 | KL-20211207-5 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-12-07 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal @ Trembley Road and F161 to F164 | 11 | F161-F164 | Trembley Falls | 0 | 44540 |  | 46 | 44545 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7651KL-20211207-5Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7651KL-20211207-5Supervisor184OEWT-PA24-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7654 | KL-20211208-3 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F198 to F208 & support of stringing equipment. Grader working on High Falls Road, F170, F175, F176, F185 to F181 & F207 access. | 11 | F170-F211 | High Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7654KL-20211208-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7654KL-20211208-3Supervisor3252OEWT-PA24-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7661 | KL-20211209-4 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying Hensen Road from hwy 17 to 17km. Sand truck sanding hills & corners with existing sand from 17km. Excavator used for loading sand. | 11 | F118-F127 | Henson | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7661KL-20211209-4Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7661KL-20211209-4Supervisor3252OEWT-PA24-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7664 | KL-20211209-7 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-12-09 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal @ F180, F172, F171, F173 & F208 to F211. Grader working on High Falls Road, F185 to F181 & access to F207 | 11 | F170-F211 | High Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7664KL-20211209-7Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7664KL-20211209-7Supervisor3252OEWT-PA24-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7668 | KL-20211210-4 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-12-10 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal to F198, F202 & F2003 to F211. Grader working on High Falls road, F180, F194 to F197 & access to F207. | 11 | F170-F211 | High Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7668KL-20211210-4Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7668KL-20211210-4Supervisor3252OEWT-PA24-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7669 | KL-20211210-5 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-12-10 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal @ Trembley Road & F161 to F164 | 11 | F161 - F164 | Trembley Falls | 0 | 44546 |  | 46 | 44551 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7669KL-20211210-5Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7669KL-20211210-5Supervisor184OEWT-PA24-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7683 | KL-20211212-3 | 53511111 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-12-12 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Scarifying from Hwy 17 to Km 17 and clearing pull offs | 11 | F118-F127 | Henson | 0 | 44551 |  | 61 | 44561 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7683KL-20211212-3Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7683KL-20211212-3Supervisor0.542OEWT-PA24-LEM | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7684 | KL-20211212-4 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-12-12 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on High Falls Road to Km 13 and F200/ Dozer working from F206 to F211 | 11 | F170-F211 | High Falls | 0 | 44551 |  | 61 | 44561 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7684KL-20211212-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7684KL-20211212-4Supervisor184OEWT-PA24-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7685 | KL-20211212-5 | 53511111 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-12-12 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Snow removal and trembley road and F161 to F164 | 11 | F161 - F164 | Trembley Falls | 0 | 44551 |  | 61 | 44560 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7685KL-20211212-5Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7685KL-20211212-5Supervisor0.542OEWT-PA24-LEM | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7688 | KL-20211213-3 | 53511111 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-12-13 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Finish snow removal from F198 to F201 | 11 | F170-F211 | High Falls | 0 | 44551 |  | 61 | 44560 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7688KL-20211213-3Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7688KL-20211213-3Supervisor0.542OEWT-PA24-LEM | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7690 | KL-20211214-2 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-12-14 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working from @ F173 to F171 and on High Falls Road to Km 13 | 11 | F170-F211 | High Falls | 0 | 44551 |  | 61 | 44560 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7690KL-20211214-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7690KL-20211214-2Supervisor184OEWT-PA24-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7691 | KL-20211214-3 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-12-14 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Scarifying hills and corners from Km 12 to Hwy 17/Dozer starting snow removal from Hensen road to F128 | 11 | F118-F127 | Henson | 0 | 44551 |  | 61 | 44560 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7691KL-20211214-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7691KL-20211214-3Supervisor2168OEWT-PA24-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7700 | KL-20211216-3 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-12-16 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F037 to F033 | 10 | F066-F118 | Paint Lake 2 | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7700KL-20211216-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7700KL-20211216-3Supervisor2168OEWT-PA24-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7708 | KL-20211219-4 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-12-19 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hensen Road to F127 | 11 | F118-F127 | Henson | 0 |  |  | 46 | 44573 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7708KL-20211219-4Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7708KL-20211219-4Supervisor2168OEWT-PA24-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7717 | KL-20211231-1 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-12-31 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hensen Road to F132 | 11 | F119-F127 | Henson | 0 |  |  | 61 | 44572 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7717KL-20211231-1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7717KL-20211231-1Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7720 | KL-20220102-1 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-02 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal, widening road and clearing pull offs from Hensen road to F132 for freezing | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7720KL-20220102-1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7720KL-20220102-1Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7721 | KL-20220102-2 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-02 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on Trembley Road from Harbour Road to Hwy 17 | 11 | F161-F164 | Trembley Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7721KL-20220102-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7721KL-20220102-2Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7722 | KL-20220102-3 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-02 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 3.5 on High Falls Road and F171 to F177 | 11 | F118-F127 | Henson | 0 | 44568 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7722KL-20220102-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7722KL-20220102-3Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7725 | KL-20220103-3 | 53511111 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2022-01-03 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F164 to F161 | 11 | F161-F164 | Trembley Falls | 0 | 44568 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7725KL-20220103-3Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7725KL-20220103-3Supervisor0.542OEWT-PA25-Lem | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7726 | KL-20220103-4 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-03 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F171 to F188 | 11 | F170-F211 | High Falls | 0 | 44568 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7726KL-20220103-4Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7726KL-20220103-4Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7727 | KL-20220103-5 | 53511111 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2022-01-03 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F169 to F165 | 11 | F165-F169 | Magpie Hills | 0 | 44568 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7727KL-20220103-5Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7727KL-20220103-5Supervisor0.542OEWT-PA25-Lem | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7730 | KL-20220104-3 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-04 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F171, F180, F165 and High Falls Road to Km 13 | 11 | F170-F211 | High Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7730KL-20220104-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7730KL-20220104-3Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7732 | KL-20220105-2 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 |  | 168 | 21.84 | 189.84 | 2022-01-05 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Hensen Road to F132 and assisting stringing crews/Excavatorcleaning up and setting up a face @Km 17 for sand access | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7732KL-20220105-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7732KL-20220105-2Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7733 | KL-20220105-3 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-05 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  |  | 11 | F161 - F164 | Trembley Falls | 0 | 44572 |  | 46 | 44562 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7733KL-20220105-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7733KL-20220105-3Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7734 | KL-20220105-4 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-05 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F171 to F188 | 11 | F170-F211 | High Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7734KL-20220105-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7734KL-20220105-4Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7735 | KL-20220105-5 | 53511111 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2022-01-05 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F169 to F165 | 11 | F165 - F169 | Magpie Hills | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7735KL-20220105-5Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7735KL-20220105-5Supervisor0.542OEWT-PA25-Lem | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7738 | KL-20220106-3 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 |  | 84 | 10.92 | 94.92 | 2022-01-06 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on filling water holes with snow, widening road and corners to F127 for stringing crews | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7738KL-20220106-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7738KL-20220106-3Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7741 | KL-20220107-3 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-07 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road and corners to F132 for stringing crews | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7741KL-20220107-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7741KL-20220107-3Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7742 | KL-20220107-4 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-07 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Trembley Road from Km 6 to Km 1 abd F161 to F164 | 11 | F161 - F164 | Trembley Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7742KL-20220107-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7742KL-20220107-4Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7743 | KL-20220107-5 | 53511111 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2022-01-07 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working from F171 to F177 | 11 | F170-F211 | High Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7743KL-20220107-5Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7743KL-20220107-5Supervisor0.542OEWT-PA25-Lem | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7745 | KL-20220108-2 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-08 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working from Hensen Road to F131, dragging road with blast mat, scraping hills and assisting stringers hauling in material | 11 | F118-F127 | Henson | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7745KL-20220108-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7745KL-20220108-2Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7746 | KL-20220108-3 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-08 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Trembley Road from Km 6 to Km 1 and F161 to F164 | 11 | F161-F164 | Trembley Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7746KL-20220108-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7746KL-20220108-3Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7747 | KL-20220108-4 | 53511111 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2022-01-08 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working from F171 to F177 | 11 | F170-F211 | High Falls | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7747KL-20220108-4Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7747KL-20220108-4Supervisor0.542OEWT-PA25-Lem | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7748 | KL-20220108-5 | 53511111 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2022-01-08 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F169 to F165 | 11 | F165 - F169 | Magpie Hills | 0 | 44572 |  | 46 | 44575 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7748KL-20220108-5Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7748KL-20220108-5Supervisor0.542OEWT-PA25-Lem | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7749 | KL-20220109-1 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-01-09 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working on snow removal from Km 17 on Hensen to Hwy 17 and clearing pull offs/Dozer pushing back snow banks from Km 17 to Km 1 on Hensen Road | 11 | F118-F127 | Henson | 0 | 44575 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7749KL-20220109-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7749KL-20220109-1Supervisor3252OEWT-PA25-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7750 | KL-20220109-2 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-09 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Snow removal from F171 to F188 and clearing pads and pull offs | 11 | F170-F211 | High Falls | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7750KL-20220109-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7750KL-20220109-2Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7752 | KL-20220110-2 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-10 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer pushing back snow banks and clearing pull offs from Km .5 to Km 17 on Hensen Road | 11 | F118-F127 | Henson | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7752KL-20220110-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7752KL-20220110-2Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7753 | KL-20220110-3 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-10 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on Trembley Road from Km 7 to Km 1 and F161 to F164 | 11 | F161 - F164 | Trembley Falls | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7753KL-20220110-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7753KL-20220110-3Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7754 | KL-20220110-4 | 53511111 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2022-01-10 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F169 to F165 and pads | 11 | F165 - F169 | Magpie Hills | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7754KL-20220110-4Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7754KL-20220110-4Supervisor0.542OEWT-PA25-Lem | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7756 | KL-20220111-2 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-11 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader dragging road with blast mat, scraping hills and filling in rough areas | 11 | F118-F127 | Henson | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7756KL-20220111-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7756KL-20220111-2Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7757 | KL-20220111-3 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-11 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from F171 to F188 | 11 | F171 - F211 | High Falls | 0 | 44574 |  | 46 | 44576 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7757KL-20220111-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7757KL-20220111-3Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7760 | KL-20220112-3 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-12 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader scraping hills, clearing spur roads and sanding Hills to F127 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7760KL-20220112-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7760KL-20220112-3Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7762 | KL-20220112-5 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-12 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader driving from High Falls, scarifing hills and corners Trembley Road from Km 7 to Km 1 and F161 to F164 | 11 | F161 - F164 | Trembley Falls | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7762KL-20220112-5Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7762KL-20220112-5Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7765 | KL-20220113-3 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-13 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding and dragging blast mat to F132 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7765KL-20220113-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7765KL-20220113-3Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7766 | KL-20220113-4 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-13 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader for support of stringing crews @ F171 | 11 | F170-F211 | High Falls | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7766KL-20220113-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7766KL-20220113-4Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7767 | KL-20220113-5 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-13 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader driving from High Falls, scarifing hills and corners Trembley Road from Km 7 to Km 1 | 11 | F161 - F164 | Trembley Falls | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7767KL-20220113-5Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7767KL-20220113-5Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7771 | KL-20220114-4 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-14 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader finishing sanding and dragging blast mat from Hensen Road to F132 for stringing crews and start sanding Hensen Road with existing material from Km 10.5 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44580 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7771KL-20220114-4Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7771KL-20220114-4Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7775 | KL-20220115-4 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-01-15 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding hills on Hensen Road with existing material from Km 10.5 / Grader scarifying and benching snow banks on Hensen road from Km .5 to Km 17 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7775KL-20220115-4Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7775KL-20220115-4Supervisor3252OEWT-PA25-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7778 | KL-20220116-3 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-16 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader clearing pull offs and sanding in Hensen East / Grader working on snow removal on Hensen road from Km .5 to Km 17 and Hensen East to F132 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7778KL-20220116-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7778KL-20220116-3Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7781 | KL-20220117-3 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-17 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding in Hensen East / Grader working on snow removal on Hensen road from Km .5 to Km 17 and Hensen East to F132 | 11 | F118-F127 | Henson | 0 | 44581 |  | 46 | 44582 | [5 empty] | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7781KL-20220117-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7781KL-20220117-3Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7784 | KL-20220118-3 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-01-18 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding in Hensen East & driving out to 0.5Km for float. Grader working on benching & pushing back on Hensen road to 15Km. | 11 | F118-F127 | Henson | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7784KL-20220118-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7784KL-20220118-3Supervisor3252OEWT-PA25-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7786 | KL-20220119-2 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-01-19 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working on snow removal from F231 to F235 & clearing pads. | 11 | F212-F235 | Anjigame | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7786KL-20220119-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7786KL-20220119-2Supervisor3252OEWT-PA25-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7787 | KL-20220119-3 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-01-19 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening road, clearing pull offs & spur roads from Hensen to F131. grader working on snow removal on Hensen to 17Km and Hensen East to F131. | 11 | F118-F127 | Henson | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7787KL-20220119-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7787KL-20220119-3Supervisor3252OEWT-PA25-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7789 | KL-20220120-2 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-20 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader finishing snow removal from F231 to F235 & clearing pads. Start snow removal from F231 to F226. | 11 | F212-F235 | Anjigame | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7789KL-20220120-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7789KL-20220120-2Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7791 | KL-20220120-4 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-20 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on Hensen road to F121, hensen East to F131 & start benching snow banks from 17Km to 13Km. | 11 | F118-F127 | Henson | 0 | 44586 |  | 36 | 44588 | [5 empty] | Mike Lecocq | 11 | KABI LAKE FOREST PRODUCTS LTD7791KL-20220120-4Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7791KL-20220120-4Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7792 | KL-20220120-5 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-20 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer tracking from 11 Km on High Falls road & Working on Snow Removal to F207. | 11 | F170 - F211 | High Falls | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7792KL-20220120-5Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7792KL-20220120-5Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7794 | KL-20220121-2 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-21 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader finishing benching and pushing snow banks from Km .5 to Km 13 | 11 | F118 - F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7794KL-20220121-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7794KL-20220121-2Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7796 | KL-20220121-4 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-21 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader snow removal from F231 to F226 and F232 to F235 | 11 | F212-F235 | Anjigame | 0 | 44589 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7796KL-20220121-4Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7796KL-20220121-4Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7797 | KL-20220122-1 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-01-22 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on Hensen Road to Km 17 and Hensen East to F132(plowed Hensen Road 3 times due to winter storm) /Loader clearing pulloffs and widening corners to Km 12 | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7797KL-20220122-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7797KL-20220122-1Supervisor3252OEWT-PA25-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7798 | KL-20220122-2 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-22 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer tracking from km 11 on High Falls Road and working on snow removal from High Falls Road to F207/track back to Km 11 | 11 | F170-F211 | High Falls | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7798KL-20220122-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7798KL-20220122-2Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7800 | KL-20220123-2 | 53511111 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2022-01-23 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal on Hensen Road to F121 and Hensen East to F132/Loader clearing pulloffs and widening corners | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7800KL-20220123-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7800KL-20220123-2Supervisor4336OEWT-PA25-Lem | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7802 | KL-20220124-2 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-01-24 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working benching snowbanks and widening road from Hwy 17 to Km 10/ Loader continuing clearing pulloffs and widening corners | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7802KL-20220124-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7802KL-20220124-2Supervisor3252OEWT-PA25-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7804 | KL-20220124-4 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-24 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from Anjigami Road to F231 and clearing pads in support of stringing crew | 11 |  | Anjigame | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7804KL-20220124-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7804KL-20220124-4Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7807 | KL-20220125-3 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-25 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Finishing benching snowbanks, scarifying and widening road from Hwy 17 to Km 10 | 11 | F118-F127 | Henson | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7807KL-20220125-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7807KL-20220125-3Supervisor2168OEWT-PA25-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7808 | KL-20220125-4 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-25 | 0 | OEWT-PA25-Lem | 44594 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal and Heli Pads in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44588 |  | 61 | 44593 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7808KL-20220125-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7808KL-20220125-4Supervisor184OEWT-PA25-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7810 | KL-20220126-2 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-26 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying road from Hwy 17 to Km 10 | 11 | F118-F127 | Henson | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7810KL-20220126-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7810KL-20220126-2Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7811 | KL-20220126-3 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-26 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader continuing working snow removal and Heli Pads in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7811KL-20220126-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7811KL-20220126-3Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7812 | KL-20220128-1 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-28 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 and Hensen east to F131 | 11 | F118-F127 | Hensen | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7812KL-20220128-1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7812KL-20220128-1Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7813 | KL-20220128-2 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-28 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from F235 to F230 and Pads in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7813KL-20220128-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7813KL-20220128-2Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7815 | KL-20220129-2 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-01-29 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal and scarifying from Hwy 17 to Km 17 on Hensen road and Hensen east to F131 | 11 | F118-F127 | Henson | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7815KL-20220129-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7815KL-20220129-2Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7817 | KL-20220130-2 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-30 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal and scarifying from Hwy 17 to Km 17 on Hensen road | 11 | F118-F127 | Henson | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7817KL-20220130-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7817KL-20220130-2Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7820 | KL-20220131-3 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-01-31 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader started benching snowbanks and scarifying from Hwy 17 to Km 6 on Hensen road | 11 | F118-F127 | Henson | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7820KL-20220131-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7820KL-20220131-3Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7821 | KL-20220131-4 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-01-31 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from F235 to F230 and Pads in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44595 |  | 37 | 44597 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7821KL-20220131-4Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7821KL-20220131-4Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7824 | KL-20220201-3 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-01 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader benching snow banks, widening road, scarifying from 6km to 10km & clearing snow drifts @ 14Km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7824KL-20220201-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7824KL-20220201-3Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7825 | KL-20220201-4 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-01 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader working snow removal from F235 to F230 and Pads in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7825KL-20220201-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7825KL-20220201-4Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7827 | KL-20220202-2 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 |  | 168 | 21.84 | 189.84 | 2022-02-02 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader finishing benching snow banks, widening road, scarifying from 10km to 17km & clearing snow drifts @ 17Km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7827KL-20220202-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7827KL-20220202-2Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7829 | KL-20220203-2 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-03 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to 17km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7829KL-20220203-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7829KL-20220203-2Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7831 | KL-20220202-3 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-02 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7831KL-20220202-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7831KL-20220202-3Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7834 | KL-20220204-3 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-04 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader widening road and scarifying from Hwy 17 to 17km on Hensen Road and Hensen East to F-131. | 11 | F118-F127 | Henson | 0 | 44603 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7834KL-20220204-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7834KL-20220204-3Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7835 | KL-20220204-4 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-04 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader in support of stringing crew | 11 | F212-F235 | Anjigame | 0 | 44601 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7835KL-20220204-4Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7835KL-20220204-4Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7838 | KL-20220205-3 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-05 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader benching snowbanks and scarifying from Hwy 17 to 17km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44603 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7838KL-20220205-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7838KL-20220205-3Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7842 | KL-20220206-2 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-06 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17Km on Hensen Road (cleared road 2 times due to heavy snow. | 11 | F118-F127 | Henson | 0 | 44603 |  | 61 | 44603 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7842KL-20220206-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7842KL-20220206-2Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7845 | KL-20220207-2 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-07 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44604 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7845KL-20220207-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7845KL-20220207-2Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7853 | KL-20220208-2 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-08 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to 17Km on Hensen Road & snow removal to F131 on Hensen East. Loader clearing pull offs & widening corners to 7km. Supervisor doing pickup shuffle. | 11 | F118 - F127 | Henson | 0 | 44604 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7853KL-20220208-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7853KL-20220208-2Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7858 | KL-20220209-1 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-09 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer finishing snow removal from F021 to F032 and clear pads @ F032 | 10 | F009-F065 | Paint Lake | 0 | 44604 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7858KL-20220209-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7858KL-20220209-1Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7862 | KL-20220209-5 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-09 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to Km 17 on Hensen road /Loader clearing pull offs and widening corners and sanding to Km 12 /Supervisor doing pickup shuffle | 11 | F118-F127 | Henson | 0 | 44604 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7862KL-20220209-5Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7862KL-20220209-5Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7867 | KL-20220210-4 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-10 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to Km 17 on Hensen road and benching snowbanks from Km .5 to Km 5/Loader clearing pull offs and widening corners and sanding from Km 5 to Km 17 | 11 | F118-F127 | Henson | 0 | 44605 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7867KL-20220210-4Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7867KL-20220210-4Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7870 | KL-20220211-2 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-11 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen road /Loader clearing pull offs and sanding from Km 10 to Km 17 | 11 | F118-F127 | Henson | 0 | 44605 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7870KL-20220211-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7870KL-20220211-2Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7876 | KL-20220212-4 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-12 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen road and Hensen Road East to F123/Loader clearing pull offs and sanding from Km 10 to Km 4 | 11 | F118-F127 | Henson | 0 | 44605 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7876KL-20220212-4Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7876KL-20220212-4Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7880 | KL-20220213-4 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-13 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Km 1 to Km 6 on Trembley road and from Trembley Road to F161 | 11 | F161 - F164 | Trembley Falls | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7880KL-20220213-4Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7880KL-20220213-4Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7889 | KL-20220215-2 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-15 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal and scarifying from Hwy 17 to Km 17 on Hensen Road | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7889KL-20220215-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7889KL-20220215-2Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7894 | KL-20220216-2 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-16 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen Road / Loader clearing entrance @ Hwy 17 and Hensen Road | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7894KL-20220216-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7894KL-20220216-2Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7898 | KL-20220217-3 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-17 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen Road and to F131 in Hensen East / Loader clearing pull off on Hensen Road and F126 Access | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7898KL-20220217-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7898KL-20220217-3Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7901 | KL-20220218-2 | 53511111 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2022-02-18 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader finishing clearing pull off, widening corners and sanding from Km 5 to Km 17/ Supervisor doing pickup shuffle | 11 | F118-F127 | Henson | 0 | 44614 |  | 61 | 44614 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7901KL-20220218-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7901KL-20220218-2Supervisor3252OEWT-PA26-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7906 | KL-20220219-2 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-19 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17km on Hensen Road & start benching snow banks | 11 | F118-F127 | Henson | 0 | 44617 |  | 61 | 44617 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7906KL-20220219-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7906KL-20220219-2Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7910 | KL-20220220-2 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-20 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17Km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44617 |  | 61 | 44617 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7910KL-20220220-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7910KL-20220220-2Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7912 | KL-20220221-2 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-21 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal & benching snow banks from Hwy 17 to 17Km on Hensen Road. Loader starting clearing of pull offs on Hensen Road & widening corners | 11 | F118-F127 | Henson | 0 | 44617 |  | 61 | 44617 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7912KL-20220221-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7912KL-20220221-2Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7914 | KL-20220222-2 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-22 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to Km 17 on Hensen Road /Grader 2 benching snow banks from Km 17 to Hwy 17 | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7914KL-20220222-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7914KL-20220222-2Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7917 | KL-20220223-2 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-23 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal from Hwy 17 to 17km on Hensen Road. Loader widening corners & assisting float trucks | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7917KL-20220223-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7917KL-20220223-2Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7921 | KL-20220224-2 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-24 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on snow removal, benching snowbanks and widening road from Hwy 17 to 17km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7921KL-20220224-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7921KL-20220224-2Supervisor2168OEWT-PA26-LEM | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7926 | KL-20220225-2 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-25 | 0 | OEWT-PA26-LEM | 44627 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying sections from Hwy 17 to 17km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44623 |  | 37 | 44624 | [5 empty] | Harold Furlong | 11 | KABI LAKE FOREST PRODUCTS LTD7926KL-20220225-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7926KL-20220225-2Supervisor184OEWT-PA26-LEM | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7939 | KL-20220227-2 | 53511111 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader working on snow removal from Hwy 17 to 17Km on Hensen Road. | 11 | F118-F127 | Henson | 0 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7939KL-20220227-2Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7939KL-20220227-2Supervisor0.542 | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7941 | KL-20220227-4 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-27 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader Starting Snow Removal From F168 To F165. Access/Winter Access Maintenance (Cost Code: 67776007556.591100.57010107) | 11 | F165 - F169 | Magpie Hills | 0 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7941KL-20220227-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7941KL-20220227-4Supervisor184 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7945 | KL-20220228-2 | 53511111 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2022-02-28 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Grader Scarifying Sections From Hwy 17 To 17 Km On Hensen Road | 11 | F118-F127 | Henson | 0 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7945KL-20220228-2Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7945KL-20220228-2Supervisor0.542 | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7946 | KL-20220228-3 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-02-28 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loader Finishing Snow Removal From F165 To F169. Access/Winter Access Maintenance (Cost Code: 67776007556.591100.57010107) | 11 | F165 - F169 | Magpie Hills | 1 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7946KL-20220228-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7946KL-20220228-3Supervisor184 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7948 | KL-20220228-5 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-02-28 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loaders Working On Snow Removal From F184 To F181 & Starting @ F175 To F171. Access/Winter Access Maintenance (Cost Code: 67776007556.591100.57010107) | 11 | F170 - F211 | High Falls | 1 | 44628 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7948KL-20220228-5Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7948KL-20220228-5Supervisor2168 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7956 | KL-20220301-3 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-03-01 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loaders finishing on snow removal from F175 to F171 Cost Code: 67776007556.591100.57010107 ) | 11 | F170 - F211 | High Falls | 1 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7956KL-20220301-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7956KL-20220301-3Supervisor2168 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7959 | KL-20220302-4 | 53511111 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2022-03-02 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Float Cat 950M loader from High Falls Road to F170/ Traffic control required ( Cost Code: 67776007556.591100.57010107 ) | 11 | F170-F211 | High Falls | 1 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7959KL-20220302-4Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7959KL-20220302-4Supervisor0.542 | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7960 | KL-20220302-5 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-03-02 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loaders finishing on snow removal and turn around @ F170 / Traffic control required for clearing of Entrance ( Cost Code: 67776007556.591100.57010107 ) | 11 | F170 - F211 | High Falls | 1 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7960KL-20220302-5Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7960KL-20220302-5Supervisor184 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7962 | KL-20220302-7 | 53511111 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2022-03-02 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader working on snow removal from Anjigami to F228 | 11 | F212-F235 | Anjigame | 0 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7962KL-20220302-7Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7962KL-20220302-7Supervisor184 | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7972 | KL-20220307-2 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-03-07 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Pending |  |  | Loader Working On Snow Removal From Anjigami Road To F228 & F235 To F233 | 11 | F212-F235 | Anjigame | 0 | 44634 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7972KL-20220307-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7972KL-20220307-2Supervisor2168 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7974 | KL-20220307-4 | 53511111 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2022-03-07 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loader Working On Snow Removal From High Falls Road To F175, F174, F172 & F171 ( Cost Code: 67776007556.591100.57010107 ) | 11 | F170-F211 | High Falls | 1 | 44634 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7974KL-20220307-4Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7974KL-20220307-4Supervisor2168 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3014 | KL-20200919-10-R1 | 53511112 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-09-19 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Pick up 500mm cross drain in Marathon and deliver to Michipicoten Harbour Road-5 F159. Corduroy road @ F-160. | 11 | F-159 to F-160 | Michipicoten Harbour Road -5 | 0 | 44098 |  | 52 | 44098 | [5 empty] | Emma Derenowski | 11 | KABI LAKE FOREST PRODUCTS LTD3014KL-20200919-10-R1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD3014KL-20200919-10-R1Supervisor2168OEWT-PA9-Lem-R1 | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3415 | KL-20200930-23 | 53511112 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2020-09-30 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pitrun from Provost pit #5 to F204 access | 11 | F-203 to F-211 | High Falls Road | 0 | 44119 |  | 48 | 44120 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3415KL-20200930-23Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD3415KL-20200930-23Supervisor3252OEWT-PA10-LEM | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7013 | KL-20210612-1 | 53511112 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-06-12 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator starting road maintenance from 11Km on Hensen to 0.5Km on Hensen East as per Valard. Supervisor doing pickup shuffle. | 11 | F119-F134 | Hensen Road | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7013KL-20210612-1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7013KL-20210612-1Supervisor2168OEWT-PA18-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7015 | KL-20210612-3 | 53511112 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-06-16 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators shaping road, working on drainage from F191 to F192.5 for pickup access & grinder. | 11 | F185-F193 | High Falls Road - 5 | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7015KL-20210612-3Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7015KL-20210612-3Supervisor0.542OEWT-PA18-Lem | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7016 | KL-20210613-1 | 53511112 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-06-13 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator working on shaping & drainage to 1Km on Hensen East. | 11 | F119-F134 | Hensen Road | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7016KL-20210613-1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7016KL-20210613-1Supervisor184OEWT-PA18-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7018 | KL-20210614-1 | 53511112 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-06-14 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator working on shaping & drainage to F122 on Hensen East. | 11 | F119-F134 | Hensen Road | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7018KL-20210614-1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7018KL-20210614-1Supervisor184OEWT-PA18-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7019 | KL-20210614-2 | 53511112 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-06-14 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road, working on drainage out from F193 to F189. | 11 | F185-F193 | High Falls Road - 5 | 0 | 44363 |  | 50 | 44363 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7019KL-20210614-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7019KL-20210614-2Supervisor2168OEWT-PA18-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7023 | KL-20210607-1 | 53511112 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-06-07 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators shaping road, working on drainage & fixing hills from F188 to F190 for pickup access. | 11 | F185-F193 | High Falls Road | 0 | 44365 |  | 50 | 44366 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7023KL-20210607-1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7023KL-20210607-1Supervisor184OEWT-PA18-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7024 | KL-20210608-1 | 53511112 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-06-08 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators continuing shaping road, working on drainage & fixing hills from F188 to F190 for pickup access and grinder | 11 | F-185 to F-193 | High Falls Road - 5 | 0 | 44365 |  | 50 | 44366 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7024KL-20210608-1Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7024KL-20210608-1Supervisor0.542OEWT-PA18-Lem | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7026 | KL-20210615-1 | 53511112 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-06-15 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator working on shaping & drainage to F127/stockpiling existing material for covering of corduroy sections | 11 | F119-F134 | Hensen Road | 0 | 44365 |  | 50 | 44366 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7026KL-20210615-1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7026KL-20210615-1Supervisor184OEWT-PA18-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7028 | KL-20210615-3 | 53511112 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-06-15 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing shaping road & levelling ruts from F189 to F185. | 11 | F185-F193 | High Falls Road - 5 | 0 | 44365 |  | 50 | 44366 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7028KL-20210615-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7028KL-20210615-3Supervisor184OEWT-PA18-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7034 | KL-20210616-1 | 53511112 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-06-16 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F excavator working on shaping & drainage to F-127 / Stockpiling existing material fro covering of corduroy sections. | 11 | F119-F134 | Hensen Road | 0 | 44368 |  | 50 | 44369 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7034KL-20210616-1Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7034KL-20210616-1Supervisor0.542OEWT-PA18-Lem | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7044 | KL-20210620-1 | 53511112 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-06-20 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator repairing washout on hill at WC 12570.00 and access to F171 for pickup access. | 11 | F171-F176 | High Falls Road 1 | 0 | 44369 |  | 50 | 44369 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7044KL-20210620-1Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7044KL-20210620-1Supervisor0.542OEWT-PA18-Lem | [5 empty] | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7058 | KL-20210621-1 | 53511112 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-06-21 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Levelling ruts and shaping access from F-171 to F-177 | 11 | F171-F176 | High Falls Road - 1 | 0 | 44370 |  | 50 | 44371 | [5 empty] | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7058KL-20210621-1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7058KL-20210621-1Supervisor184OEWT-PA18-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7194 | KL-20210803-1 | 53511112 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-08-03 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer & Operator moving rock truck from F-037 to F-119 & tracking Cat 330 excavator from 17Km on Hensen to 46Km on paint lake road 2 for gravel haul | 11 | F118-F127 | Hensen Road | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD7194KL-20210803-1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7194KL-20210803-1Supervisor184OEWT-PA20-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7484 | KL-20211023-2 | 53511112 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-10-23 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul trees for fill and start capping with existing material @ F123 to F124 access realignment | 11 | F119-F134 | Hensen Road | 0 | 44495 |  | 61 | 44496 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7484KL-20211023-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7484KL-20211023-2Supervisor3252OEWT-PA22-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7486 | KL-20211024-2 | 53511112 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-10-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from F123 access to F124 access realignment capping and start raising road and 1.5 km for crane access | 11 | F119-F134 | Hensen Road | 0 | 44495 |  | 61 | 44497 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7486KL-20211024-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7486KL-20211024-2Supervisor4336OEWT-PA23-Lem | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7489 | KL-20211025-2 | 53511112 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-10-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to 1.5 km for raising of road | 11 | F119-F134 | Hensen Road | 0 | 44496 |  | 61 | 44497 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7489KL-20211025-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7489KL-20211025-2Supervisor4336OEWT-PA23-Lem | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7493 | KL-20211026-2 | 53511112 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-10-26 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul existing material from Km 17 on Hensen Road to F124 for capping | 11 | F118-F127 | Hensen | 0 | 44501 |  | 61 | 44502 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7493KL-20211026-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7493KL-20211026-2Supervisor4336OEWT-PA23-Lem | [5 empty] | 1 | 336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7497 | KL-20211027-2 | 53511112 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul existing material from Km 17 on Hensen Road to F124 for capping/excavator speading existing material and shaping road from Hensen Road to F123 | 11 | F118-F127 | Hensen | 0 | 44501 |  | 61 | 44502 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7497KL-20211027-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7497KL-20211027-2Supervisor3252OEWT-PA23-Lem | [5 empty] | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7503 | KL-20211028-2 | 53511112 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-10-28 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking from F123 to F127 working on drainage and shaping road to F126 | 11 | F118-F127 | Hensen Road | 0 | 44501 |  | 61 | 44502 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7503KL-20211028-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7503KL-20211028-2Supervisor2168OEWT-PA23-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7511 | KL-20211030-2 | 53511112 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-10-30 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing working on drainage, shaping road and sloping excavation @ Km .5 on Hensen Road East | 11 | F119-F127 | Hensen Road | 0 | 44502 |  | 61 | 44503 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7511KL-20211030-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7511KL-20211030-2Supervisor2168OEWT-PA23-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7589 | KL-20211123-4 | 53511112 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-11-23 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader starting to scrape and sand road to Km 14 for stringing crews | 11 | F212-F235 | Ainjigame | 0 | 44529 |  | 61 | 44530 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7589KL-20211123-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7589KL-20211123-4Supervisor184OEWT-PA23-Lem | [5 empty] | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7601 | KL-20211029-2 | 53511112 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-10-29 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continue working on drainage, tracking material and shaping road @ F126 / F125 | 11 | F118 - F134 | Henson | 0 | 44501 |  | 61 | 44503 | [6 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7601KL-20211029-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7601KL-20211029-2Supervisor2168OEWT-PA23-Lem | [5 empty] | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6607 | KL-20210401-6 | 53541101 | Reclamation | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-04-01 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclaimation @ F133/ F132/ ATV used due to no pickup access | 11 | F119-F134 | Hensen Road | 0 | 44298 |  | 57 | 44305 | [5 empty] | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6607KL-20210401-6Supervisor184 | KABI LAKE FOREST PRODUCTS LTD6607KL-20210401-6Supervisor184OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6611 | KL-20210402-3 | 53541101 | Reclamation | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-04-02 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start Reclamation @ F135 to F136 | 11 | F135-F149 | Dore Lake Road | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6611KL-20210402-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD6611KL-20210402-3Supervisor184OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6614 | KL-20210403-3 | 53541101 | Reclamation | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-04-03 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F136 to F137/ side by side used due to no pickup access | 11 | F-135 to F-149 | Dore Lake Road | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6614KL-20210403-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD6614KL-20210403-3Supervisor184OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6615 | KL-20210403-4 | 53541101 | Reclamation | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-04-03 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F133 to F132/ ATV used due to no pickup access | 11 | F-119 to F-134 | Hensen Road | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6615KL-20210403-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD6615KL-20210403-4Supervisor184OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6619 | KL-20210404-4 | 53541101 | Reclamation | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-04-04 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish reclamation from F133/ F131 and track out to Km 17 on Hensen Road/ ATV used due to no pickup access | 11 | F119-F134 | Hensen Road | 0 | 44298 |  | 15 | 44303 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD6619KL-20210404-4Supervisor184 | KABI LAKE FOREST PRODUCTS LTD6619KL-20210404-4Supervisor184OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6620 | KL-20210404-5 | 53541101 | Reclamation | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-04-04 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 336 Excavator to Km 3 on Dore Lake road for Reclamation of Dore Lake Road West | 11 | F-135 to F-149 | Dore Lake Road | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6620KL-20210404-5Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD6620KL-20210404-5Supervisor0.542OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6624 | KL-20210405-4-R1 | 53541101 | Reclamation | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-04-05 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F137 to F138/ Cat 336 excavator tracking in from km 3 on Dore Road and starting @ F140. Chapman Reclamation of Dore lake Road East - CE-195. Excavator/pickup hours reduced for tracking time from signed ticket per Valard direction. Tracking time will be submitted on LEM KL-20210405-4-S1 | 11 | F-135 to F-149 | Dore lake Road | 0 | 44298 |  | 56 | 44329 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6624KL-20210405-4-R1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD6624KL-20210405-4-R1Supervisor184OEWT-PA17-LEM |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6661 | KL-20210406-5-R1 | 53541101 | Reclamation | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-04-06 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F138 to F141. Two hours of equipment/live out and pick up time removed from each excavator/operator from approved field ticket as per Valard direction. Those charges now listed on LEM KL-20210406-5-S1. | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | 44328 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6661KL-20210406-5-R1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD6661KL-20210406-5-R1Supervisor3252OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6662 | KL-20210406-6 | 53541101 | Reclamation | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-04-06 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F150 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44292 |  | 56 | 44305 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6662KL-20210406-6Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD6662KL-20210406-6Supervisor0.542OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6677 | KL-20210408-2 | 53541101 | Reclamation | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-04-08 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 1 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  | 29 | Approved | STR & PAD SITE RECLAIM | 8008 | Continue Reclamation @ F151/ sloping crane pads and assembly pad | 11 | F150-F151 | Michipicoten Harbour Road -1 | 1 | 44305 |  | 56 | 44307 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6677KL-20210408-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD6677KL-20210408-2Supervisor184OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6687 | KL-20210409-7 | 53541101 | Reclamation | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-04-09 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 1 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  | 29 | Approved | STR & PAD SITE RECLAIM | 8008 | Continue Reclamation @F151/ Sloping crane pad and assembley pad | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44306 |  | 56 | 44309 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6687KL-20210409-7Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD6687KL-20210409-7Supervisor0.542OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6704 | KL-20210412-6 | 53541101 | Reclamation | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-04-12 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @F151 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44308 |  | 56 | 44309 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6704KL-20210412-6Supervisor184 | KABI LAKE FOREST PRODUCTS LTD6704KL-20210412-6Supervisor184OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6757 | KL-20210414-6 | 53541101 | Reclamation | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-04-14 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue reclamation @ F151 and F150. | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44309 |  | 56 | 44312 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6757KL-20210414-6Supervisor184 | KABI LAKE FOREST PRODUCTS LTD6757KL-20210414-6Supervisor184OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6610 | KL-20210402-2-R1 | 53541101 | Reclamation | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-04-02 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track out to Km 1 on Hensen East for refueling and back to F132/ Continue reclamation @ F132/ ATV used due to no pickup access. Excavator time reduced from signed ticket for tracking as per Valard direction. Remaining excavator time will be submitted on KL-20210402-2-S1 | 11 | F119-F134 | Hensen Road | 0 | 44298 |  | 56 | 44329 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6610KL-20210402-2-R1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD6610KL-20210402-2-R1Supervisor184OEWT-PA17-LEM |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6781 | KL-20210415-2 | 53541101 | Reclamation | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-04-15 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F151 and F150 (Revised ). Removing wood, re-contouring road area. | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44317 |  | 56 | 44319 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6781KL-20210415-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD6781KL-20210415-2Supervisor184OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6786 | KL-20210407-8 | 53541101 | Reclamation | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-04-07 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F139 to F143 (third revision.) Quad was used for operator travel to excavator, no tracking of excavator. | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44320 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6786KL-20210407-8Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD6786KL-20210407-8Supervisor0.542OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6787 | KL-20210407-9 | 53541101 | Reclamation | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-04-07 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation of structure pads @ F141 to F143 (fourth revision.) | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44320 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6787KL-20210407-9Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD6787KL-20210407-9Supervisor0.542OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6788 | KL-20210408-6 | 53541101 | Reclamation | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-04-08 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator working on Reclamation @F139 to F140. Quad used for operator travel, no tracking of excavator. | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6788KL-20210408-6Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD6788KL-20210408-6Supervisor0.542OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6789 | KL-20210408-7 | 53541101 | Reclamation | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-04-08 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator working on Reclamationof structure pads and access @ F145/F144 (fourth revision) | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44320 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6789KL-20210408-7Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD6789KL-20210408-7Supervisor0.542OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6790 | KL-20210409-8 | 53541101 | Reclamation | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-04-09 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator working on reclamation @f139 to F140. (Third Revision). Quad used for operator travel, no tracking time for equipment. | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44320 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6790KL-20210409-8Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD6790KL-20210409-8Supervisor0.542OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6791 | KL-20210409-9 | 53541101 | Reclamation | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-04-09 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 Excavator working on reclamation @f139 to F140. (Third Revision). Quad used for operator travel, no tracking time for equipment. | 11 | F135-F149 | Dore Lake Road | 0 | 44317 |  | 56 | 44320 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6791KL-20210409-9Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD6791KL-20210409-9Supervisor0.542OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6793 | KL-20210412-8 | 53541101 | Reclamation | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-04-12 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 excavator working on Reclamation @ F141/F142 (fourth revision) | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6793KL-20210412-8Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD6793KL-20210412-8Supervisor0.542OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6795 | KL-20210413-6 | 53541101 | Reclamation | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-04-13 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 and Cat 330 Excavators workimg on Reclamation @F141 and F143 (4th Revision) | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6795KL-20210413-6Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD6795KL-20210413-6Supervisor3252OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6797 | KL-20210414-9 | 53541101 | Reclamation | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-04-14 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 and Cat 336 excavators working on Reclamation @ F142 and F143 (3rd revision) | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6797KL-20210414-9Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD6797KL-20210414-9Supervisor3252OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6800 | KL-20210416-3 | 53541101 | Reclamation | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-04-16 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @F150 and F151 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6800KL-20210416-3Supervisor184 | KABI LAKE FOREST PRODUCTS LTD6800KL-20210416-3Supervisor184OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6802 | KL-20210417-2 | 53541101 | Reclamation | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-04-17 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator working on Reclamation @F143 and F144 | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6802KL-20210417-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD6802KL-20210417-2Supervisor184OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6808 | KL-20210418-1 | 53541101 | Reclamation | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-04-18 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator working on reclamation @F144 and F145 ( Second revision). Chapman access reclamation at 7.5Km. | 11 | F135-F149 | Dore Lake Road | 0 | 44322 |  | 56 | 44323 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6808KL-20210418-1Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD6808KL-20210418-1Supervisor2168OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 168 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6840 | KL-20210331-5 | 53541101 | Reclamation | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-03-31 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track to F133 from Km 17 on Hensen and start reclaimation @ F133/F132. ATV used for crew due to no pickup access | 11 | F119-F134 | Hensen Road | 0 | 44326 |  | 57 | 44327 | [5 empty] | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6840KL-20210331-5Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD6840KL-20210331-5Supervisor3252OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 252 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6628 | KL-20210405-8 | 53541105 | Reclamation | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-04-05 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Erosion Cont Inst/Mon/Rem |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start Reclamation @ F150 | 11 | F-150 to F-151 | Michipicoten Harbour Road -1 | 0 | 44298 |  | 56 | 44303 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6628KL-20210405-8Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD6628KL-20210405-8Supervisor0.542OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4849 | KL-20201212-14 | 53551103 | Earthworks | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-12 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic Breaker & support excavator starting on F123 Access breaking outcrops on steep grades /straighten corners/ operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 48 | 44203 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4849KL-20201212-14Supervisor184 | KABI LAKE FOREST PRODUCTS LTD4849KL-20201212-14Supervisor184OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4988 | KL-20201213-13 | 53551103 | Earthworks | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-12-13 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic breaker and support Excavator working on F123 access breaking outcrops on steep grade and straighten corners/ oper. travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 55 | 44209 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4988KL-20201213-13Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD4988KL-20201213-13Supervisor2168OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5010 | KL-20201214-13 | 53551103 | Earthworks | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator hydaulic breaker and support excavator working onF123 access breaking outcrops on steep grades and straighten corners / operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44196 |  | 55 | 44209 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5010KL-20201214-13Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD5010KL-20201214-13Supervisor2168OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5038 | KL-20201216-10 | 53551103 | Earthworks | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-12-16 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic Breaker and Support Excavator working on F127 access breaking outcrops on steep grades and straighten corners/ operator travel as per valard | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5038KL-20201216-10Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD5038KL-20201216-10Supervisor2168OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5062 | KL-20201219-9 | 53551103 | Earthworks | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-19 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc with hydraulic breaker & support exc working on F127 Access breaking outcrops on steep grades. Straighten corners. Operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5062KL-20201219-9Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5062KL-20201219-9Supervisor184OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5110 | KL-20201217-18 | 53551103 | Earthworks | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic breaker and support excavator working on F127 access Breaking outcrops on steep grades and straighten corners/ operators as per valard | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5110KL-20201217-18Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD5110KL-20201217-18Supervisor2168OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5122 | KL-20201220-9 | 53551103 | Earthworks | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2020-12-20 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker & support exc working on F127 Access breaking outcrops on steep grades & straighten corners/operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5122KL-20201220-9Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5122KL-20201220-9Supervisor184OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5217 | KL-20210104-6 | 53551103 | Earthworks | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-01-04 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker and support excavator working on F117 access breaking outcrops on steep grades and laying trees/ Operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5217KL-20210104-6Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD5217KL-20210104-6Supervisor2168OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5230 | KL-20210105-9 | 53551103 | Earthworks | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-01-05 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker and support excavator working on F117 access breaking outcrops an steep grades/ Operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5230KL-20210105-9Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD5230KL-20210105-9Supervisor2168OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5243 | KL-20210106-7 | 53551103 | Earthworks | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-01-06 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker working on F117 access breaking outcrops on steep grades/ operator travel as per valard | 11 | F119-F134 | Hensen Road | 0 | 44209 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5243KL-20210106-7Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD5243KL-20210106-7Supervisor2168OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5267 | KL-20210107-16 | 53551103 | Earthworks | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-01-07 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker working on F117 Access breaking outcrops on steep grades/operator travel as per Valard. Skagen excavator supporting breaker. | 11 | F119-F134 | Hensen Road | 0 | 44209 |  | 15 | 44219 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5267KL-20210107-16Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD5267KL-20210107-16Supervisor2168OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 84 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5628 | KL-20210126-12 | 53551103 | Earthworks | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-01-26 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | EXC with breaker & support excavator working on F111 Access breaking outcrops & laying trees. Operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44228 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5628KL-20210126-12Supervisor184 | KABI LAKE FOREST PRODUCTS LTD5628KL-20210126-12Supervisor184OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 42 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5648 | KL-20210127-16 | 53551103 | Earthworks | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-01-27 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc with hydraulic breaker & support excavator working on F111 Access breaking outcrops & laying trees/operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44228 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5648KL-20210127-16Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD5648KL-20210127-16Supervisor0.542OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 21 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5656 | KL-20210128-8 | 53551103 | Earthworks | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-01-28 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc w breaker & support exc working on F111 Access breaking outcrops & laying trees/ operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5656KL-20210128-8Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD5656KL-20210128-8Supervisor0.542OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 21 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7932 | KL-20220305-1-RCL | 53541001 | Reclamation | 0 | Foreman | 82 | 4 | HR |  |  | 82 | 0 | 328 | 42.64 | 370.64 | 2022-03-05 |  | OEWT-PA27-RCL | 2022-03-31 |  | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 330 excavator clearing snow from ditches, and spreading ripped material. 336 excavator ripping frozen roadway F033-F034 | 10 | F066-F118 | Paint Lake 2 | 0 | 44625 |  | 37 | 44625 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7932KL-20220305-1-RCLForeman4328 | KABI LAKE FOREST PRODUCTS LTD7932KL-20220305-1-RCLForeman4328 | WF10-Access | WF10-Access | WF10-Access | 1 | 1 | 1 | 328 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 888 | KL-20200114-2 | 53510711 | Access | 0 | Operator | 80 | 0 | HR |  |  | 80 | 0 | 0 | 0 | 0 | 2020-01-17 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Winter Access Maintenance, dozer opening roads | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD888KL-20200114-2Operator00 | KABI LAKE FOREST PRODUCTS LTD888KL-20200114-2Operator00OEWT-PA1-LEM | [5 empty] | 1 | 0 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7932 | KL-20220305-1-RCL | 53541001 | Reclamation | 0 | Operator | 80 | 2 | HR |  |  | 80 | 0 | 160 | 20.8 | 180.8 | 2022-03-05 |  | OEWT-PA27-RCL | 2022-03-31 |  | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 330 excavator clearing snow from ditches, and spreading ripped material. 336 excavator ripping frozen roadway F033-F034 | 10 | F066-F118 | Paint Lake 2 | 0 | 44625 |  | 37 | 44625 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7932KL-20220305-1-RCLOperator2160 | KABI LAKE FOREST PRODUCTS LTD7932KL-20220305-1-RCLOperator2160 | WF10-Access | WF10-Access | WF10-Access | 1 | 1 | 1 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7932 | KL-20220305-1-RCL | 53541001 | Reclamation | 0 | Operator | 80 | 2 | HR |  |  | 80 | 0 | 160 | 20.8 | 180.8 | 2022-03-05 |  | OEWT-PA27-RCL | 2022-03-31 |  | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 330 excavator clearing snow from ditches, and spreading ripped material. 336 excavator ripping frozen roadway F033-F034 | 10 | F066-F118 | Paint Lake 2 | 0 | 44625 |  | 37 | 44625 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7932KL-20220305-1-RCLOperator2160 | KABI LAKE FOREST PRODUCTS LTD7932KL-20220305-1-RCLOperator2160 | WF10-Access | WF10-Access | WF10-Access | 1 | 1 | 1 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5248 | KL-20210106-12 | 53511102 | Access | 0 | Operator | 80 | 2 | HR |  |  | 80 | 0 | 160 | 20.8 | 180.8 | 2021-01-06 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track Excavator from F117 to F127 due to no float Access/ Operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44209 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5248KL-20210106-12Operator2160 | KABI LAKE FOREST PRODUCTS LTD5248KL-20210106-12Operator2160OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5309 | KL-20210111-9 | 53511102 | Access | 0 | Operator | 80 | 4 | HR |  |  | 80 | 0 | 320 | 41.6 | 361.6 | 2021-01-11 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Operator travel for F127 to F134 MFN Road Building. | 11 | F119-F134 | Hensen Road | 0 | 44211 |  | 15 | 44219 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5309KL-20210111-9Operator4320 | KABI LAKE FOREST PRODUCTS LTD5309KL-20210111-9Operator4320OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 320 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5322 | KL-20210112-9 | 53511102 | Access | 0 | Operator | 80 | 2 | HR |  |  | 80 | 0 | 160 | 20.8 | 180.8 | 2021-01-12 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi operator travel to F145 MFN Road building/based out of White River (Revised) | 11 | F135-F149 | Dore Lake Road | 0 | 44214 |  | 56 | 44219 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5322KL-20210112-9Operator2160 | KABI LAKE FOREST PRODUCTS LTD5322KL-20210112-9Operator2160OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5333 | KL-20210112-20 | 53511102 | Access | 0 | Operator | 80 | 6 | HR |  |  | 80 | 0 | 480 | 62.4 | 542.4 | 2021-01-12 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Operator travel for F127 to F134 MFN Road Building. | 11 | F119-F134 | Hensen Road | 0 | 44214 |  | 15 | 44219 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5333KL-20210112-20Operator6480 | KABI LAKE FOREST PRODUCTS LTD5333KL-20210112-20Operator6480OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 480 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5340 | KL-20210113-6 | 53511102 | Access | 0 | Operator | 80 | 1 | HR |  |  | 80 | 0 | 80 | 10.4 | 90.4 | 2021-01-13 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Operator travel to F134, F145 MFN Clearing. Track in Dumonski buncher. | 11 | F119-F134 | Hensen Road | 0 | 44214 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5340KL-20210113-6Operator180 | KABI LAKE FOREST PRODUCTS LTD5340KL-20210113-6Operator180OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 80 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5344 | KL-20210113-10 | 53511102 | Access | 0 | Operator | 80 | 6 | HR |  |  | 80 | 0 | 480 | 62.4 | 542.4 | 2021-01-13 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Operator travel from F127 to F134 MFN Road Building | 11 | F119-F134 | Hensen Raod | 0 | 44214 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5344KL-20210113-10Operator6480 | KABI LAKE FOREST PRODUCTS LTD5344KL-20210113-10Operator6480OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 480 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5345 | KL-20210113-11 | 53511102 | Access | 0 | Operator | 80 | 2 | HR |  |  | 80 | 0 | 160 | 20.8 | 180.8 | 2021-01-13 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi excavator operator extra travel to F145 MFN Road Building/Based out of White River | 11 | F135-F149 | Dore Lake Road | 0 | 44214 |  | 56 | 44219 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5345KL-20210113-11Operator2160 | KABI LAKE FOREST PRODUCTS LTD5345KL-20210113-11Operator2160OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5365 | KL-20210114-11 | 53511102 | Access | 0 | Operator | 80 | 6 | HR |  |  | 80 | 0 | 480 | 62.4 | 542.4 | 2021-01-14 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Operator travel for F127 to F134 MFN Road building. Dumonski cutting for corduroy @ F-133. | 11 | F119-F134 | Hensen Road | 0 | 44218 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5365KL-20210114-11Operator6480 | KABI LAKE FOREST PRODUCTS LTD5365KL-20210114-11Operator6480OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 480 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5367 | KL-20210114-13 | 53511102 | Access | 0 | Operator | 80 | 2 | HR |  |  | 80 | 0 | 160 | 20.8 | 180.8 | 2021-01-14 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator Operators extra travel to F145 MFN road building/ Based out of White River | 11 | F-135 to F-149 | Dore Lake Road | 0 | 44218 |  | 56 | 44220 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5367KL-20210114-13Operator2160 | KABI LAKE FOREST PRODUCTS LTD5367KL-20210114-13Operator2160OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5381 | KL-20210115-12 | 53511102 | Access | 0 | Operator | 80 | 2 | HR |  |  | 80 | 0 | 160 | 20.8 | 180.8 | 2021-01-15 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator operators extra travel to F145 MFN road building/ Based out of White River | 11 | F135-F149 | Dore Lake Road | 0 | 44218 |  | 56 | 44220 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5381KL-20210115-12Operator2160 | KABI LAKE FOREST PRODUCTS LTD5381KL-20210115-12Operator2160OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5383 | KL-20210115-14 | 53511102 | Access | 0 | Operator | 80 | 6 | HR |  |  | 80 | 0 | 480 | 62.4 | 542.4 | 2021-01-15 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Operator Travel for F127 to F134 MFN road Building. Dumonski to travel and track in for clearing. | 11 | F119-F134 | Hensen Road | 0 | 44218 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5383KL-20210115-14Operator6480 | KABI LAKE FOREST PRODUCTS LTD5383KL-20210115-14Operator6480OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 480 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5401 | KL-20210116-8 | 53511102 | Access | 0 | Operator | 80 | 4 | HR |  |  | 80 | 0 | 320 | 41.6 | 361.6 | 2021-01-16 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Operator travel for F127 to F134 MFN road Building | 11 | F119-F134 | Hensen Road | 0 | 44216 |  | 15 | 44233 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5401KL-20210116-8Operator4320 | KABI LAKE FOREST PRODUCTS LTD5401KL-20210116-8Operator4320OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 320 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5422 | KL-20210117-10 | 53511102 | Access | 0 | Operator | 80 | 6 | HR |  |  | 80 | 0 | 480 | 62.4 | 542.4 | 2021-01-17 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Operator travel for F127 to F134 MFN road building | 11 | F119-F134 | Hensen Road | 0 | 44216 |  | 15 | 44238 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5422KL-20210117-10Operator6480 | KABI LAKE FOREST PRODUCTS LTD5422KL-20210117-10Operator6480OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 480 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5425 | KL-20210117-13 | 53511102 | Access | 0 | Operator | 80 | 2 | HR |  |  | 80 | 0 | 160 | 20.8 | 180.8 | 2021-01-17 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator Operator extra travel to F145 MFN clearing/based out of White River | 11 | F135-F149 | Dore Lake Road | 0 | 44216 |  | 56 | 44229 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5425KL-20210117-13Operator2160 | KABI LAKE FOREST PRODUCTS LTD5425KL-20210117-13Operator2160OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5438 | KL-20210118-12 | 53511102 | Access | 0 | Operator | 80 | 6 | HR |  |  | 80 | 0 | 480 | 62.4 | 542.4 | 2021-01-18 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Operator travel for F127 to F134 MFN Road Building | 11 | F119-F134 | Hensen Road | 0 | 44216 |  | 15 | 44238 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5438KL-20210118-12Operator6480 | KABI LAKE FOREST PRODUCTS LTD5438KL-20210118-12Operator6480OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 480 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5446 | KL-20210118-20 | 53511102 | Access | 0 | Operator | 80 | 2 | HR |  |  | 80 | 0 | 160 | 20.8 | 180.8 | 2021-01-18 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator Operators extra travel to F145 MFN Clearing/Based out of White River. | 11 | F135-F149 | Dore Lake Road | 0 | 44216 |  | 56 | 44229 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5446KL-20210118-20Operator2160 | KABI LAKE FOREST PRODUCTS LTD5446KL-20210118-20Operator2160OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5464 | KL-20210119-15 | 53511102 | Access | 0 | Operator | 80 | 2 | HR |  |  | 80 | 0 | 160 | 20.8 | 180.8 | 2021-01-19 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator Operators extra travel to F145 MFN Road Building/Based out of White River | 11 | F135-F149 | Dore Lake Road | 0 | 44222 |  | 56 | 44229 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5464KL-20210119-15Operator2160 | KABI LAKE FOREST PRODUCTS LTD5464KL-20210119-15Operator2160OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5476 | KL-20210119-27 | 53511102 | Access | 0 | Operator | 80 | 4 | HR |  |  | 80 | 0 | 320 | 41.6 | 361.6 | 2021-01-19 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Operator travel for F127 to F134 MFN Road Building. | 11 | F119-F134 | Hensen Road | 0 | 44222 |  | 15 | 44238 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5476KL-20210119-27Operator4320 | KABI LAKE FOREST PRODUCTS LTD5476KL-20210119-27Operator4320OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 320 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5488 | KL-20210120-10 | 53511102 | Access | 0 | Operator | 80 | 2 | HR |  |  | 80 | 0 | 160 | 20.8 | 180.8 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavators extra travel to F145 MFN Road Building/Based out of White River | 11 | F135-F149 | Dore Lake Road | 0 | 44224 |  | 56 | 44229 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5488KL-20210120-10Operator2160 | KABI LAKE FOREST PRODUCTS LTD5488KL-20210120-10Operator2160OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5516 | KL-20210121-15 | 53511102 | Access | 0 | Operator | 80 | 1 | HR |  |  | 80 | 0 | 80 | 10.4 | 90.4 | 2021-01-21 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator Operator Extra Travel to F145 MFN Road Building/Based out of White River. | 11 | F135-F149 | Dore Lake Road | 0 | 44224 |  | 56 | 44229 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5516KL-20210121-15Operator180 | KABI LAKE FOREST PRODUCTS LTD5516KL-20210121-15Operator180OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 80 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5533 | KL-20210122-11 | 53511102 | Access | 0 | Operator | 80 | 2 | HR |  |  | 80 | 0 | 160 | 20.8 | 180.8 | 2021-01-22 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Exc Operators extra travel to F145 MFN Road Building/Based out of White River | 11 | F135-F149 | Dore Lake Road | 0 | 44224 |  | 56 | 44230 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5533KL-20210122-11Operator2160 | KABI LAKE FOREST PRODUCTS LTD5533KL-20210122-11Operator2160OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5510 | KL-20210121-9 | 53511111 | Access | 0 | Operator | 80 | 2 | HR |  |  | 80 | 0 | 160 | 20.8 | 180.8 | 2021-01-21 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer doing snow removal from km 17 on Hensen Rd to F133/Operator extra travel/Based out of White River. | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5510KL-20210121-9Operator2160 | KABI LAKE FOREST PRODUCTS LTD5510KL-20210121-9Operator2160OEWT-PA13-LEM | [5 empty] | 1 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5632 | KL-20210126-16 | 53511111 | Access | 0 | Operator | 80 | 1 | HR |  |  | 80 | 0 | 80 | 10.4 | 90.4 | 2021-01-26 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | D6K Dozer finishing snow removal from km 17 on Hensen to F133. | 11 | F119-F134 | Hensen Road | 0 | 44222 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5632KL-20210126-16Operator180 | KABI LAKE FOREST PRODUCTS LTD5632KL-20210126-16Operator180OEWT-PA14-Lem-R1 | [5 empty] | 1 | 80 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4849 | KL-20201212-14 | 53551103 | Earthworks | 0 | Operator | 80 | 3 | HR |  |  | 80 | 0 | 240 | 31.2 | 271.2 | 2020-12-12 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic Breaker & support excavator starting on F123 Access breaking outcrops on steep grades /straighten corners/ operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 48 | 44203 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4849KL-20201212-14Operator3240 | KABI LAKE FOREST PRODUCTS LTD4849KL-20201212-14Operator3240OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 120 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4988 | KL-20201213-13 | 53551103 | Earthworks | 0 | Operator | 80 | 4 | HR |  |  | 80 | 0 | 320 | 41.6 | 361.6 | 2020-12-13 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic breaker and support Excavator working on F123 access breaking outcrops on steep grade and straighten corners/ oper. travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 55 | 44209 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4988KL-20201213-13Operator4320 | KABI LAKE FOREST PRODUCTS LTD4988KL-20201213-13Operator4320OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5010 | KL-20201214-13 | 53551103 | Earthworks | 0 | Operator | 80 | 4 | HR |  |  | 80 | 0 | 320 | 41.6 | 361.6 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator hydaulic breaker and support excavator working onF123 access breaking outcrops on steep grades and straighten corners / operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44196 |  | 55 | 44209 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5010KL-20201214-13Operator4320 | KABI LAKE FOREST PRODUCTS LTD5010KL-20201214-13Operator4320OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5038 | KL-20201216-10 | 53551103 | Earthworks | 0 | Operator | 80 | 4 | HR |  |  | 80 | 0 | 320 | 41.6 | 361.6 | 2020-12-16 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic Breaker and Support Excavator working on F127 access breaking outcrops on steep grades and straighten corners/ operator travel as per valard | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5038KL-20201216-10Operator4320 | KABI LAKE FOREST PRODUCTS LTD5038KL-20201216-10Operator4320OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5062 | KL-20201219-9 | 53551103 | Earthworks | 0 | Operator | 80 | 4 | HR |  |  | 80 | 0 | 320 | 41.6 | 361.6 | 2020-12-19 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc with hydraulic breaker & support exc working on F127 Access breaking outcrops on steep grades. Straighten corners. Operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5062KL-20201219-9Operator4320 | KABI LAKE FOREST PRODUCTS LTD5062KL-20201219-9Operator4320OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5110 | KL-20201217-18 | 53551103 | Earthworks | 0 | Operator | 80 | 4 | HR |  |  | 80 | 0 | 320 | 41.6 | 361.6 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with Hydraulic breaker and support excavator working on F127 access Breaking outcrops on steep grades and straighten corners/ operators as per valard | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5110KL-20201217-18Operator4320 | KABI LAKE FOREST PRODUCTS LTD5110KL-20201217-18Operator4320OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5122 | KL-20201220-9 | 53551103 | Earthworks | 0 | Operator | 80 | 2 | HR |  |  | 80 | 0 | 160 | 20.8 | 180.8 | 2020-12-20 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker & support exc working on F127 Access breaking outcrops on steep grades & straighten corners/operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5122KL-20201220-9Operator2160 | KABI LAKE FOREST PRODUCTS LTD5122KL-20201220-9Operator2160OEWT-PA12-LEM-R1 |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 80 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5217 | KL-20210104-6 | 53551103 | Earthworks | 0 | Operator | 80 | 4 | HR |  |  | 80 | 0 | 320 | 41.6 | 361.6 | 2021-01-04 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker and support excavator working on F117 access breaking outcrops on steep grades and laying trees/ Operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5217KL-20210104-6Operator4320 | KABI LAKE FOREST PRODUCTS LTD5217KL-20210104-6Operator4320OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5230 | KL-20210105-9 | 53551103 | Earthworks | 0 | Operator | 80 | 4 | HR |  |  | 80 | 0 | 320 | 41.6 | 361.6 | 2021-01-05 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker and support excavator working on F117 access breaking outcrops an steep grades/ Operator travel as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5230KL-20210105-9Operator4320 | KABI LAKE FOREST PRODUCTS LTD5230KL-20210105-9Operator4320OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5243 | KL-20210106-7 | 53551103 | Earthworks | 0 | Operator | 80 | 2 | HR |  |  | 80 | 0 | 160 | 20.8 | 180.8 | 2021-01-06 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker working on F117 access breaking outcrops on steep grades/ operator travel as per valard | 11 | F119-F134 | Hensen Road | 0 | 44209 |  | 15 | 44224 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5243KL-20210106-7Operator2160 | KABI LAKE FOREST PRODUCTS LTD5243KL-20210106-7Operator2160OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 80 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5267 | KL-20210107-16 | 53551103 | Earthworks | 0 | Operator | 80 | 2 | HR |  |  | 80 | 0 | 160 | 20.8 | 180.8 | 2021-01-07 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker working on F117 Access breaking outcrops on steep grades/operator travel as per Valard. Skagen excavator supporting breaker. | 11 | F119-F134 | Hensen Road | 0 | 44209 |  | 15 | 44219 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5267KL-20210107-16Operator2160 | KABI LAKE FOREST PRODUCTS LTD5267KL-20210107-16Operator2160OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 80 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5628 | KL-20210126-12 | 53551103 | Earthworks | 0 | Operator | 80 | 4 | HR |  |  | 80 | 0 | 320 | 41.6 | 361.6 | 2021-01-26 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | EXC with breaker & support excavator working on F111 Access breaking outcrops & laying trees. Operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44228 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5628KL-20210126-12Operator4320 | KABI LAKE FOREST PRODUCTS LTD5628KL-20210126-12Operator4320OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5648 | KL-20210127-16 | 53551103 | Earthworks | 0 | Operator | 80 | 4 | HR |  |  | 80 | 0 | 320 | 41.6 | 361.6 | 2021-01-27 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc with hydraulic breaker & support excavator working on F111 Access breaking outcrops & laying trees/operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44228 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5648KL-20210127-16Operator4320 | KABI LAKE FOREST PRODUCTS LTD5648KL-20210127-16Operator4320OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5656 | KL-20210128-8 | 53551103 | Earthworks | 0 | Operator | 80 | 4 | HR |  |  | 80 | 0 | 320 | 41.6 | 361.6 | 2021-01-28 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc w breaker & support exc working on F111 Access breaking outcrops & laying trees/ operator travel as per Valard. | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5656KL-20210128-8Operator4320 | KABI LAKE FOREST PRODUCTS LTD5656KL-20210128-8Operator4320OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 160 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1159 | KL-20200224-4 | 53510711 | Access | 0 | Truck Driver | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2020-02-24 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Pick up buncher and drop off skidder | 7 | D-009 to D-017 | Three Finger Lake | 0 | 43889 |  | 43 | 43890 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1159KL-20200224-4Truck Driver2140 | KABI LAKE FOREST PRODUCTS LTD1159KL-20200224-4Truck Driver2140OEWT-PA2-LEM-R1 | [5 empty] | 1 | 140 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 966 | KL-20200131-5 | 53510711 | Access | 0 | Labourer | 65 | 2 | HR |  |  | 65 | 0 | 130 | 16.9 | 146.9 | 2020-01-31 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clean and sweep off sand, gravel and snow off bridge | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 43867 |  | 41 | 43869 | [5 empty] | Tom Anderson | 07 | KABI LAKE FOREST PRODUCTS LTD966KL-20200131-5Labourer2130 | KABI LAKE FOREST PRODUCTS LTD966KL-20200131-5Labourer2130OEWT-PA2-LEM-R1 | [5 empty] | 1 | 130 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 975 | KL-20200131-10 | 53510711 | Access | 0 | Labourer | 65 | 2 | HR |  |  | 65 | 0 | 130 | 16.9 | 146.9 | 2020-01-31 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clean sand, gravel and snow from bridge on White Lake Road | 7 | D-142 to E-002 | White Lake | 0 | 43867 |  | 41 | 43869 | [5 empty] | Tom Anderson | 07 | KABI LAKE FOREST PRODUCTS LTD975KL-20200131-10Labourer2130 | KABI LAKE FOREST PRODUCTS LTD975KL-20200131-10Labourer2130OEWT-PA2-LEM-R1 | [5 empty] | 1 | 130 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1159 | KL-20200224-4 | 53510711 | Access | 0 | Labourer | 65 | 2 | HR |  |  | 65 | 0 | 130 | 16.9 | 146.9 | 2020-02-24 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Pick up buncher and drop off skidder | 7 | D-009 to D-017 | Three Finger Lake | 0 | 43889 |  | 43 | 43890 | [5 empty] | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1159KL-20200224-4Labourer2130 | KABI LAKE FOREST PRODUCTS LTD1159KL-20200224-4Labourer2130OEWT-PA2-LEM-R1 | [5 empty] | 1 | 130 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1353 | KL-20200322-2 | 53510711 | Access | 0 | Labourer | 65 | 4 | HR |  |  | 65 | 0 | 260 | 33.8 | 293.8 | 2020-03-22 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | PICK UP BLASTING MAT FOR ROAD MAINTENANCE | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 43915 |  | 46 | 43919 | [5 empty] | Dave Ofukany | 07 | KABI LAKE FOREST PRODUCTS LTD1353KL-20200322-2Labourer4260 | KABI LAKE FOREST PRODUCTS LTD1353KL-20200322-2Labourer4260OEWT-PA3-LEM | [5 empty] | 1 | 260 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1150 | KL-20200224-6 | 53510811 | Access | 0 | Labourer | 65 | 3 | HR |  |  | 65 | 0 | 195 | 25.35 | 220.35 | 2020-02-24 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Flag to drop off Dozer D6 | 8 | E086 - E094 | Blue Cedar E | 0 | 43889 |  | 43 | 43890 | [5 empty] | Dean MacArthur | 08 | KABI LAKE FOREST PRODUCTS LTD1150KL-20200224-6Labourer3195 | KABI LAKE FOREST PRODUCTS LTD1150KL-20200224-6Labourer3195OEWT-PA2-LEM-R1 | [5 empty] | 1 | 195 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4787 | KL-20201203-7 | 53510811 | Access | 0 | Labourer | 65 | 6 | HR |  |  | 65 | 0 | 390 | 50.7 | 440.7 | 2020-12-03 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Padda Roadlines hauling pit run from 5 km pit on 100 road to stockpile/labourers sanding access to stockpile with pickup and shovels. | 8 | E004-E016 | White Lake East | 0 | 44193 |  | 53 | 44207 | [5 empty] | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4787KL-20201203-7Labourer6390 | KABI LAKE FOREST PRODUCTS LTD4787KL-20201203-7Labourer6390OEWT-PA12-LEM-R1 | [5 empty] | 1 | 390 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4207 | KL-20201107-1 | 53510812 | Access | 0 | Labourer | 65 | 8 | HR |  |  | 65 | 0 | 520 | 67.6 | 587.6 | 2020-11-07 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Scrape Mud from exiting vehicles to hwy 17 at entrance to silver sity. Pickup with beacon, flag paddle and radio contact watching traffic | 8 | E025-E036 | Silver City | 0 | 44162 |  | 56 | 44163 | [5 empty] | Mandy Sandhu | 08 | KABI LAKE FOREST PRODUCTS LTD4207KL-20201107-1Labourer8520 | KABI LAKE FOREST PRODUCTS LTD4207KL-20201107-1Labourer8520OEWT-PA11-LEM | [5 empty] | 1 | 520 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6959 | KL-20210520-1 | 53510812 | Access | 0 | Labourer | 65 | 8 | HR |  |  | 65 | 0 | 520 | 67.6 | 587.6 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul and spread existing material @ 1.5 km and pit run from stock pile for road repair on E007/E006 main access road/ Laboures laying Geo ( revised) | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6959KL-20210520-1Labourer8520 | KABI LAKE FOREST PRODUCTS LTD6959KL-20210520-1Labourer8520OEWT-PA17-LEM | [5 empty] | 1 | 520 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6965 | KL-20210520-7 | 53510812 | Access | 0 | Labourer | 65 | 4 | HR |  |  | 65 | 0 | 260 | 33.8 | 293.8 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourers shovelling, sweeping bridges & signage repairs @ 9020.00-WC, 801.00-WC, 9010.00-WC & 9040.00-WC. | 8 | E004-E016 | White Lake East | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6965KL-20210520-7Labourer4260 | KABI LAKE FOREST PRODUCTS LTD6965KL-20210520-7Labourer4260OEWT-PA17-LEM | [5 empty] | 1 | 260 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4299 | KL-20201110-9 | 53510912 | Access | 0 | Labourer | 65 | 4 | HR |  |  | 65 | 0 | 260 | 33.8 | 293.8 | 2020-11-10 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load 1 roll of Geo @ Kabi Laydown & Deliver @ E-139 | 9 | E091-E102 | 600 Road | 0 | 44166 |  | 50 | 44168 | [5 empty] | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD4299KL-20201110-9Labourer4260 | KABI LAKE FOREST PRODUCTS LTD4299KL-20201110-9Labourer4260OEWT-PA11-LEM | [5 empty] | 1 | 260 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6953 | KL-20210519-4 | 53510912 | Access | 0 | Labourer | 65 | 1 | HR |  |  | 65 | 0 | 65 | 8.45 | 73.45 | 2021-05-19 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 14M grader started road maintenance from Km 1 to Km 18 on 600 road labourers spotted pickup @Km 18 for grader operator (revised) | 9 | E091-E102 | 600 Road | 0 | 44345 |  | 14 | 44352 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD6953KL-20210519-4Labourer165 | KABI LAKE FOREST PRODUCTS LTD6953KL-20210519-4Labourer165OEWT-PA17-LEM | [5 empty] | 1 | 65 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6962 | KL-20210520-4 | 53510912 | Access | 0 | Labourer | 65 | 1 | HR |  |  | 65 | 0 | 65 | 8.45 | 73.45 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 14M grader continuing grading of 600 road and repairing small wash out/ labourer spotting pickup @ 22km for grader operator ( revised ) | 9 | E091-E102 | 600 Road | 0 | 44345 |  | 14 | 44351 | [5 empty] | William Ouimet | 09 | KABI LAKE FOREST PRODUCTS LTD6962KL-20210520-4Labourer165 | KABI LAKE FOREST PRODUCTS LTD6962KL-20210520-4Labourer165OEWT-PA17-LEM | [5 empty] | 1 | 65 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3780 | KL-20201015-27 | 53511012 | Access | 0 | Labourer | 65 | 6 | HR |  |  | 65 | 0 | 390 | 50.7 | 440.7 | 2020-10-15 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Take broken 3" pump to Marathon Valard Yard | 10 | F-021 to F-032 | Paint Lake Raod 1-B | 0 | 44130 |  | 50 | 44132 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD3780KL-20201015-27Labourer6390 | KABI LAKE FOREST PRODUCTS LTD3780KL-20201015-27Labourer6390OEWT-PA10-LEM | [5 empty] | 1 | 390 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7427 | KL-20211005-1 | 53511012 | Access | 0 | Labourer | 65 | 6 | HR |  |  | 65 | 0 | 390 | 50.7 | 440.7 | 2021-10-05 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F112. Excavator 2 working @ 43/42km. Rock trucks hauling from 37.5km to Skagen @ 36km. Labourer hauling fuel to 35km as per Valard. Supervision of Skagen/Morin. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-1Labourer6390 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-1Labourer6390OEWT-PA22-Lem | [5 empty] | 1 | 390 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7444 | KL-20211008-1-R1 | 53511012 | Access | 0 | Labourer | 65 | 10 | HR |  |  | 65 | 0 | 650 | 84.5 | 734.5 | 2021-10-08 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7444KL-20211008-1-R1Labourer10650 | KABI LAKE FOREST PRODUCTS LTD7444KL-20211008-1-R1Labourer10650OEWT-PA22-Lem | [5 empty] | 1 | 650 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7453 | KL-20211014-1 | 53511012 | Access | 0 | Labourer | 65 | 8 | HR |  |  | 65 | 0 | 520 | 67.6 | 587.6 | 2021-10-14 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from 46 to 39Km, levelling ruts & drainage. Rock trucks haulig existing material from F088 to 34.5Km. Labourer hauling fuel as per Valard. Supervision of Morin, Skagen & Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-1Labourer8520 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-1Labourer8520OEWT-PA22-Lem | [5 empty] | 1 | 520 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7475 | KL-20211019-1 | 53511012 | Access | 0 | Labourer | 65 | 16 | HR |  |  | 65 | 0 | 1040 | 135.2 | 1175.2 | 2021-10-19 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts, laying Geo and spreading existing material @ Km 42 hill/rock trucks hauling existing material from F088 to Km 34 as per Valard. Labourers picking up 4 roll of Geo @12km on Paint Lake Road 2and deliver it to km 42/worked late to finish capping @km 42 for pickup access/Supervision of Morin, Skagen, Pleson and Opas | 10 |  | Paint | 0 | 44494 |  | 61 | 44495 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1Labourer161040 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-1Labourer161040OEWT-PA22-Lem | [5 empty] | 1 | 1040 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7419 | KL-20211002-1 | 53511012 | Access | 0 | Labourer | 65 | 7 | HR |  |  | 65 | 0 | 455 | 59.15 | 514.15 | 2021-10-02 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-1Labourer7455 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-1Labourer7455OEWT-PA22-Lem | [5 empty] | 1 | 455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7421 | KL-20211003-1 | 53511012 | Access | 0 | Labourer | 65 | 17 | HR |  |  | 65 | 0 | 1105 | 143.65 | 1248.65 | 2021-10-03 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading & hauling from 46km to 45km. Labourers hauling fuel to 35km & installing silt fencing as per Valard. Supervision o Skagen & Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-1Labourer171105 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-1Labourer171105OEWT-PA22-Lem | [5 empty] | 1 | 1105 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7500 | KL-20211027-5 | 53511012 | Access | 0 | Labourer | 65 | 8 | HR |  |  | 65 | 0 | 520 | 67.6 | 587.6 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Pick up 3 rolls of Geo in Pic River West and 6 partial rolls @ Marathon Yard and deliver to Km 44 on Paint Lake Road 2/Supervisor loading Geo with Labourer@Pic River West | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7500KL-20211027-5Labourer8520 | KABI LAKE FOREST PRODUCTS LTD7500KL-20211027-5Labourer8520OEWT-PA23-Lem | [5 empty] | 1 | 520 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4143 | KL-20201103-13 | 53511103 | Access | 0 | Labourer | 65 | 9 | HR |  |  | 65 | 0 | 585 | 76.05 | 661.05 | 2020-11-03 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Go down to Hensen Road and pick up 8 rolls of Geo and take back to White River Yard | 11 | F119-F134 | Hensen Road | 0 | 44153 |  | 56 | 44163 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD4143KL-20201103-13Labourer9585 | KABI LAKE FOREST PRODUCTS LTD4143KL-20201103-13Labourer9585OEWT-PA11-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 585 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3273 | KL-20200927-17 | 53511104 | Access | 0 | Labourer | 65 | 0 | HR |  |  | 65 | 0 | 0 | 0 | 0 | 2020-09-27 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pit runfrom Provost pit #5/Dozer spreading | 11 | F-119 to F-134 | Hensen Road | 0 | 43900 |  | 48 | 43871 | [5 empty] | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3273KL-20200927-17Labourer00 | KABI LAKE FOREST PRODUCTS LTD3273KL-20200927-17Labourer00OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 0 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5846 | KL-20210210-8 | 53511111 | Access | 0 | Labourer | 65 | 14 | HR |  |  | 65 | 0 | 910 | 118.3 | 1028.3 | 2021-02-10 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Go to Hensen Rd and steam a culvert @ km 3.5. Cover corduroy in shoefly past F73. Clear snow from road from 0 to 15Km on Hensen West and from Hwy17 to 17Km. | 11 | F119-F134 | Hensen Road | 0 | 44244 |  | 15 | 44250 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5846KL-20210210-8Labourer14910 | KABI LAKE FOREST PRODUCTS LTD5846KL-20210210-8Labourer14910OEWT-PA14-Lem-R1 | [5 empty] | 1 | 910 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5931 | KL-20210216-12 | 53511111 | Access | 0 | Labourer | 65 | 10 | HR |  |  | 65 | 0 | 650 | 84.5 | 734.5 | 2021-02-16 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Lake and Cress float with Legos, access mats and bearing timbers for 12970.00 WC/ Excavator unloaded and storing/labourer cleaning snow off the Dam | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44249 |  | 15 | 44254 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5931KL-20210216-12Labourer10650 | KABI LAKE FOREST PRODUCTS LTD5931KL-20210216-12Labourer10650OEWT-PA14-Lem-R1 | [5 empty] | 1 | 650 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5945 | KL-20210217-9 | 53511111 | Access | 0 | Labourer | 65 | 18 | HR |  |  | 65 | 0 | 1170 | 152.1 | 1322.1 | 2021-02-17 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Steam Pipe at km 3.5 on Hensen Rd | 11 | F119-F134 | Hensen Road | 0 | 44251 |  | 15 | 44254 | [5 empty] | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5945KL-20210217-9Labourer181170 | KABI LAKE FOREST PRODUCTS LTD5945KL-20210217-9Labourer181170OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1170 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6096 | KL-20210226-6 | 53511111 | Access | 0 | Labourer | 65 | 16 | HR |  |  | 65 | 0 | 1040 | 135.2 | 1175.2 | 2021-02-26 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Go down to Hensen Road and steamed pipe at Km 3.6 and install heat trace top | 11 | F119-F134 | Hensen Road | 0 | 44262 |  | 56 | 44265 | [5 empty] | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6096KL-20210226-6Labourer161040 | KABI LAKE FOREST PRODUCTS LTD6096KL-20210226-6Labourer161040OEWT PA15-LEM | [5 empty] | 1 | 1040 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5616 | KL-20210125-13 | 53511111 | Access | 0 | Labourer | 65 | 11 | HR |  |  | 65 | 0 | 715 | 92.95 | 807.95 | 2021-01-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Snow removal, drilling holes & pumping water for flooding of ice crossing @WC 12100.01 (2 floods). Cress prepping and doing lock block install WC 11333.00. Excavators prepping & doing lock block install, had to rent chipper due to blocks not matching up. CR-101260. | 11 | F119-F134 | Hensen Road | 0 | 44225 |  | 55 | 44232 | [5 empty] | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5616KL-20210125-13Labourer11715 | KABI LAKE FOREST PRODUCTS LTD5616KL-20210125-13Labourer11715OEWT-PA14-Lem-R1 | [5 empty] | 1 | 715 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7959 | KL-20220302-4 | 53511111 | Access | 0 | Labourer | 65 | 3 | HR |  |  | 65 | 0 | 195 | 25.35 | 220.35 | 2022-03-02 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Float Cat 950M loader from High Falls Road to F170/ Traffic control required ( Cost Code: 67776007556.591100.57010107 ) | 11 | F170-F211 | High Falls | 1 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7959KL-20220302-4Labourer3195 | KABI LAKE FOREST PRODUCTS LTD7959KL-20220302-4Labourer3195 | [5 empty] | 1 | 195 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7959 | KL-20220302-4 | 53511111 | Access | 0 | Labourer | 65 | 3 | HR |  |  | 65 | 0 | 195 | 25.35 | 220.35 | 2022-03-02 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Float Cat 950M loader from High Falls Road to F170/ Traffic control required ( Cost Code: 67776007556.591100.57010107 ) | 11 | F170-F211 | High Falls | 1 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7959KL-20220302-4Labourer3195 | KABI LAKE FOREST PRODUCTS LTD7959KL-20220302-4Labourer3195 | [5 empty] | 1 | 195 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7960 | KL-20220302-5 | 53511111 | Access | 0 | Labourer | 65 | 2 | HR |  |  | 65 | 0 | 130 | 16.9 | 146.9 | 2022-03-02 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loaders finishing on snow removal and turn around @ F170 / Traffic control required for clearing of Entrance ( Cost Code: 67776007556.591100.57010107 ) | 11 | F170 - F211 | High Falls | 1 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7960KL-20220302-5Labourer2130 | KABI LAKE FOREST PRODUCTS LTD7960KL-20220302-5Labourer2130 | [5 empty] | 1 | 130 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7960 | KL-20220302-5 | 53511111 | Access | 0 | Labourer | 65 | 2 | HR |  |  | 65 | 0 | 130 | 16.9 | 146.9 | 2022-03-02 |  |  |  |  | 1 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  | 30 | Pending | NextBridge Extra | 8009 | Loaders finishing on snow removal and turn around @ F170 / Traffic control required for clearing of Entrance ( Cost Code: 67776007556.591100.57010107 ) | 11 | F170 - F211 | High Falls | 1 | 44630 | [9 empty] | 11 | KABI LAKE FOREST PRODUCTS LTD7960KL-20220302-5Labourer2130 | KABI LAKE FOREST PRODUCTS LTD7960KL-20220302-5Labourer2130 | [5 empty] | 1 | 130 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7194 | KL-20210803-1 | 53511112 | Access | 0 | Labourer | 65 | 7 | HR |  |  | 65 | 0 | 455 | 59.15 | 514.15 | 2021-08-03 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer & Operator moving rock truck from F-037 to F-119 & tracking Cat 330 excavator from 17Km on Hensen to 46Km on paint lake road 2 for gravel haul | 11 | F118-F127 | Hensen Road | 0 | 44420 |  | 14 | 44421 | [5 empty] | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD7194KL-20210803-1Labourer7455 | KABI LAKE FOREST PRODUCTS LTD7194KL-20210803-1Labourer7455OEWT-PA20-Lem | [5 empty] | 1 | 455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 888 | KL-20200114-2 | 53510711 | Access | 0 | L.O.A. | 244 | 1 | Day |  |  | 0 | 0 | 244 | 31.72 | 275.72 | 2020-01-17 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Winter Access Maintenance, dozer opening roads | 7 | D-142 to E-002 | White Lake | 0 |  |  | 17 | 43858 | [5 empty] | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD888KL-20200114-2L.O.A.1244 | KABI LAKE FOREST PRODUCTS LTD888KL-20200114-2L.O.A.1244OEWT-PA1-LEM | [5 empty] | 1 | 244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2565 | KL-20200823-6 | 53510912 | Access | 0 | L.O.A. | 244 | 0.27273 | Day |  |  | 0 | 0 | 66.5455 | 8.6509 | 75.1964 | 2020-08-23 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road maintenance work from E-165 to E-167 | 9 | E-091 to E-102 | 600 Road | 0 | 44068 |  | 15 | 44071 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2565KL-20200823-6L.O.A.0.272727366.5455 | KABI LAKE FOREST PRODUCTS LTD2565KL-20200823-6L.O.A.0.272727366.5455OEWT-PA8-LEM | [5 empty] | 1 | 66.5455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2585 | KL-20200824-6 | 53510912 | Access | 0 | L.O.A. | 244 | 0.45455 | Day |  |  | 0 | 0 | 110.9091 | 14.4182 | 125.3273 | 2020-08-24 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading 600 Road from 9 to 13 Km | 9 | E-091 to E-102 | 600 Road | 0 | 44069 |  | 15 | 44071 | [5 empty] | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2585KL-20200824-6L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD2585KL-20200824-6L.O.A.0.4545455110.9091OEWT-PA8-LEM | [5 empty] | 1 | 110.9091 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7123 | 31587 | 53531001 | Rig/Access Mats | 0 | Supervisor | 101.49 | 10.5 | HR |  |  | 129 | 3 | 1452.645 | 188.8439 | 1641.4888 | 2021-06-30 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel In. Travel to jobsite. Complete site walkthrough, toolbox talk and safety talk with Valard. Unload and rack 261 Mats. Ensure mat safety. Travel out. ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44382 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712331587Supervisor10.51452.645 | Northern Mat & Bridge712331587Supervisor10.51452.645ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1452.645 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7123 | 31587 | 53531001 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 4 | 1327.92 | 172.6296 | 1500.5496 | 2021-06-30 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel In. Travel to jobsite. Complete site walkthrough, toolbox talk and safety talk with Valard. Unload and rack 261 Mats. Ensure mat safety. Travel out. ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44382 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712331587Supervisor81327.92 | Northern Mat & Bridge712331587Supervisor81327.92ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1327.92 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7124 | 21603 | 53531001 | Rig/Access Mats | 0 | Supervisor | 101.49 | 9.5 | HR |  |  | 129 |  | 964.155 | 125.3401 | 1089.4951 | 2021-07-01 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Should have stat holiday rates, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | Jason, Cutler travel to site. Safety meeting with Valard. Load G&G flatbeds from laydown to km 17 Henson Rd. Rest of crew awaiting covid test results and travelling from Thunder Bay. Crew arrived, started shuttling mats to ROW. Crew travelled out. ## Covid 19 protocols in place ## | 10 | F109 | Hensen Road | 0 | 44383 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712421603Supervisor9.5964.155 | Northern Mat & Bridge712421603Supervisor9.5964.155ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 964.155 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7125 | 21604 | 53531001 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 8 | 1843.92 | 239.7096 | 2083.6296 | 2021-07-02 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Entered with regular rates however LEM had stat holiday rates, sent back for revision, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks at km1 laydown. Haulmats from laydown to km 17 Henson rd. shuttle mats from km 17 to Row. Lay mats as per valard intruction. Crew travelled out. ## COVID-19 protocols in effect ## | 10 | F109 | Hensen Road | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712521604Supervisor81843.92 | Northern Mat & Bridge712521604Supervisor81843.92ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1843.92 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7126 | 21607 | 53531001 | Rig/Access Mats | 0 | Supervisor | 101.49 |  | HR |  |  | 129 | 14 | 1806 | 234.78 | 2040.78 | 2021-07-03 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travel to site. Safety meeting. Load, unload trucks. Haul mats onsite from laydown to KM17. shuttle and lay mats as per Valard instruction. ## COVID 19 protocol in effect ## | 10 | F065-F118 | Paint Lake 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712621607Supervisor1806 | Northern Mat & Bridge712621607Supervisor1806ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1806 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7128 | 20611 | 53531001 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 6 | 1585.92 | 206.1696 | 1792.0896 | 2021-07-05 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | Crew travelled in. safety meeting. Load unload trucks, shuttle mats, lay mats as per Valard instructions. Corey Trembett finished covid test in Thunder Bay and travelled to site to run 2nd shuttle ## COVID 19 policies in effect ## | 10 | F065-F118 | Paint lake Road 2 | 0 | 44384 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712820611Supervisor81585.92 | Northern Mat & Bridge712820611Supervisor81585.92ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1585.92 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7129 | 21613 | 53531001 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 5.5 | 1521.42 | 197.7846 | 1719.2046 | 2021-07-06 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew traveled to location, safety meeting, Load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew traveled out. ## COVID-19 policies in effect ## Dylan Thompson travelling to Thunder Bay for Valard COVID test. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712921613Supervisor81521.42 | Northern Mat & Bridge712921613Supervisor81521.42ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1521.42 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7130 | 21615 | 53531001 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 5.5 | 1521.42 | 197.7846 | 1719.2046 | 2021-07-07 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew travelled in, safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Shuttle one load of mats with roll off, determined high potential for a spill, use roll off to move mats to Paint lake road as per Valard, moved 28 mats to Paint Lake road. Dylan Thompson enroute to Thunder Bay for Valard covid test. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa fore work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge713021615Supervisor81521.42 | Northern Mat & Bridge713021615Supervisor81521.42ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1521.42 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7141 | 21617 | 53531001 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 5.5 | 1521.42 | 197.7846 | 1719.2046 | 2021-07-08 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew Travelled to site, Safety meeting, load unload trucks, shuttle mats, lays mats as per Valard instruction. Crew travelled out. ## Covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714121617Supervisor81521.42 | Northern Mat & Bridge714121617Supervisor81521.42ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1521.42 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7142 | 21619 | 53531001 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 6 | 1585.92 | 206.1696 | 1792.0896 | 2021-07-09 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in. safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Deliver another load of 10 mats to km 7-8 on paint lake with roll-off for road repair. Total of 32 mats at km 7-8 on Paint Lake Rd. crew travelled out. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa for work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44387 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714221619Supervisor81585.92 | Northern Mat & Bridge714221619Supervisor81585.92ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1585.92 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Supervisor | 101.49 |  | HR |  |  | 129 | 14 | 1806 | 234.78 | 2040.78 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Supervisor1806 | Northern Mat & Bridge714321620Supervisor1806ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1806 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7145 | 21622 | 53531001 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 5.5 | 1521.42 | 197.7846 | 1719.2046 | 2021-07-12 | 0 | ESI10770 | 44452 | 68 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44390 |  | 14 | 44449 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714521622Supervisor81521.42 | Northern Mat & Bridge714521622Supervisor81521.42ESI10770 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1521.42 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7146 | 21623 | 53531001 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 5 | 1456.92 | 189.3996 | 1646.3196 | 2021-07-13 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44391 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714621623Supervisor81456.92 | Northern Mat & Bridge714621623Supervisor81456.92ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1456.92 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7147 | 21624 | 53531001 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 5 | 1456.92 | 189.3996 | 1646.3196 | 2021-07-14 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled to site, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instructiions, crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slowly with over a 25km round trip. Released on site haulers. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44392 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714721624Supervisor81456.92 | Northern Mat & Bridge714721624Supervisor81456.92ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1456.92 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7148 | 21625 | 53531001 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 4 | 1327.92 | 172.6296 | 1500.5496 | 2021-07-15 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load shuttles, shuttlemats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44393 |  | 36 | 44394 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714821625Supervisor81327.92 | Northern Mat & Bridge714821625Supervisor81327.92ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1327.92 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7149 | 21626 | 53531001 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 5 | 1456.92 | 189.3996 | 1646.3196 | 2021-07-16 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44394 |  | 36 | 44395 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714921626Supervisor81456.92 | Northern Mat & Bridge714921626Supervisor81456.92ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1456.92 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7150 | 21627 | 53531001 | Rig/Access Mats | 0 | Supervisor | 101.49 | 0 | HR |  |  | 129 | 13 | 1677 | 218.01 | 1895.01 | 2021-07-17 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instructions. Crew tavelled out. ## covid 19 policies in effect ## Jason got Shane set up laying mats at valard camp in WaWa then Travel to marathon to scout next jobsite with Mike Lecocq, Then returned to crews | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44395 |  | 36 | 44396 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715021627Supervisor01677 | Northern Mat & Bridge715021627Supervisor01677ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1677 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7152 | 21631 | 53531001 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 5 | 1456.92 | 189.3996 | 1646.3196 | 2021-07-19 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting. Load shuttles, shuttle mats, lay mats as per Valard instructions. Crew travelled out. ## Covid 19 policies in effect ## very hot, dusty and rugged terrian, taking a long time to shuttle mats to excavator. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44397 |  | 36 | 44398 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715221631Supervisor81456.92 | Northern Mat & Bridge715221631Supervisor81456.92ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1456.92 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7168 | 31593 | 53531001 | Rig/Access Mats | 0 | Supervisor | 101.49 | 11 | HR |  |  | 129 | 0 | 1116.39 | 145.1307 | 1261.5207 | 2021-06-28 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | NO description on LEM however it appears that it is all travel time to mobilize in to the job. Sent email to NMB requesting more detail | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44385 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge716831593Supervisor111116.39 | Northern Mat & Bridge716831593Supervisor111116.39ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1116.39 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7168 | 31593 | 53531001 | Rig/Access Mats | 0 | Supervisor | 101.49 | 10.5 | HR |  |  | 129 | 0 | 1065.645 | 138.5339 | 1204.1789 | 2021-06-28 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | NO description on LEM however it appears that it is all travel time to mobilize in to the job. Sent email to NMB requesting more detail | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44385 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge716831593Supervisor10.51065.645 | Northern Mat & Bridge716831593Supervisor10.51065.645ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1065.645 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7169 | 31585 R1 | 53531001 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 6 | 1585.92 | 206.1696 | 1792.0896 | 2021-06-29 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel and standby time for Jason and Cutler. Travel to Thunder Bay, wait on and receive Covid tests. Myself, Aaron and Dylan worked on site. Essentially I was wrangling Kawartha trucks about 5KM’s from site. Aaron Jones was unloading trucks at the laydown pad. Dylan escorted Andre into KM17 with the excavator and then assisted Aaron with unloading trucks and getting them turned around to head out ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge716931585 R1Supervisor81585.92 | Northern Mat & Bridge716931585 R1Supervisor81585.92ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1585.92 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7169 | 31585 R1 | 53531001 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 2 | 1069.92 | 139.0896 | 1209.0096 | 2021-06-29 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel and standby time for Jason and Cutler. Travel to Thunder Bay, wait on and receive Covid tests. Myself, Aaron and Dylan worked on site. Essentially I was wrangling Kawartha trucks about 5KM’s from site. Aaron Jones was unloading trucks at the laydown pad. Dylan escorted Andre into KM17 with the excavator and then assisted Aaron with unloading trucks and getting them turned around to head out ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge716931585 R1Supervisor81069.92 | Northern Mat & Bridge716931585 R1Supervisor81069.92ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1069.92 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7124 | 21603 | 53531001 | Rig/Access Mats | 0 | Supervisor - Sunday/Stat Holidays |  | 0 |  |  |  | 156.9 | 14 | 2196.6 | 285.558 | 2482.158 | 2021-07-01 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Should have stat holiday rates, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | Jason, Cutler travel to site. Safety meeting with Valard. Load G&G flatbeds from laydown to km 17 Henson Rd. Rest of crew awaiting covid test results and travelling from Thunder Bay. Crew arrived, started shuttling mats to ROW. Crew travelled out. ## Covid 19 protocols in place ## | 10 | F109 | Hensen Road | 0 | 44383 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712421603Supervisor - Sunday/Stat Holidays02196.6 | Northern Mat & Bridge712421603Supervisor - Sunday/Stat Holidays02196.6ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2196.6 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7127 | 21608 | 53531001 | Rig/Access Mats | 0 | Supervisor - Sunday/Stat Holidays |  | 0 |  |  |  | 156.9 | 13 | 2039.7 | 265.161 | 2304.861 | 2021-07-04 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks. Haul mats on site, shuttle and lay mats as per Valard instuction. Crew travelled out. ## covid 19 policies in effect ## Cory Trembeltt travel time 18 hrs total for mob in and drive to TB for COVID test and drive to site Wawa. | 10 | F065-F118 | Paint Lake Road 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712721608Supervisor - Sunday/Stat Holidays02039.7 | Northern Mat & Bridge712721608Supervisor - Sunday/Stat Holidays02039.7ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2039.7 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7144 | 21621 | 53531001 | Rig/Access Mats | 0 | Supervisor - Sunday/Stat Holidays |  | 0 |  |  |  | 156.9 | 13 | 2039.7 | 265.161 | 2304.861 | 2021-07-11 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | crew travelled in, safety meeting,load unload trucks, shuttle mats, lay mats as per Valard instructions. ## covid 19 policies in effect ## crew travelled out | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44389 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714421621Supervisor - Sunday/Stat Holidays02039.7 | Northern Mat & Bridge714421621Supervisor - Sunday/Stat Holidays02039.7ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2039.7 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7151 | 21629 | 53531001 | Rig/Access Mats | 0 | Supervisor - Sunday/Stat Holidays |  | 0 |  |  |  | 156.9 | 13 | 2039.7 | 265.161 | 2304.861 | 2021-07-18 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per valard instructions. Crew travelled out. ## covid 19 policies in effect ## very rough terrian, very hot and dusty, taking a long time to get mats in. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44396 |  | 36 | 44397 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715121629Supervisor - Sunday/Stat Holidays02039.7 | Northern Mat & Bridge715121629Supervisor - Sunday/Stat Holidays02039.7ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2039.7 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7123 | 31587 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 3 | 1058.64 | 137.6232 | 1196.2632 | 2021-06-30 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel In. Travel to jobsite. Complete site walkthrough, toolbox talk and safety talk with Valard. Unload and rack 261 Mats. Ensure mat safety. Travel out. ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44382 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712331587Operator81058.64 | Northern Mat & Bridge712331587Operator81058.64ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1058.64 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7123 | 31587 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-06-30 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel In. Travel to jobsite. Complete site walkthrough, toolbox talk and safety talk with Valard. Unload and rack 261 Mats. Ensure mat safety. Travel out. ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44382 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712331587Operator8931.6 | Northern Mat & Bridge712331587Operator8931.6ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 931.6 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7123 | 31587 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 13.5 | Hr |  |  | 127.04 | 0 | 1143.315 | 148.631 | 1291.946 | 2021-06-30 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel In. Travel to jobsite. Complete site walkthrough, toolbox talk and safety talk with Valard. Unload and rack 261 Mats. Ensure mat safety. Travel out. ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44382 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712331587Operator13.51143.315 | Northern Mat & Bridge712331587Operator13.51143.315ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1143.315 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7123 | 31587 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-06-30 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel In. Travel to jobsite. Complete site walkthrough, toolbox talk and safety talk with Valard. Unload and rack 261 Mats. Ensure mat safety. Travel out. ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44382 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712331587Operator8931.6 | Northern Mat & Bridge712331587Operator8931.6ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 931.6 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7123 | 31587 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-06-30 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel In. Travel to jobsite. Complete site walkthrough, toolbox talk and safety talk with Valard. Unload and rack 261 Mats. Ensure mat safety. Travel out. ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44382 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712331587Operator8931.6 | Northern Mat & Bridge712331587Operator8931.6ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 931.6 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7125 | 21604 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 3 | 1058.64 | 137.6232 | 1196.2632 | 2021-07-02 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Entered with regular rates however LEM had stat holiday rates, sent back for revision, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks at km1 laydown. Haulmats from laydown to km 17 Henson rd. shuttle mats from km 17 to Row. Lay mats as per valard intruction. Crew travelled out. ## COVID-19 protocols in effect ## | 10 | F109 | Hensen Road | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712521604Operator81058.64 | Northern Mat & Bridge712521604Operator81058.64ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1058.64 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7125 | 21604 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-02 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Entered with regular rates however LEM had stat holiday rates, sent back for revision, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks at km1 laydown. Haulmats from laydown to km 17 Henson rd. shuttle mats from km 17 to Row. Lay mats as per valard intruction. Crew travelled out. ## COVID-19 protocols in effect ## | 10 | F109 | Hensen Road | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712521604Operator81185.68 | Northern Mat & Bridge712521604Operator81185.68ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7125 | 21604 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4.5 | 1249.2 | 162.396 | 1411.596 | 2021-07-02 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Entered with regular rates however LEM had stat holiday rates, sent back for revision, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks at km1 laydown. Haulmats from laydown to km 17 Henson rd. shuttle mats from km 17 to Row. Lay mats as per valard intruction. Crew travelled out. ## COVID-19 protocols in effect ## | 10 | F109 | Hensen Road | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712521604Operator81249.2 | Northern Mat & Bridge712521604Operator81249.2ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1249.2 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7125 | 21604 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-07-02 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Entered with regular rates however LEM had stat holiday rates, sent back for revision, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks at km1 laydown. Haulmats from laydown to km 17 Henson rd. shuttle mats from km 17 to Row. Lay mats as per valard intruction. Crew travelled out. ## COVID-19 protocols in effect ## | 10 | F109 | Hensen Road | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712521604Operator8931.6 | Northern Mat & Bridge712521604Operator8931.6ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 931.6 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7125 | 21604 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 3 | 1058.64 | 137.6232 | 1196.2632 | 2021-07-02 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Entered with regular rates however LEM had stat holiday rates, sent back for revision, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks at km1 laydown. Haulmats from laydown to km 17 Henson rd. shuttle mats from km 17 to Row. Lay mats as per valard intruction. Crew travelled out. ## COVID-19 protocols in effect ## | 10 | F109 | Hensen Road | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712521604Operator81058.64 | Northern Mat & Bridge712521604Operator81058.64ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1058.64 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7126 | 21607 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | Hr |  |  | 127.04 | 13 | 1651.52 | 214.6976 | 1866.2176 | 2021-07-03 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travel to site. Safety meeting. Load, unload trucks. Haul mats onsite from laydown to KM17. shuttle and lay mats as per Valard instruction. ## COVID 19 protocol in effect ## | 10 | F065-F118 | Paint Lake 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712621607Operator01651.52 | Northern Mat & Bridge712621607Operator01651.52ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1651.52 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7126 | 21607 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | Hr |  |  | 127.04 | 11 | 1397.44 | 181.6672 | 1579.1072 | 2021-07-03 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travel to site. Safety meeting. Load, unload trucks. Haul mats onsite from laydown to KM17. shuttle and lay mats as per Valard instruction. ## COVID 19 protocol in effect ## | 10 | F065-F118 | Paint Lake 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712621607Operator01397.44 | Northern Mat & Bridge712621607Operator01397.44ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1397.44 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7126 | 21607 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | Hr |  |  | 127.04 | 12 | 1524.48 | 198.1824 | 1722.6624 | 2021-07-03 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travel to site. Safety meeting. Load, unload trucks. Haul mats onsite from laydown to KM17. shuttle and lay mats as per Valard instruction. ## COVID 19 protocol in effect ## | 10 | F065-F118 | Paint Lake 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712621607Operator01524.48 | Northern Mat & Bridge712621607Operator01524.48ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1524.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7126 | 21607 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | Hr |  |  | 127.04 | 11.5 | 1460.96 | 189.9248 | 1650.8848 | 2021-07-03 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travel to site. Safety meeting. Load, unload trucks. Haul mats onsite from laydown to KM17. shuttle and lay mats as per Valard instruction. ## COVID 19 protocol in effect ## | 10 | F065-F118 | Paint Lake 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712621607Operator01460.96 | Northern Mat & Bridge712621607Operator01460.96ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1460.96 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7126 | 21607 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | Hr |  |  | 127.04 | 9.5 | 1206.88 | 156.8944 | 1363.7744 | 2021-07-03 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travel to site. Safety meeting. Load, unload trucks. Haul mats onsite from laydown to KM17. shuttle and lay mats as per Valard instruction. ## COVID 19 protocol in effect ## | 10 | F065-F118 | Paint Lake 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712621607Operator01206.88 | Northern Mat & Bridge712621607Operator01206.88ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1206.88 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7127 | 21608 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 18 | Hr |  |  | 127.04 | 0 | 1524.42 | 198.1746 | 1722.5946 | 2021-07-04 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks. Haul mats on site, shuttle and lay mats as per Valard instuction. Crew travelled out. ## covid 19 policies in effect ## Cory Trembeltt travel time 18 hrs total for mob in and drive to TB for COVID test and drive to site Wawa. | 10 | F065-F118 | Paint Lake Road 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712721608Operator181524.42 | Northern Mat & Bridge712721608Operator181524.42ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1524.42 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7128 | 20611 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-05 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | Crew travelled in. safety meeting. Load unload trucks, shuttle mats, lay mats as per Valard instructions. Corey Trembett finished covid test in Thunder Bay and travelled to site to run 2nd shuttle ## COVID 19 policies in effect ## | 10 | F065-F118 | Paint lake Road 2 | 0 | 44384 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712820611Operator81185.68 | Northern Mat & Bridge712820611Operator81185.68ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7128 | 20611 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 3 | 1058.64 | 137.6232 | 1196.2632 | 2021-07-05 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | Crew travelled in. safety meeting. Load unload trucks, shuttle mats, lay mats as per Valard instructions. Corey Trembett finished covid test in Thunder Bay and travelled to site to run 2nd shuttle ## COVID 19 policies in effect ## | 10 | F065-F118 | Paint lake Road 2 | 0 | 44384 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712820611Operator81058.64 | Northern Mat & Bridge712820611Operator81058.64ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1058.64 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7128 | 20611 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 5 | 1312.72 | 170.6536 | 1483.3736 | 2021-07-05 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | Crew travelled in. safety meeting. Load unload trucks, shuttle mats, lay mats as per Valard instructions. Corey Trembett finished covid test in Thunder Bay and travelled to site to run 2nd shuttle ## COVID 19 policies in effect ## | 10 | F065-F118 | Paint lake Road 2 | 0 | 44384 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712820611Operator81312.72 | Northern Mat & Bridge712820611Operator81312.72ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1312.72 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7128 | 20611 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-05 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | Crew travelled in. safety meeting. Load unload trucks, shuttle mats, lay mats as per Valard instructions. Corey Trembett finished covid test in Thunder Bay and travelled to site to run 2nd shuttle ## COVID 19 policies in effect ## | 10 | F065-F118 | Paint lake Road 2 | 0 | 44384 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712820611Operator81185.68 | Northern Mat & Bridge712820611Operator81185.68ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7128 | 20611 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-07-05 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | Crew travelled in. safety meeting. Load unload trucks, shuttle mats, lay mats as per Valard instructions. Corey Trembett finished covid test in Thunder Bay and travelled to site to run 2nd shuttle ## COVID 19 policies in effect ## | 10 | F065-F118 | Paint lake Road 2 | 0 | 44384 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712820611Operator8931.6 | Northern Mat & Bridge712820611Operator8931.6ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 931.6 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7128 | 20611 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 0 | 677.52 | 88.0776 | 765.5976 | 2021-07-05 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | Crew travelled in. safety meeting. Load unload trucks, shuttle mats, lay mats as per Valard instructions. Corey Trembett finished covid test in Thunder Bay and travelled to site to run 2nd shuttle ## COVID 19 policies in effect ## | 10 | F065-F118 | Paint lake Road 2 | 0 | 44384 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712820611Operator8677.52 | Northern Mat & Bridge712820611Operator8677.52ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 677.52 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7129 | 21613 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 3.5 | 1122.16 | 145.8808 | 1268.0408 | 2021-07-06 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew traveled to location, safety meeting, Load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew traveled out. ## COVID-19 policies in effect ## Dylan Thompson travelling to Thunder Bay for Valard COVID test. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712921613Operator81122.16 | Northern Mat & Bridge712921613Operator81122.16ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1122.16 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7129 | 21613 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-06 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew traveled to location, safety meeting, Load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew traveled out. ## COVID-19 policies in effect ## Dylan Thompson travelling to Thunder Bay for Valard COVID test. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712921613Operator81185.68 | Northern Mat & Bridge712921613Operator81185.68ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7129 | 21613 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4.5 | 1249.2 | 162.396 | 1411.596 | 2021-07-06 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew traveled to location, safety meeting, Load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew traveled out. ## COVID-19 policies in effect ## Dylan Thompson travelling to Thunder Bay for Valard COVID test. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712921613Operator81249.2 | Northern Mat & Bridge712921613Operator81249.2ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1249.2 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7129 | 21613 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-06 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew traveled to location, safety meeting, Load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew traveled out. ## COVID-19 policies in effect ## Dylan Thompson travelling to Thunder Bay for Valard COVID test. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712921613Operator81185.68 | Northern Mat & Bridge712921613Operator81185.68ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7129 | 21613 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 2.5 | 995.12 | 129.3656 | 1124.4856 | 2021-07-06 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew traveled to location, safety meeting, Load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew traveled out. ## COVID-19 policies in effect ## Dylan Thompson travelling to Thunder Bay for Valard COVID test. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712921613Operator8995.12 | Northern Mat & Bridge712921613Operator8995.12ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 995.12 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7129 | 21613 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 2.5 | 995.12 | 129.3656 | 1124.4856 | 2021-07-06 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew traveled to location, safety meeting, Load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew traveled out. ## COVID-19 policies in effect ## Dylan Thompson travelling to Thunder Bay for Valard COVID test. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712921613Operator8995.12 | Northern Mat & Bridge712921613Operator8995.12ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 995.12 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7130 | 21615 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-07 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew travelled in, safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Shuttle one load of mats with roll off, determined high potential for a spill, use roll off to move mats to Paint lake road as per Valard, moved 28 mats to Paint Lake road. Dylan Thompson enroute to Thunder Bay for Valard covid test. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa fore work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge713021615Operator81185.68 | Northern Mat & Bridge713021615Operator81185.68ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7130 | 21615 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4.5 | 1249.2 | 162.396 | 1411.596 | 2021-07-07 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew travelled in, safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Shuttle one load of mats with roll off, determined high potential for a spill, use roll off to move mats to Paint lake road as per Valard, moved 28 mats to Paint Lake road. Dylan Thompson enroute to Thunder Bay for Valard covid test. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa fore work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge713021615Operator81249.2 | Northern Mat & Bridge713021615Operator81249.2ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1249.2 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7130 | 21615 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4.5 | 1249.2 | 162.396 | 1411.596 | 2021-07-07 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew travelled in, safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Shuttle one load of mats with roll off, determined high potential for a spill, use roll off to move mats to Paint lake road as per Valard, moved 28 mats to Paint Lake road. Dylan Thompson enroute to Thunder Bay for Valard covid test. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa fore work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge713021615Operator81249.2 | Northern Mat & Bridge713021615Operator81249.2ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1249.2 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7130 | 21615 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-07 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew travelled in, safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Shuttle one load of mats with roll off, determined high potential for a spill, use roll off to move mats to Paint lake road as per Valard, moved 28 mats to Paint Lake road. Dylan Thompson enroute to Thunder Bay for Valard covid test. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa fore work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge713021615Operator81185.68 | Northern Mat & Bridge713021615Operator81185.68ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7130 | 21615 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 2.5 | 995.12 | 129.3656 | 1124.4856 | 2021-07-07 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew travelled in, safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Shuttle one load of mats with roll off, determined high potential for a spill, use roll off to move mats to Paint lake road as per Valard, moved 28 mats to Paint Lake road. Dylan Thompson enroute to Thunder Bay for Valard covid test. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa fore work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge713021615Operator8995.12 | Northern Mat & Bridge713021615Operator8995.12ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 995.12 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7130 | 21615 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 6.5 | Hr |  |  | 127.04 | 0 | 550.485 | 71.5631 | 622.048 | 2021-07-07 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew travelled in, safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Shuttle one load of mats with roll off, determined high potential for a spill, use roll off to move mats to Paint lake road as per Valard, moved 28 mats to Paint Lake road. Dylan Thompson enroute to Thunder Bay for Valard covid test. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa fore work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge713021615Operator6.5550.485 | Northern Mat & Bridge713021615Operator6.5550.485ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 550.485 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7141 | 21617 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-08 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew Travelled to site, Safety meeting, load unload trucks, shuttle mats, lays mats as per Valard instruction. Crew travelled out. ## Covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714121617Operator81185.68 | Northern Mat & Bridge714121617Operator81185.68ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7141 | 21617 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-08 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew Travelled to site, Safety meeting, load unload trucks, shuttle mats, lays mats as per Valard instruction. Crew travelled out. ## Covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714121617Operator81185.68 | Northern Mat & Bridge714121617Operator81185.68ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7141 | 21617 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4.5 | 1249.2 | 162.396 | 1411.596 | 2021-07-08 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew Travelled to site, Safety meeting, load unload trucks, shuttle mats, lays mats as per Valard instruction. Crew travelled out. ## Covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714121617Operator81249.2 | Northern Mat & Bridge714121617Operator81249.2ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1249.2 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7141 | 21617 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 3.5 | 1122.16 | 145.8808 | 1268.0408 | 2021-07-08 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew Travelled to site, Safety meeting, load unload trucks, shuttle mats, lays mats as per Valard instruction. Crew travelled out. ## Covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714121617Operator81122.16 | Northern Mat & Bridge714121617Operator81122.16ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1122.16 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7141 | 21617 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 0 | 677.52 | 88.0776 | 765.5976 | 2021-07-08 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew Travelled to site, Safety meeting, load unload trucks, shuttle mats, lays mats as per Valard instruction. Crew travelled out. ## Covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714121617Operator8677.52 | Northern Mat & Bridge714121617Operator8677.52ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 677.52 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7141 | 21617 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 3.5 | 1122.16 | 145.8808 | 1268.0408 | 2021-07-08 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew Travelled to site, Safety meeting, load unload trucks, shuttle mats, lays mats as per Valard instruction. Crew travelled out. ## Covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714121617Operator81122.16 | Northern Mat & Bridge714121617Operator81122.16ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1122.16 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7141 | 21617 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 3 | 1058.64 | 137.6232 | 1196.2632 | 2021-07-08 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew Travelled to site, Safety meeting, load unload trucks, shuttle mats, lays mats as per Valard instruction. Crew travelled out. ## Covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714121617Operator81058.64 | Northern Mat & Bridge714121617Operator81058.64ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1058.64 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7142 | 21619 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-09 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in. safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Deliver another load of 10 mats to km 7-8 on paint lake with roll-off for road repair. Total of 32 mats at km 7-8 on Paint Lake Rd. crew travelled out. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa for work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44387 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714221619Operator81185.68 | Northern Mat & Bridge714221619Operator81185.68ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7142 | 21619 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 5 | 1312.72 | 170.6536 | 1483.3736 | 2021-07-09 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in. safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Deliver another load of 10 mats to km 7-8 on paint lake with roll-off for road repair. Total of 32 mats at km 7-8 on Paint Lake Rd. crew travelled out. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa for work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44387 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714221619Operator81312.72 | Northern Mat & Bridge714221619Operator81312.72ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1312.72 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7142 | 21619 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 3 | 1058.64 | 137.6232 | 1196.2632 | 2021-07-09 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in. safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Deliver another load of 10 mats to km 7-8 on paint lake with roll-off for road repair. Total of 32 mats at km 7-8 on Paint Lake Rd. crew travelled out. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa for work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44387 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714221619Operator81058.64 | Northern Mat & Bridge714221619Operator81058.64ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1058.64 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7142 | 21619 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 5 | 1312.72 | 170.6536 | 1483.3736 | 2021-07-09 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in. safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Deliver another load of 10 mats to km 7-8 on paint lake with roll-off for road repair. Total of 32 mats at km 7-8 on Paint Lake Rd. crew travelled out. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa for work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44387 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714221619Operator81312.72 | Northern Mat & Bridge714221619Operator81312.72ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1312.72 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7142 | 21619 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 5 | 1312.72 | 170.6536 | 1483.3736 | 2021-07-09 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in. safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Deliver another load of 10 mats to km 7-8 on paint lake with roll-off for road repair. Total of 32 mats at km 7-8 on Paint Lake Rd. crew travelled out. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa for work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44387 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714221619Operator81312.72 | Northern Mat & Bridge714221619Operator81312.72ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1312.72 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7142 | 21619 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 2.5 | 995.12 | 129.3656 | 1124.4856 | 2021-07-09 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in. safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Deliver another load of 10 mats to km 7-8 on paint lake with roll-off for road repair. Total of 32 mats at km 7-8 on Paint Lake Rd. crew travelled out. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa for work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44387 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714221619Operator8995.12 | Northern Mat & Bridge714221619Operator8995.12ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 995.12 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7142 | 21619 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 5.5 | Hr |  |  | 127.04 | 0 | 465.795 | 60.5534 | 526.3483 | 2021-07-09 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in. safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Deliver another load of 10 mats to km 7-8 on paint lake with roll-off for road repair. Total of 32 mats at km 7-8 on Paint Lake Rd. crew travelled out. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa for work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44387 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714221619Operator5.5465.795 | Northern Mat & Bridge714221619Operator5.5465.795ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 465.795 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | Hr |  |  | 127.04 | 12 | 1524.48 | 198.1824 | 1722.6624 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Operator01524.48 | Northern Mat & Bridge714321620Operator01524.48ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1524.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | Hr |  |  | 127.04 | 12 | 1524.48 | 198.1824 | 1722.6624 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Operator01524.48 | Northern Mat & Bridge714321620Operator01524.48ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1524.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | Hr |  |  | 127.04 | 11.5 | 1460.96 | 189.9248 | 1650.8848 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Operator01460.96 | Northern Mat & Bridge714321620Operator01460.96ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1460.96 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | Hr |  |  | 127.04 | 12 | 1524.48 | 198.1824 | 1722.6624 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Operator01524.48 | Northern Mat & Bridge714321620Operator01524.48ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1524.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | Hr |  |  | 127.04 | 13 | 1651.52 | 214.6976 | 1866.2176 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Operator01651.52 | Northern Mat & Bridge714321620Operator01651.52ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1651.52 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | Hr |  |  | 127.04 | 11 | 1397.44 | 181.6672 | 1579.1072 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Operator01397.44 | Northern Mat & Bridge714321620Operator01397.44ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1397.44 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7145 | 21622 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4.5 | 1249.2 | 162.396 | 1411.596 | 2021-07-12 | 0 | ESI10770 | 44452 | 68 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44390 |  | 14 | 44449 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714521622Operator81249.2 | Northern Mat & Bridge714521622Operator81249.2ESI10770 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1249.2 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7145 | 21622 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4.5 | 1249.2 | 162.396 | 1411.596 | 2021-07-12 | 0 | ESI10770 | 44452 | 68 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44390 |  | 14 | 44449 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714521622Operator81249.2 | Northern Mat & Bridge714521622Operator81249.2ESI10770 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1249.2 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7145 | 21622 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-12 | 0 | ESI10770 | 44452 | 68 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44390 |  | 14 | 44449 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714521622Operator81185.68 | Northern Mat & Bridge714521622Operator81185.68ESI10770 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7145 | 21622 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4.5 | 1249.2 | 162.396 | 1411.596 | 2021-07-12 | 0 | ESI10770 | 44452 | 68 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44390 |  | 14 | 44449 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714521622Operator81249.2 | Northern Mat & Bridge714521622Operator81249.2ESI10770 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1249.2 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7145 | 21622 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-12 | 0 | ESI10770 | 44452 | 68 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44390 |  | 14 | 44449 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714521622Operator81185.68 | Northern Mat & Bridge714521622Operator81185.68ESI10770 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7145 | 21622 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-12 | 0 | ESI10770 | 44452 | 68 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44390 |  | 14 | 44449 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714521622Operator81185.68 | Northern Mat & Bridge714521622Operator81185.68ESI10770 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7146 | 21623 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-13 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44391 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714621623Operator81185.68 | Northern Mat & Bridge714621623Operator81185.68ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7146 | 21623 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 3.5 | 1122.16 | 145.8808 | 1268.0408 | 2021-07-13 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44391 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714621623Operator81122.16 | Northern Mat & Bridge714621623Operator81122.16ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1122.16 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7146 | 21623 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 3 | 1058.64 | 137.6232 | 1196.2632 | 2021-07-13 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44391 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714621623Operator81058.64 | Northern Mat & Bridge714621623Operator81058.64ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1058.64 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7146 | 21623 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 2.5 | 995.12 | 129.3656 | 1124.4856 | 2021-07-13 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44391 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714621623Operator8995.12 | Northern Mat & Bridge714621623Operator8995.12ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 995.12 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7146 | 21623 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-13 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44391 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714621623Operator81185.68 | Northern Mat & Bridge714621623Operator81185.68ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7146 | 21623 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-13 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44391 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714621623Operator81185.68 | Northern Mat & Bridge714621623Operator81185.68ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7147 | 21624 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-14 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled to site, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instructiions, crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slowly with over a 25km round trip. Released on site haulers. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44392 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714721624Operator81185.68 | Northern Mat & Bridge714721624Operator81185.68ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7147 | 21624 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-14 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled to site, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instructiions, crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slowly with over a 25km round trip. Released on site haulers. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44392 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714721624Operator81185.68 | Northern Mat & Bridge714721624Operator81185.68ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7147 | 21624 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 3 | 1058.64 | 137.6232 | 1196.2632 | 2021-07-14 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled to site, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instructiions, crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slowly with over a 25km round trip. Released on site haulers. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44392 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714721624Operator81058.64 | Northern Mat & Bridge714721624Operator81058.64ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1058.64 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7147 | 21624 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 3.5 | 1122.16 | 145.8808 | 1268.0408 | 2021-07-14 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled to site, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instructiions, crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slowly with over a 25km round trip. Released on site haulers. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44392 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714721624Operator81122.16 | Northern Mat & Bridge714721624Operator81122.16ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1122.16 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7147 | 21624 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-14 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled to site, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instructiions, crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slowly with over a 25km round trip. Released on site haulers. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44392 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714721624Operator81185.68 | Northern Mat & Bridge714721624Operator81185.68ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7147 | 21624 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-14 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled to site, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instructiions, crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slowly with over a 25km round trip. Released on site haulers. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44392 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714721624Operator81185.68 | Northern Mat & Bridge714721624Operator81185.68ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7148 | 21625 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-15 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load shuttles, shuttlemats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44393 |  | 36 | 44394 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714821625Operator81185.68 | Northern Mat & Bridge714821625Operator81185.68ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7148 | 21625 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 0 | 677.52 | 88.0776 | 765.5976 | 2021-07-15 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load shuttles, shuttlemats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44393 |  | 36 | 44394 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714821625Operator8677.52 | Northern Mat & Bridge714821625Operator8677.52ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 677.52 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7148 | 21625 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 2.5 | 995.12 | 129.3656 | 1124.4856 | 2021-07-15 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load shuttles, shuttlemats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44393 |  | 36 | 44394 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714821625Operator8995.12 | Northern Mat & Bridge714821625Operator8995.12ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 995.12 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7148 | 21625 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-07-15 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load shuttles, shuttlemats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44393 |  | 36 | 44394 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714821625Operator8931.6 | Northern Mat & Bridge714821625Operator8931.6ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 931.6 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7148 | 21625 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-15 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load shuttles, shuttlemats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44393 |  | 36 | 44394 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714821625Operator81185.68 | Northern Mat & Bridge714821625Operator81185.68ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7148 | 21625 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 3 | 1058.64 | 137.6232 | 1196.2632 | 2021-07-15 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load shuttles, shuttlemats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44393 |  | 36 | 44394 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714821625Operator81058.64 | Northern Mat & Bridge714821625Operator81058.64ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1058.64 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7149 | 21626 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-16 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44394 |  | 36 | 44395 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714921626Operator81185.68 | Northern Mat & Bridge714921626Operator81185.68ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7149 | 21626 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-16 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44394 |  | 36 | 44395 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714921626Operator81185.68 | Northern Mat & Bridge714921626Operator81185.68ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7149 | 21626 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 0 | 677.52 | 88.0776 | 765.5976 | 2021-07-16 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44394 |  | 36 | 44395 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714921626Operator8677.52 | Northern Mat & Bridge714921626Operator8677.52ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 677.52 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7149 | 21626 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4.5 | 1249.2 | 162.396 | 1411.596 | 2021-07-16 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44394 |  | 36 | 44395 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714921626Operator81249.2 | Northern Mat & Bridge714921626Operator81249.2ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1249.2 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7149 | 21626 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-16 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44394 |  | 36 | 44395 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714921626Operator81185.68 | Northern Mat & Bridge714921626Operator81185.68ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7149 | 21626 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-16 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44394 |  | 36 | 44395 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714921626Operator81185.68 | Northern Mat & Bridge714921626Operator81185.68ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7150 | 21627 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | Hr |  |  | 127.04 | 12 | 1524.48 | 198.1824 | 1722.6624 | 2021-07-17 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instructions. Crew tavelled out. ## covid 19 policies in effect ## Jason got Shane set up laying mats at valard camp in WaWa then Travel to marathon to scout next jobsite with Mike Lecocq, Then returned to crews | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44395 |  | 36 | 44396 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715021627Operator01524.48 | Northern Mat & Bridge715021627Operator01524.48ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1524.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7150 | 21627 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | Hr |  |  | 127.04 | 12 | 1524.48 | 198.1824 | 1722.6624 | 2021-07-17 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instructions. Crew tavelled out. ## covid 19 policies in effect ## Jason got Shane set up laying mats at valard camp in WaWa then Travel to marathon to scout next jobsite with Mike Lecocq, Then returned to crews | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44395 |  | 36 | 44396 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715021627Operator01524.48 | Northern Mat & Bridge715021627Operator01524.48ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1524.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7150 | 21627 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | Hr |  |  | 127.04 | 12 | 1524.48 | 198.1824 | 1722.6624 | 2021-07-17 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instructions. Crew tavelled out. ## covid 19 policies in effect ## Jason got Shane set up laying mats at valard camp in WaWa then Travel to marathon to scout next jobsite with Mike Lecocq, Then returned to crews | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44395 |  | 36 | 44396 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715021627Operator01524.48 | Northern Mat & Bridge715021627Operator01524.48ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1524.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7150 | 21627 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | Hr |  |  | 127.04 | 12 | 1524.48 | 198.1824 | 1722.6624 | 2021-07-17 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instructions. Crew tavelled out. ## covid 19 policies in effect ## Jason got Shane set up laying mats at valard camp in WaWa then Travel to marathon to scout next jobsite with Mike Lecocq, Then returned to crews | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44395 |  | 36 | 44396 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715021627Operator01524.48 | Northern Mat & Bridge715021627Operator01524.48ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1524.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7150 | 21627 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | Hr |  |  | 127.04 | 12 | 1524.48 | 198.1824 | 1722.6624 | 2021-07-17 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instructions. Crew tavelled out. ## covid 19 policies in effect ## Jason got Shane set up laying mats at valard camp in WaWa then Travel to marathon to scout next jobsite with Mike Lecocq, Then returned to crews | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44395 |  | 36 | 44396 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715021627Operator01524.48 | Northern Mat & Bridge715021627Operator01524.48ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1524.48 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7152 | 21631 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-19 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting. Load shuttles, shuttle mats, lay mats as per Valard instructions. Crew travelled out. ## Covid 19 policies in effect ## very hot, dusty and rugged terrian, taking a long time to shuttle mats to excavator. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44397 |  | 36 | 44398 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715221631Operator81185.68 | Northern Mat & Bridge715221631Operator81185.68ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7152 | 21631 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-19 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting. Load shuttles, shuttle mats, lay mats as per Valard instructions. Crew travelled out. ## Covid 19 policies in effect ## very hot, dusty and rugged terrian, taking a long time to shuttle mats to excavator. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44397 |  | 36 | 44398 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715221631Operator81185.68 | Northern Mat & Bridge715221631Operator81185.68ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7152 | 21631 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-19 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting. Load shuttles, shuttle mats, lay mats as per Valard instructions. Crew travelled out. ## Covid 19 policies in effect ## very hot, dusty and rugged terrian, taking a long time to shuttle mats to excavator. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44397 |  | 36 | 44398 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715221631Operator81185.68 | Northern Mat & Bridge715221631Operator81185.68ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7152 | 21631 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-19 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting. Load shuttles, shuttle mats, lay mats as per Valard instructions. Crew travelled out. ## Covid 19 policies in effect ## very hot, dusty and rugged terrian, taking a long time to shuttle mats to excavator. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44397 |  | 36 | 44398 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715221631Operator81185.68 | Northern Mat & Bridge715221631Operator81185.68ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7152 | 21631 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-19 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting. Load shuttles, shuttle mats, lay mats as per Valard instructions. Crew travelled out. ## Covid 19 policies in effect ## very hot, dusty and rugged terrian, taking a long time to shuttle mats to excavator. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44397 |  | 36 | 44398 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715221631Operator81185.68 | Northern Mat & Bridge715221631Operator81185.68ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7153 | 21633 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-20 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, Safety, load shuttles, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## COVID 19 policies in effect ## very hot, dusty and rough terrian taking a long time to shuttle mats. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44398 |  | 36 | 44399 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715321633Operator81185.68 | Northern Mat & Bridge715321633Operator81185.68ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7153 | 21633 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-20 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, Safety, load shuttles, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## COVID 19 policies in effect ## very hot, dusty and rough terrian taking a long time to shuttle mats. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44398 |  | 36 | 44399 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715321633Operator81185.68 | Northern Mat & Bridge715321633Operator81185.68ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7153 | 21633 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-20 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, Safety, load shuttles, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## COVID 19 policies in effect ## very hot, dusty and rough terrian taking a long time to shuttle mats. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44398 |  | 36 | 44399 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715321633Operator81185.68 | Northern Mat & Bridge715321633Operator81185.68ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7153 | 21633 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-20 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, Safety, load shuttles, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## COVID 19 policies in effect ## very hot, dusty and rough terrian taking a long time to shuttle mats. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44398 |  | 36 | 44399 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715321633Operator81185.68 | Northern Mat & Bridge715321633Operator81185.68ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7153 | 21633 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-07-20 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, Safety, load shuttles, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## COVID 19 policies in effect ## very hot, dusty and rough terrian taking a long time to shuttle mats. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44398 |  | 36 | 44399 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715321633Operator81185.68 | Northern Mat & Bridge715321633Operator81185.68ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1185.68 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7169 | 31585 R1 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-06-29 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel and standby time for Jason and Cutler. Travel to Thunder Bay, wait on and receive Covid tests. Myself, Aaron and Dylan worked on site. Essentially I was wrangling Kawartha trucks about 5KM’s from site. Aaron Jones was unloading trucks at the laydown pad. Dylan escorted Andre into KM17 with the excavator and then assisted Aaron with unloading trucks and getting them turned around to head out ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge716931585 R1Operator8931.6 | Northern Mat & Bridge716931585 R1Operator8931.6ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 931.6 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7169 | 31585 R1 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 5 | 1312.72 | 170.6536 | 1483.3736 | 2021-06-29 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel and standby time for Jason and Cutler. Travel to Thunder Bay, wait on and receive Covid tests. Myself, Aaron and Dylan worked on site. Essentially I was wrangling Kawartha trucks about 5KM’s from site. Aaron Jones was unloading trucks at the laydown pad. Dylan escorted Andre into KM17 with the excavator and then assisted Aaron with unloading trucks and getting them turned around to head out ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge716931585 R1Operator81312.72 | Northern Mat & Bridge716931585 R1Operator81312.72ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1312.72 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7169 | 31585 R1 | 53531001 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | Hr |  |  | 127.04 | 5 | 1312.72 | 170.6536 | 1483.3736 | 2021-06-29 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel and standby time for Jason and Cutler. Travel to Thunder Bay, wait on and receive Covid tests. Myself, Aaron and Dylan worked on site. Essentially I was wrangling Kawartha trucks about 5KM’s from site. Aaron Jones was unloading trucks at the laydown pad. Dylan escorted Andre into KM17 with the excavator and then assisted Aaron with unloading trucks and getting them turned around to head out ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge716931585 R1Operator81312.72 | Northern Mat & Bridge716931585 R1Operator81312.72ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1312.72 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7124 | 21603 | 53531001 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 12 | 2033.04 | 264.2952 | 2297.3352 | 2021-07-01 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Should have stat holiday rates, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | Jason, Cutler travel to site. Safety meeting with Valard. Load G&G flatbeds from laydown to km 17 Henson Rd. Rest of crew awaiting covid test results and travelling from Thunder Bay. Crew arrived, started shuttling mats to ROW. Crew travelled out. ## Covid 19 protocols in place ## | 10 | F109 | Hensen Road | 0 | 44383 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712421603Operator - Sunday/Stat Holidays02033.04 | Northern Mat & Bridge712421603Operator - Sunday/Stat Holidays02033.04ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2033.04 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7124 | 21603 | 53531001 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 10.5 | 1778.91 | 231.2583 | 2010.1683 | 2021-07-01 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Should have stat holiday rates, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | Jason, Cutler travel to site. Safety meeting with Valard. Load G&G flatbeds from laydown to km 17 Henson Rd. Rest of crew awaiting covid test results and travelling from Thunder Bay. Crew arrived, started shuttling mats to ROW. Crew travelled out. ## Covid 19 protocols in place ## | 10 | F109 | Hensen Road | 0 | 44383 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712421603Operator - Sunday/Stat Holidays01778.91 | Northern Mat & Bridge712421603Operator - Sunday/Stat Holidays01778.91ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1778.91 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7124 | 21603 | 53531001 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 10.5 | 1778.91 | 231.2583 | 2010.1683 | 2021-07-01 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Should have stat holiday rates, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | Jason, Cutler travel to site. Safety meeting with Valard. Load G&G flatbeds from laydown to km 17 Henson Rd. Rest of crew awaiting covid test results and travelling from Thunder Bay. Crew arrived, started shuttling mats to ROW. Crew travelled out. ## Covid 19 protocols in place ## | 10 | F109 | Hensen Road | 0 | 44383 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712421603Operator - Sunday/Stat Holidays01778.91 | Northern Mat & Bridge712421603Operator - Sunday/Stat Holidays01778.91ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1778.91 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7124 | 21603 | 53531001 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 10.5 | 1778.91 | 231.2583 | 2010.1683 | 2021-07-01 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Should have stat holiday rates, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | Jason, Cutler travel to site. Safety meeting with Valard. Load G&G flatbeds from laydown to km 17 Henson Rd. Rest of crew awaiting covid test results and travelling from Thunder Bay. Crew arrived, started shuttling mats to ROW. Crew travelled out. ## Covid 19 protocols in place ## | 10 | F109 | Hensen Road | 0 | 44383 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712421603Operator - Sunday/Stat Holidays01778.91 | Northern Mat & Bridge712421603Operator - Sunday/Stat Holidays01778.91ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1778.91 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7124 | 21603 | 53531001 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 9 | 1524.78 | 198.2214 | 1723.0014 | 2021-07-01 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Should have stat holiday rates, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | Jason, Cutler travel to site. Safety meeting with Valard. Load G&G flatbeds from laydown to km 17 Henson Rd. Rest of crew awaiting covid test results and travelling from Thunder Bay. Crew arrived, started shuttling mats to ROW. Crew travelled out. ## Covid 19 protocols in place ## | 10 | F109 | Hensen Road | 0 | 44383 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712421603Operator - Sunday/Stat Holidays01524.78 | Northern Mat & Bridge712421603Operator - Sunday/Stat Holidays01524.78ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1524.78 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7127 | 21608 | 53531001 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 11.5 | 1948.33 | 253.2829 | 2201.6129 | 2021-07-04 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks. Haul mats on site, shuttle and lay mats as per Valard instuction. Crew travelled out. ## covid 19 policies in effect ## Cory Trembeltt travel time 18 hrs total for mob in and drive to TB for COVID test and drive to site Wawa. | 10 | F065-F118 | Paint Lake Road 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712721608Operator - Sunday/Stat Holidays01948.33 | Northern Mat & Bridge712721608Operator - Sunday/Stat Holidays01948.33ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1948.33 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7127 | 21608 | 53531001 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 11 | 1863.62 | 242.2706 | 2105.8906 | 2021-07-04 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks. Haul mats on site, shuttle and lay mats as per Valard instuction. Crew travelled out. ## covid 19 policies in effect ## Cory Trembeltt travel time 18 hrs total for mob in and drive to TB for COVID test and drive to site Wawa. | 10 | F065-F118 | Paint Lake Road 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712721608Operator - Sunday/Stat Holidays01863.62 | Northern Mat & Bridge712721608Operator - Sunday/Stat Holidays01863.62ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1863.62 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7127 | 21608 | 53531001 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 12 | 2033.04 | 264.2952 | 2297.3352 | 2021-07-04 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks. Haul mats on site, shuttle and lay mats as per Valard instuction. Crew travelled out. ## covid 19 policies in effect ## Cory Trembeltt travel time 18 hrs total for mob in and drive to TB for COVID test and drive to site Wawa. | 10 | F065-F118 | Paint Lake Road 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712721608Operator - Sunday/Stat Holidays02033.04 | Northern Mat & Bridge712721608Operator - Sunday/Stat Holidays02033.04ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2033.04 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7127 | 21608 | 53531001 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 11 | 1863.62 | 242.2706 | 2105.8906 | 2021-07-04 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks. Haul mats on site, shuttle and lay mats as per Valard instuction. Crew travelled out. ## covid 19 policies in effect ## Cory Trembeltt travel time 18 hrs total for mob in and drive to TB for COVID test and drive to site Wawa. | 10 | F065-F118 | Paint Lake Road 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712721608Operator - Sunday/Stat Holidays01863.62 | Northern Mat & Bridge712721608Operator - Sunday/Stat Holidays01863.62ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1863.62 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7127 | 21608 | 53531001 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 10 | 1694.2 | 220.246 | 1914.446 | 2021-07-04 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks. Haul mats on site, shuttle and lay mats as per Valard instuction. Crew travelled out. ## covid 19 policies in effect ## Cory Trembeltt travel time 18 hrs total for mob in and drive to TB for COVID test and drive to site Wawa. | 10 | F065-F118 | Paint Lake Road 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712721608Operator - Sunday/Stat Holidays01694.2 | Northern Mat & Bridge712721608Operator - Sunday/Stat Holidays01694.2ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1694.2 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7144 | 21621 | 53531001 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 12 | 2033.04 | 264.2952 | 2297.3352 | 2021-07-11 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | crew travelled in, safety meeting,load unload trucks, shuttle mats, lay mats as per Valard instructions. ## covid 19 policies in effect ## crew travelled out | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44389 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714421621Operator - Sunday/Stat Holidays02033.04 | Northern Mat & Bridge714421621Operator - Sunday/Stat Holidays02033.04ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2033.04 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7144 | 21621 | 53531001 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 12 | 2033.04 | 264.2952 | 2297.3352 | 2021-07-11 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | crew travelled in, safety meeting,load unload trucks, shuttle mats, lay mats as per Valard instructions. ## covid 19 policies in effect ## crew travelled out | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44389 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714421621Operator - Sunday/Stat Holidays02033.04 | Northern Mat & Bridge714421621Operator - Sunday/Stat Holidays02033.04ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2033.04 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7144 | 21621 | 53531001 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 12 | 2033.04 | 264.2952 | 2297.3352 | 2021-07-11 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | crew travelled in, safety meeting,load unload trucks, shuttle mats, lay mats as per Valard instructions. ## covid 19 policies in effect ## crew travelled out | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44389 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714421621Operator - Sunday/Stat Holidays02033.04 | Northern Mat & Bridge714421621Operator - Sunday/Stat Holidays02033.04ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2033.04 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7144 | 21621 | 53531001 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 12 | 2033.04 | 264.2952 | 2297.3352 | 2021-07-11 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | crew travelled in, safety meeting,load unload trucks, shuttle mats, lay mats as per Valard instructions. ## covid 19 policies in effect ## crew travelled out | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44389 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714421621Operator - Sunday/Stat Holidays02033.04 | Northern Mat & Bridge714421621Operator - Sunday/Stat Holidays02033.04ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2033.04 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7144 | 21621 | 53531001 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 12 | 2033.04 | 264.2952 | 2297.3352 | 2021-07-11 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | crew travelled in, safety meeting,load unload trucks, shuttle mats, lay mats as per Valard instructions. ## covid 19 policies in effect ## crew travelled out | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44389 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714421621Operator - Sunday/Stat Holidays02033.04 | Northern Mat & Bridge714421621Operator - Sunday/Stat Holidays02033.04ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2033.04 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7144 | 21621 | 53531001 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 12 | 2033.04 | 264.2952 | 2297.3352 | 2021-07-11 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | crew travelled in, safety meeting,load unload trucks, shuttle mats, lay mats as per Valard instructions. ## covid 19 policies in effect ## crew travelled out | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44389 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714421621Operator - Sunday/Stat Holidays02033.04 | Northern Mat & Bridge714421621Operator - Sunday/Stat Holidays02033.04ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2033.04 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7151 | 21629 | 53531001 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 12.5 | 2117.75 | 275.3075 | 2393.0575 | 2021-07-18 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per valard instructions. Crew travelled out. ## covid 19 policies in effect ## very rough terrian, very hot and dusty, taking a long time to get mats in. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44396 |  | 36 | 44397 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715121629Operator - Sunday/Stat Holidays02117.75 | Northern Mat & Bridge715121629Operator - Sunday/Stat Holidays02117.75ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2117.75 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7151 | 21629 | 53531001 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 12 | 2033.04 | 264.2952 | 2297.3352 | 2021-07-18 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per valard instructions. Crew travelled out. ## covid 19 policies in effect ## very rough terrian, very hot and dusty, taking a long time to get mats in. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44396 |  | 36 | 44397 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715121629Operator - Sunday/Stat Holidays02033.04 | Northern Mat & Bridge715121629Operator - Sunday/Stat Holidays02033.04ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2033.04 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7151 | 21629 | 53531001 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 12.5 | 2117.75 | 275.3075 | 2393.0575 | 2021-07-18 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per valard instructions. Crew travelled out. ## covid 19 policies in effect ## very rough terrian, very hot and dusty, taking a long time to get mats in. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44396 |  | 36 | 44397 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715121629Operator - Sunday/Stat Holidays02117.75 | Northern Mat & Bridge715121629Operator - Sunday/Stat Holidays02117.75ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2117.75 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7151 | 21629 | 53531001 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 12.5 | 2117.75 | 275.3075 | 2393.0575 | 2021-07-18 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per valard instructions. Crew travelled out. ## covid 19 policies in effect ## very rough terrian, very hot and dusty, taking a long time to get mats in. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44396 |  | 36 | 44397 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715121629Operator - Sunday/Stat Holidays02117.75 | Northern Mat & Bridge715121629Operator - Sunday/Stat Holidays02117.75ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2117.75 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7151 | 21629 | 53531001 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 12.5 | 2117.75 | 275.3075 | 2393.0575 | 2021-07-18 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per valard instructions. Crew travelled out. ## covid 19 policies in effect ## very rough terrian, very hot and dusty, taking a long time to get mats in. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44396 |  | 36 | 44397 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715121629Operator - Sunday/Stat Holidays02117.75 | Northern Mat & Bridge715121629Operator - Sunday/Stat Holidays02117.75ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2117.75 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Operator - Travel | 84.69 | 5.5 | Hr |  |  |  | 0 | 465.795 | 60.5534 | 526.3483 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Operator - Travel5.5465.795 | Northern Mat & Bridge714321620Operator - Travel5.5465.795ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 465.795 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Operator - Travel | 84.69 | 12 | Hr |  |  |  | 0 | 1016.28 | 132.1164 | 1148.3964 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Operator - Travel121016.28 | Northern Mat & Bridge714321620Operator - Travel121016.28ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1016.28 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7168 | 31593 | 53531001 | Rig/Access Mats | 0 | Operator - Travel | 84.69 | 28 | Hr |  |  |  | 0 | 2371.32 | 308.2716 | 2679.5916 | 2021-06-28 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | NO description on LEM however it appears that it is all travel time to mobilize in to the job. Sent email to NMB requesting more detail | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44385 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge716831593Operator - Travel282371.32 | Northern Mat & Bridge716831593Operator - Travel282371.32ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2371.32 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7128 | 20611 | 53531001 | Rig/Access Mats | 0 | Travel per KM | 0.82 | 522 | km |  |  |  | 0 | 428.04 | 55.6452 | 483.6852 | 2021-07-05 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | Crew travelled in. safety meeting. Load unload trucks, shuttle mats, lay mats as per Valard instructions. Corey Trembett finished covid test in Thunder Bay and travelled to site to run 2nd shuttle ## COVID 19 policies in effect ## | 10 | F065-F118 | Paint lake Road 2 | 0 | 44384 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712820611Travel per KM522428.04 | Northern Mat & Bridge712820611Travel per KM522428.04ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 428.04 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7129 | 21613 | 53531001 | Rig/Access Mats | 0 | Travel per KM | 0.82 | 670 | km |  |  |  | 0 | 549.4 | 71.422 | 620.822 | 2021-07-06 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew traveled to location, safety meeting, Load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew traveled out. ## COVID-19 policies in effect ## Dylan Thompson travelling to Thunder Bay for Valard COVID test. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712921613Travel per KM670549.4 | Northern Mat & Bridge712921613Travel per KM670549.4ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 549.4 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7130 | 21615 | 53531001 | Rig/Access Mats | 0 | Travel per KM | 0.82 | 1404 | km |  |  |  | 0 | 1151.28 | 149.6664 | 1300.9464 | 2021-07-07 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew travelled in, safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Shuttle one load of mats with roll off, determined high potential for a spill, use roll off to move mats to Paint lake road as per Valard, moved 28 mats to Paint Lake road. Dylan Thompson enroute to Thunder Bay for Valard covid test. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa fore work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge713021615Travel per KM14041151.28 | Northern Mat & Bridge713021615Travel per KM14041151.28ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1151.28 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7141 | 21617 | 53531001 | Rig/Access Mats | 0 | Travel per KM | 0.82 | 482 | km |  |  |  | 0 | 395.24 | 51.3812 | 446.6212 | 2021-07-08 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew Travelled to site, Safety meeting, load unload trucks, shuttle mats, lays mats as per Valard instruction. Crew travelled out. ## Covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714121617Travel per KM482395.24 | Northern Mat & Bridge714121617Travel per KM482395.24ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 395.24 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7142 | 21619 | 53531001 | Rig/Access Mats | 0 | Travel per KM | 0.82 | 1267 | km |  |  |  | 0 | 1038.94 | 135.0622 | 1174.0022 | 2021-07-09 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in. safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Deliver another load of 10 mats to km 7-8 on paint lake with roll-off for road repair. Total of 32 mats at km 7-8 on Paint Lake Rd. crew travelled out. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa for work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44387 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714221619Travel per KM12671038.94 | Northern Mat & Bridge714221619Travel per KM12671038.94ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1038.94 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Travel per KM | 0.82 | 481 | km |  |  |  | 0 | 394.42 | 51.2746 | 445.6946 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Travel per KM481394.42 | Northern Mat & Bridge714321620Travel per KM481394.42ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 394.42 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7127 | 21608 | 53531001 | Rig/Access Mats | 0 | Travel per KM | 0.82 | 1592 | km |  |  |  | 0 | 1305.44 | 169.7072 | 1475.1472 | 2021-07-04 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks. Haul mats on site, shuttle and lay mats as per Valard instuction. Crew travelled out. ## covid 19 policies in effect ## Cory Trembeltt travel time 18 hrs total for mob in and drive to TB for COVID test and drive to site Wawa. | 10 | F065-F118 | Paint Lake Road 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712721608Travel per KM15921305.44 | Northern Mat & Bridge712721608Travel per KM15921305.44ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1305.44 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7123 | 31587 | 53531001 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 7 | Day |  |  |  | 0 | 1575 | 204.75 | 1779.75 | 2021-06-30 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel In. Travel to jobsite. Complete site walkthrough, toolbox talk and safety talk with Valard. Unload and rack 261 Mats. Ensure mat safety. Travel out. ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44382 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712331587Subsistence Per Day71575 | Northern Mat & Bridge712331587Subsistence Per Day71575ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1575 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7124 | 21603 | 53531001 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 5 | Day |  |  |  | 0 | 1125 | 146.25 | 1271.25 | 2021-07-01 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Should have stat holiday rates, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | Jason, Cutler travel to site. Safety meeting with Valard. Load G&G flatbeds from laydown to km 17 Henson Rd. Rest of crew awaiting covid test results and travelling from Thunder Bay. Crew arrived, started shuttling mats to ROW. Crew travelled out. ## Covid 19 protocols in place ## | 10 | F109 | Hensen Road | 0 | 44383 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712421603Subsistence Per Day51125 | Northern Mat & Bridge712421603Subsistence Per Day51125ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1125 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7125 | 21604 | 53531001 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 4 | Day |  |  |  | 0 | 900 | 117 | 1017 | 2021-07-02 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Entered with regular rates however LEM had stat holiday rates, sent back for revision, pending revision, emailed NMB again regarding this on Sept 6 |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks at km1 laydown. Haulmats from laydown to km 17 Henson rd. shuttle mats from km 17 to Row. Lay mats as per valard intruction. Crew travelled out. ## COVID-19 protocols in effect ## | 10 | F109 | Hensen Road | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712521604Subsistence Per Day4900 | Northern Mat & Bridge712521604Subsistence Per Day4900ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 900 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7126 | 21607 | 53531001 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 4 | Day |  |  |  | 0 | 900 | 117 | 1017 | 2021-07-03 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travel to site. Safety meeting. Load, unload trucks. Haul mats onsite from laydown to KM17. shuttle and lay mats as per Valard instruction. ## COVID 19 protocol in effect ## | 10 | F065-F118 | Paint Lake 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712621607Subsistence Per Day4900 | Northern Mat & Bridge712621607Subsistence Per Day4900ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 900 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7127 | 21608 | 53531001 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 6 | Day |  |  |  | 0 | 1350 | 175.5 | 1525.5 | 2021-07-04 | 0 | ESI10335A | 44452 | 63 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | crew travelled to site. Safety meeting. Load unload trucks. Haul mats on site, shuttle and lay mats as per Valard instuction. Crew travelled out. ## covid 19 policies in effect ## Cory Trembeltt travel time 18 hrs total for mob in and drive to TB for COVID test and drive to site Wawa. | 10 | F065-F118 | Paint Lake Road 2 | 0 |  |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712721608Subsistence Per Day61350 | Northern Mat & Bridge712721608Subsistence Per Day61350ESI10335A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1350 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7128 | 20611 | 53531001 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 4 | Day |  |  |  | 0 | 900 | 117 | 1017 | 2021-07-05 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, |  | Approved |  |  | Crew travelled in. safety meeting. Load unload trucks, shuttle mats, lay mats as per Valard instructions. Corey Trembett finished covid test in Thunder Bay and travelled to site to run 2nd shuttle ## COVID 19 policies in effect ## | 10 | F065-F118 | Paint lake Road 2 | 0 | 44384 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712820611Subsistence Per Day4900 | Northern Mat & Bridge712820611Subsistence Per Day4900ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 900 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7129 | 21613 | 53531001 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 6 | Day |  |  |  | 0 | 1350 | 175.5 | 1525.5 | 2021-07-06 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew traveled to location, safety meeting, Load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew traveled out. ## COVID-19 policies in effect ## Dylan Thompson travelling to Thunder Bay for Valard COVID test. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge712921613Subsistence Per Day61350 | Northern Mat & Bridge712921613Subsistence Per Day61350ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1350 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7130 | 21615 | 53531001 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 4 | Day |  |  |  | 0 | 900 | 117 | 1017 | 2021-07-07 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | crew travelled in, safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Shuttle one load of mats with roll off, determined high potential for a spill, use roll off to move mats to Paint lake road as per Valard, moved 28 mats to Paint Lake road. Dylan Thompson enroute to Thunder Bay for Valard covid test. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa fore work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge713021615Subsistence Per Day4900 | Northern Mat & Bridge713021615Subsistence Per Day4900ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 900 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7141 | 21617 | 53531001 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 5 | Day |  |  |  | 0 | 1125 | 146.25 | 1271.25 | 2021-07-08 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew Travelled to site, Safety meeting, load unload trucks, shuttle mats, lays mats as per Valard instruction. Crew travelled out. ## Covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44386 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714121617Subsistence Per Day51125 | Northern Mat & Bridge714121617Subsistence Per Day51125ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1125 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7142 | 21619 | 53531001 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 4 | Day |  |  |  | 0 | 900 | 117 | 1017 | 2021-07-09 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in. safety meeting, load unload trucks, shuttle mats. Lay mats as per Valard instruction. Deliver another load of 10 mats to km 7-8 on paint lake with roll-off for road repair. Total of 32 mats at km 7-8 on Paint Lake Rd. crew travelled out. ## COVID 19 policies in effect ## Operators coming in from Barrie, travel to Wawa, then to Thunder Bay for Covid testing, then back to wawa for work. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44387 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714221619Subsistence Per Day4900 | Northern Mat & Bridge714221619Subsistence Per Day4900ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 900 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7143 | 21620 | 53531001 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 4 | Day |  |  |  | 0 | 900 | 117 | 1017 | 2021-07-10 | 0 | ESI10349A | 44452 | 64 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | NMB lowered their overtime rate on the float truck so I adjusted the hours to match the reduced rate. Pending revision, emailed NMB Aug 08 and again regarding this on Sept 6, Original LEM approved by Will Ouimet however after further consideration, revision to supervisor hours was requested. |  | Approved |  |  | Crew travelled in, safety meeting. Unload 2nd track carrier off Andre, escort Andre in and out of Henson Rd. Cory run TC until Keagan arrives. 3 G&G onsite mat hauler back on the job. Load & unload trucks, shuttle mats, lay mats as per Valard instruction. Keagan to late to bring to site. crew travelled out. ##Covid 19 policies in effect ## 2 G&G travelled previous day | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44448 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714321620Subsistence Per Day4900 | Northern Mat & Bridge714321620Subsistence Per Day4900ESI10349A |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 900 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7144 | 21621 | 53531001 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 4 | Day |  |  |  | 0 | 900 | 117 | 1017 | 2021-07-11 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | crew travelled in, safety meeting,load unload trucks, shuttle mats, lay mats as per Valard instructions. ## covid 19 policies in effect ## crew travelled out | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44389 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714421621Subsistence Per Day4900 | Northern Mat & Bridge714421621Subsistence Per Day4900ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 900 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7145 | 21622 | 53531001 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 4 | Day |  |  |  | 0 | 900 | 117 | 1017 | 2021-07-12 | 0 | ESI10770 | 44452 | 68 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44390 |  | 14 | 44449 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714521622Subsistence Per Day4900 | Northern Mat & Bridge714521622Subsistence Per Day4900ESI10770 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 900 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7146 | 21623 | 53531001 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 4 | Day |  |  |  | 0 | 900 | 117 | 1017 | 2021-07-13 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled in, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slow to prevent over heating and breakdown. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44391 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714621623Subsistence Per Day4900 | Northern Mat & Bridge714621623Subsistence Per Day4900ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 900 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7147 | 21624 | 53531001 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 4 | Day |  |  |  | 0 | 900 | 117 | 1017 | 2021-07-14 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval to NMB |  | Approved |  |  | Crew travelled to site, safety meeting, load unload trucks, shuttle mats, lay mats as per Valard instructiions, crew travelled out. ## covid 19 policies in effect ## very hot and dusty shuttles are moving slowly with over a 25km round trip. Released on site haulers. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44392 |  | 14 | 44393 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge714721624Subsistence Per Day4900 | Northern Mat & Bridge714721624Subsistence Per Day4900ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 900 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7149 | 21626 | 53531001 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 4 | Day |  |  |  | 0 | 900 | 117 | 1017 | 2021-07-16 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## covid 19 policies in effect ## | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44394 |  | 36 | 44395 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge714921626Subsistence Per Day4900 | Northern Mat & Bridge714921626Subsistence Per Day4900ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 900 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7150 | 21627 | 53531001 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 3 | Day |  |  |  | 0 | 675 | 87.75 | 762.75 | 2021-07-17 | 0 | ESI10347 | 44416 | 71 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per Valard instructions. Crew tavelled out. ## covid 19 policies in effect ## Jason got Shane set up laying mats at valard camp in WaWa then Travel to marathon to scout next jobsite with Mike Lecocq, Then returned to crews | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44395 |  | 36 | 44396 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715021627Subsistence Per Day3675 | Northern Mat & Bridge715021627Subsistence Per Day3675ESI10347 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 675 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7151 | 21629 | 53531001 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 3 | Day |  |  |  | 0 | 675 | 87.75 | 762.75 | 2021-07-18 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, safety meeting, load shuttles, shuttle mats, lay mats as per valard instructions. Crew travelled out. ## covid 19 policies in effect ## very rough terrian, very hot and dusty, taking a long time to get mats in. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44396 |  | 36 | 44397 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715121629Subsistence Per Day3675 | Northern Mat & Bridge715121629Subsistence Per Day3675ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 675 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7152 | 21631 | 53531001 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 3 | Day |  |  |  | 0 | 675 | 87.75 | 762.75 | 2021-07-19 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | crew travelled in, safety meeting. Load shuttles, shuttle mats, lay mats as per Valard instructions. Crew travelled out. ## Covid 19 policies in effect ## very hot, dusty and rugged terrian, taking a long time to shuttle mats to excavator. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44397 |  | 36 | 44398 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715221631Subsistence Per Day3675 | Northern Mat & Bridge715221631Subsistence Per Day3675ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 675 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7153 | 21633 | 53531001 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 3 | Day |  |  |  | 0 | 675 | 87.75 | 762.75 | 2021-07-20 | 0 | ESI10336 | 44416 | 69 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Crew travelled in, Safety, load shuttles, shuttle mats, lay mats as per Valard instruction. Crew travelled out. ## COVID 19 policies in effect ## very hot, dusty and rough terrian taking a long time to shuttle mats. | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44398 |  | 36 | 44399 | [5 empty] | Mike Lecocq | 10 | Northern Mat & Bridge715321633Subsistence Per Day3675 | Northern Mat & Bridge715321633Subsistence Per Day3675ESI10336 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 675 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7168 | 31593 | 53531001 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 5 | Day |  |  |  | 0 | 1125 | 146.25 | 1271.25 | 2021-06-28 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | NO description on LEM however it appears that it is all travel time to mobilize in to the job. Sent email to NMB requesting more detail | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44385 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge716831593Subsistence Per Day51125 | Northern Mat & Bridge716831593Subsistence Per Day51125ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1125 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7169 | 31585 R1 | 53531001 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 5 | Day |  |  |  | 0 | 1125 | 146.25 | 1271.25 | 2021-06-29 | 0 | ESI10627 | 44452 | 67 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  | Email approval sent from W.Ouimet to NMB < Mon 7/5/2021 7:26 PM > |  | Approved |  |  | Travel and standby time for Jason and Cutler. Travel to Thunder Bay, wait on and receive Covid tests. Myself, Aaron and Dylan worked on site. Essentially I was wrangling Kawartha trucks about 5KM’s from site. Aaron Jones was unloading trucks at the laydown pad. Dylan escorted Andre into KM17 with the excavator and then assisted Aaron with unloading trucks and getting them turned around to head out ***COVID-19 Protocols in Effect*** | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44388 |  | 14 | 44382 | [5 empty] | William Ouimet | 10 | Northern Mat & Bridge716931585 R1Subsistence Per Day51125 | Northern Mat & Bridge716931585 R1Subsistence Per Day51125ESI10627 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 1125 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6066 | AGCE-20210129-1 | 53511111 | Access | 0 | Supervisor | 79.96 | 0.5 | Hr |  |  | 0 | 0 | 39.98 | 5.1974 | 45.1774 | 2021-01-29 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andy N, removed |  | Approved |  |  | Sand michhipicoten turn off, Harbour Rd to Dore Lake Road | 11 | F135-F150 | Harbour Road / Dore Lake Road | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6066AGCE-20210129-1Supervisor0.539.98 | AG Chapman Enterprises6066AGCE-20210129-1Supervisor0.539.98AGCE-2021-01-30 | [5 empty] | 1 | 39.98 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6067 | AGCE-20210201-2 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-02-01 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andy N, not eligible, Local |  | Approved |  |  | Sanded roads: Michipicoten Harbour Rd, Dore Lake Road, Trembley Flats Rd | 11 | F160-F164 | Trembley Falls Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6067AGCE-20210201-2Supervisor179.96 | AG Chapman Enterprises6067AGCE-20210201-2Supervisor179.96AGCE-2021-02-10 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6341 | AGCE-20210114-01-R1 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-01-29 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | Is treated sand in the contract? If not where are they getting it from? |  | Approved |  |  | Sanding Tremblay Flats road with treated sand. 2 TON treated sand. | 11 |  | MFN | 0 |  |  | 54 | 44328 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6341AGCE-20210114-01-R1Supervisor179.96 | AG Chapman Enterprises6341AGCE-20210114-01-R1Supervisor179.96AGCE-2021-01-30 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6363 | AGCE-20210116-1 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-01-16 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Sanding Trembley Flats road with treated sand | 11 |  | Trembley Flats Rd | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6363AGCE-20210116-1Supervisor179.96 | AG Chapman Enterprises6363AGCE-20210116-1Supervisor179.96AGCE-2021-01-30 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6364 | AGCE-20210120-1 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-01-20 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Sanding roads: Dore, Harbour. Note Chapman was told they had to use treated sand from reserve resources. | 11 |  | MFN - Harbour Rd 1, 2, 3, 4, 5 | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6364AGCE-20210120-1Supervisor179.96 | AG Chapman Enterprises6364AGCE-20210120-1Supervisor179.96AGCE-2021-01-30 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6365 | AGCE-20210121-1 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-01-21 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA Phil S |  | Approved |  |  | D6 dozer clear Dore Lake Road 7 am to 4 pm. LOA for Phil Swanson | 11 | F149-F135 | Dore Lake Road | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6365AGCE-20210121-1Supervisor179.96 | AG Chapman Enterprises6365AGCE-20210121-1Supervisor179.96AGCE-2021-01-30 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6377 | AGCE-20210206-2 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-02-06 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Track Harbour Rd 2 | 11 |  | Harbour Rd 2 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6377AGCE-20210206-2Supervisor179.96 | AG Chapman Enterprises6377AGCE-20210206-2Supervisor179.96AGCE-2021-02-10 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6380 | AGCE-20210208-1 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-02-08 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S |  | Approved |  |  | Walkk dzr from Harbour Rd 1 to Harbour Rd 2, plow and track rd | 11 | F150-F151 | Harbour Rd's | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6380AGCE-20210208-1Supervisor179.96 | AG Chapman Enterprises6380AGCE-20210208-1Supervisor179.96AGCE-2021-02-10 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6383 | AGCE-20210209-1 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-02-09 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S |  | Approved |  |  | Plowed and tracked Harb Rd 2 | 11 | F152-F154 | Harbour Rd 2 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6383AGCE-20210209-1Supervisor179.96 | AG Chapman Enterprises6383AGCE-20210209-1Supervisor179.96AGCE-2021-02-10 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6386 | AGCE-20210210-1 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-02-10 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Open up and track Harbour Rd 1, 3, 4, 5 | 11 | F150-F160 | Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6386AGCE-20210210-1Supervisor179.96 | AG Chapman Enterprises6386AGCE-20210210-1Supervisor179.96AGCE-2021-02-10 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6389 | AGCE-20210211-1 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-02-11 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D |  | Approved |  |  | Graded Dore, Harbour Rd | 11 |  | Dore, Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6389AGCE-20210211-1Supervisor179.96 | AG Chapman Enterprises6389AGCE-20210211-1Supervisor179.96AGCE-2021-02-11-20 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6394 | AGCE-20210212-2 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-02-12 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Widen Roads Dore Lake and then float to Hensen Road | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6394AGCE-20210212-2Supervisor179.96 | AG Chapman Enterprises6394AGCE-20210212-2Supervisor179.96AGCE-2021-02-11-20 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6396 | AGCE-20210213-1 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-02-13 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Cleared and wiiden Hensen Road | 11 | F119-F134 | Hensen Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6396AGCE-20210213-1Supervisor179.96 | AG Chapman Enterprises6396AGCE-20210213-1Supervisor179.96AGCE-2021-02-11-20 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6400 | AGCE-20210214-1 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-02-14 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Open up road and truck turnarounds Harbour Rd 2, 3, 4, 5 | 11 |  | Harbour Rd 2, 3, 4, 5 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6400AGCE-20210214-1Supervisor179.96 | AG Chapman Enterprises6400AGCE-20210214-1Supervisor179.96AGCE-2021-02-11-20 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6405 | AGCE-20210215-2 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-02-15 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Clear roads and scrape ice Hensen Road | 11 | F112-F117 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6405AGCE-20210215-2Supervisor179.96 | AG Chapman Enterprises6405AGCE-20210215-2Supervisor179.96AGCE-2021-02-11-20 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6413 | AGCE-20210217-1 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-02-17 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Scott M |  | Approved |  |  | Back blade Habour Rd 2 | 11 | F152-F154 | Harbour Rd 2 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6413AGCE-20210217-1Supervisor179.96 | AG Chapman Enterprises6413AGCE-20210217-1Supervisor179.96AGCE-2021-02-11-20 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6422 | AGCE-20210219-1 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-02-19 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Back blade hills, widen rds, plowed to Km 6 | 11 |  | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6422AGCE-20210219-1Supervisor179.96 | AG Chapman Enterprises6422AGCE-20210219-1Supervisor179.96AGCE-2021-02-11-20 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6428 | AGCE-20210220-1 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-02-20 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Widen Dore Rd and clear turn arounds | 11 |  | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6428AGCE-20210220-1Supervisor179.96 | AG Chapman Enterprises6428AGCE-20210220-1Supervisor179.96AGCE-2021-02-11-20 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6431 | AGCE-20210221-1 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-02-21 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Push snow on Harbour Rd 2 | 11 | F150-F157 | Harbour Rd 2 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6431AGCE-20210221-1Supervisor179.96 | AG Chapman Enterprises6431AGCE-20210221-1Supervisor179.96AGCE-2021-02-21-28 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6434 | AGCE-20210222-1 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-02-22 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Plowing High Falls Rd | 11 | F172-F211 | High Falls Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6434AGCE-20210222-1Supervisor179.96 | AG Chapman Enterprises6434AGCE-20210222-1Supervisor179.96AGCE-2021-02-21-28 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6501 | AGCE-20210304-05-R1 | 53511111 | Access | 1 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-03-04 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E LOA for Paul K |  | Approved |  |  | Reg Rd maint and repair on dore | 11 | F135-F149 | Dore lake Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6501AGCE-20210304-05-R1Supervisor179.96 | AG Chapman Enterprises6501AGCE-20210304-05-R1Supervisor179.96AGCE-2021-03-01-10 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6505 | AGCE-20210305-01 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-03-05 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Joe B |  | Approved |  |  | Dozing abnd back blading the road HR 4 | 11 | F154 | Harbour Rd 4 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6505AGCE-20210305-01Supervisor179.96 | AG Chapman Enterprises6505AGCE-20210305-01Supervisor179.96AGCE-2021-03-01-10 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6409 | AGCE-20210216-2 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-02-16 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Widen roads Dore Lake East and West. | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6409AGCE-20210216-2Supervisor179.96 | AG Chapman Enterprises6409AGCE-20210216-2Supervisor179.96AGCE-2021-02-11-20 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6418 | AGCE-20210218-2 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-02-18 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Push snow on High Falls road | 11 | F172-F211 | High Falls Rd 1, 2, 3 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6418AGCE-20210218-2Supervisor179.96 | AG Chapman Enterprises6418AGCE-20210218-2Supervisor179.96AGCE-2021-02-11-20 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6445 | AGCE-20210224-01-R1 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-02-24 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D |  | Approved |  |  | Graded Trembley rd to Harbour rd 1 | 11 | F128-F164 | Trembley Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6445AGCE-20210224-01-R1Supervisor179.96 | AG Chapman Enterprises6445AGCE-20210224-01-R1Supervisor179.96AGCE-2021-02-21-28 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7054 | AGCE-20210314-07 | 53511111 | Access | 0 | Supervisor | 79.96 | 1 | Hr |  |  | 0 | 0 | 79.96 | 10.3948 | 90.3548 | 2021-03-14 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Walk Dozer out to Trembley Rd from Dore area to be demobed to Salt Ste | 11 | F135 | Dore | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7054AGCE-20210314-07Supervisor179.96 | AG Chapman Enterprises7054AGCE-20210314-07Supervisor179.96AGCE-2021-03-11-20 | [5 empty] | 1 | 79.96 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6401 | AGCE-20210214-2 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-14 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | No work description, may need to bill throough kabi | 11 |  | Dore Lake Rd E & W | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6401AGCE-20210214-2LOA1250 | AG Chapman Enterprises6401AGCE-20210214-2LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6365 | AGCE-20210121-1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-01-21 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA Phil S |  | Approved |  |  | D6 dozer clear Dore Lake Road 7 am to 4 pm. LOA for Phil Swanson | 11 | F149-F135 | Dore Lake Road | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6365AGCE-20210121-1LOA1250 | AG Chapman Enterprises6365AGCE-20210121-1LOA1250AGCE-2021-01-30 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6061 | AGCE-20210205-1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-05 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | This will need to be billed out through Kabi to capture escort time |  | Pending |  |  | Walk dozer from High Falls Rd to Michipicoten Habour Rd 4 | 11 | F150 | Harbour Rd 4 | 0 | [10 empty] | 11 | AG Chapman Enterprises6061AGCE-20210205-1LOA1250 | AG Chapman Enterprises6061AGCE-20210205-1LOA1250 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6376 | AGCE-20210206-1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-06 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S |  | Approved |  |  | Back Blade harbour rd 4 | 11 |  | Harbour Rd 4 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6376AGCE-20210206-1LOA1250 | AG Chapman Enterprises6376AGCE-20210206-1LOA1250AGCE-2021-02-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6380 | AGCE-20210208-1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-08 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S |  | Approved |  |  | Walkk dzr from Harbour Rd 1 to Harbour Rd 2, plow and track rd | 11 | F150-F151 | Harbour Rd's | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6380AGCE-20210208-1LOA1250 | AG Chapman Enterprises6380AGCE-20210208-1LOA1250AGCE-2021-02-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6383 | AGCE-20210209-1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-09 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S |  | Approved |  |  | Plowed and tracked Harb Rd 2 | 11 | F152-F154 | Harbour Rd 2 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6383AGCE-20210209-1LOA1250 | AG Chapman Enterprises6383AGCE-20210209-1LOA1250AGCE-2021-02-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6384 | AGCE-20210209-2 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-09 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D |  | Approved |  |  | Grade roads from office to trembley rd and return | 11 |  | Trembley Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6384AGCE-20210209-2LOA1250 | AG Chapman Enterprises6384AGCE-20210209-2LOA1250AGCE-2021-02-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6386 | AGCE-20210210-1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-10 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Open up and track Harbour Rd 1, 3, 4, 5 | 11 | F150-F160 | Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6386AGCE-20210210-1LOA1250 | AG Chapman Enterprises6386AGCE-20210210-1LOA1250AGCE-2021-02-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6387 | AGCE-20210210-2 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-10 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D |  | Approved |  |  | Grade Harbour Rd 1, Dore Rd, | 11 |  | Harbour Rd 1, Dore Rd, | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6387AGCE-20210210-2LOA1250 | AG Chapman Enterprises6387AGCE-20210210-2LOA1250AGCE-2021-02-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6388 | AGCE-20210210-3 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-10 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S |  | Approved |  |  | Plowed and tracked Harbour Rd | 11 | F152-F154 | Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6388AGCE-20210210-3LOA1250 | AG Chapman Enterprises6388AGCE-20210210-3LOA1250AGCE-2021-02-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6367 | AGCE-20210121-2 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-01-21 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | 1 LOA on ticket for Robert Eshkibad |  | Approved |  |  | D6 clear road of snow, back blade and pack snow. | 11 | F146-F148 | Harbour Road 4 | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6367AGCE-20210121-2LOA1250 | AG Chapman Enterprises6367AGCE-20210121-2LOA1250AGCE-2021-01-30 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6392 | AGCE-20210211-4 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-11 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N Supervisor and truck removed |  | Approved |  |  | Open roads and parking at F150 | 11 | F150-F151 | Harbour Rd 1 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6392AGCE-20210211-4LOA1250 | AG Chapman Enterprises6392AGCE-20210211-4LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6397 | AGCE-20210213-2 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-13 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Cllear and widen Harbour Rd 3, 4, 5 | 11 |  | Harbour Rd 3, 4, 5 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6397AGCE-20210213-2LOA1250 | AG Chapman Enterprises6397AGCE-20210213-2LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6398 | AGCE-20210213-3 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-13 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D Supervisor and truck removed |  | Approved |  |  | Grading Dore Rd, Trembley Rd, Harbour Rd | 11 | F119-F160 | Dore Lake Rd, Trembley Rd, Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6398AGCE-20210213-3LOA1250 | AG Chapman Enterprises6398AGCE-20210213-3LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6399 | AGCE-20210213-4 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-13 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Widen Dore Lake Rd | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6399AGCE-20210213-4LOA1250 | AG Chapman Enterprises6399AGCE-20210213-4LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6400 | AGCE-20210214-1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-14 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Open up road and truck turnarounds Harbour Rd 2, 3, 4, 5 | 11 |  | Harbour Rd 2, 3, 4, 5 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6400AGCE-20210214-1LOA1250 | AG Chapman Enterprises6400AGCE-20210214-1LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6402 | AGCE-20210214-3 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-14 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C Supervisor and truck removed |  | Approved |  |  | Plow and open up roads Hensnen Rd | 11 | F119-F134 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6402AGCE-20210214-3LOA1250 | AG Chapman Enterprises6402AGCE-20210214-3LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6405 | AGCE-20210215-2 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-15 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Clear roads and scrape ice Hensen Road | 11 | F112-F117 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6405AGCE-20210215-2LOA1250 | AG Chapman Enterprises6405AGCE-20210215-2LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6406 | AGCE-20210215-3 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-15 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E Supervisor and truck removed |  | Approved |  |  | Widen roads at F146-F149 Dore | 11 | F146-F149 | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6406AGCE-20210215-3LOA1250 | AG Chapman Enterprises6406AGCE-20210215-3LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6409 | AGCE-20210216-2 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-16 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Widen roads Dore Lake East and West. | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6409AGCE-20210216-2LOA1250 | AG Chapman Enterprises6409AGCE-20210216-2LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6411 | AGCE-20210216-4 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-16 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D Supervisor and truck removed |  | Approved |  |  | Grade Trembley Rd | 11 | F160-F164 | Trembley Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6411AGCE-20210216-4LOA1250 | AG Chapman Enterprises6411AGCE-20210216-4LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6414 | AGCE-20210217-2 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-17 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E Supervisor and truck removed |  | Approved |  |  | Plowed and widened Dore lake Rd | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6414AGCE-20210217-2LOA1250 | AG Chapman Enterprises6414AGCE-20210217-2LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6416 | AGCE-20210217-4 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-17 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C Supervisor and truck removed |  | Approved |  |  | Scrape roads on Hensen | 11 | F118-F133 | Hensen Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6416AGCE-20210217-4LOA1250 | AG Chapman Enterprises6416AGCE-20210217-4LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6417 | AGCE-20210217-5 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-17 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D Supervisor and truck removed |  | Approved |  |  | Grading High Falls Road 1, 2, 3, 5 | 11 | F172-F211 | High Falls Road 1, 2, 3, 5 | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6417AGCE-20210217-5LOA1250 | AG Chapman Enterprises6417AGCE-20210217-5LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6419 | AGCE-20210218-3 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-18 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E Supervisor and truck removed |  | Approved |  |  | Pushed out Dore Lake Rd and back bladed the turn around | 11 |  | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6419AGCE-20210218-3LOA1250 | AG Chapman Enterprises6419AGCE-20210218-3LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6420 | AGCE-20210218-4 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-18 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C Supervisor and truck removed |  | Approved |  |  | Scraped Hensen Rd East | 11 | F117-F134 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6420AGCE-20210218-4LOA1250 | AG Chapman Enterprises6420AGCE-20210218-4LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6422 | AGCE-20210219-1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-19 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Back blade hills, widen rds, plowed to Km 6 | 11 |  | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6422AGCE-20210219-1LOA1250 | AG Chapman Enterprises6422AGCE-20210219-1LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6423 | AGCE-20210219-2 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-19 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N Supervisor and truck removed |  | Approved |  |  | Cleared all roads at Dore Lake | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6423AGCE-20210219-2LOA1250 | AG Chapman Enterprises6423AGCE-20210219-2LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6425 | AGCE-20210219-4 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-19 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C Supervisor and truck removed |  | Approved |  |  | Scraped hensen rd | 11 | F117-F135 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6425AGCE-20210219-4LOA1250 | AG Chapman Enterprises6425AGCE-20210219-4LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6426 | AGCE-20210219-5 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-19 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D Supervisor and truck removed |  | Approved |  |  | Grade harbour rd | 11 | F148-F159 | Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6426AGCE-20210219-5LOA1250 | AG Chapman Enterprises6426AGCE-20210219-5LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6428 | AGCE-20210220-1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-20 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Widen Dore Rd and clear turn arounds | 11 |  | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6428AGCE-20210220-1LOA1250 | AG Chapman Enterprises6428AGCE-20210220-1LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6430 | AGCE-20210220-4 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-20 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C Supervisor and truck removed |  | Approved |  |  | Scraped road on Hensen E | 11 | F115-F133 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6430AGCE-20210220-4LOA1250 | AG Chapman Enterprises6430AGCE-20210220-4LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6389 | AGCE-20210211-1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-11 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D |  | Approved |  |  | Graded Dore, Harbour Rd | 11 |  | Dore, Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6389AGCE-20210211-1LOA1250 | AG Chapman Enterprises6389AGCE-20210211-1LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6394 | AGCE-20210212-2 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-12 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Widen Roads Dore Lake and then float to Hensen Road | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6394AGCE-20210212-2LOA1250 | AG Chapman Enterprises6394AGCE-20210212-2LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6396 | AGCE-20210213-1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-13 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Cleared and wiiden Hensen Road | 11 | F119-F134 | Hensen Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6396AGCE-20210213-1LOA1250 | AG Chapman Enterprises6396AGCE-20210213-1LOA1250AGCE-2021-02-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6432 | AGCE-20210221-2 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-21 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C Superviosr and truck removed |  | Approved |  |  | Scraped Hensen Rd | 11 | F117-F133 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6432AGCE-20210221-2LOA1250 | AG Chapman Enterprises6432AGCE-20210221-2LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6433 | AGCE-20210221-3 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-21 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E Supervisor and truck removed |  | Approved |  |  | push snow from Km 6 to Km 9.5 Dore Rd | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6433AGCE-20210221-3LOA1250 | AG Chapman Enterprises6433AGCE-20210221-3LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6434 | AGCE-20210222-1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-22 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Plowing High Falls Rd | 11 | F172-F211 | High Falls Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6434AGCE-20210222-1LOA1250 | AG Chapman Enterprises6434AGCE-20210222-1LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6436 | AGCE-20210223-2 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-23 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Steve B Supervisor and truck removed |  | Approved |  |  | Cleaned and plowed Dore Lake Rd | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6436AGCE-20210223-2LOA1250 | AG Chapman Enterprises6436AGCE-20210223-2LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6437 | AGCE-20210223-3 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-23 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E Supervisor and truck removed |  | Approved |  |  | Plowed Dore Lake Rd | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6437AGCE-20210223-3LOA1250 | AG Chapman Enterprises6437AGCE-20210223-3LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6438 | AGCE-20210223-4 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-23 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S Supervisor and truck removed |  | Approved |  |  | Grade Trembley Rd, Harbour Rd, Dore Lake Rd | 11 | F128-F164 | Trembley Road, Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6438AGCE-20210223-4LOA1250 | AG Chapman Enterprises6438AGCE-20210223-4LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6439 | AGCE-20210223-5 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-23 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N Supervisor and truck removed |  | Approved |  |  | Pow and widen Harbour Rd and Dore Lake Rd | 11 |  | Dore Lake Rd, Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6439AGCE-20210223-5LOA1250 | AG Chapman Enterprises6439AGCE-20210223-5LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6440 | AGCE-20210223-6 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-23 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C Supervisor and truck removed |  | Approved |  |  | Scraped Hensen Rd East | 11 | F115-F133 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6440AGCE-20210223-6LOA1250 | AG Chapman Enterprises6440AGCE-20210223-6LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6442 | AGCE-20210223-8 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-23 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andrew B Supervisor and truck removed |  | Approved |  |  | Plow and level off roads on Dore Lake Rd | 11 | F135-F149 | Dore Lake Rd East | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6442AGCE-20210223-8LOA1250 | AG Chapman Enterprises6442AGCE-20210223-8LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6445 | AGCE-20210224-01-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-24 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D |  | Approved |  |  | Graded Trembley rd to Harbour rd 1 | 11 | F128-F164 | Trembley Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6445AGCE-20210224-01-R1LOA1250 | AG Chapman Enterprises6445AGCE-20210224-01-R1LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6446 | AGCE-20210224-02-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-24 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | back Blade and touch up michtpicoten Harbour roads 1234 | 11 | F150-F159 | Harbour Roads | 0 |  |  | 54 | 44252 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6446AGCE-20210224-02-R1LOA1250 | AG Chapman Enterprises6446AGCE-20210224-02-R1LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6447 | AGCE-20210224-03 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-24 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | Supervisor removed |  | Approved |  |  | Plowed to F187 access to tower site Road 9 access, F206, F207, F208 | 11 | F206-F209 | High Falls | 0 |  |  | 54 | 44252 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6447AGCE-20210224-03LOA1250 | AG Chapman Enterprises6447AGCE-20210224-03LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6449 | AGCE-20210224-04 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-24 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Scraped Hensen Road east. Need to pull Rock truck off and bill to Kabi | 11 | F135-F149 | Hensen Road E | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6449AGCE-20210224-04LOA1250 | AG Chapman Enterprises6449AGCE-20210224-04LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6450 | AGCE-20210224-05 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-24 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Plowed Dore Lake Rd 8.5 KM west to end of road | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 54 | 44252 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6450AGCE-20210224-05LOA1250 | AG Chapman Enterprises6450AGCE-20210224-05LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6451 | AGCE-20210224-07-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-24 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andrew B, Split exc time off to Kabi |  | Approved |  |  | Clean up banks around km 2, Pack holes in road with snow, widen road. | 11 | F135 | Dore Lake Rd | 0 |  |  | 54 | 44345 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6451AGCE-20210224-07-R1LOA1250 | AG Chapman Enterprises6451AGCE-20210224-07-R1LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6452 | AGCE-20210225-01-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-25 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Scrape and widen roads in Hensen | 11 | F117-F133 | Hensen Rd | 0 |  |  | 54 | 44345 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6452AGCE-20210225-01-R1LOA1250 | AG Chapman Enterprises6452AGCE-20210225-01-R1LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6455 | AGCE-20210225-05 | 53511111 | Access | 1 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-25 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andrew B |  | Approved |  |  | Plowed Dore lake Rd | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 54 | 44345 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6455AGCE-20210225-05LOA1250 | AG Chapman Enterprises6455AGCE-20210225-05LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6456 | AGCE-20210225-02 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-25 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Back blade to Dore west | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 54 | 44345 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6456AGCE-20210225-02LOA1250 | AG Chapman Enterprises6456AGCE-20210225-02LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6453 | AGCE-20210225-03 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-25 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Stephen B |  | Approved |  |  | Clean snow off road and fix up hill. | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 54 | 44345 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6453AGCE-20210225-03LOA1250 | AG Chapman Enterprises6453AGCE-20210225-03LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6454 | AGCE-20210225-04 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-25 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Plowed and widened harbour rd 1, 2 ,3 ,4 5 | 11 | F150-F159 | Harbour Rd | 0 |  |  | 54 | 44345 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6454AGCE-20210225-04LOA1250 | AG Chapman Enterprises6454AGCE-20210225-04LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6457 | AGCE-20210226-01-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-26 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S, no LOA for Andy N |  | Approved |  |  | Grade and sand roads dore lake road - Trembley | 11 | F161 | Trembley Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6457AGCE-20210226-01-R1LOA1250 | AG Chapman Enterprises6457AGCE-20210226-01-R1LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6458 | AGCE-20210226-02-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-26 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Scrape and repair Hensen rd | 11 | F119-F134 | Hensen Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6458AGCE-20210226-02-R1LOA1250 | AG Chapman Enterprises6458AGCE-20210226-02-R1LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6459 | AGCE-20210226-03-R1 | 53511111 | Access | 1 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-26 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andrew B |  | Approved |  |  | Touch and plow rds on Dore Lake Rd | 11 | F135-F149 | Dore lake Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6459AGCE-20210226-03-R1LOA1250 | AG Chapman Enterprises6459AGCE-20210226-03-R1LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6461 | AGCE-20210226-05-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-26 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Ploe and push back bank on Dore Lake Rd | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6461AGCE-20210226-05-R1LOA1250 | AG Chapman Enterprises6461AGCE-20210226-05-R1LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6462 | AGCE-20210226-06-R1 | 53511111 | Access | 1 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-26 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Stephen B |  | Approved |  |  | Clean and fix Dore Lake Road | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6462AGCE-20210226-06-R1LOA1250 | AG Chapman Enterprises6462AGCE-20210226-06-R1LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6466 | AGCE-20210227-03-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-27 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Back blade and push snow. | 11 | F172-F211 | Harbour Rd 1 - 5 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6466AGCE-20210227-03-R1LOA1250 | AG Chapman Enterprises6466AGCE-20210227-03-R1LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6467 | AGCE-20210227-04-R1 | 53511111 | Access | 0 | LOA | 250 | 2 | Day |  |  | 0 | 0 | 500 | 65 | 565 | 2021-02-27 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Greg B Loa for Stephen B |  | Approved |  |  | Fix roads and back blade Dore Lake Rd | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6467AGCE-20210227-04-R1LOA2500 | AG Chapman Enterprises6467AGCE-20210227-04-R1LOA2500AGCE-2021-02-21-28 | [5 empty] | 1 | 500 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6469 | AGCE-20210227-06-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-27 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | Mike Woods LOA |  | Approved |  |  | Plow roads dore east | 11 | F135-F149 | Dore lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6469AGCE-20210227-06-R1LOA1250 | AG Chapman Enterprises6469AGCE-20210227-06-R1LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6470 | AGCE-20210228-01-R1 | 53511111 | Access | 0 | LOA | 250 | 2 | Day |  |  | 0 | 0 | 500 | 65 | 565 | 2021-02-28 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Push snow and repair Hills, scrape and fix dore, Plow road and clear parking spots | 11 | F135-F149 | Dore lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6470AGCE-20210228-01-R1LOA2500 | AG Chapman Enterprises6470AGCE-20210228-01-R1LOA2500AGCE-2021-02-21-28 | [5 empty] | 1 | 500 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6471 | AGCE-20210228-02-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-28 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Mike W |  | Approved |  |  | Creape roads and push snow Hensen Rd | 11 | F119-F134 | Hensen Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6471AGCE-20210228-02-R1LOA1250 | AG Chapman Enterprises6471AGCE-20210228-02-R1LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6472 | AGCE-20210228-03-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-02-28 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E No truck on ticket |  | Approved |  |  | Plow roads on Dore Lake | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6472AGCE-20210228-03-R1LOA1250 | AG Chapman Enterprises6472AGCE-20210228-03-R1LOA1250AGCE-2021-02-21-28 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6523 | AGCE-20210311-01 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-11 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andrew B |  | Approved |  |  | Grade and push back banks | 11 | F160 | Trembley Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6523AGCE-20210311-01LOA1250 | AG Chapman Enterprises6523AGCE-20210311-01LOA1250AGCE-2021-03-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6474 | AGCE-20210301-02-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Joe B |  | Approved |  |  | Grade Dore LK Rd to to Km 4 | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6474AGCE-20210301-02-R1LOA1250 | AG Chapman Enterprises6474AGCE-20210301-02-R1LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6473 | AGCE-20210301-01-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Mike W |  | Approved |  |  | Push snow to km 5 on Hensen rd | 11 | F119-F135 | Hensen Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6473AGCE-20210301-01-R1LOA1250 | AG Chapman Enterprises6473AGCE-20210301-01-R1LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6475 | AGCE-20210301-03-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Adam D No truck on ticket |  | Approved |  |  | Grade harbour to trembley | 11 | F148-F160 | Harbour Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6475AGCE-20210301-03-R1LOA1250 | AG Chapman Enterprises6475AGCE-20210301-03-R1LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6479 | AGCE-20210301-05.1-R1 | 53511111 | Access | 1 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Back Blade Rds on Dore | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6479AGCE-20210301-05.1-R1LOA1250 | AG Chapman Enterprises6479AGCE-20210301-05.1-R1LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6480 | AGCE-20210301-06-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Ben R |  | Approved |  |  | Push snow and clean turn arounds on Dore lk rd | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6480AGCE-20210301-06-R1LOA1250 | AG Chapman Enterprises6480AGCE-20210301-06-R1LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6481 | AGCE-20210301-07-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N LOA for Alfred C Same dozer billed 14.5 hours, might have been partial night shift |  | Approved |  |  | Plow Harbour Rd 1, 2, 3 and fix hills, partial night shift for dozer | 11 |  | Harbour Rd 1, 2, 3 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6481AGCE-20210301-07-R1LOA1250 | AG Chapman Enterprises6481AGCE-20210301-07-R1LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6483 | AGCE-20210302-02-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-02 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Joe B |  | Approved |  |  | Graded main rd to Dore Lk Rd km 4 | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6483AGCE-20210302-02-R1LOA1250 | AG Chapman Enterprises6483AGCE-20210302-02-R1LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6485 | AGCE-20210302-04-R1 | 53511111 | Access | 1 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-02 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Paul K |  | Approved |  |  | Back blade Dore Lk Rd West to east | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6485AGCE-20210302-04-R1LOA1250 | AG Chapman Enterprises6485AGCE-20210302-04-R1LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6488 | AGCE-20210302-07-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-02 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Back blade from Km 4 to km 8.5 Dore Lk Rd | 11 | F135-F149 | Dore Lake Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6488AGCE-20210302-07-R1LOA1250 | AG Chapman Enterprises6488AGCE-20210302-07-R1LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6489 | AGCE-20210302-08-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-02 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Wided roads and clear parking | 11 | F150-F159 | Harbour Rd 1, 2 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6489AGCE-20210302-08-R1LOA1250 | AG Chapman Enterprises6489AGCE-20210302-08-R1LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6492 | AGCE-20210303-03-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-03 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Ben R No truck on ticket |  | Approved |  |  | Push snow and banks on Hensen east | 11 | F119-F134 | Hensen Road | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6492AGCE-20210303-03-R1LOA1250 | AG Chapman Enterprises6492AGCE-20210303-03-R1LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6493 | AGCE-20210303-04-R1 | 53511111 | Access | 1 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-03 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E |  | Approved |  |  | Pack snow on to roads to fix and track pack | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6493AGCE-20210303-04-R1LOA1250 | AG Chapman Enterprises6493AGCE-20210303-04-R1LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6494 | AGCE-20210303-05-R1 | 53511111 | Access | 1 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-03 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Paul K |  | Approved |  |  | Plowed Rds and packed roads on Dore | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6494AGCE-20210303-05-R1LOA1250 | AG Chapman Enterprises6494AGCE-20210303-05-R1LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6495 | AGCE-20210303-06-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-03 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Joe B |  | Approved |  |  | Graded roads in harbour to dore km 1 to km 4.5 | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6495AGCE-20210303-06-R1LOA1250 | AG Chapman Enterprises6495AGCE-20210303-06-R1LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6497 | AGCE-20210303-08-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-03 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Roland N |  | Approved |  |  | Maint and fix rds on Harbour rd 1, 2 | 11 | F150-F154 | Harbour Rd 1,2 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6497AGCE-20210303-08-R1LOA1250 | AG Chapman Enterprises6497AGCE-20210303-08-R1LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6499 | AGCE-20210303-10-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-03 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Greg B |  | Approved |  |  | Plowed and did regular rd maint on Dore Lk Rd | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6499AGCE-20210303-10-R1LOA1250 | AG Chapman Enterprises6499AGCE-20210303-10-R1LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6500 | AGCE-20210304-02-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-04 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Joe B |  | Approved |  |  | Widen roads on Harbour | 11 | F156-F160 | Harbour Rd 4, 5 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6500AGCE-20210304-02-R1LOA1250 | AG Chapman Enterprises6500AGCE-20210304-02-R1LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6501 | AGCE-20210304-05-R1 | 53511111 | Access | 1 | LOA | 250 | 2 | Day |  |  | 0 | 0 | 500 | 65 | 565 | 2021-03-04 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert E LOA for Paul K |  | Approved |  |  | Reg Rd maint and repair on dore | 11 | F135-F149 | Dore lake Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6501AGCE-20210304-05-R1LOA2500 | AG Chapman Enterprises6501AGCE-20210304-05-R1LOA2500AGCE-2021-03-01-10 | [5 empty] | 1 | 500 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6505 | AGCE-20210305-01 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-05 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Joe B |  | Approved |  |  | Dozing abnd back blading the road HR 4 | 11 | F154 | Harbour Rd 4 | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6505AGCE-20210305-01LOA1250 | AG Chapman Enterprises6505AGCE-20210305-01LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6509 | AGCE-20210306-02 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-06 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Joe B |  | Approved |  |  | Grade and support on Trembley Rd | 11 | F160 | Trembley Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6509AGCE-20210306-02LOA1250 | AG Chapman Enterprises6509AGCE-20210306-02LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6511 | AGCE-20210306-04 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-06 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Chris C |  | Approved |  |  | Walk dozer out to be floated awat, Pick up eco diesel | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6511AGCE-20210306-04LOA1250 | AG Chapman Enterprises6511AGCE-20210306-04LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6513 | AGCE-20210307-01 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-07 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Sanded Rds Dore Lk - Harbour Rd - Trembley Rd | 11 | F128-F160 | Trembley Rd - Dore Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6513AGCE-20210307-01LOA1250 | AG Chapman Enterprises6513AGCE-20210307-01LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7048 | AGCE-20210312-04 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-12 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andrew Blackmore |  | Approved |  |  | Graded Washboard | 11 | F161-F164 | Trembley Flats Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7048AGCE-20210312-04LOA1250 | AG Chapman Enterprises7048AGCE-20210312-04LOA1250AGCE-2021-03-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7049 | AGCE-20210313-01 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-13 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Grading of Michipicoten and Trembley Rds | 11 | F150-F164 | Michipicoten to Trembley | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7049AGCE-20210313-01LOA1250 | AG Chapman Enterprises7049AGCE-20210313-01LOA1250AGCE-2021-03-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7052 | AGCE-20210314-04 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-14 |  |  |  |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Pending |  |  | Graded roads, not enough description sent back to Chapman | 11 |  |  | 0 | [10 empty] | 11 | AG Chapman Enterprises7052AGCE-20210314-04LOA1250 | AG Chapman Enterprises7052AGCE-20210314-04LOA1250 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7053 | AGCE-20210314-05 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-14 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert M, turns out he is not local |  | Approved |  |  | Grade roads as per email from Mandy | 11 | F120-F160 | Harbour, Trembley, Dore | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7053AGCE-20210314-05LOA1250 | AG Chapman Enterprises7053AGCE-20210314-05LOA1250AGCE-2021-03-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7054 | AGCE-20210314-07 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-14 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Walk Dozer out to Trembley Rd from Dore area to be demobed to Salt Ste | 11 | F135 | Dore | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7054AGCE-20210314-07LOA1250 | AG Chapman Enterprises7054AGCE-20210314-07LOA1250AGCE-2021-03-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6529 | AGCE-20210316-05 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-16 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Greg B Escort time removed |  | Approved |  |  | Move d6 to Dore Lk for support | 11 |  | Dore | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6529AGCE-20210316-05LOA1250 | AG Chapman Enterprises6529AGCE-20210316-05LOA1250AGCE-2021-03-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7057 | AGCE-20210318-02 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-18 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert M |  | Approved |  |  | Grading harbour Road in morning and afternoon | 11 | F150-F159 | Harbour Road | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7057AGCE-20210318-02LOA1250 | AG Chapman Enterprises7057AGCE-20210318-02LOA1250AGCE-2021-03-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6535 | AGCE-20210319-01 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-19 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert M No truck on ticket |  | Approved |  |  | Grade Harbour Rd | 11 | F150-F159 | Harbour Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6535AGCE-20210319-01LOA1250 | AG Chapman Enterprises6535AGCE-20210319-01LOA1250AGCE-2021-03-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6536 | AGCE-20210319-02 | 53511111 | Access | 0 | LOA | 250 | 2 | Day |  |  | 0 | 0 | 500 | 65 | 565 | 2021-03-19 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Ben R Escort time removed |  | Approved |  |  | Walked D5 from east to west dore km 7 morning shift | 11 | F135-F149 | Dore Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6536AGCE-20210319-02LOA2500 | AG Chapman Enterprises6536AGCE-20210319-02LOA2500AGCE-2021-03-11-20 | [5 empty] | 1 | 500 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6538 | AGCE-20210320-01 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-20 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Back blade Dore Lk rd km 6.5 | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6538AGCE-20210320-01LOA1250 | AG Chapman Enterprises6538AGCE-20210320-01LOA1250AGCE-2021-03-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6476 | AGCE-20210301-04-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-01 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert M |  | Approved |  |  | Plowed roads on Dore Lk Rd | 11 | F1353-F149 | Dore Lake Road | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6476AGCE-20210301-04-R1LOA1250 | AG Chapman Enterprises6476AGCE-20210301-04-R1LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6498 | AGCE-20210303-09-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-03 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert M |  | Approved |  |  | Maint rd on Dore Lk | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6498AGCE-20210303-09-R1LOA1250 | AG Chapman Enterprises6498AGCE-20210303-09-R1LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6486 | AGCE-20210302-05-R1 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-02 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert M No truck on ticket |  | Approved |  |  | Plow and rd maint | 11 | F135-F149 | Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6486AGCE-20210302-05-R1LOA1250 | AG Chapman Enterprises6486AGCE-20210302-05-R1LOA1250AGCE-2021-03-01-10 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7140 | AGCE-20210315-06 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-15 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Robert mcCabe |  | Approved |  |  | Grading Hensen Road | 11 | F118-F127 | Hensen Road | 0 |  |  | 54 | 44398 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7140AGCE-20210315-06LOA1250 | AG Chapman Enterprises7140AGCE-20210315-06LOA1250AGCE-2021-03-11-20 | [5 empty] | 1 | 250 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7047 | AGCE-20210311-02 | 53511111 | Access | 0 | LOA | 250 | 1 | Day |  |  | 0 | 0 | 250 | 32.5 | 282.5 | 2021-03-11 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | No LOA for Andrew B as it was already billed out on this day |  | Approved |  |  | Grading Washboard | 11 | F150 | Harbour Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7047AGCE-20210311-02LOA1250 | AG Chapman Enterprises7047AGCE-20210311-02LOA1250AGCE-2021-03-11-20 | [5 empty] | 1 | 250 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1322 | KL-20200317-7 | 53510812 | Access | 0 | Screened Sand | 10.5 | 18 | Hourly |  |  |  |  | 189 | 24.57 | 213.57 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | RV-40002 SPREAD GRAVEL; HAUL GRAVEL IN SOFT SOPT ACROSS HONI LINE AND TO GAIN ACCESS OVER ROCK IN EXISTING ENTRANCE RD | 8 | E-077 to E-091 | Blue Cedar W | 0 | 43911 |  | 42 | 43915 |  | Sand Road/ Access |  |  |  | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7Screened Sand18189 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7Screened Sand18189OEWT-PA3-LEM | [5 empty] | 1 | 189 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5207 | KL-20210103-5 | 53511111 | Access | 0 | Screened Sand | 10.5 | 15 | Hourly |  |  |  |  | 157.5 | 20.475 | 177.975 | 2021-01-03 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load of sand from White River town pit/ sanding hills and corners on hensen road from hwy to 17km with existing material as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 |  | White River Town Pit |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5207KL-20210103-5Screened Sand15157.5 | KABI LAKE FOREST PRODUCTS LTD5207KL-20210103-5Screened Sand15157.5OEWT-PA13-LEM | [5 empty] | 1 | 157.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5283 | KL-20210109-6 | 53511111 | Access | 0 | Screened Sand | 10.5 | 18 | Hourly |  |  |  |  | 189 | 24.57 | 213.57 | 2021-01-09 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Take 1 load of screened sand from town pit, and finish sanding Hensen Rd to km 17. Floats with existing sand as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44211 |  | 15 | 44219 |  | Town Pit |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5283KL-20210109-6Screened Sand18189 | KABI LAKE FOREST PRODUCTS LTD5283KL-20210109-6Screened Sand18189OEWT-PA13-LEM | [5 empty] | 1 | 189 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5363 | KL-20210114-9 | 53511111 | Access | 0 | Screened Sand | 10.5 | 19.5 | Hourly |  |  |  |  | 204.75 | 26.6175 | 231.3675 | 2021-01-14 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load screened sand from town pit and finished sanding Hensen Road to 17km with existing sand as per Valard/ Excavator cleaning up @ F119 for Sand | 11 | F119-F134 | Hensen Road | 0 | 44218 |  | 15 | 44224 |  | From Town Pit |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5363KL-20210114-9Screened Sand19.5204.75 | KABI LAKE FOREST PRODUCTS LTD5363KL-20210114-9Screened Sand19.5204.75OEWT-PA13-LEM | [5 empty] | 1 | 204.75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5413 | KL-20210117-1 | 53510911 | Access | 0 | Screened Sand | 10.5 | 18 | Hourly |  |  |  |  | 189 | 24.57 | 213.57 | 2021-01-17 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding hills on 600 Road between km 52 and Km 22, float truck was stuck on 47km hill | 9 | E091-E102 | 600 Road | 0 | 44216 |  | 53 | 44229 |  | White River Town Pit |  |  |  | Clint Maerz | 09 | KABI LAKE FOREST PRODUCTS LTD5413KL-20210117-1Screened Sand18189 | KABI LAKE FOREST PRODUCTS LTD5413KL-20210117-1Screened Sand18189OEWT-PA13-LEM | [5 empty] | 1 | 189 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5746 | KL-20210203-3 | 53511011 | Access | 0 | Screened Sand | 10.5 | 18 | Hourly |  |  |  |  | 189 | 24.57 | 213.57 | 2021-02-03 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track excavator out and in, sand Paint Lake Road 2. Lay corduroy and cap road near WC 11159.00 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44243 |  | 50 | 44246 |  | Town Pit |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5746KL-20210203-3Screened Sand18189 | KABI LAKE FOREST PRODUCTS LTD5746KL-20210203-3Screened Sand18189OEWT-PA14-Lem-R1 | [5 empty] | 1 | 189 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6048 | KL-20210225-16 | 53511111 | Access | 0 | Screened Sand | 10.5 | 18 | Hourly |  |  |  |  | 189 | 24.57 | 213.57 | 2021-02-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load of screeded sand from Town Pit/Haul 2 loads of screened sand from MacIntyre Pit/Sand hills & corners to km 17 on Hensen, drive back to White River | 11 | F119-F134 | Hensen Road | 0 | 44256 |  | 56 | 44262 |  | From town pit |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6048KL-20210225-16Screened Sand18189 | KABI LAKE FOREST PRODUCTS LTD6048KL-20210225-16Screened Sand18189OEWT-PA14-Lem-R1 | [5 empty] | 1 | 189 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1322 | KL-20200317-7 | 53510812 | Access | 0 | Pit Run | 7.5 | 319.3 | Hourly |  |  |  |  | 2394.75 | 311.3175 | 2706.0675 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | RV-40002 SPREAD GRAVEL; HAUL GRAVEL IN SOFT SOPT ACROSS HONI LINE AND TO GAIN ACCESS OVER ROCK IN EXISTING ENTRANCE RD | 8 | E-077 to E-091 | Blue Cedar W | 0 | 43911 |  | 42 | 43915 |  | Fill Material |  |  |  | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7Pit Run319.32394.75 | KABI LAKE FOREST PRODUCTS LTD1322KL-20200317-7Pit Run319.32394.75OEWT-PA3-LEM | [5 empty] | 1 | 2394.75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 908 | KL-20200121-3 | 53510711 | Access | 0 | 3rd Party Services | 1 | 1808.26 | Each |  |  |  |  | 1808.26 | 235.0738 | 2043.3338 | 2020-01-21 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Subcontractor: Used loader to plow raod. Stooped at locked gate to boyscout camp. Contacted property owner to have gate unlocked. | 7 | D-009 to D-017 | Three Finger Lake | 0 |  |  | 17 | 43859 | CR-20200121-1 | Clearing Road |  |  |  | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD908KL-20200121-33rd Party Services1808.261808.26 | KABI LAKE FOREST PRODUCTS LTD908KL-20200121-33rd Party Services1808.261808.26OEWT-PA1-LEM | [5 empty] | 1 | 1808.26 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 911 | KL-20200122-4 | 53510711 | Access | 0 | 3rd Party Services | 1 | 1726.86 | Each |  |  |  |  | 1726.86 | 224.4918 | 1951.3518 | 2020-01-22 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Push Open Road over Muskeg into Powerline | 7 | D-018 to D-031 | Pie River | 0 |  |  | 17 | 43859 | CR-20200122-1 | Push Open Road Over Muskeg into Powerline |  |  |  | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD911KL-20200122-43rd Party Services1726.861726.86 | KABI LAKE FOREST PRODUCTS LTD911KL-20200122-43rd Party Services1726.861726.86OEWT-PA1-LEM | [5 empty] | 1 | 1726.86 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 913 | KL-20200122-6 | 53510711 | Access | 0 | 3rd Party Services | 1 | 667.64 | Each |  |  |  |  | 667.64 | 86.7932 | 754.4332 | 2020-01-22 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plowing raod as far as conditions allowed | 7 | D-018 to D-031 | Pie River | 0 |  |  | 17 | 43859 | CR-20200122-3 | Plowing raod as far as conditions allowed |  |  |  | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD913KL-20200122-63rd Party Services667.64667.64 | KABI LAKE FOREST PRODUCTS LTD913KL-20200122-63rd Party Services667.64667.64OEWT-PA1-LEM | [5 empty] | 1 | 667.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 921 | KL-20200124-3 | 53510711 | Access | 0 | 3rd Party Services | 1 | 991.8 | Each |  |  |  |  | 991.8 | 128.934 | 1120.734 | 2020-01-24 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Completed Three Finger Lake Access | 7 | D-009 to D-017 | Three Finger Lake | 0 |  |  | 17 | 43859 | CR-20200124-1 | Completed Three Finger Lake Access |  |  |  | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD921KL-20200124-33rd Party Services991.8991.8 | KABI LAKE FOREST PRODUCTS LTD921KL-20200124-33rd Party Services991.8991.8OEWT-PA1-LEM | [5 empty] | 1 | 991.8 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 922 | KL-20200124-4 | 53510711 | Access | 0 | 3rd Party Services | 1 | 2061.38 | Each |  |  |  |  | 2061.38 | 267.9794 | 2329.3594 | 2020-01-24 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open Pie River West Road Access | 7 | D-018 to D-031 | Pie River | 0 |  |  | 17 | 43859 | CR-20200124-2 | Open Pie River Road Access |  |  |  | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD922KL-20200124-43rd Party Services2061.382061.38 | KABI LAKE FOREST PRODUCTS LTD922KL-20200124-43rd Party Services2061.382061.38OEWT-PA1-LEM | [5 empty] | 1 | 2061.38 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 926 | KL-20200125-2-R1 | 53510711 | Access | 0 | 3rd Party Services | 1 | 2121.04 | Each |  |  |  |  | 2121.04 | 275.7352 | 2396.7752 | 2020-01-25 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Flag to drop off Cres Dozer to Open road | 7 | D-032 to D-055 | Black River | 0 |  |  | 17 | 43859 | CR-20200125-2 |  |  |  |  | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD926KL-20200125-2-R13rd Party Services2121.042121.04 | KABI LAKE FOREST PRODUCTS LTD926KL-20200125-2-R13rd Party Services2121.042121.04OEWT-PA1-LEM | [5 empty] | 1 | 2121.04 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 931 | KL-20200125-7 | 53510711 | Access | 0 | 3rd Party Services | 1 | 2441.04 | Each |  |  |  |  | 2441.04 | 317.3352 | 2758.3752 | 2020-01-25 | 1 | OEWT-PA1-LEM | 43861 | 4 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clearing Roadways at Pie River West | 7 | D-018 to D-031 | Pie River | 0 |  |  | 17 | 43859 | CR-20200125-7 | Clearing Roads At Pie River West |  |  |  | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD931KL-20200125-73rd Party Services2441.042441.04 | KABI LAKE FOREST PRODUCTS LTD931KL-20200125-73rd Party Services2441.042441.04OEWT-PA1-LEM | [5 empty] | 1 | 2441.04 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 936 | KL-20200127-2-R1 | 53510711 | Access | 0 | 3rd Party Services | 1 | 2286 | Each |  |  |  |  | 2286 | 297.18 | 2583.18 | 2020-01-27 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clearing Snow off roadway: Peninsula Road | 7 | D-001 to Highway 17 | Peninsula Road | 0 | 43857 |  | 17 | 43861 | CR-20200127-2 | Clearing Snow Off Roadway |  |  |  | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD936KL-20200127-2-R13rd Party Services22862286 | KABI LAKE FOREST PRODUCTS LTD936KL-20200127-2-R13rd Party Services22862286OEWT-PA2-LEM-R1 | [5 empty] | 1 | 2286 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 938 | KL-20200127-4 | 53510711 | Access | 0 | 3rd Party Services | 1 | 774.5 | Each |  |  |  |  | 774.5 | 100.685 | 875.185 | 2020-01-27 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clearing snow at Black River West, floated D6 from Black River to Peninsula Road | 7 | D-032 to D-055 | Black River | 0 | 43858 |  | 17 | 43861 | CR-20200127-4 | clearing snow from raod |  |  |  | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD938KL-20200127-43rd Party Services774.5774.5 | KABI LAKE FOREST PRODUCTS LTD938KL-20200127-43rd Party Services774.5774.5OEWT-PA2-LEM-R1 | [5 empty] | 1 | 774.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 952 | KL-20200129-8-R1 | 53510711 | Access | 0 | 3rd Party Services | 1 | 452.36 | Each |  |  |  |  | 452.36 | 58.8068 | 511.1668 | 2020-01-29 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clearing snow at Peninsula Rd. | 7 | D-001 to Highway 17 | Peninsula Road | 0 | 43864 |  | 17 | 43865 | CR-20200129-8 |  |  |  |  | David Mercer | 07 | KABI LAKE FOREST PRODUCTS LTD952KL-20200129-8-R13rd Party Services452.36452.36 | KABI LAKE FOREST PRODUCTS LTD952KL-20200129-8-R13rd Party Services452.36452.36OEWT-PA2-LEM-R1 | [5 empty] | 1 | 452.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 995 | KL-20200203-3 | 53510711 | Access | 0 | 3rd Party Services | 1 | 462.95 | Each |  |  |  |  | 462.95 | 60.1835 | 523.1335 | 2020-02-03 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cleared road at Pie River East | 7 | D-009 to D-017 | Three Finger Lake | 0 | 43868 |  | 43 | 43889 | CR-20200203-3 | Cleared road at pie river East |  |  |  | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD995KL-20200203-33rd Party Services462.95462.95 | KABI LAKE FOREST PRODUCTS LTD995KL-20200203-33rd Party Services462.95462.95OEWT-PA2-LEM-R1 | [5 empty] | 1 | 462.95 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1005 | KL-20200205-2 | 53510711 | Access | 0 | 3rd Party Services | 1 | 80.09 | Each |  |  |  |  | 80.09 | 10.4117 | 90.5017 | 2020-02-05 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float drop off of 336 excavator, signage | 7 | D-018 to D-031 | Pie River | 0 | 43872 |  | 42 | 43882 | CR-20200204-2 | Clearing snow |  |  |  | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1005KL-20200205-23rd Party Services80.0980.09 | KABI LAKE FOREST PRODUCTS LTD1005KL-20200205-23rd Party Services80.0980.09OEWT-PA2-LEM-R1 | [5 empty] | 1 | 80.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1005 | KL-20200205-2 | 53510711 | Access | 0 | 3rd Party Services | 1 | 320.36 | Each |  |  |  |  | 320.36 | 41.6468 | 362.0068 | 2020-02-05 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float drop off of 336 excavator, signage | 7 | D-018 to D-031 | Pie River | 0 | 43872 |  | 42 | 43882 | CR-20200205-2 | Fixing soft spots on Pie River West road |  |  |  | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1005KL-20200205-23rd Party Services320.36320.36 | KABI LAKE FOREST PRODUCTS LTD1005KL-20200205-23rd Party Services320.36320.36OEWT-PA2-LEM-R1 | [5 empty] | 1 | 320.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1027 | KL-20200207-8 | 53510711 | Access | 0 | 3rd Party Services | 1 | 1543.23 | Each |  |  |  |  | 1543.23 | 200.6199 | 1743.8499 | 2020-02-07 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Traffic control; float picking up brusher | 7 | D-018 to D-031 | Pie River | 0 | 43872 |  | 42 | 43882 | CR-20200207-8 | Repairing roadway for corduroy, winter road |  |  |  | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1027KL-20200207-83rd Party Services1543.231543.23 | KABI LAKE FOREST PRODUCTS LTD1027KL-20200207-83rd Party Services1543.231543.23OEWT-PA2-LEM-R1 | [5 empty] | 1 | 1543.23 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1049 | KL-20200211-9 | 53510811 | Access | 0 | 3rd Party Services | 1 | 833.32 | Each |  |  |  |  | 833.32 | 108.3316 | 941.6516 | 2020-02-11 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clearing snow from North Regan Road | 8 | E-017 to E-024 | North Reagan Road | 0 | 43875 |  | 42 | 43882 | CR-20200211-9 | Clearing snow from North Regan Road |  |  |  | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1049KL-20200211-93rd Party Services833.32833.32 | KABI LAKE FOREST PRODUCTS LTD1049KL-20200211-93rd Party Services833.32833.32OEWT-PA2-LEM-R1 | [5 empty] | 1 | 833.32 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1056 | KL-20200212-1-R1 | 53510811 | Access | 0 | 3rd Party Services | 1 | 2012 | Each |  |  |  |  | 2012 | 261.56 | 2273.56 | 2020-02-12 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow to open existing road 2.8km | 8 | E-017 to E-024 | North Regan Road | 0 | 43878 |  | 42 | 43882 | CR-20200212-1 | Plow to open existing road 2.8km |  |  |  | Glen Greening | 08 | KABI LAKE FOREST PRODUCTS LTD1056KL-20200212-1-R13rd Party Services20122012 | KABI LAKE FOREST PRODUCTS LTD1056KL-20200212-1-R13rd Party Services20122012OEWT-PA2-LEM-R1 | [5 empty] | 1 | 2012 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1067 | KL-20200213-10 | 53510811 | Access | 0 | 3rd Party Services | 1 | 2339 | Each |  |  |  |  | 2339 | 304.07 | 2643.07 | 2020-02-13 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | CR-10064 Open road from highway, load Kabi float truck | 8 | E-017 to E-024 | North Regan Road | 0 | 43878 |  | 43 | 43889 | CR-20200213-10 | Open road from highway in 2.8km. Finished load on float for shipping to Green Lakes on Kabi float. |  |  |  | Dean MacArthur | 08 | KABI LAKE FOREST PRODUCTS LTD1067KL-20200213-103rd Party Services23392339 | KABI LAKE FOREST PRODUCTS LTD1067KL-20200213-103rd Party Services23392339OEWT-PA2-LEM-R1 | [5 empty] | 1 | 2339 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1068 | KL-20200213-11 | 53510711 | Access | 0 | 3rd Party Services | 1 | 437.95 | Each |  |  |  |  | 437.95 | 56.9335 | 494.8835 | 2020-02-13 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | CR-10065 Plow field open on black river road | 7 | D-032 to D-055 | Black River | 0 | 43878 |  | 43 | 43889 | CR-20200213-11 | CR-10065 Plow field open on black river road |  |  |  | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1068KL-20200213-113rd Party Services437.95437.95 | KABI LAKE FOREST PRODUCTS LTD1068KL-20200213-113rd Party Services437.95437.95OEWT-PA2-LEM-R1 | [5 empty] | 1 | 437.95 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1081 | KL-20200215-2 | 53510711 | Access | 0 | 3rd Party Services | 1 | 1609.45 | Each |  |  |  |  | 1609.45 | 209.2285 | 1818.6785 | 2020-02-15 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clear snow from Three Finger Lake Rd. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 43881 |  | 43 | 43889 | CR-20200215-2 | Clear Snow |  |  |  | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1081KL-20200215-23rd Party Services1609.451609.45 | KABI LAKE FOREST PRODUCTS LTD1081KL-20200215-23rd Party Services1609.451609.45OEWT-PA2-LEM-R1 | [5 empty] | 1 | 1609.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1082 | KL-20200216-3 | 53510711 | Access | 0 | 3rd Party Services | 1 | 743.55 | Each |  |  |  |  | 743.55 | 96.6615 | 840.2115 | 2020-02-16 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Deliver gravel and rip rap, plow snow from Pic River West | 7 | D-018 to D-031 | Pie River | 0 | 43881 |  | 43 | 43889 | CR-20200215-5 | Plow Snow with 950k loader |  |  |  | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1082KL-20200216-33rd Party Services743.55743.55 | KABI LAKE FOREST PRODUCTS LTD1082KL-20200216-33rd Party Services743.55743.55OEWT-PA2-LEM-R1 | [5 empty] | 1 | 743.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1084 | KL-20200217-2 | 53510811 | Access | 0 | 3rd Party Services | 1 | 2339 | Each |  |  |  |  | 2339 | 304.07 | 2643.07 | 2020-02-17 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Complete Green Lakes Road and started opening up Blue Cedar Road | 8 | E-059-E-061 | Green Lakes Road | 0 | 43881 |  | 43 | 43889 | CR-20200214-10 | Open road from highway to Honi Line |  |  |  | Dean MacArthur | 08 | KABI LAKE FOREST PRODUCTS LTD1084KL-20200217-23rd Party Services23392339 | KABI LAKE FOREST PRODUCTS LTD1084KL-20200217-23rd Party Services23392339OEWT-PA2-LEM-R1 | [5 empty] | 1 | 2339 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1084 | KL-20200217-2 | 53510811 | Access | 0 | 3rd Party Services | 1 | 2095 | Each |  |  |  |  | 2095 | 272.35 | 2367.35 | 2020-02-17 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Complete Green Lakes Road and started opening up Blue Cedar Road | 8 | E-059-E-061 | Green Lakes Road | 0 | 43881 |  | 43 | 43889 | CR-20200215-3 | Open up road from Hwy 17 to EWT |  |  |  | Dean MacArthur | 08 | KABI LAKE FOREST PRODUCTS LTD1084KL-20200217-23rd Party Services20952095 | KABI LAKE FOREST PRODUCTS LTD1084KL-20200217-23rd Party Services20952095OEWT-PA2-LEM-R1 | [5 empty] | 1 | 2095 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1084 | KL-20200217-2 | 53510811 | Access | 0 | 3rd Party Services | 1 | 1768 | Each |  |  |  |  | 1768 | 229.84 | 1997.84 | 2020-02-17 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Complete Green Lakes Road and started opening up Blue Cedar Road | 8 | E-059-E-061 | Green Lakes Road | 0 | 43881 |  | 43 | 43889 | CR-20200216-3 | Open road from Hwy 17 to EWT |  |  |  | Dean MacArthur | 08 | KABI LAKE FOREST PRODUCTS LTD1084KL-20200217-23rd Party Services17681768 | KABI LAKE FOREST PRODUCTS LTD1084KL-20200217-23rd Party Services17681768OEWT-PA2-LEM-R1 | [5 empty] | 1 | 1768 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1084 | KL-20200217-2 | 53510811 | Access | 0 | 3rd Party Services | 1 | 1305 | Each |  |  |  |  | 1305 | 169.65 | 1474.65 | 2020-02-17 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Complete Green Lakes Road and started opening up Blue Cedar Road | 8 | E-059-E-061 | Green Lakes Road | 0 | 43881 |  | 43 | 43889 | CR-20200217-2 | Complete Green Lakes Road Opening Blue Cedar |  |  |  | Dean MacArthur | 08 | KABI LAKE FOREST PRODUCTS LTD1084KL-20200217-23rd Party Services13051305 | KABI LAKE FOREST PRODUCTS LTD1084KL-20200217-23rd Party Services13051305OEWT-PA2-LEM-R1 | [5 empty] | 1 | 1305 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1099 | KL-20200218-3 | 53510811 | Access | 0 | 3rd Party Services | 1 | 2339 | Each |  |  |  |  | 2339 | 304.07 | 2643.07 | 2020-02-18 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open road to Hone. Finish at Hone and clean up on the way out | 8 |  | Blue Cedar Road | 0 | 43882 |  | 43 | 43889 | CR-20200218-3 | Finish opening road at hne |  |  |  | Dean MacArthur | 08 | KABI LAKE FOREST PRODUCTS LTD1099KL-20200218-33rd Party Services23392339 | KABI LAKE FOREST PRODUCTS LTD1099KL-20200218-33rd Party Services23392339OEWT-PA2-LEM-R1 | [5 empty] | 1 | 2339 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1111 | KL-20200220-8 | 53510711 | Access | 0 | 3rd Party Services | 1 | 1013.73 | Each |  |  |  |  | 1013.73 | 131.7849 | 1145.5149 | 2020-02-20 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Flag to pick up grinder and log loader | 7 | D-009 to D-017 | Three Finger Lake | 0 | 43885 |  | 43 | 43889 | CR-20200219-5 | CR-10088 Plow Road |  |  |  | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1111KL-20200220-83rd Party Services1013.731013.73 | KABI LAKE FOREST PRODUCTS LTD1111KL-20200220-83rd Party Services1013.731013.73OEWT-PA2-LEM-R1 | [5 empty] | 1 | 1013.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1133 | KL-20200223-7 | 53510711 | Access | 0 | 3rd Party Services | 1 | 301.77 | Each |  |  |  |  | 301.77 | 39.2301 | 341.0001 | 2020-02-23 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow and maintain road | 7 | D-032 to D-055 | Black River | 0 | 43887 |  | 43 | 43889 | CR-20200221-13 | plough snow and touch up access raod |  |  |  | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1133KL-20200223-73rd Party Services301.77301.77 | KABI LAKE FOREST PRODUCTS LTD1133KL-20200223-73rd Party Services301.77301.77OEWT-PA2-LEM-R1 | [5 empty] | 1 | 301.77 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1134 | KL-20200223-8 | 53510711 | Access | 0 | 3rd Party Services | 1 | 301.77 | Each |  |  |  |  | 301.77 | 39.2301 | 341.0001 | 2020-02-23 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow and clean access roads. Also pick up and place GeoTech | 7 | D-018 to D-031 | Pie River | 0 | 43887 |  | 43 | 43889 | CR-20200221-12 | Plow snow and touch up road. CR-10097 |  |  |  | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1134KL-20200223-83rd Party Services301.77301.77 | KABI LAKE FOREST PRODUCTS LTD1134KL-20200223-83rd Party Services301.77301.77OEWT-PA2-LEM-R1 | [5 empty] | 1 | 301.77 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1134 | KL-20200223-8 | 53510711 | Access | 0 | 3rd Party Services | 1 | 201.18 | Each |  |  |  |  | 201.18 | 26.1534 | 227.3334 | 2020-02-23 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow and clean access roads. Also pick up and place GeoTech | 7 | D-018 to D-031 | Pie River | 0 | 43887 |  | 43 | 43889 | CR-20200221-11 | Plow snow and touch up road. CR-10096 |  |  |  | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1134KL-20200223-83rd Party Services201.18201.18 | KABI LAKE FOREST PRODUCTS LTD1134KL-20200223-83rd Party Services201.18201.18OEWT-PA2-LEM-R1 | [5 empty] | 1 | 201.18 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1142 | KL-20200222-9 | 53510711 | Access | 0 | 3rd Party Services | 1 | 301.77 | Each |  |  |  |  | 301.77 | 39.2301 | 341.0001 | 2020-02-22 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dropped off drill, plowed snow and touched up access road with grader | 7 | D-009 to D-017 | Three Finger Lake | 0 | 43888 |  | 43 | 43890 | CR-20200221-7 |  |  |  |  | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1142KL-20200222-93rd Party Services301.77301.77 | KABI LAKE FOREST PRODUCTS LTD1142KL-20200222-93rd Party Services301.77301.77OEWT-PA2-LEM-R1 | [5 empty] | 1 | 301.77 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1157 | KL-20200225-7-R1 | 53510711 | Access | 0 | 3rd Party Services | 1 | 115 | Each |  |  |  |  | 115 | 14.95 | 129.95 | 2020-02-25 | 1 | OEWT-PA2-LEM-R1 | 43894 | 5 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sand road for haul trucks, fill +2M cuts on existing roadway | 7 | D-009 to D-017 | Three Finger Lake | 0 | 43889 |  | 43 | 43890 | CR-20200225-8 | sand road for haul trucks. CR-10102 |  |  |  | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1157KL-20200225-7-R13rd Party Services115115 | KABI LAKE FOREST PRODUCTS LTD1157KL-20200225-7-R13rd Party Services115115OEWT-PA2-LEM-R1 | [5 empty] | 1 | 115 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1282 | KL-20200313-9-R1 | 53510711 | Access | 0 | 3rd Party Services | 1 | 644.5 | Each |  |  |  |  | 644.5 | 83.785 | 728.285 | 2020-03-13 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | CR-10142 Plow road, fuel and parking areas | 7 | D-032 to D-055 | Black River | 0 | 43908 |  | 42 | 43914 | CR-20200313-1 | Plow Black River West fuel and parking areas. CR-10142 |  |  |  | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1282KL-20200313-9-R13rd Party Services644.5644.5 | KABI LAKE FOREST PRODUCTS LTD1282KL-20200313-9-R13rd Party Services644.5644.5OEWT-PA3-LEM | [5 empty] | 1 | 644.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1283 | KL-20200313-10-R1 | 53510711 | Access | 0 | 3rd Party Services | 1 | 201.18 | Each |  |  |  |  | 201.18 | 26.1534 | 227.3334 | 2020-03-13 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade road at Pic River West. CR-10145 | 7 | D-018 to D-031 | Pie River | 0 | 43908 |  | 42 | 43914 | CR-20200313-2 | Grade Road at Pic River West |  |  |  | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1283KL-20200313-10-R13rd Party Services201.18201.18 | KABI LAKE FOREST PRODUCTS LTD1283KL-20200313-10-R13rd Party Services201.18201.18OEWT-PA3-LEM | [5 empty] | 1 | 201.18 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1284 | KL-20200313-11 | 53510711 | Access | 0 | 3rd Party Services | 1 | 301.77 | Each |  |  |  |  | 301.77 | 39.2301 | 341.0001 | 2020-03-13 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Peninsula Road. CR-10143 | 7 | D-001 to Highway 17 | Peninsula Road | 0 | 43908 |  | 42 | 43914 | CR-20200313-3 | Grade Peninsula Road, CR-10143 |  |  |  | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1284KL-20200313-113rd Party Services301.77301.77 | KABI LAKE FOREST PRODUCTS LTD1284KL-20200313-113rd Party Services301.77301.77OEWT-PA3-LEM | [5 empty] | 1 | 301.77 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1287 | KL-20200315-1 | 53510711 | Access | 0 | 3rd Party Services | 1 | 385 | Each |  |  |  |  | 385 | 50.05 | 435.05 | 2020-03-15 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow road, corduroy road, and haul gravel at Umbatta Falls. CR-10153, CR-10146, CR-10147 | 7 | D-056 to D-073 | Umbatta Falls | 0 | 43908 |  | 42 | 43915 | CR-20200313-4 | Use D5 to plow road from hwy 17 in to D-056. CR-10147 |  |  |  | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1287KL-20200315-13rd Party Services385385 | KABI LAKE FOREST PRODUCTS LTD1287KL-20200315-13rd Party Services385385OEWT-PA3-LEM | [5 empty] | 1 | 385 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1308 | KL-20200316-2 | 53510711 | Access | 0 | 3rd Party Services | 1 | 1403.41 | Each |  |  |  |  | 1403.41 | 182.4433 | 1585.8533 | 2020-03-14 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading and plowing Three Finger Lake Rd. CR-10144, CR-10154, CR-10156. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 43908 |  | 42 | 43915 | CR-20200315-3 | Complete plowing into D-017. CR-10154 |  |  |  | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1308KL-20200316-23rd Party Services1403.411403.41 | KABI LAKE FOREST PRODUCTS LTD1308KL-20200316-23rd Party Services1403.411403.41OEWT-PA3-LEM | [5 empty] | 1 | 1403.41 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1308 | KL-20200316-2 | 53510711 | Access | 0 | 3rd Party Services | 1 | 1646 | Each |  |  |  |  | 1646 | 213.98 | 1859.98 | 2020-03-14 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading and plowing Three Finger Lake Rd. CR-10144, CR-10154, CR-10156. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 43908 |  | 42 | 43915 | CR-20200316-1 | Plow road into D-014. CR-10156 |  |  |  | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1308KL-20200316-23rd Party Services16461646 | KABI LAKE FOREST PRODUCTS LTD1308KL-20200316-23rd Party Services16461646OEWT-PA3-LEM | [5 empty] | 1 | 1646 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1308 | KL-20200316-2 | 53510711 | Access | 0 | 3rd Party Services | 1 | 89.5 | Each |  |  |  |  | 89.5 | 11.635 | 101.135 | 2020-03-14 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading and plowing Three Finger Lake Rd. CR-10144, CR-10154, CR-10156. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 43908 |  | 42 | 43915 | CR-20200313-7 | Grade Three Finger Road. CR-10144 |  |  |  | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1308KL-20200316-23rd Party Services89.589.5 | KABI LAKE FOREST PRODUCTS LTD1308KL-20200316-23rd Party Services89.589.5OEWT-PA3-LEM | [5 empty] | 1 | 89.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1317 | KL-20200317-2-R1 | 53510711 | Access | 0 | 3rd Party Services | 1 | 1661.69 | Each |  |  |  |  | 1661.69 | 216.0197 | 1877.7097 | 2020-03-17 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Assess the roads required @ D-010 & D-015, CR-10149 Float D6 Cat Dozer from Heron Bay yard to Three Finger Lk to plow road, scrape hills cleaned road to D-016. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 43911 |  | 42 | 43917 | CR-20200309-2-R1 | Float D6 Cat Dozer from Heron Bay yard to Three Finger Lk to plow road, scrape hills cleaned road to D-016. |  |  |  | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1317KL-20200317-2-R13rd Party Services1661.691661.69 | KABI LAKE FOREST PRODUCTS LTD1317KL-20200317-2-R13rd Party Services1661.691661.69OEWT-PA3-LEM | [5 empty] | 1 | 1661.69 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1335 | KL-20200319-9 | 53510711 | Access | 0 | 3rd Party Services | 1 | 1617.86 | Each |  |  |  |  | 1617.86 | 210.3218 | 1828.1818 | 2020-03-19 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | CR-10164 Grading snow at Black River East | 7 | D-032 to D-055 | Black River | 0 | 43913 |  | 42 | 43915 | CR-20200319-5 | CR-10164 GRADING SNOW AT BLACK RIVER EAST |  |  |  | Glen Greening | 07 | KABI LAKE FOREST PRODUCTS LTD1335KL-20200319-93rd Party Services1617.861617.86 | KABI LAKE FOREST PRODUCTS LTD1335KL-20200319-93rd Party Services1617.861617.86OEWT-PA3-LEM | [5 empty] | 1 | 1617.86 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1346 | KL-20200320-6 | 53510711 | Access | 0 | 3rd Party Services | 1 | 684 | Each |  |  |  |  | 684 | 88.92 | 772.92 | 2020-03-20 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | FLAG TO DROP OFF SKIDDER FROM ALDER | 7 | D-009 to D-017 | Three Finger Lake | 0 | 43915 |  | 43 | 43951 | CR-20200320-1 | Snow removal on Three Finger Lake |  |  |  | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1346KL-20200320-63rd Party Services684684 | KABI LAKE FOREST PRODUCTS LTD1346KL-20200320-63rd Party Services684684OEWT PA4-LEM-R1 | [5 empty] | 1 | 684 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1350 | KL-20200320-10 | 53510711 | Access | 0 | 3rd Party Services | 1 | 979 | Each |  |  |  |  | 979 | 127.27 | 1106.27 | 2020-03-20 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | CR-10165 SNOW REMOVAL | 7 | D-032 to D-055 | Black River | 0 | 43915 |  | 46 | 43919 | CR-20200320-2 | SNOW REMOVAL - GRADER |  |  |  | Dave Ofukany | 07 | KABI LAKE FOREST PRODUCTS LTD1350KL-20200320-103rd Party Services979979 | KABI LAKE FOREST PRODUCTS LTD1350KL-20200320-103rd Party Services979979OEWT-PA3-LEM | [5 empty] | 1 | 979 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1355 | KL-20200322-4 | 53510711 | Access | 0 | 3rd Party Services | 1 | 1575.09 | Each |  |  |  |  | 1575.09 | 204.7617 | 1779.8517 | 2020-03-22 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | DROP OFF D6 DOZER AT CAMP 36 ROAD near Umbatta. Towers D-065 to D-066. CR-10178 | 7 | D-065 to D-066 | Umbatta Falls- Camp 36 | 0 | 43915 |  | 46 | 43919 | CR-20200322-5 | CR-10178 DOZER OPENING 'CAMP 36' ROAD BY ROUSE LAKE |  |  |  | Dave Ofukany | 07 | KABI LAKE FOREST PRODUCTS LTD1355KL-20200322-43rd Party Services1575.091575.09 | KABI LAKE FOREST PRODUCTS LTD1355KL-20200322-43rd Party Services1575.091575.09OEWT-PA3-LEM | [5 empty] | 1 | 1575.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1356 | KL-20200322-5 | 53510712 | Access | 0 | 3rd Party Services | 1 | 1291.14 | Each |  |  |  |  | 1291.14 | 167.8482 | 1458.9882 | 2020-03-22 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | CR 10173, CR-10174 FIXING ENTRANCE | 7 | D-056 to D-073 | Umbatta Falls | 0 | 43915 |  | 46 | 43919 | CR-20200322-4 | CR-10174 Fixed Entrance at Umbatta Falls |  |  |  | Dave Ofukany | 07 | KABI LAKE FOREST PRODUCTS LTD1356KL-20200322-53rd Party Services1291.141291.14 | KABI LAKE FOREST PRODUCTS LTD1356KL-20200322-53rd Party Services1291.141291.14OEWT-PA3-LEM | [5 empty] | 1 | 1291.14 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1359 | KL-20200322-8 | 53510811 | Access | 0 | 3rd Party Services | 1 | 908 | Each |  |  |  |  | 908 | 118.04 | 1026.04 | 2020-03-22 | 1 | OEWT-PA3-LEM | 43921 | 6 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | RV-40006 OPENING UP ROAD TO 2ND BRIDGE ON BLUE CEDAR | 8 | E-077 to E-091 | Blue Cedar Road | 0 | 43915 |  | 46 | 43919 | RV-20200322-1 | RV-40006 OPENING UP ROAD TO 2ND BRIDGE ON BLUE CEDAR |  |  |  | Dave Ofukany | 08 | KABI LAKE FOREST PRODUCTS LTD1359KL-20200322-83rd Party Services908908 | KABI LAKE FOREST PRODUCTS LTD1359KL-20200322-83rd Party Services908908OEWT-PA3-LEM | [5 empty] | 1 | 908 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1366 | KL-20200323-2 | 53510811 | Access | 0 | 3rd Party Services | 1 | 996.73 | Each |  |  |  |  | 996.73 | 129.5749 | 1126.3049 | 2020-03-23 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | RV-40007 Widening Access Road | 8 | E-077 to E-091 | Blue Cedar W | 0 | 43917 |  | 46 | 43921 | RV-20200323-1 | Widening Access road. RV-40007 |  |  |  | Dave Ofukany | 08 | KABI LAKE FOREST PRODUCTS LTD1366KL-20200323-23rd Party Services996.73996.73 | KABI LAKE FOREST PRODUCTS LTD1366KL-20200323-23rd Party Services996.73996.73OEWT PA4-LEM-R1 | [5 empty] | 1 | 996.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1370 | KL-20200323-6 | 53510711 | Access | 0 | 3rd Party Services | 1 | 2591.5 | Each |  |  |  |  | 2591.5 | 336.895 | 2928.395 | 2020-03-23 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | CR-10179 opening of Camp 36 Road (between Umbatta/Brett's Road) for access | 7 | D-64 to D-74 | Camp 36 Road | 0 | 43917 |  | 46 | 43921 | CR-20200323-1 | Opening Camp 36 Road (between Umbatta/Brett's Road) for access |  |  |  | Dave Ofukany | 07 | KABI LAKE FOREST PRODUCTS LTD1370KL-20200323-63rd Party Services2591.52591.5 | KABI LAKE FOREST PRODUCTS LTD1370KL-20200323-63rd Party Services2591.52591.5OEWT PA4-LEM-R1 | [5 empty] | 1 | 2591.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1373 | KL-20200324-3 | 53510711 | Access | 0 | 3rd Party Services | 1 | 606 | Each |  |  |  |  | 606 | 78.78 | 684.78 | 2020-03-24 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | CR-10182 Demob D6 to Heron Bay | 7 | D-009 to D-017 | Three Finger Lake | 0 | 43917 |  | 46 | 43921 | CR-20200324-3 | CR-10182 Demob D6 to Heron Bay |  |  |  | Dave Ofukany | 07 | KABI LAKE FOREST PRODUCTS LTD1373KL-20200324-33rd Party Services606606 | KABI LAKE FOREST PRODUCTS LTD1373KL-20200324-33rd Party Services606606OEWT PA4-LEM-R1 | [5 empty] | 1 | 606 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1390 | KL-20200326-8 | 53510711 | Access | 0 | 3rd Party Services | 1 | 712.55 | Each |  |  |  |  | 712.55 | 92.6315 | 805.1815 | 2020-03-26 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading road for winter access, CR-10187 | 7 | D-056 to D-073 | Umbatta Falls | 0 | 43922 |  | 45 | 43923 | CR-20200326-3 | Grading Road - CR-10187 |  |  |  | Howard Beaudet | 07 | KABI LAKE FOREST PRODUCTS LTD1390KL-20200326-83rd Party Services712.55712.55 | KABI LAKE FOREST PRODUCTS LTD1390KL-20200326-83rd Party Services712.55712.55OEWT PA4-LEM-R1 | [5 empty] | 1 | 712.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1409 | KL-20200329-3 | 53510712 | Access | 0 | 3rd Party Services | 1 | 489.5 | Each |  |  |  |  | 489.5 | 63.635 | 553.135 | 2020-03-29 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | CR-10201 Grubbing roadway | 7 | D-056 to D-073 | Umbatta Falls | 0 | 43927 |  | 45 | 43924 | CR-20200329-3 | CR-10201 Grubbing roadway |  |  |  | Howard Beaudet | 07 | KABI LAKE FOREST PRODUCTS LTD1409KL-20200329-33rd Party Services489.5489.5 | KABI LAKE FOREST PRODUCTS LTD1409KL-20200329-33rd Party Services489.5489.5OEWT PA4-LEM-R1 | [5 empty] | 1 | 489.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1414 | KL-20200330-2 | 53510712 | Access | 0 | 3rd Party Services | 1 | 320.36 | Each |  |  |  |  | 320.36 | 41.6468 | 362.0068 | 2020-03-30 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | CR-10203 Fixing Access Road and Draining off water | 7 | D-056 to D-073 | Umbatta Falls | 0 | 43928 |  |  |  | CR-20200330-2 | Fixing access road and draining water off. CR-10203 |  |  |  |  | 07 | KABI LAKE FOREST PRODUCTS LTD1414KL-20200330-23rd Party Services320.36320.36 | KABI LAKE FOREST PRODUCTS LTD1414KL-20200330-23rd Party Services320.36320.36OEWT PA4-LEM-R1 | [5 empty] | 1 | 320.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1433 | KL-20200401-3 | 53510711 | Access | 0 | 3rd Party Services | 1 | 1466.09 | Each |  |  |  |  | 1466.09 | 190.5917 | 1656.6817 | 2020-04-01 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | CR-10209 Plow snow from Camp 36 road into 8660 bridge site | 7 | D065-D066 | Camp 36 Road | 0 | 43930 |  | 43 | 43931 | CR-20200401-3 | plow snow from Camp 36 Road into 8660 bridge site |  |  |  | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1433KL-20200401-33rd Party Services1466.091466.09 | KABI LAKE FOREST PRODUCTS LTD1433KL-20200401-33rd Party Services1466.091466.09OEWT PA4-LEM-R1 | [5 empty] | 1 | 1466.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1440 | KL-20200402-1 | 53510711 | Access | 0 | 3rd Party Services | 1 | 269.18 | Each |  |  |  |  | 269.18 | 34.9934 | 304.1734 | 2020-04-02 | 1 | OEWT PA4-LEM-R1 | 43951 | 7 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | CR-10215 blade off Umbatta Fall access road | 7 | D-056 to D-073 | Umbatta Falls | 0 | 43930 |  | 43 | 43933 | CR-20200402-1 | Blade off Umbatta Falls access road. CR-10215 |  |  |  | Dean MacArthur | 07 | KABI LAKE FOREST PRODUCTS LTD1440KL-20200402-13rd Party Services269.18269.18 | KABI LAKE FOREST PRODUCTS LTD1440KL-20200402-13rd Party Services269.18269.18OEWT PA4-LEM-R1 | [5 empty] | 1 | 269.18 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1546 | KL-20200520-17 | 53510712 | Access | 0 | 3rd Party Services | 1 | 1032.73 | Each |  |  |  |  | 1032.73 | 134.2549 | 1166.9849 | 2020-05-20 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Ditching Camp 36 Road. CR-10236 | 7 | D065-D066 | Camp 36 Road | 0 | 43976 |  | 15 | 43977 | CR-20200520-6 | Ditching Road |  |  |  | Martin Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD1546KL-20200520-173rd Party Services1032.731032.73 | KABI LAKE FOREST PRODUCTS LTD1546KL-20200520-173rd Party Services1032.731032.73OEWT-PA5-LEM | [5 empty] | 1 | 1032.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1553 | KL-20200521-5 | 53510712 | Access | 0 | 3rd Party Services | 1 | 1357.09 | Each |  |  |  |  | 1357.09 | 176.4217 | 1533.5117 | 2020-05-21 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Camp 36 Road - CR-10238 | 7 | D065-D066 | Camp 36 Road | 0 | 43977 |  | 15 | 43977 | CR-20200521-1 | Grading |  |  |  | Martin Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD1553KL-20200521-53rd Party Services1357.091357.09 | KABI LAKE FOREST PRODUCTS LTD1553KL-20200521-53rd Party Services1357.091357.09OEWT-PA5-LEM | [5 empty] | 1 | 1357.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1562 | KL-20200522-4 | 53510712 | Access | 0 | 3rd Party Services | 1 | 3857.23 | Each |  |  |  |  | 3857.23 | 501.4399 | 4358.6699 | 2020-05-22 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Ditching and grading Camp 36. CR-10243 | 7 | D065-D066 | Camp 36 Road | 0 | 43978 |  |  |  | CR-20200522-2 | Ditching and Grading |  |  |  |  | 07 | KABI LAKE FOREST PRODUCTS LTD1562KL-20200522-43rd Party Services3857.233857.23 | KABI LAKE FOREST PRODUCTS LTD1562KL-20200522-43rd Party Services3857.233857.23OEWT-PA5-LEM | [5 empty] | 1 | 3857.23 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1563 | KL-20200523-1 | 53510712 | Access | 0 | 3rd Party Services | 1 | 3167 | Each |  |  |  |  | 3167 | 411.71 | 3578.71 | 2020-05-23 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Ditching Camp 36 Road. CR-10244 | 7 | D065-D066 | Camp 36 Road | 0 | 43978 |  |  |  | CR-20200523-1 | Ditching at Camp 36 |  |  |  |  | 07 | KABI LAKE FOREST PRODUCTS LTD1563KL-20200523-13rd Party Services31673167 | KABI LAKE FOREST PRODUCTS LTD1563KL-20200523-13rd Party Services31673167OEWT-PA5-LEM | [5 empty] | 1 | 3167 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1567 | KL-20200524-1 | 53510712 | Access | 0 | 3rd Party Services | 1 | 3142 | Each |  |  |  |  | 3142 | 408.46 | 3550.46 | 2020-05-24 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF | [6 empty] | Ditching Camp 36 Road - CR-10246 | 7 | D065-D066 | Camp 36 Road | 0 | 43978 |  |  |  | CR-20200524-1 | Ditching Camp 36 Road |  |  |  |  | 07 | KABI LAKE FOREST PRODUCTS LTD1567KL-20200524-13rd Party Services31423142 | KABI LAKE FOREST PRODUCTS LTD1567KL-20200524-13rd Party Services31423142OEWT-PA5-LEM | [5 empty] | 1 | 3142 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1572 | KL-20200525-3 | 53510712 | Access | 0 | 3rd Party Services | 1 | 3142 | Each |  |  |  |  | 3142 | 408.46 | 3550.46 | 2020-05-25 | 1 | OEWT-PA5-LEM | 43982 | 8 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Ditching Camp 36 Road - CR-10247 | 7 | D065-D066 | Camp 36 Raod | 0 | 43979 |  | 15 | 43980 | CR-20200525-4 | Ditching Road |  |  |  | Martin Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD1572KL-20200525-33rd Party Services31423142 | KABI LAKE FOREST PRODUCTS LTD1572KL-20200525-33rd Party Services31423142OEWT-PA5-LEM | [5 empty] | 1 | 3142 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1582 | KL-20200526-3 | 53510712 | Access | 0 | 3rd Party Services | 1 | 1977 | Each |  |  |  |  | 1977 | 257.01 | 2234.01 | 2020-05-26 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourers hand shoveled off Bridges- CR-10253 | 7 | D-056 to D-073 | Umbatta Falls | 0 | 43980 |  | 15 | 43981 | CR-20200526-4 | Shoveled Off Bridges |  |  |  | Martin Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD1582KL-20200526-33rd Party Services19771977 | KABI LAKE FOREST PRODUCTS LTD1582KL-20200526-33rd Party Services19771977OEWT-PA6-LEM | [5 empty] | 1 | 1977 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1788 | KL-20200618-14 | 53510712 | Access | 0 | 3rd Party Services | 1 | 277.77 | Each |  |  |  |  | 277.77 | 36.1101 | 313.8801 | 2020-06-18 | 1 | OEWT-PA6-LEM | 44012 | 9 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul and place gravel near D-067/D-068. Corduroy sections near structures D-058, D-063, and D-069. | 7 | D-056 to D-073 | Umbatta Falls | 0 | 44005 |  | 47 | 44006 | CR-20200618-1 | Fix ruts from use near D-052/D-053 from. CR. 10315 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD1788KL-20200618-143rd Party Services277.77277.77 | KABI LAKE FOREST PRODUCTS LTD1788KL-20200618-143rd Party Services277.77277.77OEWT-PA6-LEM | [5 empty] | 1 | 277.77 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1905 | KL-20200629-3 | 53510712 | Access | 0 | 3rd Party Services | 1 | 913.73 | Each |  |  |  |  | 913.73 | 118.7849 | 1032.5149 | 2020-06-29 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Black River Access CR-10352 | 7 | D-032 to D-055 | Black River | 0 | 44014 |  | 47 | 44014 | CR-20200629-4 | Grading Access. CR-10352 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD1905KL-20200629-33rd Party Services913.73913.73 | KABI LAKE FOREST PRODUCTS LTD1905KL-20200629-33rd Party Services913.73913.73OEWT-PA7-LEM | [5 empty] | 1 | 913.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1986 | KL-20200710-4 | 53510812 | Access | 0 | 3rd Party Services | 1 | 2179.64 | Each |  |  |  |  | 2179.64 | 283.3532 | 2462.9932 | 2020-07-10 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shape AU2 access to E077 from Stock pile after rain for gravel Haul - RV-40054 | 8 | E086 - E093 | Blue Cedar W | 0 | 44027 |  | 50 | 44027 | RV-20200710-1 | Shaping AU2 Access |  |  |  | Jim Budgell | 08 | KABI LAKE FOREST PRODUCTS LTD1986KL-20200710-43rd Party Services2179.642179.64 | KABI LAKE FOREST PRODUCTS LTD1986KL-20200710-43rd Party Services2179.642179.64OEWT-PA7-LEM | [5 empty] | 1 | 2179.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 1998 | KL-20200711-4 | 53510912 | Access | 0 | 3rd Party Services | 1 | 2639 | Each |  |  |  |  | 2639 | 343.07 | 2982.07 | 2020-07-11 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair Road E144 | 9 | E-091 to E-102 | 600 Road | 0 | 44027 |  | 50 | 44028 | OP-20200711-1 | Road Repair, OP-90010 |  |  |  | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD1998KL-20200711-43rd Party Services26392639 | KABI LAKE FOREST PRODUCTS LTD1998KL-20200711-43rd Party Services26392639OEWT-PA7-LEM | [5 empty] | 1 | 2639 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2191 | KL-20200630-14 | 53510712 | Access | 0 | 3rd Party Services | 1 | 452.36 | Each |  |  |  |  | 452.36 | 58.8068 | 511.1668 | 2020-06-30 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Graded Roadway - CR-10355 | 7 | D-065 to D-066 Graded Roadway - CR-10355 LABOUR EQUIPMENT VC7556-2019-016 883154429RT0001 D-065 to D-066 | Camp 36 Road | 0 | 44036 |  | 47 | 44038 | CR-20200630-6 | Grading road |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD2191KL-20200630-143rd Party Services452.36452.36 | KABI LAKE FOREST PRODUCTS LTD2191KL-20200630-143rd Party Services452.36452.36OEWT-PA7-LEM | [5 empty] | 1 | 452.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2227 | KL-20200723-3 | 53510712 | Access | 0 | 3rd Party Services | 1 | 2541.64 | Each |  |  |  |  | 2541.64 | 330.4132 | 2872.0532 | 2020-07-23 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finished sloping corner at Wabakoba by 115 - CR-10437 | 7 | D-109 to D-118 | Wabakoba Creek | 0 | 44040 |  | 48 | 44040 | CR-20200723-3 | Sloping Corner. CR-10437 |  |  |  | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2227KL-20200723-33rd Party Services2541.642541.64 | KABI LAKE FOREST PRODUCTS LTD2227KL-20200723-33rd Party Services2541.642541.64OEWT-PA7-LEM | [5 empty] | 1 | 2541.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2261 | KL-20200725-1 | 53510712 | Access | 0 | 3rd Party Services | 1 | 1692.5 | Each |  |  |  |  | 1692.5 | 220.025 | 1912.525 | 2020-07-25 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fixing and Shaping up Roads and bridge access - CR-10447 | 7 | D-056 to D-073 | Umbatta Falls | 0 | 44041 |  | 48 | 44041 | CR-20200725-1 | Fixing and shaping of road |  |  |  | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2261KL-20200725-13rd Party Services1692.51692.5 | KABI LAKE FOREST PRODUCTS LTD2261KL-20200725-13rd Party Services1692.51692.5OEWT-PA7-LEM | [5 empty] | 1 | 1692.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2263 | KL-20200725-3 | 53510712 | Access | 0 | 3rd Party Services | 1 | 1101.55 | Each |  |  |  |  | 1101.55 | 143.2015 | 1244.7515 | 2020-07-25 | 0 | OEWT-PA7-LEM | 44043 | 12 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 2 rock trucks hauling from stock pile to D045/ D046 | 7 | D-032 to D-055 | Black River | 0 | 44041 |  | 48 | 44041 | CR-20200725-3 | Fixed and shape road - CR-10445 |  |  |  | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2263KL-20200725-33rd Party Services1101.551101.55 | KABI LAKE FOREST PRODUCTS LTD2263KL-20200725-33rd Party Services1101.551101.55OEWT-PA7-LEM | [5 empty] | 1 | 1101.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2270 | KL-20200726-1 | 53510712 | Access | 0 | 3rd Party Services | 1 | 2346.64 | Each |  |  |  |  | 2346.64 | 305.0632 | 2651.7032 | 2020-07-26 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Rock truck hauling from stock pile on access to D-059 | 7 | D-056 to D-073 | Umbatta Falls | 0 | 44041 |  | 48 | 44041 | CR-20200726-2 | Fix and patch road - CR-10451 |  |  |  | Larse Hunt | 07 | KABI LAKE FOREST PRODUCTS LTD2270KL-20200726-13rd Party Services2346.642346.64 | KABI LAKE FOREST PRODUCTS LTD2270KL-20200726-13rd Party Services2346.642346.64OEWT-PA8-LEM | [5 empty] | 1 | 2346.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2426 | KL-20200812-2 | 53510712 | Access | 0 | 3rd Party Services | 1 | 2799.5 | Each |  |  |  |  | 2799.5 | 363.935 | 3163.435 | 2020-08-12 | 0 | OEWT-PA8-LEM | 44074 | 13 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 2 Rock Trucks hauling from stock pile to D132/ Excavator loading | 7 | D-119 to D-141 | Alder Creek | 0 | 44060 |  | 47 | 44061 | CR-20200812-1 | Repair road and encroachment onto bridge, Pit run material hauled from Stockpile. CR-10479 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD2426KL-20200812-23rd Party Services2799.52799.5 | KABI LAKE FOREST PRODUCTS LTD2426KL-20200812-23rd Party Services2799.52799.5OEWT-PA8-LEM | [5 empty] | 1 | 2799.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2843 | KL-20200911-11 | 53510712 | Access | 0 | 3rd Party Services | 1 | 674 | Each |  |  |  |  | 674 | 87.62 | 761.62 | 2020-09-11 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clean and shovel off bridge Black River West - BMC-30082 | 7 | D-032 to D-055 | Black River | 0 | 44094 |  | 47 | 44095 | BMC-20200911-2 | Clean Bridges. BMC-30082 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD2843KL-20200911-113rd Party Services674674 | KABI LAKE FOREST PRODUCTS LTD2843KL-20200911-113rd Party Services674674OEWT-PA9-Lem-R1 | [5 empty] | 1 | 674 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2891 | KL-20200913-13 | 53510712 | Access | 0 | 3rd Party Services | 1 | 1194 | Each |  |  |  |  | 1194 | 155.22 | 1349.22 | 2020-09-13 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clean Bridges Camp 36 to Wabakoba - BMC-30085 | 7 | D-065 to D-066 | Camp 36 | 0 | 44095 |  | 51 | 44096 | BMC-20200913-2 | Cleaning bridges |  |  |  | Michael Jean | 07 | KABI LAKE FOREST PRODUCTS LTD2891KL-20200913-133rd Party Services11941194 | KABI LAKE FOREST PRODUCTS LTD2891KL-20200913-133rd Party Services11941194OEWT-PA9-Lem-R1 | [5 empty] | 1 | 1194 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2932 | KL-20200915-3 | 53510912 | Access | 0 | 3rd Party Services | 1 | 1029.24 | Each |  |  |  |  | 1029.24 | 133.8012 | 1163.0412 | 2020-09-15 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of CDSL Logging Inc. for cross drain installs and fixing access roads. Cress floating equipment to 600 Rd | 9 | E-091 to E-102 | 600 Road | 0 | 44096 |  | 15 | 44097 | KL-20200915-3 | 200mm plastic cross drain culvert-supplied by Kabi |  |  |  | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2932KL-20200915-33rd Party Services1029.241029.24 | KABI LAKE FOREST PRODUCTS LTD2932KL-20200915-33rd Party Services1029.241029.24OEWT-PA9-Lem-R1 | [5 empty] | 1 | 1029.24 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 2932 | KL-20200915-3 | 53510912 | Access | 0 | 3rd Party Services | 1 | 2639 | Each |  |  |  |  | 2639 | 343.07 | 2982.07 | 2020-09-15 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of CDSL Logging Inc. for cross drain installs and fixing access roads. Cress floating equipment to 600 Rd | 9 | E-091 to E-102 | 600 Road | 0 | 44096 |  | 15 | 44097 | CDSL-20200915-1 | Fixing access roads E-185/E-190. CDSL-16005 |  |  |  | Martin Hunt | 09 | KABI LAKE FOREST PRODUCTS LTD2932KL-20200915-33rd Party Services26392639 | KABI LAKE FOREST PRODUCTS LTD2932KL-20200915-33rd Party Services26392639OEWT-PA9-Lem-R1 | [5 empty] | 1 | 2639 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3080 | KL-20200921-2 | 53510712 | Access | 0 | 3rd Party Services | 1 | 484.36 | Each |  |  |  |  | 484.36 | 62.9668 | 547.3268 | 2020-09-21 | 0 | OEWT-PA9-Lem-R1 | 44110 | 17 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Gravel Haul - CR-10634 / CR-10635 / CR-10636 / CR-10637 | 7 | D-074 to D-079 | Brett’s Road | 0 | 44102 |  | 51 | 44102 | CR-20200921-2 | remove rock access road |  |  |  | Michael Jean | 07 | KABI LAKE FOREST PRODUCTS LTD3080KL-20200921-23rd Party Services484.36484.36 | KABI LAKE FOREST PRODUCTS LTD3080KL-20200921-23rd Party Services484.36484.36OEWT-PA9-Lem-R1 | [5 empty] | 1 | 484.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3273 | KL-20200927-17 | 53511104 | Access | 0 | 3rd Party Services | 1 | 3336 | Each |  |  |  |  | 3336 | 433.68 | 3769.68 | 2020-09-27 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pit runfrom Provost pit #5/Dozer spreading | 11 | F-119 to F-134 | Hensen Road | 0 | 43900 |  | 48 | 43871 | CR-20200927-6 | Haul Gravel - CR-10707 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3273KL-20200927-173rd Party Services33363336 | KABI LAKE FOREST PRODUCTS LTD3273KL-20200927-173rd Party Services33363336OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 3336 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3273 | KL-20200927-17 | 53511104 | Access | 0 | 3rd Party Services | 1 | 1708 | Each |  |  |  |  | 1708 | 222.04 | 1930.04 | 2020-09-27 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pit runfrom Provost pit #5/Dozer spreading | 11 | F-119 to F-134 | Hensen Road | 0 | 43900 |  | 48 | 43871 | GT-20200927-1 | Haul Gravel - GT-11004 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3273KL-20200927-173rd Party Services17081708 | KABI LAKE FOREST PRODUCTS LTD3273KL-20200927-173rd Party Services17081708OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 1708 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3295 | KL-20200928-18 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2648.82 | Each |  |  |  |  | 2648.82 | 344.3466 | 2993.1666 | 2020-09-28 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade AU1 Access to F204 - SSF-14021 | 11 | F-203 to F-211 | High Falls Road- 9 | 0 | 44109 |  | 50 | 44110 | SSF-20200928-1 | Grade AU1 Access to F204 - SSF-14021 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD3295KL-20200928-183rd Party Services2648.822648.82 | KABI LAKE FOREST PRODUCTS LTD3295KL-20200928-183rd Party Services2648.822648.82OEWT-PA10-LEM | [5 empty] | 1 | 2648.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3300 | KL-20200928-23 | 53511104 | Access | 0 | 3rd Party Services | 1 | 3138.55 | Each |  |  |  |  | 3138.55 | 408.0115 | 3546.5615 | 2020-09-28 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauling pit run from Provost Pit #5 to AE1 on Henson Road /Dozer spreading and widening areas | 11 | F-119 to F-134 | Hensen Road | 0 | 44109 |  | 50 | 44110 | BMC-20200928-2 | Hauling pit run from Provost Pit #5 to AE1 on Henson Road /Dozer spreading and widening areas |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD3300KL-20200928-233rd Party Services3138.553138.55 | KABI LAKE FOREST PRODUCTS LTD3300KL-20200928-233rd Party Services3138.553138.55OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 3138.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3300 | KL-20200928-23 | 53511104 | Access | 0 | 3rd Party Services | 1 | 1513.91 | Each |  |  |  |  | 1513.91 | 196.8083 | 1710.7183 | 2020-09-28 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauling pit run from Provost Pit #5 to AE1 on Henson Road /Dozer spreading and widening areas | 11 | F-119 to F-134 | Hensen Road | 0 | 44109 |  | 50 | 44110 | JJR-20200928-2 | haul pit run fron provost pit #5 to AE1 on Hensen Road - JJR-70088 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD3300KL-20200928-233rd Party Services1513.911513.91 | KABI LAKE FOREST PRODUCTS LTD3300KL-20200928-233rd Party Services1513.911513.91OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 1513.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3336 | KL-20200929-27 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2648.82 | Each |  |  |  |  | 2648.82 | 344.3466 | 2993.1666 | 2020-09-29 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauling pit run from Provost pit #5 to F204 access and bridge approach. Skagen grade road and spread gravel. | 11 | F203-F211 | High Falls Road- 9 | 0 | 44109 |  | 50 | 44115 | SSF-20200929-1 | Grade AU1 Access For gravel Haul - SSF-14024 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD3336KL-20200929-273rd Party Services2648.822648.82 | KABI LAKE FOREST PRODUCTS LTD3336KL-20200929-273rd Party Services2648.822648.82OEWT-PA10-LEM | [5 empty] | 1 | 2648.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3358 | KL-20201001-4 | 53510712 | Access | 0 | 3rd Party Services | 1 | 1899 | Each |  |  |  |  | 1899 | 246.87 | 2145.87 | 2020-10-01 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Yellow Brick Road on hill to tailings - CR-10727 / Hauling gravel to Yellow Brick Stock Pile - 470.61 tons pit run from Cress pit - CR-10732 | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44118 |  | 47 | 44121 | CR-20201001-4 | grader |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD3358KL-20201001-43rd Party Services18991899 | KABI LAKE FOREST PRODUCTS LTD3358KL-20201001-43rd Party Services18991899OEWT-PA10-LEM | [5 empty] | 1 | 1899 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3376 | KL-20201001-22 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2588.82 | Each |  |  |  |  | 2588.82 | 336.5466 | 2925.3666 | 2020-10-01 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Triaxles hauling Pit Run from Provost pit #5 , Dozer spreading and widening areas.Grade Hensen road for gravel Haul - SSF-14029.Haul Pit Run from Provost Pit #5 to AE1 on Hensen Road - JJR-70095. Hauled Gravel to Hensen Road from Provost Pit #5 - BMC-30121 | 11 | F-119 to F-134 | Hensen Road | 0 | 44118 |  | 48 | 44123 | SSF-20201001-1 | Grade Haul Road- SSF-14029 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3376KL-20201001-223rd Party Services2588.822588.82 | KABI LAKE FOREST PRODUCTS LTD3376KL-20201001-223rd Party Services2588.822588.82OEWT-PA10-LEM | [5 empty] | 1 | 2588.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3376 | KL-20201001-22 | 53511104 | Access | 0 | 3rd Party Services | 1 | 1513.91 | Each |  |  |  |  | 1513.91 | 196.8083 | 1710.7183 | 2020-10-01 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Triaxles hauling Pit Run from Provost pit #5 , Dozer spreading and widening areas.Grade Hensen road for gravel Haul - SSF-14029.Haul Pit Run from Provost Pit #5 to AE1 on Hensen Road - JJR-70095. Hauled Gravel to Hensen Road from Provost Pit #5 - BMC-30121 | 11 | F-119 to F-134 | Hensen Road | 0 | 44118 |  | 48 | 44123 | JJR-20201001-2 | Haul Gravel - JJR-70095 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3376KL-20201001-223rd Party Services1513.911513.91 | KABI LAKE FOREST PRODUCTS LTD3376KL-20201001-223rd Party Services1513.911513.91OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 1513.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3376 | KL-20201001-22 | 53511104 | Access | 0 | 3rd Party Services | 1 | 2210.36 | Each |  |  |  |  | 2210.36 | 287.3468 | 2497.7068 | 2020-10-01 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Triaxles hauling Pit Run from Provost pit #5 , Dozer spreading and widening areas.Grade Hensen road for gravel Haul - SSF-14029.Haul Pit Run from Provost Pit #5 to AE1 on Hensen Road - JJR-70095. Hauled Gravel to Hensen Road from Provost Pit #5 - BMC-30121 | 11 | F-119 to F-134 | Hensen Road | 0 | 44118 |  | 48 | 44123 | BMC-20201001-2 | Haul Gravel - BMC-30121 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3376KL-20201001-223rd Party Services2210.362210.36 | KABI LAKE FOREST PRODUCTS LTD3376KL-20201001-223rd Party Services2210.362210.36OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 2210.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3380 | KL-20201001-26 | 53511103 | Access | 0 | 3rd Party Services | 1 | 3719.82 | Each |  |  |  |  | 3719.82 | 483.5766 | 4203.3966 | 2020-10-01 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Corduroy @ F207 Access - SSF-14032 | 11 | F-119 to F-134 | Hensen Road | 0 | 44118 |  | 48 | 44123 | SSF-20201001-2 | Corduroy |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3380KL-20201001-263rd Party Services3719.823719.82 | KABI LAKE FOREST PRODUCTS LTD3380KL-20201001-263rd Party Services3719.823719.82OEWT-PA10-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 3719.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3404 | KL-20201002-24 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2479.82 | Each |  |  |  |  | 2479.82 | 322.3766 | 2802.1966 | 2020-10-02 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Tri axles hauling pit run from Provost Pit 5 - Dozer spreading and widening road. Haul Pit Run from Provost pit #5 to AE1 on Hensen Road - JJR-70096 | 11 | F-119 to F-134 | Hensen Road | 0 | 44106 |  | 48 | 44123 | SSF-20201002-3 | Grade Road - SSF-14030 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3404KL-20201002-243rd Party Services2479.822479.82 | KABI LAKE FOREST PRODUCTS LTD3404KL-20201002-243rd Party Services2479.822479.82OEWT-PA10-LEM | [5 empty] | 1 | 2479.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3404 | KL-20201002-24 | 53511104 | Access | 0 | 3rd Party Services | 1 | 1441.82 | Each |  |  |  |  | 1441.82 | 187.4366 | 1629.2566 | 2020-10-02 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Tri axles hauling pit run from Provost Pit 5 - Dozer spreading and widening road. Haul Pit Run from Provost pit #5 to AE1 on Hensen Road - JJR-70096 | 11 | F-119 to F-134 | Hensen Road | 0 | 44106 |  | 48 | 44123 | JJR-20201002-2 | Hauled Gravel - JJR-70096 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3404KL-20201002-243rd Party Services1441.821441.82 | KABI LAKE FOREST PRODUCTS LTD3404KL-20201002-243rd Party Services1441.821441.82OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 1441.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3404 | KL-20201002-24 | 53511104 | Access | 0 | 3rd Party Services | 1 | 1647 | Each |  |  |  |  | 1647 | 214.11 | 1861.11 | 2020-10-02 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Tri axles hauling pit run from Provost Pit 5 - Dozer spreading and widening road. Haul Pit Run from Provost pit #5 to AE1 on Hensen Road - JJR-70096 | 11 | F-119 to F-134 | Hensen Road | 0 | 44106 |  | 48 | 44123 | CBT-20201002-1 | Hauled Gravel - CBT-21005 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3404KL-20201002-243rd Party Services16471647 | KABI LAKE FOREST PRODUCTS LTD3404KL-20201002-243rd Party Services16471647OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 1647 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3411 | KL-20200930-19 | 53511104 | Access | 0 | 3rd Party Services | 1 | 2957.46 | Each |  |  |  |  | 2957.46 | 384.4698 | 3341.9298 | 2020-09-30 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer spreading Pit Run from Provost Pit #5 and widening areas. Trucks hauling gravel from Provost Pit | 11 | F-119 to F-134 | Hensen Road | 0 | 44119 |  | 48 | 44120 | BMC-20200930-2 | haul Gravel - BMC-30116 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3411KL-20200930-193rd Party Services2957.462957.46 | KABI LAKE FOREST PRODUCTS LTD3411KL-20200930-193rd Party Services2957.462957.46OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 2957.46 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3411 | KL-20200930-19 | 53511104 | Access | 0 | 3rd Party Services | 1 | 1513.91 | Each |  |  |  |  | 1513.91 | 196.8083 | 1710.7183 | 2020-09-30 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer spreading Pit Run from Provost Pit #5 and widening areas. Trucks hauling gravel from Provost Pit | 11 | F-119 to F-134 | Hensen Road | 0 | 44119 |  | 48 | 44120 | JJR-20200930-2 | Haul Gravel - JJR-70091 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3411KL-20200930-193rd Party Services1513.911513.91 | KABI LAKE FOREST PRODUCTS LTD3411KL-20200930-193rd Party Services1513.911513.91OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 1513.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3411 | KL-20200930-19 | 53511104 | Access | 0 | 3rd Party Services | 1 | 1555.91 | Each |  |  |  |  | 1555.91 | 202.2683 | 1758.1783 | 2020-09-30 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer spreading Pit Run from Provost Pit #5 and widening areas. Trucks hauling gravel from Provost Pit | 11 | F-119 to F-134 | Hensen Road | 0 | 44119 |  | 48 | 44120 | CR-20200930-6 | Haul Gravel - CR-10722 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3411KL-20200930-193rd Party Services1555.911555.91 | KABI LAKE FOREST PRODUCTS LTD3411KL-20200930-193rd Party Services1555.911555.91OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 1555.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3415 | KL-20200930-23 | 53511112 | Access | 0 | 3rd Party Services | 1 | 548.36 | Each |  |  |  |  | 548.36 | 71.2868 | 619.6468 | 2020-09-30 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pitrun from Provost pit #5 to F204 access | 11 | F-203 to F-211 | High Falls Road | 0 | 44119 |  | 48 | 44120 | SSF-20200930-2 | Grade road - SSF-14026 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3415KL-20200930-233rd Party Services548.36548.36 | KABI LAKE FOREST PRODUCTS LTD3415KL-20200930-233rd Party Services548.36548.36OEWT-PA10-LEM | [5 empty] | 1 | 548.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3415 | KL-20200930-23 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2673.82 | Each |  |  |  |  | 2673.82 | 347.5966 | 3021.4166 | 2020-09-30 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pitrun from Provost pit #5 to F204 access | 11 | F-203 to F-211 | High Falls Road | 0 | 44119 |  | 48 | 44120 | SSF-20200930-3 | Spread Gravel - SSF-14028 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3415KL-20200930-233rd Party Services2673.822673.82 | KABI LAKE FOREST PRODUCTS LTD3415KL-20200930-233rd Party Services2673.822673.82OEWT-PA10-LEM | [5 empty] | 1 | 2673.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3463 | KL-20201004-11 | 53510812 | Access | 0 | 3rd Party Services | 1 | 1950.37 | Each |  |  |  |  | 1950.37 | 253.5481 | 2203.9181 | 2020-10-04 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair Rutted areas to ensure Drainage@ White Lake Road East - AM-60092 | 8 | E-004 to E-016 | White Lake East | 0 | 44120 |  | 53 | 44122 | AM-20201004-2 | Fixing road for drainage |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD3463KL-20201004-113rd Party Services1950.371950.37 | KABI LAKE FOREST PRODUCTS LTD3463KL-20201004-113rd Party Services1950.371950.37OEWT-PA10-LEM | [5 empty] | 1 | 1950.37 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3480 | KL-20201005-5 | 53510812 | Access | 0 | 3rd Party Services | 1 | 1804.27 | Each |  |  |  |  | 1804.27 | 234.5551 | 2038.8251 | 2020-10-05 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road realignment due to tower anchor locations, fixed rutted areas to ensure drainage - AM-60096 | 8 | E-004 to E-016 | White Lake East | 0 | 44123 |  | 47 | 44128 | AM-20201005-3 | Fix Rutted areas - AM-60096 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3480KL-20201005-53rd Party Services1804.271804.27 | KABI LAKE FOREST PRODUCTS LTD3480KL-20201005-53rd Party Services1804.271804.27OEWT-PA10-LEM | [5 empty] | 1 | 1804.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3506 | KL-20201006-4 | 53510812 | Access | 0 | 3rd Party Services | 1 | 3656.55 | Each |  |  |  |  | 3656.55 | 475.3515 | 4131.9015 | 2020-10-06 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fix rutted out areas due to heavy precipitation with blast rock and corduroy - AM-60079 | 8 | E-004 to E-016 | White Lake East | 0 | 44124 |  | 47 | 44125 | AM-20201006-1 | Fixed rutted road- AM-60079 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3506KL-20201006-43rd Party Services3656.553656.55 | KABI LAKE FOREST PRODUCTS LTD3506KL-20201006-43rd Party Services3656.553656.55OEWT-PA10-LEM | [5 empty] | 1 | 3656.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3528 | KL-20201006-24 | 53511104 | Access | 0 | 3rd Party Services | 1 | 3913 | Each |  |  |  |  | 3913 | 508.69 | 4421.69 | 2020-10-06 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer widening areas and spreading gravel | 11 | F-119 to F-134 | Hensen Road | 0 | 44124 |  | 48 | 44126 | CR-20201006-5 | hauled Gravel - CR-10764 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3528KL-20201006-243rd Party Services39133913 | KABI LAKE FOREST PRODUCTS LTD3528KL-20201006-243rd Party Services39133913OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 3913 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3552 | KL-20201007-7 | 53510812 | Access | 0 | 3rd Party Services | 1 | 7145.64 | Each |  |  |  |  | 7145.64 | 928.9332 | 8074.5732 | 2020-10-07 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load Blast rock haul to rutted areas and spread blast rock - AM-60082 | 8 | E-004 to E-016 | White Lake East | 0 | 44125 |  | 47 | 44128 | AM-20201007-4 | Fixing rutted road -AM-60082 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3552KL-20201007-73rd Party Services7145.647145.64 | KABI LAKE FOREST PRODUCTS LTD3552KL-20201007-73rd Party Services7145.647145.64OEWT-PA10-LEM | [5 empty] | 1 | 7145.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3553 | KL-20201007-8 | 53510812 | Access | 0 | 3rd Party Services | 1 | 1955.45 | Each |  |  |  |  | 1955.45 | 254.2085 | 2209.6585 | 2020-10-07 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fix ruts - realign Road - AM-60084 | 8 | E-042 to E-053 | Denis Lake W | 0 | 44125 |  | 47 | 44128 | AM-20201007-5 | Fixing rutted road -AM-60084 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3553KL-20201007-83rd Party Services1955.451955.45 | KABI LAKE FOREST PRODUCTS LTD3553KL-20201007-83rd Party Services1955.451955.45OEWT-PA10-LEM | [5 empty] | 1 | 1955.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3565 | KL-20201007-20 | 53511112 | Access | 0 | 3rd Party Services | 1 | 928.73 | Each |  |  |  |  | 928.73 | 120.7349 | 1049.4649 | 2020-10-07 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade AU1 Access - SSF-14041 | 11 | F-203 to F-211 | High Falls Road 9 | 0 | 44125 |  | 55 | 44128 | SSF-20201007-2 | Grading - SSF-14041 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD3565KL-20201007-203rd Party Services928.73928.73 | KABI LAKE FOREST PRODUCTS LTD3565KL-20201007-203rd Party Services928.73928.73OEWT-PA10-LEM | [5 empty] | 1 | 928.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3588 | KL-20201008-8 | 53510712 | Access | 0 | 3rd Party Services | 1 | 9488.82 | Each |  |  |  |  | 9488.82 | 1233.5466 | 10722.3666 | 2020-10-08 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hauling Gravel - AM-60097 / Fixing rutted road for drainage - AM-60098 / Unload bridge - AM-60099. 25 ton rock truck hauling pit run to hill near WC 801 - AM-60097. Load blast rock and cut down blast rock hill, 25T rock truck hauling blast rock, Spreading blast rock in rutted areas to ensure drainage - AM-60098. Unload Bridge @ Hwy 17 intersection, Move bridge to laydown Area - AM-60099 | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44125 |  | 47 | 44129 | AM-20201008-5 | Fix road - AM-60098 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD3588KL-20201008-83rd Party Services9488.829488.82 | KABI LAKE FOREST PRODUCTS LTD3588KL-20201008-83rd Party Services9488.829488.82OEWT-PA10-LEM | [5 empty] | 1 | 9488.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3616 | KL-20201009-5 | 53510712 | Access | 0 | 3rd Party Services | 1 | 2058.5 | Each |  |  |  |  | 2058.5 | 267.605 | 2326.105 | 2020-10-09 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul Pit run from Cress Pit to stock pile and D092. Cress grading road. | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44125 |  | 47 | 44129 | CR-20201009-5 | Grade Road - CR-10777 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD3616KL-20201009-53rd Party Services2058.52058.5 | KABI LAKE FOREST PRODUCTS LTD3616KL-20201009-53rd Party Services2058.52058.5OEWT-PA10-LEM | [5 empty] | 1 | 2058.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3618 | KL-20201009-7 | 53510812 | Access | 0 | 3rd Party Services | 1 | 5194 | Each |  |  |  |  | 5194 | 675.22 | 5869.22 | 2020-10-09 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load Blast rock in 25t rock truck and haul to unpassable areas, Spreading blast rock in rutted areas to ensure drainage - AM-60105 | 8 | E-004 to E-016 | White Lake East | 0 | 44125 |  | 47 | 44129 | AM-20201009-4 | Fixing Road - AM-60105 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3618KL-20201009-73rd Party Services51945194 | KABI LAKE FOREST PRODUCTS LTD3618KL-20201009-73rd Party Services51945194OEWT-PA10-LEM | [5 empty] | 1 | 5194 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3638 | KL-20201010-2 | 53510712 | Access | 0 | 3rd Party Services | 1 | 1077.73 | Each |  |  |  |  | 1077.73 | 140.1049 | 1217.8349 | 2020-10-10 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul gravel to stockpile, lay corduroy near D-086/D-087. Fix soft spots on road. Lay corduroy into structures D-086/D-087. CR-10785. Stockpile pit run received from triaxles, load 25T and 35T rock truck, forward to dozer. AM-60111. 2X triaxle loads were dumped near 092 after approval from Bruce (Valard). Walked 330F to location, fixed soft/rutted spots. AM-60108. Haul gravel with rock truck from stockpile to D-088 access. BMC-30127 | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44125 |  | 47 | 44129 | AM-20201010-2 | Fix soft spots/ruts on road. AM-60108 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD3638KL-20201010-23rd Party Services1077.731077.73 | KABI LAKE FOREST PRODUCTS LTD3638KL-20201010-23rd Party Services1077.731077.73OEWT-PA10-LEM | [5 empty] | 1 | 1077.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3644 | KL-20201010-8 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2639 | Each |  |  |  |  | 2639 | 343.07 | 2982.07 | 2020-10-10 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Widen road and ditching between F-012 and F-013. MNC-41023 | 10 | F-009 to F-020 | Paint Lake Road 1-A | 0 | 44125 |  | 15 | 44129 | MNC-20201010-1 | Widen Road. MNC-41023 |  |  |  | Martin Hunt | 10 | KABI LAKE FOREST PRODUCTS LTD3644KL-20201010-83rd Party Services26392639 | KABI LAKE FOREST PRODUCTS LTD3644KL-20201010-83rd Party Services26392639OEWT-PA10-LEM | [5 empty] | 1 | 2639 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3655 | KL-20201010-19 | 53511112 | Access | 0 | 3rd Party Services | 1 | 678.55 | Each |  |  |  |  | 678.55 | 88.2115 | 766.7615 | 2020-10-10 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade rough sections on Road 9 from F-203 to F-207. SSF-14044 | 11 | F-203 to F-211 | High Falls Road- 9 | 0 | 44125 |  | 55 | 44129 | SSF-20201010-1 | Grade rough sections of road |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD3655KL-20201010-193rd Party Services678.55678.55 | KABI LAKE FOREST PRODUCTS LTD3655KL-20201010-193rd Party Services678.55678.55OEWT-PA10-LEM | [5 empty] | 1 | 678.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3659 | KL-20201004-24 | 53510712 | Access | 0 | 3rd Party Services | 1 | 2509.05 | Each |  |  |  |  | 2509.05 | 326.1765 | 2835.2265 | 2020-10-04 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Cohl's Heavy Equipment for Corduroy near structure D-090. Skid all main roads in @access #80 to # 90 - Plus skid #84 thru to #89 on main line - CHE-77005 | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44126 |  | 47 | 44130 | CHE-20201004-1 | Skidding wood - CHE-77005 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD3659KL-20201004-243rd Party Services2509.052509.05 | KABI LAKE FOREST PRODUCTS LTD3659KL-20201004-243rd Party Services2509.052509.05OEWT-PA10-LEM | [5 empty] | 1 | 2509.05 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3664 | KL-20201011-4 | 53510812 | Access | 0 | 3rd Party Services | 1 | 2105.45 | Each |  |  |  |  | 2105.45 | 273.7085 | 2379.1585 | 2020-10-11 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Delivering Geo Textile, loading rock truck and spreading gravel over corduroy and Geo. Travel From White Lake East to Yellow Brick Road West to get 200mm poly cross drains for Installation @ White River East. AS per Frank (Kabi) and Darcy (Valard) Direction, obtain 2 rolls of woven poly Geo Textile and transport it to Valard's camp in Marathon for Enviornmental - AM-60116. 330F loading gravel into rock truck from stock pile, hauling to hill past existing powerline but before WC 9010, 350 spreading gravel on top of corduroy and Geo - AM-60115. Bail Blast rock to Raise elevation of road @ Bottom of blast hill | 8 | E-004 to E-016 | White Lake East | 0 | 44157 |  | 47 | 44130 | AM-20201011-6 | Stock piling & loading trucks |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3664KL-20201011-43rd Party Services2105.452105.45 | KABI LAKE FOREST PRODUCTS LTD3664KL-20201011-43rd Party Services2105.452105.45OEWT-PA10-LEM | [5 empty] | 1 | 2105.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3673 | KL-20201011-13 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2639 | Each |  |  |  |  | 2639 | 343.07 | 2982.07 | 2020-10-11 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Widen road and ditching between F16 to F18 - MNC-41022 | 10 | F-009 to F-020 | Paint Lake Road 1-A | 0 | 44126 |  | 15 | 44131 | MNC-20201011-1 | Widening and ditching - MNC-41022 |  |  |  | Martin Hunt | 10 | KABI LAKE FOREST PRODUCTS LTD3673KL-20201011-133rd Party Services26392639 | KABI LAKE FOREST PRODUCTS LTD3673KL-20201011-133rd Party Services26392639OEWT-PA10-LEM | [5 empty] | 1 | 2639 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3692 | KL-20201012-10 | 53510812 | Access | 0 | 3rd Party Services | 1 | 1116.73 | Each |  |  |  |  | 1116.73 | 145.1749 | 1261.9049 | 2020-10-12 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Tuning up truck ruts on Access - CR-10794 | 8 | E-004 to E-016 | White Lake East | 0 | 44126 |  | 47 | 44130 | CR-20201012-4 | Tuning up Road - CR-10794 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3692KL-20201012-103rd Party Services1116.731116.73 | KABI LAKE FOREST PRODUCTS LTD3692KL-20201012-103rd Party Services1116.731116.73OEWT-PA10-LEM | [5 empty] | 1 | 1116.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3693 | KL-20201012-11 | 53510812 | Access | 0 | 3rd Party Services | 1 | 5666.91 | Each |  |  |  |  | 5666.91 | 736.6983 | 6403.6083 | 2020-10-12 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 330 scaling blast rock l to find usable rock while still maintaining access, loaded rock truck, hauled to locations unpassable by pick ups, place and grade rock - AM-60118 | 8 | E-004 to E-016 | White Lake East | 0 | 44126 |  | 47 | 44130 | AM-20201012-3 | Fixing Road - AM-60118 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3693KL-20201012-113rd Party Services5666.915666.91 | KABI LAKE FOREST PRODUCTS LTD3693KL-20201012-113rd Party Services5666.915666.91OEWT-PA10-LEM | [5 empty] | 1 | 5666.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3695 | KL-20201012-13 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2639 | Each |  |  |  |  | 2639 | 343.07 | 2982.07 | 2020-10-12 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Widening road and ditching between F16 to F18 - MNC-41024 | 10 | F-009 to F-020 | Paint Lake Road 1-A | 0 | 44126 |  | 15 | 44132 | MNC-20201012-1 | Widenein and ditching - MNC-41024 |  |  |  | Martin Hunt | 10 | KABI LAKE FOREST PRODUCTS LTD3695KL-20201012-133rd Party Services26392639 | KABI LAKE FOREST PRODUCTS LTD3695KL-20201012-133rd Party Services26392639OEWT-PA10-LEM | [5 empty] | 1 | 2639 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3708 | KL-20201013-2 | 53510712 | Access | 0 | 3rd Party Services | 1 | 528 | Each |  |  |  |  | 528 | 68.64 | 596.64 | 2020-10-13 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fixing Access road to Structure 90- AM-60123 / Realignment of road way - AM-60122 / Unclogging cross drains - AM-60124. realign road to 89 as per Valard. Use corduroy to raise road to eliminate S curve. Place new Geo and gravel on realigned corduroy. Construct truck turn around - AM-60122. Two labourers unclogging crossdrain at intersection of Access road to structures D089/D090. AM-60124. 290 Linkbelt smoothing out rutted areas to ensure drainage on access road to Structure 90. AM-60123 | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44129 |  | 47 | 44131 | AM-20201013-3 | Realign Road - AM-60122 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD3708KL-20201013-23rd Party Services528528 | KABI LAKE FOREST PRODUCTS LTD3708KL-20201013-23rd Party Services528528OEWT-PA10-LEM | [5 empty] | 1 | 528 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3708 | KL-20201013-2 | 53510712 | Access | 0 | 3rd Party Services | 1 | 593.36 | Each |  |  |  |  | 593.36 | 77.1368 | 670.4968 | 2020-10-13 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fixing Access road to Structure 90- AM-60123 / Realignment of road way - AM-60122 / Unclogging cross drains - AM-60124. realign road to 89 as per Valard. Use corduroy to raise road to eliminate S curve. Place new Geo and gravel on realigned corduroy. Construct truck turn around - AM-60122. Two labourers unclogging crossdrain at intersection of Access road to structures D089/D090. AM-60124. 290 Linkbelt smoothing out rutted areas to ensure drainage on access road to Structure 90. AM-60123 | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44129 |  | 47 | 44131 | AM-20201013-4 | Unclog cross drains - AM-60124 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD3708KL-20201013-23rd Party Services593.36593.36 | KABI LAKE FOREST PRODUCTS LTD3708KL-20201013-23rd Party Services593.36593.36OEWT-PA10-LEM | [5 empty] | 1 | 593.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3713 | KL-20201013-7 | 53510812 | Access | 0 | 3rd Party Services | 1 | 4193.73 | Each |  |  |  |  | 4193.73 | 545.1849 | 4738.9149 | 2020-10-13 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 330 excavating existing road on top of blast Hill to find usable material. 350 excavating crest of hill to find bedrock so grade can be reestablished - AM-60125 | 8 | E-004 to E-016 | White Lake East | 0 | 44129 |  | 47 | 44131 | AM-20201013-5 | Fix Road - AM-60125 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3713KL-20201013-73rd Party Services4193.734193.73 | KABI LAKE FOREST PRODUCTS LTD3713KL-20201013-73rd Party Services4193.734193.73OEWT-PA10-LEM | [5 empty] | 1 | 4193.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3730 | KL-20201014-1 | 53510712 | Access | 0 | 3rd Party Services | 1 | 849.73 | Each |  |  |  |  | 849.73 | 110.4649 | 960.1949 | 2020-10-14 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Blade ruts and shape road from D090 to stock pile - CR-10803 / Tram Material Over road and push with dozer over Geo between D097-98 - BMC-30130 | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44129 |  | 47 | 44131 | CR-20201014-1 | Fix ruts in road - CR-10803 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD3730KL-20201014-13rd Party Services849.73849.73 | KABI LAKE FOREST PRODUCTS LTD3730KL-20201014-13rd Party Services849.73849.73OEWT-PA10-LEM | [5 empty] | 1 | 849.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3730 | KL-20201014-1 | 53510712 | Access | 0 | 3rd Party Services | 1 | 3563.86 | Each |  |  |  |  | 3563.86 | 463.3018 | 4027.1618 | 2020-10-14 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Blade ruts and shape road from D090 to stock pile - CR-10803 / Tram Material Over road and push with dozer over Geo between D097-98 - BMC-30130 | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44129 |  | 47 | 44131 | BMC-20201014-1 | Spread material over Geo - BMC-30130 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD3730KL-20201014-13rd Party Services3563.863563.86 | KABI LAKE FOREST PRODUCTS LTD3730KL-20201014-13rd Party Services3563.863563.86OEWT-PA10-LEM | [5 empty] | 1 | 3563.86 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3741 | KL-20201014-12 | 53510912 | Access | 0 | 3rd Party Services | 1 | 257.31 | Each |  |  |  |  | 257.31 | 33.4503 | 290.7603 | 2020-10-14 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load Trucks from 650 pit, fix roads and haul gravel to E168 to E171 and spread over corduroy, install cross drain at F6. | 9 | E-091 to E-102 | 600 Road | 0 | 44129 |  | 50 | 44132 | KL-20201014-12 | 200mm x 9M plastic crossdrain-supplied by Kabi |  |  |  | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD3741KL-20201014-123rd Party Services257.31257.31 | KABI LAKE FOREST PRODUCTS LTD3741KL-20201014-123rd Party Services257.31257.31OEWT-PA10-LEM | [5 empty] | 1 | 257.31 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3751 | KL-20201014-22 | 53510812 | Access | 0 | 3rd Party Services | 1 | 1077.73 | Each |  |  |  |  | 1077.73 | 140.1049 | 1217.8349 | 2020-10-14 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 330 re-establishing grade at top of blast hill and scale rock that has potential to fall on road - AM-60129 | 8 | E-004 to E-016 | White Lake East | 0 | 44129 |  | 47 | 44131 | AM-20201014-4 | Scale rock, grade. AM-60129 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3751KL-20201014-223rd Party Services1077.731077.73 | KABI LAKE FOREST PRODUCTS LTD3751KL-20201014-223rd Party Services1077.731077.73OEWT-PA10-LEM | [5 empty] | 1 | 1077.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3762 | KL-20201015-10 | 53510812 | Access | 0 | 3rd Party Services | 1 | 2897.73 | Each |  |  |  |  | 2897.73 | 376.7049 | 3274.4349 | 2020-10-15 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading Blast rock into rock truck and hauling between blast hill and WC 9000 where need to get pick up access to WC 801. Job Suspendedat 10:24 am - AM-60134 | 8 | E-004 to E-016 | White Lake East | 0 | 44130 |  | 47 | 44131 | AM-20201015-5 | Fix access road - AM-60134 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3762KL-20201015-103rd Party Services2897.732897.73 | KABI LAKE FOREST PRODUCTS LTD3762KL-20201015-103rd Party Services2897.732897.73OEWT-PA10-LEM | [5 empty] | 1 | 2897.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3789 | KL-20201016-7 | 53510812 | Access | 0 | 3rd Party Services | 1 | 6703.23 | Each |  |  |  |  | 6703.23 | 871.4199 | 7574.6499 | 2020-10-16 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load blast rock into RT, haul to areas needed to gain access to WC 801 as per Valards direction, RT stop hauling at 3pm, Excavators fixed ruts to ensure drainage | 8 | E-004 to E-016 | White Lake East | 0 | 44130 |  | 47 | 44131 | AM-20201016-2 | Fixing ruts in road- AM-60140 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3789KL-20201016-73rd Party Services6703.236703.23 | KABI LAKE FOREST PRODUCTS LTD3789KL-20201016-73rd Party Services6703.236703.23OEWT-PA10-LEM | [5 empty] | 1 | 6703.23 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3805 | KL-20201017-5 | 53510812 | Access | 0 | 3rd Party Services | 1 | 7255.73 | Each |  |  |  |  | 7255.73 | 943.2449 | 8198.9749 | 2020-10-17 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading Gravel - AM-60138 / Repairing road - AM-60139 | 8 | E-004 to E-016 | White Lake East | 0 | 44130 |  | 47 | 44131 | AM-20201017-2 | Repairing unpassale road - AM_60139 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3805KL-20201017-53rd Party Services7255.737255.73 | KABI LAKE FOREST PRODUCTS LTD3805KL-20201017-53rd Party Services7255.737255.73OEWT-PA10-LEM | [5 empty] | 1 | 7255.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3816 | KL-20201017-16 | 53511112 | Access | 0 | 3rd Party Services | 1 | 968.73 | Each |  |  |  |  | 968.73 | 125.9349 | 1094.6649 | 2020-10-17 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Drainage, cleaning up road Km 10-14 - CR-10817 | 11 | F-119 to F-134 | Hensen Road | 0 | 44130 |  | 55 | 44132 | CR-20201017-4 | Draining and cleaning up road - CR-10817 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD3816KL-20201017-163rd Party Services968.73968.73 | KABI LAKE FOREST PRODUCTS LTD3816KL-20201017-163rd Party Services968.73968.73OEWT-PA10-LEM | [5 empty] | 1 | 968.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3870 | KL-20201020-19 | 53510812 | Access | 0 | 3rd Party Services | 1 | 1295.73 | Each |  |  |  |  | 1295.73 | 168.4449 | 1464.1749 | 2020-10-20 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Covering Geo - AM-60146 / Road Realignment - AM-60147 | 8 | E-025 to E-036 | Silver City | 0 | 44131 |  | 47 | 44132 | AM-20201020-2 | Road Realignment - AM-60147 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD3870KL-20201020-193rd Party Services1295.731295.73 | KABI LAKE FOREST PRODUCTS LTD3870KL-20201020-193rd Party Services1295.731295.73OEWT-PA10-LEM | [5 empty] | 1 | 1295.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3883 | KL-20201023-2 | 53510712 | Access | 0 | 3rd Party Services | 1 | 1186.73 | Each |  |  |  |  | 1186.73 | 154.2749 | 1341.0049 | 2020-10-23 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Utilize in-situ material to ensure proper drainage, clean out and regrade ditches, flare apron - AM-60148 | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44133 |  | 47 | 44133 | AM-20201023-1 | ensure proper drainage - AM-60148 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD3883KL-20201023-23rd Party Services1186.731186.73 | KABI LAKE FOREST PRODUCTS LTD3883KL-20201023-23rd Party Services1186.731186.73OEWT-PA10-LEM | [5 empty] | 1 | 1186.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3931 | KL-20201024-9 | 53511104 | Access | 0 | 3rd Party Services | 1 | 4706.94 | Each |  |  |  |  | 4706.94 | 611.9022 | 5318.8422 | 2020-10-24 | 0 | OEWT-PA10-LEM | 44137 | 29 | 0 | 0 | Dahl Arlene | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul gravel, crushed stone to KM 17 of Hensen road. AU1 upgrade ditching and shaping road. | 11 | F-119 to F-134 | Hensen Road | 0 | 44133 |  | 48 | 44132 | CR-20201024-2 | Hauling Special Rock - CR-10839 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD3931KL-20201024-93rd Party Services4706.944706.94 | KABI LAKE FOREST PRODUCTS LTD3931KL-20201024-93rd Party Services4706.944706.94OEWT-PA10-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 4706.94 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3981 | KL-20201026-6 | 53510712 | Access | 0 | 3rd Party Services | 1 | 1195.09 | Each |  |  |  |  | 1195.09 | 155.3617 | 1350.4517 | 2020-10-26 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Blade off roadway with Dozer D088 D086 to Stock pile - CR-10844 / Flattening out ruts on road to D093 -D099 - BMC-30135 | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44147 |  | 47 | 44151 | CR-20201026-3 | Blade off roadway with Dozer D088 D086 and to Stock pile - CR-10844 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD3981KL-20201026-63rd Party Services1195.091195.09 | KABI LAKE FOREST PRODUCTS LTD3981KL-20201026-63rd Party Services1195.091195.09OEWT-PA11-LEM | [5 empty] | 1 | 1195.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 3981 | KL-20201026-6 | 53510712 | Access | 0 | 3rd Party Services | 1 | 2479.82 | Each |  |  |  |  | 2479.82 | 322.3766 | 2802.1966 | 2020-10-26 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Blade off roadway with Dozer D088 D086 to Stock pile - CR-10844 / Flattening out ruts on road to D093 -D099 - BMC-30135 | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44147 |  | 47 | 44151 | BMC-20201026-1 | Flattening out ruts on road to D093 -D099 - BMC-30135 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD3981KL-20201026-63rd Party Services2479.822479.82 | KABI LAKE FOREST PRODUCTS LTD3981KL-20201026-63rd Party Services2479.822479.82OEWT-PA11-LEM | [5 empty] | 1 | 2479.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4014 | KL-20201028-1 | 53510711 | Access | 0 | 3rd Party Services | 1 | 2257.5 | Each |  |  |  |  | 2257.5 | 293.475 | 2550.975 | 2020-10-28 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Gravel haul and winter maintenance on Yellow Brick Road West | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44147 |  | 47 | 44151 | CR-20201028-1 | Grader was on roadway at Yellow Brick & Sander as well - CR-10850 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4014KL-20201028-13rd Party Services2257.52257.5 | KABI LAKE FOREST PRODUCTS LTD4014KL-20201028-13rd Party Services2257.52257.5OEWT-PA11-LEM | [5 empty] | 1 | 2257.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4014 | KL-20201028-1 | 53510711 | Access | 0 | 3rd Party Services | 1 | 10986.64 | Each |  |  |  |  | 10986.64 | 1428.2632 | 12414.9032 | 2020-10-28 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Gravel haul and winter maintenance on Yellow Brick Road West | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44147 |  | 47 | 44151 | CR-20201028-2 | Hauled Gravel to stock pile pushed up with D5, cleaned road of snow before trucks show up-CR-10852 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4014KL-20201028-13rd Party Services10986.6410986.64 | KABI LAKE FOREST PRODUCTS LTD4014KL-20201028-13rd Party Services10986.6410986.64OEWT-PA11-LEM | [5 empty] | 1 | 10986.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4055 | KL-20201029-21 | 53511111 | Access | 0 | 3rd Party Services | 1 | 925.91 | Each |  |  |  |  | 925.91 | 120.3683 | 1046.2783 | 2020-10-29 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer shaping & Levelling Road for Cold Weather From F203 to F205-SSF-14062 | 11 | F203-F211 | High Falls Road- 9 | 0 | 44152 |  | 48 | 44154 | SSF-20201029-2 | Dozer shaping & Levelling Road for Cold Weather From F203 to F205-SSF-14062 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4055KL-20201029-213rd Party Services925.91925.91 | KABI LAKE FOREST PRODUCTS LTD4055KL-20201029-213rd Party Services925.91925.91OEWT-PA11-LEM | [5 empty] | 1 | 925.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4085 | KL-20201031-11 | 53511112 | Access | 0 | 3rd Party Services | 1 | 277.77 | Each |  |  |  |  | 277.77 | 36.1101 | 313.8801 | 2020-10-31 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Blade Ruts on AE1 an AN Access to F205 for freezing - SSF-14065 | 11 | F203-F211 | High Falls Road -9 | 0 | 44152 |  | 48 | 44154 | SSF-20201031-1 | Blade Ruts on AE1 an AN Access to F205 for freezing - SSF-14065 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4085KL-20201031-113rd Party Services277.77277.77 | KABI LAKE FOREST PRODUCTS LTD4085KL-20201031-113rd Party Services277.77277.77OEWT-PA11-LEM | [5 empty] | 1 | 277.77 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4090 | KL-20201101-2 | 53510712 | Access | 0 | 3rd Party Services | 1 | 3126.32 | Each |  |  |  |  | 3126.32 | 406.4216 | 3532.7416 | 2020-11-01 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Deliver geo from vallard yard CR-10863 and plow and sand Yellow Brick Road CR-10864.Delivered 12 rolls of geo to Yellow Brick Rd. from Valard Yard. CR-10863. Plowed and Sanded Yellow Brick Rd CR-10864 | 7 | D-074 to D-079 | Brett’s Road | 0 | 44153 |  | 47 | 44158 | CR-20201101-3 | Plowed and Sanded Yellow Brick Rd CR-10864 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4090KL-20201101-23rd Party Services3126.323126.32 | KABI LAKE FOREST PRODUCTS LTD4090KL-20201101-23rd Party Services3126.323126.32OEWT-PA11-LEM | [5 empty] | 1 | 3126.32 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4106 | KL-20201102-2 | 53510711 | Access | 0 | 3rd Party Services | 1 | 544 | Each |  |  |  |  | 544 | 70.72 | 614.72 | 2020-11-02 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pit run from cress pit to stock pile @D087/D0. Used Sander for 2 loads at Yellow Brick Road - CR-10865 | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44153 |  | 47 | 44158 | CR-20201102-2 | Used Sander for 2 loads at Yellow Brick Road - CR-10865 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4106KL-20201102-23rd Party Services544544 | KABI LAKE FOREST PRODUCTS LTD4106KL-20201102-23rd Party Services544544OEWT-PA11-LEM | [5 empty] | 1 | 544 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4170 | KL-20201105-4 | 53510812 | Access | 0 | 3rd Party Services | 1 | 348 | Each |  |  |  |  | 348 | 45.24 | 393.24 | 2020-11-05 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Spreading pit run @ E032/E031 Corduroy and crush gravel to stock pile | 8 | E025-E036 | Silver City | 0 | 44160 |  | 47 | 44163 | AM-20201105-3 | Scrape Mud -AM-60180 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4170KL-20201105-43rd Party Services348348 | KABI LAKE FOREST PRODUCTS LTD4170KL-20201105-43rd Party Services348348OEWT-PA11-LEM | [5 empty] | 1 | 348 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4191 | KL-20201106-3 | 53510712 | Access | 0 | 3rd Party Services | 1 | 858 | Each |  |  |  |  | 858 | 111.54 | 969.54 | 2020-11-06 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float 140M grader from Cress yard to Yellow Brick Road - CR-10888 / 140M grader grading mine road from KM2.5 asphalt ends to Tailing pond - CR-10886 | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44162 |  | 47 | 44163 | CR-20201106-6 | Grade Roads - CR-10886 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4191KL-20201106-33rd Party Services858858 | KABI LAKE FOREST PRODUCTS LTD4191KL-20201106-33rd Party Services858858OEWT-PA11-LEM | [5 empty] | 1 | 858 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4192 | KL-20201106-4 | 53510712 | Access | 0 | 3rd Party Services | 1 | 2744.27 | Each |  |  |  |  | 2744.27 | 356.7551 | 3101.0251 | 2020-11-06 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul Pit run from Cress pit to Stock pile @ D087/D088/ supervision of Padda Roadlines | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44162 |  | 56 | 44163 | CR-20201106-8 | Road Maintenance - CR-10884 |  |  |  | Mandy Sandhu | 07 | KABI LAKE FOREST PRODUCTS LTD4192KL-20201106-43rd Party Services2744.272744.27 | KABI LAKE FOREST PRODUCTS LTD4192KL-20201106-43rd Party Services2744.272744.27OEWT-PA11-LEM | [5 empty] | 1 | 2744.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4195 | KL-20201106-7 | 53510812 | Access | 0 | 3rd Party Services | 1 | 622 | Each |  |  |  |  | 622 | 80.86 | 702.86 | 2020-11-06 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Tandem Hauling pit run from 5km pit 100 road/ Dozer spreading pit run @ E031/E030 corduroy/ supervision of Padda Roadlines | 8 | E025-E036 | Silver City | 0 | 44162 |  | 56 | 44163 | AM-20201106-1 | Clean entrance- AM-60181 |  |  |  | Mandy Sandhu | 08 | KABI LAKE FOREST PRODUCTS LTD4195KL-20201106-73rd Party Services622622 | KABI LAKE FOREST PRODUCTS LTD4195KL-20201106-73rd Party Services622622OEWT-PA11-LEM | [5 empty] | 1 | 622 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4211 | KL-20201107-5 | 53510712 | Access | 0 | 3rd Party Services | 1 | 2175.5 | Each |  |  |  |  | 2175.5 | 282.815 | 2458.315 | 2020-11-07 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Tri-axles hauling to D5 dozer, dozer cleaning up and maintaining road | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44162 |  | 56 | 44163 | CR-20201107-5 | Road maintenance CR-10896 |  |  |  | Mandy Sandhu | 07 | KABI LAKE FOREST PRODUCTS LTD4211KL-20201107-53rd Party Services2175.52175.5 | KABI LAKE FOREST PRODUCTS LTD4211KL-20201107-53rd Party Services2175.52175.5OEWT-PA11-LEM | [5 empty] | 1 | 2175.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4212 | KL-20201107-6 | 53510712 | Access | 0 | 3rd Party Services | 1 | 2293 | Each |  |  |  |  | 2293 | 298.09 | 2591.09 | 2020-11-07 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 140M Grader, grading mine road km 2.5 to tailing pond. CR-10897 | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44162 |  | 56 | 44163 | CR-20201107-6 | Grading Road |  |  |  | Mandy Sandhu | 07 | KABI LAKE FOREST PRODUCTS LTD4212KL-20201107-63rd Party Services22932293 | KABI LAKE FOREST PRODUCTS LTD4212KL-20201107-63rd Party Services22932293OEWT-PA11-LEM | [5 empty] | 1 | 2293 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4227 | KL-20201108-6 | 53510812 | Access | 0 | 3rd Party Services | 1 | 3058 | Each |  |  |  |  | 3058 | 397.54 | 3455.54 | 2020-11-08 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F cutting out muddy areas, re-establishing ditches and placing gravel, 2 labourers rolling geotextile as needed AM-60185 | 8 | E025-E036 | Silver City | 0 | 44162 |  | 56 | 44166 | AM-20201108-2 | 330 cut out muddy areas re establish AM-60185 |  |  |  | Mandy Sandhu | 08 | KABI LAKE FOREST PRODUCTS LTD4227KL-20201108-63rd Party Services30583058 | KABI LAKE FOREST PRODUCTS LTD4227KL-20201108-63rd Party Services30583058OEWT-PA11-LEM | [5 empty] | 1 | 3058 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4228 | KL-20201108-7 | 53511112 | Access | 0 | 3rd Party Services | 1 | 1187.55 | Each |  |  |  |  | 1187.55 | 154.3815 | 1341.9315 | 2020-11-08 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul existing material for bridge approach @ F117 Access as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44162 |  | 56 | 44166 | CR-20201108-5 | layed geo CR-10906 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD4228KL-20201108-73rd Party Services1187.551187.55 | KABI LAKE FOREST PRODUCTS LTD4228KL-20201108-73rd Party Services1187.551187.55OEWT-PA11-LEM | [5 empty] | 1 | 1187.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4228 | KL-20201108-7 | 53511104 | Access | 0 | 3rd Party Services | 1 | 1508.91 | Each |  |  |  |  | 1508.91 | 196.1583 | 1705.0683 | 2020-11-08 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul existing material for bridge approach @ F117 Access as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44162 |  | 56 | 44166 | CR-20201108-7 | gravel haul CR-10904 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD4228KL-20201108-73rd Party Services1508.911508.91 | KABI LAKE FOREST PRODUCTS LTD4228KL-20201108-73rd Party Services1508.911508.91OEWT-PA11-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 1508.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4259 | KL-20201109-8 | 53510812 | Access | 0 | 3rd Party Services | 1 | 1077.73 | Each |  |  |  |  | 1077.73 | 140.1049 | 1217.8349 | 2020-11-09 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 realigning road at structure E033 to accommodate foundation locations - AM-60188 | 8 | E025-E036 | Silver City | 0 | 44164 |  | 53 | 44168 | AM-20201109-3 | Move road - AM-60186 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4259KL-20201109-83rd Party Services1077.731077.73 | KABI LAKE FOREST PRODUCTS LTD4259KL-20201109-83rd Party Services1077.731077.73OEWT-PA11-LEM | [5 empty] | 1 | 1077.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4284 | KL-20201101-14 | 53510812 | Access | 0 | 3rd Party Services | 1 | 1319.91 | Each |  |  |  |  | 1319.91 | 171.5883 | 1491.4983 | 2020-11-01 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Tune up road to structure 33 to allow for gravel hauling. Maintenance of road that had previously been completed. AM-60157- revised | 8 | E025-E036 | Silver City | 0 | 44166 |  | 53 | 44168 | AM-20201101-4 | Road maintenance to allow hauling |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4284KL-20201101-143rd Party Services1319.911319.91 | KABI LAKE FOREST PRODUCTS LTD4284KL-20201101-143rd Party Services1319.911319.91OEWT-PA11-LEM | [5 empty] | 1 | 1319.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4306 | KL-20201111-1 | 53510712 | Access | 0 | 3rd Party Services | 1 | 4352.27 | Each |  |  |  |  | 4352.27 | 565.7951 | 4918.0651 | 2020-11-11 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and spread gravel and wood chips D071- D073 - BMC-30145 / Volvo 25t rock truck hauling gravel on Camp 36 Road - AM-60191 | 7 | D065-D066 | Camp 36 Road | 0 | 44166 |  | 53 | 44168 | BMC-20201111-1 | Load and spread gravel - BMC-30145 |  |  |  | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD4306KL-20201111-13rd Party Services4352.274352.27 | KABI LAKE FOREST PRODUCTS LTD4306KL-20201111-13rd Party Services4352.274352.27OEWT-PA11-LEM | [5 empty] | 1 | 4352.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4309 | KL-20201111-4 | 53510711 | Access | 0 | 3rd Party Services | 1 | 544 | Each |  |  |  |  | 544 | 70.72 | 614.72 | 2020-11-11 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pit run from cress pit to @D086/D085, Cress repairing road. Access/Supervision of 3 Padda Roadlines triaxles | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44166 |  | 53 | 44168 | CR-20201111-3 | Sand Haul Road - CR-10932 |  |  |  | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD4309KL-20201111-43rd Party Services544544 | KABI LAKE FOREST PRODUCTS LTD4309KL-20201111-43rd Party Services544544OEWT-PA11-LEM | [5 empty] | 1 | 544 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4321 | KL-20201112-3 | 53510712 | Access | 0 | 3rd Party Services | 1 | 900.64 | Each |  |  |  |  | 900.64 | 117.0832 | 1017.7232 | 2020-11-12 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Blade and track pack road from Hwy to Honi - BMC-30144 | 7 | D065-D066 | Camp 36 | 0 | 44166 |  | 53 | 44168 | BMC-20201112-1 | Repairing Road - BMC-30144 |  |  |  | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD4321KL-20201112-33rd Party Services900.64900.64 | KABI LAKE FOREST PRODUCTS LTD4321KL-20201112-33rd Party Services900.64900.64OEWT-PA11-LEM | [5 empty] | 1 | 900.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4325 | KL-20201112-8 | 53510812 | Access | 0 | 3rd Party Services | 1 | 2369 | Each |  |  |  |  | 2369 | 307.97 | 2676.97 | 2020-11-12 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 290 link belt cutting out soft areas, Re-establishing road with corduroy, Geo and gravel as needed, 2 labourers cleaning mud of Hwy 17 Entrance Twice - AM-60203 | 8 | E025-E036 | Silver City | 0 | 44166 |  | 53 | 44168 | AM-20201112-4 | Corduroy - AM-60203 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4325KL-20201112-83rd Party Services23692369 | KABI LAKE FOREST PRODUCTS LTD4325KL-20201112-83rd Party Services23692369OEWT-PA11-LEM | [5 empty] | 1 | 2369 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4334 | KL-20201113-2 | 53510712 | Access | 0 | 3rd Party Services | 1 | 1013.73 | Each |  |  |  |  | 1013.73 | 131.7849 | 1145.5149 | 2020-11-13 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Blade and trackpack from highway to D073 BMC-30146 | 7 | D065-D066 | Camp 36 Road | 0 | 44166 |  | 47 | 44168 | BMC-20201113-1 | Blade & trackpack from hwy to D073 BMC-30146 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4334KL-20201113-23rd Party Services1013.731013.73 | KABI LAKE FOREST PRODUCTS LTD4334KL-20201113-23rd Party Services1013.731013.73OEWT-PA11-LEM | [5 empty] | 1 | 1013.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4339 | KL-20201113-7 | 53510812 | Access | 0 | 3rd Party Services | 1 | 2149 | Each |  |  |  |  | 2149 | 279.37 | 2428.37 | 2020-11-13 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 6 Padda Triaxles hauling pit run from 5km on 100 Road to E028/E027 Corduroy/Supervision of Padda. Amikwaa spreading gravel, fixing ruts. | 8 | E025-E036 | Silver City | 0 | 44166 |  | 56 | 44169 | AM-20201113-2 | fill in ruts- clean mud off Hwy 17 AM-60204 |  |  |  | Mandy Sandhu | 08 | KABI LAKE FOREST PRODUCTS LTD4339KL-20201113-73rd Party Services21492149 | KABI LAKE FOREST PRODUCTS LTD4339KL-20201113-73rd Party Services21492149OEWT-PA11-LEM | [5 empty] | 1 | 2149 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4351 | KL-20201114-4 | 53510712 | Access | 0 | 3rd Party Services | 1 | 2257.73 | Each |  |  |  |  | 2257.73 | 293.5049 | 2551.2349 | 2020-11-14 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Blade and Track pack from Hwy to D073 BMC-30147 | 7 | D065-D066 | Camp 36 | 0 | 44166 |  | 47 | 44170 | BMC-20201114-1 | blade & trackpack from hwy to D073 BMC-30147 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4351KL-20201114-43rd Party Services2257.732257.73 | KABI LAKE FOREST PRODUCTS LTD4351KL-20201114-43rd Party Services2257.732257.73OEWT-PA11-LEM | [5 empty] | 1 | 2257.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4355 | KL-20201114-8 | 53510812 | Access | 0 | 3rd Party Services | 1 | 2309 | Each |  |  |  |  | 2309 | 300.17 | 2609.17 | 2020-11-14 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 8 Padda & 1 Kabi triaxle hauling pit run from 5km on 100 Rd to E028/E027 Corduroy/Supervison of Padda Roadlines. Grader on 100 Rd & Silver City for gravel haul. | 8 | E025-E036 | Silver City | 0 | 44166 |  | 53 | 44171 | AM-20201114-1 | exc filling ruts from triaxles AM-60211 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4355KL-20201114-83rd Party Services23092309 | KABI LAKE FOREST PRODUCTS LTD4355KL-20201114-83rd Party Services23092309OEWT-PA11-LEM | [5 empty] | 1 | 2309 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4387 | KL-20201115-1 | 53510712 | Access | 0 | 3rd Party Services | 1 | 702.64 | Each |  |  |  |  | 702.64 | 91.3432 | 793.9832 | 2020-11-15 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float 336 to Alder Creek, plow Alder road & laydown area. Labourers flagged, floated 336F from Brett's Rd to Alder, floated D5 from 614 RD to Alder CR-10946-6. Plow Alder Rd and laydown, clean up mud and snow CR-10946-4. | 7 | D-119 to D-141 | Alder Creek | 0 | 44167 |  | 53 | 44171 | CR-20201115-2 | Plow Alder Rd and laydown, clean up mud and snow CR-10946-4 |  |  |  | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD4387KL-20201115-13rd Party Services702.64702.64 | KABI LAKE FOREST PRODUCTS LTD4387KL-20201115-13rd Party Services702.64702.64OEWT-PA11-LEM | [5 empty] | 1 | 702.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4391 | KL-20201115-5 | 53510712 | Access | 0 | 3rd Party Services | 1 | 1126.82 | Each |  |  |  |  | 1126.82 | 146.4866 | 1273.3066 | 2020-11-15 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Blade & track pack from Hwy to D073 BMC-30148 | 7 | D065-D066 | Camp 36 | 0 | 44167 |  | 53 | 44170 | BMC-20201115-1 | Blade & track pack from Hwy to D073 BMC-30148 |  |  |  | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD4391KL-20201115-53rd Party Services1126.821126.82 | KABI LAKE FOREST PRODUCTS LTD4391KL-20201115-53rd Party Services1126.821126.82OEWT-PA11-LEM | [5 empty] | 1 | 1126.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4393 | KL-20201115-7 | 53510712 | Access | 0 | 3rd Party Services | 1 | 1116 | Each |  |  |  |  | 1116 | 145.08 | 1261.08 | 2020-11-15 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pit run from Cress Pit to D085 Access & Corduroy. Graded the road of snow and mud CR-10946-3. Haul Pit run from Heron Bay to dozer D86 - D85 CR-10946-7. Lay out geo over existing road and have dozer spread material going forward towards D86 CR-10946-2 | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44167 |  | 53 | 44171 | CR-20201115-4 | Graded the road of snow and mud CR-10946-3 |  |  |  | Clint Maerz | 07 | KABI LAKE FOREST PRODUCTS LTD4393KL-20201115-73rd Party Services11161116 | KABI LAKE FOREST PRODUCTS LTD4393KL-20201115-73rd Party Services11161116OEWT-PA11-LEM | [5 empty] | 1 | 1116 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4395 | KL-20201115-9 | 53510812 | Access | 0 | 3rd Party Services | 1 | 2722 | Each |  |  |  |  | 2722 | 353.86 | 3075.86 | 2020-11-15 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 8 Padda Roadlines triaxles & 1 Kabi hauling pit run from 5km on 100 Road to E028/E027 Corduroy/Supervision of Padda Roadlines. 290 filling in and tracking ruts from triaxles at Silver City Rd. Trucks were postponed due to weather, after haul was complete, clean mud off Hwy. Smooth ruts AM-60207. Cat 330 spreading gravel E028-E031 from triaxles Silver City Rd. Labourers rolling out geotextile on corduroy & cleaning mud off HWY AM-60209. Haul Pit run from 5km pit on 100 Road to E028/E027 Corduroy. PD-99090. | 8 | E025-E036 | Silver City | 0 | 44167 |  | 53 | 44171 | AM-20201115-1 | 290 filling in and tracking ruts from triaxles at Silver City Rd. Trucks were postponed due to weather, after haul was complete, clean mud off Hwy. Smooth ruts AM-60207 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4395KL-20201115-93rd Party Services27222722 | KABI LAKE FOREST PRODUCTS LTD4395KL-20201115-93rd Party Services27222722OEWT-PA11-LEM | [5 empty] | 1 | 2722 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4403 | KL-20201116-3 | 53510712 | Access | 0 | 3rd Party Services | 1 | 2027.45 | Each |  |  |  |  | 2027.45 | 263.5685 | 2291.0185 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Blade & track pack from Hwy to D073 and then head west to D061 BMC-30149 | 7 | D065-D066 | Camp 36 | 0 | 44167 |  | 47 | 44171 | BMC-20201116-1 | Blade & track pack from Hwy to D073 and then head west to D061 BMC-30149 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4403KL-20201116-33rd Party Services2027.452027.45 | KABI LAKE FOREST PRODUCTS LTD4403KL-20201116-33rd Party Services2027.452027.45OEWT-PA11-LEM | [5 empty] | 1 | 2027.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4404 | KL-20201116-4 | 53510711 | Access | 0 | 3rd Party Services | 1 | 230 | Each |  |  |  |  | 230 | 29.9 | 259.9 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul Pit run from Cress Pit to D085 Access & Corduroy . Sand road for trucks to haul, lay down geo on existing road. Sanded road so trucks can haul CR-10948-3. Haul gravel from Cress pit to Yellow Brick stockpile BMC-30150. Lay down geo covering existing road use dozer to spread material over geo towards D85 CR-10948-4. | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44167 |  | 47 | 44171 | CR-20201116-3 | Haul pit run from Heron Bay to Yellow Brick Rd working towards D85 CR-10948-7 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4404KL-20201116-43rd Party Services230230 | KABI LAKE FOREST PRODUCTS LTD4404KL-20201116-43rd Party Services230230OEWT-PA11-LEM | [5 empty] | 1 | 230 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4412 | KL-20201116-11 | 53510812 | Access | 0 | 3rd Party Services | 1 | 2504 | Each |  |  |  |  | 2504 | 325.52 | 2829.52 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 8 Padda trucks hauling pit run from 5km pit on 100 Rd to E028/E027 Corduroy/Supervison of Padda Roadlines. Amikwaa fixing ruts, spreading geo. 290 filling in and tracking ruts from truck haul at Silver City Rd. Clean out ditches, re-grade to ensure positive drainage AM-60213. 330F spreading gravel on corduroy E026-E028 received from triaxles. Labourers roll out geo on corduroy and clean mud off Hwy from trucks AM-60214. Haul pit run from 5km pit on 100 RD to E028/E027 Corduroy PD-99092. | 8 | E025-E036 | Silver City | 0 | 44167 |  | 47 | 44171 | AM-20201116-3 | 290 filling in and tracking ruts from truck haul at Silver City Rd. Clean out ditches, re-grade to ensure positive drainage AM-60213 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4412KL-20201116-113rd Party Services25042504 | KABI LAKE FOREST PRODUCTS LTD4412KL-20201116-113rd Party Services25042504OEWT-PA11-LEM | [5 empty] | 1 | 2504 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4412 | KL-20201116-11 | 53510812 | Access | 0 | 3rd Party Services | 1 | 5073.82 | Each |  |  |  |  | 5073.82 | 659.5966 | 5733.4166 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 8 Padda trucks hauling pit run from 5km pit on 100 Rd to E028/E027 Corduroy/Supervison of Padda Roadlines. Amikwaa fixing ruts, spreading geo. 290 filling in and tracking ruts from truck haul at Silver City Rd. Clean out ditches, re-grade to ensure positive drainage AM-60213. 330F spreading gravel on corduroy E026-E028 received from triaxles. Labourers roll out geo on corduroy and clean mud off Hwy from trucks AM-60214. Haul pit run from 5km pit on 100 RD to E028/E027 Corduroy PD-99092. | 8 | E025-E036 | Silver City | 0 | 44167 |  | 47 | 44171 | AM-20201116-4 | 330F spreading gravel on corduroy E026-E028 received from triaxles. Labourers roll out geo on corduroy and clean mud off Hwy from trucks AM-60214 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4412KL-20201116-113rd Party Services5073.825073.82 | KABI LAKE FOREST PRODUCTS LTD4412KL-20201116-113rd Party Services5073.825073.82OEWT-PA11-LEM | [5 empty] | 1 | 5073.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4412 | KL-20201116-11 | 53510812 | Access | 0 | 3rd Party Services | 1 | 13664 | Each |  |  |  |  | 13664 | 1776.32 | 15440.32 | 2020-11-16 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 8 Padda trucks hauling pit run from 5km pit on 100 Rd to E028/E027 Corduroy/Supervison of Padda Roadlines. Amikwaa fixing ruts, spreading geo. 290 filling in and tracking ruts from truck haul at Silver City Rd. Clean out ditches, re-grade to ensure positive drainage AM-60213. 330F spreading gravel on corduroy E026-E028 received from triaxles. Labourers roll out geo on corduroy and clean mud off Hwy from trucks AM-60214. Haul pit run from 5km pit on 100 RD to E028/E027 Corduroy PD-99092. | 8 | E025-E036 | Silver City | 0 | 44167 |  | 47 | 44171 | PD-20201116-1 | Haul pit run from 5km pit on 100 RD to E028/E027 Corduroy PD-99092 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4412KL-20201116-113rd Party Services1366413664 | KABI LAKE FOREST PRODUCTS LTD4412KL-20201116-113rd Party Services1366413664OEWT-PA11-LEM | [5 empty] | 1 | 13664 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4423 | KL-20201117-3 | 53510711 | Access | 0 | 3rd Party Services | 1 | 230 | Each |  |  |  |  | 230 | 29.9 | 259.9 | 2020-11-17 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul Pit Run from Cress pit to D085 & D084 Access Corduroy. Sand road and haul pit run to dozer | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44167 |  | 47 | 44172 | CR-20201117-2 | Sand Road for truck haul CR-10953 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4423KL-20201117-33rd Party Services230230 | KABI LAKE FOREST PRODUCTS LTD4423KL-20201117-33rd Party Services230230OEWT-PA11-LEM | [5 empty] | 1 | 230 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4424 | KL-20201117-4 | 53510812 | Access | 0 | 3rd Party Services | 1 | 1209 | Each |  |  |  |  | 1209 | 157.17 | 1366.17 | 2020-11-17 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 9 Padda trucks hauling pit run from km5 pit on 100 road to E028/E027 corduroy. Amikwaa filling tracks/ruts, spreading gravel over corduroy. 290 filling in and tracking ruts from triaxles at Silver City Access Road AM-60216. 330 spreading gravel on Corduroy E026-E027 received from triaxles. Labourers lay out geo on corduroy and clean mud off Hwy 17 @entrance AM-60218. Haul pit run from 5km pit on 100 Road to E028/E027 Corduroy PD-99093 | 8 | E025-E036 | Silver City | 0 | 44167 |  | 47 | 44172 | AM-20201117-2 | 290 filling in and tracking ruts from triaxles at Silver City Access Road AM-60216 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4424KL-20201117-43rd Party Services12091209 | KABI LAKE FOREST PRODUCTS LTD4424KL-20201117-43rd Party Services12091209OEWT-PA11-LEM | [5 empty] | 1 | 1209 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4428 | KL-20201117-7 | 53510712 | Access | 0 | 3rd Party Services | 1 | 2253.64 | Each |  |  |  |  | 2253.64 | 292.9732 | 2546.6132 | 2020-11-17 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Blade & track pack from Hwy to D073 and then to D062 BMC-30151 | 7 | D065-D066 | Camp 36 | 0 | 44167 |  | 47 | 44172 | BMC-20201117-1 | Blade & track pack from Hwy to D073 and then to D062 BMC-30151 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4428KL-20201117-73rd Party Services2253.642253.64 | KABI LAKE FOREST PRODUCTS LTD4428KL-20201117-73rd Party Services2253.642253.64OEWT-PA11-LEM | [5 empty] | 1 | 2253.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4434 | KL-20201117-13 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2069.82 | Each |  |  |  |  | 2069.82 | 269.0766 | 2338.8966 | 2020-11-17 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on Hensen shaping and levelling for ruts for freezing SSF-14073. | 11 | F119-F134 | Hensen Road | 0 | 44167 |  | 55 | 44171 | SSF-20201117-2 | Dozer working on Hensen shaping and levelling for ruts for freezing SSF-14073 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4434KL-20201117-133rd Party Services2069.822069.82 | KABI LAKE FOREST PRODUCTS LTD4434KL-20201117-133rd Party Services2069.822069.82OEWT-PA11-LEM | [5 empty] | 1 | 2069.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4440 | KL-20201118-1 | 53510712 | Access | 0 | 3rd Party Services | 1 | 1579.18 | Each |  |  |  |  | 1579.18 | 205.2934 | 1784.4734 | 2020-11-18 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Blade and track pack from D061 - 73 and from rite away to Hwy - BMC-30152 | 7 | D065-D066 | Camp 36 | 0 | 44167 |  | 47 | 44172 | BMC-20201118-1 | Blade and track pack from D061 - 73 and from rite away to Hwy - BMC-30152 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4440KL-20201118-13rd Party Services1579.181579.18 | KABI LAKE FOREST PRODUCTS LTD4440KL-20201118-13rd Party Services1579.181579.18OEWT-PA11-LEM | [5 empty] | 1 | 1579.18 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4448 | KL-20201118-9 | 53510812 | Access | 0 | 3rd Party Services | 1 | 1429 | Each |  |  |  |  | 1429 | 185.77 | 1614.77 | 2020-11-18 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 9 Padda Roadline triaxles hauling pit run from 5km pit on 100 road to E028/E027 Corduroy/ Supervision of Padda Roadlines. Cat 330 spreading gravel on Corduroy (E026-E027) from Triaxles, Labourers rolling out Geo on corduroy and cleaning mud off Hwy 17 at entrance Silver City -AM-60221. 290 LinkBelt filling in and tracking ruts from tri-axle D/T's at Silver City Access Road. AM-60219. Haul Pit run from 5km pit on 100 road to E028/E027 corduroy and 4" minus on AU1 Access. PD-99094. | 8 | e025-e036 | Silver City | 0 | 44167 |  | 47 | 44173 | AM-20201118-2 | 290 LinkBelt filling in and tracking ruts from tri-axle D/T's at Silver City Access Road. AM-60219 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4448KL-20201118-93rd Party Services14291429 | KABI LAKE FOREST PRODUCTS LTD4448KL-20201118-93rd Party Services14291429OEWT-PA11-LEM | [5 empty] | 1 | 1429 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4453 | KL-20201118-15 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2069.82 | Each |  |  |  |  | 2069.82 | 269.0766 | 2338.8966 | 2020-11-18 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continue working on Hensen road shaping and leveling ruts for freezeing - SSF-1407 | 11 | F119-F134 | Hensen Road | 0 | 44167 |  | 55 | 44172 | SSF-20201118-1 | Dozer continue working on Hensen road shaping and leveling ruts for freezeing - SSF-1407 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4453KL-20201118-153rd Party Services2069.822069.82 | KABI LAKE FOREST PRODUCTS LTD4453KL-20201118-153rd Party Services2069.822069.82OEWT-PA11-LEM | [5 empty] | 1 | 2069.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4461 | KL-20201119-7 | 53510812 | Access | 0 | 3rd Party Services | 1 | 90 | Each |  |  |  |  | 90 | 11.7 | 101.7 | 2020-11-19 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 9 Padda Roadlines Triaxles hauling pit run from 5km pit on 100 road to E028/E027 corduroy/ Supervision of Padda Roadlines. Cleaning of road entrance at Silver City X 2 - AM-60225. Spreading Gravel from Triaxles with Linkbelt 290 onto Geo covered corduroy wetland on Silver City Road - AM-60224. Hauled pit run from 5km pit on 100 road to E028/E027 corduroy and 4" minus on AU1 Access. | 8 | E025-E036 | Silver City | 0 | 44167 |  | 47 | 44172 | AM-20201119-2 | Cleaning of road entrance at Silver City X 2 - AM-60225 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4461KL-20201119-73rd Party Services9090 | KABI LAKE FOREST PRODUCTS LTD4461KL-20201119-73rd Party Services9090OEWT-PA11-LEM | [5 empty] | 1 | 90 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4468 | KL-20201119-14 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2069.82 | Each |  |  |  |  | 2069.82 | 269.0766 | 2338.8966 | 2020-11-19 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continue working on Hensen Road shaping and Leveling ruts for freezing - SSF-14076. Dozer continue working on Hensen Road shaping and Leveling ruts for freezing - SSF-14076 | 11 | F119-F134 | Hensen Road | 0 | 44167 |  | 55 | 44172 | SSF-20201119-1 | Dozer continue working on Hensen Road shaping and Leveling ruts for freezing - SSF-14076 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4468KL-20201119-143rd Party Services2069.822069.82 | KABI LAKE FOREST PRODUCTS LTD4468KL-20201119-143rd Party Services2069.822069.82OEWT-PA11-LEM | [5 empty] | 1 | 2069.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4482 | KL-20201120-8 | 53510711 | Access | 0 | 3rd Party Services | 1 | 329.5 | Each |  |  |  |  | 329.5 | 42.835 | 372.335 | 2020-11-20 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Build branch road from WC 8800 to D084. Haul pit run to dozer and stock pile. Sand road to tailings pond. | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44167 |  | 47 | 44173 | CR-20201120-4 | Sand Road from Hwy to Tail Pond CR-101012 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4482KL-20201120-83rd Party Services329.5329.5 | KABI LAKE FOREST PRODUCTS LTD4482KL-20201120-83rd Party Services329.5329.5OEWT-PA11-LEM | [5 empty] | 1 | 329.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4483 | KL-20201120-9 | 53510812 | Access | 0 | 3rd Party Services | 1 | 90 | Each |  |  |  |  | 90 | 11.7 | 101.7 | 2020-11-20 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 6 Padda Hauling pit run from 5km pit on 100 Rd to E028/E027 corduroy/Supervison of Padda Roadlines. Spreading gravel on corduroy, cleaning Hwy entrance. | 8 | E025-E036 | Silver City | 0 | 44167 |  | 47 | 44173 | AM-20201120-2 | clean road entrance at Hwy from gravel haul AM-60227 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4483KL-20201120-93rd Party Services9090 | KABI LAKE FOREST PRODUCTS LTD4483KL-20201120-93rd Party Services9090OEWT-PA11-LEM | [5 empty] | 1 | 90 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4493 | KL-20201120-19 | 53511112 | Access | 0 | 3rd Party Services | 1 | 1150.18 | Each |  |  |  |  | 1150.18 | 149.5234 | 1299.7034 | 2020-11-20 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | dozer repairing road from hwy, fixing washouts, pot holes etc. Placing trees in ravine for buncher access. | 11 | F119-F134 | Hensen Road | 0 | 44167 |  | 48 | 44171 | CR-20201120-7 | dozer repairing road from hwy, fixing washouts, pot holes etc CR-101009 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4493KL-20201120-193rd Party Services1150.181150.18 | KABI LAKE FOREST PRODUCTS LTD4493KL-20201120-193rd Party Services1150.181150.18OEWT-PA11-LEM | [5 empty] | 1 | 1150.18 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4493 | KL-20201120-19 | 53511102 | Access | 0 | 3rd Party Services | 1 | 3126.82 | Each |  |  |  |  | 3126.82 | 406.4866 | 3533.3066 | 2020-11-20 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | dozer repairing road from hwy, fixing washouts, pot holes etc. Placing trees in ravine for buncher access. | 11 | F119-F134 | Hensen Road | 0 | 44167 |  | 48 | 44171 | CR-20201120-8 | 336 placing trees in ravine to allow buncher to proceed forward CR-101010 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4493KL-20201120-193rd Party Services3126.823126.82 | KABI LAKE FOREST PRODUCTS LTD4493KL-20201120-193rd Party Services3126.823126.82OEWT-PA11-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 3126.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4494 | KL-20201120-20 | 53541105 | Reclamation | 0 | 3rd Party Services | 1 | 1283 | Each |  |  |  |  | 1283 | 166.79 | 1449.79 | 2020-11-20 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Erosion Cont Inst/Mon/Rem |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer placing and repairing silt fence where required, cleaning up site CR-101011 | 11 | F119-F134 | Hensen Road | 0 | 44167 |  | 48 | 44171 | CR-20201120-9 | Labourer placing and repairing silt fence where required, cleaning up site CR-101011 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4494KL-20201120-203rd Party Services12831283 | KABI LAKE FOREST PRODUCTS LTD4494KL-20201120-203rd Party Services12831283OEWT-PA11-LEM |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1283 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4503 | KL-20201121-4 | 53510711 | Access | 0 | 3rd Party Services | 1 | 329.5 | Each |  |  |  |  | 329.5 | 42.835 | 372.335 | 2020-12-02 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pit run from Cress pit to D083/D084 access & corduroy/Supervision of 3 Padda Trucks | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44167 |  | 54 | 44548 | CR-20201121-2 | Sand Road CR-10973 |  |  |  | Betty Moghrabi | 07 | KABI LAKE FOREST PRODUCTS LTD4503KL-20201121-43rd Party Services329.5329.5 | KABI LAKE FOREST PRODUCTS LTD4503KL-20201121-43rd Party Services329.5329.5OEWT-PA12-LEM-R1 | [5 empty] | 1 | 329.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4520 | KL-20201121-21 | 53511102 | Access | 0 | 3rd Party Services | 1 | 3017.82 | Each |  |  |  |  | 3017.82 | 392.3166 | 3410.1366 | 2020-11-21 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 336 placing trees in ravine to allow buncher to proceed forward, dozer repairing road from highway | 11 | F119-F134 | Hensen Road | 0 | 44167 |  | 55 | 44175 | CR-20201121-7 | 336 placing trees in ravine to allow buncher to proceed forward Cr-10969 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4520KL-20201121-213rd Party Services3017.823017.82 | KABI LAKE FOREST PRODUCTS LTD4520KL-20201121-213rd Party Services3017.823017.82OEWT-PA11-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 3017.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4545 | KL-20201122-3 | 53510812 | Access | 0 | 3rd Party Services | 1 | 264 | Each |  |  |  |  | 264 | 34.32 | 298.32 | 2020-11-22 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator adjusting road, spread rock over Geo , labourers assist in Burritos / Sweep gravel off hwy at entrance/ Cat 330 spreading gravel over corduroy and install Geo | 8 | E025-E036 | Silver City | 0 | 44172 |  | 47 | 44183 | AM-20201122-3 | Sweep gravel off highway at silver City Road entrance am/pm - AM-60236 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4545KL-20201122-33rd Party Services264264 | KABI LAKE FOREST PRODUCTS LTD4545KL-20201122-33rd Party Services264264OEWT-PA11-LEM | [5 empty] | 1 | 264 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4555 | KL-20201122-13 | 53511112 | Access | 0 | 3rd Party Services | 1 | 484.36 | Each |  |  |  |  | 484.36 | 62.9668 | 547.3268 | 2020-11-22 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shape level ruts on access F174 to F141 for Freezing - MC-13073 | 11 | F171-F176 | High Falls Road- 1 | 0 | 44172 |  | 55 | 44175 | MC-20201122-1 | Shape level ruts on access F174 to F141 for Freezing - MC-13073 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4555KL-20201122-133rd Party Services484.36484.36 | KABI LAKE FOREST PRODUCTS LTD4555KL-20201122-133rd Party Services484.36484.36OEWT-PA11-LEM | [5 empty] | 1 | 484.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4564 | KL-20201123-2 | 53510711 | Access | 0 | 3rd Party Services | 1 | 1682 | Each |  |  |  |  | 1682 | 218.66 | 1900.66 | 2020-11-23 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade and sand road - CR-10985 / Build road, load trucks, spread gravel - CR-10986/ Haul Gravel - PD-99102 | 7 | D080-D093 | Yellow Brick Road West | 0 | 44172 |  | 47 | 44175 | CR-20201123-2 | Grader clearing snow and mud, sander sanding road - CR-10985 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4564KL-20201123-23rd Party Services16821682 | KABI LAKE FOREST PRODUCTS LTD4564KL-20201123-23rd Party Services16821682OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1682 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4565 | KL-20201123-3 | 53510711 | Access | 0 | 3rd Party Services | 1 | 264 | Each |  |  |  |  | 264 | 34.32 | 298.32 | 2020-11-23 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clean road entrance -AM-60239 / Put up signs - AM-60240 / Laying out Geo - AM-60243 | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44172 |  | 47 | 44257 | AM-20201123-2 | Sweeping off highway entrance am/pm 30mins each time - CR-60239 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4565KL-20201123-33rd Party Services264264 | KABI LAKE FOREST PRODUCTS LTD4565KL-20201123-33rd Party Services264264OEWT-PA14-Lem-R1 | [5 empty] | 1 | 264 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4584 | KL-20201123-22 | 53511112 | Access | 0 | 3rd Party Services | 1 | 1220.09 | Each |  |  |  |  | 1220.09 | 158.6117 | 1378.7017 | 2020-11-23 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul existing material to F108 access corduroy. Placing mats - CR-10983 / installing culverts - CR-10982. Dozer scraping Hensen Road for Truck access - SSF-14079. Skid trees from road/Access log deck up to new cut MOC for additional corduroy - SSF-14078. | 11 | F119-F134 | Hensen Road | 0 | 44172 |  | 55 | 44175 | SSF-20201123-1 | Dozer scraping Hensen Road for Truck access - SSF-14079 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4584KL-20201123-223rd Party Services1220.091220.09 | KABI LAKE FOREST PRODUCTS LTD4584KL-20201123-223rd Party Services1220.091220.09OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1220.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4584 | KL-20201123-22 | 53511102 | Access | 0 | 3rd Party Services | 1 | 2765.64 | Each |  |  |  |  | 2765.64 | 359.5332 | 3125.1732 | 2020-11-23 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul existing material to F108 access corduroy. Placing mats - CR-10983 / installing culverts - CR-10982. Dozer scraping Hensen Road for Truck access - SSF-14079. Skid trees from road/Access log deck up to new cut MOC for additional corduroy - SSF-14078. | 11 | F119-F134 | Hensen Road | 0 | 44172 |  | 55 | 44175 | SSF-20201123-2 | Skid trees from road/Access log deck up to new cut MOC for additional corduroy - SSF-14078 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4584KL-20201123-223rd Party Services2765.642765.64 | KABI LAKE FOREST PRODUCTS LTD4584KL-20201123-223rd Party Services2765.642765.64OEWT-PA12-LEM-R1 |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 2765.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4602 | KL-20201124-5 | 53510812 | Access | 0 | 3rd Party Services | 1 | 90 | Each |  |  |  |  | 90 | 11.7 | 101.7 | 2020-11-24 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 2 triaxles hauling from 5km pit 100 road to E026/ E025 | 8 | E025-E036 | Silver City | 0 | 44172 |  | 47 | 44179 | AM-20201124-2 | Hauling wood chips from Cress Excavator@structure 120 to BMC dozer @ 123 to 125 fixing road - AM-60244 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4602KL-20201124-53rd Party Services9090 | KABI LAKE FOREST PRODUCTS LTD4602KL-20201124-53rd Party Services9090OEWT-PA11-LEM | [5 empty] | 1 | 90 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4616 | KL-20201124-18 | 53511112 | Access | 0 | 3rd Party Services | 1 | 1499.45 | Each |  |  |  |  | 1499.45 | 194.9285 | 1694.3785 | 2020-11-24 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer blading road - CR-10988 /Corduroy - CR-10987 / Skid trees for Corduroy - SSF-14083 / Skid trees to excavator for corduroy - SSF-14080 | 11 | F119-F134 | Hensen Road | 0 | 44172 |  | 55 | 44179 | CR-20201124-5 | Dozer blading road up from WC 11900.01 past WC 15103 and into WC 15105 - CR-10988 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4616KL-20201124-183rd Party Services1499.451499.45 | KABI LAKE FOREST PRODUCTS LTD4616KL-20201124-183rd Party Services1499.451499.45OEWT-PA11-LEM | [5 empty] | 1 | 1499.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4616 | KL-20201124-18 | 53511103 | Access | 0 | 3rd Party Services | 1 | 4103.86 | Each |  |  |  |  | 4103.86 | 533.5018 | 4637.3618 | 2020-11-24 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer blading road - CR-10988 /Corduroy - CR-10987 / Skid trees for Corduroy - SSF-14083 / Skid trees to excavator for corduroy - SSF-14080 | 11 | F119-F134 | Hensen Road | 0 | 44172 |  | 55 | 44179 | CR-20201124-6 | 330 Layed corduroy past WC 15103, 336 placing corduroy just past WC 15105, labourers brought geo to work area past WC 15103 - CR-10987 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4616KL-20201124-183rd Party Services4103.864103.86 | KABI LAKE FOREST PRODUCTS LTD4616KL-20201124-183rd Party Services4103.864103.86OEWT-PA11-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 4103.86 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4616 | KL-20201124-18 | 53511103 | Access | 0 | 3rd Party Services | 1 | 1290.73 | Each |  |  |  |  | 1290.73 | 167.7949 | 1458.5249 | 2020-11-24 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer blading road - CR-10988 /Corduroy - CR-10987 / Skid trees for Corduroy - SSF-14083 / Skid trees to excavator for corduroy - SSF-14080 | 11 | F119-F134 | Hensen Road | 0 | 44172 |  | 55 | 44179 | SSF-20201124-1 | Skid trees from road/ Access log deck to Buncher for corduroy @ F117 Access - SSF-14083 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4616KL-20201124-183rd Party Services1290.731290.73 | KABI LAKE FOREST PRODUCTS LTD4616KL-20201124-183rd Party Services1290.731290.73OEWT-PA11-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 1290.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4616 | KL-20201124-18 | 53511103 | Access | 0 | 3rd Party Services | 1 | 1771.09 | Each |  |  |  |  | 1771.09 | 230.2417 | 2001.3317 | 2020-11-24 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer blading road - CR-10988 /Corduroy - CR-10987 / Skid trees for Corduroy - SSF-14083 / Skid trees to excavator for corduroy - SSF-14080 | 11 | F119-F134 | Hensen Road | 0 | 44172 |  | 55 | 44179 | SSF-20201124-2 | Skid trees from road/ Access log deck to Cress Excavator for corduroy @ F117 Access - SSF-14080 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4616KL-20201124-183rd Party Services1771.091771.09 | KABI LAKE FOREST PRODUCTS LTD4616KL-20201124-183rd Party Services1771.091771.09OEWT-PA11-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 1771.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4622 | KL-20201124-24 | 53511112 | Access | 0 | 3rd Party Services | 1 | 968.73 | Each |  |  |  |  | 968.73 | 125.9349 | 1094.6649 | 2020-11-24 | 0 | OEWT-PA11-LEM | 44187 | 33 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping and doing repairs 17 to 15 km on hensen road - SSF-14081 | 11 | F119-F134 | Hensen Road | 0 | 44172 |  | 55 | 44179 | SSF-20201124-3 | Excavator shaping and doing repairs 17 to 15 km on hensen road - SSF-14081 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4622KL-20201124-243rd Party Services968.73968.73 | KABI LAKE FOREST PRODUCTS LTD4622KL-20201124-243rd Party Services968.73968.73OEWT-PA11-LEM | [5 empty] | 1 | 968.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4626 | KL-20201125-3 | 53510711 | Access | 0 | 3rd Party Services | 1 | 514.5 | Each |  |  |  |  | 514.5 | 66.885 | 581.385 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pit run from Cress Pit to D083/D084 access & corduroy/ Supervision of Padda Roadlines. Sand and ditch road. | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44173 |  | 47 | 44227 | CR-20201125-2 | Sand Yellow Brick Rd twice CR-10998 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4626KL-20201125-33rd Party Services514.5514.5 | KABI LAKE FOREST PRODUCTS LTD4626KL-20201125-33rd Party Services514.5514.5OEWT-PA12-LEM-R1 | [5 empty] | 1 | 514.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4631 | KL-20201125-8 | 53510812 | Access | 0 | 3rd Party Services | 1 | 90 | Each |  |  |  |  | 90 | 11.7 | 101.7 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clean road from structure 125 turnaround. Clean up left over cardboard and geo. AM-60251 | 8 | E025-E036 | Silver City | 0 | 44173 |  | 47 | 44183 | AM-20201125-4 | Clean road from structure 125 turnaround. Clean up left over cardboard and geo. AM-60251 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4631KL-20201125-83rd Party Services9090 | KABI LAKE FOREST PRODUCTS LTD4631KL-20201125-83rd Party Services9090OEWT-PA12-LEM-R1 | [5 empty] | 1 | 90 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4645 | KL-20201125-21 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1884.64 | Each |  |  |  |  | 1884.64 | 245.0032 | 2129.6432 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer cleared road, excavator moving wood off roadline. Bringing geotec, signs to Hensen Road. | 11 | F119-F134 | Hensen Road | 0 | 44173 |  | 55 | 44182 | CR-20201125-6 | Dozer cleared road from WC 11900.01, past WC 15103, and into WC 15103. Also cleared into F117 CR-10996 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4645KL-20201125-213rd Party Services1884.641884.64 | KABI LAKE FOREST PRODUCTS LTD4645KL-20201125-213rd Party Services1884.641884.64OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1884.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4645 | KL-20201125-21 | 53511102 | Access | 0 | 3rd Party Services | 1 | 2549.46 | Each |  |  |  |  | 2549.46 | 331.4298 | 2880.8898 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer cleared road, excavator moving wood off roadline. Bringing geotec, signs to Hensen Road. | 11 | F119-F134 | Hensen Road | 0 | 44173 |  | 55 | 44182 | CR-20201125-7 | Excavators moving hand fall wood out of way to build road. Ok from Valard for hourly rate to move. CR-10997 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4645KL-20201125-213rd Party Services2549.462549.46 | KABI LAKE FOREST PRODUCTS LTD4645KL-20201125-213rd Party Services2549.462549.46OEWT-PA12-LEM-R1 |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 2549.46 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4645 | KL-20201125-21 | 53511103 | Access | 0 | 3rd Party Services | 1 | 1053 | Each |  |  |  |  | 1053 | 136.89 | 1189.89 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer cleared road, excavator moving wood off roadline. Bringing geotec, signs to Hensen Road. | 11 | F119-F134 | Hensen Road | 0 | 44173 |  | 55 | 44182 | CR-20201125-8 | Load up geo, signs, and posts and take to Henson Rd from Valard's yard in Marathon CR101000 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4645KL-20201125-213rd Party Services10531053 | KABI LAKE FOREST PRODUCTS LTD4645KL-20201125-213rd Party Services10531053OEWT-PA12-LEM-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 1053 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4646 | KL-20201125-22 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1481.45 | Each |  |  |  |  | 1481.45 | 192.5885 | 1674.0385 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer removing snow, excavator laying corduroy near F-122 and F-123. | 11 | F119-F134 | Hensen Road | 0 | 44173 |  | 55 | 44182 | SSF-20201125-2 | Dozer doing snow removal on Hensen Rd hills & Corners SSF-14085 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4646KL-20201125-223rd Party Services1481.451481.45 | KABI LAKE FOREST PRODUCTS LTD4646KL-20201125-223rd Party Services1481.451481.45OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1481.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4646 | KL-20201125-22 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2269.28 | Each |  |  |  |  | 2269.28 | 295.0064 | 2564.2864 | 2020-11-25 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer removing snow, excavator laying corduroy near F-122 and F-123. | 11 | F119-F134 | Hensen Road | 0 | 44173 |  | 55 | 44182 | SSF-20201125-3 | Excavator laying corduroy on F123/F122 Access/Buncher laying corduroy on F117 Access SSF-14086 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD4646KL-20201125-223rd Party Services2269.282269.28 | KABI LAKE FOREST PRODUCTS LTD4646KL-20201125-223rd Party Services2269.282269.28OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2269.28 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4652 | KL-20201126-6 | 53510812 | Access | 0 | 3rd Party Services | 1 | 2046.46 | Each |  |  |  |  | 2046.46 | 266.0398 | 2312.4998 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fixing of signs and KM markers/High Voltage signs- AM-60252 / 290 ex and 330ex worked way into hydro line maintaining/fixing/scraping access road - AM-60254 | 8 | E004-E016 | White Lake East | 0 | 44178 |  | 47 | 44183 | AM-20201126-2 | Linkbelt 290 and Cat 330 worked way into hydro line maintaining/fixinf/scraping access road on white lake east right in the morning - AM-60254 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4652KL-20201126-63rd Party Services2046.462046.46 | KABI LAKE FOREST PRODUCTS LTD4652KL-20201126-63rd Party Services2046.462046.46OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2046.46 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4668 | KL-20201126-21 | 53511103 | Access | 0 | 3rd Party Services | 1 | 684.36 | Each |  |  |  |  | 684.36 | 88.9668 | 773.3268 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Corduroy @F123/F122 Access - SSF-14087 | 11 | F119-F134 | Hensen Road | 0 | 44178 |  | 48 | 44184 | SSF-20201126-1 | Corduroy @F123/F122 Access - SSF-14087 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4668KL-20201126-213rd Party Services684.36684.36 | KABI LAKE FOREST PRODUCTS LTD4668KL-20201126-213rd Party Services684.36684.36OEWT-PA12-LEM-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 684.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4669 | KL-20201126-22 | 53511102 | Access | 0 | 3rd Party Services | 1 | 4818.91 | Each |  |  |  |  | 4818.91 | 626.4583 | 5445.3683 | 2020-11-26 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator moving wood out of way to build road towards F116, ok from Valard for hourly work to move wood - CR-101003 | 11 | F119-F134 | Hensen Road | 0 | 44178 |  | 48 | 44184 | CR-20201126-6 | Excavator moving wood out of way to build road towards F116, ok from Valard for hourly work to move wood - CR-101003 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4669KL-20201126-223rd Party Services4818.914818.91 | KABI LAKE FOREST PRODUCTS LTD4669KL-20201126-223rd Party Services4818.914818.91OEWT-PA12-LEM-R1 |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 4818.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4678 | KL-20201127-4 | 53510812 | Access | 0 | 3rd Party Services | 1 | 440 | Each |  |  |  |  | 440 | 57.2 | 497.2 | 2020-11-27 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Scrape road, pick up signs and geotextile | 8 | E004-E016 | White Lake East | 0 | 44180 |  | 47 | 44201 | AM-20201127-1 | Right in the morning both Excavators made sure road was safe to Drive on by scrapping and tracking from stock pile to Honi - AM-60259 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4678KL-20201127-43rd Party Services440440 | KABI LAKE FOREST PRODUCTS LTD4678KL-20201127-43rd Party Services440440OEWT-PA12-LEM-R1 | [5 empty] | 1 | 440 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4693 | KL-20201128-1 | 53510711 | Access | 0 | 3rd Party Services | 1 | 3897.36 | Each |  |  |  |  | 3897.36 | 506.6568 | 4404.0168 | 2020-11-28 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul Pit Run for Cress Pit. Hauling, spreading gravel. | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44181 |  | 47 | 44201 | CR-20201128-3 | Haul sand from heron Bay pit to Yellow Brick Road. Bull dozer, loader, grader plow and sand road. |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4693KL-20201128-13rd Party Services3897.363897.36 | KABI LAKE FOREST PRODUCTS LTD4693KL-20201128-13rd Party Services3897.363897.36OEWT-PA12-LEM-R1 | [5 empty] | 1 | 3897.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4694 | KL-20201128-2 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2639.82 | Each |  |  |  |  | 2639.82 | 343.1766 | 2982.9966 | 2020-11-28 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clean roadways to structure F-115, move road from hub at F-118, and clean snow off of bridge decks | 11 | F119-F134 | Hensen Road | 0 | 44181 |  | 48 | 44203 | CR-20201128-4 | Cleaned up roadways heading into structure F115. CR-101028 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4694KL-20201128-23rd Party Services2639.822639.82 | KABI LAKE FOREST PRODUCTS LTD4694KL-20201128-23rd Party Services2639.822639.82OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2639.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4694 | KL-20201128-2 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1142 | Each |  |  |  |  | 1142 | 148.46 | 1290.46 | 2020-11-28 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clean roadways to structure F-115, move road from hub at F-118, and clean snow off of bridge decks | 11 | F119-F134 | Hensen Road | 0 | 44181 |  | 48 | 44203 | CR-20201128-6 | Labourers shovelled bridge decks at WC 11870, 15105, 15104 and 15103 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4694KL-20201128-23rd Party Services11421142 | KABI LAKE FOREST PRODUCTS LTD4694KL-20201128-23rd Party Services11421142OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1142 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4696 | KL-20201128-4 | 53510811 | Access | 0 | 3rd Party Services | 1 | 440 | Each |  |  |  |  | 440 | 57.2 | 497.2 | 2020-11-28 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Install and fix signs, scrape road for access, and haul material from stockpile to near WC 9010. | 8 | E004-E016 | White Lake East | 0 | 44180 |  | 47 | 44201 | AM-20201128-4 | Both hoes making sure road was safe to work on. Sraped and tracked from SP to HONI. AM-60266 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4696KL-20201128-43rd Party Services440440 | KABI LAKE FOREST PRODUCTS LTD4696KL-20201128-43rd Party Services440440OEWT-PA12-LEM-R1 | [5 empty] | 1 | 440 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4716 | KL-20201129-3 | 53510711 | Access | 0 | 3rd Party Services | 1 | 530 | Each |  |  |  |  | 530 | 68.9 | 598.9 | 2020-11-29 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pit run to dozer at D-84 and sand from Cress pit to stockpile at YBR. | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44181 |  | 47 | 44201 | CR-20201129-2 | Haul sand from Heron Bay pit to Yellow Brick Rd stockpile CR-101038 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4716KL-20201129-33rd Party Services530530 | KABI LAKE FOREST PRODUCTS LTD4716KL-20201129-33rd Party Services530530OEWT-PA12-LEM-R1 | [5 empty] | 1 | 530 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4719 | KL-20201129-6 | 53510811 | Access | 0 | 3rd Party Services | 1 | 440 | Each |  |  |  |  | 440 | 57.2 | 497.2 | 2020-11-29 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Skidding trees to ROW access for fill to minimize steep grades. Amikwaa scraping roads/trucks, covering geo. | 8 | E004-E016 | White Lake East | 0 | 44181 |  | 47 | 44202 | AM-20201129-1 | 290 worked from stock pile and up, 330 worked from WC 9010 down on White Lake East. Both scraped and cleaned access roads for safety AM-60268 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4719KL-20201129-63rd Party Services440440 | KABI LAKE FOREST PRODUCTS LTD4719KL-20201129-63rd Party Services440440OEWT-PA12-LEM-R1 | [5 empty] | 1 | 440 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4721 | KL-20201129-9 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2658.82 | Each |  |  |  |  | 2658.82 | 345.6466 | 3004.4666 | 2020-11-29 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hoe cleaned road up and drained water up past km 2.5 on Henson West. Labourers place dgeo past WC 105035. | 11 | F119-F134 | Hensen Road | 0 | 44181 |  | 48 | 44203 | CR-20201129-4 | Hoe cleaned road up and drained water up past km 2.5 on Henson West CR-101036 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4721KL-20201129-93rd Party Services2658.822658.82 | KABI LAKE FOREST PRODUCTS LTD4721KL-20201129-93rd Party Services2658.822658.82OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2658.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4721 | KL-20201129-9 | 53511103 | Access | 0 | 3rd Party Services | 1 | 574 | Each |  |  |  |  | 574 | 74.62 | 648.62 | 2020-11-29 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hoe cleaned road up and drained water up past km 2.5 on Henson West. Labourers place dgeo past WC 105035. | 11 | F119-F134 | Hensen Road | 0 | 44181 |  | 48 | 44203 | CR-20201129-6 | Labourers placed geo just past WC 15105--6 rolls CR-101035 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4721KL-20201129-93rd Party Services574574 | KABI LAKE FOREST PRODUCTS LTD4721KL-20201129-93rd Party Services574574OEWT-PA12-LEM-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 574 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4729 | KL-20201130-2 | 53510711 | Access | 0 | 3rd Party Services | 1 | 1538 | Each |  |  |  |  | 1538 | 199.94 | 1737.94 | 2020-11-30 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul Pit run from Cress Pit to D083/D084 Access &Corduroy/Supervision of Padda. Cress ditch road, haul sand and install culvert. | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44181 |  | 47 | 44202 | CR-20201130-3 | Hauled crusher dust and sand from Heron Bay to stockpile , 950 stockpiling and sanding road |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4729KL-20201130-23rd Party Services15381538 | KABI LAKE FOREST PRODUCTS LTD4729KL-20201130-23rd Party Services15381538OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1538 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4731 | KL-20201130-12 | 53510811 | Access | 0 | 3rd Party Services | 1 | 440 | Each |  |  |  |  | 440 | 57.2 | 497.2 | 2020-11-30 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Roll out geo, cover geo with pit run from stockpile, excavators scrape road for access. | 8 | E004-E016 | White Lake East | 0 | 44181 |  | 47 | 44202 | AM-20201130-2 | 290 worked from stockpile up and Cat 330 worked from WC 9010 down on WLE. Both cleaned and scraped access road. AM-60270 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4731KL-20201130-123rd Party Services440440 | KABI LAKE FOREST PRODUCTS LTD4731KL-20201130-123rd Party Services440440OEWT-PA12-LEM-R1 | [5 empty] | 1 | 440 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4738 | KL-20201130-11 | 53511103 | Access | 0 | 3rd Party Services | 1 | 1453.09 | Each |  |  |  |  | 1453.09 | 188.9017 | 1641.9917 | 2020-11-30 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Corduroy @ F115 and F123/F122 Access SSF-14090 | 11 | F119-F134 | Hensen Road | 0 | 44181 |  | 48 | 44203 | SSF-20201130-1 | Corduroy @ F123/F122 Access SSF-14090 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4738KL-20201130-113rd Party Services1453.091453.09 | KABI LAKE FOREST PRODUCTS LTD4738KL-20201130-113rd Party Services1453.091453.09OEWT-PA12-LEM-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 1453.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4738 | KL-20201130-11 | 53511103 | Access | 0 | 3rd Party Services | 1 | 2101.09 | Each |  |  |  |  | 2101.09 | 273.1417 | 2374.2317 | 2020-11-30 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Corduroy @ F115 and F123/F122 Access SSF-14090 | 11 | F119-F134 | Hensen Road | 0 | 44181 |  | 48 | 44203 | SSF-20201130-2 | Buncher laying corduroy @F115 Access SSF-14092 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4738KL-20201130-113rd Party Services2101.092101.09 | KABI LAKE FOREST PRODUCTS LTD4738KL-20201130-113rd Party Services2101.092101.09OEWT-PA12-LEM-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 2101.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4753 | KL-20201201-7 | 53510811 | Access | 0 | 3rd Party Services | 1 | 220 | Each |  |  |  |  | 220 | 28.6 | 248.6 | 2020-12-01 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Corduroy wetland @ 9020.00 WC Bridge Approach. Excavator scraping and cleaning road | 8 | E004-E016 | White Lake East | 0 | 44181 |  | 47 | 44202 | AM-20201201-3 | Worked from stockpile up to 2km marker. 290 scraped & cleaned road for safety in the morning. AM-60276 |  |  |  | Bruce Bennett | 08 | KABI LAKE FOREST PRODUCTS LTD4753KL-20201201-73rd Party Services220220 | KABI LAKE FOREST PRODUCTS LTD4753KL-20201201-73rd Party Services220220OEWT-PA12-LEM-R1 | [5 empty] | 1 | 220 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4756 | KL-20201201-16 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1050.91 | Each |  |  |  |  | 1050.91 | 136.6183 | 1187.5283 | 2020-12-01 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fill ruts & shape road for freezing on F123 Access. Lay corduroy at F115 and from F122 to F123 | 11 | F119-F134 | Hensen Road | 0 | 44181 |  | 48 | 44209 | SSF-20201201-1 | Fill ruts & shape road for freezing on F123 Access SSF-14095 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4756KL-20201201-163rd Party Services1050.911050.91 | KABI LAKE FOREST PRODUCTS LTD4756KL-20201201-163rd Party Services1050.911050.91OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1050.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4765 | KL-20201202-8 | 53510811 | Access | 0 | 3rd Party Services | 1 | 310 | Each |  |  |  |  | 310 | 40.3 | 350.3 | 2020-12-02 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Padda hauing pit run to stockpile. Amikwaa cleaning off bridge, sweeping mud at Hwy entrance, cleaning road. | 8 | E004-E016 | White Lake East | 0 | 44193 |  | 53 | 44453 | AM-20201202-1 | Cleaned off WC 9010 on White Lake E. Covered with ice, labourers chipping it off. AM-60277 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4765KL-20201202-83rd Party Services310310 | KABI LAKE FOREST PRODUCTS LTD4765KL-20201202-83rd Party Services310310OEWT-PA12-LEM-R1 | [5 empty] | 1 | 310 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4765 | KL-20201202-8 | 53510811 | Access | 0 | 3rd Party Services | 1 | 90 | Each |  |  |  |  | 90 | 11.7 | 101.7 | 2020-12-02 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Padda hauing pit run to stockpile. Amikwaa cleaning off bridge, sweeping mud at Hwy entrance, cleaning road. | 8 | E004-E016 | White Lake East | 0 | 44193 |  | 53 | 44453 | AM-20201202-2 | Sweep entrance on Hwy at White Lake East in the morning and afternoon. AM-60288 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4765KL-20201202-83rd Party Services9090 | KABI LAKE FOREST PRODUCTS LTD4765KL-20201202-83rd Party Services9090OEWT-PA12-LEM-R1 | [5 empty] | 1 | 90 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4765 | KL-20201202-8 | 53510811 | Access | 0 | 3rd Party Services | 1 | 549 | Each |  |  |  |  | 549 | 71.37 | 620.37 | 2020-12-02 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Padda hauing pit run to stockpile. Amikwaa cleaning off bridge, sweeping mud at Hwy entrance, cleaning road. | 8 | E004-E016 | White Lake East | 0 | 44193 |  | 53 | 44453 | AM-20201202-3 | Cleaning and scraping road for safety. 290 working from the Y to the honi on White Lake East access roads. AM-60280 Revised |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4765KL-20201202-83rd Party Services549549 | KABI LAKE FOREST PRODUCTS LTD4765KL-20201202-83rd Party Services549549OEWT-PA12-LEM-R1 | [5 empty] | 1 | 549 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4765 | KL-20201202-8 | 53510811 | Access | 0 | 3rd Party Services | 1 | 9798.82 | Each |  |  |  |  | 9798.82 | 1273.8466 | 11072.6666 | 2020-12-02 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Padda hauing pit run to stockpile. Amikwaa cleaning off bridge, sweeping mud at Hwy entrance, cleaning road. | 8 | E004-E016 | White Lake East | 0 | 44193 |  | 53 | 44453 | PD-20201202-2 | Haul pit run from 5km pit on 100 rd to stockpile PD-99117 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4765KL-20201202-83rd Party Services9798.829798.82 | KABI LAKE FOREST PRODUCTS LTD4765KL-20201202-83rd Party Services9798.829798.82OEWT-PA12-LEM-R1 | [5 empty] | 1 | 9798.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4782 | KL-20201202-24 | 53511103 | Access | 0 | 3rd Party Services | 1 | 1453.09 | Each |  |  |  |  | 1453.09 | 188.9017 | 1641.9917 | 2020-12-02 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Corduroy at F122 Access SSF-14094 | 11 | F119-F134 | Hensen Road | 0 | 44193 |  | 48 | 44203 | SSF-20201202-1 | Corduroy at F122 Access SSF-14094 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4782KL-20201202-243rd Party Services1453.091453.09 | KABI LAKE FOREST PRODUCTS LTD4782KL-20201202-243rd Party Services1453.091453.09OEWT-PA12-LEM-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 1453.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4785 | KL-20201202-26 | 53511103 | Access | 0 | 3rd Party Services | 1 | 1530.73 | Each |  |  |  |  | 1530.73 | 198.9949 | 1729.7249 | 2020-12-02 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Lay corduroy near 3Km on Hensen Road, deliver geo. | 11 | F119-F134 | Hensen Road | 0 | 44193 |  | 48 | 44203 | CR-20201202-6 | 336 layed corduroy in canyon on Hensen West at approximately km 3. CR-101051 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4785KL-20201202-263rd Party Services1530.731530.73 | KABI LAKE FOREST PRODUCTS LTD4785KL-20201202-263rd Party Services1530.731530.73OEWT-PA12-LEM-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 1530.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4785 | KL-20201202-26 | 53511103 | Access | 0 | 3rd Party Services | 1 | 649 | Each |  |  |  |  | 649 | 84.37 | 733.37 | 2020-12-02 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Lay corduroy near 3Km on Hensen Road, deliver geo. | 11 | F119-F134 | Hensen Road | 0 | 44193 |  | 48 | 44203 | CR-20201202-7 | Labourers brought 15 rolls of geo back to the end of Hensen Road from Wawa CR-101052 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4785KL-20201202-263rd Party Services649649 | KABI LAKE FOREST PRODUCTS LTD4785KL-20201202-263rd Party Services649649OEWT-PA12-LEM-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 649 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4787 | KL-20201203-7 | 53510811 | Access | 0 | 3rd Party Services | 1 | 220 | Each |  |  |  |  | 220 | 28.6 | 248.6 | 2020-12-03 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Padda Roadlines hauling pit run from 5 km pit on 100 road to stockpile/labourers sanding access to stockpile with pickup and shovels. | 8 | E004-E016 | White Lake East | 0 | 44193 |  | 53 | 44207 | AM-20201203-3 | 290 cleaning and scraping road to ensure road is safe (White Lake East from Y to honi line.) AM-60283 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4787KL-20201203-73rd Party Services220220 | KABI LAKE FOREST PRODUCTS LTD4787KL-20201203-73rd Party Services220220OEWT-PA12-LEM-R1 | [5 empty] | 1 | 220 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4789 | KL-20201203-9 | 53511011 | Access | 0 | 3rd Party Services | 1 | 2261.82 | Each |  |  |  |  | 2261.82 | 294.0366 | 2555.8566 | 2020-12-03 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Open access roads from F20-F3 JJR-70171 | 10 | F009-F020 | Paint Lake Road 1-A | 0 | 44193 |  | 50 | 44206 | JJR-20201203-1 | Open access roads from F20-F3 JJR-70171 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD4789KL-20201203-93rd Party Services2261.822261.82 | KABI LAKE FOREST PRODUCTS LTD4789KL-20201203-93rd Party Services2261.822261.82OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2261.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4802 | KL-20201203-17 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1111.09 | Each |  |  |  |  | 1111.09 | 144.4417 | 1255.5317 | 2020-12-03 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fill ruts & shape road for freezing on F123/F122 Access SSF-14099 | 11 | F119-F134 | Hensen Road | 0 | 44193 |  | 48 | 44203 | SSF-20201203-3 | Fill ruts & shape road for freezing on F123/F122 Access SSF-14099 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4802KL-20201203-173rd Party Services1111.091111.09 | KABI LAKE FOREST PRODUCTS LTD4802KL-20201203-173rd Party Services1111.091111.09OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1111.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4802 | KL-20201203-17 | 53511102 | Access | 0 | 3rd Party Services | 1 | 2951.82 | Each |  |  |  |  | 2951.82 | 383.7366 | 3335.5566 | 2020-12-03 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fill ruts & shape road for freezing on F123/F122 Access SSF-14099 | 11 | F119-F134 | Hensen Road | 0 | 44193 |  | 48 | 44203 | SSF-20201203-4 | Skidding Trees to excavator to F108/109 Access Gorge. SSF-14100 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4802KL-20201203-173rd Party Services2951.822951.82 | KABI LAKE FOREST PRODUCTS LTD4802KL-20201203-173rd Party Services2951.822951.82OEWT-PA12-LEM-R1 |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 2951.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4802 | KL-20201203-17 | 53511103 | Access | 0 | 3rd Party Services | 1 | 484.36 | Each |  |  |  |  | 484.36 | 62.9668 | 547.3268 | 2020-12-03 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fill ruts & shape road for freezing on F123/F122 Access SSF-14099 | 11 | F119-F134 | Hensen Road | 0 | 44193 |  | 48 | 44203 | SSF-20201203-5 | Corduroy @ F124 access SSF-14101 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4802KL-20201203-173rd Party Services484.36484.36 | KABI LAKE FOREST PRODUCTS LTD4802KL-20201203-173rd Party Services484.36484.36OEWT-PA12-LEM-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 484.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4806 | KL-20201209-8 | 53510811 | Access | 0 | 3rd Party Services | 1 | 77.5 | Each |  |  |  |  | 77.5 | 10.075 | 87.575 | 2020-12-09 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cleared off signs in the morning before getting into rock truck from start of road to WC801 AM-60310 | 8 | E004-E016 | White Lake East | 0 | 44194 |  | 53 | 44207 | AM-20201209-1 | Cleared off signs in the morning before getting into rock truck from start of road to WC801 AM-60310 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4806KL-20201209-83rd Party Services77.577.5 | KABI LAKE FOREST PRODUCTS LTD4806KL-20201209-83rd Party Services77.577.5OEWT-PA12-LEM-R1 | [5 empty] | 1 | 77.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4807 | KL-20201209-9 | 53510811 | Access | 0 | 3rd Party Services | 1 | 1264.45 | Each |  |  |  |  | 1264.45 | 164.3785 | 1428.8285 | 2020-12-09 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scrape road, spread sand, excavator load trucks for road build and to cover corduroy. | 8 | E004-E016 | White Lake East | 0 | 44194 |  | 53 | 44207 | AM-20201209-2 | Cat 330F scraped/scratched road from 3.5km to 2.5km down. Linkbelt 290 1km to 2.5km up for road safety for rock trucks. AM-60311 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4807KL-20201209-93rd Party Services1264.451264.45 | KABI LAKE FOREST PRODUCTS LTD4807KL-20201209-93rd Party Services1264.451264.45OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1264.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4807 | KL-20201209-9 | 53510811 | Access | 0 | 3rd Party Services | 1 | 218 | Each |  |  |  |  | 218 | 28.34 | 246.34 | 2020-12-09 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scrape road, spread sand, excavator load trucks for road build and to cover corduroy. | 8 | E004-E016 | White Lake East | 0 | 44194 |  | 53 | 44207 | AM-20201209-4 | spread buckets of fines on road where icy during hauling. AM-60309 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4807KL-20201209-93rd Party Services218218 | KABI LAKE FOREST PRODUCTS LTD4807KL-20201209-93rd Party Services218218OEWT-PA12-LEM-R1 | [5 empty] | 1 | 218 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4821 | KL-20201209-18 | 53511102 | Access | 0 | 3rd Party Services | 1 | 2228.46 | Each |  |  |  |  | 2228.46 | 289.6998 | 2518.1598 | 2020-12-09 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Install signs on Hensen road, lay corduroy at 4.2Km | 11 | F119-F134 | Hensen Road | 0 | 44194 |  | 48 | 44203 | CR-20201209-6 | 330 and 336 laying corduroy at approx km 4.2 Hensen Rd. CR-101088 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4821KL-20201209-183rd Party Services2228.462228.46 | KABI LAKE FOREST PRODUCTS LTD4821KL-20201209-183rd Party Services2228.462228.46OEWT-PA12-LEM-R1 |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 2228.46 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4822 | KL-20201209-19 | 53541105 | Reclamation | 0 | 3rd Party Services | 1 | 419 | Each |  |  |  |  | 419 | 54.47 | 473.47 | 2020-12-09 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Erosion Cont Inst/Mon/Rem |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Installed silt fence at wetland, culvert draining area. CR-101090 | 11 | F119-F134 | Hensen Road | 0 | 44194 |  | 48 | 44203 | CR-20201209-5 | Installed silt fence at wetland, culvert draining area. CR-101090 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4822KL-20201209-193rd Party Services419419 | KABI LAKE FOREST PRODUCTS LTD4822KL-20201209-193rd Party Services419419OEWT-PA12-LEM-R1 |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 419 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4823 | KL-20201209-20 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1017.82 | Each |  |  |  |  | 1017.82 | 132.3166 | 1150.1366 | 2020-12-09 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade High Falls #9 Road. SSF-14110 | 11 | F203-F211 | High Falls Road- 9 | 0 | 44194 |  | 48 | 44203 | SSF-20201209-1 | Grade High Falls #9 Road. SSF-14110 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4823KL-20201209-203rd Party Services1017.821017.82 | KABI LAKE FOREST PRODUCTS LTD4823KL-20201209-203rd Party Services1017.821017.82OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1017.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4824 | KL-20201209-21 | 53511103 | Access | 0 | 3rd Party Services | 1 | 2646.54 | Each |  |  |  |  | 2646.54 | 344.0502 | 2990.5902 | 2020-12-09 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Skid trees to Excavator to F108/F109 Access/Buncher laying corduroy @F109 Access Wetland. SSF-14111 | 11 | F119-F134 | Hensen Road | 0 | 44194 |  | 48 | 44203 | SSF-20201209-2 | Skid trees to Excavator to F108/F109 Access/Buncher laying corduroy @F109 Access Wetland. SSF-14111 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4824KL-20201209-213rd Party Services2646.542646.54 | KABI LAKE FOREST PRODUCTS LTD4824KL-20201209-213rd Party Services2646.542646.54OEWT-PA12-LEM-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 2646.54 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4836 | KL-20201212-1 | 53510711 | Access | 0 | 3rd Party Services | 1 | 785.73 | Each |  |  |  |  | 785.73 | 102.1449 | 887.8749 | 2020-12-12 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader went to site to plow roadway and sites for trucks. CR-101123 | 7 | D-032 to D-055 | Black River | 0 | 44195 |  | 47 | 44203 | CR-20201212-1 | 930 plowed road for trucks. CR-101123 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4836KL-20201212-13rd Party Services785.73785.73 | KABI LAKE FOREST PRODUCTS LTD4836KL-20201212-13rd Party Services785.73785.73OEWT-PA12-LEM-R1 | [5 empty] | 1 | 785.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4843 | KL-20201212-8 | 53510811 | Access | 0 | 3rd Party Services | 1 | 220 | Each |  |  |  |  | 220 | 28.6 | 248.6 | 2020-12-12 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 290 Helped skidder with corduroy, and cleaned up left over wood. 330 dug material to cover corduroy. Labourers install signage at 4km | 8 | E004-E016 | White Lake East | 0 | 44195 |  | 53 | 44208 | AM-20201212-4 | Cleaned up wood left over. AM-60325 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4843KL-20201212-83rd Party Services220220 | KABI LAKE FOREST PRODUCTS LTD4843KL-20201212-83rd Party Services220220OEWT-PA12-LEM-R1 | [5 empty] | 1 | 220 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4847 | KL-20201212-12 | 53511102 | Access | 0 | 3rd Party Services | 1 | 1352.73 | Each |  |  |  |  | 1352.73 | 175.8549 | 1528.5849 | 2020-12-12 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer rolling out geo and hoe covering up corduroy at km 3 gorge. CR-101125 | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 48 | 44203 | CR-20201212-3 | roll geo & cover cord at km 3 gorge CR-101125 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4847KL-20201212-123rd Party Services1352.731352.73 | KABI LAKE FOREST PRODUCTS LTD4847KL-20201212-123rd Party Services1352.731352.73OEWT-PA12-LEM-R1 |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 1352.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4854 | KL-20201213-3 | 53510811 | Access | 0 | 3rd Party Services | 1 | 1867 | Each |  |  |  |  | 1867 | 242.71 | 2109.71 | 2020-12-13 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Scratch road to increase traction for gravel haul. Dig material for road building, and load trucks for corduroy. | 8 | E004-E016 | White Lake East | 0 | 44195 |  | 53 | 44209 | AM-20201213-1 | Made road safe - AM-60330 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4854KL-20201213-33rd Party Services18671867 | KABI LAKE FOREST PRODUCTS LTD4854KL-20201213-33rd Party Services18671867OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1867 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4905 | KL-20201205-8 | 53510811 | Access | 0 | 3rd Party Services | 1 | 462.18 | Each |  |  |  |  | 462.18 | 60.0834 | 522.2634 | 2020-12-05 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of 6 Padda Roadlines triaxles hauling pit run from 5km pit on 100 road to stockpile. Load and haul pit run to stockpile. | 8 | E004-E016 | White Lake East | 0 | 44193 |  | 53 | 44207 | AM-20201205-2 | 290 cleaned & scraped trk turn around AM-60289 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4905KL-20201205-83rd Party Services462.18462.18 | KABI LAKE FOREST PRODUCTS LTD4905KL-20201205-83rd Party Services462.18462.18OEWT-PA12-LEM-R1 | [5 empty] | 1 | 462.18 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4914 | KL-20201206-1 | 53510711 | Access | 0 | 3rd Party Services | 1 | 329.5 | Each |  |  |  |  | 329.5 | 42.835 | 372.335 | 2020-12-06 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | haul pitrun from Cress pit to D080/ D081 acess and Corduroy/ Supervision of gravel haul. Trucks hauling gravel, Cress also sanding roads and laying corduroy. | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44193 |  | 47 | 44202 | CR-20201206-1 | Sand Roads- CR-101071 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4914KL-20201206-13rd Party Services329.5329.5 | KABI LAKE FOREST PRODUCTS LTD4914KL-20201206-13rd Party Services329.5329.5OEWT-PA12-LEM-R1 | [5 empty] | 1 | 329.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4917 | KL-20201206-4 | 53510811 | Access | 0 | 3rd Party Services | 1 | 440 | Each |  |  |  |  | 440 | 57.2 | 497.2 | 2020-12-06 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Filling in ruts for Gravel Haul - AM-60295 / Clean up WLE access road - AM-60298 / Repair road at end of Shift - AM-60297 | 8 | E004-E016 | White Lake East | 0 | 44193 |  | 53 | 44202 | AM-20201206-3 | Repair ruts - AM-60295 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4917KL-20201206-43rd Party Services440440 | KABI LAKE FOREST PRODUCTS LTD4917KL-20201206-43rd Party Services440440OEWT-PA12-LEM-R1 | [5 empty] | 1 | 440 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4917 | KL-20201206-4 | 53510811 | Access | 0 | 3rd Party Services | 1 | 440 | Each |  |  |  |  | 440 | 57.2 | 497.2 | 2020-12-06 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Filling in ruts for Gravel Haul - AM-60295 / Clean up WLE access road - AM-60298 / Repair road at end of Shift - AM-60297 | 8 | E004-E016 | White Lake East | 0 | 44193 |  | 53 | 44202 | AM-20201206-4 | Clean up Access Road - AM-60298 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4917KL-20201206-43rd Party Services440440 | KABI LAKE FOREST PRODUCTS LTD4917KL-20201206-43rd Party Services440440OEWT-PA12-LEM-R1 | [5 empty] | 1 | 440 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4917 | KL-20201206-4 | 53510811 | Access | 0 | 3rd Party Services | 1 | 242.18 | Each |  |  |  |  | 242.18 | 31.4834 | 273.6634 | 2020-12-06 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Filling in ruts for Gravel Haul - AM-60295 / Clean up WLE access road - AM-60298 / Repair road at end of Shift - AM-60297 | 8 | E004-E016 | White Lake East | 0 | 44193 |  | 53 | 44202 | AM-20201206-5 | Repair road at end of shift - AM-60297 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4917KL-20201206-43rd Party Services242.18242.18 | KABI LAKE FOREST PRODUCTS LTD4917KL-20201206-43rd Party Services242.18242.18OEWT-PA12-LEM-R1 | [5 empty] | 1 | 242.18 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4926 | KL-20201207-1 | 53510711 | Access | 0 | 3rd Party Services | 1 | 1324 | Each |  |  |  |  | 1324 | 172.12 | 1496.12 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pit run from Cress pit to D080 access and corduroy/Supervision of 3 Padda Roadlines Triaxles | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44193 |  | 47 | 44202 | CR-20201207-1 | Sand road- CR101063 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4926KL-20201207-13rd Party Services13241324 | KABI LAKE FOREST PRODUCTS LTD4926KL-20201207-13rd Party Services13241324OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1324 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4926 | KL-20201207-1 | 53510711 | Access | 0 | 3rd Party Services | 1 | 14923.91 | Each |  |  |  |  | 14923.91 | 1940.1083 | 16864.0183 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul pit run from Cress pit to D080 access and corduroy/Supervision of 3 Padda Roadlines Triaxles | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44193 |  | 47 | 44202 | CR-20201207-2 | Haul and spread gravel - CR-101064 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4926KL-20201207-13rd Party Services14923.9114923.91 | KABI LAKE FOREST PRODUCTS LTD4926KL-20201207-13rd Party Services14923.9114923.91OEWT-PA12-LEM-R1 | [5 empty] | 1 | 14923.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4930 | KL-20201207-4 | 53510711 | Access | 0 | 3rd Party Services | 1 | 979 | Each |  |  |  |  | 979 | 127.27 | 1106.27 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Use grader to clear black river road - CR-101062 | 7 | D-032 to D-055 | Black River | 0 | 44193 |  | 47 | 44202 | CR-20201207-4 | Grade Road -CR-101062 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4930KL-20201207-43rd Party Services979979 | KABI LAKE FOREST PRODUCTS LTD4930KL-20201207-43rd Party Services979979OEWT-PA12-LEM-R1 | [5 empty] | 1 | 979 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4931 | KL-20201207-5 | 53510711 | Access | 0 | 3rd Party Services | 1 | 400 | Each |  |  |  |  | 400 | 52 | 452 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Use grader to clear Valard Camp in Marathon - CR-101066 | 7 |  | Valard Yard Marathon | 0 | 44193 |  | 47 | 44202 | CR-20201207-5 | Grade Camp -CR-101066 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4931KL-20201207-53rd Party Services400400 | KABI LAKE FOREST PRODUCTS LTD4931KL-20201207-53rd Party Services400400OEWT-PA12-LEM-R1 | [5 empty] | 1 | 400 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4934 | KL-20201207-9 | 53510811 | Access | 0 | 3rd Party Services | 1 | 330 | Each |  |  |  |  | 330 | 42.9 | 372.9 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Pick up and deliver Geo - AM-60302 / Layed Geo over Corduroy - AM-60303 / Cleaning and scraping road. AM-60304 | 8 | E004-E016 | White Lake East | 0 | 44193 |  | 53 | 44207 | AM-20201207-5 | Linkbelt cleaning and scraping road. AM-60304 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4934KL-20201207-93rd Party Services330330 | KABI LAKE FOREST PRODUCTS LTD4934KL-20201207-93rd Party Services330330OEWT-PA12-LEM-R1 | [5 empty] | 1 | 330 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4944 | KL-20201208-2 | 53510711 | Access | 0 | 3rd Party Services | 1 | 329.5 | Each |  |  |  |  | 329.5 | 42.835 | 372.335 | 2020-12-08 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sand road, bring in material to continue construction of Access. | 7 | D-080 to D-093 | Yellow Brick Road West | 0 | 44194 |  | 47 | 44202 | CR-20201208-2 | Sanding road - CR-101086 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4944KL-20201208-23rd Party Services329.5329.5 | KABI LAKE FOREST PRODUCTS LTD4944KL-20201208-23rd Party Services329.5329.5OEWT-PA12-LEM-R1 | [5 empty] | 1 | 329.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4946 | KL-20201208-4 | 53510811 | Access | 0 | 3rd Party Services | 1 | 1649 | Each |  |  |  |  | 1649 | 214.37 | 1863.37 | 2020-12-08 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Move Tigercat Skidder for skidding trees for filling grade. Skid wood and place corduroy near WC 801. | 8 | E004-E016 | White Lake East | 0 | 44194 |  | 53 | 44207 | AM-20201208-1 | Road Maintenace - AM-60305 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4946KL-20201208-43rd Party Services16491649 | KABI LAKE FOREST PRODUCTS LTD4946KL-20201208-43rd Party Services16491649OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1649 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4969 | KL-20201210-8 | 53510811 | Access | 0 | 3rd Party Services | 1 | 310 | Each |  |  |  |  | 310 | 40.3 | 350.3 | 2020-12-10 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clean road from entrance to 2 Km, sand road with fines, deliver signs from Kabi shop to White Lake East | 8 | E004-E016 | White Lake East | 0 | 44195 |  | 53 | 44207 | AM-20201210-1 | Cleaned road from entrance to km2 AM-60314 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4969KL-20201210-83rd Party Services310310 | KABI LAKE FOREST PRODUCTS LTD4969KL-20201210-83rd Party Services310310OEWT-PA12-LEM-R1 | [5 empty] | 1 | 310 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4969 | KL-20201210-8 | 53510811 | Access | 0 | 3rd Party Services | 1 | 310 | Each |  |  |  |  | 310 | 40.3 | 350.3 | 2020-12-10 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clean road from entrance to 2 Km, sand road with fines, deliver signs from Kabi shop to White Lake East | 8 | E004-E016 | White Lake East | 0 | 44195 |  | 53 | 44207 | AM-20201210-2 | Sand road with stockpile fines AM-60313 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD4969KL-20201210-83rd Party Services310310 | KABI LAKE FOREST PRODUCTS LTD4969KL-20201210-83rd Party Services310310OEWT-PA12-LEM-R1 | [5 empty] | 1 | 310 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4979 | KL-20201210-18-R1 | 53511103 | Access | 0 | 3rd Party Services | 1 | 1290.72 | Each |  |  |  |  | 1290.72 | 167.7936 | 1458.5136 | 2020-12-10 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourers sanding road, skidder bringing trees for corduroy at F-108/F-109 | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 48 | 44234 | SSF-20201210-1 | Skidding trees for corduroy @ F-108/F-109 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4979KL-20201210-18-R13rd Party Services1290.721290.72 | KABI LAKE FOREST PRODUCTS LTD4979KL-20201210-18-R13rd Party Services1290.721290.72OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 1290.72 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4979 | KL-20201210-18-R1 | 53511111 | Access | 0 | 3rd Party Services | 1 | 610 | Each |  |  |  |  | 610 | 79.3 | 689.3 | 2020-12-10 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourers sanding road, skidder bringing trees for corduroy at F-108/F-109 | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 48 | 44234 | SSF-20201210-2 | Labourers sanding road |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4979KL-20201210-18-R13rd Party Services610610 | KABI LAKE FOREST PRODUCTS LTD4979KL-20201210-18-R13rd Party Services610610OEWT-PA13-LEM | [5 empty] | 1 | 610 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4987 | KL-20201213-12 | 53511102 | Access | 0 | 3rd Party Services | 1 | 4883.09 | Each |  |  |  |  | 4883.09 | 634.8017 | 5517.8917 | 2020-12-13 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Mob 950 loader, bucket, forks and blade to Hensen From Heron Bay - CR-101131 / 336 and 330 hoes cover corduroy - CR-101129 | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 48 | 44203 | CR-20201312-6 | Corduroy - CR-101129 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4987KL-20201213-123rd Party Services4883.094883.09 | KABI LAKE FOREST PRODUCTS LTD4987KL-20201213-123rd Party Services4883.094883.09OEWT-PA12-LEM-R1 |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 4883.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4991 | KL-20201211-2 | 53510711 | Access | 0 | 3rd Party Services | 1 | 284.5 | Each |  |  |  |  | 284.5 | 36.985 | 321.485 | 2020-12-11 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sand road as requested by Frank | 7 | D032-D055 | Black River West | 0 | 44195 |  | 47 | 44202 | CR-20201211-2 | Sand road as requested by Frank. CR-101119 |  |  |  | Bruce Bennett | 07 | KABI LAKE FOREST PRODUCTS LTD4991KL-20201211-23rd Party Services284.5284.5 | KABI LAKE FOREST PRODUCTS LTD4991KL-20201211-23rd Party Services284.5284.5OEWT-PA12-LEM-R1 | [5 empty] | 1 | 284.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4992 | KL-20201211-12 | 53511111 | Access | 0 | 3rd Party Services | 1 | 835.55 | Each |  |  |  |  | 835.55 | 108.6215 | 944.1715 | 2020-12-11 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load partial load @6km pit on 600 road for sanding of hill laydown 1/ load sand from F119 and sand road for float access as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 48 | 44203 | CR-20201211-3 | Excavator loading Kabi Sander - CR-101120 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4992KL-20201211-123rd Party Services835.55835.55 | KABI LAKE FOREST PRODUCTS LTD4992KL-20201211-123rd Party Services835.55835.55OEWT-PA12-LEM-R1 | [5 empty] | 1 | 835.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 4995 | KL-20201211-15 | 53511102 | Access | 0 | 3rd Party Services | 1 | 1186.73 | Each |  |  |  |  | 1186.73 | 154.2749 | 1341.0049 | 2020-12-11 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Moved road as structure F118 was in the middle of the existing road - CR-101122 | 11 | F119-F134 | Hensen Road | 0 | 44195 |  | 48 | 44203 | CR-20201211-5 | Moved road as structure F118 was in the middle of the existing road - CR-101122 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD4995KL-20201211-153rd Party Services1186.731186.73 | KABI LAKE FOREST PRODUCTS LTD4995KL-20201211-153rd Party Services1186.731186.73OEWT-PA12-LEM-R1 |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 1186.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5009 | KL-20201214-12 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1296.27 | Each |  |  |  |  | 1296.27 | 168.5151 | 1464.7851 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | SSF-14115 Snow Removal on Hensen Road / CR-101101 - install KM signs / CR-101100 - deliver Geo / CR-101099 - Corduroy | 11 | F119-F134 | Hensen Road | 0 | 44196 |  | 55 | 44209 | SSF-20201214-1 | Dozer doing snow removal on access to F127 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5009KL-20201214-123rd Party Services1296.271296.27 | KABI LAKE FOREST PRODUCTS LTD5009KL-20201214-123rd Party Services1296.271296.27OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1296.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5009 | KL-20201214-12 | 53511103 | Access | 0 | 3rd Party Services | 1 | 464.5 | Each |  |  |  |  | 464.5 | 60.385 | 524.885 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | SSF-14115 Snow Removal on Hensen Road / CR-101101 - install KM signs / CR-101100 - deliver Geo / CR-101099 - Corduroy | 11 | F119-F134 | Hensen Road | 0 | 44196 |  | 55 | 44209 | CR-20201214-3 | Labourer brought 2 rolls of Geo to wetlands before main line, Hensen Road - CR-101100 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5009KL-20201214-123rd Party Services464.5464.5 | KABI LAKE FOREST PRODUCTS LTD5009KL-20201214-123rd Party Services464.5464.5OEWT-PA12-LEM-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 464.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5009 | KL-20201214-12 | 53511103 | Access | 0 | 3rd Party Services | 1 | 4656.9 | Each |  |  |  |  | 4656.9 | 605.397 | 5262.297 | 2020-12-14 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | SSF-14115 Snow Removal on Hensen Road / CR-101101 - install KM signs / CR-101100 - deliver Geo / CR-101099 - Corduroy | 11 | F119-F134 | Hensen Road | 0 | 44196 |  | 55 | 44209 | CR-20201214-4 | 336 and 330 excavators covering corduroy heading from main line - CR-101099 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5009KL-20201214-123rd Party Services4656.94656.9 | KABI LAKE FOREST PRODUCTS LTD5009KL-20201214-123rd Party Services4656.94656.9OEWT-PA12-LEM-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 4656.9 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5016 | KL-20201215-4 | 53510811 | Access | 0 | 3rd Party Services | 1 | 360 | Each |  |  |  |  | 360 | 46.8 | 406.8 | 2020-12-15 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330 laying corduroy near WC 9040.01. Labourers cleaning signs and laying sand. | 8 | E004-E016 | White Lake East | 0 | 44198 |  | 53 | 44210 | AM-20201215-6 | Labourers used pick ups with gravel and shovels and sanded where and when rock trucks needed through out the day - AM-60344 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD5016KL-20201215-43rd Party Services360360 | KABI LAKE FOREST PRODUCTS LTD5016KL-20201215-43rd Party Services360360OEWT-PA12-LEM-R1 | [5 empty] | 1 | 360 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5026 | KL-20201215-14 | 53511111 | Access | 0 | 3rd Party Services | 1 | 484.36 | Each |  |  |  |  | 484.36 | 62.9668 | 547.3268 | 2020-12-15 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Install overhead power signs and sand hills on Hensen Road | 11 | F119-F134 | Hensen Road | 0 | 44198 |  | 55 | 44211 | SSF-20201215-1 | Sand hills on F127 access for pick ups - SSF-14116 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5026KL-20201215-143rd Party Services484.36484.36 | KABI LAKE FOREST PRODUCTS LTD5026KL-20201215-143rd Party Services484.36484.36OEWT-PA12-LEM-R1 | [5 empty] | 1 | 484.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5037 | KL-20201216-9 | 53511111 | Access | 0 | 3rd Party Services | 1 | 4451.55 | Each |  |  |  |  | 4451.55 | 578.7015 | 5030.2515 | 2020-12-16 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Skagen and Son Forestry snow removal | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | SSF-20201216-2 | Grader plowing Hensen Road and Dozer doing snow removal on Hensen east access to F127 - SSF-14118 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5037KL-20201216-93rd Party Services4451.554451.55 | KABI LAKE FOREST PRODUCTS LTD5037KL-20201216-93rd Party Services4451.554451.55OEWT-PA12-LEM-R1 | [5 empty] | 1 | 4451.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5037 | KL-20201216-9 | 53511111 | Access | 0 | 3rd Party Services | 1 | 8084.49 | Each |  |  |  |  | 8084.49 | 1050.9837 | 9135.4737 | 2020-12-16 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Skagen and Son Forestry snow removal | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | CR-20201216-2 | 336, 330,D5 and 950 cleaning snow up Hensen west from Km 0 to 5.2, shut down some equipment due to conditions - CR-101106 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5037KL-20201216-93rd Party Services8084.498084.49 | KABI LAKE FOREST PRODUCTS LTD5037KL-20201216-93rd Party Services8084.498084.49OEWT-PA12-LEM-R1 | [5 empty] | 1 | 8084.49 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5049 | KL-20201218-10 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1228.59 | Each |  |  |  |  | 1228.59 | 159.7167 | 1388.3067 | 2020-12-18 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clearing snow from Hense Rd., Gravellng Hensen West at 2Km, widening corners to allow float access. | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | SSF-20201218-1 | Grader plowing Hensen Rd from F120 to Hwy/Dozer Plowing F127 Access. SSF-14121 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5049KL-20201218-103rd Party Services1228.591228.59 | KABI LAKE FOREST PRODUCTS LTD5049KL-20201218-103rd Party Services1228.591228.59OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1228.59 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5049 | KL-20201218-10 | 53511111 | Access | 0 | 3rd Party Services | 1 | 469 | Each |  |  |  |  | 469 | 60.97 | 529.97 | 2020-12-18 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clearing snow from Hense Rd., Gravellng Hensen West at 2Km, widening corners to allow float access. | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | CR-20201218-1 | Labourers placing markers where geo, mat, and bridges are to be placed and could be buried by snow. CR-101113 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5049KL-20201218-103rd Party Services469469 | KABI LAKE FOREST PRODUCTS LTD5049KL-20201218-103rd Party Services469469OEWT-PA12-LEM-R1 | [5 empty] | 1 | 469 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5049 | KL-20201218-10 | 53511111 | Access | 0 | 3rd Party Services | 1 | 589.55 | Each |  |  |  |  | 589.55 | 76.6415 | 666.1915 | 2020-12-18 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clearing snow from Hense Rd., Gravellng Hensen West at 2Km, widening corners to allow float access. | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | CR-20201218-2 | Dozer clearing snow from km 1 on Hensen West to WC 11790.01 CR-101114 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5049KL-20201218-103rd Party Services589.55589.55 | KABI LAKE FOREST PRODUCTS LTD5049KL-20201218-103rd Party Services589.55589.55OEWT-PA12-LEM-R1 | [5 empty] | 1 | 589.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5049 | KL-20201218-10 | 53511111 | Access | 0 | 3rd Party Services | 1 | 7730.44 | Each |  |  |  |  | 7730.44 | 1004.9572 | 8735.3972 | 2020-12-18 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clearing snow from Hense Rd., Gravellng Hensen West at 2Km, widening corners to allow float access. | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | CR-20201218-3 | Rock trucks, hoe and dozer gravelling Hensen Rd West from km2 to WC 11790.01 CR-101115 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5049KL-20201218-103rd Party Services7730.447730.44 | KABI LAKE FOREST PRODUCTS LTD5049KL-20201218-103rd Party Services7730.447730.44OEWT-PA12-LEM-R1 | [5 empty] | 1 | 7730.44 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5059 | KL-20201219-6 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2529 | Each |  |  |  |  | 2529 | 328.77 | 2857.77 | 2020-12-19 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Supervision of Skagen & Son Forestry snow removal on Hensen to Km 17. | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | SSF-20201219-1 | Grader plowing Hensen Road to 17km SSF-14122 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5059KL-20201219-63rd Party Services25292529 | KABI LAKE FOREST PRODUCTS LTD5059KL-20201219-63rd Party Services25292529OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2529 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5060 | KL-20201219-7 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2044.82 | Each |  |  |  |  | 2044.82 | 265.8266 | 2310.6466 | 2020-12-19 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Widen corners & approaches for float access, dozer plow snow from 1Km to 5Km. Labourers moving geotextile. | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 55 | 44211 | CR-20201219-2 | Dozer clearing snow from Km 1 to km5 and push outs on Hensen Rd West CR-101132 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5060KL-20201219-73rd Party Services2044.822044.82 | KABI LAKE FOREST PRODUCTS LTD5060KL-20201219-73rd Party Services2044.822044.82OEWT-PA12-LEM-R1 | [5 empty] | 1 | 2044.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5087 | KL-20201207-18 | 53511103 | Access | 0 | 3rd Party Services | 1 | 2120.28 | Each |  |  |  |  | 2120.28 | 275.6364 | 2395.9164 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Lay corduroy at 4 Km and near F-124. Skid trees to fill gorge. Labourers deliver and install geo near F-124. | 11 | F119-F134 | Hensen Road | 0 |  |  | 48 | 44203 | CR-20201207-6 | 336 and 330 laying Corduroy Henson road west at Km 4 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5087KL-20201207-183rd Party Services2120.282120.28 | KABI LAKE FOREST PRODUCTS LTD5087KL-20201207-183rd Party Services2120.282120.28OEWT-PA12-LEM-R1 |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 2120.28 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5087 | KL-20201207-18 | 53511103 | Access | 0 | 3rd Party Services | 1 | 144.5 | Each |  |  |  |  | 144.5 | 18.785 | 163.285 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Lay corduroy at 4 Km and near F-124. Skid trees to fill gorge. Labourers deliver and install geo near F-124. | 11 | F119-F134 | Hensen Road | 0 |  |  | 48 | 44203 | CR-20201207-8 | Labourers brought Geo to site location - CR-101069 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5087KL-20201207-183rd Party Services144.5144.5 | KABI LAKE FOREST PRODUCTS LTD5087KL-20201207-183rd Party Services144.5144.5OEWT-PA12-LEM-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 144.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5087 | KL-20201207-18 | 53511102 | Access | 0 | 3rd Party Services | 1 | 2120.28 | Each |  |  |  |  | 2120.28 | 275.6364 | 2395.9164 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Lay corduroy at 4 Km and near F-124. Skid trees to fill gorge. Labourers deliver and install geo near F-124. | 11 | F119-F134 | Hensen Road | 0 |  |  | 48 | 44203 | SSF-20201207-1 | Skidding trees to excavator to F108/F109 access Gorge - SSF-14107 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5087KL-20201207-183rd Party Services2120.282120.28 | KABI LAKE FOREST PRODUCTS LTD5087KL-20201207-183rd Party Services2120.282120.28OEWT-PA12-LEM-R1 |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 2120.28 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5087 | KL-20201207-18 | 53511103 | Access | 0 | 3rd Party Services | 1 | 1453.09 | Each |  |  |  |  | 1453.09 | 188.9017 | 1641.9917 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Lay corduroy at 4 Km and near F-124. Skid trees to fill gorge. Labourers deliver and install geo near F-124. | 11 | F119-F134 | Hensen Road | 0 |  |  | 48 | 44203 | SSF-20201207-2 | Corduroy @ F124/F125 Access - SFF-14106 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5087KL-20201207-183rd Party Services1453.091453.09 | KABI LAKE FOREST PRODUCTS LTD5087KL-20201207-183rd Party Services1453.091453.09OEWT-PA12-LEM-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 1453.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5087 | KL-20201207-18 | 53511103 | Access | 0 | 3rd Party Services | 1 | 870 | Each |  |  |  |  | 870 | 113.1 | 983.1 | 2020-12-07 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Lay corduroy at 4 Km and near F-124. Skid trees to fill gorge. Labourers deliver and install geo near F-124. | 11 | F119-F134 | Hensen Road | 0 |  |  | 48 | 44203 | SSF-20201207-3 | labourers Laying Geo @F124 - SSF-14105 |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5087KL-20201207-183rd Party Services870870 | KABI LAKE FOREST PRODUCTS LTD5087KL-20201207-183rd Party Services870870OEWT-PA12-LEM-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 870 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5088 | KL-20201204-21 | 53511103 | Access | 0 | 3rd Party Services | 1 | 726.55 | Each |  |  |  |  | 726.55 | 94.4515 | 821.0015 | 2020-12-04 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Skidding trees to excavator to F108/F109 Access Gorge. Laying corduroy at F-124. | 11 | F119-F134 | Hensen Road | 0 |  |  | 48 | 44216 | SSF-20201204-2 | Corduroy @F124 Access |  |  |  | Larse Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5088KL-20201204-213rd Party Services726.55726.55 | KABI LAKE FOREST PRODUCTS LTD5088KL-20201204-213rd Party Services726.55726.55OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 726.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5091 | KL-20201204-24 | 53511011 | Access | 0 | 3rd Party Services | 1 | 2463 | Each |  |  |  |  | 2463 | 320.19 | 2783.19 | 2020-12-04 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Opening access roads from F20 to F3 JJR-70176 | 10 | F009-F020 | Paint Lake Road 1-A | 0 |  |  | 50 | 44212 | JJR-20201204-3 | Opening access roads from F20 to F3 JJR-70176 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5091KL-20201204-243rd Party Services24632463 | KABI LAKE FOREST PRODUCTS LTD5091KL-20201204-243rd Party Services24632463OEWT-PA13-LEM | [5 empty] | 1 | 2463 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5106 | KL-20201217-14 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1160.91 | Each |  |  |  |  | 1160.91 | 150.9183 | 1311.8283 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Road - SSF-14119 / Snow Removal - CR-101107 / Widening Turn Around - CR-101111 | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 15 | 44211 | SSF-20201217-1 | Grade roads - SSF-14119 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5106KL-20201217-143rd Party Services1160.911160.91 | KABI LAKE FOREST PRODUCTS LTD5106KL-20201217-143rd Party Services1160.911160.91OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1160.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5106 | KL-20201217-14 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1391.1 | Each |  |  |  |  | 1391.1 | 180.843 | 1571.943 | 2020-12-17 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grading Road - SSF-14119 / Snow Removal - CR-101107 / Widening Turn Around - CR-101111 | 11 | F119-F134 | Hensen Road | 0 | 44200 |  | 15 | 44211 | CR-20201217-1 | Snow removal - CR-101107 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5106KL-20201217-143rd Party Services1391.11391.1 | KABI LAKE FOREST PRODUCTS LTD5106KL-20201217-143rd Party Services1391.11391.1OEWT-PA12-LEM-R1 | [5 empty] | 1 | 1391.1 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5114 | KL-20201220-1 | 53510811 | Access | 0 | 3rd Party Services | 1 | 270 | Each |  |  |  |  | 270 | 35.1 | 305.1 | 2020-12-20 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sand hills with pick up and shovel, install blind hill signs on White Lake East. | 8 | E004-E016 | White Lake East | 0 | 43834 |  | 53 | 44211 | AM-20201220-1 | sand hills with pick up and shovel AM-60354 |  |  |  | Clint Maerz | 08 | KABI LAKE FOREST PRODUCTS LTD5114KL-20201220-13rd Party Services270270 | KABI LAKE FOREST PRODUCTS LTD5114KL-20201220-13rd Party Services270270OEWT-PA12-LEM-R1 | [5 empty] | 1 | 270 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5158 | KL-20201228-9 | 53511103 | Access | 0 | 3rd Party Services | 1 | 2387.09 | Each |  |  |  |  | 2387.09 | 310.3217 | 2697.4117 | 2020-12-28 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hoe covered up corduroy and labourers rolled out geo for section of wetland before F108. Cloth was frozen, had to use torches to unroll. CR-101137 | 11 | F119-F134 | Hensen Road | 0 | 44202 |  | 56 | 44214 | CR-20201228-1 | Cover corduroy and lay geo F108 CR-101137 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5158KL-20201228-93rd Party Services2387.092387.09 | KABI LAKE FOREST PRODUCTS LTD5158KL-20201228-93rd Party Services2387.092387.09OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 2387.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5160 | KL-20201228-11 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2339 | Each |  |  |  |  | 2339 | 304.07 | 2643.07 | 2020-12-28 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding Hills & Corners on Hensen Rd from Hwy to Km 17 for 60' bridge delivery. Dozer and grader clearing different sections of Hensen Rd. | 11 | F119-F134 | Hensen Road | 0 | 44202 |  | 56 | 44214 | CR-20201228-3 | Dozer clearing snow on Hensen West CR-101138 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5160KL-20201228-113rd Party Services23392339 | KABI LAKE FOREST PRODUCTS LTD5160KL-20201228-113rd Party Services23392339OEWT-PA13-LEM | [5 empty] | 1 | 2339 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5160 | KL-20201228-11 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1583.27 | Each |  |  |  |  | 1583.27 | 205.8251 | 1789.0951 | 2020-12-28 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanding Hills & Corners on Hensen Rd from Hwy to Km 17 for 60' bridge delivery. Dozer and grader clearing different sections of Hensen Rd. | 11 | F119-F134 | Hensen Road | 0 | 44202 |  | 56 | 44214 | SSF-20201228-1 | Grader plowing Hensen Rd to Km 17 SSF-14123 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5160KL-20201228-113rd Party Services1583.271583.27 | KABI LAKE FOREST PRODUCTS LTD5160KL-20201228-113rd Party Services1583.271583.27OEWT-PA13-LEM | [5 empty] | 1 | 1583.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5162 | KL-20201229-1 | 53510811 | Access | 0 | 3rd Party Services | 1 | 987 | Each |  |  |  |  | 987 | 128.31 | 1115.31 | 2020-12-29 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Move 323 into White Lake East and clear snow to walk buncher in. | 8 | E004-E016 | White Lake East | 0 | 44202 |  | 36 | 44213 | CR-20201229-2 | Clear snow on walk in for buncher. CR-101144 |  |  |  | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD5162KL-20201229-13rd Party Services987987 | KABI LAKE FOREST PRODUCTS LTD5162KL-20201229-13rd Party Services987987OEWT-PA13-LEM | [5 empty] | 1 | 987 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5165 | KL-20201229-4 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1324.91 | Each |  |  |  |  | 1324.91 | 172.2383 | 1497.1483 | 2020-12-29 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanded road with loader from km 1 to km6. Hauled 1 load of sand with 740 to km4 hill. 336 Lay corduroy in wetland near WC 11775, labourer installing signs. | 11 | F119-F134 | Hensen Road | 0 | 44202 |  | 56 | 44214 | CR-20201229-3 | Sand road 1km to 6km Hensen West CR-101145 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5165KL-20201229-43rd Party Services1324.911324.91 | KABI LAKE FOREST PRODUCTS LTD5165KL-20201229-43rd Party Services1324.911324.91OEWT-PA13-LEM | [5 empty] | 1 | 1324.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5165 | KL-20201229-4 | 53511103 | Access | 0 | 3rd Party Services | 1 | 1508.91 | Each |  |  |  |  | 1508.91 | 196.1583 | 1705.0683 | 2020-12-29 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sanded road with loader from km 1 to km6. Hauled 1 load of sand with 740 to km4 hill. 336 Lay corduroy in wetland near WC 11775, labourer installing signs. | 11 | F119-F134 | Hensen Road | 0 | 44202 |  | 56 | 44214 | CR-20201229-7 | 336 Lay corduroy in wetland near WC 11775. |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5165KL-20201229-43rd Party Services1508.911508.91 | KABI LAKE FOREST PRODUCTS LTD5165KL-20201229-43rd Party Services1508.911508.91OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 1508.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5167 | KL-20201229-6 | 53531101 | Rig/Access Mats | 0 | 3rd Party Services | 1 | 883.55 | Each |  |  |  |  | 883.55 | 114.8615 | 998.4115 | 2020-12-29 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 336 placed mats at WC11775 and 11773.01 for buncher to cross. Brought in from F107.5 CR-101147 | 11 | F119-F134 | Hensen Road | 0 | 44202 |  | 56 | 44214 | CR-20201229-5 | 336 Placed mats at WC-11775 and WC-11773.01 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5167KL-20201229-63rd Party Services883.55883.55 | KABI LAKE FOREST PRODUCTS LTD5167KL-20201229-63rd Party Services883.55883.55OEWT-PA13-LEM |  |  | WF10-WaterCrossing |  |  | 1 | 883.55 | WC609 | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5177 | KL-20201230-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 3020.91 | Each |  |  |  |  | 3020.91 | 392.7183 | 3413.6283 | 2020-12-30 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | D5 plowed road into F117 to F114, 950 plowed Hensen W to km 6.5. D5 kept road clear of snow in front of equipment when pulling 50' bridges. CR-101152 | 11 | F119-F134 | Hensen Road | 0 | 44202 |  | 56 | 44215 | CR-20201230-1 | D5 Clearing road to provide access. |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5177KL-20201230-83rd Party Services3020.913020.91 | KABI LAKE FOREST PRODUCTS LTD5177KL-20201230-83rd Party Services3020.913020.91OEWT-PA13-LEM | [5 empty] | 1 | 3020.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5185 | KL-20201231-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2133.82 | Each |  |  |  |  | 2133.82 | 277.3966 | 2411.2166 | 2020-12-31 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | D5 Pushing snow and banks back from Hensen west 2.5 to 6.5 km - CR-101155 / Grader plowing Hensen Road to 17 km - SSF-14126 | 11 | F119-F134 | Hensen Road | 0 | 44204 |  | 56 | 44216 | CR-20201231-2 | D5 Pushing snow and banks back from Hensen west 2.5 to 6.5 km - CR-101155 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5185KL-20201231-83rd Party Services2133.822133.82 | KABI LAKE FOREST PRODUCTS LTD5185KL-20201231-83rd Party Services2133.822133.82OEWT-PA13-LEM | [5 empty] | 1 | 2133.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5185 | KL-20201231-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2529 | Each |  |  |  |  | 2529 | 328.77 | 2857.77 | 2020-12-31 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | D5 Pushing snow and banks back from Hensen west 2.5 to 6.5 km - CR-101155 / Grader plowing Hensen Road to 17 km - SSF-14126 | 11 | F119-F134 | Hensen Road | 0 | 44204 |  | 56 | 44216 | SSF-20201231-2 | Grader plowing Hensen road to 17 km - SSF-14126 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5185KL-20201231-83rd Party Services25292529 | KABI LAKE FOREST PRODUCTS LTD5185KL-20201231-83rd Party Services25292529OEWT-PA13-LEM | [5 empty] | 1 | 2529 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5187 | KL-20201231-10 | 53511111 | Access | 0 | 3rd Party Services | 1 | 274.36 | Each |  |  |  |  | 274.36 | 35.6668 | 310.0268 | 2020-12-31 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plowed Dore Lake Road to access of Dore lake road, Access F145 - CE-023 | 11 | F135-F149 | Dore Lake Road | 0 | 44204 |  | 56 | 44216 | CE-20201231-1 | Plowed Dore Lake Road to access of Dore lake road, Access F145 - CE-023 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5187KL-20201231-103rd Party Services274.36274.36 | KABI LAKE FOREST PRODUCTS LTD5187KL-20201231-103rd Party Services274.36274.36OEWT-PA13-LEM | [5 empty] | 1 | 274.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5202 | KL-20210102-9 | 53511103 | Access | 0 | 3rd Party Services | 1 | 9879.36 | Each |  |  |  |  | 9879.36 | 1284.3168 | 11163.6768 | 2021-01-02 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Covered corduroy with material heading into F117, covered corduroy between F107-F106 and F106- F105, labourers laying Geo | 11 | F119-F134 | Hensen Road | 0 | 44204 |  | 56 | 44216 | CR-20210102-4 | Covered corduroy with material heading into F117, covered corduroy between F107-F106 and F106- F105, labourers laying Geo |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5202KL-20210102-93rd Party Services9879.369879.36 | KABI LAKE FOREST PRODUCTS LTD5202KL-20210102-93rd Party Services9879.369879.36OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 9879.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5207 | KL-20210103-5 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1787.45 | Each |  |  |  |  | 1787.45 | 232.3685 | 2019.8185 | 2021-01-03 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load of sand from White River town pit/ sanding hills and corners on hensen road from hwy to 17km with existing material as per Valard | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 | CR-20210103-1 | D5 pushing snow at Hensen east, clearing roadways for posible bridge drag in, 336 loaded sander |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5207KL-20210103-53rd Party Services1787.451787.45 | KABI LAKE FOREST PRODUCTS LTD5207KL-20210103-53rd Party Services1787.451787.45OEWT-PA13-LEM | [5 empty] | 1 | 1787.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5216 | KL-20210104-5 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1209.18 | Each |  |  |  |  | 1209.18 | 157.1934 | 1366.3734 | 2021-01-04 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load trees into rock truck with 336 and haul to hill befroe F117 - CR-101170 / D5 pushing snow up Hensen Road east - CR-101172 | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 15 | 44218 | CR-20210104-2 | D5 pushing snow up Hensen Road east - CR-101172 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5216KL-20210104-53rd Party Services1209.181209.18 | KABI LAKE FOREST PRODUCTS LTD5216KL-20210104-53rd Party Services1209.181209.18OEWT-PA13-LEM | [5 empty] | 1 | 1209.18 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5224 | KL-20210105-3-R1 | 53510811 | Access | 0 | 3rd Party Services | 1 | 333.5 | Each |  |  |  |  | 333.5 | 43.355 | 376.855 | 2021-01-05 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Sent for revision on Jan 21, Revised back on Jan 22 |  | Approved |  |  | Met with mike from Valard , road structure E015 in the same area, moved road slightly to allow for hub, built berm at km 3.5. Assist Skidder to Access a Hill - CR-101174 | 8 | E004-E036 | White Lake East | 0 | 44207 |  | 36 | 44219 | CR-20210105-1 | Assist Skidder to Access a Hill - CR-101174 |  |  |  | Mike Lecocq | 08 | KABI LAKE FOREST PRODUCTS LTD5224KL-20210105-3-R13rd Party Services333.5333.5 | KABI LAKE FOREST PRODUCTS LTD5224KL-20210105-3-R13rd Party Services333.5333.5OEWT-PA13-LEM | [5 empty] | 1 | 333.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5233 | KL-20210105-12 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2110.82 | Each |  |  |  |  | 2110.82 | 274.4066 | 2385.2266 | 2021-01-05 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 950 plowed and sanded up Hensen Road west all day - CR-101177 | 11 | F119-F134 | Hensen Road | 0 | 44207 |  | 56 | 44218 | CR-20210105-6 | 950 plowed and sanded up Hensen Road west all day - CR-101177 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5233KL-20210105-123rd Party Services2110.822110.82 | KABI LAKE FOREST PRODUCTS LTD5233KL-20210105-123rd Party Services2110.822110.82OEWT-PA13-LEM | [5 empty] | 1 | 2110.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5243 | KL-20210106-7 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 1695.27 | Each |  |  |  |  | 1695.27 | 220.3851 | 1915.6551 | 2021-01-06 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker working on F117 access breaking outcrops on steep grades/ operator travel as per valard | 11 | F119-F134 | Hensen Road | 0 | 44209 |  | 15 | 44224 | SSF-20210106-2 | Rock Hammer support @ F117 Access - SSF-14129 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5243KL-20210106-73rd Party Services1695.271695.27 | KABI LAKE FOREST PRODUCTS LTD5243KL-20210106-73rd Party Services1695.271695.27OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 847.635 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5246 | KL-20210106-10 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1111.09 | Each |  |  |  |  | 1111.09 | 144.4417 | 1255.5317 | 2021-01-06 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer doing snow removal on Access F117 -. Skidding wood to Excavator @F104/F105/ Buncher for corduroy @ F103 Access | 11 | F119-F134 | Hensen Road | 0 | 44209 |  | 15 | 44224 | SSF-20210106-1 | Dozer doing snow removal on Access F117 - SSF-14128 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5246KL-20210106-103rd Party Services1111.091111.09 | KABI LAKE FOREST PRODUCTS LTD5246KL-20210106-103rd Party Services1111.091111.09OEWT-PA13-LEM | [5 empty] | 1 | 1111.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5262 | KL-20210107-11 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1160.91 | Each |  |  |  |  | 1160.91 | 150.9183 | 1311.8283 | 2021-01-07 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader plowing Hensen, dozer removing snow, and 950 sanding hills | 11 | F119-F134 | Hensen Road | 0 | 44209 |  | 15 | 44219 | SSF-20210107-1 | Grader plowing Hensen Rd to km 17 SSF-14133 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5262KL-20210107-113rd Party Services1160.911160.91 | KABI LAKE FOREST PRODUCTS LTD5262KL-20210107-113rd Party Services1160.911160.91OEWT-PA13-LEM | [5 empty] | 1 | 1160.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5262 | KL-20210107-11 | 53511111 | Access | 0 | 3rd Party Services | 1 | 370.36 | Each |  |  |  |  | 370.36 | 48.1468 | 418.5068 | 2021-01-07 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader plowing Hensen, dozer removing snow, and 950 sanding hills | 11 | F119-F134 | Hensen Road | 0 | 44209 |  | 15 | 44219 | SSF-20210107-2 | Dozer doing snow removal on F117 Access SSF-14132 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5262KL-20210107-113rd Party Services370.36370.36 | KABI LAKE FOREST PRODUCTS LTD5262KL-20210107-113rd Party Services370.36370.36OEWT-PA13-LEM | [5 empty] | 1 | 370.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5262 | KL-20210107-11 | 53511111 | Access | 0 | 3rd Party Services | 1 | 909.73 | Each |  |  |  |  | 909.73 | 118.2649 | 1027.9949 | 2021-01-07 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader plowing Hensen, dozer removing snow, and 950 sanding hills | 11 | F119-F134 | Hensen Road | 0 | 44209 |  | 15 | 44219 | CR-20210107-5 | 950 Sanded hills from km 1 to km6 on Hensen Rd West. CR-101187 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5262KL-20210107-113rd Party Services909.73909.73 | KABI LAKE FOREST PRODUCTS LTD5262KL-20210107-113rd Party Services909.73909.73OEWT-PA13-LEM | [5 empty] | 1 | 909.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5267 | KL-20210107-16 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 1695.27 | Each |  |  |  |  | 1695.27 | 220.3851 | 1915.6551 | 2021-01-07 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker working on F117 Access breaking outcrops on steep grades/operator travel as per Valard. Skagen excavator supporting breaker. | 11 | F119-F134 | Hensen Road | 0 | 44209 |  | 15 | 44219 | SSF-20210107-3 | Rock Hammer Support @F117 Access SSF-14131 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5267KL-20210107-163rd Party Services1695.271695.27 | KABI LAKE FOREST PRODUCTS LTD5267KL-20210107-163rd Party Services1695.271695.27OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 847.635 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5273 | KL-20210108-6 | 53511102 | Access | 0 | 3rd Party Services | 1 | 5372.34 | Each |  |  |  |  | 5372.34 | 698.4042 | 6070.7442 | 2021-01-08 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | At access to Honi there is cap rock that was to be hammered. Hammering would take too long so corduroy was done. CE-037 | 11 | F155 | Michipicoten Harbour Road -3 | 0 | 44209 |  | 56 | 44218 | CE-20210108-4 | At access to Honi there is cap rock that was to be hammered. Hammering would take too long so corduroy was done. CE-037. Buncher rate Cont. Amendment #4 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5273KL-20210108-63rd Party Services5372.345372.34 | KABI LAKE FOREST PRODUCTS LTD5273KL-20210108-63rd Party Services5372.345372.34OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 5372.34 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5275 | KL-20210108-8 | 53511103 | Access | 0 | 3rd Party Services | 1 | 10820.28 | Each |  |  |  |  | 10820.28 | 1406.6364 | 12226.9164 | 2021-01-08 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load rock trucks to cover corduroy, sand hills for rock trucks, and labourers install narrow bridge signs. | 11 | F119-F134 | Hensen Road | 0 | 44209 |  | 15 | 44219 | CR-20210108-1 | 336F loaded rock trucks then in afternoon trucks were loaded by N336 for closer haul, covered corduroy at F108 CR-101197 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5275KL-20210108-83rd Party Services10820.2810820.28 | KABI LAKE FOREST PRODUCTS LTD5275KL-20210108-83rd Party Services10820.2810820.28OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 10820.28 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5275 | KL-20210108-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 634.55 | Each |  |  |  |  | 634.55 | 82.4915 | 717.0415 | 2021-01-08 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load rock trucks to cover corduroy, sand hills for rock trucks, and labourers install narrow bridge signs. | 11 | F119-F134 | Hensen Road | 0 | 44209 |  | 15 | 44219 | CR-20210108-2 | 950 sanded hills from km2 to km5 on Hensen West for rock trucks. CR-101198 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5275KL-20210108-83rd Party Services634.55634.55 | KABI LAKE FOREST PRODUCTS LTD5275KL-20210108-83rd Party Services634.55634.55OEWT-PA13-LEM | [5 empty] | 1 | 634.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5278 | KL-20210109-1 | 53511111 | Access | 0 | 3rd Party Services | 1 | 392.36 | Each |  |  |  |  | 392.36 | 51.0068 | 443.3668 | 2021-01-09 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 950 sanded hills by F109 on Hensen West for rock trucks. 336 loaded rock trucks and D5 spreading, capping bad spots on road headed towards F104/F103 | 11 | F119-F134 | Hensen Road | 0 | 44211 |  | 15 | 44219 | CR-20210109-2 | 950 sanded hills by F109 on Hensen West for rock trucks. CR-101191 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5278KL-20210109-13rd Party Services392.36392.36 | KABI LAKE FOREST PRODUCTS LTD5278KL-20210109-13rd Party Services392.36392.36OEWT-PA13-LEM | [5 empty] | 1 | 392.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5299 | KL-20210110-12 | 53511111 | Access | 0 | 3rd Party Services | 1 | 10493.28 | Each |  |  |  |  | 10493.28 | 1364.1264 | 11857.4064 | 2021-01-10 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 336 loaded rock trucks and D5 spreading. Capping road before WC 11772 | 11 | F119-F134 | Hensen Road | 0 | 44211 |  | 15 | 44219 | CR-20210110-2 | 336 loaded rock trucks and D5 spreading. Capping road before WC 11772 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5299KL-20210110-123rd Party Services10493.2810493.28 | KABI LAKE FOREST PRODUCTS LTD5299KL-20210110-123rd Party Services10493.2810493.28OEWT-PA13-LEM | [5 empty] | 0.71325 | 7484.28 | WC493 | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5307 | KL-20210111-7 | 53511111 | Access | 0 | 3rd Party Services | 1 | 217.18 | Each |  |  |  |  | 217.18 | 28.2334 | 245.4134 | 2021-01-11 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 336 Load gravel on trucks, D5 spreading. Hoe moving wood from F-101 to F-102 due to no material to build. Road sanded for rock trucks | 11 | F119-F134 | Hensen Road | 0 | 44211 |  | 56 | 44219 | CR-20210111-2 | 950 Sanded road for rock trucks. CR-101204 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5307KL-20210111-73rd Party Services217.18217.18 | KABI LAKE FOREST PRODUCTS LTD5307KL-20210111-73rd Party Services217.18217.18OEWT-PA13-LEM | [5 empty] | 1 | 217.18 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5318 | KL-20210112-5 | 53511111 | Access | 0 | 3rd Party Services | 1 | 342.95 | Each |  |  |  |  | 342.95 | 44.5835 | 387.5335 | 2021-01-12 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Walk exc #105 out of Dore Lake Rd to MHR#2 (156-158), Exc #201 walk (152-150). Sanding Dore Lake Rd. Sand from Michipicoten First Nation sand pit | 11 | F135-F149 | Dore Lake Road | 0 | 44214 |  | 56 | 44219 | CE-20210112-2 | Sanding Dore Lake Rd. Sand from Michipicoten First Nation sand pit. CE-047 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5318KL-20210112-53rd Party Services342.95342.95 | KABI LAKE FOREST PRODUCTS LTD5318KL-20210112-53rd Party Services342.95342.95OEWT-PA13-LEM | [5 empty] | 1 | 342.95 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5325 | KL-20210112-12 | 53511111 | Access | 0 | 3rd Party Services | 1 | 217.18 | Each |  |  |  |  | 217.18 | 28.2334 | 245.4134 | 2021-01-12 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanded hills for rock trucks to haul to F103. 336 loaded rock trucks and D5 spreading, 323 sourced gravel closer to F-103, trucks went to 323 when 336 went down. | 11 | F119-F134 | Hensen Road | 0 | 44214 |  | 15 | 44233 | CR-20210112-1 | Loader sanded hills for rock trucks to haul to F103 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5325KL-20210112-123rd Party Services217.18217.18 | KABI LAKE FOREST PRODUCTS LTD5325KL-20210112-123rd Party Services217.18217.18OEWT-PA13-LEM | [5 empty] | 1 | 217.18 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5339 | KL-20210113-5 | 53511103 | Access | 0 | 3rd Party Services | 1 | 3741.12 | Each |  |  |  |  | 3741.12 | 486.3456 | 4227.4656 | 2021-01-13 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Corduroy at F132 access | 11 | F119-F134 | Hensen Road | 0 | 44214 |  | 15 | 44224 | DD-20210113-1 | Corduroy at F132/F133 Access all day. DD-33012 Buncher rate for Const Amendment #4 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5339KL-20210113-53rd Party Services3741.123741.12 | KABI LAKE FOREST PRODUCTS LTD5339KL-20210113-53rd Party Services3741.123741.12OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 3741.12 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5352 | KL-20210113-18 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-01-13 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal @ High Falls Rds. SSF-14150 | 11 | F203-F211 | Hensen Road | 0 | 44214 |  | 56 | 44219 | SSF-20210113-4 | Grader doing snow removal @ High Falls Rds. SSF-14150 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5352KL-20210113-183rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD5352KL-20210113-183rd Party Services2321.822321.82OEWT-PA13-LEM | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5360 | KL-20210114-6 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1160.91 | Each |  |  |  |  | 1160.91 | 150.9183 | 1311.8283 | 2021-01-14 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal to F184 as per Valard - SSF-14146 | 11 | F-180 to F-184 | High Falls Road- 4 | 0 | 44218 |  | 56 | 44220 | SSF-20210114-1 | Grader doing snow removal to F184 as per Valard - SSF-14146 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5360KL-20210114-63rd Party Services1160.911160.91 | KABI LAKE FOREST PRODUCTS LTD5360KL-20210114-63rd Party Services1160.911160.91OEWT-PA13-LEM | [5 empty] | 1 | 1160.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5363 | KL-20210114-9 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2328.82 | Each |  |  |  |  | 2328.82 | 302.7466 | 2631.5666 | 2021-01-14 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul 1 load screened sand from town pit and finished sanding Hensen Road to 17km with existing sand as per Valard/ Excavator cleaning up @ F119 for Sand | 11 | F119-F134 | Hensen Road | 0 | 44218 |  | 15 | 44224 | CR-20210114-3 | Loader sanded into Hensen East and West where needed - CR-101216 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5363KL-20210114-93rd Party Services2328.822328.82 | KABI LAKE FOREST PRODUCTS LTD5363KL-20210114-93rd Party Services2328.822328.82OEWT-PA13-LEM | [5 empty] | 1 | 2328.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5365 | KL-20210114-11 | 53511103 | Access | 0 | 3rd Party Services | 1 | 1496.45 | Each |  |  |  |  | 1496.45 | 194.5385 | 1690.9885 | 2021-01-14 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Operator travel for F127 to F134 MFN Road building. Dumonski cutting for corduroy @ F-133. | 11 | F119-F134 | Hensen Road | 0 | 44218 |  | 15 | 44224 | DD-20210114-3 | Corduroy @F133 access - DD-33007. Buncher rate from Const. Amend #4 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5365KL-20210114-113rd Party Services1496.451496.45 | KABI LAKE FOREST PRODUCTS LTD5365KL-20210114-113rd Party Services1496.451496.45OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 1496.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5369 | KL-20210114-15 | 53511103 | Access | 0 | 3rd Party Services | 1 | 484.36 | Each |  |  |  |  | 484.36 | 62.9668 | 547.3268 | 2021-01-14 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track From 2km on Dore lake Road to F145/F146 due to no float access - MC-13080 | 11 | F-135 to F-149 | Dore Lake Road | 0 | 44218 |  | 56 | 44220 | MC-20210114-1 | Track From 2km on Dore lake Road to F145/F146 due to no float access - MC-13080 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5369KL-20210114-153rd Party Services484.36484.36 | KABI LAKE FOREST PRODUCTS LTD5369KL-20210114-153rd Party Services484.36484.36OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 484.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5377 | KL-20210115-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1928.45 | Each |  |  |  |  | 1928.45 | 250.6985 | 2179.1485 | 2021-01-15 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding into Hensen east and west where needed - CR-101221 / Excavator laying corduroy towards F97 - CR-101219 | 11 | F119-F134 | Hensen Road | 0 | 44218 |  | 15 | 44224 | CR-20210115-1 | Loader finished sanding into Hensen east and west where needed. CR-101221 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5377KL-20210115-83rd Party Services1928.451928.45 | KABI LAKE FOREST PRODUCTS LTD5377KL-20210115-83rd Party Services1928.451928.45OEWT-PA13-LEM | [5 empty] | 1 | 1928.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5380 | KL-20210115-11 | 53511103 | Access | 0 | 3rd Party Services | 1 | 726.55 | Each |  |  |  |  | 726.55 | 94.4515 | 821.0015 | 2021-01-15 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Buncher track in and out from F147 access to F145 Junction. Morin track and place corduroy. Buncher rate from Const. Amend #4 | 11 | F135-F149 | Dore Lake Road | 0 | 44218 |  | 56 | 44220 | MC-20210115-1 | Track and Place corduroy @F147 Access. MC-13081 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5380KL-20210115-113rd Party Services726.55726.55 | KABI LAKE FOREST PRODUCTS LTD5380KL-20210115-113rd Party Services726.55726.55OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 726.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5388 | KL-20201220-11 | 53531101 | Rig/Access Mats | 0 | 3rd Party Services | 1 | 2069.82 | Each |  |  |  |  | 2069.82 | 269.0766 | 2338.8966 | 2020-12-20 | 0 | OEWT-PA12-LEM-R1 | 44215 | 38 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer moving rig mats from Km 17 in Hensen to Km 6 in Hensen West for future water crossings. CR-101135 | 11 | F119-F134 | Hensen Road | 0 |  |  | 55 | 44211 | CR-20201220-2 | Dozer moving rig mats from Km 17 in Hensen to Km 6 in Hensen West for future water crossings. CR-101135 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5388KL-20201220-113rd Party Services2069.822069.82 | KABI LAKE FOREST PRODUCTS LTD5388KL-20201220-113rd Party Services2069.822069.82OEWT-PA12-LEM-R1 |  |  | WF10-WaterCrossing |  |  | 0.5 | 1034.91 | WC609 | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5391 | KL-20210115-15 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 1195.55 | Each |  |  |  |  | 1195.55 | 155.4215 | 1350.9715 | 2021-01-15 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hammer Rock just after #12460 rigmat and before 12400 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 |  |  | 56 | 44229 | CE-20210115-2 | Hammer Rock just after #12460 rigmat and before 12400 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5391KL-20210115-153rd Party Services1195.551195.55 | KABI LAKE FOREST PRODUCTS LTD5391KL-20210115-153rd Party Services1195.551195.55OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 597.775 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5392 | KL-20210115-16 | 53511103 | Access | 0 | 3rd Party Services | 1 | 964.36 | Each |  |  |  |  | 964.36 | 125.3668 | 1089.7268 | 2021-01-15 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul Geo Fabric, Labourer and Supervisor cut and lay Geo Down, Excavator cover with debris, trees, brush etc. CE-053 | 11 | F152-F158 | Michipicoten Harbour Road -2 | 0 |  |  | 56 | 44229 | CE-20210115-3 | Haul Geo Fabric, Labourer and Supervisor cut and lay Geo Down, Excavator cover with debris, trees, brush etc. CE-053 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5392KL-20210115-163rd Party Services964.36964.36 | KABI LAKE FOREST PRODUCTS LTD5392KL-20210115-163rd Party Services964.36964.36OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 964.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5397 | KL-20210116-4 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1960.82 | Each |  |  |  |  | 1960.82 | 254.9066 | 2215.7266 | 2021-01-16 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | D5 tuned up roads from F100 to WC 11770.01 and tracking it to tighten up with frost - CR-101228 | 11 | F119-F134 | Hensen Road | 0 | 44216 |  | 15 | 44233 | CR-20210116-1 | D5 tuned up roads from F100 to WC 11770.01 and tracking it to tighten up with frost - CR-101228 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5397KL-20210116-43rd Party Services1960.821960.82 | KABI LAKE FOREST PRODUCTS LTD5397KL-20210116-43rd Party Services1960.821960.82OEWT-PA13-LEM | [5 empty] | 1 | 1960.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5398 | KL-20210116-5 | 53511102 | Access | 0 | 3rd Party Services | 1 | 1819.82 | Each |  |  |  |  | 1819.82 | 236.5766 | 2056.3966 | 2021-01-16 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator laying corduroy towards WC 11770.01 as needed - CR-101224 | 11 | F119-F134 | Hensen Road | 0 | 44216 |  | 15 | 44233 | CR-20210116-2 | Excavator laying corduroy towards WC 11770.01 as needed - CR-101224 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5398KL-20210116-53rd Party Services1819.821819.82 | KABI LAKE FOREST PRODUCTS LTD5398KL-20210116-53rd Party Services1819.821819.82OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 1819.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5402 | KL-20210116-9 | 53511103 | Access | 0 | 3rd Party Services | 1 | 726.55 | Each |  |  |  |  | 726.55 | 94.4515 | 821.0015 | 2021-01-16 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track in and out from F148. Morin lay corduroy to F147. buncher rate from Const Amend #4 | 11 | F135-F149 | Dore Lake Road | 0 | 44216 |  | 56 | 44229 | MC-20210116-1 | Track and place Corduroy @ F147 Access. MC-13082 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5402KL-20210116-93rd Party Services726.55726.55 | KABI LAKE FOREST PRODUCTS LTD5402KL-20210116-93rd Party Services726.55726.55OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 726.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5410 | KL-20210116-17 | 53511103 | Access | 0 | 3rd Party Services | 1 | 2150.89 | Each |  |  |  |  | 2150.89 | 279.6157 | 2430.5057 | 2021-01-16 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Corduroy MHR #4 access F156- F158, Skid wood to fill road to finish cut - CE-054 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 | 44216 |  | 56 | 44229 | CE-20210116-1 | Corduroy MHR #4 access F156- F158, Skid wood to fill road to finish cut - CE-054. Buncher rate from Const. Amend #4 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5410KL-20210116-173rd Party Services2150.892150.89 | KABI LAKE FOREST PRODUCTS LTD5410KL-20210116-173rd Party Services2150.892150.89OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 2150.89 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5411 | KL-20210116-18 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1508.09 | Each |  |  |  |  | 1508.09 | 196.0517 | 1704.1417 | 2021-01-16 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hoe sourcing gravel and recliaming by F-106. CR-101233 | 11 | F119-F134 | Hensen Road | 0 | 44216 |  | 15 | 44233 | CR-20210116-7 | Hoe sourcing gravel and recliaming by F-106. CR-10123 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5411KL-20210116-183rd Party Services1508.091508.09 | KABI LAKE FOREST PRODUCTS LTD5411KL-20210116-183rd Party Services1508.091508.09OEWT-PA13-LEM | [5 empty] | 1 | 1508.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5418 | KL-20210117-6 | 53511102 | Access | 0 | 3rd Party Services | 1 | 1210.91 | Each |  |  |  |  | 1210.91 | 157.4183 | 1368.3283 | 2021-01-17 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator starting to fill gorge @F144/F143 with trees for road realignment - SSF-14153 / Excavator laying corduroy to build up at blast area - CR-101230 | 11 | F119-F134 | Hensen Road | 0 | 44216 |  | 15 | 44238 | SSF-20210117-1 | Cat 330F Excavator starting to fill gorge @F144/F143 with trees for road realignment - SSF-14153 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5418KL-20210117-63rd Party Services1210.911210.91 | KABI LAKE FOREST PRODUCTS LTD5418KL-20210117-63rd Party Services1210.911210.91OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 1210.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5418 | KL-20210117-6 | 53511102 | Access | 0 | 3rd Party Services | 1 | 1708.91 | Each |  |  |  |  | 1708.91 | 222.1583 | 1931.0683 | 2021-01-17 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator starting to fill gorge @F144/F143 with trees for road realignment - SSF-14153 / Excavator laying corduroy to build up at blast area - CR-101230 | 11 | F119-F134 | Hensen Road | 0 | 44216 |  | 15 | 44238 | CR-20210117-3 | Excavator laying corduroy to build up at blast area - CR-101230 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5418KL-20210117-63rd Party Services1708.911708.91 | KABI LAKE FOREST PRODUCTS LTD5418KL-20210117-63rd Party Services1708.911708.91OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 1708.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5420 | KL-20210117-8 | 53511103 | Access | 0 | 3rd Party Services | 1 | 5481.34 | Each |  |  |  |  | 5481.34 | 712.5742 | 6193.9142 | 2021-01-17 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | MHR 1 to Access tower F150 corduroy in , not enough wood so skidder is skidding wood from surounding area corduroy over blast site - CE-055 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44216 |  | 56 | 44229 | CE-20210117-1 | MHR 1 to Access tower F150 corduroy in , not enough wood so skidder is skidding wood from surounding area corduroy over blast site - CE-055 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5420KL-20210117-83rd Party Services5481.345481.34 | KABI LAKE FOREST PRODUCTS LTD5420KL-20210117-83rd Party Services5481.345481.34OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 5481.34 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5426 | KL-20210117-14 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1508.09 | Each |  |  |  |  | 1508.09 | 196.0517 | 1704.1417 | 2021-01-17 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator sourcing gravel and reclaiming by F116 - CR-101233 | 11 | F119-F134 | Hensen Road | 0 | 44216 |  | 15 | 44238 | CR-20210117-1 | Excavator sourcing gravel and reclaiming by F116 - CR-101233 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5426KL-20210117-143rd Party Services1508.091508.09 | KABI LAKE FOREST PRODUCTS LTD5426KL-20210117-143rd Party Services1508.091508.09OEWT-PA13-LEM | [5 empty] | 1 | 1508.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5435 | KL-20210118-9 | 53511111 | Access | 0 | 3rd Party Services | 1 | 6306.73 | Each |  |  |  |  | 6306.73 | 819.8749 | 7126.6049 | 2021-01-18 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator loading 740 and sourcing material, D5 spreading material as needed from F108 to F103, excavator did reclaim work at F106 as well - CR-101235 | 11 | F119-F134 | Hensen Road | 0 | 44216 |  | 15 | 44238 | CR-20210118-2 | Excavator loading 740 and sourcing material, D5 spreading material as needed from F108 to F103, excavator did reclaim work at F106 as well - CR-101235 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5435KL-20210118-93rd Party Services6306.736306.73 | KABI LAKE FOREST PRODUCTS LTD5435KL-20210118-93rd Party Services6306.736306.73OEWT-PA13-LEM | [5 empty] | 1 | 6306.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5442 | KL-20210118-16 | 53511102 | Access | 0 | 3rd Party Services | 1 | 4753.7 | Each |  |  |  |  | 4753.7 | 617.981 | 5371.681 | 2021-01-18 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator filling gorge with trees for fill @ F144/F143 Access (Revised | 11 | F135-F149 | Dore Lake Road | 0 | 44216 |  | 56 | 44229 | SSF-20210118-2 | Skidding trees to Kabi 330F Excavator to fill gorge @ F144/F143. Buncher carrying trees for fill on F143 Access. SSF-14154. Buncher rate from Const. Amend #4 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5442KL-20210118-163rd Party Services4753.74753.7 | KABI LAKE FOREST PRODUCTS LTD5442KL-20210118-163rd Party Services4753.74753.7OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 4753.7 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5447 | KL-20210118-21 | 53511102 | Access | 0 | 3rd Party Services | 1 | 9134.94 | Each |  |  |  |  | 9134.94 | 1187.5422 | 10322.4822 | 2021-01-18 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Buncher cutting 1 hr of road cutting the rest was building road MHR#1 to access tower 150. Cut and place wood in certain areas for skidder & buncher & exc. CE-060 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44216 |  | 56 | 44229 | CE-20210118-1 | Buncher cutting 1 hr of road cutting the rest was building road MHR#1 to access tower 150. Cut and place wood in certain areas for skidder & buncher & exc. CE-060. Buncher rate from Const Amend #4 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5447KL-20210118-213rd Party Services9134.949134.94 | KABI LAKE FOREST PRODUCTS LTD5447KL-20210118-213rd Party Services9134.949134.94OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 9134.94 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5448 | KL-20210118-22 | 53511102 | Access | 0 | 3rd Party Services | 1 | 4631.27 | Each |  |  |  |  | 4631.27 | 602.0651 | 5233.3351 | 2021-01-18 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 350 exc corduroy way in and up rock face. Skidder is bringing wood to fill in rockface so shovel can build up a road. Pulling material into road. CE-059 | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44216 |  | 56 | 44229 | CE-20210118-2 | 350 exc corduroy way in and up rock face. Skidder is bringing wood to fill in rockface so shovel can build up a road. Pulling material into road. CE-059 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5448KL-20210118-223rd Party Services4631.274631.27 | KABI LAKE FOREST PRODUCTS LTD5448KL-20210118-223rd Party Services4631.274631.27OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 4631.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5449 | KL-20210118-23 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 3783.91 | Each |  |  |  |  | 3783.91 | 491.9083 | 4275.8183 | 2021-01-18 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hammer access F158 blast areas and use material in roads. Exc 225 is interchangeable to bucket with thumb. Skidder moving wood to put in road to re-skid wood. CE-058 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 | 44216 |  | 56 | 44229 | CE-20210118-3 | Hammer access F158 blast areas and use material in roads. Exc 225 is interchangeable to bucket with thumb. Skidder moving wood to put in road to re-skid wood. CE-058 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5449KL-20210118-233rd Party Services3783.913783.91 | KABI LAKE FOREST PRODUCTS LTD5449KL-20210118-233rd Party Services3783.913783.91OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 1891.955 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5457 | KL-20210119-8 | 53511102 | Access | 0 | 3rd Party Services | 1 | 7310.01 | Each |  |  |  |  | 7310.01 | 950.3013 | 8260.3113 | 2021-01-19 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shovel building road in blast area. Put corduroy in blast areas & road to move forward. Buncher cut & put corduroy in road. Skid wood to buncher & exc to move forward. | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44222 |  | 56 | 44229 | CE-20210119-1 | Shovel building road in blast area. Put corduroy in blast areas & road to move forward. Buncher cut & put corduroy in road. Skid wood to buncher & exc to move forward. Buncher rate from Const Amend #4 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5457KL-20210119-83rd Party Services7310.017310.01 | KABI LAKE FOREST PRODUCTS LTD5457KL-20210119-83rd Party Services7310.017310.01OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 7310.01 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5458 | KL-20210119-9 | 53511102 | Access | 0 | 3rd Party Services | 1 | 4755.28 | Each |  |  |  |  | 4755.28 | 618.1864 | 5373.4664 | 2021-01-19 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Skidder bring wood & fill in road. Shovel pulling aggregate to cover corduroy to move forward. This is a steep rock face being filled. CE-063 | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44222 |  | 56 | 44229 | CE-20210119-2 | Skidder bring wood & fill in road. Shovel pulling aggregate to cover corduroy to move forward. This is a steep rock face being filled. CE-063 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5458KL-20210119-93rd Party Services4755.284755.28 | KABI LAKE FOREST PRODUCTS LTD5458KL-20210119-93rd Party Services4755.284755.28OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 4755.28 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5459 | KL-20210119-10 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 5611.46 | Each |  |  |  |  | 5611.46 | 729.4898 | 6340.9498 | 2021-01-19 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Skid wood to 225 shovel to put in road. Exc w thumb changed to hammer. Hammer rock then build road after. This wood was skidded once already. CE-061 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 | 44222 |  | 56 | 44229 | CE-20210119-3 | Skid wood to 225 shovel to put in road. Exc w thumb changed to hammer. Hammer rock then build road after. This wood was skidded once already. CE-061 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5459KL-20210119-103rd Party Services5611.465611.46 | KABI LAKE FOREST PRODUCTS LTD5459KL-20210119-103rd Party Services5611.465611.46OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 2805.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5461 | KL-20210119-12 | 53511102 | Access | 0 | 3rd Party Services | 1 | 1393.08 | Each |  |  |  |  | 1393.08 | 181.1004 | 1574.1804 | 2021-01-19 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Skidding trees to buncher for fill @ F143/F142 Access. SSF-14157 | 11 | F135-F149 | Dore Lake Road | 0 | 44222 |  | 56 | 44229 | SSF-20210119-2 | Skidding trees to buncher for fill @ F143/F142 Access. SSF-14157. buncher rate from Const Amend #4 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5461KL-20210119-123rd Party Services1393.081393.08 | KABI LAKE FOREST PRODUCTS LTD5461KL-20210119-123rd Party Services1393.081393.08OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 1393.08 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5468 | KL-20210119-19 | 53531101 | Rig/Access Mats | 0 | 3rd Party Services | 1 | 3793.91 | Each |  |  |  |  | 3793.91 | 493.2083 | 4287.1183 | 2021-01-19 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc and loader brought back mats to WC 11750.01, exc installed them CR-101238 | 11 | F19-F134 | Hensen Road | 0 | 44222 |  | 15 | 44238 | CR-20210119-1 | Exc and loader brought back mats to WC 11750.01, exc installed them CR-101238 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5468KL-20210119-193rd Party Services3793.913793.91 | KABI LAKE FOREST PRODUCTS LTD5468KL-20210119-193rd Party Services3793.913793.91OEWT-PA13-LEM |  |  | WF10-WaterCrossing |  |  | 1 | 3793.91 | WC489 | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5469 | KL-20210119-20 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1508.09 | Each |  |  |  |  | 1508.09 | 196.0517 | 1704.1417 | 2021-01-19 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 336 loaded rock truck by F106 then finished reclaim work. CR-101239 | 11 | F119-F134 | Hensen Road | 0 | 44222 |  | 15 | 44238 | CR-20210119-2 | 336 loaded rock truck by F106 then finished reclaim work. CR-101239 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5469KL-20210119-203rd Party Services1508.091508.09 | KABI LAKE FOREST PRODUCTS LTD5469KL-20210119-203rd Party Services1508.091508.09OEWT-PA13-LEM | [5 empty] | 1 | 1508.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5484 | KL-20210120-6 | 53511102 | Access | 0 | 3rd Party Services | 1 | 7638.65 | Each |  |  |  |  | 7638.65 | 993.0245 | 8631.6745 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Pushing sand over corduroy under power line. Rock truck dumps before power line and dozer levels it. CE-067 | 11 | F150-F151 | Michipicoten Harbour Road -3 | 0 | 44224 |  | 56 | 44229 | CE-20210120-1 | Pushing sand over corduroy under power line. Rock truck dumps before power line and dozer levels it. CE-067. Rock truck rate from Const Amend #4 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5484KL-20210120-63rd Party Services7638.657638.65 | KABI LAKE FOREST PRODUCTS LTD5484KL-20210120-63rd Party Services7638.657638.65OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 7638.65 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5485 | KL-20210120-7 | 53511103 | Access | 0 | 3rd Party Services | 1 | 484.36 | Each |  |  |  |  | 484.36 | 62.9668 | 547.3268 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair road where skidder punched through wet area and add more corduroy. Track and push down. CE-065 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 | 44224 |  | 56 | 44229 | CE-20210120-2 | Repair road where skidder punched through wet area and add more corduroy. Track and push down. CE-065 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5485KL-20210120-73rd Party Services484.36484.36 | KABI LAKE FOREST PRODUCTS LTD5485KL-20210120-73rd Party Services484.36484.36OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 484.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5486 | KL-20210120-8 | 53511102 | Access | 0 | 3rd Party Services | 1 | 4370.73 | Each |  |  |  |  | 4370.73 | 568.1949 | 4938.9249 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 3 skidders feeding wood to excavator to fill in roads with corduroy. CE-066. Place Corduroy @ wetland on F149 Access MC-13083 | 11 | F135-F149 | Dore Lake Road | 0 | 44224 |  | 56 | 44229 | CE-20210120-4 | 3 skidders feeding wood to excavator to fill in roads with corduroy. CE-066 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5486KL-20210120-83rd Party Services4370.734370.73 | KABI LAKE FOREST PRODUCTS LTD5486KL-20210120-83rd Party Services4370.734370.73OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 4370.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5486 | KL-20210120-8 | 53511103 | Access | 0 | 3rd Party Services | 1 | 968.73 | Each |  |  |  |  | 968.73 | 125.9349 | 1094.6649 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 3 skidders feeding wood to excavator to fill in roads with corduroy. CE-066. Place Corduroy @ wetland on F149 Access MC-13083 | 11 | F135-F149 | Dore Lake Road | 0 | 44224 |  | 56 | 44229 | MC-20210120-1 | Place Corduroy @ wetland on F149 Access MC-13083 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5486KL-20210120-83rd Party Services968.73968.73 | KABI LAKE FOREST PRODUCTS LTD5486KL-20210120-83rd Party Services968.73968.73OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 968.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5487 | KL-20210120-9 | 53511103 | Access | 0 | 3rd Party Services | 1 | 3681.36 | Each |  |  |  |  | 3681.36 | 478.5768 | 4159.9368 | 2021-01-20 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Skid trees to Cat 330F Excavator to fill gorge @ F143/F142 & skidding trees to F146 Access SSF-14159 | 11 | F135-F149 | Dore Lake Road | 0 | 44224 |  | 56 | 44229 | SSF-20210120-1 | Skid trees to Cat 330F Excavator to fill gorge @ F143/F142 & skidding trees to F146 Access SSF-14159 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5487KL-20210120-93rd Party Services3681.363681.36 | KABI LAKE FOREST PRODUCTS LTD5487KL-20210120-93rd Party Services3681.363681.36OEWT-PA14-Lem-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 3681.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5491 | KL-20210120-13 | 53511103 | Access | 0 | 3rd Party Services | 1 | 733.55 | Each |  |  |  |  | 733.55 | 95.3615 | 828.9115 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Placed & levelled gravel to cover corduroy. CR-101247 | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | CR-20210120-1 | Placed & levelled gravel to cover corduroy. CR-101247 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5491KL-20210120-133rd Party Services733.55733.55 | KABI LAKE FOREST PRODUCTS LTD5491KL-20210120-133rd Party Services733.55733.55OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 733.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5492 | KL-20210120-14-R1 | 53511111 | Access | 0 | 3rd Party Services | 1 | 941.73 | Each |  |  |  |  | 941.73 | 122.4249 | 1064.1549 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repaired road between F103 and F99. Plowed snow and sanded hills. | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44232 | CR-20210120-2 | Repaired road between F103 and F99 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5492KL-20210120-14-R13rd Party Services941.73941.73 | KABI LAKE FOREST PRODUCTS LTD5492KL-20210120-14-R13rd Party Services941.73941.73OEWT-PA13-LEM | [5 empty] | 1 | 941.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5492 | KL-20210120-14-R1 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1915.32 | Each |  |  |  |  | 1915.32 | 248.9916 | 2164.3116 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repaired road between F103 and F99. Plowed snow and sanded hills. | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44232 | CR-20210120-3 | Plowed snow and sanded hills CR-101243 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5492KL-20210120-14-R13rd Party Services1915.321915.32 | KABI LAKE FOREST PRODUCTS LTD5492KL-20210120-14-R13rd Party Services1915.321915.32OEWT-PA13-LEM | [5 empty] | 1 | 1915.32 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5494 | KL-20210120-16 | 53531101 | Rig/Access Mats | 0 | 3rd Party Services | 1 | 1141.73 | Each |  |  |  |  | 1141.73 | 148.4249 | 1290.1549 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Installed 40' mats and built approaches to WC 11750.01 | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | CR-20210120-5 | Installed 40' mats and built approaches to WC 11750.01 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5494KL-20210120-163rd Party Services1141.731141.73 | KABI LAKE FOREST PRODUCTS LTD5494KL-20210120-163rd Party Services1141.731141.73OEWT-PA13-LEM |  |  | WF10-WaterCrossing |  |  | 1 | 1141.73 | WC489 | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5501 | KL-20210120-23 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 1738.82 | Each |  |  |  |  | 1738.82 | 226.0466 | 1964.8666 | 2021-01-20 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Access Rd 4 to F158-Hammer used to break down rock face and put in road to keep moving forward. CE-064 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 | 44224 |  | 56 | 44229 | CE-20210120-3 | Access Rd 4 to F158-Hammer used to break down rock face and put in road to keep moving forward. CE-064 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5501KL-20210120-233rd Party Services1738.821738.82 | KABI LAKE FOREST PRODUCTS LTD5501KL-20210120-233rd Party Services1738.821738.82OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 869.41 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5507 | KL-20210121-6 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1481.45 | Each |  |  |  |  | 1481.45 | 192.5885 | 1674.0385 | 2021-01-21 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer doing snow removal, buncher carrying trees for fill on F142 Access. | 11 | F135-F149 | Dore Lake Road | 0 | 44224 |  | 56 | 44229 | SSF-20210121-1 | Dozer doing snow removal on F145 Access to F143. SSF-14163 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5507KL-20210121-63rd Party Services1481.451481.45 | KABI LAKE FOREST PRODUCTS LTD5507KL-20210121-63rd Party Services1481.451481.45OEWT-PA13-LEM | [5 empty] | 1 | 1481.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5507 | KL-20210121-6 | 53511102 | Access | 0 | 3rd Party Services | 1 | 561.17 | Each |  |  |  |  | 561.17 | 72.9521 | 634.1221 | 2021-01-21 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer doing snow removal, buncher carrying trees for fill on F142 Access. | 11 | F135-F149 | Dore Lake Road | 0 | 44224 |  | 56 | 44229 | SSF-20210121-2 | Buncher carrying trees for fill on F142 Access. SSF-14162. Buncher rate from Const Amend #4 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5507KL-20210121-63rd Party Services561.17561.17 | KABI LAKE FOREST PRODUCTS LTD5507KL-20210121-63rd Party Services561.17561.17OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 561.17 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5509 | KL-20210121-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-01-21 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader plowing hensen road, Cress clearing snow and sanding road. | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | SSF-20210121-3 | Grader plowing Hensen Rd to km 17. SSF-14160 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5509KL-20210121-83rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD5509KL-20210121-83rd Party Services2321.822321.82OEWT-PA13-LEM | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5509 | KL-20210121-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 3100.9 | Each |  |  |  |  | 3100.9 | 403.117 | 3504.017 | 2021-01-21 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader plowing hensen road, Cress clearing snow and sanding road. | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | CR-20210121-1 | Cleared snow and sanded Hensen West km 0-14. CR-101248 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5509KL-20210121-83rd Party Services3100.93100.9 | KABI LAKE FOREST PRODUCTS LTD5509KL-20210121-83rd Party Services3100.93100.9OEWT-PA13-LEM | [5 empty] | 1 | 3100.9 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5511 | KL-20210121-10 | 53511102 | Access | 0 | 3rd Party Services | 1 | 2046.45 | Each |  |  |  |  | 2046.45 | 266.0385 | 2312.4885 | 2021-01-21 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shovel scratching for dirt & debris. Walk with debris and fill in road. CE-072 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44224 |  | 56 | 44229 | CE-20210121-2 | Shovel scratching for dirt & debris. Walk with debris and fill in road. CE-072 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5511KL-20210121-103rd Party Services2046.452046.45 | KABI LAKE FOREST PRODUCTS LTD5511KL-20210121-103rd Party Services2046.452046.45OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 2046.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5512 | KL-20210121-11 | 53511102 | Access | 0 | 3rd Party Services | 1 | 1755.59 | Each |  |  |  |  | 1755.59 | 228.2267 | 1983.8167 | 2021-01-21 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Scratch for dirt and debris to fill road, lay corduroy for fill. | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44224 |  | 56 | 44229 | CE-20210121-3 | Shovel preparing road for geo fabric. Covered then did some corduroy to continue on road building. CE-071 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5512KL-20210121-113rd Party Services1755.591755.59 | KABI LAKE FOREST PRODUCTS LTD5512KL-20210121-113rd Party Services1755.591755.59OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 1755.59 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5512 | KL-20210121-11 | 53511102 | Access | 0 | 3rd Party Services | 1 | 570.86 | Each |  |  |  |  | 570.86 | 74.2118 | 645.0718 | 2021-01-21 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Scratch for dirt and debris to fill road, lay corduroy for fill. | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44224 |  | 56 | 44229 | CE-20210121-4 | Put in road, walk and get corduroy to fill areas to keep moving forward. CE-070 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5512KL-20210121-113rd Party Services570.86570.86 | KABI LAKE FOREST PRODUCTS LTD5512KL-20210121-113rd Party Services570.86570.86OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 570.86 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5513 | KL-20210121-12 | 53511102 | Access | 0 | 3rd Party Services | 1 | 5638.05 | Each |  |  |  |  | 5638.05 | 732.9465 | 6370.9965 | 2021-01-21 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Build road over corduroy @ F155. After crew left, Valard talked to Excavator operator and told him what he wanted done to finish the job. CE-068 | 11 | F155 | Michipicoten Harbour Road -3 | 0 | 44224 |  | 56 | 44229 | CE-20210121-5 | Build road over corduroy @ F155. After crew left, Valard talked to Excavator operator and told him what he wanted done to finish the job. CE-068 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5513KL-20210121-123rd Party Services5638.055638.05 | KABI LAKE FOREST PRODUCTS LTD5513KL-20210121-123rd Party Services5638.055638.05OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 5638.05 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5514 | KL-20210121-13-R1 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 3588 | Each |  |  |  |  | 3588 | 466.44 | 4054.44 | 2021-01-21 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc hammering rock and using material for road building. Corduroy road. CE-073 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 | 44224 |  | 56 | 44235 | CE-20210121-6 | Exc hammering rock and using material for road building. Corduroy road. CE-073 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5514KL-20210121-13-R13rd Party Services35883588 | KABI LAKE FOREST PRODUCTS LTD5514KL-20210121-13-R13rd Party Services35883588OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 1794 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5519 | KL-20210109-11-R1 | 53511102 | Access | 0 | 3rd Party Services | 1 | 2448.9 | Each |  |  |  |  | 2448.9 | 318.357 | 2767.257 | 2021-01-09 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Corduroy across a rock face that was blast site, changed to corduroy to get access to ROW for clearing. Buncher rate from Const. Amend #4 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 |  |  | 56 | 44232 | CE-20210109-1 | Corduroy across a rock face that was blast site, changed to corduroy to get access to ROW for clearing. Buncher rate from Const. Amend #4 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5519KL-20210109-11-R13rd Party Services2448.92448.9 | KABI LAKE FOREST PRODUCTS LTD5519KL-20210109-11-R13rd Party Services2448.92448.9OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 2448.9 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5520 | KL-20210110-14-R1 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 1714.46 | Each |  |  |  |  | 1714.46 | 222.8798 | 1937.3398 | 2021-01-10 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hammer rock at first blast site on Access Road #4, F-158 to F-156. CE-039 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 |  |  | 56 | 44232 | CE-20210110-1 | Hammer rock at first blast site on Access Road #4, F-158 to F-156. CE-039 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5520KL-20210110-14-R13rd Party Services1714.461714.46 | KABI LAKE FOREST PRODUCTS LTD5520KL-20210110-14-R13rd Party Services1714.461714.46OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 857.23 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5521 | KL-20210111-13 | 53511102 | Access | 0 | 3rd Party Services | 1 | 7784.29 | Each |  |  |  |  | 7784.29 | 1011.9577 | 8796.2477 | 2021-01-11 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Working on road access to F-159 hill rock face, build up road by adding aggregate. CE-043 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 |  |  | 56 | 44229 | CE-20210111-1 | Working on road access to F-159 hill rock face, build up road by adding aggregate. CE-043 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5521KL-20210111-133rd Party Services7784.297784.29 | KABI LAKE FOREST PRODUCTS LTD5521KL-20210111-133rd Party Services7784.297784.29OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 7784.29 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5522 | KL-20210111-14 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 2262.68 | Each |  |  |  |  | 2262.68 | 294.1484 | 2556.8284 | 2021-01-11 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hammer rock at blast site on Access Road #4, F-158 to F-156. CE-040 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 |  |  | 56 | 44229 | CE-20210111-2 | Hammer rock at blast site on Access Road #4, F-158 to F-156. CE-040 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5522KL-20210111-143rd Party Services2262.682262.68 | KABI LAKE FOREST PRODUCTS LTD5522KL-20210111-143rd Party Services2262.682262.68OEWT-PA13-LEM |  | WF11-Blasting | WF11-Blasting |  | 0.5 | 0.5 | 1131.34 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5530 | KL-20210122-8 | 53511102 | Access | 0 | 3rd Party Services | 1 | 3501.18 | Each |  |  |  |  | 3501.18 | 455.1534 | 3956.3334 | 2021-01-22 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Skid wood to Doosan near F158 filling in road. Skid wood to F147 to put in ravine to finish road. CE-075. Building MHR 4 to access F148. Hammered rock. CE-074 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 | 44224 |  | 56 | 44230 | CE-20210122-1 | Skid wood to Doosan working towards F158 filling in road. Skid wood to 235 excavator at F147 to put in ravine to finish road. CE-075 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5530KL-20210122-83rd Party Services3501.183501.18 | KABI LAKE FOREST PRODUCTS LTD5530KL-20210122-83rd Party Services3501.183501.18OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 3501.18 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5530 | KL-20210122-8 | 53511102 | Access | 0 | 3rd Party Services | 1 | 3333.45 | Each |  |  |  |  | 3333.45 | 433.3485 | 3766.7985 | 2021-01-22 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Skid wood to Doosan near F158 filling in road. Skid wood to F147 to put in ravine to finish road. CE-075. Building MHR 4 to access F148. Hammered rock. CE-074 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 | 44224 |  | 56 | 44230 | CE-20210122-2 | Building MHR 4 to access F148. Came to rock and hammered. CE-074 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5530KL-20210122-83rd Party Services3333.453333.45 | KABI LAKE FOREST PRODUCTS LTD5530KL-20210122-83rd Party Services3333.453333.45OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 3333.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5531 | KL-20210122-9 | 53511102 | Access | 0 | 3rd Party Services | 1 | 1937.45 | Each |  |  |  |  | 1937.45 | 251.8685 | 2189.3185 | 2021-01-22 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track/carry material to cover sections of road @ F148 & F149 Access MC-13084 | 11 | F135-F149 | Dore Lake Road | 0 | 44224 |  | 56 | 44230 | MC-20210122-1 | Track/carry material to cover sections of road @ F148 & F149 Access MC-13084 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5531KL-20210122-93rd Party Services1937.451937.45 | KABI LAKE FOREST PRODUCTS LTD5531KL-20210122-93rd Party Services1937.451937.45OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 1937.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5534 | KL-20210122-12 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1239.91 | Each |  |  |  |  | 1239.91 | 161.1883 | 1401.0983 | 2021-01-22 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal at High Falls Roads SSF-14165 | 11 | F203-F211 | High Falls Road- 9 | 0 | 44224 |  | 56 | 44230 | SSF-20210122-2 | Grader doing snow removal at High Falls Roads SSF-14165 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5534KL-20210122-123rd Party Services1239.911239.91 | KABI LAKE FOREST PRODUCTS LTD5534KL-20210122-123rd Party Services1239.911239.91OEWT-PA13-LEM | [5 empty] | 1 | 1239.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5535 | KL-20210122-13 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2144.64 | Each |  |  |  |  | 2144.64 | 278.8032 | 2423.4432 | 2021-01-22 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader plowing pull offs & benching snow banks on Hensen Road to km 17. SSF-14161 | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | SSF-20210122-3 | Grader plowing pull offs & benching snow banks on Hensen Road to km 17. SSF-14161 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5535KL-20210122-133rd Party Services2144.642144.64 | KABI LAKE FOREST PRODUCTS LTD5535KL-20210122-133rd Party Services2144.642144.64OEWT-PA13-LEM | [5 empty] | 1 | 2144.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5538 | KL-20210122-16-R1 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2268.37 | Each |  |  |  |  | 2268.37 | 294.8881 | 2563.2581 | 2021-01-22 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator fixed borrow pits between F99 and F100. Loader and dozer sanding for rock trucks form km6 to km14 | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | CR-20210122-1 | "Sanded hills and cleared snow for rock truck between km 6 and km 14. CR-101254 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5538KL-20210122-16-R13rd Party Services2268.372268.37 | KABI LAKE FOREST PRODUCTS LTD5538KL-20210122-16-R13rd Party Services2268.372268.37OEWT-PA13-LEM | [5 empty] | 1 | 2268.37 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5538 | KL-20210122-16-R1 | 53511102 | Access | 0 | 3rd Party Services | 1 | 2487.14 | Each |  |  |  |  | 2487.14 | 323.3282 | 2810.4682 | 2021-01-22 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator fixed borrow pits between F99 and F100. Loader and dozer sanding for rock trucks form km6 to km14 | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | CR-20210122-3 | Excavator fixed borrow pits between F99 and F100. CR-101252 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5538KL-20210122-16-R13rd Party Services2487.142487.14 | KABI LAKE FOREST PRODUCTS LTD5538KL-20210122-16-R13rd Party Services2487.142487.14OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 2487.14 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5549 | KL-20210123-8 | 53511102 | Access | 0 | 3rd Party Services | 1 | 3913.73 | Each |  |  |  |  | 3913.73 | 508.7849 | 4422.5149 | 2021-01-23 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Building road to access F152. Filling in road & ravines with corduroy. Skidder reskidding wood to excavator. CE-077 | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44224 |  | 56 | 44230 | CE-20210123-1 | Building road to access F152. Filling in road & ravines with corduroy. Skidder reskidding wood to excavator. CE-077 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5549KL-20210123-83rd Party Services3913.733913.73 | KABI LAKE FOREST PRODUCTS LTD5549KL-20210123-83rd Party Services3913.733913.73OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 3913.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5550 | KL-20210123-9 | 53511102 | Access | 0 | 3rd Party Services | 1 | 3830.27 | Each |  |  |  |  | 3830.27 | 497.9351 | 4328.2051 | 2021-01-23 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road build to tower 156 fill in ravine. All shale rock to road build. Working near powerline and required spotter. Skidder bring wood to 2 Excavators. CE-078 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 | 44224 |  | 56 | 44230 | CE-20210123-2 | Road build to tower 156 fill in ravine. All shale rock to road build. Working near powerline and required spotter. Skidder bring wood to 2 Excavators. CE-078 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5550KL-20210123-93rd Party Services3830.273830.27 | KABI LAKE FOREST PRODUCTS LTD5550KL-20210123-93rd Party Services3830.273830.27OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 3830.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5551 | KL-20210123-10 | 53511102 | Access | 0 | 3rd Party Services | 1 | 484.36 | Each |  |  |  |  | 484.36 | 62.9668 | 547.3268 | 2021-01-23 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track/carry trees & material to cover sections of road @ F147. MC-13085 | 11 | F135-F149 | Dore Lake Road | 0 | 44224 |  | 56 | 44230 | MC-20210123-1 | Track/carry trees & material to cover sections of road @ F147. MC-13085 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5551KL-20210123-103rd Party Services484.36484.36 | KABI LAKE FOREST PRODUCTS LTD5551KL-20210123-103rd Party Services484.36484.36OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 484.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5552 | KL-20210123-11 | 53511103 | Access | 0 | 3rd Party Services | 1 | 748.22 | Each |  |  |  |  | 748.22 | 97.2686 | 845.4886 | 2021-01-23 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Carry & Place corduroy @ F141/F140 Access. SSF-14168 | 11 | F135-F149 | Dore Lake Road | 0 | 44224 |  | 56 | 44230 | SSF-20210123-1 | Carry & Place corduroy @ F141/F140 Access. SSF-14168. Buncher rate from Const Amend #4 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5552KL-20210123-113rd Party Services748.22748.22 | KABI LAKE FOREST PRODUCTS LTD5552KL-20210123-113rd Party Services748.22748.22OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 748.22 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5555 | KL-20210123-14 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1764.95 | Each |  |  |  |  | 1764.95 | 229.4435 | 1994.3935 | 2021-01-23 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336F tracking out from F127 to 17km on Hensen due to no float access. Plowed out all pullouts and F117 Access | 11 | F119-F134 | Hensen Road | 0 | 44224 |  | 55 | 44230 | CR-20210123-3 | Plowed out all pullouts and F117 Access CR-101256 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5555KL-20210123-143rd Party Services1764.951764.95 | KABI LAKE FOREST PRODUCTS LTD5555KL-20210123-143rd Party Services1764.951764.95OEWT-PA13-LEM | [5 empty] | 1 | 1764.95 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5594 | KL-20210124-6 | 53511102 | Access | 0 | 3rd Party Services | 1 | 6935.92 | Each |  |  |  |  | 6935.92 | 901.6696 | 7837.5896 | 2021-01-24 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator, rock truck, and dozer to fill in road with aggregate from rail bed. Spotter on site for rock truck and powerlines. CE-080 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44225 |  | 56 | 44232 | CE-20210124-1 | Excavator, rock truck, and dozer to fill in road with aggregate from rail bed. Spotter on site for rock truck and powerlines. CE-080 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5594KL-20210124-63rd Party Services6935.926935.92 | KABI LAKE FOREST PRODUCTS LTD5594KL-20210124-63rd Party Services6935.926935.92OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 6935.92 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5595 | KL-20210124-7 | 53511102 | Access | 0 | 3rd Party Services | 1 | 3666.36 | Each |  |  |  |  | 3666.36 | 476.6268 | 4142.9868 | 2021-01-24 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Skidder skidding wood to two areas for excavators and filling in ravines @ F156-F158 CE-079 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 | 44225 |  | 15 | 44232 | CE-20210124-2 | Skidder skidding wood to two areas for excavators and filling in ravines @ F156-F158 CE-079 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5595KL-20210124-73rd Party Services3666.363666.36 | KABI LAKE FOREST PRODUCTS LTD5595KL-20210124-73rd Party Services3666.363666.36OEWT-PA13-LEM |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 3666.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5597 | KL-20210124-9 | 53511111 | Access | 0 | 3rd Party Services | 1 | 555.55 | Each |  |  |  |  | 555.55 | 72.2215 | 627.7715 | 2021-01-24 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer doing snow removal on the hill to F140. Carry & Place corduroy @ F140/F139 Access | 11 | F135-F149 | Dore Lake Road | 0 | 44225 |  | 56 | 44232 | SSF-20210124-1 | Dozer doing snow removal on the hill to F140. SSF-14171 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5597KL-20210124-93rd Party Services555.55555.55 | KABI LAKE FOREST PRODUCTS LTD5597KL-20210124-93rd Party Services555.55555.55OEWT-PA13-LEM | [5 empty] | 1 | 555.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5597 | KL-20210124-9 | 53511103 | Access | 0 | 3rd Party Services | 1 | 748.22 | Each |  |  |  |  | 748.22 | 97.2686 | 845.4886 | 2021-01-24 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer doing snow removal on the hill to F140. Carry & Place corduroy @ F140/F139 Access | 11 | F135-F149 | Dore Lake Road | 0 | 44225 |  | 56 | 44232 | SSF-20210124-4 | Carry & Place corduroy @ F140/F139 Access SSF-14170. Buncher rate from Const Amend #4 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5597KL-20210124-93rd Party Services748.22748.22 | KABI LAKE FOREST PRODUCTS LTD5597KL-20210124-93rd Party Services748.22748.22OEWT-PA13-LEM |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 748.22 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5598 | KL-20210124-10 | 53511111 | Access | 0 | 3rd Party Services | 1 | 3687.64 | Each |  |  |  |  | 3687.64 | 479.3932 | 4167.0332 | 2021-01-24 | 0 | OEWT-PA13-LEM | 44235 | 40 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plowed Hensen Rd West from km 0 to km 14. CR-101258 | 11 | F119-F134 | Hensen Road | 0 | 44225 |  | 55 | 44232 | CR-20210124-1 | Plowed Hensen Rd West from km 0 to km 14. CR-101258 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5598KL-20210124-103rd Party Services3687.643687.64 | KABI LAKE FOREST PRODUCTS LTD5598KL-20210124-103rd Party Services3687.643687.64OEWT-PA13-LEM | [5 empty] | 1 | 3687.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5608 | KL-20210125-5 | 53511104 | Access | 0 | 3rd Party Services | 1 | 4172 | Each |  |  |  |  | 4172 | 542.36 | 4714.36 | 2021-01-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator, Rock Truck, and Dozer to fill in road with aggregate near F150. Spotter was on site. CE-081 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44225 |  | 56 | 44232 | CE-20210125-1 | Excavator, Rock Truck, and Dozer to fill in road with aggregate near F150. Spotter was on site. CE-081 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5608KL-20210125-53rd Party Services41724172 | KABI LAKE FOREST PRODUCTS LTD5608KL-20210125-53rd Party Services41724172OEWT-PA14-Lem-R1 |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 4172 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5609 | KL-20210125-6 | 53511104 | Access | 0 | 3rd Party Services | 1 | 1929.65 | Each |  |  |  |  | 1929.65 | 250.8545 | 2180.5045 | 2021-01-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Digging at sides of road to fill rock truck to dump in bad areas to make road better. Dozer levelling aggregate. Spotter helping with dumping trucks and powerline. CE-082 | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44225 |  | 56 | 44232 | CE-20210125-2 | Digging at sides of road to fill rock truck to dump in bad areas to make road better. Dozer levelling aggregate. Spotter helping with dumping trucks and powerline. CE-082 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5609KL-20210125-63rd Party Services1929.651929.65 | KABI LAKE FOREST PRODUCTS LTD5609KL-20210125-63rd Party Services1929.651929.65OEWT-PA14-Lem-R1 |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 1929.65 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5610 | KL-20210125-8 | 53511103 | Access | 0 | 3rd Party Services | 1 | 726.55 | Each |  |  |  |  | 726.55 | 94.4515 | 821.0015 | 2021-01-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 330F Excavator laying corduroy & installing 20' rig mats @ WC 15105. Drag rig mats to F145 with Excavator. Dozer & skidder dragging 20 and 40' rig mats to F140 | 11 | F135-F149 | Dore Lake Road | 0 | 44225 |  | 56 | 44232 | SSF-20210125-1 | Cat 330F Excavator laying corduroy & installing 20' rig mats @ WC 15105. SSF-14174 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5610KL-20210125-83rd Party Services726.55726.55 | KABI LAKE FOREST PRODUCTS LTD5610KL-20210125-83rd Party Services726.55726.55OEWT-PA14-Lem-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 726.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5611 | KL-20210125-7 | 53511103 | Access | 0 | 3rd Party Services | 1 | 2729.82 | Each |  |  |  |  | 2729.82 | 354.8766 | 3084.6966 | 2021-01-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc & skidder filling in ravines to make road @ F153 to F152. Steady scrape and add corduroy into road & ravines. CE-085 | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44225 |  | 56 | 44232 | CE-20210125-3 | Exc & skidder filling in ravines to make road @ F153 to F152. Steady scrape and add corduroy into road & ravines. CE-085 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5611KL-20210125-73rd Party Services2729.822729.82 | KABI LAKE FOREST PRODUCTS LTD5611KL-20210125-73rd Party Services2729.822729.82OEWT-PA14-Lem-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 2729.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5612 | KL-20210125-9 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1296.27 | Each |  |  |  |  | 1296.27 | 168.5151 | 1464.7851 | 2021-01-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Widen & raise road @ F145 as per Valard. Dozer- snow removal from 3km to F140. | 11 | F135-F149 | Dore Lake Road | 0 | 44225 |  | 56 | 44232 | SSF-20210125-2 | Dozer working on snow removal from 3 km to F140. SSF-14175 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5612KL-20210125-93rd Party Services1296.271296.27 | KABI LAKE FOREST PRODUCTS LTD5612KL-20210125-93rd Party Services1296.271296.27OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1296.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5615 | KL-20210125-12 | 53511111 | Access | 0 | 3rd Party Services | 1 | 4470.18 | Each |  |  |  |  | 4470.18 | 581.1234 | 5051.3034 | 2021-01-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators with hydraulic breaker and thumb tracking from F112 to F110 due to no float acces. Plowed Hensen to 17Km, Hensen West from 0-13 Km | 11 | F119-F134 | Hensen Road | 0 | 44225 |  | 55 | 44232 | CR-20210125-2 | Plowed Hensen W km 0 to km 13, operators started early. CR-101261 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5615KL-20210125-123rd Party Services4470.184470.18 | KABI LAKE FOREST PRODUCTS LTD5615KL-20210125-123rd Party Services4470.184470.18OEWT-PA14-Lem-R1 | [5 empty] | 1 | 4470.18 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5615 | KL-20210125-12 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2463 | Each |  |  |  |  | 2463 | 320.19 | 2783.19 | 2021-01-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators with hydraulic breaker and thumb tracking from F112 to F110 due to no float acces. Plowed Hensen to 17Km, Hensen West from 0-13 Km | 11 | F119-F134 | Hensen Road | 0 | 44225 |  | 55 | 44232 | SSF-20210125-4 | Grader plowing Hensen Rd to km 17. SSF-14173 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5615KL-20210125-123rd Party Services24632463 | KABI LAKE FOREST PRODUCTS LTD5615KL-20210125-123rd Party Services24632463OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2463 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5619 | KL-20210126-3 | 53511104 | Access | 0 | 3rd Party Services | 1 | 7803.46 | Each |  |  |  |  | 7803.46 | 1014.4498 | 8817.9098 | 2021-01-26 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc digging at side of road to fill truck to spot dump to fill in road. Dozer levelling, and spotter helping rock truck on road and around power lines. CE-083 | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44228 |  | 56 | 44232 | CE-20210126-1 | Exc digging at side of road to fill truck to spot dump to fill in road. Dozer levelling, and spotter helping rock truck on road and around power lines. CE-083 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5619KL-20210126-33rd Party Services7803.467803.46 | KABI LAKE FOREST PRODUCTS LTD5619KL-20210126-33rd Party Services7803.467803.46OEWT-PA14-Lem-R1 |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 7803.46 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5620 | KL-20210126-4 | 53511103 | Access | 0 | 3rd Party Services | 1 | 2283.45 | Each |  |  |  |  | 2283.45 | 296.8485 | 2580.2985 | 2021-01-26 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc filling in road with corduroy and aggregate to build road to F154-F152. The road has 2 rock faces and ravines to fill in with corduroy and aggregates. Rock faces 2+M | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44228 |  | 56 | 44232 | CE-20210126-2 | Exc filling in road with corduroy and aggregate to build road to F154-F152. The road has 2 rock faces and ravines to fill in with corduroy and aggregates. Rock faces 2+M |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5620KL-20210126-43rd Party Services2283.452283.45 | KABI LAKE FOREST PRODUCTS LTD5620KL-20210126-43rd Party Services2283.452283.45OEWT-PA14-Lem-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 2283.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5621 | KL-20210126-5 | 53511103 | Access | 0 | 3rd Party Services | 1 | 3304.91 | Each |  |  |  |  | 3304.91 | 429.6383 | 3734.5483 | 2021-01-26 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 225 exc w hammer building road with corduroy. Skidder reskidding wood to exc and hammering all day. Building to F158 CE-084 | 11 | F152-F154 | Michipicoten Harbour Road -4 | 0 | 44228 |  | 56 | 44232 | CE-20210126-3 | 225 exc w hammer building road with corduroy. Skidder reskidding wood to exc and hammering all day. Building to F158 CE-084 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5621KL-20210126-53rd Party Services3304.913304.91 | KABI LAKE FOREST PRODUCTS LTD5621KL-20210126-53rd Party Services3304.913304.91OEWT-PA14-Lem-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 3304.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5625 | KL-20210126-9 | 53511111 | Access | 0 | 3rd Party Services | 1 | 726.55 | Each |  |  |  |  | 726.55 | 94.4515 | 821.0015 | 2021-01-26 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track from High Falls Rd 7/Sand hill for float @ High Falls Rd 8 & clear snow from a turn around. MC-13089 | 11 | F198-F202 | High Falls Road- 8 | 0 | 44228 |  | 56 | 44232 | MC-20210126-2 | Track from High Falls Rd 7/Sand hill for float @ High Falls Rd 8 & clear a turn around. MC-13089 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5625KL-20210126-93rd Party Services726.55726.55 | KABI LAKE FOREST PRODUCTS LTD5625KL-20210126-93rd Party Services726.55726.55OEWT-PA14-Lem-R1 | [5 empty] | 1 | 726.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5626 | KL-20210126-10 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1583.27 | Each |  |  |  |  | 1583.27 | 205.8251 | 1789.0951 | 2021-01-26 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal @ High Falls Roads SSF-14177 | 11 | F203-F211 | High Falls Road- 9 | 0 | 44228 |  | 56 | 44232 | SSF-20210126-1 | Grader doing snow removal @ High Falls Roads SSF-14177 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5626KL-20210126-103rd Party Services1583.271583.27 | KABI LAKE FOREST PRODUCTS LTD5626KL-20210126-103rd Party Services1583.271583.27OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1583.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5627 | KL-20210126-11 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2110.82 | Each |  |  |  |  | 2110.82 | 274.4066 | 2385.2266 | 2021-01-26 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader clean snow on Hensen Road W. 0-11km. Skid tress for fill @ F111. Excavator fix road where corduroy showing | 11 | F119-F134 | Hensen Road | 0 | 44228 |  | 55 | 44232 | CR-20210126-1 | Loader pushed snow on Hensen west km 0- km 11 CR-101264 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5627KL-20210126-113rd Party Services2110.822110.82 | KABI LAKE FOREST PRODUCTS LTD5627KL-20210126-113rd Party Services2110.822110.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2110.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5627 | KL-20210126-11 | 53511111 | Access | 0 | 3rd Party Services | 1 | 835.55 | Each |  |  |  |  | 835.55 | 108.6215 | 944.1715 | 2021-01-26 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader clean snow on Hensen Road W. 0-11km. Skid tress for fill @ F111. Excavator fix road where corduroy showing | 11 | F119-F134 | Hensen Road | 0 | 44228 |  | 55 | 44232 | CR-20210126-2 | Exc fixed road where corduroy was starting to show. CR-101263 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5627KL-20210126-113rd Party Services835.55835.55 | KABI LAKE FOREST PRODUCTS LTD5627KL-20210126-113rd Party Services835.55835.55OEWT-PA14-Lem-R1 | [5 empty] | 1 | 835.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5635 | KL-20210127-3 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1111.09 | Each |  |  |  |  | 1111.09 | 144.4417 | 1255.5317 | 2021-01-27 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer doing snow removal and road repairs on the hills. SSF-14179 | 11 | F135-F149 | Dore Lake Road | 0 | 44228 |  | 56 | 44232 | SSF-20210127-1 | Dozer doing snow removal and road repairs on the hills. SSF-14179 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5635KL-20210127-33rd Party Services1111.091111.09 | KABI LAKE FOREST PRODUCTS LTD5635KL-20210127-33rd Party Services1111.091111.09OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1111.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5636 | KL-20210127-4 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1695.27 | Each |  |  |  |  | 1695.27 | 220.3851 | 1915.6551 | 2021-01-27 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clear snow & shape road from F205 to F208 MC-13091 | 11 | F203-F211 | High Falls Road- 9 | 0 |  |  | 56 | 44232 | MC-20210127-1 | Clear snow & shape road from F205 to F208 MC-13091 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5636KL-20210127-43rd Party Services1695.271695.27 | KABI LAKE FOREST PRODUCTS LTD5636KL-20210127-43rd Party Services1695.271695.27OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1695.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5639 | KL-20210127-8 | 53511103 | Access | 0 | 3rd Party Services | 1 | 1980.1 | Each |  |  |  |  | 1980.1 | 257.413 | 2237.513 | 2021-01-27 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Skidder skidding wood to exc. Exc fixing up Corduroy and hammering on Access F156-F158 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 | 44228 |  | 56 | 44232 | CE-20210127-3 | Skidder skidding wood to exc. Exc fixing up Corduroy and hammering on Access F156-F158 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5639KL-20210127-83rd Party Services1980.11980.1 | KABI LAKE FOREST PRODUCTS LTD5639KL-20210127-83rd Party Services1980.11980.1OEWT-PA14-Lem-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 1980.1 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5641 | KL-20210127-7 | 53511102 | Access | 0 | 3rd Party Services | 1 | 7103.37 | Each |  |  |  |  | 7103.37 | 923.4381 | 8026.8081 | 2021-01-27 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc, rock truck, and dozer working F152-F154. Exc dig material from roadside, load truck who spot dumps where needed, and dozer spreads. Exc filling in ravine with Corduroy. Skidder skidding wood to exc to lay out over corduroy in rocky area. Make turn around at end. CE-089 | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44228 |  | 56 | 44232 | CE-20210127-1 | Exc, rock truck, and dozer working F152-F154. Exc dig material from roadside, load truck who spot dumps where needed, and dozer spreads. CE-087 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5641KL-20210127-73rd Party Services7103.377103.37 | KABI LAKE FOREST PRODUCTS LTD5641KL-20210127-73rd Party Services7103.377103.37OEWT-PA14-Lem-R1 |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 7103.37 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5641 | KL-20210127-7 | 53511102 | Access | 0 | 3rd Party Services | 1 | 3060 | Each |  |  |  |  | 3060 | 397.8 | 3457.8 | 2021-01-27 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc, rock truck, and dozer working F152-F154. Exc dig material from roadside, load truck who spot dumps where needed, and dozer spreads. Exc filling in ravine with Corduroy. Skidder skidding wood to exc to lay out over corduroy in rocky area. Make turn around at end. CE-089 | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44228 |  | 56 | 44232 | CE-20210127-2 | Exc filling in ravine with Corduroy. Skidder skidding wood to exc to lay out over corduroy in rocky area. Make turn around at end. CE-089 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5641KL-20210127-73rd Party Services30603060 | KABI LAKE FOREST PRODUCTS LTD5641KL-20210127-73rd Party Services30603060OEWT-PA14-Lem-R1 |  | WF11-New All Season Development | WF11-New All Season Development |  | 1 | 1 | 3060 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5642 | KL-20210127-10 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1275.28 | Each |  |  |  |  | 1275.28 | 165.7864 | 1441.0664 | 2021-01-27 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourers put up signs to 11 Km on Hense Rd. Loader pushing snow to 11Km, excavator sourcing gravel for capping to 8.5 km | 11 | F119-F134 | Hensen Road | 0 | 44228 |  | 55 | 44232 | CR-20210127-4 | Loader pushed snow on Hensen W km 0 to km 11 CR-101267 |  |  |  | Travis Chrisholm | 11 | KABI LAKE FOREST PRODUCTS LTD5642KL-20210127-103rd Party Services1275.281275.28 | KABI LAKE FOREST PRODUCTS LTD5642KL-20210127-103rd Party Services1275.281275.28OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1275.28 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5650 | KL-20210128-2 | 53511103 | Access | 0 | 3rd Party Services | 1 | 1044.28 | Each |  |  |  |  | 1044.28 | 135.7564 | 1180.0364 | 2021-01-28 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Carry & place trees for fill @ F135 Access SSF-14180. Buncher rate from Const Amend #4 | 11 | F135-F149 | Dore Lake Road | 0 | 44228 |  | 56 | 44232 | SSF-20210128-2 | Carry & place trees for fill @ F135 Access SSF-14180. Buncher rate from Const Amend #4 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5650KL-20210128-23rd Party Services1044.281044.28 | KABI LAKE FOREST PRODUCTS LTD5650KL-20210128-23rd Party Services1044.281044.28OEWT-PA14-Lem-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 1044.28 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5651 | KL-20210128-3 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 1704.14 | Each |  |  |  |  | 1704.14 | 221.5382 | 1925.6782 | 2021-01-28 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hammer on MHR 3 Access 155. Hammer on Honi on a corner so spotter was used. CE-093 | 11 | F155 | Michipicoten Harbour Road -3 | 0 | 44228 |  | 56 | 44232 | CE-20210128-2 | Hammer on MHR 3 Access 155. Hammer on Honi on a corner so spotter was used. CE-093 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5651KL-20210128-33rd Party Services1704.141704.14 | KABI LAKE FOREST PRODUCTS LTD5651KL-20210128-33rd Party Services1704.141704.14OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 852.07 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5652 | KL-20210128-4 | 53511103 | Access | 0 | 3rd Party Services | 1 | 5352.46 | Each |  |  |  |  | 5352.46 | 695.8198 | 6048.2798 | 2021-01-28 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc requested to fix up at F156. Build spur Rd 157 then worked on F158 corduroy. Skidder skidding wood to F157/F158 CE-091 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 | 44228 |  | 56 | 44232 | CE-20210128-3 | Exc requested to fix up at F156. Build spur Rd 157 then worked on F158 corduroy. Skidder skidding wood to F157/F158 CE-091 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5652KL-20210128-43rd Party Services5352.465352.46 | KABI LAKE FOREST PRODUCTS LTD5652KL-20210128-43rd Party Services5352.465352.46OEWT-PA14-Lem-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 5352.46 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5660 | KL-20210128-12 | 53511104 | Access | 0 | 3rd Party Services | 1 | 6903.46 | Each |  |  |  |  | 6903.46 | 897.4498 | 7800.9098 | 2021-01-28 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc load rock truck and hual to top of hub tower box. Hauled gravel to third bridge in road. Filled in dips on hill after the third bridge. Dozer levelling CE-090 | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44228 |  | 56 | 44232 | CE-20210128-1 | Exc load rock truck and haul to top of hub tower box. Hauled gravel to third bridge in road. Filled in dips on hill after the third bridge. Dozer levelling CE-090 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5660KL-20210128-123rd Party Services6903.466903.46 | KABI LAKE FOREST PRODUCTS LTD5660KL-20210128-123rd Party Services6903.466903.46OEWT-PA14-Lem-R1 |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 6903.46 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5661 | KL-20210128-13 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 2744.27 | Each |  |  |  |  | 2744.27 | 356.7551 | 3101.0251 | 2021-01-28 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hammer on MHR 4 @ Access F158 make access to F158 tower. CE-092 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 | 44228 |  | 56 | 44232 | CE-20210128-4 | Hammer on MHR 4 @ Access F158 make access to F158 tower. CE-092 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5661KL-20210128-133rd Party Services2744.272744.27 | KABI LAKE FOREST PRODUCTS LTD5661KL-20210128-133rd Party Services2744.272744.27OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 1372.135 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5668 | KL-20210130-5 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 4670.91 | Each |  |  |  |  | 4670.91 | 607.2183 | 5278.1283 | 2021-01-30 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hammer working on rock closer to powerline, spotter used. Excavator clean up, small tools used to change over and keep fitting tight to avoid leaks, spotter used - CE-096 | 11 | F155 | Michipicoten Harbour Road -3 | 0 | 44231 |  | 50 | 44232 | CE-20210130-1 | Hammer working on rock closer to powerline, spotter used. Excavator clean up, small tools used to change over and keep fitting tight to avoid leaks, spotter used - CE-096 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD5668KL-20210130-53rd Party Services4670.914670.91 | KABI LAKE FOREST PRODUCTS LTD5668KL-20210130-53rd Party Services4670.914670.91OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 2335.455 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5689 | KL-20210129-7 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 3577.64 | Each |  |  |  |  | 3577.64 | 465.0932 | 4042.7332 | 2021-01-29 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hammer on MHR 3 F155 near HONI hammering rock corner - small tools are for interchanging hammer and bucket - CE-094 | 11 | F155 | Michipicoten Harbour Road -3 | 0 | 44234 |  | 56 | 44236 | CE-20210129-1 | Hammering Corner - CE-094 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5689KL-20210129-73rd Party Services3577.643577.64 | KABI LAKE FOREST PRODUCTS LTD5689KL-20210129-73rd Party Services3577.643577.64OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 1788.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5696 | KL-20210201-4 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 3730.82 | Each |  |  |  |  | 3730.82 | 485.0066 | 4215.8266 | 2021-02-01 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hammer working on rock areas to widen road - CE-100 | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44235 |  | 56 | 44236 | CE-20210201-1 | Hammer - CE-100 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5696KL-20210201-43rd Party Services3730.823730.82 | KABI LAKE FOREST PRODUCTS LTD5696KL-20210201-43rd Party Services3730.823730.82OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 1865.41 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5697 | KL-20210201-5 | 53511103 | Access | 0 | 3rd Party Services | 1 | 919.55 | Each |  |  |  |  | 919.55 | 119.5415 | 1039.0915 | 2021-02-01 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Skidder skidding wood to F158 - CE-098 / Shovel loading gravel to build road to tower structure F156 abd F157 ramps to level road to rock face - CE-099 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 | 44235 |  | 56 | 44236 | CE-20210201-2 | Skidding wood - CE-098 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5697KL-20210201-53rd Party Services919.55919.55 | KABI LAKE FOREST PRODUCTS LTD5697KL-20210201-53rd Party Services919.55919.55OEWT-PA14-Lem-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 919.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5697 | KL-20210201-5 | 53511104 | Access | 0 | 3rd Party Services | 1 | 5376 | Each |  |  |  |  | 5376 | 698.88 | 6074.88 | 2021-02-01 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Skidder skidding wood to F158 - CE-098 / Shovel loading gravel to build road to tower structure F156 abd F157 ramps to level road to rock face - CE-099 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 | 44235 |  | 56 | 44236 | CE-20210201-3 | Bluiding road up - CE-099 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5697KL-20210201-53rd Party Services53765376 | KABI LAKE FOREST PRODUCTS LTD5697KL-20210201-53rd Party Services53765376OEWT-PA14-Lem-R1 |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 5376 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5706 | KL-20210131-5 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 3506.45 | Each |  |  |  |  | 3506.45 | 455.8385 | 3962.2885 | 2021-01-31 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hammer working on rock close to powerline spotter used, Shovel cleaning up, small tools used to change over and keep fittings tight to avoid leaks spotter used - CE-097 | 11 | F155 | Michipicoten Harbour Road -3 | 0 | 44235 |  | 56 | 44236 | CE-20210131-1 | Hammer - CE-097 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5706KL-20210131-53rd Party Services3506.453506.45 | KABI LAKE FOREST PRODUCTS LTD5706KL-20210131-53rd Party Services3506.453506.45OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 1753.225 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5715 | KL-20210202-5 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1393.09 | Each |  |  |  |  | 1393.09 | 181.1017 | 1574.1917 | 2021-02-02 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying hill and corners on Hensen Road to Km 17. Excavator, D5 laying and capping corudroy between F81 and F84 | 11 | F119-F134 | Hensen Road | 0 | 44235 |  | 53 | 44242 | SSF-20210202-1 | Grading Road - SSF-14186 |  |  |  | Clint Maerz | 11 | KABI LAKE FOREST PRODUCTS LTD5715KL-20210202-53rd Party Services1393.091393.09 | KABI LAKE FOREST PRODUCTS LTD5715KL-20210202-53rd Party Services1393.091393.09OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1393.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5717 | KL-20210202-7 | 53511111 | Access | 0 | 3rd Party Services | 1 | 740.73 | Each |  |  |  |  | 740.73 | 96.2949 | 837.0249 | 2021-02-02 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 336 Excavator to Anjigmi Road after completion of road building in MFN | 11 | F135-F149 | Dore Lake Road | 0 | 44235 |  | 56 | 44237 | SSF-20210202-2 | pushing snow - SSF-14187 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5717KL-20210202-73rd Party Services740.73740.73 | KABI LAKE FOREST PRODUCTS LTD5717KL-20210202-73rd Party Services740.73740.73OEWT-PA14-Lem-R1 | [5 empty] | 1 | 740.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5722 | KL-20210202-12 | 53511111 | Access | 0 | 3rd Party Services | 1 | 774.55 | Each |  |  |  |  | 774.55 | 100.6915 | 875.2415 | 2021-02-02 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator clearing Snow to F205 - MC-13094 | 11 | F203-F211 | High Falls Road - 9 | 0 | 44235 |  | 56 | 44237 | MC-20210202-1 | Snow removal - MC-13094 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5722KL-20210202-123rd Party Services774.55774.55 | KABI LAKE FOREST PRODUCTS LTD5722KL-20210202-123rd Party Services774.55774.55OEWT-PA14-Lem-R1 | [5 empty] | 1 | 774.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5751 | KL-20210203-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1265.1 | Each |  |  |  |  | 1265.1 | 164.463 | 1429.563 | 2021-02-03 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Sourcing Material, stockpile gravel. D5 clear F82 to F83 - CR-101294 / Corduroy wetlands from F81 to F80 - CR-101293 / Sand road to move our rock truck - CR-101292 | 11 | F119-F134 | Hensen Road | 0 | 44243 |  | 53 | 44247 | CR-20210203-5 | Loader and Dozer clearing and sanding road to bring out Rock Truck - CR-101292 |  |  |  | Clint Maerz | 11 | KABI LAKE FOREST PRODUCTS LTD5751KL-20210203-83rd Party Services1265.11265.1 | KABI LAKE FOREST PRODUCTS LTD5751KL-20210203-83rd Party Services1265.11265.1OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1265.1 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5753 | KL-20210203-10 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1481.45 | Each |  |  |  |  | 1481.45 | 192.5885 | 1674.0385 | 2021-02-03 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Track in and out due to no float access, fill with trees to minimize steep grade, Cap with existing material. Make safety berms. Dozer clear road km 14 to F144 | 11 | F135-F149 | Dore Lake Road | 0 | 44243 |  | 56 | 44247 | SSF-20210203-1 | Dozer finish pushing snow back and cleaning pull offs from F144 to km14 on Dore Road - SSF-14190 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5753KL-20210203-103rd Party Services1481.451481.45 | KABI LAKE FOREST PRODUCTS LTD5753KL-20210203-103rd Party Services1481.451481.45OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1481.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5756 | KL-20210203-13 | 53511104 | Access | 0 | 3rd Party Services | 1 | 2226.14 | Each |  |  |  |  | 2226.14 | 289.3982 | 2515.5382 | 2021-02-03 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shovel and rock truck hauling gravel to hub. Shovel moved to MHR 2 Escort Shovel to next site. | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44243 |  | 56 | 44247 | CE-20210203-1 | Shovel and rock truck hauling gravel to hub, made turnaround, there was no aggregate at these areas so needed to haul aggregate found at access - CE-105 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5756KL-20210203-133rd Party Services2226.142226.14 | KABI LAKE FOREST PRODUCTS LTD5756KL-20210203-133rd Party Services2226.142226.14OEWT-PA14-Lem-R1 |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 2226.14 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5757 | KL-20210203-14 | 53511101 | Access | 0 | 3rd Party Services | 1 | 883.55 | Each |  |  |  |  | 883.55 | 114.8615 | 998.4115 | 2021-02-03 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Existing All Season Upgrade |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Berms and bumpers installed near F158- CE-107 / Skid mats, haul corduroy and lay geo. - CE-108 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 | 44243 |  | 56 | 44247 | CE-20210203-4 | Shovel put Berm and bumpers on Road near F158 - CE-107 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5757KL-20210203-143rd Party Services883.55883.55 | KABI LAKE FOREST PRODUCTS LTD5757KL-20210203-143rd Party Services883.55883.55OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 441.775 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5758 | KL-20210203-15 | 53511103 | Access | 0 | 3rd Party Services | 1 | 3839.82 | Each |  |  |  |  | 3839.82 | 499.1766 | 4338.9966 | 2021-02-03 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hammer working to widen road at rock areas - CE-104 | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44243 |  | 56 | 44247 | CE-20210203-3 | Hammer working to widen road at rock areas - CE-104 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5758KL-20210203-153rd Party Services3839.823839.82 | KABI LAKE FOREST PRODUCTS LTD5758KL-20210203-153rd Party Services3839.823839.82OEWT-PA14-Lem-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 3839.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5765 | KL-20210204-7-R1 | 53511104 | Access | 0 | 3rd Party Services | 1 | 1305.27 | Each |  |  |  |  | 1305.27 | 169.6851 | 1474.9551 | 2021-02-04 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and rock truck fixing up and adding gravel to hub. Also @F152 load, dump, spread gravel fix by adding gravel to turnarounds at structure. | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44243 |  | 56 | 44252 | CE-20210204-2 | Shovel and Rock truck working on Harbour Rd 2 @F152 load, dump, spread gravel fix by adding gravel to turnarounds at structure. CE-110. RT Rate from Const Amend #4 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5765KL-20210204-7-R13rd Party Services1305.271305.27 | KABI LAKE FOREST PRODUCTS LTD5765KL-20210204-7-R13rd Party Services1305.271305.27OEWT-PA14-Lem-R1 |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 1305.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5765 | KL-20210204-7-R1 | 53511104 | Access | 0 | 3rd Party Services | 1 | 1942.46 | Each |  |  |  |  | 1942.46 | 252.5198 | 2194.9798 | 2021-02-04 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator and rock truck fixing up and adding gravel to hub. Also @F152 load, dump, spread gravel fix by adding gravel to turnarounds at structure. | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44243 |  | 56 | 44252 | CE-20210204-3 | Shovel and Rock Truck working on Harbour 2 Rd adding gravel to hub & fixing it up. CE-111 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5765KL-20210204-7-R13rd Party Services1942.461942.46 | KABI LAKE FOREST PRODUCTS LTD5765KL-20210204-7-R13rd Party Services1942.461942.46OEWT-PA14-Lem-R1 |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 1942.46 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5766 | KL-20210204-8 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 1895.1 | Each |  |  |  |  | 1895.1 | 246.363 | 2141.463 | 2021-02-04 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Move hammer, exc, and rock truck from Harbour Rd 2 to Dore Lake Rd to continue hammering & shovel support. CE-112 | 11 | F135-F149 | Dore Lake Road | 0 | 44243 |  | 56 | 44247 | CE-20210204-4 | Move hammer, exc, and rock truck from Harbour Rd 2 to Dore Lake Rd to continue hammering & shovel support. CE-112 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5766KL-20210204-83rd Party Services1895.11895.1 | KABI LAKE FOREST PRODUCTS LTD5766KL-20210204-83rd Party Services1895.11895.1OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 947.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5774 | KL-20210204-15 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 2644.27 | Each |  |  |  |  | 2644.27 | 343.7551 | 2988.0251 | 2021-02-04 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Blasting rock areas on Harbour Road 2. CE-109 | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44243 |  | 56 | 44247 | CE-20210204-1 | Blasting rock areas on Harbour Road 2. CE-109 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5774KL-20210204-153rd Party Services2644.272644.27 | KABI LAKE FOREST PRODUCTS LTD5774KL-20210204-153rd Party Services2644.272644.27OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 1322.135 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5779 | KL-20210205-5 | 53511111 | Access | 0 | 3rd Party Services | 1 | 696.55 | Each |  |  |  |  | 696.55 | 90.5515 | 787.1015 | 2021-02-05 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal from High Falls Rd to F207 SSF-14195 | 11 | F203-F211 | High Falls Road- 9 | 0 | 44243 |  | 56 | 44247 | SSF-20210205-1 | Grader doing snow removal from High Falls Rd to F207 SSF-14195 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5779KL-20210205-53rd Party Services696.55696.55 | KABI LAKE FOREST PRODUCTS LTD5779KL-20210205-53rd Party Services696.55696.55OEWT-PA14-Lem-R1 | [5 empty] | 1 | 696.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5781 | KL-20210205-7 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1190.1 | Each |  |  |  |  | 1190.1 | 154.713 | 1344.813 | 2021-02-05 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader & dozer clearing snow from roadways from Km 0 to Km 13 Hensen West. 323 rehabed borrow pit at F83 | 11 | F119-F134 | Hensen Road | 0 | 44243 |  | 15 | 44247 | CR-20210205-1 | Loader & dozer clearing snow from roadways from Km 0 to Km 13 Hensen West. Operators started shift early. CR-101300 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5781KL-20210205-73rd Party Services1190.11190.1 | KABI LAKE FOREST PRODUCTS LTD5781KL-20210205-73rd Party Services1190.11190.1OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1190.1 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5781 | KL-20210205-7 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2529 | Each |  |  |  |  | 2529 | 328.77 | 2857.77 | 2021-02-05 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader & dozer clearing snow from roadways from Km 0 to Km 13 Hensen West. 323 rehabed borrow pit at F83 | 11 | F119-F134 | Hensen Road | 0 | 44243 |  | 15 | 44247 | SSF-20210205-2 | Grader plowing snow from Hwy 17 to km 17 on Hensen Rd. SSF-14193 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5781KL-20210205-73rd Party Services25292529 | KABI LAKE FOREST PRODUCTS LTD5781KL-20210205-73rd Party Services25292529OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2529 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5783 | KL-20210205-9 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2012 | Each |  |  |  |  | 2012 | 261.56 | 2273.56 | 2021-02-05 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer clearing snow to F135 on Dore Lake Rd. SSF-14194 | 11 | F135-F149 | Dore Lake Road | 0 | 44243 |  | 56 | 44247 | KL-20210205-9 | Dozer clearing snow to F135 on Dore Lake Rd. SSF-14194 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5783KL-20210205-93rd Party Services20122012 | KABI LAKE FOREST PRODUCTS LTD5783KL-20210205-93rd Party Services20122012OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2012 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5785 | KL-20210205-11 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 6421.64 | Each |  |  |  |  | 6421.64 | 834.8132 | 7256.4532 | 2021-02-05 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator with hydraulic breaker hammering rock to widen road. Shovel behind using material to fix up road and support hammer. CE-113 | 11 | F135-F149 | Dore Lake Road | 0 | 44243 |  | 56 | 44247 | CE-20210205-1 | Excavator with hydraulic breaker hammering rock to widen road. Shovel behind using material to fix up road and support hammer. CE-113 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5785KL-20210205-113rd Party Services6421.646421.64 | KABI LAKE FOREST PRODUCTS LTD5785KL-20210205-113rd Party Services6421.646421.64OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 3210.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5789 | KL-20210206-4 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1296.27 | Each |  |  |  |  | 1296.27 | 168.5151 | 1464.7851 | 2021-02-06 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer clearing snow on Dore Lake Rd. SSF-14198 | 11 | F135-F149 | Dore Lake Road | 0 | 44243 |  | 56 | 44247 | SSF-20210206-1 | Dozer clearing snow on Dore Lake Rd. SSF-14198 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5789KL-20210206-43rd Party Services1296.271296.27 | KABI LAKE FOREST PRODUCTS LTD5789KL-20210206-43rd Party Services1296.271296.27OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1296.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5790 | KL-20210206-5 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1160.91 | Each |  |  |  |  | 1160.91 | 150.9183 | 1311.8283 | 2021-02-06 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal from High Falls Road to F207 SSF-14197 | 11 | F203-F211 | High Falls Road- 9 | 0 | 44243 |  | 56 | 44247 | SSF-20210206-2 | Grader doing snow removal from High Falls Road to F207 SSF-14197 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5790KL-20210206-53rd Party Services1160.911160.91 | KABI LAKE FOREST PRODUCTS LTD5790KL-20210206-53rd Party Services1160.911160.91OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1160.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5793 | KL-20210206-8 | 53511103 | Access | 0 | 3rd Party Services | 1 | 2723.46 | Each |  |  |  |  | 2723.46 | 354.0498 | 3077.5098 | 2021-02-06 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Lay geo over corduroy in wetland. Clear snow from Hwy 17 to Km 17 on Hensen, 0Km to 13Km on Hensen West. | 11 | F119-F134 | Hensen Road | 0 | 44243 |  | 15 | 44248 | CR-20210206-1 | Labourers rolled geo for wetland at F79, exc covered corduroy with material. CR-101304 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5793KL-20210206-83rd Party Services2723.462723.46 | KABI LAKE FOREST PRODUCTS LTD5793KL-20210206-83rd Party Services2723.462723.46OEWT-PA14-Lem-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 2723.46 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5793 | KL-20210206-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 829.72 | Each |  |  |  |  | 829.72 | 107.8636 | 937.5836 | 2021-02-06 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Lay geo over corduroy in wetland. Clear snow from Hwy 17 to Km 17 on Hensen, 0Km to 13Km on Hensen West. | 11 | F119-F134 | Hensen Road | 0 | 44243 |  | 15 | 44248 | CR-20210206-3 | Loader & dozer clearing snow from roadways km 0 to km 13 Hensen West. Operators started shift early. CR-101307 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5793KL-20210206-83rd Party Services829.72829.72 | KABI LAKE FOREST PRODUCTS LTD5793KL-20210206-83rd Party Services829.72829.72OEWT-PA14-Lem-R1 | [5 empty] | 1 | 829.72 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5793 | KL-20210206-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-02-06 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Lay geo over corduroy in wetland. Clear snow from Hwy 17 to Km 17 on Hensen, 0Km to 13Km on Hensen West. | 11 | F119-F134 | Hensen Road | 0 | 44243 |  | 15 | 44248 | SSF-20210206-3 | Grader plowing snow from Hwy 17 to Km17 on Hensen Road |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5793KL-20210206-83rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD5793KL-20210206-83rd Party Services2321.822321.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5795 | KL-20210206-10 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 3468.64 | Each |  |  |  |  | 3468.64 | 450.9232 | 3919.5632 | 2021-02-06 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Widen & straighten road at F144-F143 CE-114 | 11 | F135-F149 | Dore Lake Road | 0 | 44243 |  | 56 | 44247 | CE-20210206-1 | Widen & straighten road at F144-F143 CE-114 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5795KL-20210206-103rd Party Services3468.643468.64 | KABI LAKE FOREST PRODUCTS LTD5795KL-20210206-103rd Party Services3468.643468.64OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 1734.32 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5796 | KL-20210206-11 | 53511103 | Access | 0 | 3rd Party Services | 1 | 3291.18 | Each |  |  |  |  | 3291.18 | 427.8534 | 3719.0334 | 2021-02-06 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Skidder skidding trees to excavator to corduroy road. Exc dig for aggregate to cover corduroy. Dozer pushed & levelled aggregate. CE-115 | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44243 |  | 56 | 44247 | CE-20210206-2 | Skidder skidding trees to excavator to corduroy road. Exc dig for aggregate to cover corduroy. Dozer pushed & levelled aggregate. CE-115 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5796KL-20210206-113rd Party Services3291.183291.18 | KABI LAKE FOREST PRODUCTS LTD5796KL-20210206-113rd Party Services3291.183291.18OEWT-PA14-Lem-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 3291.18 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5803 | KL-20210207-4 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1111.09 | Each |  |  |  |  | 1111.09 | 144.4417 | 1255.5317 | 2021-02-07 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer Scraping Hills on Dore Lake Rd to F135 SSF-14201 | 11 | F135-F149 | Dore Lake Road | 0 | 44243 |  | 56 | 44247 | SSF-20210207-1 | Dozer Scraping Hills on Dore Lake Rd to F135 SSF-14201 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5803KL-20210207-43rd Party Services1111.091111.09 | KABI LAKE FOREST PRODUCTS LTD5803KL-20210207-43rd Party Services1111.091111.09OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1111.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5805 | KL-20210207-6 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1857.45 | Each |  |  |  |  | 1857.45 | 241.4685 | 2098.9185 | 2021-02-07 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Exc laid corduroy and covered it on Honi Line at F78 due to bad conditions. Grader Plowing Snow from Hwy 17 to Km 17 on Hensen Rd. | 11 | F119-F134 | Hensen Road | 0 | 44243 |  | 15 | 44248 | SSF-20210207-2 | Grader Plowing Snow from Hwy 17 to Km 17 on Hensen Rd. SSF-14200 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5805KL-20210207-63rd Party Services1857.451857.45 | KABI LAKE FOREST PRODUCTS LTD5805KL-20210207-63rd Party Services1857.451857.45OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1857.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5807 | KL-20210207-8 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 3468.64 | Each |  |  |  |  | 3468.64 | 450.9232 | 3919.5632 | 2021-02-07 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hammer @ F144 hammering rock on access to make wider for Valard. Small tools to keep hoses tight so no leaks or sprays occur. CE-116 | 11 | F135-F149 | Dore Lake Road | 0 | 44243 |  | 56 | 44247 | CE-20210207-1 | Hammer @ F144 hammering rock on access to make wider for Valard. Small tools to keep hoses tight so no leaks or sprays occur. CE-116 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5807KL-20210207-83rd Party Services3468.643468.64 | KABI LAKE FOREST PRODUCTS LTD5807KL-20210207-83rd Party Services3468.643468.64OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 1734.32 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5813 | KL-20210208-6 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 3468.64 | Each |  |  |  |  | 3468.64 | 450.9232 | 3919.5632 | 2021-02-08 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hammer working on Dore Rd. Small tools to tighten hoses on Hammer to prevent oil leak or spray. CE-117 | 11 | F135-F149 | Dore Lake Road | 0 | 44243 |  | 56 | 44249 | CE-20210208-1 | Hammer working on Dore Rd. Small tools to tighten hoses on Hammer to prevent oil leak or spray. CE-117 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5813KL-20210208-63rd Party Services3468.643468.64 | KABI LAKE FOREST PRODUCTS LTD5813KL-20210208-63rd Party Services3468.643468.64OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 1734.32 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5814 | KL-20210208-7 | 53511111 | Access | 0 | 3rd Party Services | 1 | 464.36 | Each |  |  |  |  | 464.36 | 60.3668 | 524.7268 | 2021-02-08 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal from High Falls Rd. SSF-14204 | 11 | F203-F211 | High Falls Road- 9 | 0 | 44243 |  | 56 | 44249 | SSF-20210208-2 | Grader doing snow removal from High Falls Rd. SSF-14204 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5814KL-20210208-73rd Party Services464.36464.36 | KABI LAKE FOREST PRODUCTS LTD5814KL-20210208-73rd Party Services464.36464.36OEWT-PA14-Lem-R1 | [5 empty] | 1 | 464.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5817 | KL-20210208-10 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2198.64 | Each |  |  |  |  | 2198.64 | 285.8232 | 2484.4632 | 2021-02-08 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying Hensen Rd from Hwy 17 to Km 17. SSF-14202 | 11 | F119-F134 | Hensen Road | 0 | 44243 |  | 15 | 44248 | SSF-20210208-3 | Grader scarifying Hensen Rd from Hwy 17 to Km 17. SSF-14202Grader scarifying Hensen Rd from Hwy 17 to Km 17. SSF-14202 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5817KL-20210208-103rd Party Services2198.642198.64 | KABI LAKE FOREST PRODUCTS LTD5817KL-20210208-103rd Party Services2198.642198.64OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2198.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5819 | KL-20210208-12 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1590.45 | Each |  |  |  |  | 1590.45 | 206.7585 | 1797.2085 | 2021-02-08 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer scraping hills & pull offs on Dore Lake Rd to F135 SSF-14203 | 11 | F135-F149 | Dore Lake Road | 0 | 44243 |  | 56 | 44249 | SSF-20210208-1 | Dozer scraping hills & pull offs on Dore Lake Rd to F135 SSF-14203 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5819KL-20210208-123rd Party Services1590.451590.45 | KABI LAKE FOREST PRODUCTS LTD5819KL-20210208-123rd Party Services1590.451590.45OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1590.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5831 | KL-20210209-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-02-09 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal on High Falls Roads. SSF-14207 | 11 | F203-F211 | High Falls Road- 9 | 0 | 44243 |  | 56 | 44249 | SSF-20210209-1 | Grader doing snow removal on High Falls Roads. SSF-14207 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5831KL-20210209-83rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD5831KL-20210209-83rd Party Services2321.822321.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5832 | KL-20210209-9 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 3468.64 | Each |  |  |  |  | 3468.64 | 450.9232 | 3919.5632 | 2021-02-09 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Widen & straighten road at structure 143. Tools to tighten hoses so no leaks or spray. CE-118 | 11 | F135-F149 | Dore Lake Road | 0 | 44243 |  | 56 | 44249 | CE-20210209-1 | Widen & straighten road at structure 143. Tools to tighten hoses so no leaks or spray. CE-118 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5832KL-20210209-93rd Party Services3468.643468.64 | KABI LAKE FOREST PRODUCTS LTD5832KL-20210209-93rd Party Services3468.643468.64OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 1734.32 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5835 | KL-20210209-12 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-02-09 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourers installed overhead wire signs up Hensen West. Labourers cut and placed geo on shoefly past F73. Dozer trimming and shaping roads from F80 to F75. Grader removing snow from Hwy 17 to Km 17 | 11 | F119-F134 | Hensen Road | 0 | 44243 |  | 15 | 44250 | SSF-20210209-3 | Grader doing snow removal on Hensen Rd from Hwy 17 to km 17. SSF-14205 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5835KL-20210209-123rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD5835KL-20210209-123rd Party Services2321.822321.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5836 | KL-20210209-13 | 53531101 | Rig/Access Mats | 0 | 3rd Party Services | 1 | 1310.09 | Each |  |  |  |  | 1310.09 | 170.3117 | 1480.4017 | 2021-02-09 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader brought 40' rig mats back to WC 11260 from F83 to forward for WC 11241. 330 brought in 2 x 40' & 2 x 20' mats for WC 11240 & 11241 | 11 | F119-F134 | Hensen Road | 0 | 44243 |  | 15 | 44250 | CR-20210209-5 | Loader brought 40' rig mats back to WC 11260 from F83 to forward for WC 11241 CR-101315 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5836KL-20210209-133rd Party Services1310.091310.09 | KABI LAKE FOREST PRODUCTS LTD5836KL-20210209-133rd Party Services1310.091310.09OEWT-PA14-Lem-R1 |  |  | WF10-WaterCrossing |  |  | 1 | 1310.09 | WC610,WC611 | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5836 | KL-20210209-13 | 53531101 | Rig/Access Mats | 0 | 3rd Party Services | 1 | 1828.27 | Each |  |  |  |  | 1828.27 | 237.6751 | 2065.9451 | 2021-02-09 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader brought 40' rig mats back to WC 11260 from F83 to forward for WC 11241. 330 brought in 2 x 40' & 2 x 20' mats for WC 11240 & 11241 | 11 | F119-F134 | Hensen Road | 0 | 44243 |  | 15 | 44250 | CR-20210209-6 | 330 brought in 2 x 40' & 2 x 20' mats for WC 11240 & 11241 from WC-11270, 336 installed. CR-101316 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5836KL-20210209-133rd Party Services1828.271828.27 | KABI LAKE FOREST PRODUCTS LTD5836KL-20210209-133rd Party Services1828.271828.27OEWT-PA14-Lem-R1 |  |  | WF10-WaterCrossing |  |  | 1 | 1828.27 | WC610,WC611 | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5837 | KL-20210209-14 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1851.82 | Each |  |  |  |  | 1851.82 | 240.7366 | 2092.5566 | 2021-02-09 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer doing snow removal & pull offs on Dore Lake Rd to F135 SSF-14206 | 11 | F135-F149 | Dore Lake Road | 0 | 44243 |  | 56 | 44249 | SSF-20210209-2 | Dozer doing snow removal & pull offs on Dore Lake Rd to F135 SSF-14206 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5837KL-20210209-143rd Party Services1851.821851.82 | KABI LAKE FOREST PRODUCTS LTD5837KL-20210209-143rd Party Services1851.821851.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1851.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5843 | KL-20210210-5 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 3730.82 | Each |  |  |  |  | 3730.82 | 485.0066 | 4215.8266 | 2021-02-10 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hammer road and widen with Doosan @ F143 Dore Lake Rd. CE-119 | 11 | F135-F149 | Dore Lake Road | 0 | 44244 |  | 56 | 44249 | CE-20210210-1 | Hammer road and widen with Doosan @ F143 Dore Lake Rd. CE-119 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5843KL-20210210-53rd Party Services3730.823730.82 | KABI LAKE FOREST PRODUCTS LTD5843KL-20210210-53rd Party Services3730.823730.82OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 1865.41 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5844 | KL-20210210-6 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2720 | Each |  |  |  |  | 2720 | 353.6 | 3073.6 | 2021-02-10 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal, skidder plowing hills@F209 & excavator sanding hills. SSF-14208 | 11 | F203-F211 | High Falls Road- 9 | 0 | 44244 |  | 56 | 44249 | SSF-20210210-2 | Grader doing snow removal, skidder plowing hills@F209 & excavator sanding hills. SSF-14208 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5844KL-20210210-63rd Party Services27202720 | KABI LAKE FOREST PRODUCTS LTD5844KL-20210210-63rd Party Services27202720OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2720 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5846 | KL-20210210-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2110.82 | Each |  |  |  |  | 2110.82 | 274.4066 | 2385.2266 | 2021-02-10 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Go to Hensen Rd and steam a culvert @ km 3.5. Cover corduroy in shoefly past F73. Clear snow from road from 0 to 15Km on Hensen West and from Hwy17 to 17Km. | 11 | F119-F134 | Hensen Road | 0 | 44244 |  | 15 | 44250 | CR-20210210-3 | Loader cleared road from km 0 to km 15 on Hensen West. CR-101320 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5846KL-20210210-83rd Party Services2110.822110.82 | KABI LAKE FOREST PRODUCTS LTD5846KL-20210210-83rd Party Services2110.822110.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2110.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5846 | KL-20210210-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2430.82 | Each |  |  |  |  | 2430.82 | 316.0066 | 2746.8266 | 2021-02-10 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Go to Hensen Rd and steam a culvert @ km 3.5. Cover corduroy in shoefly past F73. Clear snow from road from 0 to 15Km on Hensen West and from Hwy17 to 17Km. | 11 | F119-F134 | Hensen Road | 0 | 44244 |  | 15 | 44250 | SSF-20210210-3 | Grader doing snow removal on Hensen Rd from Hwy 17 to km 17. SSF-14210 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5846KL-20210210-83rd Party Services2430.822430.82 | KABI LAKE FOREST PRODUCTS LTD5846KL-20210210-83rd Party Services2430.822430.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2430.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5848 | KL-20210210-10 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1960.82 | Each |  |  |  |  | 1960.82 | 254.9066 | 2215.7266 | 2021-02-10 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer doing snow removal & pull offs on Dore Lake Rd to F135 SSF-14209 | 11 | F135-F149 | Dore Lake Road | 0 | 44244 |  | 56 | 44249 | SSF-20210210-1 | Dozer doing snow removal & pull offs on Dore Lake Rd to F135 SSF-14209 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5848KL-20210210-103rd Party Services1960.821960.82 | KABI LAKE FOREST PRODUCTS LTD5848KL-20210210-103rd Party Services1960.821960.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1960.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5864 | KL-20210211-8 | 53511103 | Access | 0 | 3rd Party Services | 1 | 1399.91 | Each |  |  |  |  | 1399.91 | 181.9883 | 1581.8983 | 2021-02-11 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator layed corduroy in a few wet places before WC 11250.01 - CR-101327 | 11 | F119-F134 | Hensen Road | 0 | 44244 |  | 15 | 44250 | CR-20210211-3 | Excavator layed corduroy in a few wet places before WC 11250.01 - CR-101327 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5864KL-20210211-83rd Party Services1399.911399.91 | KABI LAKE FOREST PRODUCTS LTD5864KL-20210211-83rd Party Services1399.911399.91OEWT-PA14-Lem-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 1399.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5865 | KL-20210211-9 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2198.64 | Each |  |  |  |  | 2198.64 | 285.8232 | 2484.4632 | 2021-02-11 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Scarifying hills and corners /clearing pull offs on Hensen road from Hwy 17 to Km 17 - SSF-14211 | 11 | F119-F134 | Hensen Road | 0 | 44244 |  | 15 | 44250 | SFF-20210211-1 | Grader Scarifying hills and corners /clearing pull offs on Hensen road from Hwy 17 to Km 17 - SSF-14211 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5865KL-20210211-93rd Party Services2198.642198.64 | KABI LAKE FOREST PRODUCTS LTD5865KL-20210211-93rd Party Services2198.642198.64OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2198.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5866 | KL-20210211-10 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2069.82 | Each |  |  |  |  | 2069.82 | 269.0766 | 2338.8966 | 2021-02-11 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer doing snow removal and pull offs on Dore Lake Road F145 to F135 | 11 | F135-F149 | Dore Lake Road | 0 | 44244 |  | 14 | 44249 | SFF-20210211-2 | Dozer doing snow removal and pull offs on Dore Lake Road F145 to F135 |  |  |  | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD5866KL-20210211-103rd Party Services2069.822069.82 | KABI LAKE FOREST PRODUCTS LTD5866KL-20210211-103rd Party Services2069.822069.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2069.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5867 | KL-20210211-11-R1 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2767.82 | Each |  |  |  |  | 2767.82 | 359.8166 | 3127.6366 | 2021-02-11 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Walk to structure F147, open parking spaces CE-122 / Haul Gravel - CE-120 | 11 | F135-F149 | Dore Lake Road | 0 | 44244 |  | 56 | 44249 | CE-20210211-1 | Walked Doosan 300 to Structure 147, open parking spots and widen - CE-122 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5867KL-20210211-11-R13rd Party Services2767.822767.82 | KABI LAKE FOREST PRODUCTS LTD5867KL-20210211-11-R13rd Party Services2767.822767.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2767.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5867 | KL-20210211-11-R1 | 53511104 | Access | 0 | 3rd Party Services | 1 | 2248.23 | Each |  |  |  |  | 2248.23 | 292.2699 | 2540.4999 | 2021-02-11 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Walk to structure F147, open parking spaces CE-122 / Haul Gravel - CE-120 | 11 | F135-F149 | Dore Lake Road | 0 | 44244 |  | 56 | 44249 | CE-20210211-3 | Hauled Gravel to Dore Lake Road km 6 - CE-120 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5867KL-20210211-11-R13rd Party Services2248.232248.23 | KABI LAKE FOREST PRODUCTS LTD5867KL-20210211-11-R13rd Party Services2248.232248.23OEWT-PA14-Lem-R1 |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 2248.23 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5869 | KL-20210211-13 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 2303.55 | Each |  |  |  |  | 2303.55 | 299.4615 | 2603.0115 | 2021-02-11 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Support shovel for Hammer - CE-121 | 11 | F135-F149 | Dore Lake Road | 0 | 44244 |  | 56 | 44249 | CE-20210211-2 | Support shovel for Hammer - CE-121 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5869KL-20210211-133rd Party Services2303.552303.55 | KABI LAKE FOREST PRODUCTS LTD5869KL-20210211-133rd Party Services2303.552303.55OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 1151.775 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5874 | KL-20210212-5 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2198 | Each |  |  |  |  | 2198 | 285.74 | 2483.74 | 2021-02-12 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load 4 loads screen sand from Provost pit #5/ sand hills and corners to 17km on Hensen Road. Grader work form Hwy 17 to 17Km, loader open road to F110 to F112. | 11 | F119-F134 | Hensen Road | 0 | 44244 |  | 15 | 44254 | SSF-20210212-1 | Grader Scarifying hills and corners on Hensen Road from Hwy 17 to km 17 - SSF-14214 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5874KL-20210212-53rd Party Services21982198 | KABI LAKE FOREST PRODUCTS LTD5874KL-20210212-53rd Party Services21982198OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2198 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5874 | KL-20210212-5 | 53511111 | Access | 0 | 3rd Party Services | 1 | 175.18 | Each |  |  |  |  | 175.18 | 22.7734 | 197.9534 | 2021-02-12 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load 4 loads screen sand from Provost pit #5/ sand hills and corners to 17km on Hensen Road. Grader work form Hwy 17 to 17Km, loader open road to F110 to F112. | 11 | F119-F134 | Hensen Road | 0 | 44244 |  | 15 | 44254 | CR-20210212-1 | Loader opened up road for hand fallers F110 to F112 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5874KL-20210212-53rd Party Services175.18175.18 | KABI LAKE FOREST PRODUCTS LTD5874KL-20210212-53rd Party Services175.18175.18OEWT-PA14-Lem-R1 | [5 empty] | 1 | 175.18 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5876 | KL-20210212-7 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1739.73 | Each |  |  |  |  | 1739.73 | 226.1649 | 1965.8949 | 2021-02-12 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer trimming and maintaining roadway km 17 to km 18.5 Hensen West. Installed overhead power signs on Hensen West 8km to 11km | 11 | F119-F134 | Hensen Road | 0 | 44244 |  | 15 | 44254 | CR-20210212-4 | Dozer trimmimg and maintaining roadway km 17 to km 18.5 Hensen West - CR-101333 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5876KL-20210212-73rd Party Services1739.731739.73 | KABI LAKE FOREST PRODUCTS LTD5876KL-20210212-73rd Party Services1739.731739.73OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1739.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5878 | KL-20210212-9 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2639.82 | Each |  |  |  |  | 2639.82 | 343.1766 | 2982.9966 | 2021-02-12 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Walked 225 Excavator - fixed road, look for material to structure 143 - CE123 | 11 | F135-F149 | Dore Lake Road | 0 | 44244 |  | 14 | 44250 | CE-20210212-1 | Walked 225 Excavator - fixed road, look for material to structure 143 - CE123 |  |  |  | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD5878KL-20210212-93rd Party Services2639.822639.82 | KABI LAKE FOREST PRODUCTS LTD5878KL-20210212-93rd Party Services2639.822639.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2639.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5879 | KL-20210212-10 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1405.27 | Each |  |  |  |  | 1405.27 | 182.6851 | 1587.9551 | 2021-02-12 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer doing snow removal and pull offs on Dore Lake Road F145 to F135 | 11 | F135-F149 | Dore Lake Road | 0 | 44244 |  | 14 | 44250 | SSF-20210212-2 | Dozer doing snow removal and pull offs on Dore Lake Road F145 to F135 |  |  |  | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD5879KL-20210212-103rd Party Services1405.271405.27 | KABI LAKE FOREST PRODUCTS LTD5879KL-20210212-103rd Party Services1405.271405.27OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1405.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5886 | KL-20210213-5 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1739.73 | Each |  |  |  |  | 1739.73 | 226.1649 | 1965.8949 | 2021-02-13 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer timming and maintaining roadway km 16 to 18 Hensen Road. Loader plowed out F112 to F114, also sanded km 4 hill Hensen West | 11 | F119-F134 | Hensen Road | 0 | 44245 |  | 15 | 44254 | CR-20210213-1 | Dozer timming and maintaining roadway km 16 to 18 Hensen Road - CR-101337 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5886KL-20210213-53rd Party Services1739.731739.73 | KABI LAKE FOREST PRODUCTS LTD5886KL-20210213-53rd Party Services1739.731739.73OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1739.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5886 | KL-20210213-5 | 53511111 | Access | 0 | 3rd Party Services | 1 | 755.23 | Each |  |  |  |  | 755.23 | 98.1799 | 853.4099 | 2021-02-13 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer timming and maintaining roadway km 16 to 18 Hensen Road. Loader plowed out F112 to F114, also sanded km 4 hill Hensen West | 11 | F119-F134 | Hensen Road | 0 | 44245 |  | 15 | 44254 | CR-20210213-2 | Loader plowed out F112 to F114, also sanded km 4 hill Hensen West - CR-101336 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5886KL-20210213-53rd Party Services755.23755.23 | KABI LAKE FOREST PRODUCTS LTD5886KL-20210213-53rd Party Services755.23755.23OEWT-PA14-Lem-R1 | [5 empty] | 1 | 755.23 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5890 | KL-20210213-9 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 6842 | Each |  |  |  |  | 6842 | 889.46 | 7731.46 | 2021-02-13 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hammer and support shovel, Hammer road to widen, small tools to keep hoses tight on hammer - CE-124 | 11 | F135-F149 | Dore Lake Road | 0 | 44245 |  | 14 | 44250 | CE-20210213-1 | Hammer and support shovel, Hammer road to widen, small tools to keep hoses tight on hammer - CE-124 |  |  |  | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD5890KL-20210213-93rd Party Services68426842 | KABI LAKE FOREST PRODUCTS LTD5890KL-20210213-93rd Party Services68426842OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 3421 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5900 | KL-20210214-4 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-02-14 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal Hensen Road Hwy 17 to km 17 - SSF-14217 / loader and dozer clearing snow and sanding hills Hensen Road west 0km to km18 - CR-101339 | 11 | F119-F134 | Hensen Road | 0 | 44245 |  | 15 | 44254 | SSF-20210214-1 | Grader doing snow removal on Hensen Road Hwy 17 to km 17 - SSF-14217 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5900KL-20210214-43rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD5900KL-20210214-43rd Party Services2321.822321.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5900 | KL-20210214-4 | 53511111 | Access | 0 | 3rd Party Services | 1 | 3665.05 | Each |  |  |  |  | 3665.05 | 476.4565 | 4141.5065 | 2021-02-14 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal Hensen Road Hwy 17 to km 17 - SSF-14217 / loader and dozer clearing snow and sanding hills Hensen Road west 0km to km18 - CR-101339 | 11 | F119-F134 | Hensen Road | 0 | 44245 |  | 15 | 44254 | CR-20210214-1 | Loader and dozer clearing snow and sanding hills on Hensen Road west 0km to km18 - CR-101339 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5900KL-20210214-43rd Party Services3665.053665.05 | KABI LAKE FOREST PRODUCTS LTD5900KL-20210214-43rd Party Services3665.053665.05OEWT-PA14-Lem-R1 | [5 empty] | 1 | 3665.05 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5902 | KL-20210214-6 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 6951 | Each |  |  |  |  | 6951 | 903.63 | 7854.63 | 2021-02-14 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hammer and support excavator, widening road, small tools keep hoses tight on hammer - CE-125 | 11 | F135-F149 | Dore Lake Road | 0 | 44245 |  | 14 | 44253 | CE-20210214-1 | Hammer and support excavator, widening road, small tools keep hoses tight on hammer - CE-125 |  |  |  | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD5902KL-20210214-63rd Party Services69516951 | KABI LAKE FOREST PRODUCTS LTD5902KL-20210214-63rd Party Services69516951OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 3475.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5911 | KL-20210215-6 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1847 | Each |  |  |  |  | 1847 | 240.11 | 2087.11 | 2021-02-15 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourers clean out culvert km 4 on Hensen Road - CR-101342 / loader and Dozer cleaning snow,sanding hills Hensen West Km 0 to18, rock truck hauling sand - CR-101341 | 11 | F119-F134 | Hensen Road | 0 | 44249 |  | 15 | 44254 | CR-20210215-1 | Labourers clear ice from culvert near km 4 on Hensen Road - CR-101342 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5911KL-20210215-63rd Party Services18471847 | KABI LAKE FOREST PRODUCTS LTD5911KL-20210215-63rd Party Services18471847OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1847 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5911 | KL-20210215-6 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2927.37 | Each |  |  |  |  | 2927.37 | 380.5581 | 3307.9281 | 2021-02-15 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourers clean out culvert km 4 on Hensen Road - CR-101342 / loader and Dozer cleaning snow,sanding hills Hensen West Km 0 to18, rock truck hauling sand - CR-101341 | 11 | F119-F134 | Hensen Road | 0 | 44249 |  | 15 | 44254 | CR-20210215-2 | Loader and Dozer cleaning snow and sanding all hills on Hensen Road West Km 0 to Km 18, rock truck hauling sand - CR-101341 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5911KL-20210215-63rd Party Services2927.372927.37 | KABI LAKE FOREST PRODUCTS LTD5911KL-20210215-63rd Party Services2927.372927.37OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2927.37 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5912 | KL-20210215-7 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 5981.86 | Each |  |  |  |  | 5981.86 | 777.6418 | 6759.5018 | 2021-02-15 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hammer and Excavator support on Dore Lake Road widening road, Fixing up, small tools to keep hoses on hammer tight - CE-126 | 11 | F135-F149 | Dore Lake Road | 0 | 44249 |  | 14 | 44250 | CE-20210215-1 | Hammer and Excavator support on Dore Lake Road widening road, Fixing up, small tools to keep hoses on hammer tight - CE-126 |  |  |  | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD5912KL-20210215-73rd Party Services5981.865981.86 | KABI LAKE FOREST PRODUCTS LTD5912KL-20210215-73rd Party Services5981.865981.86OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 2990.93 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5913 | KL-20210215-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1269.91 | Each |  |  |  |  | 1269.91 | 165.0883 | 1434.9983 | 2021-02-15 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal on High Falls Roads - SSF-14220 | 11 | F203-F211 | High Falls Road- 9 | 0 | 44249 |  | 14 | 44250 | SSF-20210215-1 | Grader doing snow removal on High Falls Roads - SSF-14220 |  |  |  | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD5913KL-20210215-83rd Party Services1269.911269.91 | KABI LAKE FOREST PRODUCTS LTD5913KL-20210215-83rd Party Services1269.911269.91OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1269.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5916 | KL-20210215-11 | 53511111 | Access | 0 | 3rd Party Services | 1 | 849.73 | Each |  |  |  |  | 849.73 | 110.4649 | 960.1949 | 2021-02-15 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat D5K Dozer to F169 for snow removal. Dozer remove snow from F169 to F165. | 11 | F165-F169 | Magpie Hills Road | 0 | 44249 |  | 14 | 44250 | SSF-20210215-4 | Dozer doing snow removal from F169 to F165 - SSF-14221 |  |  |  | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD5916KL-20210215-113rd Party Services849.73849.73 | KABI LAKE FOREST PRODUCTS LTD5916KL-20210215-113rd Party Services849.73849.73OEWT-PA14-Lem-R1 | [5 empty] | 1 | 849.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5926 | KL-20210216-7 | 53511111 | Access | 0 | 3rd Party Services | 1 | 884 | Each |  |  |  |  | 884 | 114.92 | 998.92 | 2021-02-16 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer thawing ice from culvert near km 4 on Hensen Road - CR-101344 / Grader Scarifying Hensen Road to Km4 - SSF-14222 | 11 | F119-F134 | Hensen Road | 0 | 44249 |  | 15 | 44254 | CR-20210216-3 | Labourer thawing ice from culvert near km 4 on Hensen Road - CR-101344 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5926KL-20210216-73rd Party Services884884 | KABI LAKE FOREST PRODUCTS LTD5926KL-20210216-73rd Party Services884884OEWT-PA14-Lem-R1 | [5 empty] | 1 | 884 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5926 | KL-20210216-7 | 53511111 | Access | 0 | 3rd Party Services | 1 | 928.73 | Each |  |  |  |  | 928.73 | 120.7349 | 1049.4649 | 2021-02-16 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer thawing ice from culvert near km 4 on Hensen Road - CR-101344 / Grader Scarifying Hensen Road to Km4 - SSF-14222 | 11 | F119-F134 | Hensen Road | 0 | 44249 |  | 15 | 44254 | SSF-20210216-1 | Grader Scarifying Hensen Road th Km4 - SSF-14222 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5926KL-20210216-73rd Party Services928.73928.73 | KABI LAKE FOREST PRODUCTS LTD5926KL-20210216-73rd Party Services928.73928.73OEWT-PA14-Lem-R1 | [5 empty] | 1 | 928.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5927 | KL-20210216-8 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 2924 | Each |  |  |  |  | 2924 | 380.12 | 3304.12 | 2021-02-16 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Support Hammer and widen road on Dore Lake Road - CE-128 / Used Hammer on Dore Lake Road - CE-127 | 11 | F119-F134 | Hensen Road | 0 | 44249 |  | 15 | 44254 | CE-20210216-1 | Support Hammer and widen road on Dore Lake Road - CE-128 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5927KL-20210216-83rd Party Services29242924 | KABI LAKE FOREST PRODUCTS LTD5927KL-20210216-83rd Party Services29242924OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 1462 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5927 | KL-20210216-8 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 4068 | Each |  |  |  |  | 4068 | 528.84 | 4596.84 | 2021-02-16 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Support Hammer and widen road on Dore Lake Road - CE-128 / Used Hammer on Dore Lake Road - CE-127 | 11 | F119-F134 | Hensen Road | 0 | 44249 |  | 15 | 44254 | CE-20210216-2 | Used Hammer on Dore Lake Road - CE-127 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5927KL-20210216-83rd Party Services40684068 | KABI LAKE FOREST PRODUCTS LTD5927KL-20210216-83rd Party Services40684068OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 2034 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5929 | KL-20210216-10 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2430.82 | Each |  |  |  |  | 2430.82 | 316.0066 | 2746.8266 | 2021-02-16 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal to Anjigami Bridge - SSF-14223 | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44249 |  | 15 | 44254 | SSF-20210216-2 | Grader doing snow removal to Anjigami Bridge - SSF-14223 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5929KL-20210216-103rd Party Services2430.822430.82 | KABI LAKE FOREST PRODUCTS LTD5929KL-20210216-103rd Party Services2430.822430.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2430.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5942 | KL-20210217-6 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 2924 | Each |  |  |  |  | 2924 | 380.12 | 3304.12 | 2021-02-17 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hammer corners, excavator support hammer and fill in holes. | 11 | F135-F149 | Dore Lake Road | 0 | 44251 |  | 15 | 44254 | CE-20210217-1 | Widen corners, filled holes in road. (Support) CE-129 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5942KL-20210217-63rd Party Services29242924 | KABI LAKE FOREST PRODUCTS LTD5942KL-20210217-63rd Party Services29242924OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 1462 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5942 | KL-20210217-6 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 4068 | Each |  |  |  |  | 4068 | 528.84 | 4596.84 | 2021-02-17 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hammer corners, excavator support hammer and fill in holes. | 11 | F135-F149 | Dore Lake Road | 0 | 44251 |  | 15 | 44254 | CE-20210217-2 | Hammer corners, filled holes in road. CE-130 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5942KL-20210217-63rd Party Services40684068 | KABI LAKE FOREST PRODUCTS LTD5942KL-20210217-63rd Party Services40684068OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 2034 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5944 | KL-20210217-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1590.45 | Each |  |  |  |  | 1590.45 | 206.7585 | 1797.2085 | 2021-02-17 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer doing snow removal from F185 to F190 SSF-14225 | 11 | F185-F193 | High Falls Road- 5 | 0 | 44251 |  | 15 | 44254 | SSF-20210217-1 | Dozer doing snow removal from F185 to F190 SSF-14225 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5944KL-20210217-83rd Party Services1590.451590.45 | KABI LAKE FOREST PRODUCTS LTD5944KL-20210217-83rd Party Services1590.451590.45OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1590.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5945 | KL-20210217-9 | 53511111 | Access | 0 | 3rd Party Services | 1 | 649 | Each |  |  |  |  | 649 | 84.37 | 733.37 | 2021-02-17 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Steam Pipe at km 3.5 on Hensen Rd | 11 | F119-F134 | Hensen Road | 0 | 44251 |  | 15 | 44254 | CR-20210217-1 | Labourer throwing ice from culvert near km 4 on Hensen Rd CR-101348 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5945KL-20210217-93rd Party Services649649 | KABI LAKE FOREST PRODUCTS LTD5945KL-20210217-93rd Party Services649649OEWT-PA14-Lem-R1 | [5 empty] | 1 | 649 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5948 | KL-20210217-12 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-02-17 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying Hensen Rd to km 17 SSF-14224 | 11 | F119-F134 | Hensen Road | 0 | 44251 |  | 15 | 44254 | SSF-20210217-2 | Grader scarifying Hensen Rd to km 17 SSF-14224 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5948KL-20210217-123rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD5948KL-20210217-123rd Party Services2321.822321.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5951 | KL-20210218-2 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 6983 | Each |  |  |  |  | 6983 | 907.79 | 7890.79 | 2021-02-18 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Worked on Dore Lake Rd with Hammer & support excavator to widen roads. Small tools to keep fittings tight to prevent leaks. CE-131 | 11 | F135-F149 | Dore Lake Road | 0 | 44252 |  | 15 | 44254 | CE-20210218-1 | Worked on Dore Lake Rd with Hammer & support excavator to widen roads. Small tools to keep fittings tight to prevent leaks. CE-131 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5951KL-20210218-23rd Party Services69836983 | KABI LAKE FOREST PRODUCTS LTD5951KL-20210218-23rd Party Services69836983OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 3491.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5953 | KL-20210218-4 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1269.91 | Each |  |  |  |  | 1269.91 | 165.0883 | 1434.9983 | 2021-02-18 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Install Km markers on Hensen West. Grader scarifying hills & corners on Hensen Rd to km 17. | 11 | F119-F134 | Hensen Road | 0 | 44252 |  | 15 | 44254 | SSF-20210218-1 | Grader scarifying hills & corners on Hensen Rd to km 17. SSF-14228 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5953KL-20210218-43rd Party Services1269.911269.91 | KABI LAKE FOREST PRODUCTS LTD5953KL-20210218-43rd Party Services1269.911269.91OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1269.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5955 | KL-20210218-6 | 53511111 | Access | 0 | 3rd Party Services | 1 | 370.36 | Each |  |  |  |  | 370.36 | 48.1468 | 418.5068 | 2021-02-18 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer doing snow removal from F190 to F191 SSF-14227 | 11 | F185-F193 | High Falls Road- 5 | 0 | 44252 |  | 15 | 44254 | SSF-20210218-2 | Dozer doing snow removal from F190 to F191 SSF-14227 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5955KL-20210218-63rd Party Services370.36370.36 | KABI LAKE FOREST PRODUCTS LTD5955KL-20210218-63rd Party Services370.36370.36OEWT-PA14-Lem-R1 | [5 empty] | 1 | 370.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5966 | KL-20210219-4 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 6390.95 | Each |  |  |  |  | 6390.95 | 830.8235 | 7221.7735 | 2021-02-19 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hammer & shovel--widen road on Dore Lake Rd. Support shovel to Hammer. CE-132 | 11 | F135-F149 | Dore Lake Road | 0 | 44252 |  | 15 | 44254 | CE-20210219-1 | Hammer & shovel--widen road on Dore Lake Rd. Support shovel to Hammer. CE-132 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5966KL-20210219-43rd Party Services6390.956390.95 | KABI LAKE FOREST PRODUCTS LTD5966KL-20210219-43rd Party Services6390.956390.95OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 3195.475 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5968 | KL-20210219-5 | 53511111 | Access | 0 | 3rd Party Services | 1 | 4757 | Each |  |  |  |  | 4757 | 618.41 | 5375.41 | 2021-02-19 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Installing km markers, power line above signs on Hensen West. Loader and dozer clear snow from 0 to 19Km. Grader do snow removal from Hwy 17 to 17Km | 11 | F119-F134 | Hensen Road | 0 | 44252 |  | 15 | 44254 | CR-20210219-2 | Loader cleared snow from km 0 to km 9 on Hensen West. Dozer cleared km 9 to km 19, operators came in early. CR-101354 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5968KL-20210219-53rd Party Services47574757 | KABI LAKE FOREST PRODUCTS LTD5968KL-20210219-53rd Party Services47574757OEWT-PA14-Lem-R1 | [5 empty] | 1 | 4757 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5968 | KL-20210219-5 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2539.82 | Each |  |  |  |  | 2539.82 | 330.1766 | 2869.9966 | 2021-02-19 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Installing km markers, power line above signs on Hensen West. Loader and dozer clear snow from 0 to 19Km. Grader do snow removal from Hwy 17 to 17Km | 11 | F119-F134 | Hensen Road | 0 | 44252 |  | 15 | 44254 | SSF-20210219-1 | Grader doing snow removal from Hwy 17 to km 17 on Hensen Rd. SSF-14229 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5968KL-20210219-53rd Party Services2539.822539.82 | KABI LAKE FOREST PRODUCTS LTD5968KL-20210219-53rd Party Services2539.822539.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2539.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5969 | KL-20210219-6 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2069.82 | Each |  |  |  |  | 2069.82 | 269.0766 | 2338.8966 | 2021-02-19 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer doing snow removal from F185 to F193 SSF-14230 | 11 | F185-F193 | High Falls Road- 5 | 0 | 44252 |  | 15 | 44254 | SSF-20210219-2 | Dozer doing snow removal from F185 to F193 SSF-14230 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5969KL-20210219-63rd Party Services2069.822069.82 | KABI LAKE FOREST PRODUCTS LTD5969KL-20210219-63rd Party Services2069.822069.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2069.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5970 | KL-20210219-7 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2539.82 | Each |  |  |  |  | 2539.82 | 330.1766 | 2869.9966 | 2021-02-19 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal to Anjigami Bridge & pull offs. SSF-14231 | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44252 |  | 15 | 44254 | SSF-20210219-3 | Grader doing snow removal to Anjigami Bridge & pull offs. SSF-14231 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5970KL-20210219-73rd Party Services2539.822539.82 | KABI LAKE FOREST PRODUCTS LTD5970KL-20210219-73rd Party Services2539.822539.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2539.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5977 | KL-20210220-4 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2736.95 | Each |  |  |  |  | 2736.95 | 355.8035 | 3092.7535 | 2021-02-20 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader, plow and loader clearing snow from Hensen road 0km to 17km, and Hensen West. | 11 | F119-F134 | Hensen Road | 0 | 44252 |  | 15 | 44254 | CR-20210220-1 | D5 & 950 cleared snow on Hensen West from km 0 to km 20, operators came in early. CR-101355 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5977KL-20210220-43rd Party Services2736.952736.95 | KABI LAKE FOREST PRODUCTS LTD5977KL-20210220-43rd Party Services2736.952736.95OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2736.95 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5977 | KL-20210220-4 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2165.32 | Each |  |  |  |  | 2165.32 | 281.4916 | 2446.8116 | 2021-02-20 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader, plow and loader clearing snow from Hensen road 0km to 17km, and Hensen West. | 11 | F119-F134 | Hensen Road | 0 | 44252 |  | 15 | 44254 | CR-20210220-2 | Night shift---950 loader opened up Hensen West from km 0 to km 18 CR-101357 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5977KL-20210220-43rd Party Services2165.322165.32 | KABI LAKE FOREST PRODUCTS LTD5977KL-20210220-43rd Party Services2165.322165.32OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2165.32 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5977 | KL-20210220-4 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-02-20 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader, plow and loader clearing snow from Hensen road 0km to 17km, and Hensen West. | 11 | F119-F134 | Hensen Road | 0 | 44252 |  | 15 | 44254 | SSF-20210220-1 | Grader doing snow removal from Hwy 17 to km 17 on Hensen Rd. SSF-14233 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5977KL-20210220-43rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD5977KL-20210220-43rd Party Services2321.822321.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5984 | KL-20210221-3 | 53511111 | Access | 0 | 3rd Party Services | 1 | 350.36 | Each |  |  |  |  | 350.36 | 45.5468 | 395.9068 | 2021-02-21 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Night Shift, 950 loader plowed snow into F111, grader plow to 17km. . D5 trimming roads km 18 to km 20. Labourer fixed all signs up Hensen West from km 5 to km 19 | 11 | F119-F134 | Hensen Road | 0 | 44252 |  | 15 | 44254 | CR-20210221-1 | Night Shift, 950 loader plowed snow into F111 CR-101358 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5984KL-20210221-33rd Party Services350.36350.36 | KABI LAKE FOREST PRODUCTS LTD5984KL-20210221-33rd Party Services350.36350.36OEWT-PA14-Lem-R1 | [5 empty] | 1 | 350.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5984 | KL-20210221-3 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1830.14 | Each |  |  |  |  | 1830.14 | 237.9182 | 2068.0582 | 2021-02-21 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Night Shift, 950 loader plowed snow into F111, grader plow to 17km. . D5 trimming roads km 18 to km 20. Labourer fixed all signs up Hensen West from km 5 to km 19 | 11 | F119-F134 | Hensen Road | 0 | 44252 |  | 15 | 44254 | CR-20210221-2 | D5 trimming roads km 18 to km 20 Hensen West. CR-101359 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5984KL-20210221-33rd Party Services1830.141830.14 | KABI LAKE FOREST PRODUCTS LTD5984KL-20210221-33rd Party Services1830.141830.14OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1830.14 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5984 | KL-20210221-3 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2747 | Each |  |  |  |  | 2747 | 357.11 | 3104.11 | 2021-02-21 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Night Shift, 950 loader plowed snow into F111, grader plow to 17km. . D5 trimming roads km 18 to km 20. Labourer fixed all signs up Hensen West from km 5 to km 19 | 11 | F119-F134 | Hensen Road | 0 | 44252 |  | 15 | 44254 | SSF-20210221-1 | Grader doing snow removal from Hwy 17 to km 17 on Hensen Rd/Assist float hauling Pile Driver. SSF-14235 |  |  |  | Martin Hunt | 11 | KABI LAKE FOREST PRODUCTS LTD5984KL-20210221-33rd Party Services27472747 | KABI LAKE FOREST PRODUCTS LTD5984KL-20210221-33rd Party Services27472747OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2747 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5991 | KL-20210221-9 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 4225.5 | Each |  |  |  |  | 4225.5 | 549.315 | 4774.815 | 2021-02-21 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Worked on Dore Lake Rd at km 6.5, structures F135 F149 CE-134 hammering | 11 | F135-F149 | Dore Lake Road | 0 | 44252 |  | 56 | 44253 | CE-20210221-1 | Hammer worked on Dore Lake Rd at km 6.5, structures F135 F149 CE-134 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5991KL-20210221-93rd Party Services4225.54225.5 | KABI LAKE FOREST PRODUCTS LTD5991KL-20210221-93rd Party Services4225.54225.5OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 2112.75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5999 | KL-20210222-5 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 2282.09 | Each |  |  |  |  | 2282.09 | 296.6717 | 2578.7617 | 2021-02-22 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Break Road (rock bed) at km 6 and km 6.5 on Dore Lake Rd. F135-F149 Access CE-135 Excavator fix roads and support hammer. | 11 | F135-F149 | Dore Lake Road | 0 | 44254 |  | 56 | 44254 | CE-20210222-1 | Break Road (rock bed) at km 6 on Dore Lake Rd. F135-F149 Access CE-135 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5999KL-20210222-53rd Party Services2282.092282.09 | KABI LAKE FOREST PRODUCTS LTD5999KL-20210222-53rd Party Services2282.092282.09OEWT PA15-LEM | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 1141.045 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5999 | KL-20210222-5 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 2282.09 | Each |  |  |  |  | 2282.09 | 296.6717 | 2578.7617 | 2021-02-22 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Break Road (rock bed) at km 6 and km 6.5 on Dore Lake Rd. F135-F149 Access CE-135 Excavator fix roads and support hammer. | 11 | F135-F149 | Dore Lake Road | 0 | 44254 |  | 56 | 44254 | CE-20210222-2 | Hammer work on Dore Lake Rd km 6.5 Access F135 to F149 CE-136 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5999KL-20210222-53rd Party Services2282.092282.09 | KABI LAKE FOREST PRODUCTS LTD5999KL-20210222-53rd Party Services2282.092282.09OEWT PA15-LEM | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 1141.045 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5999 | KL-20210222-5 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 2807.41 | Each |  |  |  |  | 2807.41 | 364.9633 | 3172.3733 | 2021-02-22 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Break Road (rock bed) at km 6 and km 6.5 on Dore Lake Rd. F135-F149 Access CE-135 Excavator fix roads and support hammer. | 11 | F135-F149 | Dore Lake Road | 0 | 44254 |  | 56 | 44254 | CE-20210222-3 | Fixed roads, assisted hammer on Dore Lake Rd @ km 6.5 Access F135-F149 CE-138 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5999KL-20210222-53rd Party Services2807.412807.41 | KABI LAKE FOREST PRODUCTS LTD5999KL-20210222-53rd Party Services2807.412807.41OEWT PA15-LEM | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 1403.705 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6002 | KL-20210222-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1077.73 | Each |  |  |  |  | 1077.73 | 140.1049 | 1217.8349 | 2021-02-22 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 330F excavator back for road building of F227 to F212. Grader doing snow removal to Anjigami Bridge & pull offs/Crane Support | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44254 |  | 56 | 44254 | SSF-20210222-1 | Excavator sanding hills on Access to WC 12970 for Crane. SSF-14236 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6002KL-20210222-83rd Party Services1077.731077.73 | KABI LAKE FOREST PRODUCTS LTD6002KL-20210222-83rd Party Services1077.731077.73OEWT PA15-LEM | [5 empty] | 1 | 1077.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6002 | KL-20210222-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2539.82 | Each |  |  |  |  | 2539.82 | 330.1766 | 2869.9966 | 2021-02-22 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat 330F excavator back for road building of F227 to F212. Grader doing snow removal to Anjigami Bridge & pull offs/Crane Support | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44254 |  | 56 | 44254 | SSF-20210222-2 | Grader doing snow removal to Anjigami Bridge & pull offs/Crane Support SSF-14238 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6002KL-20210222-83rd Party Services2539.822539.82 | KABI LAKE FOREST PRODUCTS LTD6002KL-20210222-83rd Party Services2539.822539.82OEWT PA15-LEM | [5 empty] | 1 | 2539.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6004 | KL-20210222-10 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2165.32 | Each |  |  |  |  | 2165.32 | 281.4916 | 2446.8116 | 2021-02-22 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Night shift, 950 loader cleared road km 0 to km 17 on Hensen West. Grader doing snow removal from Hwy 17 to km 17 on Hensen Rd | 11 | F119-F134 | Hensen Road | 0 | 44254 |  | 56 | 44254 | CR-20210222-1 | Night shift, 950 loader cleared road km 0 to km 17 on Hensen West. CR-101363 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6004KL-20210222-103rd Party Services2165.322165.32 | KABI LAKE FOREST PRODUCTS LTD6004KL-20210222-103rd Party Services2165.322165.32OEWT PA15-LEM | [5 empty] | 1 | 2165.32 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6004 | KL-20210222-10 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2430.82 | Each |  |  |  |  | 2430.82 | 316.0066 | 2746.8266 | 2021-02-22 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Night shift, 950 loader cleared road km 0 to km 17 on Hensen West. Grader doing snow removal from Hwy 17 to km 17 on Hensen Rd | 11 | F119-F134 | Hensen Road | 0 | 44254 |  | 56 | 44254 | SSF-20210222-3 | Grader doing snow removal from Hwy 17 to km 17 on Hensen Rd SSF-14239 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6004KL-20210222-103rd Party Services2430.822430.82 | KABI LAKE FOREST PRODUCTS LTD6004KL-20210222-103rd Party Services2430.822430.82OEWT PA15-LEM | [5 empty] | 1 | 2430.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6012 | KL-20210223-5 | 53511111 | Access | 0 | 3rd Party Services | 1 | 4235.09 | Each |  |  |  |  | 4235.09 | 550.5617 | 4785.6517 | 2021-02-23 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start Brushing AE1 Access for F228 Clearing. Grader doing snow removal & support for Gravel haul/Excavator sanding hills on Access to WC 12970 for Gravel haul. | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44253 |  | 56 | 44257 | SSF-20210223-2 | Grader doing snow removal & support for Gravel haul/Excavator sanding hills on Access to WC 12970 for Gravel haul. SSF-14242 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6012KL-20210223-53rd Party Services4235.094235.09 | KABI LAKE FOREST PRODUCTS LTD6012KL-20210223-53rd Party Services4235.094235.09OEWT-PA14-Lem-R1 | [5 empty] | 1 | 4235.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6013 | KL-20210223-6 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 4383 | Each |  |  |  |  | 4383 | 569.79 | 4952.79 | 2021-02-23 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Breaker working on Dore Lake Rd F135-F145, F145-F149, and @km 6.5 | 11 | F135-F149 | Dore Lake Road | 0 | 44253 |  | 56 | 44257 | CE-20210223-1 | Break Bedrock on Dore Lake Rd @ km 6.5--Access F135-F149 CE-140 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6013KL-20210223-63rd Party Services43834383 | KABI LAKE FOREST PRODUCTS LTD6013KL-20210223-63rd Party Services43834383OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 2191.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6013 | KL-20210223-6 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 2644.27 | Each |  |  |  |  | 2644.27 | 343.7551 | 2988.0251 | 2021-02-23 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Breaker working on Dore Lake Rd F135-F145, F145-F149, and @km 6.5 | 11 | F135-F149 | Dore Lake Road | 0 | 44253 |  | 56 | 44257 | CE-20210223-2 | Breaker working on Dore Lake Rd F135-F145 @km 6.5 CE-141 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6013KL-20210223-63rd Party Services2644.272644.27 | KABI LAKE FOREST PRODUCTS LTD6013KL-20210223-63rd Party Services2644.272644.27OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 1322.135 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6015 | KL-20210223-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 855.23 | Each |  |  |  |  | 855.23 | 111.1799 | 966.4099 | 2021-02-23 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Night Shift, 950 cleaned up and pushed banks back from km 4 to km 5 on Hensen West. Dozer trimmed up road and patched up road from km 18 to km 20 on Hensen West. Grader doing snow removal from Hwy 17 to km 17 on Hensen Rd. | 11 | F119-F134 | Hensen Road | 0 | 44253 |  | 56 | 44257 | CR-20210223-1 | Night Shift, 950 cleaned up and pushed banks back from km 4 to km 5 on Hensen West. CR-101366 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6015KL-20210223-83rd Party Services855.23855.23 | KABI LAKE FOREST PRODUCTS LTD6015KL-20210223-83rd Party Services855.23855.23OEWT-PA14-Lem-R1 | [5 empty] | 1 | 855.23 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6015 | KL-20210223-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1884.64 | Each |  |  |  |  | 1884.64 | 245.0032 | 2129.6432 | 2021-02-23 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Night Shift, 950 cleaned up and pushed banks back from km 4 to km 5 on Hensen West. Dozer trimmed up road and patched up road from km 18 to km 20 on Hensen West. Grader doing snow removal from Hwy 17 to km 17 on Hensen Rd. | 11 | F119-F134 | Hensen Road | 0 | 44253 |  | 56 | 44257 | CR-20210223-2 | Dozer trimmed up road and patched up road from km 18 to km 20 on Hensen West. CR-101367 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6015KL-20210223-83rd Party Services1884.641884.64 | KABI LAKE FOREST PRODUCTS LTD6015KL-20210223-83rd Party Services1884.641884.64OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1884.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6015 | KL-20210223-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2430.82 | Each |  |  |  |  | 2430.82 | 316.0066 | 2746.8266 | 2021-02-23 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Night Shift, 950 cleaned up and pushed banks back from km 4 to km 5 on Hensen West. Dozer trimmed up road and patched up road from km 18 to km 20 on Hensen West. Grader doing snow removal from Hwy 17 to km 17 on Hensen Rd. | 11 | F119-F134 | Hensen Road | 0 | 44253 |  | 56 | 44257 | SSF-20210223-3 | Grader doing snow removal from Hwy 17 to km 17 on Hensen Rd. SSF-14243 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6015KL-20210223-83rd Party Services2430.822430.82 | KABI LAKE FOREST PRODUCTS LTD6015KL-20210223-83rd Party Services2430.822430.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2430.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6016 | KL-20210223-9 | 53511103 | Access | 0 | 3rd Party Services | 1 | 634 | Each |  |  |  |  | 634 | 82.42 | 716.42 | 2021-02-23 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer delivering geo to km 3.5 on Hensen Rd. SSF-14244. | 11 | F119-F134 | Hensen Road | 0 | 44253 |  | 56 | 44257 | SSF-20210223-4 | Labourer delivering geo to km 3.5 on Hensen Rd. SSF-14244 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6016KL-20210223-93rd Party Services634634 | KABI LAKE FOREST PRODUCTS LTD6016KL-20210223-93rd Party Services634634OEWT-PA14-Lem-R1 |  | WF11-Wetland Access Development | WF11-Wetland Access Development |  | 1 | 1 | 634 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6024 | KL-20210224-4 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1960.82 | Each |  |  |  |  | 1960.82 | 254.9066 | 2215.7266 | 2021-02-24 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on AE1 Access to F227. Dozer plowing snow on AE1 to F227 | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44256 |  | 56 | 44259 | SSF-20210224-2 | Dozer plowing snow on AE1 to F227 SSF-14246 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6024KL-20210224-43rd Party Services1960.821960.82 | KABI LAKE FOREST PRODUCTS LTD6024KL-20210224-43rd Party Services1960.821960.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1960.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6028 | KL-20210224-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1884.64 | Each |  |  |  |  | 1884.64 | 245.0032 | 2129.6432 | 2021-02-24 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer and grader plow snow. Labourers haul geo to F66, and fix signs from 9km - 20km on Hensen West. | 11 | F119-F134 | Hensen Road | 0 | 44256 |  | 56 | 44259 | CR-20210224-3 | Dozer clearing snow and trimming roads from km 14 to km 20 on Hensen Road West. CR-101370 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6028KL-20210224-83rd Party Services1884.641884.64 | KABI LAKE FOREST PRODUCTS LTD6028KL-20210224-83rd Party Services1884.641884.64OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1884.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6028 | KL-20210224-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2430.82 | Each |  |  |  |  | 2430.82 | 316.0066 | 2746.8266 | 2021-02-24 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer and grader plow snow. Labourers haul geo to F66, and fix signs from 9km - 20km on Hensen West. | 11 | F119-F134 | Hensen Road | 0 | 44256 |  | 56 | 44259 | SSF-20210224-3 | Grader doing snow removal from Hwy 17 to km 17 on Hensen Rd. SSF-14247 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6028KL-20210224-83rd Party Services2430.822430.82 | KABI LAKE FOREST PRODUCTS LTD6028KL-20210224-83rd Party Services2430.822430.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2430.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6029 | KL-20210224-9 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 4383 | Each |  |  |  |  | 4383 | 569.79 | 4952.79 | 2021-02-24 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Day shift and night shifting hammering and assisting in road repairs on Dore Lake Rd km 6 to km 8. F135-F149/Fix & patch road. | 11 | F135-F149 | Dore Lake Road | 0 | 44256 |  | 56 | 44259 | CE-20210224-1 | Night shift assisted in road repairs on Dore Lake Rd km 3 to km 9. CE-144 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6029KL-20210224-93rd Party Services43834383 | KABI LAKE FOREST PRODUCTS LTD6029KL-20210224-93rd Party Services43834383OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 2191.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6029 | KL-20210224-9 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 4492 | Each |  |  |  |  | 4492 | 583.96 | 5075.96 | 2021-02-24 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Day shift and night shifting hammering and assisting in road repairs on Dore Lake Rd km 6 to km 8. F135-F149/Fix & patch road. | 11 | F135-F149 | Dore Lake Road | 0 | 44256 |  | 56 | 44259 | CE-20210224-2 | Day shift assisted in road repairs on Dore Lake Rd km 6 to km 8. F135-F149/Fix & patch road. CE-143 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6029KL-20210224-93rd Party Services44924492 | KABI LAKE FOREST PRODUCTS LTD6029KL-20210224-93rd Party Services44924492OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 2246 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6035 | KL-20210225-3 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2182.59 | Each |  |  |  |  | 2182.59 | 283.7367 | 2466.3267 | 2021-02-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer & Loader pushing back banks and kept hills in safe driving conditions. Excavator & Dozer covered corduroy at F66 Wetland. | 11 | D009-D017 | Three Finger Lake | 0 | 44256 |  | 56 | 44262 | CR-20210225-2 | Dozer & Loader pushing back banks and kept hills in safe driving conditions. Operators came in early. CR-101379 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6035KL-20210225-33rd Party Services2182.592182.59 | KABI LAKE FOREST PRODUCTS LTD6035KL-20210225-33rd Party Services2182.592182.59OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2182.59 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6037 | KL-20210225-5 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 8766 | Each |  |  |  |  | 8766 | 1139.58 | 9905.58 | 2021-02-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Break bed rock on Dore Lake Rd @ km 7. Support for Hammer @ km 7 and patch roads. | 11 | F135-F149 | Dore Lake Road | 0 | 44256 |  | 56 | 44259 | CE-20210225-1 | Break bed rock on Dore Lake Rd @ km 7. CE-145 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6037KL-20210225-53rd Party Services87668766 | KABI LAKE FOREST PRODUCTS LTD6037KL-20210225-53rd Party Services87668766OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 4383 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6037 | KL-20210225-5 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 2994 | Each |  |  |  |  | 2994 | 389.22 | 3383.22 | 2021-02-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Break bed rock on Dore Lake Rd @ km 7. Support for Hammer @ km 7 and patch roads. | 11 | F135-F149 | Dore Lake Road | 0 | 44256 |  | 56 | 44259 | CE-20210225-2 | Support for Hammer @ km 7 and patch roads. CE-146 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6037KL-20210225-53rd Party Services29942994 | KABI LAKE FOREST PRODUCTS LTD6037KL-20210225-53rd Party Services29942994OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 1497 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6042 | KL-20210225-10 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1960.82 | Each |  |  |  |  | 1960.82 | 254.9066 | 2215.7266 | 2021-02-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continue on snow removal on AE1 to F212 SSF-14251 | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44256 |  | 56 | 44259 | SSF-20210225-2 | Dozer continue on snow removal on AE1 to F212 SSF-14251 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6042KL-20210225-103rd Party Services1960.821960.82 | KABI LAKE FOREST PRODUCTS LTD6042KL-20210225-103rd Party Services1960.821960.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1960.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6047 | KL-20210225-15 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-02-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal from Hwy 17 to km 17 on Hensen Rd. SSF-14252 | 11 | F119-F134 | Hensen Road | 0 | 44256 |  | 56 | 44259 | SSF-20210225-3 | Grader doing snow removal from Hwy 17 to km 17 on Hensen Rd. SSF-14252 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6047KL-20210225-153rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD6047KL-20210225-153rd Party Services2321.822321.82OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6044 | KL-20210225-12-R1 | 53511011 | Access | 0 | 3rd Party Services | 1 | 2642 | Each |  |  |  |  | 2642 | 343.46 | 2985.46 | 2021-02-25 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, load and haul gravel, move bridge, and sand road. WC 12000.00 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44256 |  | 56 | 44259 | JJR-20210225-1-R1 | Clear snow to KM 24 |  |  |  | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6044KL-20210225-12-R13rd Party Services26422642 | KABI LAKE FOREST PRODUCTS LTD6044KL-20210225-12-R13rd Party Services26422642OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2642 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6058 | KL-20210220-10 | 53551103 | Earthworks | 0 | 3rd Party Services | 1 | 4383 | Each |  |  |  |  | 4383 | 569.79 | 4952.79 | 2021-02-20 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Worked on Dore Lake Road @ km 6.5, Access F135 to F149 CE-133 hammering | 11 | F135-F149 | Dore Lake Road | 0 | 44253 |  | 56 | 44259 | CE-20210220-1 | Worked on Dore Lake Road @ km 6.5, Access F135 to F149 CE-133 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6058KL-20210220-103rd Party Services43834383 | KABI LAKE FOREST PRODUCTS LTD6058KL-20210220-103rd Party Services43834383OEWT-PA14-Lem-R1 | WF11-Blasting |  | WF11-Blasting | 0.5 |  | 0.5 | 2191.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6096 | KL-20210226-6 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1830.14 | Each |  |  |  |  | 1830.14 | 237.9182 | 2068.0582 | 2021-02-26 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Go down to Hensen Road and steamed pipe at Km 3.6 and install heat trace top | 11 | F119-F134 | Hensen Road | 0 | 44262 |  | 56 | 44265 | CR-20210226-5 | Clean snow off road - CR-101387 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6096KL-20210226-63rd Party Services1830.141830.14 | KABI LAKE FOREST PRODUCTS LTD6096KL-20210226-63rd Party Services1830.141830.14OEWT PA15-LEM | [5 empty] | 1 | 1830.14 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6096 | KL-20210226-6 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-02-26 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Go down to Hensen Road and steamed pipe at Km 3.6 and install heat trace top | 11 | F119-F134 | Hensen Road | 0 | 44262 |  | 56 | 44265 | SSF-20210226-1 | Grading road - SSF-14249 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6096KL-20210226-63rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD6096KL-20210226-63rd Party Services2321.822321.82OEWT PA15-LEM | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6099 | KL-20210226-9 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1481.45 | Each |  |  |  |  | 1481.45 | 192.5885 | 1674.0385 | 2021-02-26 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer continuing on snow removal on AE1 to F212 - SSF-14248 | 11 | F-212 to F-214 | Michipicoten Road- 1 | 0 | 44262 |  | 56 | 44265 | SSF-20210226-2 | Snow removal - SSF-14248 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6099KL-20210226-93rd Party Services1481.451481.45 | KABI LAKE FOREST PRODUCTS LTD6099KL-20210226-93rd Party Services1481.451481.45OEWT PA15-LEM | [5 empty] | 1 | 1481.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6106 | KL-20210227-4 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-02-27 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to Km 17 on Hensen Road - SSF-14255 / D5 trimming roadway from km 15 to km20 , 950 plowing and sanding hills km 1, to 12, - CR-101388 | 11 | F119-C134 | Hensen Road | 0 | 44262 |  | 56 | 44265 | SSF-20210227-1 | Grading Road - SSF-14255 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6106KL-20210227-43rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD6106KL-20210227-43rd Party Services2321.822321.82OEWT PA15-LEM | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6106 | KL-20210227-4 | 53511111 | Access | 0 | 3rd Party Services | 1 | 4153.14 | Each |  |  |  |  | 4153.14 | 539.9082 | 4693.0482 | 2021-02-27 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying from Hwy 17 to Km 17 on Hensen Road - SSF-14255 / D5 trimming roadway from km 15 to km20 , 950 plowing and sanding hills km 1, to 12, - CR-101388 | 11 | F119-C134 | Hensen Road | 0 | 44262 |  | 56 | 44265 | CR-20210227-1 | winter road work - CR-101388 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6106KL-20210227-43rd Party Services4153.144153.14 | KABI LAKE FOREST PRODUCTS LTD6106KL-20210227-43rd Party Services4153.144153.14OEWT PA15-LEM | [5 empty] | 1 | 4153.14 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6117 | KL-20210228-3 | 53511111 | Access | 0 | 3rd Party Services | 1 | 4531.14 | Each |  |  |  |  | 4531.14 | 589.0482 | 5120.1882 | 2021-02-28 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer clearing and trimming road to Km 20, loader plowing, sanding hills km 1 to km 15 - CR-101391 / Grader snow removal, scarifying Hensen Road - SSF-14254 | 11 | F119-F134 | Hensen Road | 0 | 44263 |  | 56 | 44265 | CR-2021228-1 | Winter road maintenance - CR-101391 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6117KL-20210228-33rd Party Services4531.144531.14 | KABI LAKE FOREST PRODUCTS LTD6117KL-20210228-33rd Party Services4531.144531.14OEWT PA15-LEM | [5 empty] | 1 | 4531.14 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6117 | KL-20210228-3 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-02-28 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer clearing and trimming road to Km 20, loader plowing, sanding hills km 1 to km 15 - CR-101391 / Grader snow removal, scarifying Hensen Road - SSF-14254 | 11 | F119-F134 | Hensen Road | 0 | 44263 |  | 56 | 44265 | SSF-20210228-1 | Winter road maintenance - SSF-14254 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6117KL-20210228-33rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD6117KL-20210228-33rd Party Services2321.822321.82OEWT PA15-LEM | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6118 | KL-20210228-4 | 53511111 | Access | 0 | 3rd Party Services | 1 | 887.23 | Each |  |  |  |  | 887.23 | 115.3399 | 1002.5699 | 2021-02-28 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finished building chopper pad at Km 17 Hensen Road - CR-101392 | 11 | F119-F134 | Hensen Road | 0 | 44263 |  | 56 | 44265 | CR-20210228-2 | Build Chopper Pad - CR-101392 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6118KL-20210228-43rd Party Services887.23887.23 | KABI LAKE FOREST PRODUCTS LTD6118KL-20210228-43rd Party Services887.23887.23OEWT PA15-LEM | [5 empty] | 1 | 887.23 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6129 | KL-20210301-5 | 53511011 | Access | 0 | 3rd Party Services | 1 | 2463 | Each |  |  |  |  | 2463 | 320.19 | 2783.19 | 2021-03-01 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow on access road, load and haul gravel, sand road, skid corduroy, placing corduroy, cut bundles in half | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44263 |  | 57 | 44266 | JJR-20210301-1 | Scratching Hills for access |  |  |  | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD6129KL-20210301-53rd Party Services24632463 | KABI LAKE FOREST PRODUCTS LTD6129KL-20210301-53rd Party Services24632463OEWT PA15-LEM | [5 empty] | 1 | 2463 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6130 | KL-20210301-6 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-03-01 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal from Hwy 17 to Km 17 Hensen road - SSF-14256 / Dozer and loader cleaning roadway up Hensen west Km 1 to Km 21, - CR-101394 | 11 | F119-C134 | Hensen Road | 0 | 44263 |  | 56 | 44265 | SSF-20210301-1 | Grading Snow - SSF-14256 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6130KL-20210301-63rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD6130KL-20210301-63rd Party Services2321.822321.82OEWT PA15-LEM | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6130 | KL-20210301-6 | 53511111 | Access | 0 | 3rd Party Services | 1 | 4306.14 | Each |  |  |  |  | 4306.14 | 559.7982 | 4865.9382 | 2021-03-01 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal from Hwy 17 to Km 17 Hensen road - SSF-14256 / Dozer and loader cleaning roadway up Hensen west Km 1 to Km 21, - CR-101394 | 11 | F119-C134 | Hensen Road | 0 | 44263 |  | 56 | 44265 | CR-20210301-2 | Clearing Snow - CR-101394 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6130KL-20210301-63rd Party Services4306.144306.14 | KABI LAKE FOREST PRODUCTS LTD6130KL-20210301-63rd Party Services4306.144306.14OEWT PA15-LEM | [5 empty] | 1 | 4306.14 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6132 | KL-20210301-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2815 | Each |  |  |  |  | 2815 | 365.95 | 3180.95 | 2021-03-01 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator doing snow removal from High Falls road to F194/F197 for pickup access | 11 | F198-F202 | High Falls Road-8 | 0 | 44256 |  | 56 | 44265 | MC-20210301-1 | Clearing snow-MC-13096 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6132KL-20210301-83rd Party Services28152815 | KABI LAKE FOREST PRODUCTS LTD6132KL-20210301-83rd Party Services28152815OEWT PA15-LEM | [5 empty] | 1 | 2815 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6133 | KL-20210301-9 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2089.64 | Each |  |  |  |  | 2089.64 | 271.6532 | 2361.2932 | 2021-03-01 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal on AE1 to E215 Access - SSF-14258 / Dozer snow removal on AE1 and From F227 to F224 - SSF-14257 | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44263 |  | 56 | 44265 | SSF-20210301-2 | Grading snow - SSF-14258 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6133KL-20210301-93rd Party Services2089.642089.64 | KABI LAKE FOREST PRODUCTS LTD6133KL-20210301-93rd Party Services2089.642089.64OEWT PA15-LEM | [5 empty] | 1 | 2089.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6133 | KL-20210301-9 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1111.09 | Each |  |  |  |  | 1111.09 | 144.4417 | 1255.5317 | 2021-03-01 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal on AE1 to E215 Access - SSF-14258 / Dozer snow removal on AE1 and From F227 to F224 - SSF-14257 | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44263 |  | 56 | 44265 | SSF-20210301-3 | Snow removal - SSF-14257 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6133KL-20210301-93rd Party Services1111.091111.09 | KABI LAKE FOREST PRODUCTS LTD6133KL-20210301-93rd Party Services1111.091111.09OEWT PA15-LEM | [5 empty] | 1 | 1111.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6144 | KL-20210302-3 | 53511011 | Access | 0 | 3rd Party Services | 1 | 5358 | Each |  |  |  |  | 5358 | 696.54 | 6054.54 | 2021-03-02 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loading and hauling gravel, skid corduroy, cut bundles in half for corduroy F36 F35 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44269 |  | 57 | 44277 | JJR-20210302-1 | Sloping road/filling ditches |  |  |  | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD6144KL-20210302-33rd Party Services53585358 | KABI LAKE FOREST PRODUCTS LTD6144KL-20210302-33rd Party Services53585358OEWT PA15-LEM | [5 empty] | 1 | 5358 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6145 | KL-20210302-4 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-03-02 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal from Hwy 17 to Km 17 on Hensen Road - SSF-14261 / Dozer and loader cleaning roadway up to Hensen West Km 0 to Km 21 - CR-101396 | 11 | F119-F134 | Hensen Road | 0 | 44269 |  | 56 | 44270 | SSF-20210302-1 | Grader snow removal - SSF-14261 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6145KL-20210302-43rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD6145KL-20210302-43rd Party Services2321.822321.82OEWT PA15-LEM | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6145 | KL-20210302-4 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2815.05 | Each |  |  |  |  | 2815.05 | 365.9565 | 3181.0065 | 2021-03-02 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal from Hwy 17 to Km 17 on Hensen Road - SSF-14261 / Dozer and loader cleaning roadway up to Hensen West Km 0 to Km 21 - CR-101396 | 11 | F119-F134 | Hensen Road | 0 | 44269 |  | 56 | 44270 | CR-20210302-1 | Snow removal - CR-101396 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6145KL-20210302-43rd Party Services2815.052815.05 | KABI LAKE FOREST PRODUCTS LTD6145KL-20210302-43rd Party Services2815.052815.05OEWT PA15-LEM | [5 empty] | 1 | 2815.05 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6146 | KL-20210302-5 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2797.05 | Each |  |  |  |  | 2797.05 | 363.6165 | 3160.6665 | 2021-03-02 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator stripping for material at F67 for road maintenance, loader spreading gravel in some bad spots - CR-101397 | 11 | F119-F134 | Hensen Road | 0 | 44269 |  | 56 | 44277 | CR-20210302-2 | Road maintenance - CR-101397 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6146KL-20210302-53rd Party Services2797.052797.05 | KABI LAKE FOREST PRODUCTS LTD6146KL-20210302-53rd Party Services2797.052797.05OEWT PA15-LEM | [5 empty] | 1 | 2797.05 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6156 | KL-20210303-1 | 53510711 | Access | 0 | 3rd Party Services | 1 | 1411.5 | Each |  |  |  |  | 1411.5 | 183.495 | 1594.995 | 2021-03-03 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Mob 312 to Three Finger Road - CR-101400 / Repair road near structures D11 and D12 as required - CR-101401 | 7 | D-009 to D-017 | Three Finger Lake | 0 | 44270 |  | 56 | 44270 | CR-20210303-2 | Repair Road - CR-101401 |  |  |  | Mandy Sandhu | 07 | KABI LAKE FOREST PRODUCTS LTD6156KL-20210303-13rd Party Services1411.51411.5 | KABI LAKE FOREST PRODUCTS LTD6156KL-20210303-13rd Party Services1411.51411.5OEWT PA15-LEM | [5 empty] | 1 | 1411.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6158 | KL-20210303-3 | 53511011 | Access | 0 | 3rd Party Services | 1 | 5454 | Each |  |  |  |  | 5454 | 709.02 | 6163.02 | 2021-03-03 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel and cover corduroy at F57, place corduroy at F35, open up road with loader | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44270 |  | 57 | 44270 | JJR-20210303-1 | Slope ditches, repair roads. |  |  |  | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD6158KL-20210303-33rd Party Services54545454 | KABI LAKE FOREST PRODUCTS LTD6158KL-20210303-33rd Party Services54545454OEWT PA15-LEM | [5 empty] | 1 | 5454 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6161 | KL-20210303-6 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2370.18 | Each |  |  |  |  | 2370.18 | 308.1234 | 2678.3034 | 2021-03-03 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader clearing Hensen west also plowed F117, F114, / Grader doing snow removal and scarifying from Hwy 17 to Km 17 on Hensen Road - SSF-14263 | 11 | F119-F134 | Hensen Road | 0 | 44270 |  | 56 | 44270 | CR-20210303-3 | Cleaning roadways - CR-101399 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6161KL-20210303-63rd Party Services2370.182370.18 | KABI LAKE FOREST PRODUCTS LTD6161KL-20210303-63rd Party Services2370.182370.18OEWT PA15-LEM | [5 empty] | 1 | 2370.18 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6161 | KL-20210303-6 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-03-03 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader clearing Hensen west also plowed F117, F114, / Grader doing snow removal and scarifying from Hwy 17 to Km 17 on Hensen Road - SSF-14263 | 11 | F119-F134 | Hensen Road | 0 | 44270 |  | 56 | 44270 | SSF-20210303-1 | Grading, scarifying road - SSF-14263 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6161KL-20210303-63rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD6161KL-20210303-63rd Party Services2321.822321.82OEWT PA15-LEM | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6162 | KL-20210303-7 | 53511111 | Access | 0 | 3rd Party Services | 1 | 3867.28 | Each |  |  |  |  | 3867.28 | 502.7464 | 4370.0264 | 2021-03-03 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator loading truck and D5 spreading material to patch up road km 20 to km 17 Hensen west - CR-101398 | 11 | F119-F134 | Hensen Road | 0 | 44270 |  | 56 | 44270 | CR-20210303-4 | Patching up Road - CR-101398 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6162KL-20210303-73rd Party Services3867.283867.28 | KABI LAKE FOREST PRODUCTS LTD6162KL-20210303-73rd Party Services3867.283867.28OEWT PA15-LEM | [5 empty] | 1 | 3867.28 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6187 | KL-20210304-1 | 53510711 | Access | 0 | 3rd Party Services | 1 | 856.32 | Each |  |  |  |  | 856.32 | 111.3216 | 967.6416 | 2021-03-04 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair road near structures D11 and D12 as required - CR-101403 | 7 | D-009 to D-017 | Three Finger Lake | 0 | 44271 |  | 56 | 44271 | CR-20210304-1 | Repairing Road -CR-101403 |  |  |  | Mandy Sandhu | 07 | KABI LAKE FOREST PRODUCTS LTD6187KL-20210304-13rd Party Services856.32856.32 | KABI LAKE FOREST PRODUCTS LTD6187KL-20210304-13rd Party Services856.32856.32OEWT PA15-LEM | [5 empty] | 1 | 856.32 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6190 | KL-20210304-4 | 53511011 | Access | 0 | 3rd Party Services | 1 | 2642 | Each |  |  |  |  | 2642 | 343.46 | 2985.46 | 2021-03-04 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Walk out 950, 330 and buncher, skidded corduroy to bridge, excavator loaded dirt into rock trucks on one side of bridge and other excavator working on road | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44271 |  | 57 | 44273 | JJR-20210304-1 | Dozeer opening structure access |  |  |  | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD6190KL-20210304-43rd Party Services26422642 | KABI LAKE FOREST PRODUCTS LTD6190KL-20210304-43rd Party Services26422642OEWT PA15-LEM | [5 empty] | 1 | 2642 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6193 | KL-20210304-7 | 53511111 | Access | 0 | 3rd Party Services | 1 | 3404.59 | Each |  |  |  |  | 3404.59 | 442.5967 | 3847.1867 | 2021-03-04 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator loading truck and D5 spreading material to patch up road F69 to F70 - CR-101407 / Move rock truck to km 1.6 for demob - CR-101408 | 11 | F119-F134 | Hensen Road | 0 | 44271 |  | 56 | 44271 | CR-20210304-2 | Patching up road - CR-101407 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6193KL-20210304-73rd Party Services3404.593404.59 | KABI LAKE FOREST PRODUCTS LTD6193KL-20210304-73rd Party Services3404.593404.59OEWT PA15-LEM | [5 empty] | 1 | 3404.59 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6195 | KL-20210304-9 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1335.27 | Each |  |  |  |  | 1335.27 | 173.5851 | 1508.8551 | 2021-03-04 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader Clearing road, trimming banks Hensen West km 4 to 16 - CR-101406 / Grader benching snow banks, scarifying from Hwy 17 to Km 17 on Hensen Road - SSF-14265 | 11 | F119-F134 | Hensen Road | 0 | 44271 |  | 56 | 44271 | CR-20210304-6 | clearing road ways - CR-101406 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6195KL-20210304-93rd Party Services1335.271335.27 | KABI LAKE FOREST PRODUCTS LTD6195KL-20210304-93rd Party Services1335.271335.27OEWT PA15-LEM | [5 empty] | 1 | 1335.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6195 | KL-20210304-9 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-03-04 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader Clearing road, trimming banks Hensen West km 4 to 16 - CR-101406 / Grader benching snow banks, scarifying from Hwy 17 to Km 17 on Hensen Road - SSF-14265 | 11 | F119-F134 | Hensen Road | 0 | 44271 |  | 56 | 44271 | SSF-20210304-1 | Pushing banks back - SSF-14265 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6195KL-20210304-93rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD6195KL-20210304-93rd Party Services2321.822321.82OEWT PA15-LEM | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5617 | KL-20210126-1 | 53511011 | Access | 0 | 3rd Party Services | 1 | 5642 | Each |  |  |  |  | 5642 | 733.46 | 6375.46 | 2021-01-26 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Drag 70' bridge in from km 9 laydown, plow snow, grade PL2 Rd and F20-F10. Haul gravel and corduroy, sand roads, unload bridge, skidder drag mats to WC 11150 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44228 |  | 50 | 44232 | JJR-20210126-1 | plow and open up roads |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5617KL-20210126-13rd Party Services56425642 | KABI LAKE FOREST PRODUCTS LTD5617KL-20210126-13rd Party Services56425642OEWT-PA14-Lem-R1 | [5 empty] | 1 | 5642 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5658 | KL-20210128-10 | 53511011 | Access | 0 | 3rd Party Services | 1 | 2392 | Each |  |  |  |  | 2392 | 310.96 | 2702.96 | 2021-01-28 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow snow, haul gravel & corduroy, sand roads, unload bridge, and skid corduroy. Drag 70' bridge in to WC 11150. Work on hills/corners. Place corduroy & spread gravel | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44228 |  | 50 | 44232 | JJR-20210128-1 | Plow and open up roads. |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5658KL-20210128-103rd Party Services23922392 | KABI LAKE FOREST PRODUCTS LTD5658KL-20210128-103rd Party Services23922392OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2392 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5757 | KL-20210203-14 | 53511104 | Access | 0 | 3rd Party Services | 1 | 200.18 | Each |  |  |  |  | 200.18 | 26.0234 | 226.2034 | 2021-02-03 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Berms and bumpers installed near F158- CE-107 / Skid mats, haul corduroy and lay geo. - CE-108 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 | 44243 |  | 56 | 44247 | CE-20210203-5 | Rock truck hauled gravel |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD5757KL-20210203-143rd Party Services200.18200.18 | KABI LAKE FOREST PRODUCTS LTD5757KL-20210203-143rd Party Services200.18200.18OEWT-PA14-Lem-R1 |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 200.18 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5899 | KL-20210214-3 | 53511011 | Access | 0 | 3rd Party Services | 1 | 2642 | Each |  |  |  |  | 2642 | 343.46 | 2985.46 | 2021-02-14 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Skid corduroy, grade Paint Lake Road 2, unload and load legos, load and haul Gravel. Loading , Hauling and spreading gravel, drag in 50' bridge WC 11190,- | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44245 |  | 50 | 44251 | JJR-20210214-1 | Plow snow off hills |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD5899KL-20210214-33rd Party Services26422642 | KABI LAKE FOREST PRODUCTS LTD5899KL-20210214-33rd Party Services26422642OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2642 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5964 | KL-20210219-2 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2642 | Each |  |  |  |  | 2642 | 343.46 | 2985.46 | 2021-02-19 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Hammering access road, corduroy, plowing snow near F62. JJR-70245 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44252 |  | 57 | 44252 | JJR-20210219-1 | Plowing snow F062 |  |  |  | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD5964KL-20210219-23rd Party Services26422642 | KABI LAKE FOREST PRODUCTS LTD5964KL-20210219-23rd Party Services26422642OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2642 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5976 | KL-20210220-3 | 53511011 | Access | 0 | 3rd Party Services | 1 | 2642 | Each |  |  |  |  | 2642 | 343.46 | 2985.46 | 2021-02-20 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Paint Lake 2 Road, Plow snow on access road. Corduroy F62-F63 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44252 |  | 57 | 44252 | JJR-20210220-1 | Plowing snow |  |  |  | Wesley Seminowich | 10 | KABI LAKE FOREST PRODUCTS LTD5976KL-20210220-33rd Party Services26422642 | KABI LAKE FOREST PRODUCTS LTD5976KL-20210220-33rd Party Services26422642OEWT-PA14-Lem-R1 | [5 empty] | 1 | 2642 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 5990 | KL-20210221-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1809.45 | Each |  |  |  |  | 1809.45 | 235.2285 | 2044.6785 | 2021-02-21 | 0 | OEWT-PA14-Lem-R1 | 44277 | 43 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade Paint Lake 2 Rd, plow snow on access rd, haul geo from km 9 to km 23, skid corduroy | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44252 |  | 57 | 44255 | JJR-20210221-1 | Plow snow |  |  |  | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD5990KL-20210221-83rd Party Services1809.451809.45 | KABI LAKE FOREST PRODUCTS LTD5990KL-20210221-83rd Party Services1809.451809.45OEWT-PA14-Lem-R1 | [5 empty] | 1 | 1809.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6225 | KL-20210305-5 | 53511111 | Access | 0 | 3rd Party Services | 1 | 3745.46 | Each |  |  |  |  | 3745.46 | 486.9098 | 4232.3698 | 2021-03-05 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer and loader opening up roadways getting ready for spring break up. Grader scarifying Hills & Corners from Hwy 17 to km 17 on Hensen Road. | 11 | F119-F134 | Hensen Road | 0 | 44277 |  | 56 | 44277 | CR-20210305-1 | Dozer and loader opening up roadways getting ready for spring break up. CR-101410 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6225KL-20210305-53rd Party Services3745.463745.46 | KABI LAKE FOREST PRODUCTS LTD6225KL-20210305-53rd Party Services3745.463745.46OEWT PA15-LEM | [5 empty] | 1 | 3745.46 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6225 | KL-20210305-5 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-03-05 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer and loader opening up roadways getting ready for spring break up. Grader scarifying Hills & Corners from Hwy 17 to km 17 on Hensen Road. | 11 | F119-F134 | Hensen Road | 0 | 44277 |  | 56 | 44277 | SSF-20210305-1 | Grader scarifying Hills & Corners from Hwy 17 to km 17 on Hensen Road. SSF-14264 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6225KL-20210305-53rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD6225KL-20210305-53rd Party Services2321.822321.82OEWT PA15-LEM | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6245 | KL-20210306-11 | 53511111 | Access | 0 | 3rd Party Services | 1 | 5753.1 | Each |  |  |  |  | 5753.1 | 747.903 | 6501.003 | 2021-03-06 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer, loader & excavator punch holes in snow banks on way out km 21 to km 0 Hensen W. Night Shift- Dozer moving snow for spring run off km 5 to km 21 on Hensen W. | 11 | F119-F134 | Hensen Road | 0 | 44277 |  | 56 | 44280 | CR-20210306-3 | Dozer, loader & excavator punching holes in snow banks on way out km 21 to km 0 Hensen West. CR-101411 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6245KL-20210306-113rd Party Services5753.15753.1 | KABI LAKE FOREST PRODUCTS LTD6245KL-20210306-113rd Party Services5753.15753.1OEWT PA15-LEM | [5 empty] | 1 | 5753.1 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6245 | KL-20210306-11 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1775.64 | Each |  |  |  |  | 1775.64 | 230.8332 | 2006.4732 | 2021-03-06 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer, loader & excavator punch holes in snow banks on way out km 21 to km 0 Hensen W. Night Shift- Dozer moving snow for spring run off km 5 to km 21 on Hensen W. | 11 | F119-F134 | Hensen Road | 0 | 44277 |  | 56 | 44280 | CR-20210306-4 | Night Shift----Dozer moving snow for spring run off km 5 to km 21 on Hensen West. CR-101412 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6245KL-20210306-113rd Party Services1775.641775.64 | KABI LAKE FOREST PRODUCTS LTD6245KL-20210306-113rd Party Services1775.641775.64OEWT PA15-LEM | [5 empty] | 1 | 1775.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6246 | KL-20210306-12 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-03-06 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators laid corduroy at finger for F104-F102. Very long tram for cord at F103. Grader scarifying hills & corners from Hwy 17 to km 17 on Hensen Rd | 11 | F119-F134 | Hensen Road | 0 | 44277 |  | 56 | 44280 | SSF-20210306-1 | Grader scarifying hills & corners from Hwy 17 to km 17 on Hensen Rd SSF-14266 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6246KL-20210306-123rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD6246KL-20210306-123rd Party Services2321.822321.82OEWT PA15-LEM | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6252 | KL-20210307-5 | 53511011 | Access | 0 | 3rd Party Services | 1 | 5378 | Each |  |  |  |  | 5378 | 699.14 | 6077.14 | 2021-03-07 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 290 Loading Corduroy, 725 hauling Corduroy, D6T opening up structure roads and plowing snow, 336 Cat repairing Access Roads. JJR-70261 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44277 |  | 56 | 44278 | JJR-20210307-1 | D6T plow snow and open up roads |  |  |  | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6252KL-20210307-53rd Party Services53785378 | KABI LAKE FOREST PRODUCTS LTD6252KL-20210307-53rd Party Services53785378OEWT PA15-LEM | [5 empty] | 1 | 5378 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6261 | KL-20210307-14 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-03-07 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying hills & corners from Hwy 17 to Km17 on Hensen Road. SSF-14267 | 11 | F119-F134 | Hensen Road | 0 | 44277 |  | 56 | 44279 | SSF-20210307-1 | Grader scarifying hills & corners from Hwy 17 to Km17 on Hensen Road. SSF-14267 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6261KL-20210307-143rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD6261KL-20210307-143rd Party Services2321.822321.82OEWT PA15-LEM | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6262 | KL-20210307-15 | 53511111 | Access | 0 | 3rd Party Services | 1 | 10135.2 | Each |  |  |  |  | 10135.2 | 1317.576 | 11452.776 | 2021-03-07 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Equipment working their way out removing snow for drainage and patching up km 4 hill | 11 | F119-F134 | Hensen Road | 0 | 44277 |  | 56 | 44279 | CR-20210307-5 | Equipment working their way out removing snow for drainage and patching up km 4 hill |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6262KL-20210307-153rd Party Services10135.210135.2 | KABI LAKE FOREST PRODUCTS LTD6262KL-20210307-153rd Party Services10135.210135.2OEWT PA15-LEM | [5 empty] | 1 | 10135.2 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6273 | KL-20210308-10 | 53511111 | Access | 0 | 3rd Party Services | 1 | 10435.24 | Each |  |  |  |  | 10435.24 | 1356.5812 | 11791.8212 | 2021-03-08 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Equipment working to remove snow and open ditches for spring run off km 4 to km 0 on Hensen W. Grader scarifying hills & corners from Hwy 17 to km 17 on Hensen | 11 | F119-F134 | Hensen Road | 0 | 44278 |  | 56 | 44280 | CR-20210308-1 | Equipment working to remove snow and opening up ditches for spring run off km 4 to km 0 on Hensen West. CR-101420 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6273KL-20210308-103rd Party Services10435.2410435.24 | KABI LAKE FOREST PRODUCTS LTD6273KL-20210308-103rd Party Services10435.2410435.24OEWT PA15-LEM | [5 empty] | 1 | 10435.24 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6273 | KL-20210308-10 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1857.45 | Each |  |  |  |  | 1857.45 | 241.4685 | 2098.9185 | 2021-03-08 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Equipment working to remove snow and open ditches for spring run off km 4 to km 0 on Hensen W. Grader scarifying hills & corners from Hwy 17 to km 17 on Hensen | 11 | F119-F134 | Hensen Road | 0 | 44278 |  | 56 | 44280 | SSF-20210308-1 | Grader scarifying hills & corners from Hwy 17 to km 17 on Hensen Rd. SSF-14268 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6273KL-20210308-103rd Party Services1857.451857.45 | KABI LAKE FOREST PRODUCTS LTD6273KL-20210308-103rd Party Services1857.451857.45OEWT PA15-LEM | [5 empty] | 1 | 1857.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6275 | KL-20210308-12 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1306.45 | Each |  |  |  |  | 1306.45 | 169.8385 | 1476.2885 | 2021-03-08 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fill Holes to fix hills from Km 5 to Km 9 - CE-169 | 11 | F135-F149 | Dore lake Road | 0 | 44278 |  | 56 | 44280 | CE-20210308-1 | Fill Holes to fix hills from Km 5 to Km 9 - CE-169 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6275KL-20210308-123rd Party Services1306.451306.45 | KABI LAKE FOREST PRODUCTS LTD6275KL-20210308-123rd Party Services1306.451306.45OEWT PA15-LEM | [5 empty] | 1 | 1306.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6282 | KL-20210309-5 | 53511111 | Access | 0 | 3rd Party Services | 1 | 795.23 | Each |  |  |  |  | 795.23 | 103.3799 | 898.6099 | 2021-03-09 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer opened up to F121 CR-101422 | 11 | F119-F134 | Hensen Road | 0 | 44278 |  | 56 | 44280 | CR-20210309-1 | Dozer opened up to F121 CR-101422 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6282KL-20210309-53rd Party Services795.23795.23 | KABI LAKE FOREST PRODUCTS LTD6282KL-20210309-53rd Party Services795.23795.23OEWT PA15-LEM | [5 empty] | 1 | 795.23 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6299 | KL-20210310-12 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1265.41 | Each |  |  |  |  | 1265.41 | 164.5033 | 1429.9133 | 2021-03-10 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator draining water up Hensen East on his way to F134 CR-101427 | 11 | F119-F134 | Hensen Road | 0 | 44278 |  | 56 | 44280 | CR-20210310-2 | Excavator draining water up Hensen East on his way to F134 CR-101427 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6299KL-20210310-123rd Party Services1265.411265.41 | KABI LAKE FOREST PRODUCTS LTD6299KL-20210310-123rd Party Services1265.411265.41OEWT PA15-LEM | [5 empty] | 1 | 1265.41 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6301 | KL-20210311-2 | 53511011 | Access | 0 | 3rd Party Services | 1 | 10556 | Each |  |  |  |  | 10556 | 1372.28 | 11928.28 | 2021-03-11 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal & scarifying Paint Lake 2 Rd. JJR pushing snowbanks back. CDSL excavator walking out to float access. | 10 | F033-F118 | Paint Lake Raod 2 | 0 | 44278 |  | 56 | 44280 | JJR-20210311-1 | 290 Linkbelt walk out and push banks back. 290 Walk out for float. 750 Dozer plow snow and walk out. Track D6 dozer for float. 336 push snow and walk out. JJR-70265 |  |  |  | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6301KL-20210311-23rd Party Services1055610556 | KABI LAKE FOREST PRODUCTS LTD6301KL-20210311-23rd Party Services1055610556OEWT PA15-LEM | [5 empty] | 1 | 10556 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6302 | KL-20210311-3 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1857.45 | Each |  |  |  |  | 1857.45 | 241.4685 | 2098.9185 | 2021-03-11 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader pushing back snow banks on AE1 for drainage. SSF-14269. Main Anjigame road from hwy access | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44278 |  | 56 | 44280 | SSF-20210311-1 | Grader pushing back snow banks on AE1 for drainage. SSF-14269 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6302KL-20210311-33rd Party Services1857.451857.45 | KABI LAKE FOREST PRODUCTS LTD6302KL-20210311-33rd Party Services1857.451857.45OEWT PA15-LEM | [5 empty] | 1 | 1857.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6305 | KL-20210312-2 | 53511011 | Access | 0 | 3rd Party Services | 1 | 2559 | Each |  |  |  |  | 2559 | 332.67 | 2891.67 | 2021-03-12 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | 336 Cat pushing back banks, D6T widening road. JJR-70266 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44250 |  | 56 | 44280 | JJR-20210312-1 | 336 Cat pushing back banks, D6T widening road. JJR-70266 |  |  |  | Mandy Sandhu | 10 | KABI LAKE FOREST PRODUCTS LTD6305KL-20210312-23rd Party Services25592559 | KABI LAKE FOREST PRODUCTS LTD6305KL-20210312-23rd Party Services25592559OEWT PA15-LEM | [5 empty] | 1 | 2559 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6306 | KL-20210312-3 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1666.64 | Each |  |  |  |  | 1666.64 | 216.6632 | 1883.3032 | 2021-03-12 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer levelling ruts and pushing snow banks back for drainage on AE1 to F227 Access. SSF-14270 | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44278 |  | 56 | 44280 | SSF-20210312-1 | Dozer levelling ruts and pushing snow banks back for drainage on AE1 to F227 Access. SSF-14270 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6306KL-20210312-33rd Party Services1666.641666.64 | KABI LAKE FOREST PRODUCTS LTD6306KL-20210312-33rd Party Services1666.641666.64OEWT PA15-LEM | [5 empty] | 1 | 1666.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6311 | KL-20210312-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1741.27 | Each |  |  |  |  | 1741.27 | 226.3651 | 1967.6351 | 2021-03-12 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator did work up Hensen east on water control and fix up bad spots -CR-101432 | 11 | F119-F134 | Hensen Road | 0 | 44278 |  | 56 | 44280 | CR-20210312-2 | Excavator did work up Hensen east on water control and fix up bad spots -CR-101432 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6311KL-20210312-83rd Party Services1741.271741.27 | KABI LAKE FOREST PRODUCTS LTD6311KL-20210312-83rd Party Services1741.271741.27OEWT PA15-LEM | [5 empty] | 1 | 1741.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6314 | KL-20210312-11 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 781.05 | Each |  |  |  |  | 781.05 | 101.5365 | 882.5865 | 2021-03-12 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator reclaimed Structure site F134 - CR-101430 | 11 | F119-F134 | Hensen Road | 0 | 44278 |  | 56 | 44280 | CR-20210312-4 | Excavator reclaimed Structure site F134 - CR-101430 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6314KL-20210312-113rd Party Services781.05781.05 | KABI LAKE FOREST PRODUCTS LTD6314KL-20210312-113rd Party Services781.05781.05OEWT PA15-LEM |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 781.05 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6328 | KL-20210313-5 | 53511111 | Access | 0 | 3rd Party Services | 1 | 3440.23 | Each |  |  |  |  | 3440.23 | 447.2299 | 3887.4599 | 2021-03-13 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader ditching, diverting water Hensen, Excavator fixing water troubles Hensen E. - CR-101437 / Grader Scarifying, pushing snow banks back Hensen Rd - SSF-14271 | 11 | F119-F134 | Hensen Road | 0 | 44279 |  | 56 | 44280 | CR-20210313-1 | Loader ditching and deverting water on hensen main road, Excavator fixing water troubles up Hensen East - CR-101437 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6328KL-20210313-53rd Party Services3440.233440.23 | KABI LAKE FOREST PRODUCTS LTD6328KL-20210313-53rd Party Services3440.233440.23OEWT PA15-LEM | [5 empty] | 1 | 3440.23 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6328 | KL-20210313-5 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-03-13 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader ditching, diverting water Hensen, Excavator fixing water troubles Hensen E. - CR-101437 / Grader Scarifying, pushing snow banks back Hensen Rd - SSF-14271 | 11 | F119-F134 | Hensen Road | 0 | 44279 |  | 56 | 44280 | SSF-20210313-1 | Grader Scarifying build up ice and pushing snow banks back for drainage from Hwy 17 to Km 17 on Hensen Road - SSF-14271 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6328KL-20210313-53rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD6328KL-20210313-53rd Party Services2321.822321.82OEWT PA15-LEM | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6329 | KL-20210313-6 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 2639.82 | Each |  |  |  |  | 2639.82 | 343.1766 | 2982.9966 | 2021-03-13 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator reclaiming from F134 to F133, moved wood out from 134 for grinder - CR-101436 | 11 | F119-F134 | Hensen Road | 0 | 44279 |  | 56 | 44280 | CR-20210313-2 | Excavator reclaiming from F134 to F133, moved wood out from 134 for grinder - CR-101436 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6329KL-20210313-63rd Party Services2639.822639.82 | KABI LAKE FOREST PRODUCTS LTD6329KL-20210313-63rd Party Services2639.822639.82OEWT PA15-LEM |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2639.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6339 | KL-20210315-7 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-03-15 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying build up ice and pushing snow banks back for drainage from hwy 17 to Km 17 on hensen Road - SSF-14272 | 11 | F119-F134 | Hensen Road | 0 | 44279 |  | 56 | 44280 | SSF-20210315-1 | Grader scarifying build up ice and pushing snow banks back for drainage from hwy 17 to Km 17 on hensen Road - SSF-14272 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6339KL-20210315-73rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD6339KL-20210315-73rd Party Services2321.822321.82OEWT PA15-LEM | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6344 | KL-20210316-3 | 53511111 | Access | 0 | 3rd Party Services | 1 | 696.55 | Each |  |  |  |  | 696.55 | 90.5515 | 787.1015 | 2021-03-16 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying built up ice on hills for float truck - SSF-14273 | 11 | F119-F134 | Hensen Road | 0 | 44281 |  | 56 | 44282 | SSF-20210316-1 | Grader scarifying built up ice on hills for float truck - SSF-14273 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6344KL-20210316-33rd Party Services696.55696.55 | KABI LAKE FOREST PRODUCTS LTD6344KL-20210316-33rd Party Services696.55696.55OEWT PA15-LEM | [5 empty] | 1 | 696.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6545 | KL-20210314-4 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 2046.45 | Each |  |  |  |  | 2046.45 | 266.0385 | 2312.4885 | 2021-03-14 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finished reclaim from F134 to F133 - CR-101438 | 11 | F119-F134 | Hensen Road | 0 | 44279 |  | 56 | 44288 | CR-20210314-1 | Excavator finished reclaim from F134 to F133 - CR-101438 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6545KL-20210314-43rd Party Services2046.452046.45 | KABI LAKE FOREST PRODUCTS LTD6545KL-20210314-43rd Party Services2046.452046.45OEWT PA15-LEM |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2046.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6558 | KL-20210321-4 | 53511104 | Access | 0 | 3rd Party Services | 1 | 1633.46 | Each |  |  |  |  | 1633.46 | 212.3498 | 1845.8098 | 2021-03-21 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Installed culvert at Michipicoten Harbor Road 1, F150-F151, Graveled hauled from Dore Lake Pit - CE-176 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44284 |  | 57 | 44289 | CE-20210321-1 | Hauled gravel to F150-F151. CE-176 |  |  |  | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6558KL-20210321-43rd Party Services1633.461633.46 | KABI LAKE FOREST PRODUCTS LTD6558KL-20210321-43rd Party Services1633.461633.46OEWT PA15-LEM |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 1633.46 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6559 | KL-20210322-1 | 53511111 | Access | 0 | 3rd Party Services | 1 | 464.36 | Each |  |  |  |  | 464.36 | 60.3668 | 524.7268 | 2021-03-22 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader leveling ruts and pushing snow banks for Drainage - SSF-14275 | 11 | F212-F214 | Michipicoten Road- 1 | 0 | 44284 |  | 57 | 44289 | SSF-20210322-1 | Grader leveling ruts and pushing snow banks for Drainage - SSF-14275 |  |  |  | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6559KL-20210322-13rd Party Services464.36464.36 | KABI LAKE FOREST PRODUCTS LTD6559KL-20210322-13rd Party Services464.36464.36OEWT PA15-LEM | [5 empty] | 1 | 464.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6585 | KL-20210228-12 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1626.59 | Each |  |  |  |  | 1626.59 | 211.4567 | 1838.0467 | 2021-02-28 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fixing road and holes on Dore Lake Road. Skidder skid mats to Dore Lake Rd from Michipicoten Harbour #5. CE-168 | 11 | F135-F149 | Dore Lake Road | 0 | 44280 |  | 56 | 44297 | CE-20210228-2 | Fixing road and holes on Dore Lake |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6585KL-20210228-123rd Party Services1626.591626.59 | KABI LAKE FOREST PRODUCTS LTD6585KL-20210228-123rd Party Services1626.591626.59OEWT PA15-LEM | [5 empty] | 1 | 1626.59 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6585 | KL-20210228-12 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1848.91 | Each |  |  |  |  | 1848.91 | 240.3583 | 2089.2683 | 2021-02-28 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fixing road and holes on Dore Lake Road. Skidder skid mats to Dore Lake Rd from Michipicoten Harbour #5. CE-168 | 11 | F135-F149 | Dore Lake Road | 0 | 44280 |  | 56 | 44297 | CE-20210228-2 | Skidder move mats to Dore Lake |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6585KL-20210228-123rd Party Services1848.911848.91 | KABI LAKE FOREST PRODUCTS LTD6585KL-20210228-123rd Party Services1848.911848.91OEWT PA15-LEM | [5 empty] | 1 | 1848.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6586 | KL-20210301-14 | 53511111 | Access | 0 | 3rd Party Services | 1 | 903.64 | Each |  |  |  |  | 903.64 | 117.4732 | 1021.1132 | 2021-03-01 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fixed hill @ km8- lay sand mats. CE159 | 11 | F135-F149 | Dore Lake Road | 0 | 44280 |  | 56 | 44297 | CE-20210301-1 | Fixed hill @ km8- lay sand mats. CE159 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6586KL-20210301-143rd Party Services903.64903.64 | KABI LAKE FOREST PRODUCTS LTD6586KL-20210301-143rd Party Services903.64903.64OEWT PA15-LEM | [5 empty] | 1 | 903.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6587 | KL-20210301-15 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2845.5 | Each |  |  |  |  | 2845.5 | 369.915 | 3215.415 | 2021-03-01 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fix and patch roads, forward material from km 6.5. CE-160 | 11 | F135-F149 | Dore Lake Road | 0 | 44280 |  | 56 | 44297 | CE-20210301-2 | Fix and patch roads, forward material from km 6.5. CE-160 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6587KL-20210301-153rd Party Services2845.52845.5 | KABI LAKE FOREST PRODUCTS LTD6587KL-20210301-153rd Party Services2845.52845.5OEWT PA15-LEM | [5 empty] | 1 | 2845.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6588 | KL-20210303-14 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2736.5 | Each |  |  |  |  | 2736.5 | 355.745 | 3092.245 | 2021-03-03 | 0 | OEWT PA15-LEM | 44307 | 46 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road repair on Michipicoten Harbour Road #2. CE-161 | 11 | F135-F149 | Dore Lake Road | 0 | 44280 |  | 56 | 44297 | CE-20210303-1 | Road repair on Michipicoten Harbour Road #2. CE-161 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6588KL-20210303-143rd Party Services2736.52736.5 | KABI LAKE FOREST PRODUCTS LTD6588KL-20210303-143rd Party Services2736.52736.5OEWT PA15-LEM | [5 empty] | 1 | 2736.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6593 | KL-20210331-7 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1805.91 | Each |  |  |  |  | 1805.91 | 234.7683 | 2040.6783 | 2021-03-31 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Push dirt to build up edges along Dore Road. Bring in skidder for Valard tow call- float in bank. | 11 | F135-F149 | Dore Lake Road | 0 | 44295 |  | 56 | 44297 | CE-20210211-4 | Push dirt to build up edges of road |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6593KL-20210331-73rd Party Services1805.911805.91 | KABI LAKE FOREST PRODUCTS LTD6593KL-20210331-73rd Party Services1805.911805.91OEWT-PA16-Lem | [5 empty] | 1 | 1805.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6593 | KL-20210331-7 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1880 | Each |  |  |  |  | 1880 | 244.4 | 2124.4 | 2021-03-31 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Push dirt to build up edges along Dore Road. Bring in skidder for Valard tow call- float in bank. | 11 | F135-F149 | Dore Lake Road | 0 | 44295 |  | 56 | 44297 | CE-20210212-2 | Push dirt, widen road at Dore Lake Rd, F135-F149. CE-123-2 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6593KL-20210331-73rd Party Services18801880 | KABI LAKE FOREST PRODUCTS LTD6593KL-20210331-73rd Party Services18801880OEWT-PA16-Lem | [5 empty] | 1 | 1880 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6593 | KL-20210331-7 | 53511111 | Access | 0 | 3rd Party Services | 1 | 885.55 | Each |  |  |  |  | 885.55 | 115.1215 | 1000.6715 | 2021-03-31 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Push dirt to build up edges along Dore Road. Bring in skidder for Valard tow call- float in bank. | 11 | F135-F149 | Dore Lake Road | 0 | 44295 |  | 56 | 44297 | CE-20210219-2 | Run skidder out for tow call- Valard float in bank. CE-132-2 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6593KL-20210331-73rd Party Services885.55885.55 | KABI LAKE FOREST PRODUCTS LTD6593KL-20210331-73rd Party Services885.55885.55OEWT-PA16-Lem | [5 empty] | 1 | 885.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6594 | KL-20210331-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1880 | Each |  |  |  |  | 1880 | 244.4 | 2124.4 | 2021-03-31 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Push dirt to build up edges along Dore Road. Skid 4 loads to Km5 on Hensen Rd East, walked in to float, floated to Hensen, walked to Mat pick up area. | 11 | F119-F134 | Hensen Road | 0 | 44295 |  | 56 | 44297 | CE-20210216-3 | Scraped the roads, build berms on Hensen. CE-128-2. |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6594KL-20210331-83rd Party Services18801880 | KABI LAKE FOREST PRODUCTS LTD6594KL-20210331-83rd Party Services18801880OEWT-PA16-Lem | [5 empty] | 1 | 1880 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6594 | KL-20210331-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2642.18 | Each |  |  |  |  | 2642.18 | 343.4834 | 2985.6634 | 2021-03-31 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Push dirt to build up edges along Dore Road. Skid 4 loads to Km5 on Hensen Rd East, walked in to float, floated to Hensen, walked to Mat pick up area. | 11 | F119-F134 | Hensen Road | 0 | 44295 |  | 56 | 44297 | CE-20210218-2 | 4 loads to Km5 on Hensen Rd East, walked in to float, floated to Hensen, walked to Mat pick up area. CE-131-2 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6594KL-20210331-83rd Party Services2642.182642.18 | KABI LAKE FOREST PRODUCTS LTD6594KL-20210331-83rd Party Services2642.182642.18OEWT-PA16-Lem | [5 empty] | 1 | 2642.18 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6594 | KL-20210331-8 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1693 | Each |  |  |  |  | 1693 | 220.09 | 1913.09 | 2021-03-31 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Push dirt to build up edges along Dore Road. Skid 4 loads to Km5 on Hensen Rd East, walked in to float, floated to Hensen, walked to Mat pick up area. | 11 | F119-F134 | Hensen Road | 0 | 44295 |  | 56 | 44297 | CE-20210302-1 | Pushed snow on Hensen East and fix pot holes, back blade, etc. CE-160-2. |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6594KL-20210331-83rd Party Services16931693 | KABI LAKE FOREST PRODUCTS LTD6594KL-20210331-83rd Party Services16931693OEWT-PA16-Lem | [5 empty] | 1 | 1693 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6595 | KL-20210331-9 | 53511104 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-03-31 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | CE-20210224-3 appears to be a night shift LEM |  | Approved |  |  | Forward material from ditch on dore lake road to 6km. | 11 | F135-F149 | Dore Lake Road | 0 | 44295 |  | 56 | 44297 | CE-20210223-2 | Forward materials to patch road from 4km to 6km on Dore Road. CE-140-2. |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6595KL-20210331-93rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD6595KL-20210331-93rd Party Services2323.642323.64OEWT-PA16-Lem |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 2323.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6595 | KL-20210331-9 | 53511104 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-03-31 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | CE-20210224-3 appears to be a night shift LEM |  | Approved |  |  | Forward material from ditch on dore lake road to 6km. | 11 | F135-F149 | Dore Lake Road | 0 | 44295 |  | 56 | 44297 | CE-20210224-3 | Forward material from ditch on dore lake road to 6km. CE-141-2 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6595KL-20210331-93rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD6595KL-20210331-93rd Party Services2323.642323.64OEWT-PA16-Lem |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 2323.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6596 | KL-20210331-10 | 53511104 | Access | 0 | 3rd Party Services | 1 | 2251.83 | Each |  |  |  |  | 2251.83 | 292.7379 | 2544.5679 | 2021-03-31 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul aggregate to Hensen Road West. | 11 | F119-F134 | Hensen Road | 0 | 44295 |  | 56 | 44297 | CE-20210302-2 | Haul gravel to Hensen Road West. CE-160-3 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6596KL-20210331-103rd Party Services2251.832251.83 | KABI LAKE FOREST PRODUCTS LTD6596KL-20210331-103rd Party Services2251.832251.83OEWT-PA16-Lem |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 2251.83 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6596 | KL-20210331-10 | 53511104 | Access | 0 | 3rd Party Services | 1 | 2251.83 | Each |  |  |  |  | 2251.83 | 292.7379 | 2544.5679 | 2021-03-31 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul aggregate to Hensen Road West. | 11 | F119-F134 | Hensen Road | 0 | 44295 |  | 56 | 44297 | CE-20210303-2 | Haul aggregate to Hensen Road West. CE-161-2 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6596KL-20210331-103rd Party Services2251.832251.83 | KABI LAKE FOREST PRODUCTS LTD6596KL-20210331-103rd Party Services2251.832251.83OEWT-PA16-Lem |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 2251.83 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6596 | KL-20210331-10 | 53511104 | Access | 0 | 3rd Party Services | 1 | 3733.64 | Each |  |  |  |  | 3733.64 | 485.3732 | 4219.0132 | 2021-03-31 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Haul aggregate to Hensen Road West. | 11 | F119-F134 | Hensen Road | 0 | 44295 |  | 56 | 44297 | CE-20210304-2 | Haul aggregate to Hensen Road West. CE-162-3 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6596KL-20210331-103rd Party Services3733.643733.64 | KABI LAKE FOREST PRODUCTS LTD6596KL-20210331-103rd Party Services3733.643733.64OEWT-PA16-Lem |  | WF11-Gravel Hauling | WF11-Gravel Hauling |  | 1 | 1 | 3733.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6597 | KL-20210331-11 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1880 | Each |  |  |  |  | 1880 | 244.4 | 2124.4 | 2021-03-31 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Smoothed out ruts from 6.5km to 4km on Dore Lake and assisted stuck equipment. Assisted Kabi crew access, continued to remove boulders and fix holes near 8km hill. | 11 | F135-F149 | Dore Lake Road | 0 | 44295 |  | 57 | 44305 | CE-20210324-2 | Smoothed out ruts from 6.5km to 4km on Dore Lake and assisted stuck equipment. CE-178. |  |  |  | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6597KL-20210331-113rd Party Services18801880 | KABI LAKE FOREST PRODUCTS LTD6597KL-20210331-113rd Party Services18801880OEWT-PA16-Lem | [5 empty] | 1 | 1880 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6597 | KL-20210331-11 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2552.5 | Each |  |  |  |  | 2552.5 | 331.825 | 2884.325 | 2021-03-31 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Smoothed out ruts from 6.5km to 4km on Dore Lake and assisted stuck equipment. Assisted Kabi crew access, continued to remove boulders and fix holes near 8km hill. | 11 | F135-F149 | Dore Lake Road | 0 | 44295 |  | 57 | 44305 | CE-20210325-1 | Assisted Kabi crew access, continued to remove boulders and fix holes near 8km hill. CE-179. |  |  |  | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6597KL-20210331-113rd Party Services2552.52552.5 | KABI LAKE FOREST PRODUCTS LTD6597KL-20210331-113rd Party Services2552.52552.5OEWT-PA16-Lem | [5 empty] | 1 | 2552.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6598 | KL-20210331-12 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1244 | Each |  |  |  |  | 1244 | 161.72 | 1405.72 | 2021-03-31 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer clearing snow and maintaining road at Michipicoten Harbour #2. CE-162-4 | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44295 |  | 56 | 44297 | CE-20210304-3 | Dozer clearing snow and maintaining road at Michipicoten Harbour #2. CE-162-4 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6598KL-20210331-123rd Party Services12441244 | KABI LAKE FOREST PRODUCTS LTD6598KL-20210331-123rd Party Services12441244OEWT-PA16-Lem | [5 empty] | 1 | 1244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6600 | KL-20210331-13 | 53511111 | Access | 0 | 3rd Party Services | 1 | 779.32 | Each |  |  |  |  | 779.32 | 101.3116 | 880.6316 | 2021-03-31 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Plow road for log truck to access High Falls Road. CE-167-2 | 11 | F171-F176 | High Falls Road- 1 | 0 | 44295 |  | 56 | 44297 | CE-20210306-4 | Plow road for log truck to access High Falls Road. CE-167-2 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6600KL-20210331-133rd Party Services779.32779.32 | KABI LAKE FOREST PRODUCTS LTD6600KL-20210331-133rd Party Services779.32779.32OEWT-PA16-Lem | [5 empty] | 1 | 779.32 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6601 | KL-20210331-15 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 2736.36 | Each |  |  |  |  | 2736.36 | 355.7268 | 3092.0868 | 2021-03-31 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator to taper hill around pad tower, level pad, spread wood at bottom of pad. CE-180. | 11 | F135-F149 | Dore Lake Road | 0 | 44295 |  | 57 | 44309 | CE-20210325-2 | Excavator to taper hill around pad tower, level pad, spread wood at bottom of pad. CE-180. |  |  |  | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6601KL-20210331-153rd Party Services2736.362736.36 | KABI LAKE FOREST PRODUCTS LTD6601KL-20210331-153rd Party Services2736.362736.36OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2736.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6604 | KL-20210401-3 | 53541104 | Reclamation | 0 | 3rd Party Services | 1 | 3179.73 | Each |  |  |  |  | 3179.73 | 413.3649 | 3593.0949 | 2021-04-01 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Gravel Removal (Access) |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Reclaim Michipicoten Harbor Road #4 - CE-186 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 | 44298 |  | 57 | 44305 | CE-20210401-1 | Reclaim Roadway - CE-186 |  |  |  | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6604KL-20210401-33rd Party Services3179.733179.73 | KABI LAKE FOREST PRODUCTS LTD6604KL-20210401-33rd Party Services3179.733179.73OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 3179.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6605 | KL-20210401-4 | 53541104 | Reclamation | 0 | 3rd Party Services | 1 | 3166.41 | Each |  |  |  |  | 3166.41 | 411.6333 | 3578.0433 | 2021-04-01 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Gravel Removal (Access) |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Reclaim Dore Lake Road East - CE-187 | 11 | F135-F149 | Dore Lake Road | 0 | 44298 |  | 57 | 44305 | CE-20210401-2 | Reclaim Roadway - CE-187 |  |  |  | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6605KL-20210401-43rd Party Services3166.413166.41 | KABI LAKE FOREST PRODUCTS LTD6605KL-20210401-43rd Party Services3166.413166.41OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 3166.41 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6609 | KL-20210402-1 | 53541104 | Reclamation | 0 | 3rd Party Services | 1 | 3204.5 | Each |  |  |  |  | 3204.5 | 416.585 | 3621.085 | 2021-04-02 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Gravel Removal (Access) |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Reclaim Michipicoten Harbor Road 4 - CE-189 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 | 44298 |  | 56 | 44303 | CE-20210402-1 | Reclaimation - CE-189 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6609KL-20210402-13rd Party Services3204.53204.5 | KABI LAKE FOREST PRODUCTS LTD6609KL-20210402-13rd Party Services3204.53204.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 3204.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6613 | KL-20210403-2 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 2857 | Each |  |  |  |  | 2857 | 371.41 | 3228.41 | 2021-04-03 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Reclaim Road #4, take out bridge, haul two matts to front - CE191 | 11 | F156-F158 | Michipicoten Harbour Road -4 | 0 | 44298 |  | 56 | 44303 | CE-20210403-1 | Reclamation - CE-191 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6613KL-20210403-23rd Party Services28572857 | KABI LAKE FOREST PRODUCTS LTD6613KL-20210403-23rd Party Services28572857OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2857 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6614 | KL-20210403-3 | 53541105 | Reclamation | 0 | 3rd Party Services | 1 | 3228.5 | Each |  |  |  |  | 3228.5 | 419.705 | 3648.205 | 2021-04-03 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Erosion Cont Inst/Mon/Rem |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F136 to F137/ side by side used due to no pickup access | 11 | F-135 to F-149 | Dore Lake Road | 0 | 44298 |  | 56 | 44303 | CE-20210403-2 | Reclamation - CE-190 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6614KL-20210403-33rd Party Services3228.53228.5 | KABI LAKE FOREST PRODUCTS LTD6614KL-20210403-33rd Party Services3228.53228.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 3228.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6616 | KL-20210404-1 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 5269.45 | Each |  |  |  |  | 5269.45 | 685.0285 | 5954.4785 | 2021-04-04 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Reclamation on Dore Lake Road East - CE-193 | 11 | F-135 to F-149 | Dore Lake Road | 0 | 44298 |  | 56 | 44303 | CE-20210404-1 | Reclamation - CE-193 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6616KL-20210404-13rd Party Services5269.455269.45 | KABI LAKE FOREST PRODUCTS LTD6616KL-20210404-13rd Party Services5269.455269.45OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 5269.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6617 | KL-20210404-2 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 2857 | Each |  |  |  |  | 2857 | 371.41 | 3228.41 | 2021-04-04 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shovel working on Michipicoten Harbor Road 4 - CE-192 | 11 | F-156 to F-158 | Michipicoten Harbour Road -4 | 0 | 44298 |  | 56 | 44303 | CE-20210404-2 | Reclamation - CE-192 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6617KL-20210404-23rd Party Services28572857 | KABI LAKE FOREST PRODUCTS LTD6617KL-20210404-23rd Party Services28572857OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2857 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6618 | KL-20210404-3 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-04-04 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying ice build up on hills and leveling ruts from hwy 17 to Km 17 on hensen Roadfor float access - SSF-14277 | 11 | F119-F134 | Hensen Road | 0 | 44298 |  | 56 | 44303 | SSF-2021404-1 | Grade road - SSF-14277 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6618KL-20210404-33rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD6618KL-20210404-33rd Party Services2321.822321.82OEWT-PA16-Lem | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6624 | KL-20210405-4-R1 | 53541105 | Reclamation | 0 | 3rd Party Services | 1 | 6403.23 | Each |  |  |  |  | 6403.23 | 832.4199 | 7235.6499 | 2021-04-05 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | Erosion Cont Inst/Mon/Rem |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F137 to F138/ Cat 336 excavator tracking in from km 3 on Dore Road and starting @ F140. Chapman Reclamation of Dore lake Road East - CE-195. Excavator/pickup hours reduced for tracking time from signed ticket per Valard direction. Tracking time will be submitted on LEM KL-20210405-4-S1 | 11 | F-135 to F-149 | Dore lake Road | 0 | 44298 |  | 56 | 44329 | CE-20210405-1 | Reclamation - CE-195 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6624KL-20210405-4-R13rd Party Services6403.236403.23 | KABI LAKE FOREST PRODUCTS LTD6624KL-20210405-4-R13rd Party Services6403.236403.23OEWT-PA17-LEM |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 6403.23 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6626 | KL-20210405-6 | 53541105 | Reclamation | 0 | 3rd Party Services | 1 | 2857 | Each |  |  |  |  | 2857 | 371.41 | 3228.41 | 2021-04-05 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Erosion Cont Inst/Mon/Rem |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Reclamation of Michipicoten Harbor Road 4 - CE-194 | 11 | F-156 to F-158 | Michipicoten Harbour Road -4 | 0 | 44298 |  | 56 | 44303 | CE-20210405-2 | Reclamation - CE-194 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6626KL-20210405-63rd Party Services28572857 | KABI LAKE FOREST PRODUCTS LTD6626KL-20210405-63rd Party Services28572857OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2857 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6634 | KL-20210326-3 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1657.45 | Each |  |  |  |  | 1657.45 | 215.4685 | 1872.9185 | 2021-03-26 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grade from Office to Smoke Shop and Back Track- Michipicoten Harbor Road 1 - CE182 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44294 |  | 57 | 44306 | CE-20210326-2 | Grade from Office to Smoke Shop and Back Track- Michipicoten Harbor Road 1 - CE182 |  |  |  | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6634KL-20210326-33rd Party Services1657.451657.45 | KABI LAKE FOREST PRODUCTS LTD6634KL-20210326-33rd Party Services1657.451657.45OEWT-PA16-Lem | [5 empty] | 1 | 1657.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6635 | KL-20210326-4 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-03-26 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader Scarifying build up ice and leveling ruts from Hwy 17 to Km 17 on Hensen for float access - SSF-14276 | 11 | F119-F134 | Hensen Road | 0 | 44294 |  | 57 | 44306 | SSF-20210326-1 | Grader Scarifying build up ice and leveling ruts from Hwy 17 to Km 17 on Hensen for float access - SSF-14276 |  |  |  | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6635KL-20210326-43rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD6635KL-20210326-43rd Party Services2321.822321.82OEWT-PA16-Lem | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6638 | KL-20210327-1 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 2587.27 | Each |  |  |  |  | 2587.27 | 336.3451 | 2923.6151 | 2021-03-27 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Remove Corduroy and touch up road to Wes Specs.>Andrew supervised for reclaimation for tower 146 rd to watch Roland N didn't cause damage to tower or surrounding area structures -CE-183 | 11 | F135-F149 | Dore Lake Road | 0 | 44294 |  | 57 | 44306 | CE-20210327-1 | Remove Corduroy and touch up road to Wes Specs.>Andrew supervised for reclaimation for tower 146 rd to watch Roland N didn't cause damage to tower or surrounding area structures -CE-183 |  |  |  | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6638KL-20210327-13rd Party Services2587.272587.27 | KABI LAKE FOREST PRODUCTS LTD6638KL-20210327-13rd Party Services2587.272587.27OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2587.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6660 | KL-20210406-4 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 3107 | Each |  |  |  |  | 3107 | 403.91 | 3510.91 | 2021-04-06 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Reclamation Activites with Shovel - CE-196 | 11 | F155 | Michipicoten Harbour Road -3 | 0 | 44305 |  | 56 | 44305 | CE-20210406-1 | Reclamation Activites with Shovel - CE-196 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6660KL-20210406-43rd Party Services31073107 | KABI LAKE FOREST PRODUCTS LTD6660KL-20210406-43rd Party Services31073107OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 3107 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6661 | KL-20210406-5-R1 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 3340.18 | Each |  |  |  |  | 3340.18 | 434.2234 | 3774.4034 | 2021-04-06 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F138 to F141. Two hours of equipment/live out and pick up time removed from each excavator/operator from approved field ticket as per Valard direction. Those charges now listed on LEM KL-20210406-5-S1. | 11 | F135-F149 | Dore Lake Road | 0 |  |  | 56 | 44328 | CE-20210406-2 | Removal of corduroy from road, take road back to contour with land scape - CE-197 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6661KL-20210406-5-R13rd Party Services3340.183340.18 | KABI LAKE FOREST PRODUCTS LTD6661KL-20210406-5-R13rd Party Services3340.183340.18OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 3340.18 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6673 | KL-20210407-5 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 3107 | Each |  |  |  |  | 3107 | 403.91 | 3510.91 | 2021-04-07 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Reclamation Activities with shovel on Michipicoten Harbor Road 3 - CE-199 | 11 | F155 | Michipicoten Harbour Road -3 | 0 | 44305 |  | 56 | 44310 | CE-20210407-1 | Reclamation Activities with shovel on Michipicoten Harbor Road 3 - CE-199 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6673KL-20210407-53rd Party Services31073107 | KABI LAKE FOREST PRODUCTS LTD6673KL-20210407-53rd Party Services31073107OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 3107 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6675 | KL-20210407-7 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 2640.63 | Each |  |  |  |  | 2640.63 | 343.2819 | 2983.9119 | 2021-04-07 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Reclamation on Dore Lake Road East, removing corduroy from km 0-1 | 11 | F135-F149 | Dore Lake Road | 0 | 44305 |  | 56 | 44309 | CE-20210407-2 | Reclamation on Dore Lake Road East, removing corduroy from km 0-1 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6675KL-20210407-73rd Party Services2640.632640.63 | KABI LAKE FOREST PRODUCTS LTD6675KL-20210407-73rd Party Services2640.632640.63OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2640.63 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6678 | KL-20210408-3 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 2155.45 | Each |  |  |  |  | 2155.45 | 280.2085 | 2435.6585 | 2021-04-08 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Reclamation activities with shovel on Michipicoten Harbor Road 3 - CE-201 | 11 | F155 | Michipicoten Harbour Road -3 | 0 | 44305 |  | 56 | 44307 | CE-20210408-1 | Reclamation activities with shovel on Michipicoten Harbor Road 3 - CE-201 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6678KL-20210408-33rd Party Services2155.452155.45 | KABI LAKE FOREST PRODUCTS LTD6678KL-20210408-33rd Party Services2155.452155.45OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2155.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6679 | KL-20210408-4 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 4134.36 | Each |  |  |  |  | 4134.36 | 537.4668 | 4671.8268 | 2021-04-08 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Closure of last 400 m of Dore Lake Road East - CE-200 | 11 | F135-F149 | Dore Lake Road | 0 | 44305 |  | 56 | 44307 | CE-20210408-2 | Closure of last 400 m of Dore Lake Road East - CE-200 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6679KL-20210408-43rd Party Services4134.364134.36 | KABI LAKE FOREST PRODUCTS LTD6679KL-20210408-43rd Party Services4134.364134.36OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 4134.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6680 | KL-20210408-5-R1 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 2065.45 | Each |  |  |  |  | 2065.45 | 268.5085 | 2333.9585 | 2021-04-08 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Skagen 350 Excavator from Ajigami for Reclamation. Start Reclamation @F152. Supervisor and pickup hours from signed ticket removed per Valard direction, will be listed on KL-20210408-5-S1. | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44305 |  | 56 | 44329 | SSF-20210408-1 | Start Reclamation @F152 - SSF-14278-2 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6680KL-20210408-5-R13rd Party Services2065.452065.45 | KABI LAKE FOREST PRODUCTS LTD6680KL-20210408-5-R13rd Party Services2065.452065.45OEWT-PA17-LEM |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2065.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6684 | KL-20210409-4 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 1210.91 | Each |  |  |  |  | 1210.91 | 157.4183 | 1368.3283 | 2021-04-09 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Recamation activities on Michipicoten Harbor Road 3 with shovel - CE-202 | 11 | F155 | Michipicoten Harbour Road -3 | 0 | 44306 |  | 56 | 44309 | CE-20210409-1 | Recamation activities on Michipicoten Harbor Road 3 with shovel - CE-202 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6684KL-20210409-43rd Party Services1210.911210.91 | KABI LAKE FOREST PRODUCTS LTD6684KL-20210409-43rd Party Services1210.911210.91OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1210.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6685 | KL-20210409-5 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 1400.73 | Each |  |  |  |  | 1400.73 | 182.0949 | 1582.8249 | 2021-04-09 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Recamation activities on Dore Lake Road Km 6.5 - CE-203 | 11 | F135-F149 | Dore Lake Road | 0 | 44306 |  | 56 | 44309 | CE-20210409-2 | Recamation activities on Dore Lake Road Km 6.5 - CE-203 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6685KL-20210409-53rd Party Services1400.731400.73 | KABI LAKE FOREST PRODUCTS LTD6685KL-20210409-53rd Party Services1400.731400.73OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1400.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6686 | KL-20210409-6 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 1290.91 | Each |  |  |  |  | 1290.91 | 167.8183 | 1458.7283 | 2021-04-09 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @F152 - SSF-14278 | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44306 |  | 56 | 44309 | SSF-20210409-1 | Continue Reclamation @F152 - SSF-14278 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6686KL-20210409-63rd Party Services1290.911290.91 | KABI LAKE FOREST PRODUCTS LTD6686KL-20210409-63rd Party Services1290.911290.91OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1290.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6694 | KL-20210413-1-R1 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-04-13 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator Continue Reclamation at structure 153 and 154 - SSF-14283. ATV listed on signed ticket removed per Valard direction. Will be listed on LEM KL-20210413-1-S1. | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44308 |  | 57 | 44324 | SSF-20210413-1-R1 | Excavator Continue Reclamation at structure 153 and 154 - SSF-14283. ATV listed on signed ticket removed per Valard direction. Will be listed on LEM KL-20210413-1-S1. |  |  |  | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6694KL-20210413-1-R13rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD6694KL-20210413-1-R13rd Party Services2581.822581.82OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6695 | KL-20210413-2 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 3204.5 | Each |  |  |  |  | 3204.5 | 416.585 | 3621.085 | 2021-04-13 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Reclamation of Michipicoten Harbor Roads near F-153, Alfred used the truck/trailer to haul culvert on road 3 near F-155 with the 300 to haul it to dore sand pit - CE-210 | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44308 |  | 56 | 44309 | CE-20210413-1 | Reclamation of Michipicoten Harbor Road near F-155. CE-207 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6695KL-20210413-23rd Party Services3204.53204.5 | KABI LAKE FOREST PRODUCTS LTD6695KL-20210413-23rd Party Services3204.53204.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 3204.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6696 | KL-20210413-3 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 2799.82 | Each |  |  |  |  | 2799.82 | 363.9766 | 3163.7966 | 2021-04-13 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Reclamation Activities on Dore Lake Road at F-146. - CE-208 | 11 | F135-F149 | Dore Lake Road | 0 | 44308 |  | 56 | 44309 | CE-20210413-2 | Reclamation Activities on Dore Lake Road at F-146. - CE-208 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6696KL-20210413-33rd Party Services2799.822799.82 | KABI LAKE FOREST PRODUCTS LTD6696KL-20210413-33rd Party Services2799.822799.82OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2799.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6697 | KL-20210413-4 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 2919.82 | Each |  |  |  |  | 2919.82 | 379.5766 | 3299.3966 | 2021-04-13 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Skid wood to the 6.5 Km Dore Lake Road - CE-211 | 11 | F135-F149 | Dore Lake Road | 0 | 44308 |  | 56 | 44309 | CE-20210413-3 | Skid wood to the 6.5 Km Dore Lake Road - CE-211 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6697KL-20210413-43rd Party Services2919.822919.82 | KABI LAKE FOREST PRODUCTS LTD6697KL-20210413-43rd Party Services2919.822919.82OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2919.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6701 | KL-20210412-3 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 2065.45 | Each |  |  |  |  | 2065.45 | 268.5085 | 2333.9585 | 2021-04-12 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continue reclamation at structure 152. SSF-14282 | 11 | F-152 to F-154 | Michipicoten Harbour Road -2 | 0 | 44308 |  | 56 | 44309 | SSF-20210412-1 | Excavator continue reclamation at structure 152. SSF-14282 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6701KL-20210412-33rd Party Services2065.452065.45 | KABI LAKE FOREST PRODUCTS LTD6701KL-20210412-33rd Party Services2065.452065.45OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2065.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6702 | KL-20210412-4 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 1391.73 | Each |  |  |  |  | 1391.73 | 180.9249 | 1572.6549 | 2021-04-12 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Reclamation on Dore Lake Road - CE-206 | 11 | F135-F149 | Dore Lake Road | 0 | 44308 |  | 56 | 44309 | CE-20210412-1 | Reclamation on Dore Lake Road - CE-206 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6702KL-20210412-43rd Party Services1391.731391.73 | KABI LAKE FOREST PRODUCTS LTD6702KL-20210412-43rd Party Services1391.731391.73OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1391.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6703 | KL-20210412-5-R1 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 1328.5 | Each |  |  |  |  | 1328.5 | 172.705 | 1501.205 | 2021-04-12 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Reclamation/Hand falling topping trees for tree length truck - CE-205 /Haul Wood to Dump from Michipicoten Harbor Road 3 - CE-204 | 11 | F155 | Michipicoten Harbour Road -3 | 0 | 44308 |  | 56 | 44324 | CE-20210412-2-R1 | Reclamation on Michipicoten Harbor Road 3/ Hand falling, topping trees for tree length truck - small tools charged to cover cost of chainsaw fuel and chain - CE-205 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6703KL-20210412-5-R13rd Party Services1328.51328.5 | KABI LAKE FOREST PRODUCTS LTD6703KL-20210412-5-R13rd Party Services1328.51328.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1328.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6754 | KL-20210414-3 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 3342 | Each |  |  |  |  | 3342 | 434.46 | 3776.46 | 2021-04-14 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Reclamation of MHR's 2 and 3 ,Alfred used truck and trailer to haul the culvert that Rolly loaded with the 300 to haul to the dore lake sand pit - CE210 | 11 |  | Michipicoten Harbour Road -3 | 0 | 44309 |  | 56 | 44312 | CE-20210414-1 | Reclamation of MHR's 2 and 3 ,Alfred used truck and trailer to haul the culvert that Rolly loaded with the 300 to haul to the dore lake sand pit - CE210 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6754KL-20210414-33rd Party Services33423342 | KABI LAKE FOREST PRODUCTS LTD6754KL-20210414-33rd Party Services33423342OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 3342 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6755 | KL-20210414-4 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 5929.82 | Each |  |  |  |  | 5929.82 | 770.8766 | 6700.6966 | 2021-04-14 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F151 and F150. Reclamation on Dore Lake Road with shovel and Skidder- Walked the 350 from Dore Lake to MHR 1 | 11 | F135-F149 | Dore Lake Road | 0 | 44309 |  | 56 | 44312 | CE-20210414-2 | Reclamation on Dore Lake Road with shovel and Skidder- Walked the 350 from Dore Lake to MHR 1 - CE-212 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6755KL-20210414-43rd Party Services5929.825929.82 | KABI LAKE FOREST PRODUCTS LTD6755KL-20210414-43rd Party Services5929.825929.82OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 5929.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6756 | KL-20210414-5-R1 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 2920.5 | Each |  |  |  |  | 2920.5 | 379.665 | 3300.165 | 2021-04-14 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator Continue Reclamation at structure 154 - SSF-14284. Side-by-side listed on approved ticket removed from LEM per Valard direction. Now listed on LEM KL-20210414-5-S1. | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44309 |  | 56 | 44327 | SSF-20210414-1 | Excavator Continue Reclamation at structure 154 - SSF-14284. Side-by-side listed on approved ticket removed from LEM per Valard direction. Now listed on LEM KL-20210414-5-S1. |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6756KL-20210414-5-R13rd Party Services2920.52920.5 | KABI LAKE FOREST PRODUCTS LTD6756KL-20210414-5-R13rd Party Services2920.52920.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2920.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6779 | KL-20210412-7 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 3063.5 | Each |  |  |  |  | 3063.5 | 398.255 | 3461.755 | 2021-04-12 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Reclamation on Michipicoten Harbor Road 3 | 11 | F-155 | Michipicoten Harbour Road -3 | 0 |  |  | 56 | 44324 | CE-20210412-4 | Reclamation on Michipicoten Harbor Road 3 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6779KL-20210412-73rd Party Services3063.53063.5 | KABI LAKE FOREST PRODUCTS LTD6779KL-20210412-73rd Party Services3063.53063.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 3063.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6781 | KL-20210415-2 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 3304.91 | Each |  |  |  |  | 3304.91 | 429.6383 | 3734.5483 | 2021-04-15 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F151 and F150 (Revised ). Removing wood, re-contouring road area. | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44317 |  | 56 | 44319 | CE-20210415-1 | Reclamation at F-151. CE-214 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6781KL-20210415-23rd Party Services3304.913304.91 | KABI LAKE FOREST PRODUCTS LTD6781KL-20210415-23rd Party Services3304.913304.91OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 3304.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6781 | KL-20210415-2 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 2916.41 | Each |  |  |  |  | 2916.41 | 379.1333 | 3295.5433 | 2021-04-15 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @ F151 and F150 (Revised ). Removing wood, re-contouring road area. | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44317 |  | 56 | 44319 | CE-20210415-2 | Reclamation on MHR #1- CE-215 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6781KL-20210415-23rd Party Services2916.412916.41 | KABI LAKE FOREST PRODUCTS LTD6781KL-20210415-23rd Party Services2916.412916.41OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2916.41 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6783 | KL-20210415-4 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 2065.45 | Each |  |  |  |  | 2065.45 | 268.5085 | 2333.9585 | 2021-04-15 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator Continue Reclamation at Structure 154 | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44317 |  | 56 | 44319 | SSF-20210415-1 | Reclamation - SSF-14285 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6783KL-20210415-43rd Party Services2065.452065.45 | KABI LAKE FOREST PRODUCTS LTD6783KL-20210415-43rd Party Services2065.452065.45OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2065.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6798 | KL-20210416-1 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 2920.5 | Each |  |  |  |  | 2920.5 | 379.665 | 3300.165 | 2021-04-16 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator Continue Reclamation at Structure 154 ( Second Revision ). SSF-14286 | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44318 |  | 56 | 44321 | SSF-20210416-1 | Reclamation - SSF-14286 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6798KL-20210416-13rd Party Services2920.52920.5 | KABI LAKE FOREST PRODUCTS LTD6798KL-20210416-13rd Party Services2920.52920.5OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2920.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6799 | KL-20210416-2 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 762.18 | Each |  |  |  |  | 762.18 | 99.0834 | 861.2634 | 2021-04-16 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator working on Reclamation @F142 and F143. Skidder removing WC-12150 | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | CE-20210416-1 | Reclamation - CE-217 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6799KL-20210416-23rd Party Services762.18762.18 | KABI LAKE FOREST PRODUCTS LTD6799KL-20210416-23rd Party Services762.18762.18OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 762.18 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6800 | KL-20210416-3 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 3336.82 | Each |  |  |  |  | 3336.82 | 433.7866 | 3770.6066 | 2021-04-16 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Reclamation @F150 and F151 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44318 |  | 56 | 44321 | CE-20210416-2 | Reclamation - CE-216 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6800KL-20210416-33rd Party Services3336.823336.82 | KABI LAKE FOREST PRODUCTS LTD6800KL-20210416-33rd Party Services3336.823336.82OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 3336.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6804 | KL-20210417-4 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 1032.73 | Each |  |  |  |  | 1032.73 | 134.2549 | 1166.9849 | 2021-04-17 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator removing Rig Mats @ WC 12423.00 on F154 Access - SSF-14287-2 / Excavator Finish Reclamation @ F154 Access - SSF-14287 | 11 | F152-F154 | Michipicoten Harbour Road -2 | 0 | 44318 |  | 56 | 44321 | SSF-20210417-2 | Reclamation - SSF-14287 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6804KL-20210417-43rd Party Services1032.731032.73 | KABI LAKE FOREST PRODUCTS LTD6804KL-20210417-43rd Party Services1032.731032.73OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1032.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6806 | KL-20210417-6 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 801.45 | Each |  |  |  |  | 801.45 | 104.1885 | 905.6385 | 2021-04-17 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Rolly Walked Skidder to Km 8 on Dore Lake Road ( 53541105) Walking out D6 Dozer from Km 5 on Dore lake Road (53511107) Prepping for Reclamation work - CE-219-2 | 11 | F135-F149 | Dore Lake Road | 0 | 44318 |  | 56 | 44321 | CE-20210417-2 | Prep for reclamation work. |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6806KL-20210417-63rd Party Services801.45801.45 | KABI LAKE FOREST PRODUCTS LTD6806KL-20210417-63rd Party Services801.45801.45OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 801.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6807 | KL-20210417-7 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 1726.91 | Each |  |  |  |  | 1726.91 | 224.4983 | 1951.4083 | 2021-04-17 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Reclamation Activities on Michipicoten Harbor Road 1 - CE-218 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44318 |  | 56 | 44321 | CE-20210417-3 | Reclamation - CE-218 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6807KL-20210417-73rd Party Services1726.911726.91 | KABI LAKE FOREST PRODUCTS LTD6807KL-20210417-73rd Party Services1726.911726.91OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1726.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6808 | KL-20210418-1 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 3115.32 | Each |  |  |  |  | 3115.32 | 404.9916 | 3520.3116 | 2021-04-18 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator working on reclamation @F144 and F145 ( Second revision). Chapman access reclamation at 7.5Km. | 11 | F135-F149 | Dore Lake Road | 0 | 44322 |  | 56 | 44323 | CE-20210418-1 | Reclamation - CE-221 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6808KL-20210418-13rd Party Services3115.323115.32 | KABI LAKE FOREST PRODUCTS LTD6808KL-20210418-13rd Party Services3115.323115.32OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 3115.32 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6808 | KL-20210418-1 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 2421.82 | Each |  |  |  |  | 2421.82 | 314.8366 | 2736.6566 | 2021-04-18 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator working on reclamation @F144 and F145 ( Second revision). Chapman access reclamation at 7.5Km. | 11 | F135-F149 | Dore Lake Road | 0 | 44322 |  | 56 | 44323 | CE-20210418-2 | Reclamation - CE-220 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6808KL-20210418-13rd Party Services2421.822421.82 | KABI LAKE FOREST PRODUCTS LTD6808KL-20210418-13rd Party Services2421.822421.82OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2421.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6810 | KL-20210419-1 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 2429.64 | Each |  |  |  |  | 2429.64 | 315.8532 | 2745.4932 | 2021-04-19 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 excavator working on reclamation on access to F145 (revised). Chapman removing access material from 7km to 4km Dore Lake Road. | 11 | F135-F149 | Dore Lake Road | 0 | 44322 |  | 57 | 44323 | CE-20210419-1 | Reclamation - CE-223 |  |  |  | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6810KL-20210419-13rd Party Services2429.642429.64 | KABI LAKE FOREST PRODUCTS LTD6810KL-20210419-13rd Party Services2429.642429.64OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2429.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6810 | KL-20210419-1 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 2936.96 | Each |  |  |  |  | 2936.96 | 381.8048 | 3318.7648 | 2021-04-19 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 excavator working on reclamation on access to F145 (revised). Chapman removing access material from 7km to 4km Dore Lake Road. | 11 | F135-F149 | Dore Lake Road | 0 | 44322 |  | 57 | 44323 | ce-20210419-2 | Reclamation - CE-222 |  |  |  | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6810KL-20210419-13rd Party Services2936.962936.96 | KABI LAKE FOREST PRODUCTS LTD6810KL-20210419-13rd Party Services2936.962936.96OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 2936.96 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6811 | KL-20210420-1 | 53541101 | Reclamation | 0 | 3rd Party Services | 1 | 1945.27 | Each |  |  |  |  | 1945.27 | 252.8851 | 2198.1551 | 2021-04-20 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Glenda Pevie | Access Re-cont | Access Re-cont | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Cat 336 Excavator completing reclamation on access to F145 ( revised as per Valard ) | 11 | F135-F149 | Dore lake Road | 0 | 44322 |  | 57 | 44323 | CE-20210420-1 | Reclamation - CE-224 |  |  |  | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6811KL-20210420-13rd Party Services1945.271945.27 | KABI LAKE FOREST PRODUCTS LTD6811KL-20210420-13rd Party Services1945.271945.27OEWT-PA16-Lem |  | WF11-Reclamation | WF11-Reclamation |  | 1 | 1 | 1945.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6819 | KL-20210423-1 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2639 | Each |  |  |  |  | 2639 | 343.07 | 2982.07 | 2021-04-23 | 0 | OEWT-PA16-Lem | 44330 | 52 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator unclogged cross drain culverts and repaired small washouts on AE1 access road from Anjigami bridge to F213/216 - MC-13099 | 11 | F150-F151 | Michipicoten Harbour Road -1 | 0 | 44324 |  | 57 | 44324 | MC-20210423-1 | Excavator unclogged cross drain culverts and repaired small washouts on AE1 access road from Anjigami bridge to F213/216 - MC-13099 |  |  |  | Wesley Seminowich | 11 | KABI LAKE FOREST PRODUCTS LTD6819KL-20210423-13rd Party Services26392639 | KABI LAKE FOREST PRODUCTS LTD6819KL-20210423-13rd Party Services26392639OEWT-PA16-Lem | [5 empty] | 1 | 2639 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6910 | KL-20210513-2 | 53511112 | Access | 0 | 3rd Party Services | 1 | 774.55 | Each |  |  |  |  | 774.55 | 100.6915 | 875.2415 | 2021-05-13 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float 350 John Deere Excavator to F175 for working on road maintenance levelling ruts and shaping hills F171 to F173 | 11 | F171-F176 | High Falls Road-1 | 0 | 44337 |  | 56 | 44342 | SSF-20210513-2 | Road maintenance - SSF-14290 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6910KL-20210513-23rd Party Services774.55774.55 | KABI LAKE FOREST PRODUCTS LTD6910KL-20210513-23rd Party Services774.55774.55OEWT-PA17-LEM | [5 empty] | 1 | 774.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6930 | KL-20210517-4 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-05-17 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish grading and shaping of Hensen to Km 17 - SSF-14294 | 11 | F119-F134 | Hensen Road | 0 | 44337 |  | 56 | 44342 | SSF-20210517-1 | Grading Hensen Road - SSF-14294 |  |  |  | Mandy Sandhu | 11 | KABI LAKE FOREST PRODUCTS LTD6930KL-20210517-43rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD6930KL-20210517-43rd Party Services2321.822321.82OEWT-PA17-LEM | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6955 | KL-20210519-6 | 53510812 | Access | 0 | 3rd Party Services | 1 | 2086.72 | Each |  |  |  |  | 2086.72 | 271.2736 | 2357.9936 | 2021-05-19 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair Road from 48 Km Down - CR-101451 | 11 | F119-F134 | Hensen Road | 0 | 44345 |  | 14 | 44352 | CR-20210519-1 | Repair Road from 48 Km Down |  |  |  | William Ouimet | 08 | KABI LAKE FOREST PRODUCTS LTD6955KL-20210519-63rd Party Services2086.722086.72 | KABI LAKE FOREST PRODUCTS LTD6955KL-20210519-63rd Party Services2086.722086.72OEWT-PA17-LEM | [5 empty] | 1 | 2086.72 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6964 | KL-20210520-6 | 53511112 | Access | 0 | 3rd Party Services | 1 | 4000 | Each |  |  |  |  | 4000 | 520 | 4520 | 2021-05-20 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Clean up ditches along 47-48, dozer blading road filling in ruta, swales and replace culvert, worked on ditches and road leading to F117 - CR-101452 | 11 | F119-F134 | Hensen Road | 0 | 44345 |  | 14 | 44351 | CR-20210520-1 | Clean up ditches along 47-48, dozer blading road filling in ruts, swales and replace culvert, worked on ditches and road leading to F117 - CR-101452 |  |  |  | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD6964KL-20210520-63rd Party Services40004000 | KABI LAKE FOREST PRODUCTS LTD6964KL-20210520-63rd Party Services40004000OEWT-PA17-LEM | [5 empty] | 1 | 4000 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6969 | KL-20210521-4 | 53511112 | Access | 0 | 3rd Party Services | 1 | 4777.05 | Each |  |  |  |  | 4777.05 | 621.0165 | 5398.0665 | 2021-05-21 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Repair ruts and swales, ditching where need - move lego blocks to protect f120 structure guide wires - CR-101453 | 11 | F119-F134 | Hensen Road | 0 | 44345 |  | 14 | 44351 | CR-20210521-1 | Repair ruts and swales, ditching where need - move lego blocks to protect f120 structure guide wires - CR-101453 |  |  |  | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD6969KL-20210521-43rd Party Services4777.054777.05 | KABI LAKE FOREST PRODUCTS LTD6969KL-20210521-43rd Party Services4777.054777.05OEWT-PA17-LEM | [5 empty] | 1 | 4777.05 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6972 | KL-20210522-3 | 53511112 | Access | 0 | 3rd Party Services | 1 | 4026.27 | Each |  |  |  |  | 4026.27 | 523.4151 | 4549.6851 | 2021-05-22 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish ditching to Km 16, level ruts on Hensen East, clean up road from Km 17 to F117 spur and spread material from side of road - CR-101454 | 11 | F119-F134 | Hensen Road | 0 | 44345 |  | 14 | 44351 | CR-20210522-1 | Finish ditching to Km 16, level ruts on Hensen East, clean up road from Km 17 to F117 spur and spread material from side of road - CR-101454 |  |  |  | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD6972KL-20210522-33rd Party Services4026.274026.27 | KABI LAKE FOREST PRODUCTS LTD6972KL-20210522-33rd Party Services4026.274026.27OEWT-PA17-LEM | [5 empty] | 1 | 4026.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 6979 | KL-20210523-5 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2300.82 | Each |  |  |  |  | 2300.82 | 299.1066 | 2599.9266 | 2021-05-23 | 0 | OEWT-PA17-LEM | 44357 | 55 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Complete ditching, clean up ruts on Hensen Road east entrence, clean up road from Km 17 west to spur road at F117-Shutdown at noon by Valard poor conditions. | 11 | F119-F134 | Hensen Road | 0 | 44345 |  | 14 | 44351 | CR-20210523-1 | Complete ditching, clean up ruts on Hensen Road east entrence, clean up road from Km 17 west to spur road at F117-Shutdown at noon by Valard poor conditions. |  |  |  | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD6979KL-20210523-53rd Party Services2300.822300.82 | KABI LAKE FOREST PRODUCTS LTD6979KL-20210523-53rd Party Services2300.822300.82OEWT-PA17-LEM | [5 empty] | 1 | 2300.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7021 | KL-20210614-4 | 53511112 | Access | 0 | 3rd Party Services | 1 | 1265.41 | Each |  |  |  |  | 1265.41 | 164.5033 | 1429.9133 | 2021-06-14 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting shaping & drainage access to F-199. SSF-14295 | 11 | F203-F211 | High Falls Road - 9 | 0 | 44363 |  | 50 | 44363 | SSF-20210614-1 | Excav drainage and shaping to F199 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7021KL-20210614-43rd Party Services1265.411265.41 | KABI LAKE FOREST PRODUCTS LTD7021KL-20210614-43rd Party Services1265.411265.41OEWT-PA18-Lem | [5 empty] | 1 | 1265.41 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7022 | KL-20210614-5 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2065.45 | Each |  |  |  |  | 2065.45 | 268.5085 | 2333.9585 |  | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator beginning to level ruts and shape road from F229-F227 | 11 | F212-F214 | Michipicoten Road - 1 | 0 | 44363 |  | 50 | 44363 | MC-20210614-1 | Ex level and shape road |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7022KL-20210614-53rd Party Services2065.452065.45 | KABI LAKE FOREST PRODUCTS LTD7022KL-20210614-53rd Party Services2065.452065.45OEWT-PA18-Lem | [5 empty] | 1 | 2065.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7032 | KL-20210615-7 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-06-15 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator sontinue shaping and working drainage on access to F-199 - SSF-14296 | 11 | F203-F211 | High Falls Road - 9 | 0 | 44365 |  | 50 | 44366 | SSF-20210615-1 | shape and work on drainage at F199 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7032KL-20210615-73rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7032KL-20210615-73rd Party Services2581.822581.82OEWT-PA18-Lem | [5 empty] | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7033 | KL-20210615-8 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2452.73 | Each |  |  |  |  | 2452.73 | 318.8549 | 2771.5849 | 2021-06-15 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and shaping road at F225 and F226 access, MC-13102 | 11 | F212-F214 | Michipicoten Road - 1 | 0 | 44365 |  | 50 | 44366 | MC-20210515-1 | Excavator repair access at F225-F226 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7033KL-20210615-83rd Party Services2452.732452.73 | KABI LAKE FOREST PRODUCTS LTD7033KL-20210615-83rd Party Services2452.732452.73OEWT-PA18-Lem | [5 empty] | 1 | 2452.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7036 | KL-20210616-3 | 53511112 | Access | 0 | 3rd Party Services | 1 | 1807.27 | Each |  |  |  |  | 1807.27 | 234.9451 | 2042.2151 | 2021-06-16 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fixing ruts and improving drainage of access from F-201 to F-202. SSF-14298 | 11 | F203-F211 | High Falls Road 9 | 0 | 44368 |  | 50 | 44369 | SSF-20210616-2 | Fixing ruts and improving drainage of access from F-201 to F-202. SSF-14298 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7036KL-20210616-33rd Party Services1807.271807.27 | KABI LAKE FOREST PRODUCTS LTD7036KL-20210616-33rd Party Services1807.271807.27OEWT-PA18-Lem | [5 empty] | 1 | 1807.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7037 | KL-20210616-4 | 53511112 | Access | 0 | 3rd Party Services | 1 | 1032.73 | Each |  |  |  |  | 1032.73 | 134.2549 | 1166.9849 | 2021-06-16 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage for Access Road @ F-225 & F-226. MC-13103 | 11 | F212-F214 | Michipicoten Road 1 | 0 | 44368 |  | 50 | 44369 | MC-20210616-1 | Excavator working on drainage for Access Road @ F-225 & F-226. MC-13103 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7037KL-20210616-43rd Party Services1032.731032.73 | KABI LAKE FOREST PRODUCTS LTD7037KL-20210616-43rd Party Services1032.731032.73OEWT-PA18-Lem | [5 empty] | 1 | 1032.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7038 | KL-20210617-1 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-06-17 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fixing ruts and improving drainage of access from F-202 to F-204. SSF-14299 | 11 | F203-F211 | High Falls Road 9 | 0 | 44368 |  | 50 | 44369 | SSF-20210617-1 | Fixing ruts and improving drainage of access from F-202 to F-204. SSF-14299 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7038KL-20210617-13rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7038KL-20210617-13rd Party Services2581.822581.82OEWT-PA18-Lem | [5 empty] | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7039 | KL-20210617-2 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-06-17 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage for Access Road @ F-224. MC-13104 | 11 | F218-F227 | Michipicoten Road | 0 | 44368 |  | 50 | 44369 | MC-20210617-1 | Excavator working on drainage for Access Road @ F-224. MC-13104 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7039KL-20210617-23rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7039KL-20210617-23rd Party Services2323.642323.64OEWT-PA18-Lem | [5 empty] | 1 | 2323.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7040 | KL-20210618-1 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2065.45 | Each |  |  |  |  | 2065.45 | 268.5085 | 2333.9585 | 2021-06-18 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator repairing road and improving drainage for Access Road to F-224/F-223. MC-13105 | 11 |  | Michipicoten Road | 0 | 44368 |  | 50 | 44369 | MC-20210618-1 | Excavator repairing road and improving drainage for Access Road to F-224/F-223. MC-13105 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7040KL-20210618-13rd Party Services2065.452065.45 | KABI LAKE FOREST PRODUCTS LTD7040KL-20210618-13rd Party Services2065.452065.45OEWT-PA18-Lem | [5 empty] | 1 | 2065.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7042 | KL-20210619-1 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-06-19 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fix ruts and improve drainage for road maintenance of access to F-209. SSF-14301 | 11 | F203-F211 | High Falls Road 9 | 0 | 44366 |  | 50 | 44369 | SSF-20210619-1 | Fix ruts and improve drainage for road maintenance of access to F-209. SSF-14301 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7042KL-20210619-13rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7042KL-20210619-13rd Party Services2581.822581.82OEWT-PA18-Lem | [5 empty] | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7043 | KL-20210619-2 | 53511112 | Access | 0 | 3rd Party Services | 1 | 1549.09 | Each |  |  |  |  | 1549.09 | 201.3817 | 1750.4717 | 2021-06-19 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator repairing road and improving drainage for Access to F-221 | 11 | F218-F227 | Michipicoten Road 3 | 0 | 44368 |  | 50 | 44369 | MC-20210619-1 | Excavator repairing road and improving drainage for Access to F-221 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7043KL-20210619-23rd Party Services1549.091549.09 | KABI LAKE FOREST PRODUCTS LTD7043KL-20210619-23rd Party Services1549.091549.09OEWT-PA18-Lem | [5 empty] | 1 | 1549.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7045 | KL-20210620-2 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2452.73 | Each |  |  |  |  | 2452.73 | 318.8549 | 2771.5849 | 2021-06-20 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator reapiring road and upgrading drainage channnels for access to F220 MCC 13107 | 11 | F218-F227 | Michipicoten Road 3 | 0 | 44369 |  | 50 | 44369 | MC-20210620-1 | Excavator reapiring road and upgrading drainage channnels for access to F220 MCC 13107 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7045KL-20210620-23rd Party Services2452.732452.73 | KABI LAKE FOREST PRODUCTS LTD7045KL-20210620-23rd Party Services2452.732452.73OEWT-PA18-Lem | [5 empty] | 1 | 2452.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7046 | KL-20210620-3 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-06-20 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Fix ruts and improve drainage for road maintenanace of access to F211 SSF-14302 | 11 |  | High falls | 0 | 44369 |  | 50 | 44369 | SSF-20210620-1 | Fix ruts and improve drainage for road maintenanace of access to F211 SSF-14302 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7046KL-20210620-33rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7046KL-20210620-33rd Party Services2581.822581.82OEWT-PA18-Lem | [5 empty] | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7059 | KL-20210621-2 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-06-21 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator repairing road and improving drainage for Access to F-218. MC-13108 | 11 | F218-F227 | Michipicoten Road - 3 | 0 | 44370 |  | 50 | 44371 | MC-20210621-1 | Excavator repairing road and improving drainage for Access to F-218. MC-13108 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7059KL-20210621-23rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7059KL-20210621-23rd Party Services2323.642323.64OEWT-PA18-Lem | [5 empty] | 1 | 2323.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7060 | KL-20210622-1 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-06-22 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator fixing and maintaining road from F-211 to F-210 working its way out. SSF-14303 | 11 | F203-F211 | High Falls Road - 9 | 0 | 44371 |  | 50 | 44371 | SSF-20210622-1 | Excavator fixing and maintaining road from F-211 to F-210 working its way out. SSF-14303 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7060KL-20210622-13rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7060KL-20210622-13rd Party Services2581.822581.82OEWT-PA18-Lem | [5 empty] | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7061 | KL-20210622-2 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-06-22 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road maintenance working out from F-218. MC-13109 | 11 | F218-F227 | Michipicoten Road - 3 | 0 | 44371 |  | 50 | 44371 | MC-20210622-1 | Road maintenance working out from F-218. MC-13109 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7061KL-20210622-23rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7061KL-20210622-23rd Party Services2323.642323.64OEWT-PA18-Lem | [5 empty] | 1 | 2323.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7062 | KL-20210623-1 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2194.55 | Each |  |  |  |  | 2194.55 | 285.2915 | 2479.8415 | 2021-06-23 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator fixing and maintaining road from F-210 to F-208 working its way out. SSF-14304 | 11 | F203-F211 | High Falls Road - 9 | 0 | 44372 |  | 50 | 44372 | SSF-20210623-1 | Excavator fixing and maintaining road from F-210 to F-208 working its way out. SSF-14304 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7062KL-20210623-13rd Party Services2194.552194.55 | KABI LAKE FOREST PRODUCTS LTD7062KL-20210623-13rd Party Services2194.552194.55OEWT-PA18-Lem | [5 empty] | 1 | 2194.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7064 | KL-20210623-3 | 53511112 | Access | 0 | 3rd Party Services | 1 | 1290.91 | Each |  |  |  |  | 1290.91 | 167.8183 | 1458.7283 | 2021-06-23 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Road maintenance working out from F-223. MC-13110 | 11 | F218-F227 | Michipicoten Road - 3 | 0 | 44372 |  | 50 | 44370 | MC-20210623-1 | Road maintenance working out from F-223. MC-13110 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7064KL-20210623-33rd Party Services1290.911290.91 | KABI LAKE FOREST PRODUCTS LTD7064KL-20210623-33rd Party Services1290.911290.91OEWT-PA18-Lem | [5 empty] | 1 | 1290.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7085 | KL-20210624-1 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-06-24 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing out from F-223 & starting @ F-215 main access road to ROW. MC-13111 | 11 | F218-F227 | Michipicoten Road - 3 | 0 | 44376 |  | 50 | 44378 | MC-20210624-1 | Excavator finishing out from F-223 & starting @ F-215 main access road to ROW. MC-13111 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7085KL-20210624-13rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7085KL-20210624-13rd Party Services2581.822581.82OEWT-PA18-Lem | [5 empty] | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7086 | KL-20210624-2 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-06-24 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing road maintenance from F-208 to F-203. SSF-14306 | 11 | F203-F211 | High Falls Road - 9 | 0 | 44375 |  | 50 | 44378 | SSF-20210624-1 | Excavator finishing road maintenance from F-208 to F-203. SSF-14306 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7086KL-20210624-23rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7086KL-20210624-23rd Party Services2323.642323.64OEWT-PA18-Lem | [5 empty] | 1 | 2323.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7088 | KL-20210625-1 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2452.73 | Each |  |  |  |  | 2452.73 | 318.8549 | 2771.5849 | 2021-06-25 | 0 | OEWT-PA18-Lem | 44379 | 58 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continue to level ruts & shape main access road to F-215/F-216. MC-13112 | 11 | F215-F217 | Michipicoten Road - 2 | 0 | 44376 |  | 50 | 44378 | MC-20210625-1 | Excavator continue to level ruts & shape main access road to F-215/F-216. MC-13112 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7088KL-20210625-13rd Party Services2452.732452.73 | KABI LAKE FOREST PRODUCTS LTD7088KL-20210625-13rd Party Services2452.732452.73OEWT-PA18-Lem | [5 empty] | 1 | 2452.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7193 | KL-20210804-2 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2463 | Each |  |  |  |  | 2463 | 320.19 | 2783.19 | 2021-08-04 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run Grader from High Falls & Start grading sections on Hensen Road from hwy to 6Km. SSF-14318 | 11 | F118-F127 | Hensen Road | 0 | 44420 |  | 14 | 44421 | SSF-20210804-1 | Grading sections of Hensen from Hwy to 6Km |  |  |  | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD7193KL-20210804-23rd Party Services24632463 | KABI LAKE FOREST PRODUCTS LTD7193KL-20210804-23rd Party Services24632463OEWT-PA20-Lem | [5 empty] | 1 | 2463 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7203 | KL-20210805-2 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2463 | Each |  |  |  |  | 2463 | 320.19 | 2783.19 | 2021-08-05 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading sections on Hensen Road from 6Km to 11Km. SSF-14319 | 11 | F118-F127 | Hensen Road | 0 | 44420 |  | 14 | 44421 | SSF-20210805-1 | Grading sections of Hensen from Hwy to 6Km |  |  |  | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD7203KL-20210805-23rd Party Services24632463 | KABI LAKE FOREST PRODUCTS LTD7203KL-20210805-23rd Party Services24632463OEWT-PA20-Lem | [5 empty] | 1 | 2463 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7205 | KL-20210806-2 | 53511112 | Access | 0 | 3rd Party Services | 1 | 1244 | Each |  |  |  |  | 1244 | 161.72 | 1405.72 | 2021-08-06 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading sections on Hensen Road from 11Km to 17Km. SSF-14320 | 11 | F118-F127 | Hensen Road | 0 | 44420 |  | 14 | 44421 | SSF-20210806-1 | Grading sections of Hensen from Hwy to 6Km |  |  |  | William Ouimet | 11 | KABI LAKE FOREST PRODUCTS LTD7205KL-20210806-23rd Party Services12441244 | KABI LAKE FOREST PRODUCTS LTD7205KL-20210806-23rd Party Services12441244OEWT-PA20-Lem | [5 empty] | 1 | 1244 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7208 | KL-20210809-2 | 53511112 | Access | 0 | 3rd Party Services | 1 | 1044.82 | Each |  |  |  |  | 1044.82 | 135.8266 | 1180.6466 | 2021-08-09 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish grading sections on Hensen Road from Km 11 to .5 km - SSF-14321 | 11 | F119-F134 | Hensen Road | 0 | 44427 |  | 50 | 44428 | SSF-20210807-1 | Grading road - SSF-14321 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7208KL-20210809-23rd Party Services1044.821044.82 | KABI LAKE FOREST PRODUCTS LTD7208KL-20210809-23rd Party Services1044.821044.82OEWT-PA20-Lem | [5 empty] | 1 | 1044.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7217 | KL-20210814-2 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2065.45 | Each |  |  |  |  | 2065.45 | 268.5085 | 2333.9585 | 2021-08-14 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float grader to Hensen Road and start road maintenance leveling ruts and shaping road from F124 to F127 - SSF-14326 | 11 | F119-F134 | Hensen Road | 0 | 44427 |  | 50 | 44428 | SSF-20210814-1 | Road Maintenance - SSF-14326 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7217KL-20210814-23rd Party Services2065.452065.45 | KABI LAKE FOREST PRODUCTS LTD7217KL-20210814-23rd Party Services2065.452065.45OEWT-PA20-Lem | [5 empty] | 1 | 2065.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7219 | KL-20210815-2 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-08-15 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue road maintenance leveling ruts and shaping road from F124 to F127 - SSF-14328 | 11 | F119-F134 | Hensen Road | 0 | 44427 |  | 50 | 44428 | SSF-20210815-1 | Road Maintenance - SSF-14328 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7219KL-20210815-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7219KL-20210815-23rd Party Services2581.822581.82OEWT-PA20-Lem | [5 empty] | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7220 | KL-20210815-3 | 53510912 | Access | 0 | 3rd Party Services | 1 | 1857.45 | Each |  |  |  |  | 1857.45 | 241.4685 | 2098.9185 | 2021-08-15 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Run Grader from Paint Lake Road 2 to Km 64 on the 600 Road and start Grading - SSF-14327 | 9 | E091-E102 | 600 Road | 0 | 44427 |  | 50 | 44428 | SSF-20210815-2 | Road Maintenance - SSF-14327 |  |  |  | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD7220KL-20210815-33rd Party Services1857.451857.45 | KABI LAKE FOREST PRODUCTS LTD7220KL-20210815-33rd Party Services1857.451857.45OEWT-PA20-Lem | [5 empty] | 1 | 1857.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7222 | KL-20210816-2 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-08-16 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue road maintenance leveling ruts and shaping road from F125 to F123 - SSF-14329 | 11 | F119-F134 | Hensen Road | 0 | 44427 |  | 50 | 44428 | SSF-20210816-1 | Road Maintenance - SSF-14329 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7222KL-20210816-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7222KL-20210816-23rd Party Services2581.822581.82OEWT-PA20-Lem | [5 empty] | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7223 | KL-20210816-3 | 53510912 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-08-16 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road from Km 60 to Km 55 - SSF-14330 | 9 | E091-E102 | 600 Road | 0 | 44427 |  | 50 | 44428 | SSF-20210816-2 | Road Maintenance - SSF-14330 |  |  |  | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD7223KL-20210816-33rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD7223KL-20210816-33rd Party Services2321.822321.82OEWT-PA20-Lem | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7225 | KL-20210817-2 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-08-17 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue road maintenance leveling ruts and shaping road from F125 to F123 - SSF-14332 | 11 | F119-F134 | Hensen Road | 0 | 44427 |  | 50 | 44428 | SSF-20210817-1 | Road Maintenance - SSF-14332 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7225KL-20210817-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7225KL-20210817-23rd Party Services2581.822581.82OEWT-PA20-Lem | [5 empty] | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7226 | KL-20210817-3 | 53510912 | Access | 0 | 3rd Party Services | 1 | 2529 | Each |  |  |  |  | 2529 | 328.77 | 2857.77 | 2021-08-17 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading 600 Road from Km 55 to Km 49 - SSF-14331 | 9 | E091-E102 | 600 Road | 0 | 44427 |  | 50 | 44428 | SSF-20210817-2 | Road Maintenance - SSF-14331 |  |  |  | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD7226KL-20210817-33rd Party Services25292529 | KABI LAKE FOREST PRODUCTS LTD7226KL-20210817-33rd Party Services25292529OEWT-PA20-Lem | [5 empty] | 1 | 2529 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7242 | KL-20210818-1 | 53510912 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-08-18 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road from Km 49 to Km 43 - SSF-14334 | 9 | E091-E102 | 600 Road | 0 | 44433 |  | 37 | 44433 | SSF-20210818-1 | Continue grading 600 road from Km 49 to Km 43 - SSF-14334 |  |  |  | Harold Furlong | 09 | KABI LAKE FOREST PRODUCTS LTD7242KL-20210818-13rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD7242KL-20210818-13rd Party Services2321.822321.82OEWT-PA20-Lem | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7243 | KL-20210818-2 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-08-18 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finishing road maintenance leveling ruts and shaping road from F122 to Hensen Road - SSF-14333 | 11 | F119-F127 | Hensen Road | 0 | 44433 |  | 50 | 44435 | SSF-20210818-2 | Finishing road maintenance leveling ruts and shaping road from F122 to Hensen Road - SSF-14333 |  |  |  | Jim Budgell | 11 | KABI LAKE FOREST PRODUCTS LTD7243KL-20210818-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7243KL-20210818-23rd Party Services2581.822581.82OEWT-PA20-Lem | [5 empty] | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7247 | KL-20210819-3 | 53510912 | Access | 0 | 3rd Party Services | 1 | 2529 | Each |  |  |  |  | 2529 | 328.77 | 2857.77 | 2021-08-19 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road from Km 43 to Km 37 - SSF-14335 | 9 | E091-E102 | 600 Road | 0 | 44436 |  | 50 | 44466 | SSF-20210819-1 | Continue grading 600 Road from Km 43 to Km 37 - SSF-14335 |  |  |  | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD7247KL-20210819-33rd Party Services25292529 | KABI LAKE FOREST PRODUCTS LTD7247KL-20210819-33rd Party Services25292529OEWT-PA20-Lem | [5 empty] | 1 | 2529 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7248 | KL-20210819-4 | 53511004 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-08-19 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44433 |  | 50 | 44435 | SSF-20210819-2 | Start leveling ruts and shaping road from Km 49 to km 46 - SSF-14336 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7248KL-20210819-43rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7248KL-20210819-43rd Party Services2581.822581.82OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7251 | KL-20210820-4 | 53510912 | Access | 0 | 3rd Party Services | 1 | 2089.64 | Each |  |  |  |  | 2089.64 | 271.6532 | 2361.2932 | 2021-08-20 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road from Km 43 to Km 37 - SSF-14338 | 9 | E091-E102 | 600 Road | 0 | 44433 |  | 37 | 44433 | SSF-20210820-1 | Continue grading 600 Road from Km 43 to Km 37 - SSF-14338 |  |  |  | Harold Furlong | 09 | KABI LAKE FOREST PRODUCTS LTD7251KL-20210820-43rd Party Services2089.642089.64 | KABI LAKE FOREST PRODUCTS LTD7251KL-20210820-43rd Party Services2089.642089.64OEWT-PA20-Lem | [5 empty] | 1 | 2089.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7256 | KL-20210821-4 | 53510912 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-08-21 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road from Km 33 to KM 28 - SSF-14339 | 9 | E091-E102 | 600 Road | 0 | 44434 |  | 50 | 44435 | SSF-20210821-1 | Continue grading 600 road from Km 33 to KM 28 - SSF-14339 |  |  |  | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD7256KL-20210821-43rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD7256KL-20210821-43rd Party Services2321.822321.82OEWT-PA20-Lem | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7270 | KL-20210823-4 | 53510912 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-08-23 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road from Km 24 to KM 19.5 - SSF-14342 | 9 | E091-E102 | 600 Road | 0 | 44438 |  | 50 | 44440 | SSF-20210823-1 | Continue grading 600 road from Km 24 to KM 19.5 - SSF-14342 |  |  |  | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD7270KL-20210823-43rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD7270KL-20210823-43rd Party Services2321.822321.82OEWT-PA20-Lem | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7414 | KL-20211001-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2831.83 | Each |  |  |  |  | 2831.83 | 368.1379 | 3199.9679 | 2021-10-01 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | SFF-20211001-1 | Excavator working on soft areas & shaping road from 36km to 34km for rock trucks. SSF-14387 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-13rd Party Services2831.832831.83 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-13rd Party Services2831.832831.83OEWT-PA22-Lem | [5 empty] | 1 | 2831.83 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7414 | KL-20211001-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6763.28 | Each |  |  |  |  | 6763.28 | 879.2264 | 7642.5064 | 2021-10-01 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | MC-20211001-1 | Excavator 1 placing corduroy & capping @ 35km. Excavator 2 loading trees & existing material @ 38km. Rock truck hauling from 38km to 35km. MC-13169 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-13rd Party Services6763.286763.28 | KABI LAKE FOREST PRODUCTS LTD7414KL-20211001-13rd Party Services6763.286763.28OEWT-PA22-Lem | [5 empty] | 1 | 6763.28 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7419 | KL-20211002-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2573.64 | Each |  |  |  |  | 2573.64 | 334.5732 | 2908.2132 | 2021-10-02 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | SFF-20211002-1 | Excavator working on soft areas & shaping road from 36km to 35km for rock trucks. SSF-14388 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-13rd Party Services2573.642573.64 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-13rd Party Services2573.642573.64OEWT-PA22-Lem | [5 empty] | 1 | 2573.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7419 | KL-20211002-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6304.92 | Each |  |  |  |  | 6304.92 | 819.6396 | 7124.5596 | 2021-10-02 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, @ F104 & F102. Excavator 1 tracking out to 44km. Rock trucks hauling trees & gravel from 38km to Morin @ 35km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | MC-20211002-1 | Excavator 1 continuing placing corduroy & capping @ 35km. Excavator 2 loading existing material @ 38km. Rock truck hauling from 38km to 35km. MC-13170 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-13rd Party Services6304.926304.92 | KABI LAKE FOREST PRODUCTS LTD7419KL-20211002-13rd Party Services6304.926304.92OEWT-PA22-Lem | [5 empty] | 1 | 6304.92 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7421 | KL-20211003-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2573.64 | Each |  |  |  |  | 2573.64 | 334.5732 | 2908.2132 | 2021-10-03 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading & hauling from 46km to 45km. Labourers hauling fuel to 35km & installing silt fencing as per Valard. Supervision o Skagen & Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | SSF-20211003-1 | Excavator continuing work on soft areas & shaping road from 36km to 37km for rock trucks and pickups. SSF-14389 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-13rd Party Services2573.642573.64 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-13rd Party Services2573.642573.64OEWT-PA22-Lem | [5 empty] | 1 | 2573.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7421 | KL-20211003-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6304.92 | Each |  |  |  |  | 6304.92 | 819.6396 | 7124.5596 | 2021-10-03 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading & hauling from 46km to 45km. Labourers hauling fuel to 35km & installing silt fencing as per Valard. Supervision o Skagen & Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | MC-20211003-1 | Excavator 1 continuing placing corduroy & capping @ 35km. Excavator 2 loading existing material @ 37.5km. Rock truck hauling from 38km to 35km. MC-13171 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-13rd Party Services6304.926304.92 | KABI LAKE FOREST PRODUCTS LTD7421KL-20211003-13rd Party Services6304.926304.92OEWT-PA22-Lem | [5 empty] | 1 | 6304.92 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7424 | KL-20211004-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2573.64 | Each |  |  |  |  | 2573.64 | 334.5732 | 2908.2132 | 2021-10-04 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working from Paint 2 to F115. excavator 2 working from 45km to 43km. Rock truck hauling existing material from 37.5km to Skagen @36km. Supervision of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | SSF-20211004-1 | Excavator placing corduroy & spreading existing material @ 36 to 36.5 Km. SSF-14390 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7424KL-20211004-13rd Party Services2573.642573.64 | KABI LAKE FOREST PRODUCTS LTD7424KL-20211004-13rd Party Services2573.642573.64OEWT-PA22-Lem | [5 empty] | 1 | 2573.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7424 | KL-20211004-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6304.92 | Each |  |  |  |  | 6304.92 | 819.6396 | 7124.5596 | 2021-10-04 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working from Paint 2 to F115. excavator 2 working from 45km to 43km. Rock truck hauling existing material from 37.5km to Skagen @36km. Supervision of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | MC-20211004-1 | Excavator 1 continuing placing corduroy @ 35/34km. Excavator 2 loading existing material @ 37.5km. Rock truck hauling from 38km to 35km. MC-13171 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7424KL-20211004-13rd Party Services6304.926304.92 | KABI LAKE FOREST PRODUCTS LTD7424KL-20211004-13rd Party Services6304.926304.92OEWT-PA22-Lem | [5 empty] | 1 | 6304.92 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7427 | KL-20211005-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2573.64 | Each |  |  |  |  | 2573.64 | 334.5732 | 2908.2132 | 2021-10-05 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F112. Excavator 2 working @ 43/42km. Rock trucks hauling from 37.5km to Skagen @ 36km. Labourer hauling fuel to 35km as per Valard. Supervision of Skagen/Morin. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | SSF-20211005-1 | Excavator continuing placing corduroy & spreading existing material @ 35.5 to 36.5 Km. SSF-14391 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-13rd Party Services2573.642573.64 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-13rd Party Services2573.642573.64OEWT-PA22-Lem | [5 empty] | 1 | 2573.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7427 | KL-20211005-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6304.92 | Each |  |  |  |  | 6304.92 | 819.6396 | 7124.5596 | 2021-10-05 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F112. Excavator 2 working @ 43/42km. Rock trucks hauling from 37.5km to Skagen @ 36km. Labourer hauling fuel to 35km as per Valard. Supervision of Skagen/Morin. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44477 |  | 50 | 44478 | MC-20211005-1 | Excavator 1 continuing placing corduroy @ 35/34km. Excavator 2 loading existing material @ 37.5km. Rock truck hauling from 37.5km to Skagen @ 36.5km. MC-13173 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-13rd Party Services6304.926304.92 | KABI LAKE FOREST PRODUCTS LTD7427KL-20211005-13rd Party Services6304.926304.92OEWT-PA22-Lem | [5 empty] | 1 | 6304.92 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7335 | KL-20210913-2 | 53511004 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-09-13 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44460 |  |  | 44461 | SSF-20210913-1 | Excavator Continue loading Existing material @ km 38 /morking on access for rock trucks - SSF-14369 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-23rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-23rd Party Services2323.642323.64OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.79105 | 1838.1125 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7350 | KL-20210916-1 | 53511004 | Access | 0 | 3rd Party Services | 1 | 2831.82 | Each |  |  |  |  | 2831.82 | 368.1366 | 3199.9566 | 2021-09-16 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator loading and hauling from 18 to19.5 km /Chapman rock truck and Kabi 30 ton rock truck hauling from 38 to 42/43 km with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44463 |  |  | 44464 | SSF-20210916-1 | Excavator loading rock trucks with existing material @ 38km / leveling ruts on excavation access at end of shift - SSF-14373 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-13rd Party Services2831.822831.82 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-13rd Party Services2831.822831.82OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.76183 | 2157.3536 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7453 | KL-20211014-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2573.64 | Each |  |  |  |  | 2573.64 | 334.5732 | 2908.2132 | 2021-10-14 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from 46 to 39Km, levelling ruts & drainage. Rock trucks haulig existing material from F088 to 34.5Km. Labourer hauling fuel as per Valard. Supervision of Morin, Skagen & Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | SSF-20211014-1 | Excavator working on road sections from 34.SKm to 37Km for rock truck haul & maintain pickup access. SSF-14400 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-13rd Party Services2573.642573.64 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-13rd Party Services2573.642573.64OEWT-PA22-Lem | [5 empty] | 1 | 2573.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7453 | KL-20211014-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6004.55 | Each |  |  |  |  | 6004.55 | 780.5915 | 6785.1415 | 2021-10-14 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from 46 to 39Km, levelling ruts & drainage. Rock trucks haulig existing material from F088 to 34.5Km. Labourer hauling fuel as per Valard. Supervision of Morin, Skagen & Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | MC-20211014-1 | Excavator 1 spreading existing material@ 34.5km. Excavator 2 loading existing material@ F088 as per Valard. Rock truck hauling form F088 to 34.SKm. MC-13182 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-13rd Party Services6004.556004.55 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-13rd Party Services6004.556004.55OEWT-PA22-Lem | [5 empty] | 1 | 6004.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7453 | KL-20211014-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 3114 | Each |  |  |  |  | 3114 | 404.82 | 3518.82 | 2021-10-14 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from 46 to 39Km, levelling ruts & drainage. Rock trucks haulig existing material from F088 to 34.5Km. Labourer hauling fuel as per Valard. Supervision of Morin, Skagen & Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | OP-20211014-1 | Finish carrying & placing trees on access@ 16.5km. Level ruts & shape road to 19Km. OP-90085 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-13rd Party Services31143114 | KABI LAKE FOREST PRODUCTS LTD7453KL-20211014-13rd Party Services31143114OEWT-PA22-Lem | [5 empty] | 1 | 3114 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7456 | KL-20211014-4 | 53511112 | Access | 0 | 3rd Party Services | 1 | 1509.18 | Each |  |  |  |  | 1509.18 | 196.1934 | 1705.3734 | 2021-10-14 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start grading of Hensen Road from Hwy 17 to 2 Km. SSF-14401 | 11 | F119-F134 | Hensen Road | 0 | 44487 |  | 61 | 44491 | SSF-20211014-2 | Start grading of Hensen Road from Hwy 17 to 2 Km. SSF-14401 |  |  |  |  | 11 | KABI LAKE FOREST PRODUCTS LTD7456KL-20211014-43rd Party Services1509.181509.18 | KABI LAKE FOREST PRODUCTS LTD7456KL-20211014-43rd Party Services1509.181509.18OEWT-PA22-Lem | [5 empty] | 1 | 1509.18 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7457 | KL-20211015-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4816.82 | Each |  |  |  |  | 4816.82 | 626.1866 | 5443.0066 | 2021-10-15 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Flll toFlOO level ruts & drainage isting material from F088 to 34.SKm as per Valard. Supervise Morin, Skagen, Pleson, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | JJR-20211015-1 | Track from 12 to 16.SKm, carry & place trees in wet area. Lay geo & start capping. Rock truck driving in from O.SKm & hauling existing material from 19 to 16.SKm. JJR-70267 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-13rd Party Services4816.824816.82 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-13rd Party Services4816.824816.82OEWT-PA22-Lem | [5 empty] | 1 | 4816.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7457 | KL-20211015-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2702.73 | Each |  |  |  |  | 2702.73 | 351.3549 | 3054.0849 | 2021-10-15 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Flll toFlOO level ruts & drainage isting material from F088 to 34.SKm as per Valard. Supervise Morin, Skagen, Pleson, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | SSF-20211015-1 | Excavator working & spreading existing material on road sections from 34.5 to 37km for rock truck haul and maintaining pickup access. SSF-14403 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-13rd Party Services2702.732702.73 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-13rd Party Services2702.732702.73OEWT-PA22-Lem | [5 empty] | 1 | 2702.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7457 | KL-20211015-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6655.19 | Each |  |  |  |  | 6655.19 | 865.1747 | 7520.3647 | 2021-10-15 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Flll toFlOO level ruts & drainage isting material from F088 to 34.SKm as per Valard. Supervise Morin, Skagen, Pleson, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | MC-20211015-1 | Excavator 1 continuing spreading existing material @ 34.5 to 35Km. Excavator 2 loading existing material @ F088 as per Valard. Rock truck hauling from F088 to 34.SKm. MC-13182 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-13rd Party Services6655.196655.19 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-13rd Party Services6655.196655.19OEWT-PA22-Lem | [5 empty] | 1 | 6655.19 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7457 | KL-20211015-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 3114 | Each |  |  |  |  | 3114 | 404.82 | 3518.82 | 2021-10-15 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Flll toFlOO level ruts & drainage isting material from F088 to 34.SKm as per Valard. Supervise Morin, Skagen, Pleson, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | OP-20211015-1 | Level ruts & shape road to 19.SKm. Start stripping & loading existing material @ 19km for capping@ 16.5 Km as per Valard. OP-90086 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-13rd Party Services31143114 | KABI LAKE FOREST PRODUCTS LTD7457KL-20211015-13rd Party Services31143114OEWT-PA22-Lem | [5 empty] | 1 | 3114 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7458 | KL-20211015-2 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2529 | Each |  |  |  |  | 2529 | 328.77 | 2857.77 | 2021-10-15 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading sections of Hensen Road from Hwy 2 Km to 7 Km. SSF-14402 | 11 | F119-F134 | Hensen Road | 0 | 44487 |  | 61 | 44491 | SSF-20211015-2 | Continue grading sections of Hensen Road from Hwy 2 Km to 7 Km. SSF-14402 |  |  |  |  | 11 | KABI LAKE FOREST PRODUCTS LTD7458KL-20211015-23rd Party Services25292529 | KABI LAKE FOREST PRODUCTS LTD7458KL-20211015-23rd Party Services25292529OEWT-PA22-Lem | [5 empty] | 1 | 2529 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7460 | KL-20211016-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2702.73 | Each |  |  |  |  | 2702.73 | 351.3549 | 3054.0849 | 2021-10-16 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F194 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44491 | SSF-20211016-1 | Excavator working and spreading existing material on road sections from km 34.5 to Km 37 for rock truck hauling and maintain pickup access - SSF-14405 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-13rd Party Services2702.732702.73 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-13rd Party Services2702.732702.73OEWT-PA22-Lem | [5 empty] | 1 | 2702.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7460 | KL-20211016-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6688.46 | Each |  |  |  |  | 6688.46 | 869.4998 | 7557.9598 | 2021-10-16 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F194 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44491 | MC-20211016-1 | Excavator 1 continue spreading existing material @ Km 34.5 to Km 34/Excavator 2 loading existing material @ F088 as per Valard/rock truck hauling from F088 to Km 34.5 - MC-13184 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-13rd Party Services6688.466688.46 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-13rd Party Services6688.466688.46OEWT-PA22-Lem | [5 empty] | 1 | 6688.46 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7460 | KL-20211016-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2671.82 | Each |  |  |  |  | 2671.82 | 347.3366 | 3019.1566 | 2021-10-16 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F194 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44491 | OP-20211016-1 | Start stripping, sloping and loading existing material @ km 17 for capping @ km 16.5 as per Valard - OP-90087 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-13rd Party Services2671.822671.82 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-13rd Party Services2671.822671.82OEWT-PA22-Lem | [5 empty] | 1 | 2671.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7460 | KL-20211016-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4583.64 | Each |  |  |  |  | 4583.64 | 595.8732 | 5179.5132 | 2021-10-16 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F194 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44491 | JJR-20211016-1 | Carry and place trees in wet area, lay Geo and start capping @ 16.5 km/ rock truck hauling existing material from km 17 to km 16.5 -JJR-70268 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-13rd Party Services4583.644583.64 | KABI LAKE FOREST PRODUCTS LTD7460KL-20211016-13rd Party Services4583.644583.64OEWT-PA22-Lem | [5 empty] | 1 | 4583.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7462 | KL-20211016-3 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2529 | Each |  |  |  |  | 2529 | 328.77 | 2857.77 | 2021-10-16 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start Grading of Hensen Road from Km 7 to Km 10 - SSF-14404 | 11 | F119-F134 | Hensen Road | 0 | 44494 |  | 61 | 44495 | SSF-20211016-2 | Start Grading of Hensen Road from Km 7 to Km 10 - SSF-14404 |  |  |  |  | 11 | KABI LAKE FOREST PRODUCTS LTD7462KL-20211016-33rd Party Services25292529 | KABI LAKE FOREST PRODUCTS LTD7462KL-20211016-33rd Party Services25292529OEWT-PA22-Lem | [5 empty] | 1 | 2529 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7465 | KL-20211017-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2831.82 | Each |  |  |  |  | 2831.82 | 368.1366 | 3199.9566 | 2021-10-17 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F108, F105,and F103 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | PAINT Lake Road 2 | 0 | 44494 |  | 61 | 44495 | SSF-20211017-1 | Excavator tracking to F078 Fly Yard piling up trees and carrying to the road for corduroy @ F077 - SSF-14407 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-13rd Party Services2831.822831.82 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-13rd Party Services2831.822831.82OEWT-PA22-Lem | [5 empty] | 1 | 2831.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7465 | KL-20211017-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6655.19 | Each |  |  |  |  | 6655.19 | 865.1747 | 7520.3647 | 2021-10-17 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F108, F105,and F103 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | PAINT Lake Road 2 | 0 | 44494 |  | 61 | 44495 | MC-20211017-1 | Excavator 1 continue Laying Geo and spreading existing material @ Km 34.5 to Km 34/Excavator 2 loading existing material @ F088 as per Valard/rock truck hauling from F088 to Km 34.5 - MC-13185 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-13rd Party Services6655.196655.19 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-13rd Party Services6655.196655.19OEWT-PA22-Lem | [5 empty] | 1 | 6655.19 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7274 | KL-20210824-2 | 53510912 | Access | 0 | 3rd Party Services | 1 | 928.73 | Each |  |  |  |  | 928.73 | 120.7349 | 1049.4649 | 2021-08-24 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road from Km 19.5 to Km 18 - SSF-14345 | 9 | E091-E102 | 600 Road | 0 | 44438 |  | 50 | 44441 | SSF-20210824-1 | Continue grading 600 Road from Km 19.5 to Km 18 - SSF-14345 |  |  |  | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD7274KL-20210824-23rd Party Services928.73928.73 | KABI LAKE FOREST PRODUCTS LTD7274KL-20210824-23rd Party Services928.73928.73OEWT-PA20-Lem | [5 empty] | 1 | 928.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7278 | KL-20210825-2 | 53510812 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-08-25 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road from Km 19 to Km 15 - SSF-14347 | 9 | E091-E102 | 600 Road | 0 | 44438 |  | 50 | 44441 | SSF-20210825-1 | Continue grading 600 Road from Km 19 to Km 15 - SSF-14347 |  |  |  | Jim Budgell | 08 | KABI LAKE FOREST PRODUCTS LTD7278KL-20210825-23rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD7278KL-20210825-23rd Party Services2321.822321.82OEWT-PA20-Lem | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7279 | KL-20210825-3 | 53511004 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-08-25 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 42 to Morin Excavator/ Excavator 2 fixing up access from Km 44 to Km 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44438 |  | 37 | 44444 | SSF-20210825-2 | Loading rock trucks with existing material @ km 43 for graveling road sections - SSF-14348 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7279KL-20210825-33rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7279KL-20210825-33rd Party Services2581.822581.82OEWT-PA20-Lem |  | WF10-Access | WF10-Access |  | 1 | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7280 | KL-20210826-2 | 53510912 | Access | 0 | 3rd Party Services | 1 | 1625.27 | Each |  |  |  |  | 1625.27 | 211.2851 | 1836.5551 | 2021-08-26 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road from Km 15 to Km 12 - SSF-14349 | 9 | E091-E102 | 600 Road | 0 | 44438 |  | 50 | 44441 | SSF-20210826-1 | Continue grading 600 Road from Km 15 to Km 12 - SSF-14349 |  |  |  | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD7280KL-20210826-23rd Party Services1625.271625.27 | KABI LAKE FOREST PRODUCTS LTD7280KL-20210826-23rd Party Services1625.271625.27OEWT-PA21-LEM | [5 empty] | 1 | 1625.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7282 | KL-20210827-2 | 53510912 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-08-27 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 Road from Km 12 to Km 7 - SSF-14351 | 9 | E091-E102 | 600 Road | 0 | 44438 |  | 50 | 44441 | SSF-20210827-1 | Continue grading 600 Road from Km 12 to Km 7 - SSF-14351 |  |  |  | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD7282KL-20210827-23rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD7282KL-20210827-23rd Party Services2321.822321.82OEWT-PA21-LEM | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7284 | KL-20210828-2 | 53510912 | Access | 0 | 3rd Party Services | 1 | 2529 | Each |  |  |  |  | 2529 | 328.77 | 2857.77 | 2021-08-28 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish grading 600 Road from Km 7 to Hwy 17 - SSF-14353 | 9 | E091-E102 | 600 Road | 0 | 44438 |  | 50 | 44441 | SSF-20210828-1 | Finish grading 600 Road from Km 7 to Hwy 17 - SSF-14353 |  |  |  | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD7284KL-20210828-23rd Party Services25292529 | KABI LAKE FOREST PRODUCTS LTD7284KL-20210828-23rd Party Services25292529OEWT-PA21-LEM | [5 empty] | 1 | 2529 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7291 | KL-20210822-5 | 53510912 | Access | 0 | 3rd Party Services | 1 | 1625.27 | Each |  |  |  |  | 1625.27 | 211.2851 | 1836.5551 | 2021-08-22 | 0 | OEWT-PA20-Lem | 44447 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue grading 600 road from Km 28 to KM 24 - SSF-14342 | 9 |  | 600 Road | 0 | 44442 |  | 50 | 44443 | SSF-20210822-2 | Continue grading 600 road from Km 28 to KM 24 - SSF-14342 |  |  |  | Jim Budgell | 09 | KABI LAKE FOREST PRODUCTS LTD7291KL-20210822-53rd Party Services1625.271625.27 | KABI LAKE FOREST PRODUCTS LTD7291KL-20210822-53rd Party Services1625.271625.27OEWT-PA20-Lem | [5 empty] | 1 | 1625.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7311 | KL-20210902-2 | 53511004 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-02 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from 38.5 km Morin excavator @ km 40/41 for road capping | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 37 | 44457 | MC-20210902-1 | Excavator spreading gravel for capping @ km 40/41 Km / 6 rock trucks hauling - MC-13139 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7311KL-20210902-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7311KL-20210902-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-Access |  | 0 | 0.68975 | 1780.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7312 | KL-20210903-2 | 53511004 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-03 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from 38.5 km Morin excavator @ km 40/41 for road capping | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44449 |  | 50 | 44450 | MC-20210903-1 | Excavator continuing to spread gravel for capping @ km 41/42 Km - MC-13140 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7312KL-20210903-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7312KL-20210903-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-Access |  | 0 | 0.72423 | 1869.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7327 | KL-20210909-2 | 53511004 | Access | 0 | 3rd Party Services | 1 | 2815 | Each |  |  |  |  | 2815 | 365.95 | 3180.95 | 2021-09-09 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 38 to Km 16 / rock truck hauling from 38 km to Morin Excavator @ 40/42 km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44454 |  | 50 | 44462 | SSF-20210909-1 | Excavator loading Gravel @ km 38 and building access for rock trucks /helping out Valard pickup broke down # km 33 - SSF-14365 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-23rd Party Services28152815 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-23rd Party Services28152815OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 2815 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7327 | KL-20210909-2 | 53511004 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-09-09 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 38 to Km 16 / rock truck hauling from 38 km to Morin Excavator @ 40/42 km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44454 |  | 50 | 44462 | MC-20210909-1 | Excavator Continuing road repairs and spreading gravel @ km 42 to 40 Km - MC-13146 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-23rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-23rd Party Services2323.642323.64OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 1 | 2323.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7361 | KL-20210919-1 | 53511003 | Access | 0 | 3rd Party Services | 1 | 2573.64 | Each |  |  |  |  | 2573.64 | 334.5732 | 2908.2132 | 2021-09-19 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km and pulling pickups @ end of shift /Chapman rock truck hauling trees from F104 to Morin @ km 41 and 42. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44466 |  | 50 | 44466 | SSF-20210919-1 | Excavator loading Chapman Rock Truck with trees for corduroy and working on Access @ F104 - SSF-14376 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-13rd Party Services2573.642573.64 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-13rd Party Services2573.642573.64OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 1286.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7361 | KL-20210919-1 | 53511003 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-09-19 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km and pulling pickups @ end of shift /Chapman rock truck hauling trees from F104 to Morin @ km 41 and 42. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44466 |  | 50 | 44466 | MC-20210919-1 | Excavator 1 placing corduroy in low areas @ km 41 and 42/Excavator 2 working on road maintenance @ km 44/46 - MC- 13156 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-13rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-13rd Party Services2323.642323.64OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 1161.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511003 | Access | 0 | 3rd Party Services | 1 | 2702.73 | Each |  |  |  |  | 2702.73 | 351.3549 | 3054.0849 | 2021-09-20 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44466 |  | 50 | 44466 | SSF-20210920-1 | Loading wood for corduroy - SSF-14377 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-13rd Party Services2702.732702.73 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-13rd Party Services2702.732702.73OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.59731 | 1614.3707 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511003 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-20 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44466 |  | 50 | 44466 | MC-20210920-1 | Placing corduroy - MC-13157 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-13rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-13rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.59731 | 1542.1498 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7370 | KL-20210921-1 | 53511003 | Access | 0 | 3rd Party Services | 1 | 2702.73 | Each |  |  |  |  | 2702.73 | 351.3549 | 3054.0849 | 2021-09-21 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 17 to 20 km/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44467 |  | 50 | 44467 | SSF-20210921-1 | Excavator loading Chapman Rock Truck and Morin rock truck with trees for corduroy and working on Access @ F104 - SSF-14378 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-13rd Party Services2702.732702.73 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-13rd Party Services2702.732702.73OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.51171 | 1383.0075 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7370 | KL-20210921-1 | 53511003 | Access | 0 | 3rd Party Services | 1 | 3996.19 | Each |  |  |  |  | 3996.19 | 519.5047 | 4515.6947 | 2021-09-21 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 17 to 20 km/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44467 |  | 50 | 44467 | MC-20210921-1 | Excavator 1 placing corduroy in low areas @ km 43 Hill/Excavator 2 working on ditching for drainage/rock truck driving in from Hwy and hauling trees from F104 to Km 43 hill - MC- 13158 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-13rd Party Services3996.193996.19 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-13rd Party Services3996.193996.19OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.51171 | 2044.8809 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7379 | KL-20210923-1 | 53511003 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-09-23 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees@ 18 km, excavator 2 placing trees/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 61 | 44471 | SSF-20210923-1 | Excavator loading Chapman Rock Truck and Morin rock truck with trees for corduroy and Carrying trees from F104.5 to F104 for loading/fixing F104 access - SSF-14380 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-13rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-13rd Party Services2323.642323.64OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 1161.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7379 | KL-20210923-1 | 53511003 | Access | 0 | 3rd Party Services | 1 | 6563.1 | Each |  |  |  |  | 6563.1 | 853.203 | 7416.303 | 2021-09-23 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees@ 18 km, excavator 2 placing trees/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 61 | 44471 | MC-20210923-1 | Excavator 1 placing corduroy in low areas @ km 43.5 /Excavator loading trees and tracking from km 42 to 38 leveling ruts /rock truck hauling trees from F104 to Km 43 - MC- 13160 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-13rd Party Services6563.16563.1 | KABI LAKE FOREST PRODUCTS LTD7379KL-20210923-13rd Party Services6563.16563.1OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.5 | 3281.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7384 | KL-20210924-1 | 53511003 | Access | 0 | 3rd Party Services | 1 | 6304.92 | Each |  |  |  |  | 6304.92 | 819.6396 | 7124.5596 | 2021-09-24 | 0 | OEWT-PA21-LEM | 44477 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees, excavator 2 placing trees @km 16.5 and Km 21 hill/Chapman rock truck hauling Gravel From km 38 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44468 |  | 50 | 44470 | MC-20210924-1 | Excavator 1 placing corduroy in low areas @ km 43.5 and spreading gravel/Excavator 2 loading existing material @Km 38/ rock truck hauling existing material from km 38 to km 43.5 - MC- 13161 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-13rd Party Services6304.926304.92 | KABI LAKE FOREST PRODUCTS LTD7384KL-20210924-13rd Party Services6304.926304.92OEWT-PA21-LEM |  | WF10-Access | WF10-Access |  | 1 | 0.51268 | 3232.4101 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7431 | KL-20211006-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 510 | Each |  |  |  |  | 510 | 66.3 | 576.3 | 2021-10-06 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 44484 |  | 63 | 44484 | SSF-20211006-1 | Haul Fuel to km 35 as per Valard - SSF-14392 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-13rd Party Services510510 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-13rd Party Services510510OEWT-PA22-Lem | [5 empty] | 1 | 510 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7431 | KL-20211006-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6530.1 | Each |  |  |  |  | 6530.1 | 848.913 | 7379.013 | 2021-10-06 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 44484 |  | 63 | 44484 | MC-20211006-1 | Excavator 1 placing Corduroy and spreading existing material @Km35/36 /excavator 2 loading exsiting material @ km 37.5/ rock truck hauling from km 37.5 to Skagen @ km 36/35 - MC-13174 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-13rd Party Services6530.16530.1 | KABI LAKE FOREST PRODUCTS LTD7431KL-20211006-13rd Party Services6530.16530.1OEWT-PA22-Lem | [5 empty] | 1 | 6530.1 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7434 | KL-20211007-1-R1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2573.64 | Each |  |  |  |  | 2573.64 | 334.5732 | 2908.2132 | 2021-10-07 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | SSF-20211007-1 | Excavator placing corduroy & spreading existing material on sections @ 36 to 37km. SSF-14393 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R13rd Party Services2573.642573.64 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R13rd Party Services2573.642573.64OEWT-PA22-Lem | [5 empty] | 1 | 2573.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7434 | KL-20211007-1-R1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6530.1 | Each |  |  |  |  | 6530.1 | 848.913 | 7379.013 | 2021-10-07 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | MC-20211007-1 | Excavator 1 spreading existing material on sections @ 36 to 35km. Excavator 2 loading existing material @37.5km. Rock truck hauling from 37.5km to 36/35km. MC-13175 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R13rd Party Services6530.16530.1 | KABI LAKE FOREST PRODUCTS LTD7434KL-20211007-1-R13rd Party Services6530.16530.1OEWT-PA22-Lem | [5 empty] | 1 | 6530.1 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7439 | KL-20211009-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2573.64 | Each |  |  |  |  | 2573.64 | 334.5732 | 2908.2132 | 2021-10-09 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km. Rock trucks on site for gravel haul. Supervision of Morin & Skagen. | 10 | F033 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | SSF-20211009-1 | Excavator starting removal of wet material & filling with trees & stumps @ 34.5km. SSF-14395 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-13rd Party Services2573.642573.64 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-13rd Party Services2573.642573.64OEWT-PA22-Lem | [5 empty] | 1 | 2573.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7439 | KL-20211009-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 3324.55 | Each |  |  |  |  | 3324.55 | 432.1915 | 3756.7415 | 2021-10-09 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km. Rock trucks on site for gravel haul. Supervision of Morin & Skagen. | 10 | F033 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | MC-20211009-1 | Excavator starting @ 34 hill removing wet material, placing corduroy & shaping road. Rock truck on site for gravel hauling. MC-13177 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-13rd Party Services3324.553324.55 | KABI LAKE FOREST PRODUCTS LTD7439KL-20211009-13rd Party Services3324.553324.55OEWT-PA22-Lem | [5 empty] | 1 | 3324.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7441 | KL-20211010-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2315.45 | Each |  |  |  |  | 2315.45 | 301.0085 | 2616.4585 | 2021-10-10 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, corduroy & cap 43km hill. Rock trucks on site for gravel haul. Supervise Morin & Skagen. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | SSF-20211010-1 | Excavator continuing removal of wet material & filling with trees & stumps @34.5km & 34km. SSF-14396 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-13rd Party Services2315.452315.45 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-13rd Party Services2315.452315.45OEWT-PA22-Lem | [5 empty] | 1 | 2315.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7441 | KL-20211010-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2866.18 | Each |  |  |  |  | 2866.18 | 372.6034 | 3238.7834 | 2021-10-10 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, corduroy & cap 43km hill. Rock trucks on site for gravel haul. Supervise Morin & Skagen. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | MC-20211010-1 | Excavator finishing @ 34 hill removing wet material, placing corduroy & shaping road. Rock truck on site for gravel hauling. MC-13178 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-13rd Party Services2866.182866.18 | KABI LAKE FOREST PRODUCTS LTD7441KL-20211010-13rd Party Services2866.182866.18OEWT-PA22-Lem | [5 empty] | 1 | 2866.18 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7442 | KL-20211011-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2573.64 | Each |  |  |  |  | 2573.64 | 334.5732 | 2908.2132 | 2021-10-11 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, levelling ruts & drainage. Rock trucks on site for gravel haul. Supervisor touring for blasting locations. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | SSF-20211011-1 | Excavator continuing removal of wet material & filling with trees & stumps @34.5km & 33.5km. SSF-14397 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-13rd Party Services2573.642573.64 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-13rd Party Services2573.642573.64OEWT-PA22-Lem | [5 empty] | 1 | 2573.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7442 | KL-20211011-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 3124.37 | Each |  |  |  |  | 3124.37 | 406.1681 | 3530.5381 | 2021-10-11 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45km to 43km. Excavator 2 working from 43km to 40.5km, levelling ruts & drainage. Rock trucks on site for gravel haul. Supervisor touring for blasting locations. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44484 | MC-20211011-1 | Excavator working from 36km to 41km levelling ruts & shaping road. Rock truck on site for gravel hauling. MC-13179 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-13rd Party Services3124.373124.37 | KABI LAKE FOREST PRODUCTS LTD7442KL-20211011-13rd Party Services3124.373124.37OEWT-PA22-Lem | [5 empty] | 1 | 3124.37 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7444 | KL-20211008-1-R1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2573.64 | Each |  |  |  |  | 2573.64 | 334.5732 | 2908.2132 | 2021-10-08 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | SSF-20211008-1 | Excavator fixing ruts & shaping road on sections form 37km to 35km for Rock Trucks. SSF-14394 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7444KL-20211008-1-R13rd Party Services2573.642573.64 | KABI LAKE FOREST PRODUCTS LTD7444KL-20211008-1-R13rd Party Services2573.642573.64OEWT-PA22-Lem | [5 empty] | 1 | 2573.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7444 | KL-20211008-1-R1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 7656 | Each |  |  |  |  | 7656 | 995.28 | 8651.28 | 2021-10-08 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ F116 to F108/Excavator 2 working @ 43/41 km/rock trucks hauling existing material from km 37.5 to Morin@ km 36/35/Supervision of Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44484 |  | 63 | 44487 | MC-20211008-1 | Excavator 1 spreading existing material @ 35km. Excavator 2 loading existing material @37.5km. Rock truck hauling from 37.5km to 35km. Worked late to finish capping before rain. MC-13176 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7444KL-20211008-1-R13rd Party Services76567656 | KABI LAKE FOREST PRODUCTS LTD7444KL-20211008-1-R13rd Party Services76567656OEWT-PA22-Lem | [5 empty] | 1 | 7656 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7445 | KL-20211012-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2573.64 | Each |  |  |  |  | 2573.64 | 334.5732 | 2908.2132 | 2021-10-12 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45 to 43km. Excavator 2 working from 43 to 40.5km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervisor site visit with blaster. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | SSF-20211012-1 | Excavator working on drainage & filling holes with trees @ 34.5km to 36km SSF-14398 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-13rd Party Services2573.642573.64 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-13rd Party Services2573.642573.64OEWT-PA22-Lem | [5 empty] | 1 | 2573.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7445 | KL-20211012-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2980.37 | Each |  |  |  |  | 2980.37 | 387.4481 | 3367.8181 | 2021-10-12 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 45 to 43km. Excavator 2 working from 43 to 40.5km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervisor site visit with blaster. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | MC-20211012-1 | Excavator working from 41km to 38km on drainage & shaping road. Start cleaning up excavation @ 38km. Rock truck on site for gravel hauling. MC-13180 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-13rd Party Services2980.372980.37 | KABI LAKE FOREST PRODUCTS LTD7445KL-20211012-13rd Party Services2980.372980.37OEWT-PA22-Lem | [5 empty] | 1 | 2980.37 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7448 | KL-20211013-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2186.36 | Each |  |  |  |  | 2186.36 | 284.2268 | 2470.5868 | 2021-10-13 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 46 to 43km. Excavator 2 working from 43 to 39km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervision of Morin, Skagen, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | SSF-20211013-1 | Excavator working on drainage @ 34.5km to 37km. Load trees on Morin rock truck. SSF-14399 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-13rd Party Services2186.362186.36 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-13rd Party Services2186.362186.36OEWT-PA22-Lem | [5 empty] | 1 | 2186.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7448 | KL-20211013-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5304.01 | Each |  |  |  |  | 5304.01 | 689.5213 | 5993.5313 | 2021-10-13 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 46 to 43km. Excavator 2 working from 43 to 39km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervision of Morin, Skagen, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | MC-20211013-1 | Excavator 1 working from 34.5km using big rocks for fill & shaping road. Excavator 2 finish cleaning up excavation @ 38km & starting @ 37.5. Rock truck hauling trees & on site for gravel hauling. MC-13181 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-13rd Party Services5304.015304.01 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-13rd Party Services5304.015304.01OEWT-PA22-Lem | [5 empty] | 1 | 5304.01 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7448 | KL-20211013-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2421.82 | Each |  |  |  |  | 2421.82 | 314.8366 | 2736.6566 | 2021-10-13 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 working @ 46 to 43km. Excavator 2 working from 43 to 39km levelling ruts & drainage. Rock trucks on site for gravel hauling. Supervision of Morin, Skagen, Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44487 |  | 61 | 44491 | OP-20211013-1 | Track from 12km to 16.5km, carry & place trees on access. OP-90084 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-13rd Party Services2421.822421.82 | KABI LAKE FOREST PRODUCTS LTD7448KL-20211013-13rd Party Services2421.822421.82OEWT-PA22-Lem | [5 empty] | 1 | 2421.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7465 | KL-20211017-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 3084 | Each |  |  |  |  | 3084 | 400.92 | 3484.92 | 2021-10-17 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F108, F105,and F103 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | PAINT Lake Road 2 | 0 | 44494 |  | 61 | 44495 | OP-20211017-1 | Stripping, sloping and loading existing material @ km 17 and spread for capping @ km 16.5 as per Valard - OP-90088 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-13rd Party Services30843084 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-13rd Party Services30843084OEWT-PA22-Lem | [5 empty] | 1 | 3084 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7465 | KL-20211017-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2101.91 | Each |  |  |  |  | 2101.91 | 273.2483 | 2375.1583 | 2021-10-17 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from F111 to F108, F105,and F103 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34.5as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | PAINT Lake Road 2 | 0 | 44494 |  | 61 | 44495 | JJR-20211017-1 | Rock truck hauling existing material from km 17 to km 16.5 and culverts from km 18 -JJR-70269 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-13rd Party Services2101.912101.91 | KABI LAKE FOREST PRODUCTS LTD7465KL-20211017-13rd Party Services2101.912101.91OEWT-PA22-Lem | [5 empty] | 1 | 2101.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7467 | KL-20211017-3 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2529 | Each |  |  |  |  | 2529 | 328.77 | 2857.77 | 2021-10-17 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading of Hensen Road from Hwy 10 to 13.5- SSF-14406 | 11 | F119-F134 | Henson Road | 0 | 44494 |  | 61 | 44495 | SSF-20211017-2 | Continue Grading of Hensen Road from Km 10 to Km 13.5 - SSF-14406 |  |  |  |  | 11 | KABI LAKE FOREST PRODUCTS LTD7467KL-20211017-33rd Party Services25292529 | KABI LAKE FOREST PRODUCTS LTD7467KL-20211017-33rd Party Services25292529OEWT-PA22-Lem | [5 empty] | 1 | 2529 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7471 | KL-20211018-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2831.82 | Each |  |  |  |  | 2831.82 | 368.1366 | 3199.9566 | 2021-10-18 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34 as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | SSF-20211018-1 | Excavator start carrying trees for corduroy on hill @ F077 spreading existing material @ Km 34- SSF-14409 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-13rd Party Services2831.822831.82 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-13rd Party Services2831.822831.82OEWT-PA22-Lem | [5 empty] | 1 | 2831.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7471 | KL-20211018-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5493.37 | Each |  |  |  |  | 5493.37 | 714.1381 | 6207.5081 | 2021-10-18 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34 as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | MC-20211018-1 | Excavator 1 continue Laying Geo and spreading existing material @ Km 34/Excavator 2 loading existing material @ F088 as per Valard/rock truck hauling from F088 to Km 34 - MC-13186 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-13rd Party Services5493.375493.37 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-13rd Party Services5493.375493.37OEWT-PA22-Lem | [5 empty] | 1 | 5493.37 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7471 | KL-20211018-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 3084 | Each |  |  |  |  | 3084 | 400.92 | 3484.92 | 2021-10-18 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34 as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | OP-20211018-1 | Stripping, sloping and loading existing material @ for capping @ km 16.5 as per Valard - OP-90089 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-13rd Party Services30843084 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-13rd Party Services30843084OEWT-PA22-Lem | [5 empty] | 1 | 3084 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7471 | KL-20211018-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5406 | Each |  |  |  |  | 5406 | 702.78 | 6108.78 | 2021-10-18 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts and drainage/rock trucks hauling existing material from F088 to Km 34 as per Valard/Supervision of Morin and Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | JJR-20211018-1 | Continue spreading existing material and laying Geo for capping of corduroy @ Km 16.5 /rock truck hauling existing material from km 17 to km 16.5 -JJR-70270 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-13rd Party Services54065406 | KABI LAKE FOREST PRODUCTS LTD7471KL-20211018-13rd Party Services54065406OEWT-PA22-Lem | [5 empty] | 1 | 5406 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7472 | KL-20211018-2 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-10-18 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Grading of Hensen Road from Km 13 to Km 17.- SSF-14408 | 11 | F119-F134 | Hensen Road | 0 | 44494 |  | 61 | 44495 | SSF-20211018-2 | Continue Grading of Hensen Road from Km 13 to Km 17 - SSF-14408 |  |  |  |  | 11 | KABI LAKE FOREST PRODUCTS LTD7472KL-20211018-23rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD7472KL-20211018-23rd Party Services2321.822321.82OEWT-PA22-Lem | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7475 | KL-20211019-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2831.82 | Each |  |  |  |  | 2831.82 | 368.1366 | 3199.9566 | 2021-10-19 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts, laying Geo and spreading existing material @ Km 42 hill/rock trucks hauling existing material from F088 to Km 34 as per Valard. Labourers picking up 4 roll of Geo @12km on Paint Lake Road 2and deliver it to km 42/worked late to finish capping @km 42 for pickup access/Supervision of Morin, Skagen, Pleson and Opas | 10 |  | Paint | 0 | 44494 |  | 61 | 44495 | SSF-20211019-1 | Excavator Finishing carrying trees for corduroy on hill @ F077 / track packing for Access - SSF-14411 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-13rd Party Services2831.822831.82 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-13rd Party Services2831.822831.82OEWT-PA22-Lem | [5 empty] | 1 | 2831.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7475 | KL-20211019-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6755.28 | Each |  |  |  |  | 6755.28 | 878.1864 | 7633.4664 | 2021-10-19 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts, laying Geo and spreading existing material @ Km 42 hill/rock trucks hauling existing material from F088 to Km 34 as per Valard. Labourers picking up 4 roll of Geo @12km on Paint Lake Road 2and deliver it to km 42/worked late to finish capping @km 42 for pickup access/Supervision of Morin, Skagen, Pleson and Opas | 10 |  | Paint | 0 | 44494 |  | 61 | 44495 | MC-20211019-1 | Excavator 1 continue spreading existing material @ Km 34 and leveling ruts to Km 37/Excavator 2 loading existing material @ F088 as per Valard/rock truck hauling from F088 to Km 34 and Km 42 - MC-13187 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-13rd Party Services6755.286755.28 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-13rd Party Services6755.286755.28OEWT-PA22-Lem | [5 empty] | 1 | 6755.28 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7475 | KL-20211019-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 3084 | Each |  |  |  |  | 3084 | 400.92 | 3484.92 | 2021-10-19 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts, laying Geo and spreading existing material @ Km 42 hill/rock trucks hauling existing material from F088 to Km 34 as per Valard. Labourers picking up 4 roll of Geo @12km on Paint Lake Road 2and deliver it to km 42/worked late to finish capping @km 42 for pickup access/Supervision of Morin, Skagen, Pleson and Opas | 10 |  | Paint | 0 | 44494 |  | 61 | 44495 | OP-20211019-1 | Finish sloping and loading existing material @ for capping @ km 16.5 - OP-900 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-13rd Party Services30843084 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-13rd Party Services30843084OEWT-PA22-Lem | [5 empty] | 1 | 3084 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7475 | KL-20211019-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5406 | Each |  |  |  |  | 5406 | 702.78 | 6108.78 | 2021-10-19 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working from Km 44 to Km 40 leveling ruts, laying Geo and spreading existing material @ Km 42 hill/rock trucks hauling existing material from F088 to Km 34 as per Valard. Labourers picking up 4 roll of Geo @12km on Paint Lake Road 2and deliver it to km 42/worked late to finish capping @km 42 for pickup access/Supervision of Morin, Skagen, Pleson and Opas | 10 |  | Paint | 0 | 44494 |  | 61 | 44495 | JJR-20211019-1 | Continue spreading existing material and laying Geo for capping of corduroy @ Km 16.5 /rock truck hauling existing material from km 17 to km 16.5 -JJR-70271 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-13rd Party Services54065406 | KABI LAKE FOREST PRODUCTS LTD7475KL-20211019-13rd Party Services54065406OEWT-PA22-Lem | [5 empty] | 1 | 5406 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7476 | KL-20211019-2 | 53511112 | Access | 0 | 3rd Party Services | 1 | 1625.27 | Each |  |  |  |  | 1625.27 | 211.2851 | 1836.5551 | 2021-10-19 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish Grading of Hensen Road from Km 17 to Hwy 17.- SSF-14410 | 11 | F119-F134 | Hensen Road | 0 | 44494 |  | 61 | 44495 | SSF-20211019-2 | Finish Grading of Hensen Road from Km 17 to Hwy 17.- SSF-14410 |  |  |  |  | 11 | KABI LAKE FOREST PRODUCTS LTD7476KL-20211019-23rd Party Services1625.271625.27 | KABI LAKE FOREST PRODUCTS LTD7476KL-20211019-23rd Party Services1625.271625.27OEWT-PA22-Lem | [5 empty] | 1 | 1625.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7478 | KL-20211020-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2831.82 | Each |  |  |  |  | 2831.82 | 368.1366 | 3199.9566 | 2021-10-20 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material @ Km 42.5/rock trucks hauling existing material from F088 to Km 34 and Km 42.5 as per Valard. Excavator 3 tracking from Km 49, starting @ F112 to F114 leveling ruts,shaping and drainage/725 rock truck driving to Km .5 for float/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | SSF-20211020-1 | Excavator Tracking from Km 34 to Km 30, start carrying trees and placing corduroy on hill for pickup access - SSF-14412 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-13rd Party Services2831.822831.82 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-13rd Party Services2831.822831.82OEWT-PA22-Lem | [5 empty] | 1 | 2831.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7478 | KL-20211020-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6688.46 | Each |  |  |  |  | 6688.46 | 869.4998 | 7557.9598 | 2021-10-20 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material @ Km 42.5/rock trucks hauling existing material from F088 to Km 34 and Km 42.5 as per Valard. Excavator 3 tracking from Km 49, starting @ F112 to F114 leveling ruts,shaping and drainage/725 rock truck driving to Km .5 for float/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | MC-20211020-1 | Excavator 1 continue spreading existing material @ Km 34 and leveling ruts to Km 36 for pickup access/Excavator 2 loading existing material @ F088 as per Valard/rock truck hauling from F088 to Km 34 and Km 42 - MC-13188 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-13rd Party Services6688.466688.46 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-13rd Party Services6688.466688.46OEWT-PA22-Lem | [5 empty] | 1 | 6688.46 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7478 | KL-20211020-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 3084 | Each |  |  |  |  | 3084 | 400.92 | 3484.92 | 2021-10-20 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material @ Km 42.5/rock trucks hauling existing material from F088 to Km 34 and Km 42.5 as per Valard. Excavator 3 tracking from Km 49, starting @ F112 to F114 leveling ruts,shaping and drainage/725 rock truck driving to Km .5 for float/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | OP-20211020-1 | Loading existing material @ Km 17 for capping @ km 18 - OP-90091 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-13rd Party Services30843084 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-13rd Party Services30843084OEWT-PA22-Lem | [5 empty] | 1 | 3084 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7478 | KL-20211020-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5195 | Each |  |  |  |  | 5195 | 675.35 | 5870.35 | 2021-10-20 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material @ Km 42.5/rock trucks hauling existing material from F088 to Km 34 and Km 42.5 as per Valard. Excavator 3 tracking from Km 49, starting @ F112 to F114 leveling ruts,shaping and drainage/725 rock truck driving to Km .5 for float/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44494 |  | 61 | 44495 | JJR-20211020-1 | Start spreading existing material and laying Geo for capping of corduroy @ Km 17.5 /Km 18 /rock truck hauling existing material from km 17 -JJR-70272 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-13rd Party Services51955195 | KABI LAKE FOREST PRODUCTS LTD7478KL-20211020-13rd Party Services51955195OEWT-PA22-Lem | [5 empty] | 1 | 5195 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7480 | KL-20211021-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2831.82 | Each |  |  |  |  | 2831.82 | 368.1366 | 3199.9566 | 2021-10-21 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material on sections/rock trucks hauling existing material from F088 as per Valard. Excavator 3 continuing @ F113 to F115 leveling ruts,shaping and drainage for freezing/ Supervision of Morin, Skagen, Pleson and Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 61 | 44495 | SSF-20211021-1 | Excavator leveling ruts and shaping road from Km 33.5 to Km 32, for assembly crew access to Km 30 - SSF-14413 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-13rd Party Services2831.822831.82 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-13rd Party Services2831.822831.82OEWT-PA22-Lem | [5 empty] | 1 | 2831.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7480 | KL-20211021-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5103.83 | Each |  |  |  |  | 5103.83 | 663.4979 | 5767.3279 | 2021-10-21 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material on sections/rock trucks hauling existing material from F088 as per Valard. Excavator 3 continuing @ F113 to F115 leveling ruts,shaping and drainage for freezing/ Supervision of Morin, Skagen, Pleson and Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 61 | 44495 | MC-20211021-1 | Excavator 1 using existing material for capping @ Km 33.5 hill and leveling ruts to Km 36 for pickup access/Excavator 2 loading existing material and sloping@ F088 as per Valard/rock truck driving to km 0.5 for demob - MC-13189 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-13rd Party Services5103.835103.83 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-13rd Party Services5103.835103.83OEWT-PA22-Lem | [5 empty] | 1 | 5103.83 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7480 | KL-20211021-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 3084 | Each |  |  |  |  | 3084 | 400.92 | 3484.92 | 2021-10-21 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material on sections/rock trucks hauling existing material from F088 as per Valard. Excavator 3 continuing @ F113 to F115 leveling ruts,shaping and drainage for freezing/ Supervision of Morin, Skagen, Pleson and Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 61 | 44495 | OP-20211021-1 | Loading existing material @ Km 19 for capping @ km 18/19 - OP-90092 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-13rd Party Services30843084 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-13rd Party Services30843084OEWT-PA22-Lem | [5 empty] | 1 | 3084 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7480 | KL-20211021-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5406 | Each |  |  |  |  | 5406 | 702.78 | 6108.78 | 2021-10-21 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 and 2 working from Km 44 to Km 40 Shaping, laying Geo and spreading existing material on sections/rock trucks hauling existing material from F088 as per Valard. Excavator 3 continuing @ F113 to F115 leveling ruts,shaping and drainage for freezing/ Supervision of Morin, Skagen, Pleson and Opas. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 61 | 44495 | JJR-20211021-1 | Excavator spreading existing material and laying Geo for capping @ Km 18/19 /rock truck hauling existing material from km 19 -JJR-70273 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-13rd Party Services54065406 | KABI LAKE FOREST PRODUCTS LTD7480KL-20211021-13rd Party Services54065406OEWT-PA22-Lem | [5 empty] | 1 | 5406 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7482 | KL-20211022-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2300.73 | Each |  |  |  |  | 2300.73 | 299.0949 | 2599.8249 | 2021-10-22 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 working from Km 43 to Km 40 and F105 access Shaping road/ excavator 2 working from Km 43 to Km 45 and F111 shaping road. Excavator 3 Finishing @ F115 to F117 leveling ruts,shaping for freezing and track to F123/ Supervision of Morin, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44495 |  | 61 | 44495 | MC-20211022-1 | Excavator shaping road from Km 37 to Km 34 and leveling ruts from Km 33 to Km 30 for assembly crews pickup access - MC-13190 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7482KL-20211022-13rd Party Services2300.732300.73 | KABI LAKE FOREST PRODUCTS LTD7482KL-20211022-13rd Party Services2300.732300.73OEWT-PA22-Lem | [5 empty] | 1 | 2300.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7482 | KL-20211022-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 3084 | Each |  |  |  |  | 3084 | 400.92 | 3484.92 | 2021-10-22 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 working from Km 43 to Km 40 and F105 access Shaping road/ excavator 2 working from Km 43 to Km 45 and F111 shaping road. Excavator 3 Finishing @ F115 to F117 leveling ruts,shaping for freezing and track to F123/ Supervision of Morin, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44495 |  | 61 | 44495 | OP-20211022-1 | Excavator spreading existing material for capping and shaping road @ Km 19.5 - OP-90093 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7482KL-20211022-13rd Party Services30843084 | KABI LAKE FOREST PRODUCTS LTD7482KL-20211022-13rd Party Services30843084OEWT-PA22-Lem | [5 empty] | 1 | 3084 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7482 | KL-20211022-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5017 | Each |  |  |  |  | 5017 | 652.21 | 5669.21 | 2021-10-22 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 working from Km 43 to Km 40 and F105 access Shaping road/ excavator 2 working from Km 43 to Km 45 and F111 shaping road. Excavator 3 Finishing @ F115 to F117 leveling ruts,shaping for freezing and track to F123/ Supervision of Morin, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44495 |  | 61 | 44495 | JJR-20211022-1 | Excavator loading existing material and shaping excavation @ Km 19 /rock truck hauling existing material from km 19 to Opas -JJR-70274 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7482KL-20211022-13rd Party Services50175017 | KABI LAKE FOREST PRODUCTS LTD7482KL-20211022-13rd Party Services50175017OEWT-PA22-Lem | [5 empty] | 1 | 5017 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7483 | KL-20211023-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2831.82 | Each |  |  |  |  | 2831.82 | 368.1366 | 3199.9566 | 2021-10-23 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 shaping road from Km 43 to Km 40 anf F098/ Excavator 2 shaping road from 45 to 49 km and starting in F123 access/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44495 |  | 61 | 44496 | SSF-20211023-1 | Excavator leveling ruts and shaping road to Km 32 and F072 Access - SSF-14414 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7483KL-20211023-13rd Party Services2831.822831.82 | KABI LAKE FOREST PRODUCTS LTD7483KL-20211023-13rd Party Services2831.822831.82OEWT-PA22-Lem | [5 empty] | 1 | 2831.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7483 | KL-20211023-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2300.73 | Each |  |  |  |  | 2300.73 | 299.0949 | 2599.8249 | 2021-10-23 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 shaping road from Km 43 to Km 40 anf F098/ Excavator 2 shaping road from 45 to 49 km and starting in F123 access/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44495 |  | 61 | 44496 | MC-20211023-1 | Excavator shaping road and leveling ruts from km 33 to km 30 and capping corduroy @ km 30 with existing material - MC-13191 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7483KL-20211023-13rd Party Services2300.732300.73 | KABI LAKE FOREST PRODUCTS LTD7483KL-20211023-13rd Party Services2300.732300.73OEWT-PA22-Lem | [5 empty] | 1 | 2300.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7483 | KL-20211023-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2889 | Each |  |  |  |  | 2889 | 375.57 | 3264.57 | 2021-10-23 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 shaping road from Km 43 to Km 40 anf F098/ Excavator 2 shaping road from 45 to 49 km and starting in F123 access/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44495 |  | 61 | 44496 | OP-20211023-1 | Excavator continue spreading for capping and shaping road@ Km 20/ side by side used for dragging a culvert from km 22- OP-90094 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7483KL-20211023-13rd Party Services28892889 | KABI LAKE FOREST PRODUCTS LTD7483KL-20211023-13rd Party Services28892889OEWT-PA22-Lem | [5 empty] | 1 | 2889 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7483 | KL-20211023-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4616.45 | Each |  |  |  |  | 4616.45 | 600.1385 | 5216.5885 | 2021-10-23 | 0 | OEWT-PA22-Lem | 44502 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators 1 shaping road from Km 43 to Km 40 anf F098/ Excavator 2 shaping road from 45 to 49 km and starting in F123 access/Supervision of Morin, Skagen, Pleson and Opas | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44495 |  | 61 | 44496 | JJR-20211023-1 | Excavator continuing loading existing material and shaping excavation @ Km 19 /rock truck hauling existing material from km 19 to Opas @ Km 19.5 -JJR-70275 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7483KL-20211023-13rd Party Services4616.454616.45 | KABI LAKE FOREST PRODUCTS LTD7483KL-20211023-13rd Party Services4616.454616.45OEWT-PA22-Lem | [5 empty] | 1 | 4616.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7485 | KL-20211024-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2831.82 | Each |  |  |  |  | 2831.82 | 368.1366 | 3199.9566 | 2021-10-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from Km 46 and F105 access/supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44496 |  | 61 | 44497 | SSF-20211024-1 | Excavator leveling ruts and shaping road From Km 32 to Km 25 - SSF-14415 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7485KL-20211024-13rd Party Services2831.822831.82 | KABI LAKE FOREST PRODUCTS LTD7485KL-20211024-13rd Party Services2831.822831.82OEWT-PA23-Lem | [5 empty] | 1 | 2831.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7485 | KL-20211024-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2300.73 | Each |  |  |  |  | 2300.73 | 299.0949 | 2599.8249 | 2021-10-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from Km 46 and F105 access/supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44496 |  | 61 | 44497 | MC-20211024-1 | Excavator continuing of shaping road, drainage and leveling ruts from km 33 to km 30 for freezing - MC-13192 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7485KL-20211024-13rd Party Services2300.732300.73 | KABI LAKE FOREST PRODUCTS LTD7485KL-20211024-13rd Party Services2300.732300.73OEWT-PA23-Lem | [5 empty] | 1 | 2300.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7485 | KL-20211024-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2639 | Each |  |  |  |  | 2639 | 343.07 | 2982.07 | 2021-10-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from Km 46 and F105 access/supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44496 |  | 61 | 44497 | OP-20211024-1 | Excavator tracking from 19.5 km to F046 access and spread existing material for crane pad- OP-90095 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7485KL-20211024-13rd Party Services26392639 | KABI LAKE FOREST PRODUCTS LTD7485KL-20211024-13rd Party Services26392639OEWT-PA23-Lem | [5 empty] | 1 | 2639 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7485 | KL-20211024-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5267 | Each |  |  |  |  | 5267 | 684.71 | 5951.71 | 2021-10-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from Km 46 and F105 access/supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44496 |  | 61 | 44497 | JJR-20211024-1 | Excavator tracking from km 19 to km 17 and loading existing material for Capping of F046 access/rock truck hauling existing material from km 17 to Opas @ F046 access-JJR-70276 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7485KL-20211024-13rd Party Services52675267 | KABI LAKE FOREST PRODUCTS LTD7485KL-20211024-13rd Party Services52675267OEWT-PA23-Lem | [5 empty] | 1 | 5267 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7488 | KL-20211025-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2573.64 | Each |  |  |  |  | 2573.64 | 334.5732 | 2908.2132 | 2021-10-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from Km 44 to Km 40 and F105 access/supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44496 |  | 61 | 44497 | SSF-20211025-1 | Excavator leveling ruts and shaping road From Km 32 to Km 37 - SSF-14416 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7488KL-20211025-13rd Party Services2573.642573.64 | KABI LAKE FOREST PRODUCTS LTD7488KL-20211025-13rd Party Services2573.642573.64OEWT-PA23-Lem | [5 empty] | 1 | 2573.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7488 | KL-20211025-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2179.64 | Each |  |  |  |  | 2179.64 | 283.3532 | 2462.9932 | 2021-10-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from Km 44 to Km 40 and F105 access/supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44496 |  | 61 | 44497 | MC-20211025-1 | Excavator continuing of shaping road, drainage and leveling ruts from km 33 to km 30 for pickup access- MC-13193 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7488KL-20211025-13rd Party Services2179.642179.64 | KABI LAKE FOREST PRODUCTS LTD7488KL-20211025-13rd Party Services2179.642179.64OEWT-PA23-Lem | [5 empty] | 1 | 2179.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7488 | KL-20211025-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2530.41 | Each |  |  |  |  | 2530.41 | 328.9533 | 2859.3633 | 2021-10-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from Km 44 to Km 40 and F105 access/supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44496 |  | 61 | 44497 | OP-20211025-1 | Excavator tracking from F046 to Km 17.5 and loading existing material for capping @ Km 19.5 - OP-90096 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7488KL-20211025-13rd Party Services2530.412530.41 | KABI LAKE FOREST PRODUCTS LTD7488KL-20211025-13rd Party Services2530.412530.41OEWT-PA23-Lem | [5 empty] | 1 | 2530.41 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7488 | KL-20211025-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4800.32 | Each |  |  |  |  | 4800.32 | 624.0416 | 5424.3616 | 2021-10-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from Km 44 to Km 40 and F105 access/supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44496 |  | 61 | 44497 | JJR-20211025-1 | Excavator loading existing material @km 17.5 for Capping /rock truck hauling existing material from km 17 to Opas @ 19.5 Km - JJR-70277 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7488KL-20211025-13rd Party Services4800.324800.32 | KABI LAKE FOREST PRODUCTS LTD7488KL-20211025-13rd Party Services4800.324800.32OEWT-PA23-Lem | [5 empty] | 1 | 4800.32 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7492 | KL-20211026-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2315.45 | Each |  |  |  |  | 2315.45 | 301.0085 | 2616.4585 | 2021-10-26 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from F110 to Km 41 /supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | SSF-20211026-1 | Excavator Continuing leveling ruts and shaping road From Km 36 to Km 37 - SSF-14417 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7492KL-20211026-13rd Party Services2315.452315.45 | KABI LAKE FOREST PRODUCTS LTD7492KL-20211026-13rd Party Services2315.452315.45OEWT-PA23-Lem | [5 empty] | 1 | 2315.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7492 | KL-20211026-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4201.82 | Each |  |  |  |  | 4201.82 | 546.2366 | 4748.0566 | 2021-10-26 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from F110 to Km 41 /supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | MC-20211026-1 | Excavator and rock truck working @ km 31.5 capping road with existing material for pick up access /pulling Valard rock truck@ Km 33.5 hill @ end of shift - MC-13194 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7492KL-20211026-13rd Party Services4201.824201.82 | KABI LAKE FOREST PRODUCTS LTD7492KL-20211026-13rd Party Services4201.824201.82OEWT-PA23-Lem | [5 empty] | 1 | 4201.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7492 | KL-20211026-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2421.82 | Each |  |  |  |  | 2421.82 | 314.8366 | 2736.6566 | 2021-10-26 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from F110 to Km 41 /supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | OP-20211026-1 | Excavator loading existing material @ 17.5 Km for capping @ Km 19.5 as per Valard - OP-90097 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7492KL-20211026-13rd Party Services2421.822421.82 | KABI LAKE FOREST PRODUCTS LTD7492KL-20211026-13rd Party Services2421.822421.82OEWT-PA23-Lem | [5 empty] | 1 | 2421.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7492 | KL-20211026-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4816.82 | Each |  |  |  |  | 4816.82 | 626.1866 | 5443.0066 | 2021-10-26 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road from F110 to Km 41 /supervision of Morin, Skagen, Opas and Pleson | 10 | F033-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | JJR-20211026-1 | Excavator shaping road, laying Geo and spreading existing material @km 19.5 - 20 for Capping /rock truck hauling existing material from km 17.5 - JJR-70278 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7492KL-20211026-13rd Party Services4816.824816.82 | KABI LAKE FOREST PRODUCTS LTD7492KL-20211026-13rd Party Services4816.824816.82OEWT-PA23-Lem | [5 empty] | 1 | 4816.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7494 | KL-20211026-3 | 53510912 | Access | 0 | 3rd Party Services | 1 | 1857.45 | Each |  |  |  |  | 1857.45 | 241.4685 | 2098.9185 | 2021-10-26 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Skagen Volvo Grader from Hensen Road for grading of the 600 Road. Grade from Km 1 on Paint Lake Road 2 to Km 52 on 600 road and grade towards Km 49 - SSF-14419 | 9 | E032-F009 | 600 Road | 0 | 44501 |  | 61 | 44502 | SSF-20211026-2 | Run Grader from Km 1 on Paint Lake Road 2 to Km 52 on 600 road and start grading to Km 49 - SSF-14419 |  |  |  |  | 09 | KABI LAKE FOREST PRODUCTS LTD7494KL-20211026-33rd Party Services1857.451857.45 | KABI LAKE FOREST PRODUCTS LTD7494KL-20211026-33rd Party Services1857.451857.45OEWT-PA23-Lem | [5 empty] | 1 | 1857.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7496 | KL-20211027-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2831.82 | Each |  |  |  |  | 2831.82 | 368.1366 | 3199.9566 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 44, laying Geo and spreading existing material/Excavtor 2 loading existing material@ km 17 on Hensen/rock truck hauling existing material to Km 44 supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | SSF-20211027-1 | Excavator Tracking from Km 37 to 32 place corduroy and spread existing material for capping - SSF-14421 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-13rd Party Services2831.822831.82 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-13rd Party Services2831.822831.82OEWT-PA23-Lem | [5 empty] | 1 | 2831.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7496 | KL-20211027-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4223.46 | Each |  |  |  |  | 4223.46 | 549.0498 | 4772.5098 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 44, laying Geo and spreading existing material/Excavtor 2 loading existing material@ km 17 on Hensen/rock truck hauling existing material to Km 44 supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | MC-20211027-1 | Excavator working @ km 30.5/31 loading trees and existing material for capping road/ tracking to Km 36 @ end of shift /rock truck hauling trees and existing material to Km 30.5 and 32 - MC-13195 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-13rd Party Services4223.464223.46 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-13rd Party Services4223.464223.46OEWT-PA23-Lem | [5 empty] | 1 | 4223.46 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7496 | KL-20211027-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2639 | Each |  |  |  |  | 2639 | 343.07 | 2982.07 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 44, laying Geo and spreading existing material/Excavtor 2 loading existing material@ km 17 on Hensen/rock truck hauling existing material to Km 44 supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | OP-20211027-1 | Excavator tracking from Km 17.5 to 20.5 and loading existing material for capping @ 20 Km as per Valard - OP-90098 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-13rd Party Services26392639 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-13rd Party Services26392639OEWT-PA23-Lem | [5 empty] | 1 | 2639 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7496 | KL-20211027-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4800.32 | Each |  |  |  |  | 4800.32 | 624.0416 | 5424.3616 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 44, laying Geo and spreading existing material/Excavtor 2 loading existing material@ km 17 on Hensen/rock truck hauling existing material to Km 44 supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | JJR-20211027-1 | Excavator shaping road, laying Geo and spreading existing material @km 19.5 - 20 for Capping /rock truck hauling existing material from km 20.5 - JJR-70279 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-13rd Party Services4800.324800.32 | KABI LAKE FOREST PRODUCTS LTD7496KL-20211027-13rd Party Services4800.324800.32OEWT-PA23-Lem | [5 empty] | 1 | 4800.32 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7498 | KL-20211027-3 | 53510912 | Access | 0 | 3rd Party Services | 1 | 3947.1 | Each |  |  |  |  | 3947.1 | 513.123 | 4460.223 | 2021-10-27 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 grading from Km 49 to Km 45 on 600 Road/ Grader 2 starting grading @ km O to Km 7 on 600 Road - SSF-14420 | 9 | E092-F009 | 600 road | 0 | 44501 |  | 61 | 44502 | SSF-20211027-2 | Grader 1 grading from Km 49 to Km 45 on 600 Road/ Grader 2 starting grading @ km O to Km 7 on 600 Road - SSF-14420 |  |  |  |  | 09 | KABI LAKE FOREST PRODUCTS LTD7498KL-20211027-33rd Party Services3947.13947.1 | KABI LAKE FOREST PRODUCTS LTD7498KL-20211027-33rd Party Services3947.13947.1OEWT-PA23-Lem | [5 empty] | 1 | 3947.1 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7502 | KL-20211028-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2831.82 | Each |  |  |  |  | 2831.82 | 368.1366 | 3199.9566 | 2021-10-28 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 laying Geo and spreading existing material @ Km 44 and shaping road to Km 45/Excavtor 2 cleaning up excavation @ km 17 on Hensen road and shaping road to F114 rock truck2 hauling from F088 to Km 34-33 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | SSF-20211028-1 | Excavator placing corduroy from Km 31 to 32 and shaping access to F072 - SSF-14423 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-13rd Party Services2831.822831.82 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-13rd Party Services2831.822831.82OEWT-PA23-Lem | [5 empty] | 1 | 2831.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7502 | KL-20211028-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6434.01 | Each |  |  |  |  | 6434.01 | 836.4213 | 7270.4313 | 2021-10-28 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 laying Geo and spreading existing material @ Km 44 and shaping road to Km 45/Excavtor 2 cleaning up excavation @ km 17 on Hensen road and shaping road to F114 rock truck2 hauling from F088 to Km 34-33 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | MC-20211028-1 | Excavator 1 laying Geo and spreading existing material @ Km 33-34/ Excavator 2 loading existing material @ F088 as per Valard/rock truck hauling from F088 to Km 34-33 - MC-13196 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-13rd Party Services6434.016434.01 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-13rd Party Services6434.016434.01OEWT-PA23-Lem | [5 empty] | 1 | 6434.01 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7502 | KL-20211028-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2639 | Each |  |  |  |  | 2639 | 343.07 | 2982.07 | 2021-10-28 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 laying Geo and spreading existing material @ Km 44 and shaping road to Km 45/Excavtor 2 cleaning up excavation @ km 17 on Hensen road and shaping road to F114 rock truck2 hauling from F088 to Km 34-33 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | OP-20211028-1 | Excavator laying Geo and Spreading existing material for capping @ 21 Km hill - OP-90099 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-13rd Party Services26392639 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-13rd Party Services26392639OEWT-PA23-Lem | [5 empty] | 1 | 2639 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7502 | KL-20211028-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5017 | Each |  |  |  |  | 5017 | 652.21 | 5669.21 | 2021-10-28 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 laying Geo and spreading existing material @ Km 44 and shaping road to Km 45/Excavtor 2 cleaning up excavation @ km 17 on Hensen road and shaping road to F114 rock truck2 hauling from F088 to Km 34-33 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44501 |  | 61 | 44502 | JJR-20211028-1 | Excavator loading existing material @ F052 for Capping as per Valard /rock truck hauling existing material from F052 to Km 21 hill - JJR-70280 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-13rd Party Services50175017 | KABI LAKE FOREST PRODUCTS LTD7502KL-20211028-13rd Party Services50175017OEWT-PA23-Lem | [5 empty] | 1 | 5017 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7505 | KL-20211028-3 | 53510912 | Access | 0 | 3rd Party Services | 1 | 4850.82 | Each |  |  |  |  | 4850.82 | 630.6066 | 5481.4266 | 2021-10-28 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 grading from Km 45 to Km 40 on 600 Road/ Grader 2 grading @ km 7 to Km 14 on 600 Road - SSF-14422 | 9 | E092-F009 | 600 Road | 0 | 44501 |  | 61 | 44502 | SSF-20211028-2 | Grader 1 grading from Km 45 to Km 40 on 600 Road/ Grader 2 grading @ km 7 to Km 14 on 600 Road - SSF-14422 |  |  |  |  | 09 | KABI LAKE FOREST PRODUCTS LTD7505KL-20211028-33rd Party Services4850.824850.82 | KABI LAKE FOREST PRODUCTS LTD7505KL-20211028-33rd Party Services4850.824850.82OEWT-PA23-Lem | [5 empty] | 1 | 4850.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7506 | KL-20211029-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2831.82 | Each |  |  |  |  | 2831.82 | 368.1366 | 3199.9566 | 2021-10-29 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing clean up of excavation @ Km 17 on Hensen road and start shaping road to Km 45.5. Rock truck hauling existing material from F088 to Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44502 |  | 61 | 44503 | SSF-20211029-1 | Excavator capping corduroy with existing material @ Km 30 to 31.5 hauling by Valard rock truck - SSF-14425 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7506KL-20211029-13rd Party Services2831.822831.82 | KABI LAKE FOREST PRODUCTS LTD7506KL-20211029-13rd Party Services2831.822831.82OEWT-PA23-Lem | [5 empty] | 1 | 2831.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7506 | KL-20211029-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6505.1 | Each |  |  |  |  | 6505.1 | 845.663 | 7350.763 | 2021-10-29 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing clean up of excavation @ Km 17 on Hensen road and start shaping road to Km 45.5. Rock truck hauling existing material from F088 to Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44502 |  | 61 | 44503 | MC-20211029-1 | Excavator 1 laying Geo and spreading existing material @ Km 33-34/ Excavator 2 loading existing material @ F088 as per Valard/rock truck hauling from F088 to Km 34-33 and 1 load to Km 42 @ end of shift - MC-13198 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7506KL-20211029-13rd Party Services6505.16505.1 | KABI LAKE FOREST PRODUCTS LTD7506KL-20211029-13rd Party Services6505.16505.1OEWT-PA23-Lem | [5 empty] | 1 | 6505.1 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7506 | KL-20211029-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2889 | Each |  |  |  |  | 2889 | 375.57 | 3264.57 | 2021-10-29 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing clean up of excavation @ Km 17 on Hensen road and start shaping road to Km 45.5. Rock truck hauling existing material from F088 to Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44502 |  | 61 | 44503 | OP-20211029-1 | Excavator continue laying Geo and Spreading existing material for capping @ 21/22 Km - OP-90100 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7506KL-20211029-13rd Party Services28892889 | KABI LAKE FOREST PRODUCTS LTD7506KL-20211029-13rd Party Services28892889OEWT-PA23-Lem | [5 empty] | 1 | 2889 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7506 | KL-20211029-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5017 | Each |  |  |  |  | 5017 | 652.21 | 5669.21 | 2021-10-29 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator finishing clean up of excavation @ Km 17 on Hensen road and start shaping road to Km 45.5. Rock truck hauling existing material from F088 to Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44502 |  | 61 | 44503 | JJR-20211029-1 | Excavator continuing loading existing material @ F052 for Capping as per Valard /rock truck hauling existing material from F052 to Km 21/22 - JJR-70281 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7506KL-20211029-13rd Party Services50175017 | KABI LAKE FOREST PRODUCTS LTD7506KL-20211029-13rd Party Services50175017OEWT-PA23-Lem | [5 empty] | 1 | 5017 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7508 | KL-20211029-3 | 53510912 | Access | 0 | 3rd Party Services | 1 | 4643.64 | Each |  |  |  |  | 4643.64 | 603.6732 | 5247.3132 | 2021-10-29 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 grading from Km 45 to Km 40 on 600 Road/ Grader 2 grading @ km 7 to Km 14 on 600 Road - SSF-14422 | 9 | E092-F009 | 600 Road | 0 | 44501 |  | 61 | 44503 | SSF-20211029-2 | Grader 1 grading from Km 40 to Km 33.5 on 600 Road/ Grader 2 grading @ km 14 to Km 20 on 600 Road - SSF-14424 |  |  |  |  | 09 | KABI LAKE FOREST PRODUCTS LTD7508KL-20211029-33rd Party Services4643.644643.64 | KABI LAKE FOREST PRODUCTS LTD7508KL-20211029-33rd Party Services4643.644643.64OEWT-PA23-Lem | [5 empty] | 1 | 4643.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7510 | KL-20211030-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2831.82 | Each |  |  |  |  | 2831.82 | 368.1366 | 3199.9566 | 2021-10-30 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road to Km 45 to Km 43 and spreading spotted rock trucks loads. Rock truck hauling existing material from F088 to Morin @ Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas. | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44502 |  | 61 | 44503 | SSF-20211030-1 | Excavator tracking existing material for capping of corduroy @ Km 30 to 31.5 and Valard rock truck hauling existing material from Km 27 - SSF-14427 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7510KL-20211030-13rd Party Services2831.822831.82 | KABI LAKE FOREST PRODUCTS LTD7510KL-20211030-13rd Party Services2831.822831.82OEWT-PA23-Lem | [5 empty] | 1 | 2831.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7510 | KL-20211030-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6634.19 | Each |  |  |  |  | 6634.19 | 862.4447 | 7496.6347 | 2021-10-30 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road to Km 45 to Km 43 and spreading spotted rock trucks loads. Rock truck hauling existing material from F088 to Morin @ Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas. | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44502 |  | 61 | 44503 | MC-20211030-1 | Excavator 1 continue laying Geo and spreading existing material @ Km 33.5/ Excavator 2 loading existing material @ F088 as per Valard/rock truck hauling from F088 to Km 34-33 and 1 load to Km 42 @ end of shift - MC-13199 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7510KL-20211030-13rd Party Services6634.196634.19 | KABI LAKE FOREST PRODUCTS LTD7510KL-20211030-13rd Party Services6634.196634.19OEWT-PA23-Lem | [5 empty] | 1 | 6634.19 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7510 | KL-20211030-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2389 | Each |  |  |  |  | 2389 | 310.57 | 2699.57 | 2021-10-30 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road to Km 45 to Km 43 and spreading spotted rock trucks loads. Rock truck hauling existing material from F088 to Morin @ Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas. | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44502 |  | 61 | 44503 | OP-20211030-1 | Excavator continue laying Geo and Spreading existing material for capping @ 21/22 Km - OP-90101 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7510KL-20211030-13rd Party Services23892389 | KABI LAKE FOREST PRODUCTS LTD7510KL-20211030-13rd Party Services23892389OEWT-PA23-Lem | [5 empty] | 1 | 2389 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7510 | KL-20211030-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5267 | Each |  |  |  |  | 5267 | 684.71 | 5951.71 | 2021-10-30 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road to Km 45 to Km 43 and spreading spotted rock trucks loads. Rock truck hauling existing material from F088 to Morin @ Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas. | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44502 |  | 61 | 44503 | JJR-20211030-1 | Excavator continuing loading existing material @ F052 for Capping as per Valard /rock truck hauling existing material from F052 to Km 22 - JJR-70282 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7510KL-20211030-13rd Party Services52675267 | KABI LAKE FOREST PRODUCTS LTD7510KL-20211030-13rd Party Services52675267OEWT-PA23-Lem | [5 empty] | 1 | 5267 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7512 | KL-20211030-3 | 53510912 | Access | 0 | 3rd Party Services | 1 | 4850.82 | Each |  |  |  |  | 4850.82 | 630.6066 | 5481.4266 | 2021-10-30 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 grading from Km 34 to Km 28 on 600 Road/ Grader 2 grading @ km 20 to Km 26 on 600 Road - SSF-14426 | 9 | E091-F009 | 600 Road | 0 | 44502 |  | 61 | 44472 | SSF-20211030-2 | Grader 1 grading from Km 34 to Km 28 on 600 Road/ Grader 2 grading @ km 20 to Km 26 on 600 Road - SSF-14426 |  |  |  |  | 09 | KABI LAKE FOREST PRODUCTS LTD7512KL-20211030-33rd Party Services4850.824850.82 | KABI LAKE FOREST PRODUCTS LTD7512KL-20211030-33rd Party Services4850.824850.82OEWT-PA23-Lem | [5 empty] | 1 | 4850.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7517 | KL-20211031-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 1411.82 | Each |  |  |  |  | 1411.82 | 183.5366 | 1595.3566 | 2021-10-31 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 43 to Km 40.5 and spreading spotted rock trucks loads /Excavator 2 leveling ruts and shaping road from F116 to F112 rock truck hauling existing material from F088 to Morin @ Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F033 - F071 | Paint Lake 2 | 0 | 44505 |  | 61 | 44519 | SSF-20211031-1 | Excavator Excavator leveling ruts from Km 30 to Km 33 - SSF-14429 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7517KL-20211031-13rd Party Services1411.821411.82 | KABI LAKE FOREST PRODUCTS LTD7517KL-20211031-13rd Party Services1411.821411.82OEWT-PA23-Lem | [5 empty] | 1 | 1411.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7517 | KL-20211031-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6634.19 | Each |  |  |  |  | 6634.19 | 862.4447 | 7496.6347 | 2021-10-31 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 43 to Km 40.5 and spreading spotted rock trucks loads /Excavator 2 leveling ruts and shaping road from F116 to F112 rock truck hauling existing material from F088 to Morin @ Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F033 - F071 | Paint Lake 2 | 0 | 44505 |  | 61 | 44519 | MC-20211031-1 | Excavator 1 continue laying Geo and spreading existing material @ Km 33.5/ Excavator 2 loading existing material @ F088 as per Valard/rock truck hauling from F088 to Km 34-33 and 1 load to Km 42 @ end of shift - MC-13200 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7517KL-20211031-13rd Party Services6634.196634.19 | KABI LAKE FOREST PRODUCTS LTD7517KL-20211031-13rd Party Services6634.196634.19OEWT-PA23-Lem | [5 empty] | 1 | 6634.19 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7517 | KL-20211031-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2421.82 | Each |  |  |  |  | 2421.82 | 314.8366 | 2736.6566 | 2021-10-31 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 43 to Km 40.5 and spreading spotted rock trucks loads /Excavator 2 leveling ruts and shaping road from F116 to F112 rock truck hauling existing material from F088 to Morin @ Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F033 - F071 | Paint Lake 2 | 0 | 44505 |  | 61 | 44519 | OP-20211031-1 | Excavator Spreading existing material and placing corduroy @ 22 Km - OP-90102 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7517KL-20211031-13rd Party Services2421.822421.82 | KABI LAKE FOREST PRODUCTS LTD7517KL-20211031-13rd Party Services2421.822421.82OEWT-PA23-Lem | [5 empty] | 1 | 2421.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7517 | KL-20211031-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 3582.73 | Each |  |  |  |  | 3582.73 | 465.7549 | 4048.4849 | 2021-10-31 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 43 to Km 40.5 and spreading spotted rock trucks loads /Excavator 2 leveling ruts and shaping road from F116 to F112 rock truck hauling existing material from F088 to Morin @ Km 33.5 as per Valard /supervision of Morin, Skagen, Pleson and Opas | 10 | F033 - F071 | Paint Lake 2 | 0 | 44505 |  | 61 | 44519 | JJR-20211031-1 | Excavator loading existing material @ F052 for Capping and start reclaiming excavation as per Valard /rock truck hauling existing material from F052 to Km 22 - JJR-70283 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7517KL-20211031-13rd Party Services3582.733582.73 | KABI LAKE FOREST PRODUCTS LTD7517KL-20211031-13rd Party Services3582.733582.73OEWT-PA23-Lem | [5 empty] | 1 | 3582.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7518 | KL-20211031-2 | 53510912 | Access | 0 | 3rd Party Services | 1 | 2554 | Each |  |  |  |  | 2554 | 332.02 | 2886.02 | 2021-10-31 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader 1 finish grading from Km 28 to Km 26 and sections from Km 29 to 31 on 600 Road/ Grader 2 grading hills from km 20 to Km 1 on 600 Road - SSF-14428 | 9 | E092-F009 | 600 Road | 0 | 44505 |  | 61 | 44519 | SSF-20211031-2 | Grader 1 finish grading from Km 28 to Km 26 and sections from Km 29 to 31 on 600 Road/ Grader 2 grading hills from km 20 to Km 1 on 600 Road - SSF-14428 |  |  |  |  | 09 | KABI LAKE FOREST PRODUCTS LTD7518KL-20211031-23rd Party Services25542554 | KABI LAKE FOREST PRODUCTS LTD7518KL-20211031-23rd Party Services25542554OEWT-PA23-Lem | [5 empty] | 1 | 2554 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7519 | KL-20211101-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4181.09 | Each |  |  |  |  | 4181.09 | 543.5417 | 4724.6317 | 2021-11-01 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 43 to Km 40.5 and spreading spotted rock trucks loads. Rock truck hauling existing material from F-088 to Morin @ 33.5Km as per Valard. Supervision of Morin, Skagen, JJR & Opas | 10 | F033 - F071 | Paint Lake 2 | 0 | 44501 |  | 61 | 44519 | SSF-20211101-1 | Excavator levelling ruts, tracking existing material & shaping road from 30Km to 33Km. Grader travelling from 29 Km on 600 road & start grading to 1.5Km on Paint Lake Road 2. SSF-14430 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7519KL-20211101-13rd Party Services4181.094181.09 | KABI LAKE FOREST PRODUCTS LTD7519KL-20211101-13rd Party Services4181.094181.09OEWT-PA23-Lem | [5 empty] | 1 | 4181.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7519 | KL-20211101-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6634.19 | Each |  |  |  |  | 6634.19 | 862.4447 | 7496.6347 | 2021-11-01 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 43 to Km 40.5 and spreading spotted rock trucks loads. Rock truck hauling existing material from F-088 to Morin @ 33.5Km as per Valard. Supervision of Morin, Skagen, JJR & Opas | 10 | F033 - F071 | Paint Lake 2 | 0 | 44501 |  | 61 | 44519 | MC-20211101-1 | Excavator 1 continue laying Geo and spreading existing material @ Km 33.5/ Excavator 2 loading existing material @ F088 as per Valard/rock truck hauling from F088 to Km 33.5 and 1 load to Km 42 @ end of shift - MC-13201 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7519KL-20211101-13rd Party Services6634.196634.19 | KABI LAKE FOREST PRODUCTS LTD7519KL-20211101-13rd Party Services6634.196634.19OEWT-PA23-Lem | [5 empty] | 1 | 6634.19 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7519 | KL-20211101-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2639 | Each |  |  |  |  | 2639 | 343.07 | 2982.07 | 2021-11-01 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 43 to Km 40.5 and spreading spotted rock trucks loads. Rock truck hauling existing material from F-088 to Morin @ 33.5Km as per Valard. Supervision of Morin, Skagen, JJR & Opas | 10 | F033 - F071 | Paint Lake 2 | 0 | 44501 |  | 61 | 44519 | OP-20211101-1 | Excavator continuing spreading existing material & placing corduroy @ 22Km. OP-90103 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7519KL-20211101-13rd Party Services26392639 | KABI LAKE FOREST PRODUCTS LTD7519KL-20211101-13rd Party Services26392639OEWT-PA23-Lem | [5 empty] | 1 | 2639 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7519 | KL-20211101-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5267 | Each |  |  |  |  | 5267 | 684.71 | 5951.71 | 2021-11-01 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 shaping road to Km 43 to Km 40.5 and spreading spotted rock trucks loads. Rock truck hauling existing material from F-088 to Morin @ 33.5Km as per Valard. Supervision of Morin, Skagen, JJR & Opas | 10 | F033 - F071 | Paint Lake 2 | 0 | 44501 |  | 61 | 44519 | JJR-20211101-1 | Excavator loading trees & existing material @ F052 for capping as per Valard. Rock truck hauling existing material & trees from F-052 to 22/23 Km. JJR-70284 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7519KL-20211101-13rd Party Services52675267 | KABI LAKE FOREST PRODUCTS LTD7519KL-20211101-13rd Party Services52675267OEWT-PA23-Lem | [5 empty] | 1 | 5267 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7547 | KL-20211102-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 3432.54 | Each |  |  |  |  | 3432.54 | 446.2302 | 3878.7702 | 2021-11-02 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking from Km 43 to Km 17 on Hensen Road for float access /Rock truck hauling existing material from F088 to Morin@Km 33 as per Valard. Supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | SSF-20211102-1 | Excavator leveling ruts, tracking existing material and shaping road from Km 30 to Km 33 /Grader working from Km 10.5 to Km 7 on Paint Lake Road 2 - SSF-14431 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-23rd Party Services3432.543432.54 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-23rd Party Services3432.543432.54OEWT-PA23-Lem | [5 empty] | 1 | 3432.54 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7547 | KL-20211102-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6634.19 | Each |  |  |  |  | 6634.19 | 862.4447 | 7496.6347 | 2021-11-02 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking from Km 43 to Km 17 on Hensen Road for float access /Rock truck hauling existing material from F088 to Morin@Km 33 as per Valard. Supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | MC-20211102-1 | Excavator 1 continue laying Geo and spreading existing material @ Km 33/ Excavator 2 loading existing material @ F088 as per Valard/rock truck hauling from F088 to Km 33 and 1 load to Km 42 @ end of shift - MC-13202 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-23rd Party Services6634.196634.19 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-23rd Party Services6634.196634.19OEWT-PA23-Lem | [5 empty] | 1 | 6634.19 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7547 | KL-20211102-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2889 | Each |  |  |  |  | 2889 | 375.57 | 3264.57 | 2021-11-02 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking from Km 43 to Km 17 on Hensen Road for float access /Rock truck hauling existing material from F088 to Morin@Km 33 as per Valard. Supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | OP-20211102-1 | Excavator continuing Spreading existing material and placing corduroy @ 23 Km - OP-90104 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-23rd Party Services28892889 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-23rd Party Services28892889OEWT-PA23-Lem | [5 empty] | 1 | 2889 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7547 | KL-20211102-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4783.82 | Each |  |  |  |  | 4783.82 | 621.8966 | 5405.7166 | 2021-11-02 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking from Km 43 to Km 17 on Hensen Road for float access /Rock truck hauling existing material from F088 to Morin@Km 33 as per Valard. Supervision of Morin, Skagen, Pleson and Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | JJR-20211102-1 | Excavator Finishing loading trees and existing material @ F052 for Capping @ Km 23 as per Valard /rock truck hauling existing material and trees from F052 to Km 23 - JJR-70285 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-23rd Party Services4783.824783.82 | KABI LAKE FOREST PRODUCTS LTD7547KL-20211102-23rd Party Services4783.824783.82OEWT-PA23-Lem | [5 empty] | 1 | 4783.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7549 | KL-20211103-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4129.09 | Each |  |  |  |  | 4129.09 | 536.7817 | 4665.8717 | 2021-11-03 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 41 shape road. Rock trucks haul existing material from F088 to Morin @ Km 33 as per Valard /Supervision of Morin, Skagen, JJR, Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | SSF-20211103-1 | Excavator cutting hill @ Km 31.5, piling up existing material for capping of corduroy and making turn arounds/Grader finishing grading of Paint Lake Road 2 - SSF-14432 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-23rd Party Services4129.094129.09 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-23rd Party Services4129.094129.09OEWT-PA23-Lem | [5 empty] | 1 | 4129.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7549 | KL-20211103-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6534.1 | Each |  |  |  |  | 6534.1 | 849.433 | 7383.533 | 2021-11-03 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 41 shape road. Rock trucks haul existing material from F088 to Morin @ Km 33 as per Valard /Supervision of Morin, Skagen, JJR, Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | MC-20211103-1 | Excavator 1 Continuing laying Geo and Spreading existing material @ km 33/Excavator 2 loading existing material @ F088 as per Valard/rock truck hauling from F088 to Km 33 - MC-13203 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-23rd Party Services6534.16534.1 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-23rd Party Services6534.16534.1OEWT-PA23-Lem | [5 empty] | 1 | 6534.1 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7549 | KL-20211103-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2530.41 | Each |  |  |  |  | 2530.41 | 328.9533 | 2859.3633 | 2021-11-03 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 41 shape road. Rock trucks haul existing material from F088 to Morin @ Km 33 as per Valard /Supervision of Morin, Skagen, JJR, Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | OP-20211103-1 | Excavator shaping road and working on drainage from km 23 to km 24 - OP-90105 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-23rd Party Services2530.412530.41 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-23rd Party Services2530.412530.41OEWT-PA23-Lem | [5 empty] | 1 | 2530.41 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7549 | KL-20211103-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4800.32 | Each |  |  |  |  | 4800.32 | 624.0416 | 5424.3616 | 2021-11-03 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 41 shape road. Rock trucks haul existing material from F088 to Morin @ Km 33 as per Valard /Supervision of Morin, Skagen, JJR, Opas | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | JJR-20211103-1 | Excavator cleaning up and shaping excavation @F052, Start road from Km 21 to Km 23/Rock truck hauling for striping crews@ F048 as per Valard - JJR-70286 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-23rd Party Services4800.324800.32 | KABI LAKE FOREST PRODUCTS LTD7549KL-20211103-23rd Party Services4800.324800.32OEWT-PA23-Lem | [5 empty] | 1 | 4800.32 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7550 | KL-20211104-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-11-04 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 42 shaping road and spreading existing material on road surfaces Rock trucks hauling existing material from F088 to @ Km 43/42 as per Valard /Supervision of Morin, Skagen, JJR and OPAS | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | SSF-20211104-1 | Excavator loading existing materials and trees @ Km 31.5 as per Valard - SSF-14433 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-23rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-23rd Party Services2323.642323.64OEWT-PA23-Lem | [5 empty] | 1 | 2323.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7550 | KL-20211104-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6534.1 | Each |  |  |  |  | 6534.1 | 849.433 | 7383.533 | 2021-11-04 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 42 shaping road and spreading existing material on road surfaces Rock trucks hauling existing material from F088 to @ Km 43/42 as per Valard /Supervision of Morin, Skagen, JJR and OPAS | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | MC-20211104-1 | Excavator 1 Continuing laying Geo and Spreading existing material @ km 32/Excavator 2 loading existing material @ F088 as per Valard/rock truck hauling fromKm 31 to Km 32 and trees to Km 33- MC-13204 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-23rd Party Services6534.16534.1 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-23rd Party Services6534.16534.1OEWT-PA23-Lem | [5 empty] | 1 | 6534.1 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7550 | KL-20211104-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2889 | Each |  |  |  |  | 2889 | 375.57 | 3264.57 | 2021-11-04 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 42 shaping road and spreading existing material on road surfaces Rock trucks hauling existing material from F088 to @ Km 43/42 as per Valard /Supervision of Morin, Skagen, JJR and OPAS | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | OP-20211104-1 | Excavator laying Geo and spreading existing material @ km 23 - OP-90106 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-23rd Party Services28892889 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-23rd Party Services28892889OEWT-PA23-Lem | [5 empty] | 1 | 2889 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7550 | KL-20211104-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5017 | Each |  |  |  |  | 5017 | 652.21 | 5669.21 | 2021-11-04 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 42 shaping road and spreading existing material on road surfaces Rock trucks hauling existing material from F088 to @ Km 43/42 as per Valard /Supervision of Morin, Skagen, JJR and OPAS | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44517 |  | 61 | 44519 | JJR-20211104-1 | Excavator loading existing Materials and trees @ Km 24/Rock truck hauling 2 Access mats from Km 9.2 to Km 23 and existing material from km 24 to km 23 - JJR-70287 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-23rd Party Services50175017 | KABI LAKE FOREST PRODUCTS LTD7550KL-20211104-23rd Party Services50175017OEWT-PA23-Lem | [5 empty] | 1 | 5017 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7551 | KL-20211105-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-11-05 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 42 to Km 41 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F088 to @ Km 42/41 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint lake Road 2 | 0 | 44517 |  | 61 | 44519 | SSF-20211105-1 | Excavator loading existing materials @ Km 31.5 and shaping road @ end of shift for pickup access - SSF-14434 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-23rd Party Services2581.822581.82OEWT-PA23-Lem | [5 empty] | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7551 | KL-20211105-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5646.36 | Each |  |  |  |  | 5646.36 | 734.0268 | 6380.3868 | 2021-11-05 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 42 to Km 41 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F088 to @ Km 42/41 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint lake Road 2 | 0 | 44517 |  | 61 | 44519 | MC-20211105-1 | Excavator 1 Continuing laying Geo and Spreading existing material @ km 32 for capping/Excavator 2 loading existing material @ F088 as per Valard/rock truck hauling from Km 31 to Km 32 - MC-13205 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-23rd Party Services5646.365646.36 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-23rd Party Services5646.365646.36OEWT-PA23-Lem | [5 empty] | 1 | 5646.36 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7551 | KL-20211105-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2889 | Each |  |  |  |  | 2889 | 375.57 | 3264.57 | 2021-11-05 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 42 to Km 41 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F088 to @ Km 42/41 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint lake Road 2 | 0 | 44517 |  | 61 | 44519 | OP-20211105-1 | Excavator laying Geo and spreading existing material for capping @ km 24 - OP-90107 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-23rd Party Services28892889 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-23rd Party Services28892889OEWT-PA23-Lem | [5 empty] | 1 | 2889 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7551 | KL-20211105-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5017 | Each |  |  |  |  | 5017 | 652.21 | 5669.21 | 2021-11-05 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 42 to Km 41 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F088 to @ Km 42/41 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint lake Road 2 | 0 | 44517 |  | 61 | 44519 | JJR-20211105-1 | Excavator loading existing Materials and trees @ Km 26/Rock truck hauling existing material and trees from km 26 to km 24 - JJR-70288 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-23rd Party Services50175017 | KABI LAKE FOREST PRODUCTS LTD7551KL-20211105-23rd Party Services50175017OEWT-PA23-Lem | [5 empty] | 1 | 5017 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7553 | KL-20211107-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 1290.91 | Each |  |  |  |  | 1290.91 | 167.8183 | 1458.7283 | 2021-11-07 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working fro Km 41 to Km 39 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 41/39 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44519 | SSF-20211107-1 | Excavator Finishing clean up of excavation @ Km 31.5 and leveling ruts from 31 to 32.5 Km for pickup access - SSF-14436 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-23rd Party Services1290.911290.91 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-23rd Party Services1290.911290.91OEWT-PA23-Lem | [5 empty] | 1 | 1290.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7553 | KL-20211107-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4439.96 | Each |  |  |  |  | 4439.96 | 577.1948 | 5017.1548 | 2021-11-07 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working fro Km 41 to Km 39 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 41/39 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44519 | MC-20211107-1 | Excavator loading existing material on Kabi rock truck @ F089 as per Valard/rock truck hauling from Km 27 to JJR @ KM 24 - MC-13207 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-23rd Party Services4439.964439.96 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-23rd Party Services4439.964439.96OEWT-PA23-Lem | [5 empty] | 1 | 4439.96 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7563 | KL-20211108-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2065.45 | Each |  |  |  |  | 2065.45 | 268.5085 | 2333.9585 | 2021-11-08 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 42 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | SSF-20211108-1 | Excavator leveling ruts and shaping road from 31 to 33 Km for pickup access - SSF-14437 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-33rd Party Services2065.452065.45 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-33rd Party Services2065.452065.45OEWT-PA23-Lem | [5 empty] | 1 | 2065.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7563 | KL-20211108-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4552.55 | Each |  |  |  |  | 4552.55 | 591.8315 | 5144.3815 | 2021-11-08 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 42 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | MC-20211108-1 | Excavator loading existing material on Kabi rock truck @ F089 and start shaping road from Km 37 to 36/rock truck hauling from Km 27 to JJR @ KM 24 - MC-13208 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-33rd Party Services4552.554552.55 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-33rd Party Services4552.554552.55OEWT-PA23-Lem | [5 empty] | 1 | 4552.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7563 | KL-20211108-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2889 | Each |  |  |  |  | 2889 | 375.57 | 3264.57 | 2021-11-08 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 42 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | OP-20211108-1 | Excavator continue loading existing material for capping @ km 24 - OP-90110 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-33rd Party Services28892889 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-33rd Party Services28892889OEWT-PA23-Lem | [5 empty] | 1 | 2889 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7563 | KL-20211108-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5017 | Each |  |  |  |  | 5017 | 652.21 | 5669.21 | 2021-11-08 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 42 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | JJR-20211108-1 | Excavator continuing spreading existing Materials @ Km 24/Rock truck hauling existing material from km 27 to Km 24 - JJR-70291 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-33rd Party Services50175017 | KABI LAKE FOREST PRODUCTS LTD7563KL-20211108-33rd Party Services50175017OEWT-PA23-Lem | [5 empty] | 1 | 5017 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7553 | KL-20211107-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2986.5 | Each |  |  |  |  | 2986.5 | 388.245 | 3374.745 | 2021-11-07 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working fro Km 41 to Km 39 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 41/39 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44519 | OP-20211107-1 | Excavator tracking to Km 27 and start loading existing material for capping @ km 24 - OP-90109 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-23rd Party Services2986.52986.5 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-23rd Party Services2986.52986.5OEWT-PA23-Lem | [5 empty] | 1 | 2986.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7553 | KL-20211107-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5017 | Each |  |  |  |  | 5017 | 652.21 | 5669.21 | 2021-11-07 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working fro Km 41 to Km 39 shaping road and spreading existing material on road sections Kabi Rock truck hauling existing material from F089 to Km 41/39 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44519 | JJR-20211107-1 | Excavator loading existing Materials @ F058 access and continuing @ Km 24/Rock truck hauling existing material from km 27 to F058 and Km 24 - JJR-70290 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-23rd Party Services50175017 | KABI LAKE FOREST PRODUCTS LTD7553KL-20211107-23rd Party Services50175017OEWT-PA23-Lem | [5 empty] | 1 | 5017 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7562 | KL-20211106-2-R1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-11-06 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 41 to Km 40 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F093 to @ Km 41/40 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44522 | SSF-20211106-1 | Excavator Finishing loading existing materials @ Km 31.5 and shaping road @ end of shift for pickup access - SSF-14435 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R13rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R13rd Party Services2323.642323.64OEWT-PA23-Lem | [5 empty] | 1 | 2323.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7562 | KL-20211106-2-R1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6556.28 | Each |  |  |  |  | 6556.28 | 852.3164 | 7408.5964 | 2021-11-06 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 41 to Km 40 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F093 to @ Km 41/40 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44522 | MC-20211106-1 | Excavator 1 Finishing laying Geo and Spreading existing material @ km 32/31 for capping/Excavator 2 loading existing material @ F093 as per Valard/rock truck hauling from Km 31 to Km 32 - MC-13206 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R13rd Party Services6556.286556.28 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R13rd Party Services6556.286556.28OEWT-PA23-Lem | [5 empty] | 1 | 6556.28 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7562 | KL-20211106-2-R1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2541.5 | Each |  |  |  |  | 2541.5 | 330.395 | 2871.895 | 2021-11-06 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 41 to Km 40 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F093 to @ Km 41/40 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44522 | OP-20211106-1 | Excavator continuing laying Geo and spreading existing material for capping @ km 24 and shaping road to Km 22 - OP-90108 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R13rd Party Services2541.52541.5 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R13rd Party Services2541.52541.5OEWT-PA23-Lem | [5 empty] | 1 | 2541.5 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7562 | KL-20211106-2-R1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4199.77 | Each |  |  |  |  | 4199.77 | 545.9701 | 4745.7401 | 2021-11-06 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 41 to Km 40 shaping road and spreading existing material on road sections Rock trucks hauling existing material from F093 to @ Km 41/40 as per Valard /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 61 | 44522 | JJR-20211106-1 | Excavator loading existing Materials @ Km 26 and shaping road to F058/Rock truck hauling existing material from km 26 to Opas - JJR-70289 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R13rd Party Services4199.774199.77 | KABI LAKE FOREST PRODUCTS LTD7562KL-20211106-2-R13rd Party Services4199.774199.77OEWT-PA23-Lem | [5 empty] | 1 | 4199.77 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7564 | KL-20211109-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2452.73 | Each |  |  |  |  | 2452.73 | 318.8549 | 2771.5849 | 2021-11-09 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 44 leveling ruts and shaping road Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | SSF-20211109-1 | Excavator Continuing leveling ruts and shaping road from 34 to 39 Km for pickup access - SSF-14438 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-33rd Party Services2452.732452.73 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-33rd Party Services2452.732452.73OEWT-PA23-Lem | [5 empty] | 1 | 2452.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7564 | KL-20211109-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4206.28 | Each |  |  |  |  | 4206.28 | 546.8164 | 4753.0964 | 2021-11-09 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 44 leveling ruts and shaping road Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | MC-20211109-1 | Excavator leveling ruts from km 33 to km 30 and spreading existing material @ km 30 corduroy/ rock truck hauling from Km 27 to Km 30 - MC-13209 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-33rd Party Services4206.284206.28 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-33rd Party Services4206.284206.28OEWT-PA23-Lem | [5 empty] | 1 | 4206.28 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7564 | KL-20211109-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2694 | Each |  |  |  |  | 2694 | 350.22 | 3044.22 | 2021-11-09 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 44 leveling ruts and shaping road Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | OP-20211109-1 | Excavator continue loading existing material @ km 27 for capping as per Valard - OP-90111 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-33rd Party Services26942694 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-33rd Party Services26942694OEWT-PA23-Lem | [5 empty] | 1 | 2694 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7564 | KL-20211109-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4583.64 | Each |  |  |  |  | 4583.64 | 595.8732 | 5179.5132 | 2021-11-09 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 40 to Km 44 leveling ruts and shaping road Kabi Rock truck hauling existing material from F089 to Km 40 and 27 to Km 24 /Chapman rock truck hauling from Km 27 to JJR @ Km 24/Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | JJR-20211109-1 | Excavator continuing spreading existing Materials @ Km 24/23 /Rock truck hauling existing material from km 27 to Km 24/23 - JJR-70292 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-33rd Party Services4583.644583.64 | KABI LAKE FOREST PRODUCTS LTD7564KL-20211109-33rd Party Services4583.644583.64OEWT-PA23-Lem | [5 empty] | 1 | 4583.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7565 | KL-20211110-4 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-11-10 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 42 access leveling ruts and shaping road rock trucks hauling from Km 27 to JJR @ Km 26/24 repairing road sections /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | SSF-20211110-1 | Excavator Continuing leveling ruts and shaping road from 39 to 42 Km and spur roads- SSF-14439 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-43rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-43rd Party Services2581.822581.82OEWT-PA23-Lem | [5 empty] | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7565 | KL-20211110-4 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4423.64 | Each |  |  |  |  | 4423.64 | 575.0732 | 4998.7132 | 2021-11-10 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 42 access leveling ruts and shaping road rock trucks hauling from Km 27 to JJR @ Km 26/24 repairing road sections /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | MC-20211110-1 | Excavator continuing leveling ruts from km 33 to km 30 and spreading existing material @ km 30 corduroy/ rock truck hauling from Km 27 to Km 30 - MC-13210 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-43rd Party Services4423.644423.64 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-43rd Party Services4423.644423.64OEWT-PA23-Lem | [5 empty] | 1 | 4423.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7565 | KL-20211110-4 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2889 | Each |  |  |  |  | 2889 | 375.57 | 3264.57 | 2021-11-10 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 42 access leveling ruts and shaping road rock trucks hauling from Km 27 to JJR @ Km 26/24 repairing road sections /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | OP-20211110-1 | Excavator continue loading existing material @ km 27 for road repairs@ Km 24/26 as per Valard - OP-90112 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-43rd Party Services28892889 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-43rd Party Services28892889OEWT-PA23-Lem | [5 empty] | 1 | 2889 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7565 | KL-20211110-4 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5017 | Each |  |  |  |  | 5017 | 652.21 | 5669.21 | 2021-11-10 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 44 to Km 42 access leveling ruts and shaping road rock trucks hauling from Km 27 to JJR @ Km 26/24 repairing road sections /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | JJR-20211110-1 | Excavator spreading existing Materials @ Km 24/26 for road repairs /Rock truck hauling existing material from km 27 to Km 24/26 - JJR-70293 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-43rd Party Services50175017 | KABI LAKE FOREST PRODUCTS LTD7565KL-20211110-43rd Party Services50175017OEWT-PA23-Lem | [5 empty] | 1 | 5017 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7566 | KL-20211111-4 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-11-11 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | SSF-20211111-1 | Excavator Continuing leveling ruts and shaping road from 42 to 45 Km and spur roads- SSF-14440 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-43rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-43rd Party Services2581.822581.82OEWT-PA23-Lem | [5 empty] | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7566 | KL-20211111-4 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2251.82 | Each |  |  |  |  | 2251.82 | 292.7366 | 2544.5566 | 2021-11-11 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | MC-20211111-1 | Rock truck hauling from Km 27 to JJR @ Km 24 - MC-13211 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-43rd Party Services2251.822251.82 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-43rd Party Services2251.822251.82OEWT-PA23-Lem | [5 empty] | 1 | 2251.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7566 | KL-20211111-4 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2780.41 | Each |  |  |  |  | 2780.41 | 361.4533 | 3141.8633 | 2021-11-11 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | OP-20211111-1 | Excavator continue loading existing material @ km 27 for Capping @ Km 24/26 as per Valard - OP-90113 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-43rd Party Services2780.412780.41 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-43rd Party Services2780.412780.41OEWT-PA23-Lem | [5 empty] | 1 | 2780.41 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7566 | KL-20211111-4 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4800.32 | Each |  |  |  |  | 4800.32 | 624.0416 | 5424.3616 | 2021-11-11 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44517 |  | 46 | 44525 | JJR-20211111-1 | Excavator spreading existing Materials for Capping @ Km 24 /Rock truck hauling existing material from km 27 to Km 24 - JJR-70294 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-43rd Party Services4800.324800.32 | KABI LAKE FOREST PRODUCTS LTD7566KL-20211111-43rd Party Services4800.324800.32OEWT-PA23-Lem | [5 empty] | 1 | 4800.32 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7570 | KL-20211112-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-11-12 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44520 |  | 46 | 44525 | SSF-20211112-1 | Excavator Continuing leveling ruts and shaping road from 45 to 48 Km- SSF-14441 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7570KL-20211112-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7570KL-20211112-23rd Party Services2581.822581.82OEWT-PA23-Lem | [5 empty] | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7570 | KL-20211112-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2251.82 | Each |  |  |  |  | 2251.82 | 292.7366 | 2544.5566 | 2021-11-12 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44520 |  | 46 | 44525 | MC-20211112-1 | Rock truck on site for hauling of existing material @ 27km driving from 32km on Paint Lake Road 2 to 0.5km on Hensen Road for float access - MC-13212 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7570KL-20211112-23rd Party Services2251.822251.82 | KABI LAKE FOREST PRODUCTS LTD7570KL-20211112-23rd Party Services2251.822251.82OEWT-PA23-Lem | [5 empty] | 1 | 2251.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7570 | KL-20211112-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2429.64 | Each |  |  |  |  | 2429.64 | 315.8532 | 2745.4932 | 2021-11-12 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44520 |  | 46 | 44525 | OP-20211112-1 | Excavator starting cleaning up, shaping and sloping excavation @ 27km as per Valard - OP-90114 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7570KL-20211112-23rd Party Services2429.642429.64 | KABI LAKE FOREST PRODUCTS LTD7570KL-20211112-23rd Party Services2429.642429.64OEWT-PA23-Lem | [5 empty] | 1 | 2429.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7570 | KL-20211112-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 3324.55 | Each |  |  |  |  | 3324.55 | 432.1915 | 3756.7415 | 2021-11-12 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from Km 43 to Km 40 leveling ruts and shaping road. rock trucks from Km 27 to JJR @ Km 24 /Supervision of Morin, Skagen, JJR and Opas | 10 | F066-F118 | Paint Lake 2 | 0 | 44520 |  | 46 | 44525 | JJR-20211112-1 | Excavator levelling ruts, shaping road and spreading existing Material @ 23 / 24Kms. Rock truck on site for hauling of existing material from km 27 - JJR-70295 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7570KL-20211112-23rd Party Services3324.553324.55 | KABI LAKE FOREST PRODUCTS LTD7570KL-20211112-23rd Party Services3324.553324.55OEWT-PA23-Lem | [5 empty] | 1 | 3324.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7571 | KL-20211113-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-11-13 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Rock truck on site for hauling of existing material @ 24km. Supervision of Morin, Skagen, JJR & Opas. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | SSF-20211113-1 | Excavator Continuing leveling ruts and shaping road from 48 Km to F114 in support of Erection Crews. SSF-14442 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7571KL-20211113-33rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7571KL-20211113-33rd Party Services2581.822581.82OEWT-PA23-Lem | [5 empty] | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7571 | KL-20211113-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2300.73 | Each |  |  |  |  | 2300.73 | 299.0949 | 2599.8249 | 2021-11-13 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Rock truck on site for hauling of existing material @ 24km. Supervision of Morin, Skagen, JJR & Opas. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | MC-20211113-1 | Excavator continuing levelling ruts & shaping road from 33 Km to 30.5 Km. MC-13213 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7571KL-20211113-33rd Party Services2300.732300.73 | KABI LAKE FOREST PRODUCTS LTD7571KL-20211113-33rd Party Services2300.732300.73OEWT-PA23-Lem | [5 empty] | 1 | 2300.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7571 | KL-20211113-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2780.41 | Each |  |  |  |  | 2780.41 | 361.4533 | 3141.8633 | 2021-11-13 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Rock truck on site for hauling of existing material @ 24km. Supervision of Morin, Skagen, JJR & Opas. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | OP-20211113-1 | Excavator finishing cleaning up, shaping and sloping excavation @ 27km. Shape road from 27 to 23.5Km. OP-90115 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7571KL-20211113-33rd Party Services2780.412780.41 | KABI LAKE FOREST PRODUCTS LTD7571KL-20211113-33rd Party Services2780.412780.41OEWT-PA23-Lem | [5 empty] | 1 | 2780.41 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7571 | KL-20211113-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 3499.14 | Each |  |  |  |  | 3499.14 | 454.8882 | 3954.0282 | 2021-11-13 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Rock truck on site for hauling of existing material @ 24km. Supervision of Morin, Skagen, JJR & Opas. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | JJR-20211113-1 | Excavator levelling ruts, shaping road @ 23 to 21Kms. Rock truck on site for hauling of existing material from km 27 for road capping @ 24Km. - JJR-70296 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7571KL-20211113-33rd Party Services3499.143499.14 | KABI LAKE FOREST PRODUCTS LTD7571KL-20211113-33rd Party Services3499.143499.14OEWT-PA23-Lem | [5 empty] | 1 | 3499.14 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7572 | KL-20211114-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-11-14 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from 44Km to 41Km levelling ruts and shaping road. Rock truck on site for hauling of existing material @ 27Km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | SSF-20211114-1 | Excavator Continuing leveling ruts and shaping road from F115 to F112 in support of Erection Crews. SSF-14443 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7572KL-20211114-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7572KL-20211114-23rd Party Services2581.822581.82OEWT-PA23-Lem | [5 empty] | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7572 | KL-20211114-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2300.73 | Each |  |  |  |  | 2300.73 | 299.0949 | 2599.8249 | 2021-11-14 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from 44Km to 41Km levelling ruts and shaping road. Rock truck on site for hauling of existing material @ 27Km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | MC-20211114-1 | Excavator continuing levelling ruts & shaping road from 33 Km to 31 Km and F-072 access. MC-13214 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7572KL-20211114-23rd Party Services2300.732300.73 | KABI LAKE FOREST PRODUCTS LTD7572KL-20211114-23rd Party Services2300.732300.73OEWT-PA23-Lem | [5 empty] | 1 | 2300.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7572 | KL-20211114-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2780.41 | Each |  |  |  |  | 2780.41 | 361.4533 | 3141.8633 | 2021-11-14 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from 44Km to 41Km levelling ruts and shaping road. Rock truck on site for hauling of existing material @ 27Km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | OP-20211114-1 | Excavator levelling ruts and shaping road from 24Km to 22Km. OP-90116 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7572KL-20211114-23rd Party Services2780.412780.41 | KABI LAKE FOREST PRODUCTS LTD7572KL-20211114-23rd Party Services2780.412780.41OEWT-PA23-Lem | [5 empty] | 1 | 2780.41 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7572 | KL-20211114-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 3499.14 | Each |  |  |  |  | 3499.14 | 454.8882 | 3954.0282 | 2021-11-14 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working from 44Km to 41Km levelling ruts and shaping road. Rock truck on site for hauling of existing material @ 27Km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | JJR-20211114-1 | Excavator continuing levelling ruts, shaping road @ 23 to 20Kms. Rock truck on site for hauling of existing material from km 27 for road capping @ 24Km. - JJR-70297 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7572KL-20211114-23rd Party Services3499.143499.14 | KABI LAKE FOREST PRODUCTS LTD7572KL-20211114-23rd Party Services3499.143499.14OEWT-PA23-Lem | [5 empty] | 1 | 3499.14 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7573 | KL-20211115-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2452.73 | Each |  |  |  |  | 2452.73 | 318.8549 | 2771.5849 | 2021-11-15 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road. Rock truck hauling existing material from 25Km and spotting dumping @ 22/23Km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | MC-20211115-1 | Excavator continuing levelling ruts & shaping road from 32 Km to 35 Km. MC-13215 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7573KL-20211115-23rd Party Services2452.732452.73 | KABI LAKE FOREST PRODUCTS LTD7573KL-20211115-23rd Party Services2452.732452.73OEWT-PA23-Lem | [5 empty] | 1 | 2452.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7573 | KL-20211115-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2550.73 | Each |  |  |  |  | 2550.73 | 331.5949 | 2882.3249 | 2021-11-15 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road. Rock truck hauling existing material from 25Km and spotting dumping @ 22/23Km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | OP-20211115-1 | Excavator loading existing material at 25Km for capping at 23/22Km. OP-90117 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7573KL-20211115-23rd Party Services2550.732550.73 | KABI LAKE FOREST PRODUCTS LTD7573KL-20211115-23rd Party Services2550.732550.73OEWT-PA23-Lem | [5 empty] | 1 | 2550.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7573 | KL-20211115-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2551 | Each |  |  |  |  | 2551 | 331.63 | 2882.63 | 2021-11-15 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road. Rock truck hauling existing material from 25Km and spotting dumping @ 22/23Km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | JJR-20211115-1 | Excavator start spreading material, levelling ruts, shaping road @ 23Kms. Rock truck hauling existing material from km 2 for road capping @ 22/23Km. - JJR-70298 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7573KL-20211115-23rd Party Services25512551 | KABI LAKE FOREST PRODUCTS LTD7573KL-20211115-23rd Party Services25512551OEWT-PA23-Lem | [5 empty] | 1 | 2551 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7574 | KL-20211115-3 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-11-15 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader start grading sections of Hensen Road to 12Km. SSF-14444 | 11 | F118 - F127 | Henson | 0 | 44524 |  | 46 | 44525 | SSF-20211115-1 | Grader start grading sections of Hensen Road to 12Km. SSF-14444 |  |  |  | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7574KL-20211115-33rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD7574KL-20211115-33rd Party Services2321.822321.82OEWT-PA23-Lem | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7575 | KL-20211116-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 1549.09 | Each |  |  |  |  | 1549.09 | 201.3817 | 1750.4717 | 2021-11-16 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road for freezing. Rock truck hauling existing material from 27Km to 23/24Km & dricing out to 9Km at end of shift for float accesss. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | SSF-20211116-1 | Excavator starting levelling ruts, shaping road from F117 to F114. SSF-14445 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-33rd Party Services1549.091549.09 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-33rd Party Services1549.091549.09OEWT-PA23-Lem | [5 empty] | 1 | 1549.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7575 | KL-20211116-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2300.73 | Each |  |  |  |  | 2300.73 | 299.0949 | 2599.8249 | 2021-11-16 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road for freezing. Rock truck hauling existing material from 27Km to 23/24Km & dricing out to 9Km at end of shift for float accesss. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | MC-20211116-1 | Excavator levelling ruts & shaping road from 33 Km to 31.5 Km for freezing. MC-13216 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-33rd Party Services2300.732300.73 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-33rd Party Services2300.732300.73OEWT-PA23-Lem | [5 empty] | 1 | 2300.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7575 | KL-20211116-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2889 | Each |  |  |  |  | 2889 | 375.57 | 3264.57 | 2021-11-16 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road for freezing. Rock truck hauling existing material from 27Km to 23/24Km & dricing out to 9Km at end of shift for float accesss. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | OP-20211116-1 | Excavator loading existing material at 27Km for capping at 24/23Km & lean up excavation. OP-90118 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-33rd Party Services28892889 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-33rd Party Services28892889OEWT-PA23-Lem | [5 empty] | 1 | 2889 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7575 | KL-20211116-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2551 | Each |  |  |  |  | 2551 | 331.63 | 2882.63 | 2021-11-16 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing working from 44Km to 41Km levelling ruts and shaping road for freezing. Rock truck hauling existing material from 27Km to 23/24Km & dricing out to 9Km at end of shift for float accesss. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | JJR-20211116-1 | Excavator start spreading material and shaping road @ 23/24Kms. Rock truck hauling existing material from 25 & 27km & driving out to 9Km @ end of shift for float access. - JJR-70299 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-33rd Party Services25512551 | KABI LAKE FOREST PRODUCTS LTD7575KL-20211116-33rd Party Services25512551OEWT-PA23-Lem | [5 empty] | 1 | 2551 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7576 | KL-20211117-4 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-11-17 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road & snow removal @ 44km to 43km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | SSF-20211117-1 | Excavator finishing levelling ruts, shaping road from F114 to F112 & Access to Paint Lake Road 2. SSF-14446 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7576KL-20211117-43rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7576KL-20211117-43rd Party Services2581.822581.82OEWT-PA23-Lem | [5 empty] | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7576 | KL-20211117-4 | 53511012 | Access | 0 | 3rd Party Services | 1 | 1807.27 | Each |  |  |  |  | 1807.27 | 234.9451 | 2042.2151 | 2021-11-17 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road & snow removal @ 44km to 43km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | MC-20211117-1 | Excavator doing snow removal & scraping hills from 35Km to 40Km. MC-13217 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7576KL-20211117-43rd Party Services1807.271807.27 | KABI LAKE FOREST PRODUCTS LTD7576KL-20211117-43rd Party Services1807.271807.27OEWT-PA23-Lem | [5 empty] | 1 | 1807.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7576 | KL-20211117-4 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2780.41 | Each |  |  |  |  | 2780.41 | 361.4533 | 3141.8633 | 2021-11-17 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road & snow removal @ 44km to 43km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | OP-20211117-1 | Excavator finishing cleaning up excaation @ 27Km, snow removal & shaping road to 23Km. OP-90119 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7576KL-20211117-43rd Party Services2780.412780.41 | KABI LAKE FOREST PRODUCTS LTD7576KL-20211117-43rd Party Services2780.412780.41OEWT-PA23-Lem | [5 empty] | 1 | 2780.41 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7576 | KL-20211117-4 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2698.41 | Each |  |  |  |  | 2698.41 | 350.7933 | 3049.2033 | 2021-11-17 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road & snow removal @ 44km to 43km. Supervision of JJR, Opas, Morin, and Skagen. | 10 | F066-F118 | Paint Lake 2 | 0 | 44524 |  | 46 | 44525 | JJR-20211117-1 | Excavator finishing cleaning up excaation @ 27Km, snow removal & shaping road to 23Km. OP-90119 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7576KL-20211117-43rd Party Services2698.412698.41 | KABI LAKE FOREST PRODUCTS LTD7576KL-20211117-43rd Party Services2698.412698.41OEWT-PA23-Lem | [5 empty] | 1 | 2698.41 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7577 | KL-20211118-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2889 | Each |  |  |  |  | 2889 | 375.57 | 3264.57 | 2021-11-18 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 43 to Km 46 due to icy conditions /Supervision of Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44525 |  | 61 | 44530 | OP-20211118-1 | Excavator scraping and shaping road from Km 23 to Km 19 due to icy conditions - OP-90120 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7577KL-20211118-33rd Party Services28892889 | KABI LAKE FOREST PRODUCTS LTD7577KL-20211118-33rd Party Services28892889OEWT-PA23-Lem | [5 empty] | 1 | 2889 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7577 | KL-20211118-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2815 | Each |  |  |  |  | 2815 | 365.95 | 3180.95 | 2021-11-18 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 43 to Km 46 due to icy conditions /Supervision of Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44525 |  | 61 | 44530 | JJR-20211118-1 | Excavator shaping road and scraping hills from Km 19 to km 16 and 10.5 hill after hours due to icy conditions - JJR-70301 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7577KL-20211118-33rd Party Services28152815 | KABI LAKE FOREST PRODUCTS LTD7577KL-20211118-33rd Party Services28152815OEWT-PA23-Lem | [5 empty] | 1 | 2815 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7583 | KL-20211119-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-11-19 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 43 to Km 40 due to icy conditions/Supervision of Morin, Skagen, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | SSF-20211119-1 | Excavator shaping road and sanding with existing material from Km 48.5 to Km 46.5 - SSF-14447 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7583KL-20211119-33rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7583KL-20211119-33rd Party Services2323.642323.64OEWT-PA23-Lem | [5 empty] | 1 | 2323.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7583 | KL-20211119-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2179.64 | Each |  |  |  |  | 2179.64 | 283.3532 | 2462.9932 | 2021-11-19 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 43 to Km 40 due to icy conditions/Supervision of Morin, Skagen, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | MC-20211119-1 | Excavator scraping, shaping road and sanding hills from Km 33 to Km 31 - MC-13218 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7583KL-20211119-33rd Party Services2179.642179.64 | KABI LAKE FOREST PRODUCTS LTD7583KL-20211119-33rd Party Services2179.642179.64OEWT-PA23-Lem | [5 empty] | 1 | 2179.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7583 | KL-20211119-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2058.55 | Each |  |  |  |  | 2058.55 | 267.6115 | 2326.1615 | 2021-11-19 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 43 to Km 40 due to icy conditions/Supervision of Morin, Skagen, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | OP-20211119-1 | Excavator scraping and sanding road with existing material from Km 12 to 13.2 due to icy conditions - OP-90121 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7583KL-20211119-33rd Party Services2058.552058.55 | KABI LAKE FOREST PRODUCTS LTD7583KL-20211119-33rd Party Services2058.552058.55OEWT-PA23-Lem | [5 empty] | 1 | 2058.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7583 | KL-20211119-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2194.55 | Each |  |  |  |  | 2194.55 | 285.2915 | 2479.8415 | 2021-11-19 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 43 to Km 40 due to icy conditions/Supervision of Morin, Skagen, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | JJR-20211119-1 | Excavator shaping road, scraping hills and sanding with existing material from Km 19 to km 16 due to icy conditions - JJR-70302 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7583KL-20211119-33rd Party Services2194.552194.55 | KABI LAKE FOREST PRODUCTS LTD7583KL-20211119-33rd Party Services2194.552194.55OEWT-PA23-Lem | [5 empty] | 1 | 2194.55 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7584 | KL-20211120-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-11-20 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 42 to Km 46 due to slippery conditions/Supervision of Morin, Skagen, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | SSF-20211120-1 | Excavator finishing shaping road to Km 46 and back to Km 49 - SSF-14448 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7584KL-20211120-33rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7584KL-20211120-33rd Party Services2581.822581.82OEWT-PA23-Lem | [5 empty] | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7584 | KL-20211120-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2300.72 | Each |  |  |  |  | 2300.72 | 299.0936 | 2599.8136 | 2021-11-20 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 42 to Km 46 due to slippery conditions/Supervision of Morin, Skagen, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | MC-20211120-1 | Excavator shaping road from Km 31 to Km 28 and F071 Access - MC-13219 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7584KL-20211120-33rd Party Services2300.722300.72 | KABI LAKE FOREST PRODUCTS LTD7584KL-20211120-33rd Party Services2300.722300.72OEWT-PA23-Lem | [5 empty] | 1 | 2300.72 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7584 | KL-20211120-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2530.41 | Each |  |  |  |  | 2530.41 | 328.9533 | 2859.3633 | 2021-11-20 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and shaping road @ Km 42 to Km 46 due to slippery conditions/Supervision of Morin, Skagen, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | OP-20211120-1 | Excavator scraping and sanding road with existing material from Km 13.5 to 14.5 and shaping road to Km 22 - OP-90122 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7584KL-20211120-33rd Party Services2530.412530.41 | KABI LAKE FOREST PRODUCTS LTD7584KL-20211120-33rd Party Services2530.412530.41OEWT-PA23-Lem | [5 empty] | 1 | 2530.41 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7585 | KL-20211121-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 1937.45 | Each |  |  |  |  | 1937.45 | 251.8685 | 2189.3185 | 2021-11-21 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and sanding road @ Km 42 to Km 46 due to slippery conditions/Supervision of Morin, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | MC-20211121-1 | Excavator shaping road and scraping hills from Km 29.5 to Km 33 and F072 access - MC-13220 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7585KL-20211121-23rd Party Services1937.451937.45 | KABI LAKE FOREST PRODUCTS LTD7585KL-20211121-23rd Party Services1937.451937.45OEWT-PA23-Lem | [5 empty] | 1 | 1937.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7585 | KL-20211121-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2179.64 | Each |  |  |  |  | 2179.64 | 283.3532 | 2462.9932 | 2021-11-21 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and sanding road @ Km 42 to Km 46 due to slippery conditions/Supervision of Morin, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | OP-20211121-1 | Excavator scraping hills and shaping road from Km 21 to 24 - OP-90123 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7585KL-20211121-23rd Party Services2179.642179.64 | KABI LAKE FOREST PRODUCTS LTD7585KL-20211121-23rd Party Services2179.642179.64OEWT-PA23-Lem | [5 empty] | 1 | 2179.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7585 | KL-20211121-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-11-21 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping and sanding road @ Km 42 to Km 46 due to slippery conditions/Supervision of Morin, Opas and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44526 |  | 61 | 44530 | JJR-20211121-1 | Excavator shaping road, scraping hills and sanding with existing material from Km 14 to km 19 - JJR-70304 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7585KL-20211121-23rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7585KL-20211121-23rd Party Services2323.642323.64OEWT-PA23-Lem | [5 empty] | 1 | 2323.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7586 | KL-20211122-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 1695.27 | Each |  |  |  |  | 1695.27 | 220.3851 | 1915.6551 | 2021-11-22 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator scraping hills and sanding hills from Km 10.5 to 13.5 - OP-90124 | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | OP-20211122-1 | Excavator scraping hills and sanding hills from Km 10.5 to 13.5 - OP-90124 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7586KL-20211122-23rd Party Services1695.271695.27 | KABI LAKE FOREST PRODUCTS LTD7586KL-20211122-23rd Party Services1695.271695.27OEWT-PA23-Lem | [5 empty] | 1 | 1695.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7587 | KL-20211123-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-11-23 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 scraping and shaping @ Km 42 to Km 46 /Excavator 2 scraping and sanding Km 13.5 to 17 for stringing crews/Supervision of Skagen and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | SSF-20211123-1 | Grader doing snow removal from Km 0 to Km 23 on Paint Lake Road 2 and filling ruts - SSF-14449 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7587KL-20211123-23rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD7587KL-20211123-23rd Party Services2321.822321.82OEWT-PA23-Lem | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7587 | KL-20211123-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-11-23 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 scraping and shaping @ Km 42 to Km 46 /Excavator 2 scraping and sanding Km 13.5 to 17 for stringing crews/Supervision of Skagen and Pleson | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | JJR-20211123-1 | Excavator shaping road, scraping hills and sanding with existing material from Km 23 to km 19 - JJR-70305 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7587KL-20211123-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7587KL-20211123-23rd Party Services2581.822581.82OEWT-PA23-Lem | [5 empty] | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7591 | KL-20211124-3 | 53511112 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-11-24 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Skagen Volvo Grader from Hensen Road for road maintenance in support og Stringing crews / Delay due to slippery roads | 11 | F212-F235 | Anjigame | 0 | 44529 |  | 61 | 44530 | SSF-20211124-1 | Grader doing snow removal from Km 7 to Hwy 101, pulling sand on road and filling ruts - SSF-14450 |  |  |  |  | 11 | KABI LAKE FOREST PRODUCTS LTD7591KL-20211124-33rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD7591KL-20211124-33rd Party Services2321.822321.82OEWT-PA23-Lem | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7593 | KL-20211125-2 | 53511011 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-11-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator shaping road @ F118, scraping and sanding hill @ Km 48. Excavator filling ruts and shaping road from km 24 to 21 for freezing - JJR-70306 | 10 | F066-F118 | Paint Lake 2 | 0 | 44529 |  | 61 | 44530 | JJR-20211125-1 | Excavator filling ruts and shaping road from km 24 to 21 for freezing - JJR-70306 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7593KL-20211125-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7593KL-20211125-23rd Party Services2581.822581.82OEWT-PA23-Lem | [5 empty] | 1 | 2581.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7594 | KL-20211125-3 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-11-25 | 0 | OEWT-PA23-Lem | 44533 | 79 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader continuing to scraping and sand road to F213, F217 and to F218 for stringing crews/ Supervision of Skagen | 11 | F212-F235 | Anjigame | 0 | 44525 |  | 61 | 44530 | SSF-20211125-1 | Grader doing snow removal and widening road to F213, F224 and F227 - SSF-14451 |  |  |  |  | 11 | KABI LAKE FOREST PRODUCTS LTD7594KL-20211125-33rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD7594KL-20211125-33rd Party Services2321.822321.82OEWT-PA23-Lem | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7598 | KL-20211126-2 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-11-26 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Skagen Volvo Grader from Anjigami to Km 13 on High Falls Road. Grader doing snow removal and widening road from Km 13 on High Falls Road to F207 and F199 - SSF- 14452 | 11 | F170 - F211 | High Falls | 0 | 44532 |  | 61 | 44534 | SSF-20211126-1 | Grader doing snow removal and widening road from Km 13 on High Falls Road to F207 and F199 - SSF-14452 |  |  |  |  | 11 | KABI LAKE FOREST PRODUCTS LTD7598KL-20211126-23rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD7598KL-20211126-23rd Party Services2321.822321.82OEWT-PA24-LEM | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7602 | KL-20211128-2 | 53511111 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-11-28 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and shaping road from F204 to F211 and to F200 / supervision of Skagen | 11 | F170-F211 | High Falls Road | 0 | 44536 |  | 61 | 44538 | SSF-20211128-1 | Grader doing snow removal and widening road from Km 13 on High Falls road to F200, F195and F175 - SSF-14453 |  |  |  |  | 11 | KABI LAKE FOREST PRODUCTS LTD7602KL-20211128-23rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD7602KL-20211128-23rd Party Services2321.822321.82OEWT-PA24-LEM | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7604 | KL-20211128-4 | 53511011 | Access | 0 | 3rd Party Services | 1 | 2179.64 | Each |  |  |  |  | 2179.64 | 283.3532 | 2462.9932 | 2021-11-28 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator doing snow removal, scraping and sanding hills from Km 33 to 37 - MC-13221 | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44536 |  | 61 | 44538 | MC-20211128-1 | Excavator doing snow removal, scraping and sanding hills from Km 33 to 37 - MC-13221 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7604KL-20211128-43rd Party Services2179.642179.64 | KABI LAKE FOREST PRODUCTS LTD7604KL-20211128-43rd Party Services2179.642179.64OEWT-PA24-LEM | [5 empty] | 1 | 2179.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7605 | KL-20211129-2 | 53511111 | Access | 0 | 3rd Party Services | 1 | 928.73 | Each |  |  |  |  | 928.73 | 120.7349 | 1049.4649 | 2021-11-29 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F203 to F185 / supervision of Skagen | 11 | F170-F211 | High Falls Road | 0 | 44536 |  | 61 | 44538 | SSF-20211129-2 | Grader doing snow removal and widening road from Km 13 on High Falls road and from F184 to F181 - SSF-14454 |  |  |  |  | 11 | KABI LAKE FOREST PRODUCTS LTD7605KL-20211129-23rd Party Services928.73928.73 | KABI LAKE FOREST PRODUCTS LTD7605KL-20211129-23rd Party Services928.73928.73OEWT-PA24-LEM | [5 empty] | 1 | 928.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7608 | KL-20211129-5 | 53511011 | Access | 0 | 3rd Party Services | 1 | 2179.64 | Each |  |  |  |  | 2179.64 | 283.3532 | 2462.9932 | 2021-11-29 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator doing snow removal, scraping and sanding hills from Km 33 to 28 - MC-13222Grader doing snow removal from Paint Lake Road to 13.5 Km on Paint Lake Road 2 - SSF-14455 | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44536 |  | 61 | 44538 | MC-20211129-1 | Excavator doing snow removal, scraping and sanding hills from Km 33 to 28 - MC-13222 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7608KL-20211129-53rd Party Services2179.642179.64 | KABI LAKE FOREST PRODUCTS LTD7608KL-20211129-53rd Party Services2179.642179.64OEWT-PA24-LEM | [5 empty] | 1 | 2179.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7608 | KL-20211129-5 | 53511011 | Access | 0 | 3rd Party Services | 1 | 1625.27 | Each |  |  |  |  | 1625.27 | 211.2851 | 1836.5551 | 2021-11-29 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator doing snow removal, scraping and sanding hills from Km 33 to 28 - MC-13222Grader doing snow removal from Paint Lake Road to 13.5 Km on Paint Lake Road 2 - SSF-14455 | 10 | F066-F118 | Paint Lake Road 2 | 0 | 44536 |  | 61 | 44538 | SSF-20211129-1 | Grader doing snow removal from Paint Lake Road to 13.5 Km on Paint Lake Road 2 - SSF-14455 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7608KL-20211129-53rd Party Services1625.271625.27 | KABI LAKE FOREST PRODUCTS LTD7608KL-20211129-53rd Party Services1625.271625.27OEWT-PA24-LEM | [5 empty] | 1 | 1625.27 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7609 | KL-20211130-2 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1393.09 | Each |  |  |  |  | 1393.09 | 181.1017 | 1574.1917 | 2021-11-30 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal on Trembley road and from F159 to F164 - SSF-14456 | 11 | F161 - F164 | Trembley Falls | 0 | 44536 |  | 61 | 44538 | SSF-20211130-2 | Grader doing snow removal on Trembley road and from F159 to F164 - SSF-14456 |  |  |  |  | 11 | KABI LAKE FOREST PRODUCTS LTD7609KL-20211130-23rd Party Services1393.091393.09 | KABI LAKE FOREST PRODUCTS LTD7609KL-20211130-23rd Party Services1393.091393.09OEWT-PA24-LEM | [5 empty] | 1 | 1393.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7611 | KL-20211130-4 | 53511111 | Access | 0 | 3rd Party Services | 1 | 928.75 | Each |  |  |  |  | 928.75 | 120.7375 | 1049.4875 | 2021-11-30 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from F184 to F181 and F177 to F171 / supervision of Skagen | 11 | F170-F211 | High Falls | 0 | 44536 |  | 61 | 44538 | SSF-20211130-1 | Grader doing snow removal on High Falls Road and F194 to F197 - SSF-14457 |  |  |  |  | 11 | KABI LAKE FOREST PRODUCTS LTD7611KL-20211130-43rd Party Services928.75928.75 | KABI LAKE FOREST PRODUCTS LTD7611KL-20211130-43rd Party Services928.75928.75OEWT-PA24-LEM | [5 empty] | 1 | 928.75 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7612 | KL-20211201-2 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1393.09 | Each |  |  |  |  | 1393.09 | 181.1017 | 1574.1917 | 2021-12-01 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal @ F179 to F180 and F193 to F181 / supervision of Skagen | 11 | F170-F212 | High Falls | 0 | 44537 |  | 61 | 44538 | SSF-20211201-1 | Grader doing snow removal on High Falls Road and F170 - SSF-14458 |  |  |  |  | 11 | KABI LAKE FOREST PRODUCTS LTD7612KL-20211201-23rd Party Services1393.091393.09 | KABI LAKE FOREST PRODUCTS LTD7612KL-20211201-23rd Party Services1393.091393.09OEWT-PA24-LEM | [5 empty] | 1 | 1393.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7614 | KL-20211201-4 | 53511111 | Access | 0 | 3rd Party Services | 1 | 928.73 | Each |  |  |  |  | 928.73 | 120.7349 | 1049.4649 | 2021-12-01 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader doing snow removal from F165 to F169 - SSF-14459 | 11 | F165 - F169 | Magpie Hills | 0 | 44537 |  | 61 | 44538 | SSF-20211201-2 | Grader doing snow removal from F165 to F169 - SSF-14459 |  |  |  |  | 11 | KABI LAKE FOREST PRODUCTS LTD7614KL-20211201-43rd Party Services928.73928.73 | KABI LAKE FOREST PRODUCTS LTD7614KL-20211201-43rd Party Services928.73928.73OEWT-PA24-LEM | [5 empty] | 1 | 928.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7618 | KL-20211201-8 | 53511011 | Access | 0 | 3rd Party Services | 1 | 2179.64 | Each |  |  |  |  | 2179.64 | 283.3532 | 2462.9932 | 2021-12-01 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator doing snow removal, shaping and sanding hills from Km 28 to F058 - MC-13223 | 10 | F066-F118 | Paint Lake 2 | 0 | 44537 |  | 61 | 44538 | MC-20211201-1 | Excavator doing snow removal, shaping and sanding hills from Km 28 to F058 - MC-13223 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7618KL-20211201-83rd Party Services2179.642179.64 | KABI LAKE FOREST PRODUCTS LTD7618KL-20211201-83rd Party Services2179.642179.64OEWT-PA24-LEM | [5 empty] | 1 | 2179.64 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7620 | KL-20211202-2 | 53511011 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Km 49 to Km 40/ loader sanding road from Km 48 to Km 46.5 with existing material | 10 | F066-F118 | Paint Lake 2 | 0 | 44539 |  | 46 | 44545 | SSF-20211202-1 | Grader doing snow removal from Paint Lake Road to Km 13 on Paint Lake Road 2 - SSF-14460 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7620KL-20211202-23rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD7620KL-20211202-23rd Party Services2321.822321.82OEWT-PA24-LEM | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7620 | KL-20211202-2 | 53511011 | Access | 0 | 3rd Party Services | 1 | 2065.45 | Each |  |  |  |  | 2065.45 | 268.5085 | 2333.9585 | 2021-12-02 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal from Km 49 to Km 40/ loader sanding road from Km 48 to Km 46.5 with existing material | 10 | F066-F118 | Paint Lake 2 | 0 | 44539 |  | 46 | 44545 | JJR-20211202-1 | Excavator sanding hills and tracking out from Km 21 to Km 9 for demobilization - JJR-70308 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7620KL-20211202-23rd Party Services2065.452065.45 | KABI LAKE FOREST PRODUCTS LTD7620KL-20211202-23rd Party Services2065.452065.45OEWT-PA24-LEM | [5 empty] | 1 | 2065.45 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7629 | KL-20211203-3 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1160.91 | Each |  |  |  |  | 1160.91 | 150.9183 | 1311.8283 | 2021-12-03 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer working on snow removal and shaping road @ F198 to F202 and track to Km 11 on High Falls Raod/ Supervision of Skagen | 11 | F170 - F211 | High Falls | 0 | 44539 |  | 46 | 44545 | SSF-20211203-1 | Grader scarifying High Falls Road from F203 to F175 - SSF-14462 |  |  |  | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7629KL-20211203-33rd Party Services1160.911160.91 | KABI LAKE FOREST PRODUCTS LTD7629KL-20211203-33rd Party Services1160.911160.91OEWT-PA24-LEM | [5 empty] | 1 | 1160.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7631 | KL-20211203-5 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1160.91 | Each |  |  |  |  | 1160.91 | 150.9183 | 1311.8283 | 2021-12-03 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying Trembley Road and F161 to F163 - SSF-14461 | 11 | F161 - F164 | Trembley Falls | 0 | 44539 |  | 46 | 44545 | SSF-20211203-2 | Grader scarifying Trembley Road and F161 to F163 - SSF-14461 |  |  |  | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7631KL-20211203-53rd Party Services1160.911160.91 | KABI LAKE FOREST PRODUCTS LTD7631KL-20211203-53rd Party Services1160.911160.91OEWT-PA24-LEM | [5 empty] | 1 | 1160.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7634 | KL-20211204-2 | 53511111 | Access | 0 | 3rd Party Services | 1 | 1393.09 | Each |  |  |  |  | 1393.09 | 181.1017 | 1574.1917 | 2021-12-04 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Dozer tracking from Km 11 to 1.5, scraping road from F177 to F171 and assist stringing crews/ Supervision of Skagen | 11 | F170-F211 | High Falls | 0 | 44539 |  | 46 | 44545 | SSF-20211204-1 | Grader scarifying High Falls Road from F207 and F177, F175 - SSF-14463 |  |  |  | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7634KL-20211204-23rd Party Services1393.091393.09 | KABI LAKE FOREST PRODUCTS LTD7634KL-20211204-23rd Party Services1393.091393.09OEWT-PA24-LEM | [5 empty] | 1 | 1393.09 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7636 | KL-20211204-4 | 53511111 | Access | 0 | 3rd Party Services | 1 | 928.73 | Each |  |  |  |  | 928.73 | 120.7349 | 1049.4649 | 2021-12-04 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader scarifying Trembley Road from Hwy 17 to F164 access - SSF-14464 | 11 | F161 - F164 | Trembley Falls | 0 | 44539 |  | 46 | 44545 | SSF-20211204-2 | Grader scarifying Trembley Road from Hwy 17 to F164 access - SSF-14464 |  |  |  | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7636KL-20211204-43rd Party Services928.73928.73 | KABI LAKE FOREST PRODUCTS LTD7636KL-20211204-43rd Party Services928.73928.73OEWT-PA24-LEM | [5 empty] | 1 | 928.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7638 | KL-20211205-1 | 53511011 | Access | 0 | 3rd Party Services | 1 | 1210.91 | Each |  |  |  |  | 1210.91 | 157.4183 | 1368.3283 | 2021-12-05 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator tracking out From Km 25 to Km 13 for demobilization - MC-13226 | 10 | F066-F118 | Paint Lake 2 | 0 | 44540 |  | 46 | 44545 | MC-20211205-1 | Excavator tracking out From Km 25 to Km 13 for demobilization - MC-13226 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7638KL-20211205-13rd Party Services1210.911210.91 | KABI LAKE FOREST PRODUCTS LTD7638KL-20211205-13rd Party Services1210.911210.91OEWT-PA24-LEM | [5 empty] | 1 | 1210.91 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7647 | KL-20211207-1 | 53511011 | Access | 0 | 3rd Party Services | 1 | 2321.82 | Each |  |  |  |  | 2321.82 | 301.8366 | 2623.6566 | 2021-12-07 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding from Km 48 to Km 40 | 10 | F066-F118 | Paint Lake 2 | 0 | 44540 |  | 46 | 44545 | SSF-20211207-1 | Grader working on snow removal from Paint Lake Road to Km 13 on Paint Lake Road 2. SSF-14465 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7647KL-20211207-13rd Party Services2321.822321.82 | KABI LAKE FOREST PRODUCTS LTD7647KL-20211207-13rd Party Services2321.822321.82OEWT-PA24-LEM | [5 empty] | 1 | 2321.82 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7648 | KL-20211207-2 | 53511111 | Access | 0 | 3rd Party Services | 1 | 968.73 | Each |  |  |  |  | 968.73 | 125.9349 | 1094.6649 | 2021-12-07 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Grader working on benching snow banks from Hwy 17 to Km 17 and clearing pull offs | 11 | F118-F127 | Henson | 0 | 44540 |  | 46 | 44545 | MC-20211207-1 | Excavator tracking out from Km 40 to Km 46/ walking out for road work @ F127 to F132. MC-13227 |  |  |  | Dave Ofukany | 11 | KABI LAKE FOREST PRODUCTS LTD7648KL-20211207-23rd Party Services968.73968.73 | KABI LAKE FOREST PRODUCTS LTD7648KL-20211207-23rd Party Services968.73968.73OEWT-PA24-LEM | [5 empty] | 1 | 968.73 |  | #N/A
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7652 | KL-20211208-1 | 53511011 | Access | 0 | 3rd Party Services | 1 | 1857.45 | Each |  |  |  |  | 1857.45 | 241.4685 | 2098.9185 | 2021-12-08 | 0 | OEWT-PA24-LEM | 44575 | 84 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Loader sanding from Km 48 to Km 45. Dozer working from 13km to 18km. Sand truck sanding from 0km to 12km in support of Valard Fuel Tank Demob. Excavator loading existing material. Skagen grader on PLR 2. | 10 | F066-F118 | Paint Lake 2 | 0 | 44546 |  | 46 | 44551 | SSF-20211208-1 | Grader working on snow removal and clearing pull offs from Paint Lake Road to 13km on Paint Lake road #2. SSF-14466 |  |  |  | Dave Ofukany | 10 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-13rd Party Services1857.451857.45 | KABI LAKE FOREST PRODUCTS LTD7652KL-20211208-13rd Party Services1857.451857.45OEWT-PA24-LEM | [5 empty] | 1 | 1857.45 |  | #N/A
Northern Mat & Bridge | 18 | 0 | 7321 | 21637 | 53531001 | Rig/Access Mats | 0 | 3rd Party | 1 | 2326.5 | Unit |  |  |  |  | 2326.5 | 302.445 | 2628.945 | 2021-07-30 | 0 | ESI10518 | 44452 | 66 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | No PO - TBD |  |  |  | Approved |  |  | Demob traffic control / travel to thunder Bay. Westmill travel in pick up loader deliver to morrisburg yard. NMB float travel in pick up excavator deliver to orangeville. NMB float travel in pick up ETC 002 deliver to Orangeville. Jason 1.5 hour paperwork DFR/LEM | 10 | F065-F118 | Paint Lake Road 2 | 0 | 44410 |  | 36 | 44411 | 005025 | Traffic Control - LH North |  |  |  | Mike Lecocq | 10 | Northern Mat & Bridge7321216373rd Party2326.52326.5 | Northern Mat & Bridge7321216373rd Party2326.52326.5ESI10518 |  | WF10-Rig/Access Mat Handling | WF10-Rig/Access Mat Handling |  | 1 | 1 | 2326.5 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6364 | AGCE-20210120-1 | 53511111 | Access | 0 | Sand un treated | 23 | 13 | Ton |  |  |  |  | 299 | 38.87 | 337.87 | 2021-01-20 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Sanding roads: Dore, Harbour. Note Chapman was told they had to use treated sand from reserve resources. | 11 |  | MFN - Harbour Rd 1, 2, 3, 4, 5 | 0 |  |  | 54 | 44327 |  | Sanding roads: Dore, Harbour. |  |  |  | Betty Moghrabi | 11 | AG Chapman Enterprises6364AGCE-20210120-1Sand un treated13299 | AG Chapman Enterprises6364AGCE-20210120-1Sand un treated13299AGCE-2021-01-30 | [5 empty] | 1 | 299 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6341 | AGCE-20210114-01-R1 | 53511111 | Access | 0 | Sand treated | 100 | 2 | Ton |  |  |  |  | 200 | 26 | 226 | 2021-01-29 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | Is treated sand in the contract? If not where are they getting it from? |  | Approved |  |  | Sanding Tremblay Flats road with treated sand. 2 TON treated sand. | 11 |  | MFN | 0 |  |  | 54 | 44328 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6341AGCE-20210114-01-R1Sand treated2200 | AG Chapman Enterprises6341AGCE-20210114-01-R1Sand treated2200AGCE-2021-01-30 | [5 empty] | 1 | 200 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6363 | AGCE-20210116-1 | 53511111 | Access | 0 | Sand treated | 100 | 2 | Ton |  |  |  |  | 200 | 26 | 226 | 2021-01-16 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Sanding Trembley Flats road with treated sand | 11 |  | Trembley Flats Rd | 0 |  |  | 54 | 44327 |  | Trembley Flats Rd |  |  |  | Betty Moghrabi | 11 | AG Chapman Enterprises6363AGCE-20210116-1Sand treated2200 | AG Chapman Enterprises6363AGCE-20210116-1Sand treated2200AGCE-2021-01-30 | [5 empty] | 1 | 200 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6371 | AGCE-20210125-1 | 53511111 | Access | 0 | Sand treated | 100 | 15 | Ton |  |  |  |  | 1500 | 195 | 1695 | 2021-01-25 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Plowe and sanded from the mission harbour road to the end of dore | 11 | F135-F160 | Habour Road 1, 2, 3, 4, 5, | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6371AGCE-20210125-1Sand treated151500 | AG Chapman Enterprises6371AGCE-20210125-1Sand treated151500AGCE-2021-01-30 | [5 empty] | 1 | 1500 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6372 | AGCE-20210125-2 | 53511111 | Access | 0 | Sand treated | 100 | 5 | Ton |  |  |  |  | 500 | 65 | 565 | 2021-01-25 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Alfred Chapman and Ryan MacIntyre, removed |  | Approved |  |  | Grade and sand Trembley Flats Road | 11 |  | Trembley Flats Road | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6372AGCE-20210125-2Sand treated5500 | AG Chapman Enterprises6372AGCE-20210125-2Sand treated5500AGCE-2021-01-30 | [5 empty] | 1 | 500 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6066 | AGCE-20210129-1 | 53511111 | Access | 0 | Sand treated | 100 | 2 | Ton |  |  |  |  | 200 | 26 | 226 | 2021-01-29 | 0 | AGCE-2021-01-30 | 44328 | 48 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andy N, removed |  | Approved |  |  | Sand michhipicoten turn off, Harbour Rd to Dore Lake Road | 11 | F135-F150 | Harbour Road / Dore Lake Road | 0 |  |  | 54 | 44327 | [5 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6066AGCE-20210129-1Sand treated2200 | AG Chapman Enterprises6066AGCE-20210129-1Sand treated2200AGCE-2021-01-30 | [5 empty] | 1 | 200 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6067 | AGCE-20210201-2 | 53511111 | Access | 0 | Sand treated | 100 | 4 | Ton |  |  |  |  | 400 | 52 | 452 | 2021-02-01 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andy N, not eligible, Local |  | Approved |  |  | Sanded roads: Michipicoten Harbour Rd, Dore Lake Road, Trembley Flats Rd | 11 | F160-F164 | Trembley Falls Road | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6067AGCE-20210201-2Sand treated4400 | AG Chapman Enterprises6067AGCE-20210201-2Sand treated4400AGCE-2021-02-10 | [5 empty] | 1 | 400 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6382 | AGCE-20210208-3 | 53511111 | Access | 0 | Sand treated | 100 | 4 | Ton |  |  |  |  | 400 | 52 | 452 | 2021-02-08 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andy N |  | Approved |  |  | Sanded to KM 4 on Dore and Trembley | 11 |  | Dore Rd, Tremlbey Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6382AGCE-20210208-3Sand treated4400 | AG Chapman Enterprises6382AGCE-20210208-3Sand treated4400AGCE-2021-02-10 | [5 empty] | 1 | 400 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6385 | AGCE-20210209-3 | 53511111 | Access | 0 | Sand treated | 100 | 4 | Ton |  |  |  |  | 400 | 52 | 452 | 2021-02-09 | 0 | AGCE-2021-02-10 | 44352 | 51 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andy N, not eligible |  | Approved |  |  | Plowed and sanded Harbour Rd, Trembley Rd, Dore Rd | 11 |  | Harbour Rd, Trembley Rd, Dore Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6385AGCE-20210209-3Sand treated4400 | AG Chapman Enterprises6385AGCE-20210209-3Sand treated4400AGCE-2021-02-10 | [5 empty] | 1 | 400 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6395 | AGCE-20210212-3 | 53511111 | Access | 0 | Sand treated | 100 | 6 | Ton |  |  |  |  | 600 | 78 | 678 | 2021-02-12 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andy N Supervisor and truck removed |  | Approved |  |  | Sanding Dore Lake, Trembley, Harbour Rd's | 11 | F135-F160 | Dore Lake, Trembley, Harbour Rd's | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6395AGCE-20210212-3Sand treated6600 | AG Chapman Enterprises6395AGCE-20210212-3Sand treated6600AGCE-2021-02-11-20 | [5 empty] | 1 | 600 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6412 | AGCE-20210216-5 | 53511111 | Access | 0 | Sand treated | 100 | 5 | Ton |  |  |  |  | 500 | 65 | 565 | 2021-02-16 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Andy N Supervisor and truck removed |  | Approved |  |  | Sanded Trembley Rd, Harbour Rd and Dore Lake Rd | 11 | F149-F164 | Trembley Rd, Harbour Rd | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6412AGCE-20210216-5Sand treated5500 | AG Chapman Enterprises6412AGCE-20210216-5Sand treated5500AGCE-2021-02-11-20 | [5 empty] | 1 | 500 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6427 | AGCE-20210219-8 | 53511111 | Access | 0 | Sand treated | 100 | 5 | Ton |  |  |  |  | 500 | 65 | 565 | 2021-02-19 | 0 | AGCE-2021-02-11-20 | 44247 | 54 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | Supervisor and truck removed |  | Approved |  |  | Plowed and sanded Trembley Rd, Harbour Rd, Dore | 11 | F128-F164 | Trembley Rd, Harbour Rd, Dore | 0 |  |  | 56 | [6 empty] | Mandy Sandhu | 11 | AG Chapman Enterprises6427AGCE-20210219-8Sand treated5500 | AG Chapman Enterprises6427AGCE-20210219-8Sand treated5500AGCE-2021-02-11-20 | [5 empty] | 1 | 500 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6457 | AGCE-20210226-01-R1 | 53511111 | Access | 0 | Sand treated | 100 | 6 | Ton |  |  |  |  | 600 | 78 | 678 | 2021-02-26 | 0 | AGCE-2021-02-21-28 | 44255 | 56 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | LOA for Phil S, no LOA for Andy N |  | Approved |  |  | Grade and sand roads dore lake road - Trembley | 11 | F161 | Trembley Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6457AGCE-20210226-01-R1Sand treated6600 | AG Chapman Enterprises6457AGCE-20210226-01-R1Sand treated6600AGCE-2021-02-21-28 | [5 empty] | 1 | 600 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6508 | AGCE-20210306-01 | 53511111 | Access | 0 | Sand treated | 100 | 6 | Ton |  |  |  |  | 600 | 78 | 678 | 2021-03-06 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | NO Loa for Andy N |  | Approved |  |  | Sand Roads Dore Lk Road to Harbour to Trembley Rd | 11 | F128--F160 | Trembley Rd - Dore Lk Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6508AGCE-20210306-01Sand treated6600 | AG Chapman Enterprises6508AGCE-20210306-01Sand treated6600AGCE-2021-03-01-10 | [5 empty] | 1 | 600 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 6513 | AGCE-20210307-01 | 53511111 | Access | 0 | Sand treated | 100 | 6 | Ton |  |  |  |  | 600 | 78 | 678 | 2021-03-07 | 0 | AGCE-2021-03-01-10 | 44266 | 57 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Sanded Rds Dore Lk - Harbour Rd - Trembley Rd | 11 | F128-F160 | Trembley Rd - Dore Rd | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises6513AGCE-20210307-01Sand treated6600 | AG Chapman Enterprises6513AGCE-20210307-01Sand treated6600AGCE-2021-03-01-10 | [5 empty] | 1 | 600 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7051 | AGCE-20210314-01 | 53511111 | Access | 0 | Sand treated | 100 | 6 | Ton |  |  |  |  | 600 | 78 | 678 | 2021-03-14 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | No LOA for Andy Neyland No Loa for Alfed C |  | Approved |  |  | Grading and Sanding Harbour and trembley Rd, and Dore | 11 | F120-F160 | Harbour, Trembley, Dore | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7051AGCE-20210314-01Sand treated6600 | AG Chapman Enterprises7051AGCE-20210314-01Sand treated6600AGCE-2021-03-11-20 | [5 empty] | 1 | 600 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7055 | AGCE-20210315-01 | 53511111 | Access | 0 | Sand treated | 100 | 6 | Ton |  |  |  |  | 600 | 78 | 678 | 2021-03-15 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  | No LOA for Andy N |  | Approved |  |  | Grade and Sand Trembley Rd | 11 | F161-F164 | Trembley Road | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7055AGCE-20210315-01Sand treated6600 | AG Chapman Enterprises7055AGCE-20210315-01Sand treated6600AGCE-2021-03-11-20 | [5 empty] | 1 | 600 |  | #N/A
AG Chapman Enterprises | 21 | 0 | 7056 | AGCE-20210316-01 | 53511111 | Access | 0 | Sand treated | 100 | 6 | Ton |  |  |  |  | 600 | 78 | 678 | 2021-03-16 | 0 | AGCE-2021-03-11-20 | 44397 | 61 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | No Contract | 39310 OS |  |  |  | Approved |  |  | Sanding of harbour, trembley and dore | 11 | F135-F160 | Harbour, Trembley, Dore | 0 |  |  | 54 | [6 empty] | Betty Moghrabi | 11 | AG Chapman Enterprises7056AGCE-20210316-01Sand treated6600 | AG Chapman Enterprises7056AGCE-20210316-01Sand treated6600AGCE-2021-03-11-20 | [5 empty] | 1 | 600 |  | #N/A